## Settings
Update the orange cells below ↓
| Team Name | Team Manager
Team 1 | Alpha | Adam
Team 2 | Bravo | Bill
Team 3 | Charlie | Charlene
Team 4 | Delta | Daryl
Team 5 | Echo | Elizabeth
Team 6 | Fox | Frank
All | Portfolio | ← Top level organization.
Current Year | 2017
Setup
Rename the "Team 1", "Team 2", "Team …" fields on the Summary Table sheets (Excel doesn't allow formulas in PivotTables).
Rename the Team sheets.
Hide this sheet when not in use.
Tips
When filling out the team sheets, never include resources who no longer work for the company. They will be included in your head count and your team will appear to have more bandwidth than they actually do.
Keep the Totals row on the team sheets visible. You can use the filters
Advanced: there's a hidden data sheet that is very hidden - research how to unhide sheets that are xlSheetVeryHidden.
Advanced: to modify the underlying data in the PivotTables, bring up the PivotTable Wizard by clcking anywhere in the pivot table and press Alt + D, P.
How to fill out the Team Sheets
Fill out the Team sheets with the resource allocation as shown below. Then reset the PivotTables by going to Data → Refresh All.

## Data
Portfolio | Description | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Total Unique Resources: | 14
Active | Alpha | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bravo | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Charlie | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delta | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Echo | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fox | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Active Subtotal | 12.25 | 14 | 16.75 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | Up to Bat - Needs Resource | 1.5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 3 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 3 | 0 | 3 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pending Subtotal | 10.5 | 12 | 15 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 22.75 | 26 | 31.75 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alpha | Team 1 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Alpha Workload | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 5.25 | 6 | 6.75 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bravo | Team 2 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Bravo Workload | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Charlie | Team 3 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Charlie Workload | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | Team 4 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Delta Workload | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Echo | Team 5 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Echo Workload | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fox | Team 6 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Fox Workload | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
You shouldn't have to edit this sheet... but if you do, save a backup of the entire workbook first.
Password: goodplusfast
Lock it when you're finished.

## Team Summary
Sum of Value | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Year: 2017 | Refresh pivot table by going to Data >> Refresh All
Team1 | Column Labels Jan: 5.25; Column Labels Feb: 6; Column Labels Mar: 6.75; Column Labels Apr: 0.02 |  |  |  | Legend: | Allocation < 100% | Allocation = 100% | Allocation > 100%
Active | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 4.25; Column Labels Apr: 0.01
Resource A (Overallocated) | Column Labels Jan: 1.25; Column Labels Feb: 1.25; Column Labels Mar: 1.25; Column Labels Apr: 0.01
Resource B (Underallocated) | Column Labels Jan: 0.75; Column Labels Feb: 0.75; Column Labels Mar: 0.75
Resource C (Optimally Allocated) | bar: Column Labels Jan to Column Labels Mar
Resource D | Column Labels Jan: 0.5; Column Labels Feb: 1; Column Labels Mar: 1.25
Pending | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.01
In the Dugout - May Happen | Column Labels Jan: 0.5; Column Labels Feb: 1; Column Labels Mar: 1
On Deck - Going to Happen | Column Labels Jan: 0.5; Column Labels Feb: 0.5; Column Labels Mar: 0.5
Up to Bat - Needs Resource | Column Labels Jan: 0.25; Column Labels Feb: 0.5; Column Labels Mar: 0.5
Bench | Column Labels Jan: 0.5; Column Labels Mar: 0.5; Column Labels Apr: 0.01
Team2 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 5; Column Labels Apr: 0.04
Team3 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 5; Column Labels Apr: 0.06
Team4 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 5; Column Labels Apr: 0.08
Team5 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 5; Column Labels Apr: 0.1
Team6 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 5; Column Labels Apr: 0.12
Grand Total | Column Labels Jan: 22.75; Column Labels Feb: 26; Column Labels Mar: 31.75; Column Labels Apr: 0.42

## Status Summary
Sum of Value | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Year: 2017 | Refresh pivot table by going to Data >> Refresh All
Active | Column Labels Jan: 12.25; Column Labels Feb: 14; Column Labels Mar: 16.75; Column Labels Apr: 0.21 |  |  |  | Legend: | Allocation < 100% | Allocation = 100% | Allocation > 100%
Team1 | Column Labels Jan: 3.5; Column Labels Feb: 4; Column Labels Mar: 4.25; Column Labels Apr: 0.01
Resource A (Overallocated) | Column Labels Jan: 1.25; Column Labels Feb: 1.25; Column Labels Mar: 1.25; Column Labels Apr: 0.01
Resource B (Underallocated) | Column Labels Jan: 0.75; Column Labels Feb: 0.75; Column Labels Mar: 0.75
Resource C (Optimally Allocated) | bar: Column Labels Jan to Column Labels Mar
Resource D | Column Labels Jan: 0.5; Column Labels Feb: 1; Column Labels Mar: 1.25
Team2 | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.02
Team3 | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.03
Team4 | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.04
Team5 | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.05
Team6 | Column Labels Jan: 1.75; Column Labels Feb: 2; Column Labels Mar: 2.5; Column Labels Apr: 0.06
Pending | Column Labels Jan: 10.5; Column Labels Feb: 12; Column Labels Mar: 15; Column Labels Apr: 0.21
Grand Total | Column Labels Jan: 22.75; Column Labels Feb: 26; Column Labels Mar: 31.75; Column Labels Apr: 0.42

## Summary Table
This table is pasted as a linked image from a very hidden sheet. Update the Settings and Team sheets to modify this table.

## Team 1
Adam | ← Manager ¦ Team → | Alpha | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A (Overallocated) | Project Manager I | Project A | 2017 Jan: 75%; 2017 Feb: 75%; 2017 Mar: 75%; 2017 Apr: 1%
Resource A (Overallocated) | Project Manager I | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B (Underallocated) | Project Manager II | Project C | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B (Underallocated) | Project Manager II | Project D | 2017 Jan: 25%; 2017 Feb: 25%; 2017 Mar: 25%
Resource C (Optimally Allocated) | Project Manager III | Project E | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource C (Optimally Allocated) | Project Manager III | Project E | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource D | Project Manager III | Project F | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 125%
Unique Resources: | 4 | Active Project Subtotal | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 1%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 5.25 | 6 | 6.75 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 2
Bill | ← Manager ¦ Team → | Bravo | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 2%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 2%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 3
Charlene | ← Manager ¦ Team → | Charlie | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 3%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 3%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 4
Daryl | ← Manager ¦ Team → | Delta | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 4%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 4%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 5
Elizabeth | ← Manager ¦ Team → | Echo | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 5%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 5%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 6
Frank | ← Manager ¦ Team → | Fox | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 6%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 6%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0