## dashboard
Achieved | time axis 2020-01-01 to 2023-12-01
Achieved
| Milestone overview | [11 empty] | next milestone | Milestone 3 | 30 | Delayed | 2020-04-01 | 0 | 2020-01-01: janvier; 2022-10-01: octobre
[6 empty] | Original due date | Revised due date | Expected date | Delivered date |  |  |  |  | Today | 2020-07-26 | N/A | future | 2030-01-01 | 2020-01-01: Q1 2020; 2020-04-01: Q2 2020; 2020-07-01: Q3 2020; 2020-10-01: Q4 2020; 2021-01-01: Q1 2021; 2021-04-01: Q2 2021; 2021-07-01: Q3 2021; 2021-10-01: Q4 2021; 2022-01-01: Q1 2022; 2022-04-01: Q2 2022; 2022-07-01: Q3 2022; 2022-10-01: Q4 2022; 2023-01-01: Q1 2023; 2023-04-01: Q2 2023; 2023-07-01: Q3 2023; 2023-10-01: Q4 2023
| Number | Milestone title | Responsible | M | Status |  |  |  |  | Comments | due date | delivery date | upcoming milestone | time axis 2020-01-01 to 2023-12-01
projet 1 | MS-1 | Milestone 1 | TBD | 50 | Achieved | 2020-01-01 | 2021-12-22 | 2021-01-01 | 2021-04-01 | Comments on milestone 1 | 2021-12-22 | 2021-04-01 | #NAME? | 5 | 5 | 5 | 5 | 2 | 2021-01-01: Expected; 2021-04-01: Achieved
projet 1 | MS-2 | Milestone 2 | TBD | 60 | On track | 2021-01-02 | 2020-10-01 | 2020-07-01 |  | Comments on milestone 2 | 2020-10-01 | 2020-07-01 | 2020-04-01 | 4 | 4 | 4 | 4 | Delayed | 2020-07-01: Expected
projet 1 | MS-3 | Milestone 3 | TBD | 30 | Delayed | 2021-01-02 | 2020-04-01 | 2020-07-01 |  |  | 2020-04-01 | 2020-07-01 | 3 | 2 | 2 | 2 | 2 |  | 2020-07-01: Expected
projet 2 | MS-1 | Milestone 1 | TBD | 50 | Achieved | 2020-01-01 | 2021-12-22 | 2022-01-01 | 2021-04-01 | Comments on milestone 1 | 2021-12-22 | 2021-04-01 | #NAME? | 5 | 5 | 5 | 5 | 2 | 2021-04-01: Achieved; 2022-01-01: Expected
projet 2 | MS-2 | Milestone 2 | TBD | 50 | Achieved | 2021-01-02 | 2020-10-01 | 2021-07-01 | 2020-12-01 | Comments on milestone 2 | 2020-10-01 | 2020-12-01 | 2020-04-01 | 5 | 5 | 5 | 5 | Delayed | 2020-12-01: Achieved; 2021-07-01: Expected
projet 2 | MS-3 | Milestone 3 | TBD | 30 | Delayed | 2021-01-02 | 2020-04-01 | 2020-07-01 |  |  | 2020-04-01 | 2020-07-01 | 3 | 2 | 2 | 2 | 2 |  | 2020-07-01: Expected
projet 2

## projet 1
General action plan info
Unique ID | Title | Domain
|  |  | Resp. company |  | Sponsor | Owner | Project Lead | Validator | Start date | End date | Last SteerCo check in
Projet 1 | Action plan title | External events |  | N |  |  | TBD | TBD | 2020-01-01 | 2021-12-01 | 2020-01-01
SteerCo discussion
Date | Comments
2020-01-01 | SteerCo meeting comments
Achieved | time axis 2020-01-01 to 2023-12-01
Achieved
Milestone overview | [15 empty] | next milestone | Milestone 3 | 30 | Delayed | 2020-04-01 | 0 | 2020-01-01: janvier; 2022-10-01: octobre
[6 empty] | Original due date | Revised due date | Expected date | Delivered date | [7 empty] | Today | 2020-07-26 | N/A | future | 2030-01-01 | 2020-01-01: Q1 2020; 2020-04-01: Q2 2020; 2020-07-01: Q3 2020; 2020-10-01: Q4 2020; 2021-01-01: Q1 2021; 2021-04-01: Q2 2021; 2021-07-01: Q3 2021; 2021-10-01: Q4 2021; 2022-01-01: Q1 2022; 2022-04-01: Q2 2022; 2022-07-01: Q3 2022; 2022-10-01: Q4 2022; 2023-01-01: Q1 2023; 2023-04-01: Q2 2023; 2023-07-01: Q3 2023; 2023-10-01: Q4 2023
Number | Milestone title |  | Responsible | M | Status |  |  |  |  | Comments |  |  |  | due date | delivery date | upcoming milestone | time axis 2020-01-01 to 2023-12-01
MS-1 | Milestone 1 |  | TBD | 50 | Achieved | 2020-01-01 | 2021-12-22 | 2021-01-01 | 2021-04-01 | Comments on milestone 1 |  |  |  | 2021-12-22 | 2021-04-01 | #NAME? | 5 | 5 | 5 | 5 | 2 | 2021-01-01: Expected; 2021-04-01: Achieved
MS-2 | Milestone 2 |  | TBD | 60 | On track | 2021-01-02 | 2020-10-01 | 2020-07-01 |  | Comments on milestone 2 |  |  |  | 2020-10-01 | 2020-07-01 | 2020-04-01 | 4 | 4 | 4 | 4 | Delayed | 2020-07-01: Expected
MS-3 | Milestone 3 |  | TBD | 30 | Delayed | 2021-01-02 | 2020-04-01 | 2020-07-01 | [5 empty] | 2020-04-01 | 2020-07-01 | 3 | 2 | 2 | 2 | 2 |  | 2020-07-01: Expected
MS-4 | Milestone 4 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-5 | Milestone 5 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-6 | Milestone 6 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-7 | Milestone 7 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-8 | Milestone 8 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-9 | Milestone 9 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-10 | Milestone 10 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-11 | Milestone 11 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-12 | Milestone 12 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-13 | Milestone 13 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-14 | Milestone 14 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-15 | Milestone 15 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-16 | Milestone 16 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-17 | Milestone 17 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-18 | Milestone 18 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-19 | Milestone 19 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-20 | Milestone 20 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
KPI overview
KPI type | Name | Value | Unit |  | Status | Comments
Progress KPI | KPI 1 |  | N/A | 20 | Pending | N/A
Impact KPI | KPI 2 |  | N/A | 50 | On track | N/A
Progress KPI | KPI 3 |  | N/A | 40 | Behind | N/A
Progress KPI | KPI 4 |  | N/A | 20 | Pending | N/A
Progress KPI | KPI 5 |  | N/A | 20 | Pending | N/A
Detailed activity plan
[6 empty] | Original start date | Revised start date | Original end date | Revised end date | Expected end date | Budget (€) |  | Actual spending (€) | [8 empty] | 2020-01-01: Q1 2020; 2020-04-01: Q2 2020; 2020-07-01: Q3 2020; 2020-10-01: Q4 2020; 2021-01-01: Q1 2021; 2021-04-01: Q2 2021; 2021-07-01: Q3 2021; 2021-10-01: Q4 2021; 2022-01-01: Q1 2022; 2022-04-01: Q2 2022; 2022-07-01: Q3 2022; 2022-10-01: Q4 2022; 2023-01-01: Q1 2023; 2023-04-01: Q2 2023; 2023-07-01: Q3 2023; 2023-10-01: Q4 2023
Act. Number | Activity | Sub activity | Responsible |  | Status | [16 empty] | 2020-01-01: 2020-01-01; 2020-04-01: 2020-04-01; 2020-07-01: 2020-07-01; 2020-10-01: 2020-10-01; 2021-01-01: 2021-01-01; 2021-04-01: 2021-04-01; 2021-07-01: 2021-07-01; 2021-10-01: 2021-10-01; 2022-01-01: 2022-01-01; 2022-04-01: 2022-04-01; 2022-07-01: 2022-07-01; 2022-10-01: 2022-10-01; 2023-01-01: 2023-01-01; 2023-04-01: 2023-04-01; 2023-07-01: 2023-07-01; 2023-10-01: 2023-10-01
1 | Main activity 1 | N/A | TBD | 40 | Risk of delay | 2020-01-01 | 2020-01-01 | 2021-01-02 | 2021-09-03 | 2021-09-04 | 500 | 300 | 300 | 2020-01-01 | 2021-09-03
1.1 | Main activity 1 | Sub activity 1.1 | TBD | 60 | On track | 2019-01-01 | 2019-01-01 | 2021-01-02 | 2022-10-01 | 2022-10-01 |  | 0 |  | 2019-01-01 | 2022-10-01
1.2 | Main activity 1 | Sub activity 1.2 | TBD | 50 | Achieved | 2019-10-01 |  | 2019-11-01 |  | 2019-11-09 |  | 0 |  | 2019-10-01 | 2019-11-01
1.3 | Main activity 2 | N/A | TBD | 20 | Pending | 2021-01-01 |  | 2022-01-01 |  |  |  | 0 |  | 2021-01-01 | 2022-01-01
| Main activity 2 | Sub activity 2.1 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 2 | Sub activity 2.2 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 3 | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 3 | Sub activity 3.1 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
Additional action plan info
General description of the action plan
Project description
Key stakeholders
Name |  |  | Department | Effort needed |  | Role
Name 1 |  |  | Department 1 | High |  | Role
Name 2 |  |  | Department 2 | Medium |  | Role
Name 3 |  |  | Department 3 | Low |  | Role
Name 4 |  |  | Department 4 | High |  | Role
Name 5 |  |  | Department 5 | Medium |  | Role
Name 6 |  |  | Department 6 | Low |  | Role
Name 7 |  |  | Department 7 | High |  | Role
Name 8 |  |  | Department 8 | Medium |  | Role
Formulas:
Sponsor = IF(AND([Validator]="",[Start date]=""),"Pending", IF([Start date]<>"","Achieved",IF(R20<=Q20,"On track",IF(AND(R20>Q20,Q20<=TODAY()),"Delayed",IF(AND(Q20<R20,R20>TODAY()),"Risk of delay","")))))
Sponsor = IF(OR(Q54>TODAY(),Q54=0),"Pending",IF([End date]<TODAY(),"Achieved",IF([End date]<=R54,"On track",IF(AND([End date]>R54,R54<=TODAY()),"Delayed",IF(AND(R54<[End date],[End date]>TODAY()),"Risk of delay","Pending")))))

## projet 2
General action plan info
Unique ID | Title | Domain
|  |  | Resp. company |  | Sponsor | Owner | Project Lead | Validator | Start date | End date | Last SteerCo check in
Projet 2 | Action plan title | External events |  | N |  |  | TBD | TBD | 2020-01-01 | 2021-12-01 | 2020-01-01
SteerCo discussion
Date | Comments
2020-01-01 | SteerCo meeting comments
Achieved | time axis 2020-01-01 to 2023-12-01
Achieved
Milestone overview | [15 empty] | next milestone | Milestone 3 | 30 | Delayed | 2020-04-01 | 0 | 2020-01-01: janvier; 2022-10-01: octobre
[6 empty] | Original due date | Revised due date | Expected date | Delivered date | [7 empty] | Today | 2020-07-26 | N/A | future | 2030-01-01 | 2020-01-01: Q1 2020; 2020-04-01: Q2 2020; 2020-07-01: Q3 2020; 2020-10-01: Q4 2020; 2021-01-01: Q1 2021; 2021-04-01: Q2 2021; 2021-07-01: Q3 2021; 2021-10-01: Q4 2021; 2022-01-01: Q1 2022; 2022-04-01: Q2 2022; 2022-07-01: Q3 2022; 2022-10-01: Q4 2022; 2023-01-01: Q1 2023; 2023-04-01: Q2 2023; 2023-07-01: Q3 2023; 2023-10-01: Q4 2023
Number | Milestone title |  | Responsible | M | Status |  |  |  |  | Comments |  |  |  | due date | delivery date | upcoming milestone | time axis 2020-01-01 to 2023-12-01
MS-1 | Milestone 1 |  | TBD | 50 | Achieved | 2020-01-01 | 2021-12-22 | 2022-01-01 | 2021-04-01 | Comments on milestone 1 |  |  |  | 2021-12-22 | 2021-04-01 | #NAME? | 5 | 5 | 5 | 5 | 2 | 2021-04-01: Achieved; 2022-01-01: Expected
MS-2 | Milestone 2 |  | TBD | 50 | Achieved | 2021-01-02 | 2020-10-01 | 2021-07-01 | 2020-12-01 | Comments on milestone 2 |  |  |  | 2020-10-01 | 2020-12-01 | 2020-04-01 | 5 | 5 | 5 | 5 | Delayed | 2020-12-01: Achieved; 2021-07-01: Expected
MS-3 | Milestone 3 |  | TBD | 30 | Delayed | 2021-01-02 | 2020-04-01 | 2020-07-01 | [5 empty] | 2020-04-01 | 2020-07-01 | 3 | 2 | 2 | 2 | 2 |  | 2020-07-01: Expected
MS-4 | Milestone 4 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-5 | Milestone 5 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-6 | Milestone 6 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-7 | Milestone 7 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-8 | Milestone 8 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-9 | Milestone 9 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-10 | Milestone 10 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-11 | Milestone 11 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-12 | Milestone 12 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-13 | Milestone 13 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-14 | Milestone 14 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-15 | Milestone 15 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-16 | Milestone 16 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-17 | Milestone 17 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-18 | Milestone 18 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-19 | Milestone 19 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
MS-20 | Milestone 20 |  | TBD | 20 | Pending | [8 empty] | 2030-01-01 | 2030-01-01 |  | 1 | 101 | 1 | 101
KPI overview
KPI type | Name | Value | Unit |  | Status | Comments
Progress KPI | KPI 1 |  | N/A | 20 | Pending | N/A
Impact KPI | KPI 2 |  | N/A | 50 | On track | N/A
Progress KPI | KPI 3 |  | N/A | 40 | Behind | N/A
Progress KPI | KPI 4 |  | N/A | 20 | Pending | N/A
Progress KPI | KPI 5 |  | N/A | 20 | Pending | N/A
Detailed activity plan
[6 empty] | Original start date | Revised start date | Original end date | Revised end date | Expected end date | Budget (€) |  | Actual spending (€) | [8 empty] | 2020-01-01: Q1 2020; 2020-04-01: Q2 2020; 2020-07-01: Q3 2020; 2020-10-01: Q4 2020; 2021-01-01: Q1 2021; 2021-04-01: Q2 2021; 2021-07-01: Q3 2021; 2021-10-01: Q4 2021; 2022-01-01: Q1 2022; 2022-04-01: Q2 2022; 2022-07-01: Q3 2022; 2022-10-01: Q4 2022; 2023-01-01: Q1 2023; 2023-04-01: Q2 2023; 2023-07-01: Q3 2023; 2023-10-01: Q4 2023
Act. Number | Activity | Sub activity | Responsible |  | Status | [16 empty] | 2020-01-01: 2020-01-01; 2020-04-01: 2020-04-01; 2020-07-01: 2020-07-01; 2020-10-01: 2020-10-01; 2021-01-01: 2021-01-01; 2021-04-01: 2021-04-01; 2021-07-01: 2021-07-01; 2021-10-01: 2021-10-01; 2022-01-01: 2022-01-01; 2022-04-01: 2022-04-01; 2022-07-01: 2022-07-01; 2022-10-01: 2022-10-01; 2023-01-01: 2023-01-01; 2023-04-01: 2023-04-01; 2023-07-01: 2023-07-01; 2023-10-01: 2023-10-01
1 | Main activity 1 | N/A | TBD | 40 | Risk of delay | 2020-01-01 | 2020-01-01 | 2021-01-02 | 2021-09-03 | 2021-09-04 | 500 | 300 | 300 | 2020-01-01 | 2021-09-03
1.1 | Main activity 1 | Sub activity 1.1 | TBD | 60 | On track | 2019-01-01 | 2019-01-01 | 2021-01-02 | 2022-10-01 | 2022-10-01 |  | 0 |  | 2019-01-01 | 2022-10-01
1.2 | Main activity 1 | Sub activity 1.2 | TBD | 50 | Achieved | 2019-10-01 |  | 2019-11-01 |  | 2019-11-09 |  | 0 |  | 2019-10-01 | 2019-11-01
1.3 | Main activity 2 | N/A | TBD | 20 | Pending | 2021-01-01 |  | 2022-01-01 |  |  |  | 0 |  | 2021-01-01 | 2022-01-01
| Main activity 2 | Sub activity 2.1 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 2 | Sub activity 2.2 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 3 | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| Main activity 3 | Sub activity 3.1 | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
| N/A | N/A | TBD | 20 | Pending | [6 empty] | 0 |  | 2030-01-01 | 2030-01-01
Additional action plan info
General description of the action plan
Project description
Key stakeholders
Name |  |  | Department | Effort needed |  | Role
Name 1 |  |  | Department 1 | High |  | Role
Name 2 |  |  | Department 2 | Medium |  | Role
Name 3 |  |  | Department 3 | Low |  | Role
Name 4 |  |  | Department 4 | High |  | Role
Name 5 |  |  | Department 5 | Medium |  | Role
Name 6 |  |  | Department 6 | Low |  | Role
Name 7 |  |  | Department 7 | High |  | Role
Name 8 |  |  | Department 8 | Medium |  | Role
Formulas:
Sponsor = IF(AND([Validator]="",[Start date]=""),"Pending", IF([Start date]<>"","Achieved",IF(R20<=Q20,"On track",IF(AND(R20>Q20,Q20<=TODAY()),"Delayed",IF(AND(Q20<R20,R20>TODAY()),"Risk of delay","")))))
Sponsor = IF(OR(Q54>TODAY(),Q54=0),"Pending",IF([End date]<TODAY(),"Achieved",IF([End date]<=R54,"On track",IF(AND([End date]>R54,R54<=TODAY()),"Delayed",IF(AND(R54<[End date],[End date]>TODAY()),"Risk of delay","Pending")))))