## Planning
[7 empty] | $DE$7 | Semaine 13 | [13 empty] | Semaine 14 | [13 empty] | Semaine 15 | [13 empty] | Semaine 16 | [13 empty] | Semaine 17
[8 empty] | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Sa | Sa | Di | Di | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Sa | Sa | Di | Di | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Sa | Sa | Di | Di | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Sa | Sa | Di | Di | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Matin | Après-midi | Sa | Sa | Di | Di
FA | Client | PN | Pièce Moteur | TAT Nom. | Début | Fin | Item | 2021-03-29 | 2021-03-29 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-04-01 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-03 | 2021-04-03 | 2021-04-04 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-06 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-09 | 2021-04-09 | 2021-04-10 | 2021-04-10 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-27 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-04-30 | 2021-05-01 | 2021-05-01 | 2021-05-02 | 2021-05-02
| SECA | CIE | PW100 - CIE | 32 |  |  | TAT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | [6 empty] | 0 | 0 | 9 | 10 | 11 | 12 | 13 | 14 | [6 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |  |  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  |  |  | 27 | 28 | 29 | 30 | 31 | 32
[5 empty] | TAT Réél |  | Opération | DECAPAGE | DECAPAGE | DECAPAGE | RESSUAGE | LANCEMENT ST. | LANCEMENT ST. | LANCEMENT ST. | LANCEMENT ST. | [8 empty] | RESSUAGE | DEPOT ST. | FIC | FIC | DEPOT ST. | DEPOT ST. | [6 empty] | FOUR VIDE | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | USINAGE ST. | USINAGE ST. |  |  |  |  | RESSUAGE | USINAGE ST. | USINAGE ST. | USINAGE ST. | PLASMA | PLASMA | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. |  |  |  |  | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST. | FINAL ST.
[5 empty] | 61 |  | Charge MO | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 5
Bonjour à tous,
Dans la cellule I6, j'aimerai trouver le nombre d'heure en fonction de plusieurs paramètres:
Pièce moteur: D4 (PW100-CIE)
L'activité: I5 (décapage)
les temps sont répertoriés dans la feuille Temps
Merci de votre aide

## TEMPS
Column1 | DECAPAGE | LANCEMENT ST. | FIC | DEPOT ST. | FOUR VIDE | MEULAGE ST. | USINAGE ST. | RESSUAGE | PLASMA | FOUR CHR. | FINAL ST.
JT15 - HT STATOR | 2.2959 | 11.4714 | 0.25 | 7.6667 | 0 | 20 | 13.1408 | 2.6667 | 0 | 0.75 | 2.3846
JT15 - SMED | 0 | 0.64286 | 0 | 0 | 0 | 0 | 0 | 3.0667 | 5.6944 | 0 | 0
JT15 - CT A-27 /-28 | 1.9143 | 6.4357 | 0.025 | 12.5467 | 1.713 | 9.7513 | 10.2535 | 1.0893 | 0.29444 | 0.55 | 6.4246
PT6 - CT A-40 /-50 Base Co | 4 | 5.5 | 0.05 | 8 | 0.1 | 14 | 4.5 | 3 | 0 | 0.4 | 7
PT6 - CT A-40 /-50 Base Ni | 4 | 5.5 | 0.05 | 8 | 0.1 | 14 | 4.5 | 3 | 0 | 0.6 | 7
PT6 - CT A-60 /-61 /-62 /-65 | 2.2776 | 5.7286 | 0.05 | 15.024 | 1.63 | 15.4957 | 9.5211 | 1.4013 | 1.2778 | 0.6 | 4.2615
PT6 - CT A-64 /-67 /-68 | 4.1041 | 4.5 | 0.05 | 16.88 | 0.812 | 15.2 | 4.7324 | 1.316 | 0.13611 | 0.55 | 4.5385
PT6 - INTERSTAGE SEAL KNIFE EDGE | 0.5102 | 0 | 0 | 0 | 0.7 | 0 | 0 | 2 | 0 | 0 | 0
PT6 - PTVR ALL Medium Series | 3 | 5 | 0.29 | 8.7 | 0.1 | 13 | 7 | 3 | 0 | 0 | 7
PT6 - PTVR ALL PT6A-60 SERIES | 2.1837 | 5.4843 | 0.05 | 10.88 | 0.525 | 9.0696 | 14.6761 | 0.92667 | 1.3472 | 0 | 1.9692
PT6 - PTVR ALL Small SERIES | 0.55102 | 9.0929 | 0.265 | 15.92 | 4.002 | 12.2435 | 20.9535 | 5.0267 | 0.88472 | 0 | 1.8
PT6 - STATOR INTER ETAGE Base Co | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0 | 0 | 0
PT6 - STATOR INTER ETAGE Base Ni | 0.5102 | 5.0643 | 0.05 | 10.5467 | 0.89 | 10.633 | 12.6197 | 2.3933 | 0.61806 | 0 | 0
PW100 - A4 Triple Phase 0 | 1.449 | 0 | 0.06 | 0 | 0.13 | 0 | 0 | 0.44 | 0 | 0.16 | 0
PW100 - A4 Triple Phase 2 | 0 | 0 | 0.22 | 0 | 0.22 | 0 | 0 | 0.44 | 0 | 0.34 | 0
PW100 - A5 Phase 0 | 4 | 6 | 0.06 | 12 | 0.13 | 30 | 3 | 3 | 0 | 0.012 | 7
PW100 - A5 Phase 2 | 4 | 6 | 0.06 | 10 | 0.1 | 25 | 3 | 3 | 0 | 0.39 | 7
PW100 - A6 | 2 | 3 | 0.06 | 7 | 0.1 | 10 | 4.5 | 3 | 0 | 0 | 7
PW100 - A7 INCO 625 | 2 | 5 | 0.1 | 7 | 0.1 | 18 | 11 | 3 | 3 | 0 | 7
PW100 - A7 INCO 713 | 2 | 5 | 0.104 | 7 | 0.1 | 18 | 11 | 3 | 3 | 0 | 7
PW100 - AIR SEAL TURBINE KNIFE EDGE | 0.5102 | 0 | 0 | 0 | 0.7 | 0 | 0 | 2 | 0 | 0 | 0
PW100 - BEARING N°5 KNIFE EDGE | 0.5102 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.53333 | 0 | 0 | 0
PW100 - Chambre Externe | 4.0204 | 1.5429 | 0 | 0 | 0.16 | 0 | 0 | 5.4267 | 14.7917 | 0 | 0
PW100 - Chambre Interne | 1.949 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0333 | 5.4861 | 0 | 0
PW100 - CIE | 2 | 5 | 0.08 | 10 | 0.1 | 10 | 8 | 3 | 3 | 0 | 7
PW100 - Flasque A5 | 0 | 1.5714 | 0 | 0 | 0 | 0 | 1.0563 | 1.5 | 1.3889 | 0 | 0.61538
PW100 - Flasque A7 | 0 | 0.35714 | 0 | 1.4667 | 0.03 | 0 | 3.5915 | 1 | 1.7083 | 0 | 1.3231
PW100 - Lugs A7 | 0.0020408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PW100 - SMED | 0.70714 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3333 | 3.4167 | 0 | 0
PW100 - Spacer A6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 0 | 0 | 0
PW100 - STUB SHAFT | 0.76531 | 0 | 0 | 0 | 5.7 | 0 | 0 | 2 | 0 | 0 | 0
PW100 - STUBSHAFT WASPALLOY | 0.76531 | 0 | 0 | 0 | 5.7 | 0 | 0 | 3 | 0 | 0 | 0
PW100 - VSH | 0.5102 | 7.0429 | 0 | 0 | 1.75 | 4.8696 | 13.8028 | 5.6533 | 1.9583 | 0 | 1.8154
PW206 - CT STATOR | 2 | 4 | 0.05 | 7 | 0.1 | 10 | 6 | 3 | 0 | 0.25 | 6
PW206 - Flasque PT | 0 | 0 | 0 | 0 | 0 | 2.9913 | 1.5211 | 2.6667 | 0 | 0 | 0.30769
PW206 - PT STATOR | 3 | 5 | 0 | 12 | 0.1 | 11 | 12 | 3 | 0 | 0 | 7
PW901 - Chambre Externe | 1.9694 | 0 | 0 | 0 | 0.32 | 0 | 0 | 8.4267 | 1.7083 | 0 | 0
PW901 - Chambre Interne | 0.38776 | 0 | 0 | 0 | 0.32 | 0 | 0 | 0 | 1.8194 | 0 | 0
PW901 - Flasque PT | 0 | 0.71429 | 0 | 3.1333 | 1.85 | 0 | 2.1127 | 1 | 0 | 0 | 0
PW901 - HT STATOR | 4.2347 | 6.44 | 0.25 | 7.6667 | 2.37 | 25.2348 | 12.3239 | 4 | 2.0833 | 0.75 | 2.3077
PW901 - LUG PT901/PT206 | 0.010204 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 0 | 0 | 0
PW901 - PT STATOR | 3 | 10 | 0.08 | 10 | 0.1 | 6.9565 | 6 | 3 | 0 | 0 | 8
PW980 - Power Turbine Vane Ring | 1.2755 | 2.1429 | 0 | 2.6667 | 1.5 | 2.1043 | 1.5493 | 4 | 0 | 0 | 11.2308
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depot+nid d'abeille+capi
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: depot+ nid d'abeille+ capi

## Scenario
DECAPAGE | LANCEMENT ST. | FIC | DEPOT ST. | FOUR VIDE | MEULAGE ST. | USINAGE ST. | RESSUAGE | PLASMA | FOUR CHR. | FINAL ST. | PN | Moteur | TAT Nominal | Commentaire | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 2 | A6 | PW100 - A6 | 18 | Standard sans FOUR CHR. TAT 24jrs en 1/8h | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 2 | PT PT6 | PT6 - PTVR ALL Medium Series | 18 | Standard sans FOUR CHR. TAT 24jrs en 1/8h | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 0 | 3 | 2 | A5 Ph 0 | PW100 - A5 Phase 0 | 22 | Standard sans FOUR CHR. TAT 30 jrs en 1/8h | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | FOUR CHR. | FOUR CHR. | FOUR CHR. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 0 | 3 | 2 | A5 Ph 2 | PW100 - A5 Phase 2 | 22 | Standard sans FOUR CHR. TAT 30 jrs en 1/8h | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | FOUR CHR. | FOUR CHR. | FOUR CHR. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 0 | 3 | 2 | CT PT6 | PT6 - CT A-40 /-50 Base Ni | 22 | Standard sans FOUR CHR. TAT 30 jrs en 1/8h | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | FOUR CHR. | FOUR CHR. | FOUR CHR. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 0 | 4 | 2 | CT PT6 base colbalt | PT6 - CT A-40 /-50 Base Co | 24 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | Nettoyage Vide | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | FOUR CHR. | FOUR CHR. | FOUR CHR. | FOUR CHR. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 3 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 0 | 2 | A7 | PW100 - A7 INCO 713 | 21 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | USINAGE ST. | PLASMA | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 3 | 2 | 1 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | CIE | PW100 - CIE | 22 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | USINAGE ST. | USINAGE ST. | PLASMA | PLASMA | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 1 | 2 | 2 | 4 | 2 | 0 | 3 | 2 | CT 206 | PW206 - CT STATOR | 22 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | USINAGE ST. | FOUR CHR. | FOUR CHR. | FOUR CHR. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 3 | 2 | 3 | 4 | 2 | 3 | 2 | 0 | 0 | 2 | PT 901 | PW901 - PT STATOR | 23 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | DEPOT ST. | FOUR VIDE | FOUR VIDE | DEPOT ST. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
2 | 2 | 2 | 3 | 4 | 2 | 3 | 2 | 0 | 0 | 2 | PT 206 | PW206 - PT STATOR | 22 |  | DECAPAGE | DECAPAGE | LANCEMENT ST. | LANCEMENT ST. | RESSUAGE | FIC | FIC | DEPOT ST. | FOUR VIDE | FOUR VIDE | MEULAGE ST. | MEULAGE ST. | RESSUAGE | DEPOT ST. | FOUR VIDE | FOUR VIDE | DEPOT ST. | USINAGE ST. | USINAGE ST. | USINAGE ST. | FINAL ST. | FINAL ST.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VSH
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0