## onglet 1
N° Projet | N°Commande | Société | Début | Fin | Prestataires | TJM | Jours estimés | Jours travaillés | Jours restants | Total | Reliquat 2022 | estimé Janvier | Reçu Janvier2 | estimée Février | Reçu Février2 | Mars | Avril | Mai | Juin | Juillet | Août | Septembre | Octobre | Novembre | Décembre
60001 | 1161-01926 | BIDULE | 2023-01-02 | 2023-02-13 | ETU | 637 | 44 | 37 | 7 | 28028 | 14 | 15 | 22
60004 | 1161-01927 | MACHIN | 2023-02-01 | 2023-02-06 | CME | 448 | 25 | 0 | 25 | 11200 | 22
60006 | 1161-01928 | CHOSE | 2023-01-16 | 2023-02-08 | CLA | 474 | 27 | 0 | 27 | 12798 | 10
60008 | 1161-01929 | TRUC | 2023-01-16 | 2023-03-15 | EPE | 515 | 57 | 0 | 57 | 29355 | 15
60011 | 1161-01930 | BIDULE | 2023-01-16 | 2023-02-17 | MUN | 493 | 49 | 0 | 49 | 24157 | 24.5
60013 | 1161-01931 | MACHIN | 2023-01-16 | 2023-01-31 | NVE | 468 | 29 | 0 | 29 | 13572 | 18
60006 | 1161-01932 | CHOSE | 2023-01-02 | 2023-01-17 | SAL | 558 | 23 | 0 | 23 |  | 11.5
60008 | 1161-01933 | BIDULE | 2023-01-02 | 2023-02-14 | LDU | 325 | 43 | 0 | 43 |  | 12
60011 | 1161-01934 | MACHIN | 2023-01-02 | 2023-03-03 | ASA | 490 | 44 | 0 | 44 | 21560
60013 | 1161-01935 | CHOSE | 2023-01-02 | 2023-03-21 | BRU | 545 | 56 | 0 | 56 | 30520
60013 | 1161-01936 | BIDULE | 2023-01-02 | 2023-02-01 | JLA | 520 | 22 | 0 | 22 | 2730
Formulas:
Fin = WORKDAY.INTL(WORKDAY.INTL(BDD_PRESTA_ESTIME3[[#This Row],[Début]],-BDD_PRESTA_ESTIME3[[#This Row],[Reliquat 2022]],1,fériés),BDD_PRESTA_ESTIME3[[#This Row],[Jours estimés]],1,fériés)
Formule : soustraire dans la colonne "E" la date de début "D" - le reliquat colonne "L" et rajouter le nombre de jours estimées colonne "H" pour déterminer la date de fin
Note on B4: Royer, Elodie: commande passée par B Pessaud

## Export données
Facturé
N° Projet | N°Commande | Société | Début | Fin | Prestataires | Janvier | Février | Mars | Avril | Mai | Juin | Juillet | Août | Septembre | Octobre | Novembre
60001 | 1161-01926 | BIDULE | 2023-01-02 |  | ETU
60004 | 1161-01927 | MACHIN | 2023-02-01 |  | CME
60006 | 1161-01928 | CHOSE | 2023-01-16 |  | CLA
60008 | 1161-01929 | TRUC | 2023-01-16 |  | EPE
60011 | 1161-01930 | BIDULE | 2023-01-16 |  | MUN
60013 | 1161-01931 | MACHIN | 2023-01-16 |  | NVE
60006 | 1161-01932 | CHOSE | 2023-01-02 |  | SAL
60008 | 1161-01933 | BIDULE | 2023-01-02 |  | LDU
60011 | 1161-01934 | MACHIN | 2023-01-02 |  | ASA
60013 | 1161-01935 | CHOSE | 2023-01-02 |  | BRU
60013 | 1161-01936 | BIDULE | 2023-01-02 |  | JLA
Note on B5: Royer, Elodie: commande passée par B Pessaud
Calculer le montant facturé par mois pour chaque prestataire: multiplier le tjm du prestataire (colonne G onglet 1) par le nombre de jours travaillés (colonne J onglet 1) pour chaque mois

## Jours fériés
Jours Fériés | Dates
Jour de l'An | 2023-01-01
Lundi de Pâques | 2023-04-10
Fête du travail | 2023-05-01
Armistice 1945 | 2023-05-08
Ascension | 2023-05-18
Lundi de Pentecôte | 2023-05-29
Fête nationale | 2023-07-14
Assomption | 2023-08-15
Toussaint | 2023-11-01
Armistice 1918 | 2023-11-11
Noël | 2023-12-25

## Liste déroulante (hidden)
Colonne1
601004 - PAS-X
601000 - SAP 4 HANA
601079 - Modernisation B80 L2 - 2022
601005 - INFRA IT
601007 - GLIMS
601008 - EMPOWER
600716 - Equipement Production OFM
601072 - PILOTAGE
601006 - MASTER CONTROL
601009 - ONGUARD
601006 - MASTER CONTROL
601068 - PROCAL

## Suivi Matériels 2022 (hidden)
Budget | PO | Société | Désignation | Date création | Date prévue | Dernière Réc | Total PO | Fact PO | Reste PO | 2021-07-01 | Aout 2021 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | Janvier | Février | Mars | Avril | Mai | Juin | Juillet | Août | Septembre | Octobre | Novembre | Décembre
601003 - STOCKWARE | PO-21-1161-00047 | ALSTEF | Portage de la plateforme Stockware | 2021-07-14 | 2022-03-31 | 2021-08-23 | 161600 | 64640 | 96960 |  | 64640
601003 - STOCKWARE | PO-22-1161-00162 | ALSTEF | Portage de la plateforme Stockware | 2022-01-19 | 2022-02-28 |  | 34700
601006 - MASTER CONTROL | 8103503267 | APSALYS | Formation MASTER CONTROL | 2021-05-31 | 2021-12-30 | 2021-09-09 | 5600 | 5600 | 0
601006 - MASTER CONTROL | PO-21-1161-00745 | APSALYS | Formation Processus et Gap Analysis | 2021-11-06 | 2022-01-04 | 2021-12-24 | 9374.5 | 0 | 9374.5
601006 - MASTER CONTROL | PO-21-1161-01103 | APSALYS | Initiation Reprise (réunion avec support et rédaction protocole) | 2021-12-21 | 2022-01-30 |  | 3000 | 0 | 3000 | [6 empty] | 5111
601079 - Modernisation B80 L2 – 2022 | PO-21-1161-01172 | CEI2 | Rédaction des IM SSC restants | 2021-12-24 | 2022-12-31 | tout au long de l'année | 25725 | 0 | 25725
601079 - Modernisation B80 L2 – 2022 | PO-21-1161-01171 | CEI2 | Suivi et surveillance des Galaxies | 2021-12-24 | 2022-12-31 | tout au long de l'année | 9135 | 0 | 9135
601005 - INFRA IT | 8103511932 | CHEOPS | Infrastructure de Sauvegarde V5 – HPE et VEEAM | 2021-05-31 | 2021-12-30 | 2021-12-24 | 111217 | 111217 | 0
601005 - INFRA IT | PO-21-1161-00832 | CHEOPS | Installation des upgrades mémoire sur les 4 serveurs en production | 2021-11-19 | 2021-12-20 | 2021-12-24 | 74142.72 | 73242.72 | 900 | [5 empty] | 73242.72
601022 - B80: Sécurisation salle serveur | PO-21-1161-00875 | CF2C | Climatisation réversible local info bâtiment 80 | 2021-11-25 | 2022-02-28 | 2022-01-04 | 5132.8 | 5132.8 | 0 | [5 empty] | 5132.8
601004 - PAS-X | PO-21-1161-00571 | COURBON | Portage de l'application MIRAIM (Suivi projet) | 2021-10-13 | 2022-09-30 | 2021-10-25 | 53900 | 16170 | 37730 |  |  |  | 16170
601009 - ONGUARD | PO-21-1161-00039 | DELTA SECURITE | LICENCES LOGICIEL ONGUARD & MILESTONE | 2021-07-13 |  | 2022-01-03 | 102300 | 88600 | 13700 | 64654.55 |  |  | 8145 |  | 8145
600728 - BASEWARE | 8103484676 | DIMO SOFTWARE | Mise enplace de BASWARE (demat compta fournisseur et remplacement SRM) | 2021-04-30 | 2021-12-30 | 2021-12-24 | 76740 | 76740 | 0
600728 - BASEWARE | PO-21-1161-00534 | DIMO SOFTWARE | Cadrage Migration SAP / Basware | 2021-10-11 | 2021-12-30 | 2021-12-24 | 4560 | 4560 | 0 |  |  | 250 | 2560 | 1250 | 250
601000 - SAP 4 HANA | PO-22-1161-00150 | DIMO SOFTWARE | Reprise interface BASWARE / SAP S4/HANA. | 2022-01-19 | 2022-04-30 |  | 6095
601007 - GLIMS | 8103472111 | LABWARE | Prestation Labware | 2021-04-24 | 2021-12-30 | 2021-12-24 | 4562 | 4562 | 0
601007 - GLIMS | PO-21-1161-00143 | LABWARE | FAREVA GLIMS installation | 2021-07-30 |  | 2021-12-24 | 452610 | 273922.5 | 178687.5 | 244110 | 1687.5 | 5325 | 8300 | 14687.5
601007 - GLIMS | PO-21-1161-00722 | LABWARE | Prestation GLIMS | 2021-12-03 |  | 2021-11-19 | 7500 | 7500 | 0 |  |  |  |  | 3750 | 1500
601005 - INFRA IT | 8103499922 | ORACLE | Licences Oracle Database Std Edition 2 | 2021-04-24 | 2021-12-30 | 2021-07-13 | 90505 | 90504.77 | 0.23
601002 - PI | 8103500571 | OSISOFT | Licences PI Software | 2021-04-06 | 2021-12-30 | 2021-12-24 | 240350 | 240350 | 0
601068 - PROCAL |  | PRIME TECHNOLOGIES | ProCalV5 Single Concurrent User Licenses - Oracle or SQL Server Edition | 2022-01-11 |  | 2022-06-30 | 59308 | 39308 | 20000 | [6 empty] | 39308
601005 - INFRA IT | PO-21-1161-00954 | SHI International SAS | Minitab Statistical Software Annual Subscription 22 MONTH de décembre 2021 à novembre 2022 | 2021-12-03 | 2021-12-16 | 2021-12-16 | 19530 | 19530 | 0 | [5 empty] | 19530
601005 - INFRA IT | PO-21-1161-00683 | SPIE ICS | Matériels informatiques | 2021-10-26 | 2021-11-27 | 2021-11-27 | 17314.76 | 17314.76 | 0 |  |  |  |  | 17314.76
601005 - INFRA IT | PO-21-1161-00832 | CHEOPS | Installation des upgrades mémoire sur les 4 serveurs en production |  |  | 2021-12-06 | 74142.72 | 73242.72 | 900
601005 - INFRA IT | PO-21-1161-01107 | SPIE ICS | CISCO ISR 4321 Bundle Licence | 2021-12-21 | 10/01/022 | 2022-01-10 | 1637.65 |  | 1637.65 | [6 empty] | 1637.665
601004 - PAS-X | PO-21-1161-00616 | TEKLYNX | Licence de test / Transition Codesoft MIRAIM | 2021-10-18 |  | 2021-12-15 | 500 | 500 | 0 |  |  |  | 500
601008 - EMPOWER | PO-22-1161-00190 | AGILENT | Kit LAN GC 6890 | 2022-01-25 |  |  | 2000
601008 - EMPOWER | PO-22-1161-00149 | WATERS | prestation de migration de projets (jusqu’à 1 000 projets) | 2022-01-12 |  |  | 2688
601008 - EMPOWER | PO-21-1161-00014 | WATERS | Empower Network | 2021-07-07 |  | 2021-12-08 | 510407 | 366666.4 | 143740.6 | 360284.3 |  |  | 5262.4
601004 - PAS-X | 8103451390 | WERUM IT SOLUTIONS | Pré-étude technique PAS-X | 2021-04-06 | 2021-12-30 | 2021-12-24 | 15995 | 15995 | 0
601004 - PAS-X | 8103497818 | WERUM IT SOLUTIONS | PAS-X Upgrade/Migration Fit Phase | 2021-05-24 | 2021-12-30 | 2021-12-24 | 46910 | 46910 | 0
601004 - PAS-X | PO-21-1161-00643 | WERUM IT SOLUTIONS | Upgrade PAS-X | 2021-10-20 |  | 2021-10-26 | 7650 | 7650 | 0 |  |  |  | 7650
601004 - PAS-X | PO-21-1161-00849 | WERUM IT SOLUTIONS | custo MSDCORE-1014 | 2021-11-20 | 2022-04-30 | 2021-12-08 | 132430 | 29205 | 103225 | [5 empty] | 29205 | 34408.33

## Engagés (Facturés) 2022 (hidden)
| 601004 - PAS-X | 601000 - SAP 4 HANA | 601005 - INFRA IT | 601007 - GLIMS | 601008 - EMPOWER | 601072 - PILOTAGE | 601006 - MASTER CONTROL | 601009 - ONGUARD | 601068 - PROCAL | 601002 - PI | 601003 - STOCKWARE
engagées au 31/12/2021 | 436510 | 2420146 | 1275306.676 | 585263.662 | 633341.596 | 0 | 407653.9 | 182000 | 0 | 248150 | 228210
Enveloppe au 30/09/2021 | 523250 | 5517700 | 2300000 | 781750 | 775387 | 689900 | 367960 | 254300 | 152400 | 289750 | 220750
Reste au 31/12/2021 | 86740 | 3097554 | 1024693.324 | 196486.338 | 142045.404 | 689900 | -39693.9 | 72300 | 152400 | 41600 | -7460
Reste au 31/01/2022 | 52331.67 | 3097554 | 1023055.659 | 196486.338 | 142045.404 | 689900 | -44804.9 | 72300 | 113092 | 41600 | -7460
Reste au 28/02/2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reste au 31/03/2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reste au 30/04/2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reste au 31/05/2022
Reste au 31/06/2022
Reste au 30/07/2022
Reste au 31/08/2022
Reste au 30/09/2022
| Janvier |  |  | Février |  |  | Mars |  |  | Avril |  |  | Mai |  |  | Juin |  |  | Juillet |  |  | Aout |  |  | Septembre |  |  | Total engagés | Reste | Total Septembre | Budget estimatif
Projet Site | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant | engagés | estimés | restant
601004 - PAS-X | 34408.33 | 63976 | 52331.67 | 0 | 67054.58 |  | 0 | 67054.58 |  | 0 | 32646.25 |  | 0 | 32646.25 |  | 0 | 32646.25 |  | 0 | 32646.25 |  | 0 | 32646.25 |  | 0 | 32646.25 | 0 | 34408.33 | 52331.67 | 393962.66 | -307222.66
601000 - SAP 4 HANA | 0 | 311110 | 3097554 | 0 | 308200 |  | 0 | 316930 |  | 0 | 305290 |  | 0 | 308200 |  | 0 | 311110 |  | 0 | 305290 |  | 0 | 282010 |  | 0 | 311110 | 0 | 0 | 3097554 | 2759250 | 338304
601005 - INFRA IT | 1637.665 | 53387 | 1023055.659 | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 |  | 0 | 53387 | 0 | 1637.665 | 1023055.659 | 480483 | 544210.324
601007 - GLIMS | 0 | 27969.2 | 196486.338 | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 |  | 0 | 27969.2 | 0 | 0 | 196486.338 | 251722.8 | -55236.462
601008 - EMPOWER | 0 | 30337 | 142045.404 | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 |  | 0 | 30337 | 0 | 0 | 142045.404 | 273033 | -130987.596
601072 - PILOTAGE | 0 | 62300 | 689900 | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 |  | 0 | 62300 | 0 | 0 | 689900 | 560700 | 129200
601006 - MASTER CONTROL | 5111 | 42685 | -44804.9 | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 |  | 0 | 51360 | 0 | 5111 | -44804.9 | 453565 | -493258.9
601009 - ONGUARD | 0 | 18550 | 72300 | 0 | 21200 |  | 0 | 21200 |  | 0 | 21200 |  | 0 | 21200 |  | 0 | 21200 |  | 0 | 21200 |  | 0 | 21200 |  | 0 | 18550 | 0 | 0 | 72300 | 185500 | -113200
601068 - PROCAL | 39308 | 44808 | 113092 | 0 | 25500 |  | 0 | 5500 |  | 0 | 5500 |  | 0 | 5500 |  | 0 | 5500 |  | 0 | 5500 |  | 0 | 5500 |  | 0 | 5500 | 0 | 39308 | 113092 | 108808 | 43592
601002 - PI | 0 |  | 41600 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 41600 | 0 | 41600
601003 - STOCKWARE | 0 |  | -7460 | 0 | 34700 |  | 0 | 32320 |  | 0 |  |  | 0 |  |  | 0 | 32320 |  | 0 |  |  | 0 | 24240 |  | 0 | 8080 | 0 | 0 | -7460 | 131660 | -139120
2021
| engagés |  | engagés | engagés |  | engagés | engagés |  | engagés | engagés |  | engagés | engagés |  | engagés | engagés
Projet | Janvier |  | Février | Mars |  | Avril | Mai |  | Juin | Juillet |  | Août | Septembre |  | Octobre | Novembre | Décembre |  |  | Total :
601004 - PAS-X | 24320 |  | 0 | 29205 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12240 |  | 13600 | 10880 | 12240 |  |  | 102485
601000 - SAP 4 HANA | 0 |  | 8450 | 24590 |  | 27865 | 39715 |  | 53585 | 46325 |  | 31170 | 83367 |  | 98603 | 92970 | 86469 |  |  | 593109
601079 - Modernisation B80 L2 - 2022 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
601005 - INFRA IT | 0 |  | 27343.01 | 119990.97 |  | 41198.55 | 58342.75 |  | 81927.75 | 52437.5 |  | 44164.125 | 58411.14 |  | 70150.88 | 74473.36 | 71777.54 |  |  | 700217.575
601007 - GLIMS | 8300 |  | 28465.75 | 11528.25 |  | 4503.55 | 21645.5 |  | 20860.5 | 11347.5 |  | 1750 | 8220 |  | 2970 | 6120 | 4200 |  |  | 129911.05
601008 - EMPOWER | 5262.4 |  | 6685.5 | 6685.5 |  | 4503.55 | 20577.75 |  | 17767.75 | 8915 |  | 3280 | 2100 |  | 14510 | 13515 | 5200 |  |  | 109002.45
600716 - Equipement Production OFM | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5885 |  | 24500 | 28143 | 12893 |  |  | 71421
601072 - PILOTAGE | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 18315 |  |  | 18315
601006 - MASTER CONTROL | 0 |  | 0 | 2874 |  | 9722 | 11682.5 |  | 16038 | 11061.5 |  | 5748 | 8622 |  | 0 | 11080 | 22570 |  |  | 99398
601009 - ONGUARD | 8145 |  | 0 | 8145 |  | 0 | 0 |  | 0 | 0 |  | 500 | 10750 |  | 10500 | 2500 | 8640 |  |  | 49180
601068 - PROCAL | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 9000 |  |  | 9000
601002 - PI | 0 |  | 0 | 9250 |  | 5750 | 0 |  | 0 | 0 |  | 0 | 0 |  | 325 | 0 | 0 |  |  | 15325
601003 - STOCKWARE | 0 |  | 0 | 7680 |  | 8160 | 6000 |  | 8640 | 9840 |  | 2400 | 0 |  | 0 | 0 | 0 |  |  | 42720
Total | 46027.4 |  | 70944.26 | 219948.72 |  | 101702.65 | 157963.5 |  | 198819 | 139926.5 |  | 89012.125 | 189595.14 |  | 235158.88 | 239681.36 | 251304.54
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: données extraites du Tableau Reporting
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on J22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on M22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on P22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on S22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on V22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on AB22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forfait Apsalys :69400/8=8675€ par mois
Note on D23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on G23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on M23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on P23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on S23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on V23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039
Note on Y23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reste 13700€ à facturer sur PO-21-1161-00039

## Enveloppes (hidden)
Budgétés (Enveloppe)
Enveloppe | Montants
600727 - SAP ECC6 | 1825000
601000 - SAP 4 HANA | 5517700
601006 - MASTER CONTROL | 367960
600728 - BASEWARE | 368640
600724 - DECIDIUM | 92500
600723 - ETEMPTATION | 83000
601004 - PAS-X | 523250
601003 - STOCKWARE | 220750
601002 - PI | 289750
XXX - GUARDIAN | 119500
XXX - TRACELINK | 125700
601007 - GLIMS | 781750
601008 - EMPOWER | 775387
601009 - ONGUARD | 254300
XXX - GMAO | 827400
601068 - PROCAL | 152400
XXX - REMEDY | 73400
601005 - INFRA IT | 2300000
XXX - SIRH | 33600
XXX - MYLEARNING | 30100
601072 - PILOTAGE | 689900