## Feuil1
Topic To Do vs Topic Done
|  |  | Prio | (Tous)
|  |  | Big Topic | (Tous)
|  |  | Status | (Tous)
|  |  | Week number | Topic's NB | Topic Done
|  |  | 2014-02-15 | 1 | 1
|  |  | 2014-02-17 | 1
|  |  | 2014-02-28 | 9 | 9
|  |  | 2014-03-04 | 1 | 1
|  |  | 2014-03-07 | 8 | 8
|  |  | 2014-03-11 | 1 | 1
|  |  | 2014-03-13 | 1 | 1
|  |  | 2014-03-14 | 1 | 1
|  |  | 2014-03-15 | 1 | 1
|  |  | 2014-03-20 | 3 | 3
|  |  | 2014-03-26 | 1 | 1
|  |  | 2014-03-27 | 4 | 4
|  |  | 2014-03-29 | 1 | 1
|  |  | 2014-04-01 | 1 | 1
|  |  | 2014-04-03 | 1 | 1
|  |  | 2014-04-14 | 2 | 3
|  |  | 2014-04-15 | 9 | 3
|  |  | 2014-04-16 | 2 | 1
|  |  | 2014-04-18 | 1
|  |  | 2014-04-25 | 8 | 6
|  |  | 2014-04-29 | 2
|  |  | 2014-04-30 | 23 | 7
|  |  | 2014-05-09 | 5
|  |  | 2014-05-14 | 1
|  |  | 2014-05-15 | 3
|  |  | 2014-05-29 | 2
|  |  | 2014-05-30 | 6
|  |  | 2014-05-31 | 7
|  |  | 2014-06-15 | 8
|  |  | 2014-06-27 | 1
|  |  | 2014-06-29 | 2
|  |  | 2014-06-30 | 28 | 1
|  |  | 2014-07-30 | 11
|  |  | 2014-08-30 | 1
|  |  | 2014-09-01 | 1
|  |  | 2014-09-28 | 1
|  |  | 2014-09-30 | 1
|  |  | 2014-10-31 | 6
|  |  | 2014-11-30 | 2
|  |  | 2014-12-30 | 2
|  |  | 2014-12-31 | 5
|  |  | (vide) | 5 | 4
|  |  | Total général | 180 | 59
File's number by big topic
| Priority | (All)
| Big Topic | Topic's NB
| D | 66
| M | 25
| p | 10
| R | 34
| T | 21
| U | 23
| Grand Total | 179

## Feuil2
|  | ê |  |  | ê |  | ê |  | ê |  | ê |  | ê |  |  |  |  | ê
Topic number | Topic requiring attention | Prio | Big Topic | Topic | Issue | Root causes | Actions to remediate root causes | Who | Real responsible | Refernce due date | due date | Week N° | Actual date (when done) | Week N° | Earliest deadline | Lastest Deadline | Temporary solution | Status | Coments from Nathalie | Stream | Business Coordinator | Activities | Description/Deliverables | Need IS project team support ? | Can/ should it be done with Sanofi ? | IS Contractor Name | IS Responsible | Business Responsible | Others people involved | Status | Who leads | Comments
1 |  | 1 | D | D1_QC__Process | No Procedure |  | Definition of the QC Check process--> Create a Pasteur QSOP, related to QSOP-008142 SHARE - Management of Data Quality Control, and send it in review | RegOps | Marion / Karina | 2014-03-29 | 2014-03-29 | 13 | 2014-03-27 | 13 |  |  |  | Completed |  | QC Check | Karina | QC Check Process & Implementation | Create a SOP and send it in review | no | no |  |  | Karina | RACC members E. Michoud / S.Melot / P.Kunert / Nicoletta |  |  | 2014/03/24 KN SOP will be sent to RACC members during this week
1 |  | 1 | D | D1_QC__Process | No Procedure |  | Review Sanofi QC documents - 3 key QDs : Sop 008142 and BTD 012412 | RegOps | Marion / Karina | 2014-04-15 | 2014-04-15 | 16 | 2014-04-10 | 15 |  |  |  | completed | [13 empty] | to be discussed with ES and Xl on April 15th
1 |  | 1 | D | D1_QC__Process | No Procedure |  | to include pasteurs requiremetns in Sop 008142 and BTD 012412 | Sanofi | E.Souchu / X,Launois | [8 empty] | On-going
2 |  | 1 | D | D1_QC__Process | No QC Process |  | Implementatio of the QC Check process - one commun process with Sanofi - Define communication plan - Communication to management - Communication to users (reading+ ISOtrain) - Train users on the rules to be applied - Ensure Follow-up and traçability (check if corrections are done in due time, with good quality) - Define KPIs (and their evolutions) and provide them to Q&CI - Data quality monitoring and summary reports (results' publication) 2014-02-05 Xavier Launois from Sanofi is agree to use SHARE QC page (Admin page+User's page) 2014-02-18 Ensure that all RPM have access to SHARE QC page Ask Sanofi to create folders on Sharepoint SHARE QC site according to QC Catalog | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going |  | QC Check | Karina | QC Check Process & Implementation | Definition of the QC Check process and its implementation. - QSOP-008142 SHARE - Management of Data Quality Control: assess if it is relevant for Pasteur --> create a Pasteur QSOP with Nicoletta's support. include the QC of reports sent to HA or PV or IO in the QSOP (= a check have to be done by the RPM before sending the report to HA) - Author a User Guide (Business Technical Document) (explain the strategy of QC Checks ex: completeness, consistency, naming convention) - 1st QC check to be done by end January (with available reports), then monthly - Train/communicate to users the rules to be applied (eg 5 days to corrects, how to do it) - Ensure Follow-up and traçability (check if corrections are done in due time, with good quality) - Define communication template - Define KPIs (and their evolutions) and provide them to Q&CI (Nicoletta). Ask Q&CI to communicate to users, Richard, Sanofi, | no | no |  |  | Karina | E. Michoud / S.Melot / P.Kunert / Nicoletta |  |  | 2014/03/24 KN SOP will be sent to RACC members during this week
3 |  | 1 | D | D1_QC__Process | No QC Catalog |  | Author a QC Catalog (Business Technical Document) - explain the strategy of QC Checks ex: completeness, consistency, naming convention Include the QC of reports sent to HA or PV or IO in the QSOP (= a check have to be done before sending the report to HA) List the regulatory key processes and define what we need to Qced for each RA process - define critical data (Usage of incorrect data vs. impact, relation between tools - SAP; ...) | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | Cancelled |  | QC Check | Karina | QC Check Process & Implementation | Definition of the QC Check process and its implementation. - QSOP-008142 SHARE - Management of Data Quality Control: assess if it is relevant for Pasteur --> create a Pasteur QSOP with Nicoletta's support. include the QC of reports sent to HA or PV or IO in the QSOP (= a check have to be done by the RPM before sending the report to HA) - Author a User Guide (Business Technical Document) (explain the strategy of QC Checks ex: completeness, consistency, naming convention) - 1st QC check to be done by end January (with available reports), then monthly - Train/communicate to users the rules to be applied (eg 5 days to corrects, how to do it) - Ensure Follow-up and traçability (check if corrections are done in due time, with good quality) - Define communication template - Define KPIs (and their evolutions) and provide them to Q&CI (Nicoletta). Ask Q&CI to communicate to users, Richard, Sanofi, | no | no |  |  | Karina | E. Michoud / S.Melot / P.Kunert / Nicoletta |  |  | 2014/03/24 KN SOP will be sent to RACC members during this week
4 |  | 1 | D | D1_QC__Process | Methodology of QC |  | Schedule meeting with Sanofi (Xavier L, Eric S.) on data QC each two weeks | RegOps | Marion / Karina | 2014-03-26 | 2014-03-26 | 13 | 2014-03-26 | 13 |  |  |  | Completed |  | QC Check | Karina | QC Check Process & Implementation |  | no | yes
5 |  | 1 | D | D4_QC_Catalogue | No QC process |  | One common Data system QC Report - QC completeness of data for PV mandatory fields based on the PSUR and PSMF Reports | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going |  | QC Check | Karina | QC Check Process & Implementation |  | no | yes |  |  |  | R. Rabiega M. Pustejovska |  |  | The specification document has been reviewed and sent on March 21
6 |  | 1 | D | D1_QC__Process | Methodology of QC |  | Approach to extract data should be reviewed - only errors vs. all records, then filter --> + ratio / metrix - several QC (by Entity or by RA process) or less QC but several data to correct - do we use Sanofi QCreports or we develop the customized QC for Pasteur Assess if we should show in the results only mandatory fields Should we put in place QC Calendar (i.e. period dedicated to data correction) | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | Cancelled
7 |  | 1 | D | D4_QC_Catalogue | Several QC to develop |  | List QC to develop and prioritize 2014/02/06 Check first new data entry and pay attention to Affiliates activities, as it is new BUT for several reasons (audit, reports, SBS) we need to ensure consistency between fields for ALL DATA 2014/01/30 Priorities: 1) Check data completness of SP business mandatory fields = missing data for not system madatory fields 2) Check consistency for mandatory fields - For each regulatory process - For SBS (check fields CCR#, Registration #, and make users sensitive to Event country status) --> end of Q1 - See if users have found inconsistencies? 3) Check completeness for not mandatory fields 4) Check data consistency of SP system mandatory fields for migrated data - Run the Pasteur remediation plan - QC for CMO PPO reports - communicate to CMO management and to Sanofi. See with Sylvie Taulelle | RegOps | Marion / Karina | 2014-05-30 | 2014-05-30 | 22 | [5 empty] | On-going
8 |  | 1 | D | D4_QC_Catalogue | Several causes : missing data, data entry errors, no data entry monitoring |  | Define QC reports to check completeness of data | RegOps / IS | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 |  |  |  |  | NA | Cancelled |  | QC Check | Karina | Data Completeness | QC Check completeness on thePasteur's mandatory fields not system mandatory. Finalization of the first QC Checks Reports + Development of additionnal Reports | yes | yes |  | Jeff | Karina
9 |  | 1 | D | D1_QC__Process | Several causes : inconsistent data, data entry errors, no data entry monitoring |  | Define QC reports to check consistency of data | RegOps / IS | Marion / Karina | 2014-08-30 | 2014-08-30 | 35 | [5 empty] | Cancelled |  | QC Check | Karina | Data consistency | QC Check conistencyon thePasteur's mandatory fields not system mandatory. Finalization of the first QC Checks Reports + Development of additionnal Reports
10 |  | 1 | D | D2_Guidance | Inconsistent data (process) The PBRER report is not always correct : issue : 402 registrations without package set (data quality issue): will be display as empty (SmPC, Marketing status, marketing status date (it was not in Register) |  | - Prepare a set of slide to explain how to create these data (Sandrine + Karina) - Process to reopen the events of the migration to correct the PDS is ongoing - we need to agree on rules - Ask the users to populate the data (QC stream) - Can we automatically create the Package set for withdrawn / Expired registrations ?--> Christophe will check with Sudha the feasibility | RegOps | Marion / Karina | 2014-04-15 | 2014-04-15 | 16 | [5 empty] | cancelled |  | QC Check | Karina | Data consistency | 402 registration without package set (see extract provided by Remy) where 201 are approved | yes | [7 empty] | when in Register, the license status has been filled in the following order: approved originally, sent to submitting body and\or submitted and approved/licensed, the "approved" was migrated as reference because in the event we cannot have 2 identical statuses. The most recent date at the Event level is the date of sent to submitting body or submitted and this is why at the Application level, the status is planned (for sent to submitting body) or submitted (for submitted)
11 |  | 1 | D | D3_Data_correction | Inconsistent data for 402 registrations without package set (correction) The PBRER report is not always correct : issue : 402 registrations without package set (data quality issue): will be display as empty (SmPC, Marketing status, marketing status date (it was not in Register) |  | Manual data entry (201 corrections to be done for Package set to be associated to registration) - Events PDS Migration must be reopened by SHARE Admin Automated update needs to go thru a change control process (FS, UAT, ...) - 5-8 weeks | Franchise & Regions TBC | Marion / Karina | 2014-05-30 | 2014-05-30 | 22 | [5 empty] | On-going |  | QC Check | Karina | Data consistency | 402 registration without package set (see extract provided by Remy) where 201 are approved | yes
12 |  | 1 | D | D4_QC_Catalogue | The difference between application status date and the registrations status date may be source of misunderstanding |  | Communicate to users OR MODIFIED IT - for eVMPD purpose, the Registration status date should be the last approval date The application status date (= date of the most recent approval is the date of the reference) and the registration status date (= date of the most ancient approval because status dates " approved originally " in eTRAC will be different. And it is logical: the application had a second approval of the HA, on the other hand, for the PBRER we take the status of the registration which has to be the most ancient date. | RegOps Véronique | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going |  | QC Check | Karina | Data consistency
13 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (registration number) Registration number values are not correct |  | QC Data Consistency_Registration Number | RegOps | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-04-01 | 14 |  |  |  | Completed |  | QC Check | Karina | Data consistency | 156 Approved Registration with registration # issue (see extract provided by Sandrine) o not specified o not speicified o No license number issued o Not applicable o No licence number issued o NOT YET KNOWN o No license number yet issued o PENDING o Not available o UN o STAMARIL o NO NUMBER ISSUED o No lincense number issued o See pack nr o OPV Merieux o There are as many license numbers as presentations o See pack number o TBD o see pack nb | yes | yes |  | Jeff
14 |  | 1 | D | D3_Data_correction | Inconsistent data (registration number) Registration number values are not correct |  | Manual correction | Franchise & Regions | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | Planned |  | QC Check | Karina | Data consistency | 156 Approved Registration with registration # issue (see extract provided by Sandrine) o not specified o not speicified o No license number issued o Not applicable o No licence number issued o NOT YET KNOWN o No license number yet issued o PENDING o Not available o UN o STAMARIL o NO NUMBER ISSUED o No lincense number issued o See pack nr o OPV Merieux o There are as many license numbers as presentations o See pack number o TBD o see pack nb | yes | yes |  | Jeff
15 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (CCR number format) The CCR number format is wrong - Sometimes, the CCR number appears three times in CCR column |  | QC Data consistency- CCR number |  | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-04-01 | 14 |  |  |  | Completed
16 |  | 1 | D | D3_Data_correction | Inconsistent data (CCR number format) Sometimes, the CCR number appears three times in CCR column |  | Manual correction Events must be reopened by SHARE Admin Automated update needs to go thru a change control process (FS, UAT, ...) - 5-8 weeks |  | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | Planned
17 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (PDS with no presentation) PDS with no presentation --> Package set name appear in APR Report |  | QC Data consistency-PDS low with no Presentation | RegOps | Marion / Karina | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 |  |  |  | Completed |  | QC Check | Karina | Data consistency | 864 PDS low with no presentation (175 application are approved but Package Set Name used in APR Reports with no filter on Application status or Registration status) ALSO 582 registration # issue: 499 registration numbers are empty -–72 are populated with the inconsistent value:  Not yet known  UNKNOWN  NOT APPLICABLE  See pack nr  NOT SPECIFIED  TBD  No license number issued  not speicified  No licence number issued  PENDING o 11 should be updated:  1154/Z AND 249/Z  585M2000 SSA (Public)  E-10350 (initial); BE-00132 (renewal)  501M2000 SSA (public)  9427-P1127-24 - No longer marketed.  STN: BL 103924; Menomune A not mfg or marketed  STN: BL 103925; Menomune A/C not mfg or marketed.  STN: BL 103923; Menomune C not mfg or marketed.  PBKD 871604A (5 mL); 880247A (10 mL)  N 4.882 (License as of Aug.2003)  128 78 23830 00 (August 15. 2007)
18 |  | 1 | D | D3_Data_correction | Inconsistent data (PDS with no presentation) PDS with no presentation --> Package set name appear in APR Report |  | Manual correction check if users can update data and inform users Events PDS Migration must be reopened by SHARE Admin Automated update needs to go thru a change control process (FS, UAT, ...) - 5-8 weeks | Franchise & Regions / Reg ops : TBC | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | Planned |  | QC Check | Karina | Data consistency | 864 PDS low with no presentation (175 application are approved but Package Set Name used in APR Reports with no filter on Application status or Registration status) ALSO 582 registration # issue: 499 registration numbers are empty -–72 are populated with the inconsistent value:  Not yet known  UNKNOWN  NOT APPLICABLE  See pack nr  NOT SPECIFIED  TBD  No license number issued  not speicified  No licence number issued  PENDING o 11 should be updated:  1154/Z AND 249/Z  585M2000 SSA (Public)  E-10350 (initial); BE-00132 (renewal)  501M2000 SSA (public)  9427-P1127-24 - No longer marketed.  STN: BL 103924; Menomune A not mfg or marketed  STN: BL 103925; Menomune A/C not mfg or marketed.  STN: BL 103923; Menomune C not mfg or marketed.  PBKD 871604A (5 mL); 880247A (10 mL)  N 4.882 (License as of Aug.2003)  128 78 23830 00 (August 15. 2007)
19 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (PDS high) | Several sites are not populated in PDS high | QC | RegOps | Marion / Karina | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 |  |  |  | Completed |  | QC Check | Karina | Data consistency | 193 PDS high where at last one function (Manufacturer, Control, Release) is not filled at Component level (157 PDS where application is approved) 125 PDS high where at last one function (Manufacturer, Control, Release) is not filled at Product level (90 PDS where application is approved)
20 |  | 1 | D | D3_Data_correction | Inconsistent data (PDS high) Several sites are not populated in PDS high at the component and at the product Level |  | manual data entry (Data consistency - The PDS high with no Component functions • Data consistency - The PDS high with no Product functions) check if users can update data and inform users Events PDS Migration must be reopened by SHARE Admin | Franchise & Regions (TBC) | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | Planned |  |  |  |  | 193 PDS high where at last one function (Manufacturer, Control, Release) is not filled at Component level (157 PDS where application is approved) 125 PDS high where at last one function (Manufacturer, Control, Release) is not filled at Product level (90 PDS where application is approved)
21 |  | 1 | D | D4_QC_Catalogue | Missing data (Field role) The field "Role", used in PV Report, is automatically populated following the data selected in Reviewing Country, Co-Rapporteur and countries. These fields are not always populated |  | QC Data completeness – only Co-Rapporteur field | RegOps | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-03-31 | 14 |  |  |  | Completed |  |  |  |  | 7 Co-Rapporteur fields are empty in Application Attributes for EU-CP procedure | yes | yes |  | Jeff |  |  |  |  | 2014/03/24 KN QC Report is not correct and should be updated
22 |  | 1 | D | D3_Data_correction | Missing data (Field role) The field "Role", used in PV Report, is automatically populated following the data selected in Reviewing Country, Co-Rapporteur and countries. These fields are not always populated |  | data correction | Franchise & Regions | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | Planned |  |  |  |  | 7 Co-Rapporteur fields are empty in Application Attributes for EU-CP procedure | [8 empty] | 2014/03/24 KN QC Report is not correct and should be updated
23 |  | 1 | D | D4_QC_Catalogue | Missing data (product dosage form) Product dosage form is not always filled |  | QC Data completeness - Product | RegOps | Marion / Karina | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 |  |  |  | Completed |  |  |  |  | 85 Products without Product Dosage Form data (56 products family status are active)
24 |  | 1 | D | D3_Data_correction | Missing data (product dosage form) Product dosage form is not always filled |  | data correction -85 Products without Product Dosage Form data (56 products family status are active), logged on SharePoint Q&A | Reg Ops | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going |  |  |  |  | 85 Products without Product Dosage Form data (56 products family status are active)
25 |  | 1 | D | D4_QC_Catalogue | Missing data (IBD and IBD country) IBD AND IBD Country are not always filled (used in PBRER report) |  | QC Data completeness | RegOps | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-03-31 | 14 |  |  |  | Completed |  |  |  |  | IBD AND IBD Country are always filled! (for Application type ='Market Authorisation Application', Application status='Approved") but in PBRER report the filter is on registration status = ‘approved’, ‘withdrawn’ or ‘expired’ | yes | yes |  | Jeff |  |  |  |  | 2014/03/24 KN QC Report is not correct and should be updated
26 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (Application status and registration status) Application status and registration status are not consistent |  | QC Data consistency | RegOps | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-03-31 | 14 |  |  |  | Completed |  |  |  |  | January - 36 inconsistencies between Application Status and Registration status. 32 errors corrected. 4 still need to be fixed
27 |  | 1 | D | D4_QC_Catalogue | The PDSs associated to applications that are no longer valid (withdrawn or expired) are still show as “approved.” |  | commun QC reports with Sanofi OR use of the Queries management process Update QC on Application status - Registratus status consistency to include PDS status | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | Planned
28 |  | 1 | D | D3_Data_correction | The PDSs associated to applications that are no longer valid (withdrawn or expired) are still show as “approved.” |  | it’s so difficult to correct all the PDS with status Approved (if the registration is approved, withdrawn or expired) manually, i think that we can identify all these cases via QC but I don’t know if we can find solution to correct it automatically --> Automated update needs to go thru a change control process (FS, UAT, ...) - 5-8 weeks | RegOps | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going
29 |  | 1 | D | D3_Data_correction | Inconsistent data (Application status and registration status) Application status and registration status are not consistent |  | data correction | RegOps & Franchise/Regions/Share writers | Marion / Karina | 2014-05-30 | 2014-05-30 | 22 | [5 empty] | On-going |  |  |  |  | February - 7 inconsistencies between Application Status and Registration status. 5 errors corrected. 2 still need to be fixed January - 36 inconsistencies between Application Status and Registration status. 32 errors corrected. 4 still need to be fixed
30 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (Business entity) Business Entity can be changed by users |  | QC Data consistency-Business Entity Check if there are similar cases than 314 HongKong, Perform correction for all similar cases | RegOps | Marion / Karina | 2014-03-11 | 2014-03-11 | 11 | 2014-03-11 | 11 |  |  |  | Completed | [5 empty] | yes | yes |  | Jeff
31 |  | 1 | D | D3_Data_correction | Inconsistent data (Business entity) Business Entity has been changed by users |  | data correction 284 Indonesia | RegOps | Marion / Karina | 2014-03-13 | 2014-03-13 | 11 | 2014-03-13 | 11 |  |  |  | Completed
32 |  | 2 | M | M1a_Missing_data | The PBRER report is not always correct | No registrations for Republic of Srpska (as requested for the migration!) | manual data entry by SHARE team |  | Denis/Jeremy |  |  |  | 2014-03-31 | 14 |  |  | add manually the Srpska registrations in the PBRER Report | Cancelled |  |  | Denis | [6 empty] | Denis
33 |  | 1 | T | P1_Process | Procedures are not available and up-to-date : Update easytrac-SHARE procedure (to replace easytrac-etrac GQ_001300) | Procedures are not available and up-to-date | Update easytrac-SHARE procedure (to replace easytrac-etrac GQ_001300) | RegOps | Jeremy/Moncef | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-31 | 2014-04-30 |  | On-going |  | Process & Procedure | Paul | procedures to be created |  | no | yes
34 |  | 1 | U | U1_User support | Inspection readiness | Training documentation not fully well managed | manage training documentation following Sanofi procedure | RegOps | Stephanie/Denis | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-31 | 2014-04-30 |  | On-going |  | Training | Denis | System Admin | Ensure that all training records are well managed, following procedure | no | no |  |  | Denis | Laurent, Valérie | on-going | Denis
35 |  | ? | M | M2_Migrated_data_incorrect | The PBRER report is not always correct | A few registration + application status wrongly migrated for MRP (position opinion taken instead of approved status) | Manual data entry for products with PBRER in Q1 2014 | RegOps | Denis/Jeremy | 2014-02-17 | 2014-02-17 | 8 |  |  | 2014-02-17 |  |  | Completed | the PBRER report should not rely on the application status
36 | Mandatory field | 1 | D | D1b_Missing_data | No data regarding marketing information | « Currently Marketing status » and « marketing date » are empty (because in etrac, field was empty) | Agree with Sanofi about the definition of the 3 fields : Marketing status, marketing date, marketing cessession date | RegOps | Edouard | 2014-04-15 | 2014-04-15 | 16 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | QC Check | Karina | Marketing status | Define a prosition paper, to be signed by PV and RA on the 3 fields to enter in SHARE : Currently marketed in country (y/n), Marketing date (= 1st marketing date), Marketing Cessession date | yes | yes | E. Donato | C. Chabert | Karina | Marion, PV for the definitions | on-going |  | 2014/03/24 KN Supplies Dpt provide us with the “marketed date” --> feasibility to assess by ED; update scenario 3 based on supply status - resume countries position taking into example MHRA sunset clause interpretation 2014/02/10 KN : Karina - prepare a position paper (issues, discussion: definitions, advantages / disadvantages of what can be done, what we propose). Rules for Qwick win are defined
37 | Mandatory field | 1 | D | D1b_Missing_data | No data regarding marketing information | « Currently Marketing status » and « marketing date » are empty (because in etrac, field was empty) | Create a shortfix to set to 'not marketed' all expired, withdrawn… registrations or products | RegOps / IS | Edouard | 2014-05-09 | 2014-05-09 | 19 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | QC Check | Karina | Marketing status | Quick win : patch ● When the Product Family Status='Inactive' in Product Family Attributes, update the "Currently Marketed in Country?" in Registration Package Set - Country to 'NO'. ● If Registration status='Withdrawn' OR 'Expired' in Registration update "Currently Marketed in Country?" in Registration Package Set - Country to 'NO' and populate the field “Marketing Cessation Date” with the value displayed in “Expiration Date/Registration Valid Until” field (Package Set Registration Entity) LE BUG Withdrawn date est au niveau de Registration status date (date at registration level is wrong), on pourra donc faire le qwick win avant de corriger ce bug ● If Application Status=’Abandoned’ update "Currently Marketed in Country?" in Registration Package Set - Country to 'NO' and populate the field “Marketing Cessation Date” with the value displayed in “Application Status Date” field and Remove “Marketing status to be verified – DO NOT USE” from the field « Registration-Package Set Country Description » | yes | yes | E. Donato | C. Chabert | Karina | Marion, PV for the definitions | on-going | Biz | 2014/02/18 KN Rules for Qwick win are defined
38 |  | 1 | D | D7_QC Report | Inconsistent data (Business entity) Business Entity can be changed by users |  | Update all QC Reports - remove the filter on Business Entity | RegOps | Marion / Karina | 2014-05-30 | 2014-05-30 | 22 | [5 empty] | Cancelled
39 |  | 2 | D | D4_QC_Catalogue | Inconsistent data (approval dates 1900) Some approval dates in 1900 are displayed (because in etrac, it was empty or 11/11/1111) |  | commun QC reports with Sanofi OR use of the Queries management processi | Reg ops | Marion / Karina | 2014-11-30 | 2014-11-30 | 49 |  |  | 2014-12-31 | 2015-01-30 |  | Planned | [5 empty] | yes | yes |  | Jeff
40 |  | 2 | D | D3_Data_correction | Inconsistent data (approval dates 1900) Some approval dates in 1900 are displayed (because in etrac, it was empty or 11/11/1111) |  | Correct the status dates in SHARE | L/F - Regions | Marion / Karina | 2014-12-31 | 2014-12-31 | 53 |  |  | 2014-12-31 | 2015-01-30 |  | Planned
41 | Mandatory field | 1 | D | D1b_Missing_data | No data regarding marketing information | « Currently Marketing status » and « marketing date » are empty (because in etrac, field was empty) | Extract from SAP and import into SHARE marketing dates and Marketing cessession dates | RegOps / IS | Edouard | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | QC Check | Karina | Marketing status | Define the process to update the data into SHARE (affiliates) (Zentiva : affiliates have 6 months to enter the data) | yes | yes | E. Donato | C. Chabert | Karina | Marion, PV for the definitions | on-going | Biz | 2014/02/04 KN : Evelyne is checking if data can be extract from "Time to Market"
42 | Mandatory field | 1 | D | D1b_Missing_data | No data regarding marketing information | « Currently Marketing status » and « marketing date » are empty (because in etrac, field was empty) | Write process (Working instruction to update the marketing status | RegOps | Edouard | 2014-05-31 | 2014-05-31 | 22 |  |  | 2014-12-31 | 2015-01-30 |  | On-going
43 |  | 1 | R | R1_PBRER_Report | How to manage "withdrawn reason" at registration level | The “Withdrawn Reason” for the registrations is not available in SHARE data model. The only value we have is the Withdrawn Reason for the Applications. The process topic will be investigated. | The process topic will be investigated.: switch the withdrawn reason at package set level : New change to be evaluated (feasibility) - update supporting documentation needed for the eVMPD purpose | RegOps/SHARE IS | Jeremy/Moncef | 2014-09-30 | 2014-09-30 | 40 |  |  | 2014-04-01 | 2014-05-01 |  | On-going
44 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (PDS primary packaging information and secondary packaging) There is no packaging in some PDS. We need to map the good packaging with a good component |  | commun QC reports with Sanofi OR use of the Queries management process QC Data consistency-PDS with no primary packaging | RegOps/IS | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-12-31 | 2015-01-30 |  | On-going | [5 empty] | yes | yes |  | Jeff |  |  |  |  | ??
45 |  | 1 | D | D3_Data_correction | Inconsistent data (PDS primary packaging information and secondary packaging) The entity “Primary Packaging” is not filled for combo (2 dilutes or 2 products). We need to map the good packaging with a good component |  | correction - map Events PDS Migration must be reopened by SHARE Admin | RegOps & Franchise/Regions/Share writers | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 |  |  | 2014-12-31 | 2015-01-30 |  | On-going | [13 empty] | ??
46 |  | 1 | R | R2_Variation_Follow_up_Report | Variation follow up report is not correct | VALEURMULTI in the Change type field (because multi reporting level entered in etrac for the same registration ie No reporting & international variation) | Communicate the corrective actions (workaround) | RegOps | Paul | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 |  |  |  | Completed | Cleaning of the status must be performed in SHARE and we should not modify the report. Each time we are doing an evolution to the report we have to balance the benefits vs the risks of regressions--> Prio 2 | Reports & Metrics
47 |  | 1 | R | R1_PBRER_Report | The PBRER report is not always correct | As many lines as number of countries in the MRP | Investigate and correct ; The difference between the lines correspond to the SmPC name which is different | RegOps / IS |  | 2014-03-20 | 2014-03-20 | 12 | 2014-03-20 | 12 | 2014-03-15 | 2014-04-14 |  | Completed
48 |  | 1 | D | D3_Data_correction | The Variation Follow up report is not always correct Product 314 Hong Kong is under "Sanofi" and not "Sanofi Pasteur" |  | Correct the value | Karina | Marion / Karina | 2014-03-04 | 2014-03-04 | 10 | 2014-03-04 | 10 | 2014-03-15 | 2014-04-14 |  | Completed | [13 empty] | which value, done by who? When? Justification?
49 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (CCR number/events) In the Reports, the “valeurmulti” value appears in CCR column and in Event status name column, when there are two events having an identical event name in SHARE. The data need to be updated in the system |  | Analyze CCR QC report results and retrieve the events to correct | RegOps/IS | Marion / Karina | 2014-05-30 | 2014-05-30 | 22 |  |  | 2014-06-30 | 2014-07-30 |  | Planned
50 |  | 1 | D | D3_Data_correction | Inconsistent data (CCR number/events) 329 Bolivia - CCR 2031436 : 2 lines for the same CCR |  | 2 similar events with different codes: => 2 lines to correct | Umanis | Marion / Karina | 2014-04-15 | 2014-04-15 | 16 |  |  | 2014-06-30 | 2014-07-30 |  | On-going
51 |  | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | Wrong information for the the "event description" | Decision to suppress the “event description” | Report team |  | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-03-15 | 2014-04-14 |  | Completed
52 |  | 1 | T | T7_BO_universe | The PBRER report is not always correct : to decide as system does not allow : workaround via BO : display date not available if 1900 ,,, | Some approval dates in 1900 are displayed (because in etrac, it was empty or 11/11/1111) | Investigate if In PBRER and PVSMF reports it is posisble to replace "1/03/1900" by "Date not known" ? (feasibility, agreement from users) | RegOps / IS | Maria | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-31 | 2014-04-30 |  | On-going
53 |  | 1 | U | U1_User support | The PBRER report is not always correct | Data entry by affiliates not always up-to-date or wrong | Perform booster traing sessions to affiliates to ensure they | RegOps | Stephanie/Denis | 2014-03-27 | 2014-03-27 | 13 | 2014-02-20 | 8 | 2014-02-25 | 2014-03-27 | NA | Completed | As this is a specific case, wouldn't it be more efficient to manually remove the 2 others lines from the report before sending it to PV ? Each time we are doing an evolution to the report we have to balance the benefits vs the risks of regressions. | Training | Denis | Training | Booster sessions |  |  |  |  | Denis | M.Kafi / S.Melot / M.Sansaet / J.Kane | Completed | Denis
54 | Compliance | ? | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | VALEURMULTI in the change type field, in case of 2 submisisons related to the same CCR with similar status and dates | Develop Workaround | RegOps / IS | Edouard/Maria | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 | 2014-02-28 |  |  | Completed | /
55 | Compliance | 1 | T |  | When updating the status of first event linked to an Application to ‘approved’, the application status is automatically updated as approved with the same date | The system interprets this first Pre-licensure events as the initial application event. Then the Application status is updated automatically by the tool to ‘approved’ and the application status date is set to the approval date of the event. | Communicate to users | Paul | Denis/Jeremy | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-03-10 |  |  | completed
56 | Compliance | 1 | T |  | When updating the status of first event linked to an Application to ‘approved’, the application status is automatically updated as approved with the same date | The system interprets this first Pre-licensure events as the initial application event. Then the Application status is updated automatically by the tool to ‘approved’ and the application status date is set to the approval date of the event. | Do we need to track pre-licensure event in SHARE. Is it within the scope of SHARE? Based on the analysis outcome, plan for correction and preventive actions (several options are possible). | Paul / Franck | Paul/Jeremy | 2014-06-15 | 2014-06-15 | 25 |  |  | 2014-03-31 | 2014-05-30 |  | On-going |  |  | Jeremy | [6 empty] | Jeremy | Denis
57 |  | 2 | R | R4_Make_Reports_more robust_to_bad_data_quality | Even if the reports are technically fine, Reports using the Application status may be wrong, as the application status may be wrong (When updating the status of first event linked to an Application to ‘approved’, the application status is automatically updated as approved with the same date)lly updated as approved with the same date | The system interprets this first In-licensure events as the initial application event. Then the Application status is updated automatically by the tool to ‘approved’ and the application status date is set to the approval date of the event. | Remove if possible appilcation status & use more robust information like registration status : Identify reports using Application Status and Application Status Date. - Suppress when possible the application status in the reports (prompts or results) | Maria / Karina | Edouard | 2014-05-31 | 2014-05-31 | 22 |  |  | 2014-03-12 |  | Corrective action (proposed by Jeremy and Antoine) is to utilize 'reference" to store pre-licensure events | On-going
58 |  | 1 | T |  | When updating the status of first event linked to an Application to ‘approved’, the application status is automatically updated as approved with the same date | The system interprets this first Pre-licensure events as the initial application event. Then the Application status is updated automatically by the tool to ‘approved’ and the application status date is set to the approval date of the event. | Based on the analysis outcome, plan for correction and preventive actions | Edouard M / Renata R. | Edouard | 2014-06-15 | 2014-06-15 | 25 |  |  | Timeline dependent on outcome of the analysis on the reports |  |  | Planned
59 |  | 1 | T | P1_Process | Inspection readiness | need to ensure that affiliates know their responsibilities for the data entry | Create a template of procedure for local affiliate | RegOps | Jeremy | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-06-30 | 2014-07-30 |  | On-going
60 |  | 1 | U | D7_Training - User support | Emphasise the importance of data entry to affiliates |  | Emphasise the importance of data entry to affiliates | Regions head | Stephanie/Denis | 2014-04-15 | 2014-04-15 | 16 |  |  | 2014-03-30 | 2014-04-29 | NA | On-going |  | Training | Denis | Training | Key message to be sent alongside the survey results |  |  |  |  | Denis | Edouard | on-going | Denis | To be communicated alongside survey results?
61 |  | 1 | U | D7_Training - User support | The PBRER report is not always correct |  | Perform survey to estimate the confort of the affiliates to perform the data entry and propose action plan if needed | RegOps | Stephanie/Denis | 2014-04-14 | 2014-04-14 | 16 | 2014-02-27 | 9 | 2014-03-15 | 2014-04-14 | NA | Completed |  | Training | Denis | Training | Survey sent to all Affiliates |  |  |  |  | Denis | Edouard | Completed | Denis
62 |  | 1 | U | D7_Training - User support | Use of the system difficult for some affiliates users | GALY codes not used/known by affiliates: difficult to identify the product when they do not call it the same way than HQ | Store in Sharepoint a table listing all Pasteur SHARE products, with they alternative local trade names | Reg Ops | Stephanie/Denis | 2014-04-18 | 2014-04-18 | 16 |  |  | 2014-04-04 | 2014-04-30 | NA | On-going |  | Training | Denis | Training | Product families table with local trade names | no | no |  |  | Denis |  | on-going | Denis | DJ to send for review to admin by 18/04
63 |  | 2 | T | P1_Process | SmPC name not always consistant (sometime full SmPC name, sometime only trademark) | SmPC name not always consistant (sometime full SmPC name, sometime only trademark) | Define with Sanofi clear rules on SmPC name (local language ?) with Sanofi (QEP2.3) | RegOps | Marion / Karina / Sanofi | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-12-31 | 2015-01-30 | NA | On-going |  | QC Check | Karina | Data Completeness | SmPC name : local language ? | no | yes
64 |  | 1 | M | M1_Missing_data | List of Commitement | Assignee : Need to have users connected at least once to be assignee . | Remind users to connect at least once ????? | RegOps | Denis/Jeremy | 2014-04-14 | 2014-04-14 | 16 | 2014-03-17 | 12 | 2014-03-15 | 2014-04-14 |  | Completed | Urgent reminder ! Before the next patch |  | Denis |  |  | no | no |  |  | Karina |  | Completed | Denis | Reminder sent March 17 + 24
65 |  | 1 | M | M1a_Missing_data | Article 46 data have not been migrated | Some article 46 applications have not been migrated. | Manual Migration | RegOps / IS | Denis/Jeremy | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-04-30 | 2014-05-30 |  | On-going | We should first migrate the Article 46 in SHARE prior to work on the Article 46 reports. --> Prio 2 |  | Denis |  | Manual entry for Article 46 events | yes | no | Remy, Soufiene, Julien | C. Chabert | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine | Planned | Denis | Activity to be launch week 13
66 |  | 1 | M | M1a_Missing_data | The Article 46 report is not always correct | 247 article 46 event have not been migrated. Is it related to the reports ??? Data are therefore missing in reports | Manual Migration | RegOps / IS | Denis/Jeremy | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-04-30 | 2014-05-30 |  | Cancelled | We should first migrate the Article 46 in SHARE prior to work on the Article 46 reports. --> Prio 2 |  | Denis |  | Manual entry for Article 46 events | yes | no | Remy, Soufiene, Julien | C. Chabert | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine | cancelled | Denis | refer to action 65
67 |  | 1 | M | M1a_Missing_data | Some primary packaging have not been migrated (mandatory fields) | Primary Packaging (30 % empty) . (map the good primary packaging with the good component) These values did not exist in Register (mainly for combo) | - Ask for a QC Report - Define a process to ask user to enter the data (+ follow-up). or find the information somewhere (deduction) ???? | RegOps | Marion/Karina | 2014-04-29 | 2014-04-29 | 18 |  |  | 2014-03-30 | 2014-04-29 |  | On-going |  | QC Check | Karina | Data Completeness | Primary Packaging (30 % empty) Checked by Hilary. (map the good primary packaging with the good component) These values did not exist in Register (mainly for combo) : - Ask for a QC Report - Define a process to ask user to enter the data (+ follow-up). or find the information somewhere (deduction) | yes | no |  | Jeff | Karina | Jeremy, Moncef | on-going | Biz | 2014/03/25 KN QC to be developped by IS ( template is ready)
68 |  | 1 | M | M1b_Missing_data | Dose per primary container might be missing (1000 have not been migrated) | Dose per primary container might be missing (1000 have not been migrated) | remigrate the doses per primary container | RegOps / IS | Denis/Jeremy | 2014-05-09 | 2014-05-09 | 19 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  |  | Jeremy |  |  | yes | no | Remy, Soufiene, Julien | C. Chabert | Jeremy |  | on-going | Jeremy
69 |  | 1 | M | M1b_Missing_data | List of Commitments | Comments on the tasks not migrated | Patch | RegOps / IS | Denis/Jeremy | 2014-05-09 | 2014-05-09 | 19 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  |  | Jeremy |  |  | yes | no |  | C. Chabert | Jeremy |  | on-going | Jeremy
70 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | Number of countries in the last lines of the report are not always correct (when CP) | Decision to Suppress the last lines of the report | Report team | Edouard/Maria | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 | 2014-02-28 | 2014-03-30 |  | completed | Yes but then as for the PBRER if we do not have Package set we won't have Smpc names displayed.
71 |  | 1 | M | M1b_Missing_data | List of Commitments | Task updates (assignnees…) not migrated | Patch | RegOps / IS | Denis/Jeremy | 2014-05-09 | 2014-05-09 | 19 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  |  | Jeremy |  |  | yes | no |  | C. Chabert | Jeremy |  | on-going | Jeremy | 2014/03/06 KN: many assignee are not identified in the system. To be checked. Send an update to Remy.
72 |  | 1 | M | M2_Migrated_data_incorrect | The PBRER report is not always correct | Withdrawn dates have been wrongly migrated | Manualy set the right date for product with PBRER in Q1 2014 | RegOps | Denis/Jeremy | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-02-17 |  |  | Completed
73 |  | 1 | M | M2_Migrated_data_incorrect | Withdrawn dates have been wrongly migrated | Withdrawn dates have been wrongly migrated | Re-migrate the good date (patch) | RegOps/IS | Denis/Jeremy | 2014-05-09 | 2014-05-09 | 19 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | Migration (automatic) | Jeremy | SHARE Change Control follow up | For automatic Data Update: - Task Update (Assignee, …) Need to have users connected at least once to be assignee . - Doses per container (1000 have been forgotten, IS has the file, to be loaded). - CT share data - IND protocols - Comments on the tasks - Marketing Status (Karina) - Withdrawn date (date at registration level is wrong also --> used in many key reports and critical ) : | yes | no | S. Fraissard | C. Chabert | Jeremy | Karina, Denis, Véronique, Stéphanie, GAP ETL | on-going | IS
74 |  | 1 | M | M2_Migrated_data_incorrect | The PBRER report is not always correct | A few registration status wrongly migrated | Check ans solve the issue of registrations approved, then withdrawn, then approved | RegOps/IS | Denis/Jeremy | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-02-18 |  |  | Completed | /
75 |  | 1 | M | M2_Migrated_data_incorrect | A few registration + application status wrongly migrated for MRP (positive opinion taken instead of approved status) | A few registration + application status wrongly migrated for MRP (positive opinion taken instead of approved status) | Manual data entry | RegOps | Denis/Jeremy | 2014-04-16 | 2014-04-16 | 16 | 2014-04-14 | 16 | 2014-03-17 | 2014-04-16 |  | Completed |  |  | Denis |  |  | No | no |  |  | Stéphanie
76 | Compliance ??? | 1 | R | R1_PBRER_Report | The PBRER report displays "European Union" information and not each European country | For the Centralized process EU – CP, the registration information is related in SHARE to European Union. Actually, the report does not display all the countries related to the application but to the registration. | This issue must be solved before April (there is no PBRER before this date with CP products). | RegOps/IS | Edouard/Maria/Moncef | 2014-04-15 | 2014-04-15 | 16 |  |  | 2014-03-15 | 2014-04-14 |  | Cancelled
77 | Compliance ??? | 1 | R | R1_PBRER_Report | The PBRER report displays identical lines | Double identical line | To be corrected | RegOps/IS | Edouard/Maria | 2014-04-15 | 2014-04-15 | 16 | 2014-03-30 | 14 | 2014-03-15 | 2014-04-14 | Use the "remove duplicate" functionality of Excel | Completed
78 | Compliance | 1 | R | R1_PBRER_Report | The PBRER report is not always correct | What is displayed as local tradename is a generic name of the product | Change the report | RegOps/IS | Edouard/Maria | 2014-02-15 | 2014-02-15 | 7 | 2014-02-15 | 7 | 2014-02-15 |  | NA | Completed | Correction should be performed as relevant in SHARE by the L/F and Regions
79 | Compliance ??? | 2 | R | R1_PBRER_Report | Enhance the PBRER report to avoid to display "registered but abandonned registrations | Etrac « registered but abandonned » applications are displayed (because the scope of the report is all approved registrations) | Remove from the scope of the report the abandonned applications | RegOps / IS | Edouard/Maria/Moncef | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-15 | 2014-04-14 |  | Cancelled | This is an enhancement compared to eTRAC. Cleaning of the status must be performed in SHARE and we should not modify the report --> Prio 2
80 |  | 2 | D | R1_PBRER_Report | The registrations are not updated to Expired | Etrac « registered but abandonned » applications are displayed (because the scope of the report is all approved registrations) | Set to « expired » the status of the concerned approved registrations if more than 5 years | L/F - Regions | Marion / Karina | 2014-12-31 | 2014-12-31 | 53 |  |  | 2014-12-31 | 2015-01-30 |  | On-going
81 | Compliance | 1 | R | R1_PBRER_Report | The PBRER report is not always correct | IN the PBRER 415 416 Croatia, in the PBRER, we have the 3 lines. We would whish to have only the CP | - Exclude in the PBRER report the registrations “Transfer to CP” (adding this criteria by default) - SOlve the issue of Application non longer valid (withdrawn or expired) when the PDS stil show "approved" - Remove from the scope of the report the abandonned applications - For the Centralized process EU – CP, the registration information is related in SHARE to European Union. Actually, the report does not display all the countries related to the application but to the registration. - Change in all reports the prompte "Business entity" by a more robust prompt: Product type = "vaccines" or "Flu Vaccines". (a QC is performed to check if some users have change the Business entity and to mitigate the risk)-low priority è Action can be completed even if not done) | Report team | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-15 | 2014-04-14 |  | On-going
82 |  | 1 | D | D3_Data_correction | IN the PBRER 415 416 Croatia, in the PBRER, we have the 3 lines. We would whish to have only the CP |  | Update the registration status and the application status for Croatia for the CP 415 416 | V. Jeandel/ M. Kafi | Marion / Karina | 2014-04-15 | 2014-04-15 | 16 |  |  | 2014-03-15 | 2014-04-14 |  | On-going | [10 empty] | M.Kafi
83 |  | 2 | R | R10_RA_data_requested_by_non_RA_functions | Inspection readiness | No specific report available (as PBRER report exists already) | Define and develop a new report with the users : Classical requests for Audit or Inspections (Cf Héloïse Bonnefond) |  | Edouard/Maria | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-30 | 2014-04-29 |  | On-going | It would be great to anticipate this kinds of request from inspection, but if the requirements are not yet defined, the prio 1 is to define the content of the report and then as a prio 2 to develop and test the report. | Reports & Metrics | Maria | New reports | Define and develop a new report with the users : Classical requests for Audit or Inspections (Cf Héloïse Bonnefond) | yes | yes | Sandrine, Jean Michel |  | Maria | Héloise | Planned | IS
84 |  | 2 | R | R14_commitment status report | Improve Commitment status reports (from Jeremy) | Add new features | Replace Existing Commitment Status Report by the one developped by Jeremy + improve it: - Add product family (+ prompt) - Add the county of the application (1 line per country and/or 1 lineper commitment) - Add secondary task type (+ prompt) - Add status of the commitment (+ prompt) - add "application status (after application code) for visibility --> not today, as the application status is not always correct - add event name (for task associated to the event for event -tasks report) - solve issue of link between Event and registration - remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority - Action will be finalized even if this correction is not done) |  | Jeremy | 2014-05-31 | 2014-05-31 | 22 | [5 empty] | On-going
85 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct |  | Suppress the wrong change type in SHARE | L/F - Regions - Transversal team | Edouard/Maria | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 | 2014-02-28 |  | Correct SHARE, and run again the report | Completed | Correction should be performed as relevant in SHARE by the L/F and Regions | 0 | Maria | VFU | Analyse the #multivalue in VFU and put in place remediation : | yes | no | Sandrine, Jean Michel | S. Fraissard | Maria |  | IS
86 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | VALEURMULTI in the change type field, in case of 2 submisisons related to the same CCR with similar status and dates | Send workaround to users | RegOps | Edouard/Maria | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 | 2014-02-28 |  | Run 2 reports (see workaround) | Completed | / |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
87 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | Wrong selection of the report (as the VFU report has been duplicated to ease the use (1 for IO, 1 for Regions).and the previous report was still existing) | Suppress the wrong BO reports | RegOps/IS | Edouard/Maria | 2014-02-28 | 2014-02-28 | 9 | 2014-02-28 | 9 | 2014-02-28 |  |  | Completed | /
88 |  | 1 | R | R2_Variation_Follow_up_Report | The PBRER report is not always correct | “License status Date” is in French and not in English | Commuicate the settings of BO | RegOps | Edouard/Maria | 2014-03-15 | 2014-03-15 | 11 | 2014-03-15 | 11 | 2014-03-15 | 2014-04-14 |  | Completed
89 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | In CP, the data exist in the report only for European Union (and not all countries) |  |  | Edouard/Maria | 2014-03-20 | 2014-03-20 | 12 | 2014-03-30 | 14 | 2014-03-15 | 2014-04-14 | copy the information from EU | Completed
90 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | The report take the date of the country schedule instead of the current status indicated in the country tab | bug under resolution |  | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 | 2014-03-20 | 12 | 2014-03-15 | 2014-04-14 |  | Completed
91 | Compliance | 1 | D | R2_Variation_Follow_up_Report | The Variation Follow up report Displays without CCR or event information | Might be due to data quality (no package set ?) for some countries (low level in eTrac) | Manual data entry | RegOps / IS | Edouard/Maria | 2014-06-30 | 2014-06-30 | 27 | 2014-03-30 | 14 |  |  |  | Completed
92 | Compliance ??? | ? | R | R2_Variation_Follow_up_Report | Ensure Robstness of Variation Follow-up report | Development use a theoretical order for the Event status, which might not be true in real life User can change the busines entity | - Event status order might bring wrong output : The status “suspensive question” for example is a status that could happened anytime.Same for the status “No submission required” . The report takes the last date of the « country Schedules » instead of the current status indicated under the tab « Country » - Naming Convention : the new applications are not displayed when there is no RegSet#. Priority : High - The VFU report create a partial Result for Hexaxim (352) - Withdrawn licenses displayed with a “/” in case of Approved MRP (medium priority - Action will be finalized even if this correction is not done) - Filter on business entity(sanofi Pasteur) which can change, and not on product type : remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority - Action will be finalized even if this correction is not done) | RegOps / IS | Edouard/Maria/Moncef | 2014-04-30 | 2014-04-30 | 18 | [5 empty] | On-going
93 | Compliance | 1 | R | R2_Variation_Follow_up_Report | The Variation Follow up report is not always correct | 314 India (MigMis3626)- CCR V2051 - The report display « No submission required » on 06.08.2006 instead of “submitted” on 18.12.2012 | Check if we have the same issue in other reports | RegOps | Edouard/Maria | 2014-03-20 | 2014-03-20 | 12 | 2014-03-20 | 12 | 2014-03-30 | 2014-04-29 |  | Completed
94 |  | ? | R | R2_Variation_Follow_up_Report | Variation Follow up region report is not correct | Need to display Approved registrations OR (and not AND) Applications with a status « planned, submitted or approved » | - 'Need to modify prompts (replace a AND by a OR) - same correction than for the variation Follow-up for Batch release - Remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority - Action will be finalized even if this correction is not done) | RegOps / IS | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 | [5 empty] | On-going
95 | Compliance ??? | 1 | R | R3_Article_46_Report | Improve Article 46 report | Adjust Report | - Add Croatia in the list of countries by default - Suppresse SPMSD countries ? - Add the registration status (or filter or approved registrations ?) -remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority) | RegOps / IS | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-06-30 | 2014-07-30 | Possible to easily add Croatia in the request | On-going
96 |  | 3 | T | T2 -etrac/RA cockpit | Intranet is not up-todate | eTrac documentation is still present | Update intranet to remove eTRAC and RACockpit |  | Jeremy/Moncef |  |  |  | 2014-03-15 | 11 | 2014-03-31 | 2014-06-29 |  | Completed |  | Communication | Paul | Communication | Update intranet to remove eTRAC and RACockpit | no | no |  |  | Maria |  | Planned
97 |  | 3 | D | D_Interface SHARE/OPX2 | Double data entry | Interface from SHARE to OPX3 | Interface SHARE -> OPX2 and SHARE -> SBS : know the list of fields used for this interface for QC |  | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-04-30 | 2014-07-29 |  | Planned |  | Interface | Jeremy | Interface SHARE -> OPX2 | Interface SHARE -> OPX2 : Test, deployment (TBC) | yes | no | E. Donato | A.Sarcelle | Jeremy | C. Chabert | on-going | IS
98 |  | 2 | M | M1a_Missing_data | Art 58 not yet migrated (2 applications) | Art 58 not yet migrated (2 applications) | Manual data entry, after redefining process nd regeneration of PIF (Priority 1 of manual data entry) | RegOps | Denis/Jeremy | 2014-04-16 | 2014-04-16 | 16 |  |  | 2014-03-15 | 2014-04-14 |  | Planned | not directly linked to the PBRER --> Prio 2 | Migration (manual /correction) | Denis | Manual Data Entry Follow up with IS support |  | yes | no | Remy, Soufiene, Julien | Christophe | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine | on-going | IS
99 |  | 1 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) : Bulks | Bulks | Manual data entry, after redefining process nd regeneration of PIF (Priority 1 of manual data entry) | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
100 |  | 2 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) : PIP | PIP | Manual data entry, after redefining process nd regeneration of PIF | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
101 |  | 2 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) : PMF1 | PMF1 | Manual data entry, after redefining process nd regeneration of PIF | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
102 |  | 2 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) : PMF2 | PMF2 | Manual data entry, after redefining process nd regeneration of PIF | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
103 |  | 2 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) : registrations with pre-licensure status | registrations with pre-licensure status | Manual data entry, after redefining process nd regeneration of PIF | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
104 |  | 1 | M | M1a_Missing_data | All data not migrated (not linked to compliance reports) | Data entry of 247 non-migrated events only (PMF 2nd step, article 46) | Manual data entry, after redefining process nd regeneration of PIF | Umanis trainee | Denis | 2014-06-15 | 2014-06-15 | 25 | [5 empty] | Planned |  |  | Denis | [6 empty] | Denis | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine
105 |  | 3 | M | M1b_Missing_data | All data not migrated (not linked to compliance reports) |  | For automatic Data Update: eDoc Link (link generation, URL integrity) : Links with RAeDoc have not been migrated (the RA number has been kept). Ensure that old links are available, and that new links will work properly with RAeDoc and its évolutions : with US IS, check the feasibility for robust solution and define an action plan |  | Christophe / Rishi | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-06-30 | 2014-09-28 |  | Planned |  | Migration | Jeremy | SHARE Change Control follow up | For automatic Data Update: eDoc Link (link generation, URL integrity) : Links with RAeDoc have not been migrated (the RA number has been kept). Ensure that old links are available, and that new links will work properly with RAeDoc and its évolutions | yes | no | E. Donato | C. Chabert | Jeremy | IS NA SHARE Team + GAP ETL | Planned | IS
106 |  | 2 | M | M1_Missing_data | All data not migrated (not linked to compliance reports) : CTA/IND extracts | Migration decision | CTA/IND extracts, post in RAeDoc, track the RAeDoc number in the reference "migration". |  | Denis/Jeremy | 2014-05-29 | 2014-05-29 | 22 |  |  | 2014-03-30 | 2014-05-29 |  | Planned |  | Migration | Jeremy | CTA/IND Extract | CTA/IND extracts, post in RAeDoc, track the RAeDoc number in the reference "migration". | yes | no |  | C. Chabert | Jeremy | Wayne | To be planned | Biz
107 |  | 2 | M | M1_Missing_data | All data not migrated : Canadian products prelicensure (contact with MDM) | Migration decision | Canadian products prelicensure (contact with MDM) |  | Denis/Jeremy | 2014-05-29 | 2014-05-29 | 22 |  |  | 2014-03-30 | 2014-05-29 |  | Planned |  | Migration (manual /correction) | Denis | Manual Data Entry Follow up without IS support | Canadian products prelicensure (contact with MDM) | no | no |  |  | Jeremy | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine | To be planned
108 |  | 2 | M | M1_Missing_data | All data not migrated : Master Files (BMF, DMF) : Mainly in US | Migration decision | Master Files (BMF, DMF) : Mainly in US |  | Denis/Jeremy | 2014-05-30 | 2014-05-30 | 22 |  |  | 2014-03-31 | 2014-05-30 |  | Planned |  | Migration (manual /correction) | Denis | Manual Data Entry Follow up without IS support | Master Files (BMF, DMF) : Mainly in US | no | no |  |  | Maria | Umanis resources, Stephanie, Véronique, Wayne, Laurent, Claudine | To be planned
109 |  | 1 | R | R6_Track_back_report | Track-back report | Track back report is not available | Finalise and roll-out the Track back report (provide "partial results") • The current version in dev environment does not run because the Event information came from the Events folder. The event info needs to come from the Events-Registration folder or the Events-Application folder. For our case, it MUST come Events-Application folder (explanation below). • Raghu started a version that includes the events associated at the Registration level. This did not give us the results of all open events. The reason it did not is because no other events had a PDS association, except for the “PDS Pasteur Migration” event. • Because the event info was not linked to the registration, we had to include the event info from the Events Application folder instead. • it would be easier to extract all the fields needed then use a macro to organize the data by application (all events, references and sequences as related to one application) • The data for each application in each country will have a mix of data coming from the event level at the application, plus data found at the registration level (Raghu, let me know if you think the associations I propose in red, are appropriate). See tab “Fields needed for TrkBk” • After we are able to confirm the data extracts properly, we need to develop and apply a macro ( see tab “Data after macro applied’) -remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority - action can be closed even if not done) | RegOps / IS | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-15 | 2014-04-14 |  | On-going
110 |  | 3 | P | P1_Process | SHANTA data not available in SHARE | Not yet in the scope | Integration of SHANTA products in SHARE email has been sent to propose a pre-study to see if the current process & responsibilities in SHARE could apply to SHANTA and to ask a name of contact to work with for this pre-study.-> Décided to postpone it | RegOps / IS | Stephanie/Denis | 2014-04-03 | 2014-04-03 | 14 | 2014-04-03 | 14 | 2015-06-30 | 2015-09-28 |  | completed |  | Process & Procedure | Paul | SHANTA | Integration of SHANTA products in SHARE email has been sent to propose a pre-study to see if the current process & responsibilities in SHARE could apply to SHANTA and to ask a name of contact to work with for this pre-study.-> Décided to postpone it | no | no |  |  |  |  | Planned
111 |  | 2 | T | T1_Inteface SHARE/MDM | Risk of mismatch between MCM country category in the procedure and the one used in the VFU reoport | The values are set in the report by itsef (no interface from MDM) | Define process to update the MCM country category list |  | Véronique | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-04-30 | 2014-05-30 |  | Planned | This info is key in the VFU ! --> prio 1 + a due date | Process & Procedure | Paul | VFU | Define process to update the MCM country category list | no | no |  |  | Véronique |  | Planned
112 |  | 2 | T | T1_Inteface SHARE/MDM | Risk of mismatch between Areas / subareas Pasteur and the MDM | The values are set in the report by itsef (no interface from MDM) | Define the process to update the area/subarea Pasteur |  | Maria | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-04-30 | 2014-05-30 |  | Planned | if no date it should be a prio 2 or 3 | Process & Procedure | Paul | geography | Define the process to update the area/subarea Pasteur (excel file given to IS) | no | no |  |  | Véronique |  | Planned
113 |  | 2 | D | D5_Coherence_with_Sanofi | Some fields definition are not very clear : To be clarified : does Sanofi doc exist? |  | Define each field of SHARE (first step: mandatory fields) Check with T.Heuvelmans what is already available.(QDS-7234) Communicate the definitions to all users | RegOps | Marion / Karina | 2014-12-31 | 2014-12-31 | 53 |  |  | 2014-06-30 | 2014-08-29 |  | Planned |  | Process & Procedure | Paul | Definition of fields | -Define each field of SHARE (first step: mandatory fields) -Check with T.Heuvelmans what is already available.(QDS-007234) - Communicate the definitions to all users | no | yes |  |  | Karina |  | Planned
114 | Compliance | 1 | R | R8_PVSMF_report | PVSMF | Improve the report | - Ivory Coast / Cote d'Ivoire not retrieved (due to EU.Not EU ?) - Need to replace the Local Trade Name by the SMPC Name for this report - Application country instead of registration country -remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (priority low - Action can be set as completeted even if this is not done) + when Marketing status will be OK : add the marketing status, marketing status date and marketing cessetion date Due DAte : April 30. Then Dec 31 (when common report with Sanofi) | RegOps / IS | Edouard/Maria | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-12-31 | 2015-03-01 |  | On-going | /
|  | 1 | R | R8_PVSMF_report |  | Report not correct for the next PSMF version due to April11 | PVSMF specifications review (line added by Marion) |  | Marion | 2014-04-14 | 2014-04-14 | 16 | 2014-04-14 | 16 |  |  |  | completed | [13 empty] | Meeting organized with1, PV (D.Gaillard) then with Ragu, Maria and Edouard on April 14th
115 |  | 1 | D | D4_QC_Catalogue | No consistency of Pasteur mandatory fieldsvs Pharma |  | identity Sanofi Pasteur mandatory fields and update Pharma documentation Some fields are not listed in the Sanofi List of mandatory fields all SHARE fields will be reviewed and analyzed in order to re-confirm, simplify and realign Pasteur critical fields=> SP list of mandatory fields is apt to change. AWARNESS : please update also 'Task Status' to 'Task Status Date', 'Licence Status Date' to 'Registration Status Date' , 'Licence Status' to 'Registration Status' and Projec Type to Project Type | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-09-30 | 2014-11-29 |  | On-going |  | QC Check | Karina | Data Completeness | Check the consistency of Pasteur mandatory field vs Pharma (do we have the same definition ?) | no | yes |  |  | Karina |  | Planned
116 |  | 3 | D | D_missing data | RPM names are not up-to-date | Moving organization, no process to update them | RPM name: remove the information (or ask Sanofi to hide the filed if not used by Sanofi) Check if others fields could be removed from SHARE ? |  | Karina | 2014-12-31 | 2014-12-31 | 53 |  |  | 2014-10-01 | 2014-12-30 |  | Planned |  | QC Check | Karina | Data Accuracy | RPM name: do we keep it ? How do we maintain it in SHARE (reg ops process)? Check if others fields could be removed from SHARE ? | no | no |  |  |  |  | Planned
117 |  | 2 | R | R9_Metrics | Not possible to provide metrics to management |  | RA & CMO Dashboard - Define if the need are different from what is done today (Pasteur or group ?), with Isabelle Marbach - Discuss with Xavier Launois (with Isabelle Marbach) - specifications, develop and test | RegOps / IS | Stéphanie | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-31 | 2014-05-30 |  | On-going |  | Reports & Metrics | Maria | Metrics | RA & CMO Dashboard (For End February) - Define if the need are different from what is done today (Pasteur or group ?), with Isabelle Marbach - Discuss with Xavier Launois (with Isabelle Marbach) - specifications, develop and test | yes | yes |  | S. Fraissard | Stéphanie | Sylvie, Isabelle | on-going | IS
118 |  | 2 | R | R9_Metrics | More complexe to follow Umanis workload |  | Metrics for the Transversal team | RegOps / IS | Stephanie | 2014-09-01 | 2014-09-01 | 36 |  |  | 2014-03-31 | 2014-05-30 |  | On-going |  | Reports & Metrics | Maria | Metrics | Metrics for the Transversal team (For January) - Kick-off January 7 | yes | no |  | C. Chabert | Stéphanie |  | on-going | IS
|  | 1 | R | R9_Metrics | Need to provide new registrations to PV |  | what do we do? Necessary not to miss PBRERS submissions in new countries (line added by Marion)
119 |  | 1 | T | T1_Inteface SHARE/MDM | The Variation Follow up report is not always correct | Korea and EU MCM country category not correct | Update the MCM country category list into MDM (Reg Ops by Feb 14) | RegOps | Jeremy/Moncef | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-02-17 |  |  | Completed | If this is linked to SHARE structure and not to the reports, then appropriate training + the list of countries listed in the footer of the report for CP could avoid an enhancement of the report with associated possible regressions --> Prio 2
120 |  | 1 | T | T1_Inteface SHARE/MDM | The Variation Follow up report is not always correct |  | Update the MCM country category list into MDM (Reg Ops by Feb 14) | RegOps | Jeremy/Moncef | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-02-17 |  |  | Completed | /
121 |  | 2 | R | R12_All_registrations_Report | Report "all applications for 1 product" is difficult to be used | The "country" is missing | Update the report |  | Edouard/Maria | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-03-15 | 2014-05-14 |  | Completed |  | Reports & Metrics | Maria | New reports | Define and develop a new report with the users : list of all applications for one product | yes | yes | Sandrine, Jean Michel | S. Fraissard | Maria |  | on-going | IS
122 |  | 2 | R | R13_All_MAA_Report | Report "MAA submitted and/or dispatched for a given country" is not easy to use | Issue with withdrawal dates | Update the report |  | Edouard/Maria | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-15 | 2014-05-14 |  | On-going |  | Reports & Metrics | Maria | New reports | Define and develop a new report with the users : list of MAA submitted and/or dispatched for a given country | yes | yes | Sandrine, Jean Michel | S. Fraissard | Maria |  | on-going | IS
123 |  | 2 | T | T8_New_Reports | No way to extract data to feed EVMPD process | No report available | Define and develop a new report with the users Changes and fileds required for xEVMPD |  | Véronique / Karina / stéphanie | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | Reports & Metrics | Maria | New reports | Define and develop a new report with the users Changes and fileds required for xEVMPD | yes | yes |  |  | Véronique | IS NA SHARE Team | Planned | Biz
124 | To be kept ??? | 3 | R | R11_Art23_report | Duplicate data entry for Article 23 | No report available | Define and develop a new report with the users : Article 23 : not possible because there are no possible filters |  | Edouard/Maria | 2014-12-31 | 2014-12-31 | 53 |  |  | 2014-03-30 | 2014-04-29 |  | Cancelled |  | Reports & Metrics | Maria | New reports | Define and develop a new report with the users : Article 23 | yes | yes | Sandrine, Jean Michel | S. Fraissard | Maria | Andrea | Planned | Biz
125 |  | 1 | T | T1_Inteface SHARE/MDM | Incomplete List of applications in RAVL | Interface SHARE-MDM | Ensure all issues are solved | RegOps/IS | Edouard / veronique | 2014-05-31 | 2014-05-31 | 22 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | Interface | Jeremy | Interface SHARE -> MDM | Finalise Interface SHARE -> MDM : cf mail Evelyne Donato in Comment | yes | no | E. Donato | Oliver | Jeremy | Véronique | on-going | IS
126 |  | 3 | U | U1_User support | Difficult to use reports | Not easy to now which report to use when | Small support on main reports (Quick reference guide) |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 |  |  | 2014-03-30 | 2014-06-28 |  | On-going |  | Reports & Metrics | Maria | user guide | Small support on main reports (Quick reference guide) | no | yes |  |  | Maria |  | Planned |  | Slides gathered by SM, under review
127 |  | 3 | R | R15_RPU Reports | Double data entry : RPU should be re-entered | RPU should be re-entered | Align the RPU report to simplify the data entry |  | Maria | 2014-09-28 | 2014-09-28 | 40 |  |  | 2014-06-30 | 2014-09-28 |  | Planned |  | Process & Procedure | Paul | RPU | Align the RPU report to simplify the data entry | no | no |  |  | Paul | Céline Rigaudeau | Planned | Paul
128 |  | 2 | U | U1_User support | Incorect use of the system | Need more training | Booster sessions : Viewers |  | Stephanie/Denis | 2014-03-27 | 2014-03-27 | 13 | 2014-02-18 | 8 | 2014-02-25 | 2014-03-27 |  | completed |  | Training | Denis | Booster sessions | Booster sessions : Viewers | no | no |  |  | Denis | M.Kafi / S.Melot / M.Sansaet / J.Kane | Completed | Denis
129 |  | 2 | U | U1_User support | Incorect use of the system | Need more training | Booster sessions : Writers HQ |  | Stephanie/Denis | 2014-03-27 | 2014-03-27 | 13 | 2014-02-18 | 8 | 2014-02-25 | 2014-03-27 |  | completed |  | Training | Denis | Booster sessions | Booster sessions : Writers HQ | no | no |  |  | Denis | S.Melot / M.Sansaet / J.Kane / Moncef | Completed | Denis
130 |  | 2 | U | U1_User support | Incorect use of the system | Need more training | Booster sessions : Writers + Viewers Affiliates |  | Stephanie/Denis | 2014-03-27 | 2014-03-27 | 13 | 2014-02-27 | 9 | 2014-02-25 | 2014-03-27 |  | completed |  | Training | Denis | Booster sessions | Booster sessions : Writers + Viewers Affiliates | no | no |  |  | Denis | S.Melot / M.Sansaet / J.Kane / Moncef | Completed | Denis
131 |  | 2 | M | Migration | Migration not finalized | Need ro review some processes | User Guide light to finalize and publish. Pre-requisit for manual migration. + communicate to users |  | Denis/Jeremy | 2014-05-14 | 2014-05-14 | 20 |  |  | 2014-03-15 | 2014-05-14 |  | on-going |  | Training | Denis | User Guide | User Guide light to finalize and publish (jan to march). Pre-requisit for manual migration | no | no |  |  | Denis |  | on-going
132 |  | 2 | D | D6_Data_entry_conventions | Inconsisent naming convention - Inconsistences between documents Inconsisent naming convention- When the user doesn’t follow the naming convention when he/she populates the Application code/number field, the Application Code is not retrieved in Reports |  | Review naming conventions to take into account FS-DM (migration rules) : need to decide migration rules or Sanofi rules | RegOps | Marion / Karina/Denis | 2014-06-29 | 2014-06-29 | 27 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  | Training | Denis | User Guide | Review naming conventions to take into account FS-DM (migration rules) | no | yes |  |  | Denis | Karina | Planned |  | 2014/02/12 KN: Delivrables are to clarify --> cf. EM email (2014/01/29) - the reference document for naming convention is the one signed with Sanofi
133 |  | 2 | D | D11_Data_entry_conventions | Inconsistences between documents | Inconsisent naming convention | documentation update |  | Denis/Karina | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  | Training | Denis | User Guide | Review naming conventions to take into account FS-DM (migration rules) + new/best practices | no | yes |  |  | Denis | Karina | Planned |  | 2014/02/12 KN: Delivrables are to clarify --> cf. EM email (2014/01/29) - the reference document for naming convention is the one signed with Sanofi
134 |  | 2 | D | D4_QC_Catalogue | Inconsisent naming convention |  | commun QC reports with Sanofi OR use of the Queries management process - naming convention | RegOps | Marion / Karina | 2014-12-30 | 2014-12-30 | 53 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  | Training | Denis | User Guide | Review naming conventions to take into account FS-DM (migration rules) | no | yes |  |  | Denis | Karina | Planned |  | 2014/02/12 KN: Delivrables are to clarify --> cf. EM email (2014/01/29) - the reference document for naming convention is the one signed with Sanofi
135 |  | 3 | U | U1_User support | No use of the "Notifications" | No use of the "Notifications" | Notification with SHARE. Draft exists, Not validated |  | Stephanie/Denis | 2014-05-15 | 2014-05-15 | 20 |  |  | 2014-04-30 | 2014-07-29 |  | Planned |  | Training | Denis | User Guide | Notification with SHARE. Draft exists, Not validated | no | yes |  |  | Denis | Moncef | on-going
136 |  | 3 | U | U1_User support | However, the only rule we provide in training supports for Application Code is MAA-Product Code-NAT. | No use of the "Notifications" | Notification for affiliates, L/F, Regions |  | Stephanie/Denis | 2014-05-15 | 2014-05-15 | 20 |  |  | 2014-04-30 | 2014-07-29 |  | Planned |  | Training | Denis | Training | Notification for affiliates, L/F, Regions | no | yes |  |  | Denis | Moncef | on-going
137 |  | 1 | T | T2 -etrac/RA cockpit |  | eTrac procedures still available | Cancel eTrac procedures | RegOps | Maria |  |  |  | 2014-03-07 | 10 | 2014-03-31 | 2014-04-30 |  | Completed |  | Process & Procedure | Paul | Cancel | All eTRAC procedures to cancel from QDoc | no | no |  |  | Claudine |  | Planned
138 |  | 2 | U | U1_User support | When the Application code/number field do not contain (<Reg Set Number>) the Application Code is not retrieved (please see my email on 7th march regarding the VFU testing results): | Training guides are not used | Make sure that the training guides are used (could be done through a survey) |  | Stephanie/Denis | 2014-06-29 | 2014-06-29 | 27 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  | Training | Denis | Training | Make sure that the training guides are used (could be done through a survey) | no | no |  |  | Denis |  | Planned
139 |  | 3 | U | U1_User support | Incorrect use of the system | risk of missing trainer | Transfer training to future contractors (if needed) |  | Stephanie/Denis | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-04-15 | 2014-10-31 |  | Planned |  | Training | Denis | Training | Transfer training to future contractors | no | no |  |  | Denis | Moncef | Planned | Denis
140 |  | 2 | U | U1_User support | Incorrect use of the system | user guides not updated | Update of the User Guides |  | Stephanie/Denis | 2014-06-27 | 2014-06-27 | 26 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  | Training | Denis | Training | Update of the User Guides | no | yes |  |  | Denis | Moncef | Planned | Denis
141 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support on reports (when in English) |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Queries & Reports | User support on reports (when in English) | no | no |  |  | Maria | Stéphanie | on-going
142 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support on reports (when in French) |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Queries & Reports | User support on reports (when in French) | no | no |  |  | Stéphanie |  | on-going
143 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support on Access request & training |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Access requests & training | User support on Access request & training | no | yes |  |  | Denis |  | on-going
144 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support on Dictionary |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Dictionary | User support on Dictionary | no | yes |  |  | Jeremy | Stéphanie | on-going
145 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support for Americas (North and South) |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Data entry | User support for Americas (North and South) | no | no |  |  | Jeremy | Maria | on-going
146 |  | 2 | U | U1_User support | Number of issues in the Q&A database | User support to be reorganized | User support for Europe & Asia, Africa, transversal team |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | 2014-04-14 | 16 | 2014-03-15 | 2014-05-14 |  | Completed |  | User Support | Stéphanie | Data entry | User support for Europe & Asia, Africa, transversal team | no | no |  |  | Stéphanie | Moncef, Denis | on-going
147 |  | 2 | P | P1_Process | The pds is not up-to-date | Pds medium not clear | PDS : the "medium" level in eTrac has been migrated to High or" low". Define the status (maybe with the relashionshp with MCM country category). Communication between high & low |  | Jeremy/Moncef | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-04-30 | 2014-06-29 |  | Planned |  |  |  | PDS | PDS : the "medium" level in eTrac has been migrated to High or" low". Define the status (maybe with the relashionshp with MCM country category). Communication between high & low
148 |  | 2 | T | T6_SHARE_evolutions | The pds is not up-to-date | inconsistencies between pds for the same product | Create a PDS templates for each product familly (clean, to be reuse for new registration and avoid bad data entry (for High and low) |  | Jeremy/Moncef | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  |  |  | PDS | Create a PDS templates for each product familly (clean, to be reuse for new registration and avoid bad data entry (for High and low)
149 |  | 2 | D | D4_QC_Catalogue | Data quality of newly entered information - PDS : sometime not the good data, sometime not complete (not a migration issue, issue in eTrac) | The pds is not up-to-date | commun QC reports with Sanofi OR use of the Queries management process : QC proposal ; compare the pds and the pds template and check that the info are the same. |  | Marion/Karina | 2014-11-30 | 2014-11-30 | 49 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | QC | Karina | PDS | PDS : sometime not the good data, sometime not complete (not a migration issue, issue in eTrac) : QC proposal ; compare the pds and the pds template and check that the info are the same. |  |  |  |  | Karina | Moncef, Denis
150 |  | 2 | p | P_roles_and_responsibilities | R&R not fully clear to use the system |  | Process and user guide to clarifty (multi products, multi procedure type, …). Relations between RPMs and Transversal team. Update training accordingly. Disconet SHARE roles and RA organization. Tools & Processes? |  | Franck | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | Process & Procedure | Paul | GPP creation | Process and user guide to clarifty (multi products, multi procedure type, …). Relations between RPMs and Transversal team New version of the R&R sop? | no | yes |  |  | Paul | Denis | To be planned | Paul
151 |  | 2 | p | P1_Process | R&R not fully clear to use the system | No full buy-in by affiliates | Many affiliates do not seem interested during booster sessions : some issues already seen : they put a date, but not more. they do not track the license number of initial application, submission status are ignored, change of local trade name during during a renewal not set, Action ???? stop local data entry ??? Update training accordingly. Disconet SHARE roles and RA organization. Tools & Processes? |  | Franck | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | Process & Procedure | Paul | Affiliates | Many affiliates do not seem interested during booster sessions : some issues already seen : they put a date, but not more. they do not track the license number of initial application, submission status are ignored, change of local trade name during during a renewal not set, Action ???? stop local data entry ??? | no | yes |  |  | Paul | Denis | To be planned | Paul
152 |  | 2 | p | P1_Process | R&R not fully clear to use the system | Process fro comitments not clear enough / please see the existing Sop Q_000543 | Clarify process for the tasks : who track the commitments, when, (between affiliates or transversal team) ? (affiliates are not trained to track the tasks and it seems difficult to do so. Update training accordingly. Disconet SHARE roles and RA organization.Cf SOP (or update it) |  | Franck | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | Process & Procedure |  | tasks | Clarify process for the tasks : who track the commitments, when, (between affiliates or transversal team) ? (affilaites are not trained to track the tasks and it seems difficult to do so. | [5 empty] | Denis
153 |  | 2 | P | P1_Process | R&R not fully clear to use the system | Need to clarify Roles and responsiblitities between L/F, regions, affiliates, Transversal team. | Clarify Roles and responsiblitities between L/F, regions, affiliates, Transversal team. Update training accordingly. Disconet SHARE roles and RA organization. Tools & Processes? |  | Franck | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-05-30 | 2014-07-29 |  | Planned |  | Process & Procedure | Paul | Roles and responsibilities | Clarify Roles and responsiblitities between L/F, regions, affiliates, Transversal team. Refer to actions D7_Training - User support | no | yes |  |  | Paul | Denis | To be planned | Paul
154 |  | 2 | P | P1_Process | R&R not fully clear to use the system | Management of the events multi CCR not well defined | Define process to manage events with multiple CCRs : use of GPP ? (with risk to have wrong data entry by the affiliates), 1 event with multiple CCRD ? Update training accordingly. Disconet SHARE roles and RA organization. Tools & Processes? |  | Franck | 2014-10-31 | 2014-10-31 | 44 |  |  | 2014-04-30 | 2014-06-29 |  | on-going |  | Process & Procedure | Paul | Roles and responsibilities | Define R&R GPP | no | yes |  |  | Paul | Franck/Céline Rigaudeau/Denis | on-going | Paul
155 |  | 3 | T | T3_Interface SHARE/OPX2 | Approval dates not always updated in OPX2 | CMO PPO report (actaul dates) not available (before interface to OPX2 | Define and implement CMO PPO report : check that the Variation follow-up meets the need of CMO PPO |  | Edouard | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-15 | 2014-04-14 |  | On-going |  | Reports & Metrics | Maria | BO Pasteur Customed Reports | Remaining Reports Product full information (on-going), Variation track back reports (Magali Chevrot will help for the specifications), CMO PPO reports (actual dates). For End January | yes | no | S. Fraissard | S. Fraissard | Maria | GAP BI, Magali Chevrot | on-going | IS
156 |  | 1 | T | T5_Admin_Doc | Procedure not up to date (inspection readiness) | Prevent feedback from inspector | Check that we have in the procedure : Report from IS and deactivation of users that have no logged in the last six month + The list of users should be corrected and the access should be blocked for any individuals no longer working for the company |  | Jeremy/Moncef with US IS | 2014-06-30 | 2014-06-30 | 27 |  |  | 2014-03-31 | 2014-04-30 |  | On-going |  | Process & Procedure | Paul | deactivation | Check that we have in the procedure : Report from IS and deactivation of users that have no logged in the last six month + The list of users should be corrected and the access should be blocked for any individuals no longer working for the company | yes | yes |  |  | Paul | IS NA SHARE Team | Planned | Biz
157 |  | 1 | T | T6_SHARE_evolutions | The Variation Follow up report is not always correct | Action type is set with a / (as this field did not exist in eTrac) | Will be available with the new data in SHARE |  | Jeremy/Moncef | 2014-03-07 | 2014-03-07 | 10 | 2014-03-07 | 10 | 2014-02-28 |  | Ignore the issue | completed | /
158 |  | 2 | U | Users support | Incorrect use of the system |  | Update user guide with the corrective action proposed above on application status (Corrective action (proposed by Jeremy and Antoine) is to utilize 'reference" to store pre-licensure events) |  | Stephanie/Denis | 2014-04-29 | 2014-04-29 | 18 | [5 empty] | On-going |  | Training | Jeremy | Training | Update User Guides | no | no |  |  | Jeremy | Denis | on-going | Denis | Minutes from meeting expected from Jeremy
159 |  | 1 | T | T7_BO_universe | The Variation Follow up report is not always correct | 314 India (MigMis3626)- CCR V2051 - The report display « No submission required » on 06.08.2006 instead of “submitted” on 18.12.2012 | Bug under resolution : the BO universe does not load the current date. This mean that the report takes the last date of the « country Schedules » instead of the current status indicated under the tab « Country » | Report team | Edouard | 2014-04-30 | 2014-04-30 | 18 |  |  | 2014-03-15 | 2014-04-14 |  | Cancelled
160 |  | 1 | T | T8_New_Reports | The Variation Follow up report is not always correct | Need to create several VFU if we have too many product impacted | Long term :It will be updated (by the US team) this year but it will reduce the performance | Report team | Jeremy/Moncef |  |  |  | 2014-03-07 | 10 | 2014-12-31 | 2015-01-30 |  | Completed
161 |  | 1 | U | Keep this action | Resource bottleneck |  | From April 18, after QCI assessment, Munish audit and PV mock up inspection, ask for additional resources if required | Franck | Franck | 2014-04-30 | 2014-04-30 | 18 | [5 empty] | On-going
162 |  | 2 | R | R_14_SPMSD _Report | Improve SPMSD report | Add information | - add the registration status (aftre the license number) and suppress the application status = approved by default in the prompt (as we have some issues with the application status) + add the procedure type and event country (concatenated if needed in one cell) ?(check if this is necessary. Need to update the communication -remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority) |  | Edouard/Maria | 2014-05-31 | 2014-05-31 | 22 | [5 empty] | On-going
163 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (events country status/ reference - registrtation status and registration status date ) The reference status may be wrong when there was several approved status (ex. 299 Israel - Approved/Licensed - 15-Aug-2007¦Expired - 01-Jan-1999¦Approved/Licensed - 15-Oct-1985¦Submitted - 03-Sep-1984 ) Registration status is approved but the registration status date is the date of abandon |  | QC | RegOps | Marion / Karina | 2014-12-30 | 2014-12-30 | 53 | [5 empty] | Planned
164 |  | 1 | D | D3_Data_correction | Inconsistent data (events country status/ reference - registrtation status) wrong Registration status for 299 Israel - 128 78 23830 00 (August 15. 2007) |  | Data cprrection | RegOps | Marion / Karina | 2014-03-14 | 2014-03-14 | 11 | 2014-03-24 | 13 |  |  |  | Completed
165 |  | 1 | D | D4_QC_Catalogue | Inconsistent data (Application approved or withdrawn with no registration ) Approved / withdrawn application do not have registraion |  | QC Cancelled for QC to be updated Data consistency_Application_registration_PDS statuses (this Report will replace the “Approved Application with no registration” Report) 5 registration # not migrated to SHARE because there is no approval date in register (applications have been migrated with approved or withdrawn status) --> action ? | RegOps | Marion / Karina | 2014-04-30 | 2014-04-30 | 18 | 2014-03-31 | 14 |  |  |  | Completed |  |  |  |  | 29 approved or withdrawn application with no registration o 2 not relevant cases  Market Authorisation Application - 314 Ad - NAT - VEN (MIGMIS3636) – withdrawn - no registration (reason = The pediatric presentation was eventually registered as an extension of the existing flu registration and not as a separate registration)  Market Authorisation Application - 253 - NAT - KOR (Reg-1995) withdrawn - no registration (reason = 'Submission withdrawn before registration')
166 |  | 1 | D | D3_Data_correction | Inconsistent data (Application approved or withdrawn with no registration ) Approved / withdrawn application do not have registraion |  | Data cprrection | RegOps | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going
167 |  | 1 | D | D3_Data_correction | 314 – V2542 - Application code/number is not retrieved in VFU report for Hong Kong licences because of naming convention not followed |  | Data cprrection | Sam Ching | Marion / Karina | 2014-04-15 | 2014-04-15 | 16 | 2014-03-27 | 13 |  |  |  | Completed
168 |  | 2 | U | GPP | R&R around creation of GPP are not clear |  | Build and communicate a training kit based on the sldie deck developpe by Célien (UMANIS). This slide deck has already been shared with french associates from Franchise on March 21 |  | Stephanie/Denis | 2014-04-25 | 2014-04-25 | 17 | [5 empty] | On-going | [13 empty] | To be reviewed SM/DJ for April 18
169 |  | 1 | D | D4_QC_Catalogue | Missing data (Action Type, Change Type, CCR number) |  | QC Data completeness- Event Attributes | RegOps | Marion / Karina | 2014-04-01 | 2014-04-01 | 14 | 2014-03-31 | 14 |  |  |  | Completed
170 |  | 1 | D | D3_Data_correction | Missing data (Action Type, Change Type, CCR number) |  | data completion Events must be reopened by SHARE Admin Automated update needs to go thru a change control process (FS, UAT, ...) - 5-8 weeks | RegOps & Franchise/Regions/Share writers | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going
171 |  | 1 | D | D4_QC_Catalogue | Missing data ( Current Marketed Date, Marketing Cessation Date AND Currently Marketed in Country?) Marketing information is not filled in |  | QC Data completeness- Marketed Date One common Data system QC Report - QC completeness of data for PV mandatory fields based on the PSUR and PSMF Reports | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going
172 |  | 1 | D | D3_Data_correction | Missing data ( Current Marketed Date, Marketing Cessation Date AND Currently Marketed in Country?) Marketing information is not filled in |  | data completion | TBC | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going | [5 empty] | yes |  |  | Jeff
173 |  | 1 | D | D4_QC_Catalogue | Missing data - "Dose(s) per primar container" - "Country Trade name" -"Marketing Company" "SMPC name" |  | QC Data completeness_PDS Marketed Date One common Data system QC Report - QC completeness of data for PV mandatory fields based on the PSUR and PSMF Reports | RegOps | Marion / Karina | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going
174 |  | 1 | D | D3_Data_correction | Missing data - "Dose(s) per primar container" - "Country Trade name" -"Marketing Company" "SMPC name" |  | data completion | RegOps & Franchise/Regions/Share writers | Marion / Karina | 2014-07-30 | 2014-07-30 | 31 | [5 empty] | On-going
175 |  | 2 | R | R_15_All_registration_report | Imporve all registration report |  | - Supress duplicates -remplace business entity = Pasteur by Product type = Vaccine or Flu Vaccine (low priority) |  | Edouard/Maria | 2014-05-31 | 2014-05-31 | 22 | [5 empty] | On-going
176 |  | 2 | P | P_CTA_IND | CTA IND process does not answer user expectation |  | Redefine CTA/IND process (number of event for all clinical trials, amendment of CTA…) |  | Jeremy / Moncef | 2014-05-31 | 2014-05-31 | 22 | [5 empty] | On-going
177 |  | 2 | P | P_VHP | VHP process not implemented |  | Define a process for VHP |  | Denis | 2014-05-15 | 2014-05-15 | 20 | [5 empty] | On-going |  |  | Denis | [7 empty] | Maria
178 |  | 2 | P | P_roles_and_responsibilities | Valences : who enter the event for products multi valence from multi sites |  | Clarify process (R&R redinition finetuning). Preparation, RACC approval, documentation and communication |  | Jeremy / Moncef / Franck | 2014-06-30 | 2014-06-30 | 27 | [5 empty] | On-going
Formulas:
Week N° = IF(ISBLANK([ê])," ",WEEKNUM([ê]))
Lastest Deadline = [Earliest deadline]+30
Note on X77: Meeting January 28 : FS/DM to update – Sandrine (for new objectives 5&6) + Nathalie + Christophe to sign Change Control documentation + Test - Sandrine For 1) Update with RPM Name for all tasks in using Product family info Provide new list of tasks with Product Family (GAP) – Link Product – RPM + validate list + communication to Assignee – Karina/Denis For 4) CT Shared Data Extract validation – Jeremy – Define solution for automatic update Rishi/Sandrine For 5) Marketing Status : Define rules and prepare SRC tables for update – Karina / Evelyne/Sandrine/GAP Team For 6) Current application/Registration Date : Impact analysis (GAP to extract withdrawn appli + Dates + … ) – Nathalie/Sandrine-GAP - Define list of PBRER that has to be issued – Veronique – Manual Data entry idf needed – Veronique/Stéphanie - Define rules and prepare SRC tables for potential automatic update – Sandrine/Stéphanie/GAP Team New Date for Change control: End of February
Note on X89: Michoud, Edouard (sanofi pasteur): workaround has been found. Communication is planned week 6
Note on X102: For Article 58 and Bulks : – Data Entry Process definition – Denis- End of Next week – Update Transco files –Jeremy/Denis - End of Next week – Extract PIFs – GAP – Week February 10 – Start working on others Extract – GAP - Week February 10
Note on H110: For the approx 200 CTA/INDs : - Extract in BO or Racockpit all the CTA/INDs activities - Post the extracts in RAeDoc (location ready) - In Share, put the RAeDoc number in the event "migration" Related to the previous patch (if we want to have the link)
Note on X110: For the approx 200 CTA/INDs : - Extract in BO or Racockpit all the CTA/INDs activities - Post the extracts in RAeDoc (location ready) - In Share, put the RAeDoc number in the event "migration" Related to the previous patch (if we want to have the link)
Note on X131: Here below analysis of SHARE-MDM Initial Data Loading report: http://eroomfr.pasteur.aventis.com/eRoom/ISProjects7/SWRD090000-RDReferential/0_16c68 1/ Actions to be done in MDM R&D: - “Application not mapped” TAB: MDM R&D Application not mapped with a SHARE one - “NAT APP not mapped” TAB: MDM R&D National Application not mapped with a SHARE Application-Country - “PMP not mapped” TAB : MDM R&D PMP not mapped with a SHARE Registration Actions”.-Packageset Could you please complete the “Business Decision” column based on our “Proposed Action”. 2/ Actions to be done in SHARE: - “SHARE Actions Follow-up” TAB Could you please analyze and inform us of action that will be done in SHARE.
Note on H166: ????? What does it mean ?