## Status
PO | Trigram | VENDOR | Material | Nb Docs | Approved |  | To be reissued by VENDOR |  | In Review SAI |  | Not Received
836717 | SV01 | TECHNIP | FLEXIBLE JUMPERS | 184 | 3 | 1.63% | 40 | 21.74% | 58 | 31.52% | 83 | 45.11%
836720 | SV02 | TECHNIP | OIL OFFLOAFING LINES | 99 | 0 | 0% | 12 | 12.12% | 13 | 13.13% | 74 | 74.75%
856251 | SV03 | VALLOUREC | CS LINEPIPES | 41 | 16 | 39.02% | 10 | 24.39% | 10 | 24.39% | 5 | 12.2%
883892 | SV04 | DAEWOO | STRUCTURAL STEEL | 17 | 0 | 0% | 12 | 70.59% | 0 | 0% | 5 | 29.41%
884754 | SV05 | ARCELOR | STRUCTURAL STEEL | 21 | 0 | 0% | 0 | 0% | 18 | 85.71% | 3 | 14.29%
886125 | SV06 | RINGMILL | RBS | 21 | 7 | 33.33% | 4 | 19.05% | 5 | 23.81% | 5 | 23.81%
893604 | SV07 | BASSI LUIGI | TEES, ELBOWS, REDUCERS | 24 | 4 | 16.67% | 5 | 20.83% | 11 | 45.83% | 5 | 20.83%
899503 | SV08 | EDGEN & MURRAY | STRUCTURAL STEEL | 33 | 4 | 12.12% | 4 | 12.12% | 6 | 18.18% | 19 | 57.58%
901777 | SV09 | VILMAR | FORGED ANCHORS | 19 | 4 | 21.05% | 5 | 26.32% | 5 | 26.32% | 5 | 26.32%
903858 | SV10 | TECHLAM | FLEXIBLE BASE & TOP CONNECTORS | 77 | 8 | 10.39% | 13 | 16.88% | 31 | 40.26% | 25 | 32.47%
904033 | SV11 | VULCAN | FORGED ANCHORS | 36 | 9 | 25% | 6 | 16.67% | 10 | 27.78% | 11 | 30.56%
907757 | SV12 | VOESTALPINE | SHR BUOYANCY TANK DOMES | 43 | 11 | 25.58% | 4 | 9.302% | 13 | 30.23% | 15 | 34.88%
916859 | SV13 | FABRICOM | CS HOT INDUCTION BENDS | 34 | 11 | 32.35% | 3 | 8.824% | 13 | 38.24% | 7 | 20.59%
927991 | SV14 | EIFFAGE | PASEYES ASSEMBLY | 38 | 3 | 7.895% | 7 | 18.42% | 9 | 23.68% | 19 | 50%
930105 | SV15 | PROJECT MATERIAL SAS | 2" PIPING | 23 | 5 | 21.74% | 3 | 13.04% | 12 | 52.17% | 3 | 13.04%
929968 | SV16 | RINGMILL | TAPERED JOINTS | 17 | 4 | 23.53% | 3 | 17.65% | 8 | 47.06% | 2 | 11.76%
934277 | SV17 | PROJECT MATERIAL SAS | MAIN STEEL TUBULAR | 31 | 5 | 16.13% | 8 | 25.81% | 4 | 12.9% | 14 | 45.16%
934363 | SV18 | BASSI LUIGI | DUPLEX INDUCTION BENDS | 27 | 4 | 14.81% | 10 | 37.04% | 7 | 25.93% | 6 | 22.22%
940818 | SV20 | BMT | RISER MONITORING SYSTEM | 106 | 0 | 0% | 3 | 2.83% | 8 | 7.547% | 95 | 89.62%
942320 | SV21 | MOFFAT | HOT STABS | 32 | 0 | 0% | 5 | 15.62% | 15 | 46.88% | 12 | 37.5%
945176 | SV22 | EDGEN & MURRAY | BEAMS | 16 | 0 | 0% | 2 | 12.5% | 4 | 25% | 10 | 62.5%
945177 | SV23 | PROJECT MATERIAL SAS | PLATES | 16 | 0 | 0% | 2 | 12.5% | 6 | 37.5% | 8 | 50%
942733 | SV24 | DUCO | UMBILICALS | 85 | 0 | 0% | 1 | 1.176% | 16 | 18.82% | 68 | 80%
955596 | SV25 | ATV | BUOYANCY TANKS VALVES | 54 | 1 | 1.852% | 20 | 37.04% | 15 | 27.78% | 18 | 33.33%
956127 | SV26 | FES | BEND STIFFENER CONNECTOR | 26 | 0 | 0% | 0 | 0% | 22 | 84.62% | 4 | 15.38%
964350 | SV27 | BASSI LUIGI | ANODES FOR IMS STRUCTURE | 27 | 0 | 0% | 0 | 0% | 13 | 48.15% | 14 | 51.85%
964762 | SV28 | ARCELOR | STRUCTURAL STEEL | 16 | 0 | 0% | 0 | 0% | 2 | 12.5% | 14 | 87.5%
966069 | SV29 | MEGA | RISER STRUCTURAL FORGING | 22 | 0 | 0% | 0 | 0% | 14 | 63.64% | 8 | 36.36%
970733 | SV30 | TECTUBI | SHR BT BALALSTING PIPING | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
969181 | SV31 | PROJECT MATERIAL SAS | CLADE LINE PIPE & BENDS | 67 | 0 | 0% | 5 | 7.463% | 28 | 41.79% | 34 | 50.75%
971635 | SV32 | BALMORAL | UMBILICAL ARCHE BUOYANCY MODULES | 38 | 0 | 0% | 0 | 0% | 0 | 0% | 38 | 100%
961218 | SV33 | ERMS | SUBSEA STRUCTURES PRE-FABRICATED ITEMS | 26 | 0 | 0% | 0 | 0% | 9 | 34.62% | 17 | 65.38%
972220 | SV34 | TRELLEBORG | INSULATION COVERS | 31 | 0 | 0% | 0 | 0% | 4 | 12.9% | 27 | 87.1%
TBA | SV35 | EDGEN & MURRAY | MISCELLANEOUS | 38 | 0 | 0% | 0 | 0% | 0 | 0% | 38 | 100%
836297 | SX01 | EWT | FAB STRUCT ASSEMBLY | 63 | 8 | 12.7% | 14 | 22.22% | 15 | 23.81% | 26 | 41.27%
TBA | SX02 | PCNL | 5LPP | 103 | 4 | 3.883% | 9 | 8.738% | 54 | 52.43% | 36 | 34.95%
892851 | SX03 | METEC | ANODES FOR LBL ARRAY | 25 | 3 | 12% | 4 | 16% | 14 | 56% | 4 | 16%
914144 | SX04 | CAMERON | SUBSEA BALL VALVES | 100 | 14 | 14% | 31 | 31% | 45 | 45% | 10 | 10%
TBA | SX05 | METEC | BLANKET ORDER FOR ANODE | 78 | 0 | 0% | 1 | 1.282% | 17 | 21.79% | 60 | 76.92%
|  |  | TOTAL of documents |  | 1754
|  |  | Approved |  | 128 | 7.298%
|  |  | To be reissued by VENDOR |  | 246 | 14.03%
|  |  | In Review SAI |  | 534 | 30.44%
|  |  | Not received |  | 847 | 48.29%

## Source
Originator | PO Description | PO Reference | Page Originator | Client Reference | Title | Current Rev | Rev date | Reception Date | Status | Class | Comment Consolidator Name | CPY Answer | Return Date to Vendor | Return Code | Next Revision Due Date | Ready for Handover (Y/N) | To be reissued by VENDOR (Y/N) | IN Review SAI (Y/N) | Document not received
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700001 | Vendor Master Document List for Flexible Jumpers | 3 | 2014-06-24 17:42 | 2014-06-26 17:42 | AFC | 2 | Huvet Guillaume | 2-Approved with comments_Nextstatus AFC | 2014-09-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-24 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700002 | Supplier HSEs Plan | 3 | 2014-04-01 12:00 | 2014-04-08 01:00 | AFC | 1 | Poullaouec Anne-Gael | 1-Approved without Comments | 2014-05-07 | 1 - Reviewed Without Comments |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700003 | Project Quality Plan | 3 | 2014-08-11 16:48 | 2014-09-04 16:48 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-10-13 | 1 - Reviewed Without Comments |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700004 | Project Schedule Flexible Jumpers and OOLs | 2 | 2014-02-14 | 2014-02-18 | IFR | 2 | Huvet Guillaume | 2-Approved with comments_Nextstatus AFC | 2014-04-18 | 3FC - Rejected and Comments on Form | 2014-05-03 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700005 | Project Execution Plan | 3 | 2014-04-22 17:50 | 2014-04-29 17:50 | IFI | 3 | Huvet Guillaume | 1-Approved without Comments | 2014-06-30 | 1 - Reviewed Without Comments |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700006 | Monthly Progress Report Flexible Jumpers | 13 | 2014-09-19 15:41 | 2014-09-22 15:42 | IFR | 2 | Huvet Guillaume | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700007 | Project Equipment List | 1 | 2014-05-28 19:45 | 2014-05-28 19:45 | IFR | 2 | Huvet Guillaume | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3FC - Rejected and Comments on Form | 2014-10-10 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700008 | Project Procurement Plan | 4 | 2014-10-10 17:22 | 2014-10-14 17:22 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700009 | Vendor Data Book Index for Flexible Jumpers | 1 | 2014-03-14 | 2014-03-27 | IFA | 1 | Quintas Stephane | 2-Approved with comments_Nextstatus IFA | 2014-07-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-24 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700010 | Vendor Data Book for Flexible Jumpers |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700011 | Flexible Jumpers Qualification Plan | 2 | 2014-04-03 | 2014-04-04 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-05-20 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700012 | RACS - Spare Parts List 2 Years Operational, Start-up and Commissioning |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700015 | RACS - Dispatch Dossier |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700016 | RACS - Dispatch Dossier Index |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-700017 | Riser Annulus Condition Surveillance - System Operational Philosophy | 0 | 2014-09-17 17:46 | 2014-09-19 17:46 | IFR | 2 | Vernouillet Philippe | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-711001 | Design Premise for Flexible Jumpers | 2 | 2014-05-02 15:27 | 2014-05-07 15:25 | IFA | 1 | CHAUVET Pierre | 2-Approved with comments_Nextstatus IFA | 2014-09-18 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-03 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-711002 | Design Premise for Flexible Jumpers for Dynamic Analysis | 3 | 2014-09-25 15:06 | 2014-09-26 15:06 | IFA | 1 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-711003 | Flexible Dynamic Jumpers Ancillary Equipment Design Premise | 1 | 2014-03-25 | 2014-04-04 | IFR | 1 | CHAUVET Pierre | 2-Approved with comments_Nextstatus IFA | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-711004 | Riser Annulus Condition Surveillance - Basis of Design | 0 | 2014-09-17 17:44 | 2014-09-19 17:44 | IFR | 1 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712001 | Failure Modes, Effects and Criticality Analysis (FMECA) | 2 | 2014-09-11 19:27 | 2014-09-16 19:27 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712002 | Flexible Jumpers Cathodic Protection Report | 1 | 2014-07-08 18:09 | 2014-07-15 18:09 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712003 | Dynamic Analysis Report for Flexible Jumpers | 1 | 2014-06-24 18:10 | 2014-06-30 18:10 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712004 | Flexible Jumpers Interference Analysis Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712005 | Fatigue Analysis Report for Flexible Jumpers |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712006 | Flexible Jumpers Service Life Assessment Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712007 | Design Report for Flexible Jumpers | 2 | 2014-05-07 18:34 | 2014-05-13 18:34 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-09 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712008 | Flexible Jumpers Bending Stiffeners Design Report | 1 | 2014-06-26 18:18 | 2014-07-04 18:18 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-18 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-03 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712009 | Flexible Jumpers Preliminary Packing Analysis Report | 1 | 2014-01-20 |  | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-03-17 | 2 - Reviewed With Comments | 2014-04-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712010 | Flexible Dynamic Jumpers BSCs Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712011 | Flexible Dynamic Jumpers I-Tube Top Flange and Lower Spool Design Report | 1 | 2014-03-20 | 2014-03-25 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-05-28 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-12 01:00 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712012 | SHR Side Connection Design Report | 0 | 2014-05-19 12:50 | 2014-05-21 11:48 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712013 | Flexible Dynamic Jumpers Insulation Covers Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712014 | Hang-Off Collars FPSO Side Design Report | 0 | 2014-08-01 12:16 | 2014-08-05 12:16 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712015 | Flexible Dynamic Jumpers End-Fittings Design Report | 0 | 2014-02-19 | 2014-02-21 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-04-07 | 2FC - Reviewed With Comments and Comments on Form | 2014-04-22 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712016 | Design Report for Counter Hubs | 2 | 2014-09-24 15:07 | 2014-09-26 15:07 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712017 | FPSO Mock-up Design report (including GA) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712018 | SHR Mock-ups Design Report | 1 | 2014-05-06 18:09 | 2014-05-12 15:20 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712019 | Reels Data Dossier (including certification) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712020 | Cradles Data Dossier (including certification) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712021 | Spreader Bar Assembly Design (including GA) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712022 | Seafastening Design Report (including GA) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712023 | Flow Induced Pulsation Study Scope of Work | 0 | 2014-07-15 18:41 | 2014-07-18 18:41 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-712024 | 11,9" Production Flexible Dynamic Jumper Sample Pulling Head - Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721001 | Flexible Dynamic Jumpers Insulation Covers Specification |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721002 | Ancillary Permanent Equipments - Paint Coating Specification | 0 | 2013-12-09 | 2013-12-11 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-01-28 | 3FC - Rejected and Comments on Form | 2014-02-12 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721003 | Ancillary Temporary Equipments - Paint Coating Specification | 1 | 2014-06-10 19:12 | 2014-06-19 19:12 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-10-10 | 2 - Reviewed With Comments | 2014-10-25 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721004 | Ancillary Equipments - Structural Welding Specification | 2 | 2014-07-03 16:04 | 2014-07-08 16:04 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-25 | 2 - Reviewed With Comments | 2014-10-10 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721005 | Ancillary Equipments - Subsea Fasteners Coating Specification | 1 | 2014-07-07 17:15 | 2014-07-21 17:15 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721006 | Annulus Monitoring System – Technical Specification | 2 | 2014-06-10 15:33 | 2014-06-13 15:33 | IFA | 1 | CHAUVET Pierre | 2-Approved with comments_Nextstatus IFA | 2014-08-27 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-11 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721007 | Passive Fire Protection Specification | 0 | 2014-07-15 17:37 | 2014-07-16 17:37 | IFR | 2 | CHAUVET Pierre | 3-Rejected_Nextstatus IFR | 2014-09-24 | 3FC - Rejected and Comments on Form | 2014-10-09 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721008 | Riser Annulus Condition Surveillance - Modbus Interface Specification | 0 | 2014-09-17 17:46 | 2014-09-19 17:46 | IFR | 2 | Vernouillet Philippe | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-721009 | RACS - Functional Design Specification |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-722001 | Ancillary Equipments - Steel Products Material Datasheets for Plates and Tubes | 1 | 2014-04-15 15:00 | 2014-04-23 01:00 | IFR | 2 | CHAUVET Pierre | 3-Rejected_Nextstatus IFR | 2014-09-24 | 3FC - Rejected and Comments on Form | 2014-10-09 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-722002 | Ancillary Equipments - Fasteners Material Datasheets | 2 | 2014-10-08 16:33 | 2014-10-14 16:33 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-722003 | Flexible Jumper Data Sheet | 2 | 2014-04-24 17:46 | 2014-04-30 17:44 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-722004 | Ancillary Equipments - Steel Products Material Datasheets for Forged Pieces | 2 | 2014-10-03 16:53 | 2014-10-14 16:33 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730001 | Flexible Jumpers Packing General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730002 | 12,5" GE Flexible Dynamic Jumper at FPSO and SHR Sides Bend Stiffener Commercial Drawing | 1 | 2014-07-24 18:04 | 2014-07-31 18:04 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730004 | 11,9" Production Flexible Dynamic Jumper at FPSO Side Bend Stiffener Commercial Drawing | 1 | 2014-07-24 18:04 | 2014-07-31 18:04 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730005 | 11,9" Production Flexible Dynamic Jumper at SHR Side Bend Stiffener Commercial Drawing | 1 | 2014-07-24 17:48 | 2014-08-04 17:48 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730006 | 11" WI Flexible Dynamic Jumper at FPSO and SHR Sides Bend Stiffener Commercial Drawing | 1 | 2014-07-24 18:04 | 2014-07-31 18:04 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730008 | 3,5" GL Flexible Dynamic Jumper at FPSO and SHR Sides Bend Stiffener Commercial Drawing | 1 | 2014-07-24 18:04 | 2014-07-31 18:04 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730010 | 12,5" GE Flexible Dynamic Jumper at FPSO Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730011 | 12,5" GE Flexible Dynamic Jumper at SHR Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730012 | 11,9" Production Flexible Dynamic Jumper at FPSO Side BSC General Arrangement Drawing | 0 | 2014-09-05 10:45 | 2014-09-17 10:45 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730013 | 11,9" Production Flexible Dynamic Jumper at SHR Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730014 | 11" WI Flexible Dynamic Jumper at FPSO Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730015 | 11" WI Flexible Dynamic Jumper at SHR Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730016 | 3,5" GL Flexible Dynamic Jumper at FPSO Side BSC General Arrangement Drawing | 0 | 2014-09-05 18:02 | 2014-09-12 18:02 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730017 | 3,5" GL Flexible Dynamic Jumper at SHR Side BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730018 | 12,5" GE Flexible Dynamic Jumper at SHR Side Spool Piece Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730019 | 11,9" Production Flexible Dynamic Jumper at SHR Side Spool Piece Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730020 | 11" WI Flexible Dynamic Jumper at SHR Side Spool Piece Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730021 | 3,5" GL Flexible Dynamic Jumper at SHR Side Spool Piece Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730022 | 11,9" Production Flexible Dynamic Jumper Insulation Covers Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730023 | 3,5" GL Flexible Dynamic Jumper Insulation Covers Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730024 | 12,5" GE Flexible Dynamic Jumper - FPSO Side Connection - General Arrangement Drawing | 0 | 2014-08-12 11:52 | 2014-08-22 11:52 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730025 | 12,5" GE Flexible Dynamic Jumper SHR Side Connection General Arrangement Drawing | 0 | 2014-05-19 20:10 | 2014-05-26 20:10 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730026 | 11,9" Production Flexible Dynamic Jumper - FPSO Side Connection - General Arrangement Drawing | 0 | 2014-08-12 11:52 | 2014-08-22 11:52 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730027 | 11,9" Production Flexible Dynamic Jumper SHR Side Connection General Arrangement Drawing | 0 | 2014-05-22 20:10 | 2014-05-26 20:10 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730028 | 11" WI Flexible Dynamic Jumper - FPSO Side Connection - General Arrangement Drawing | 0 | 2014-08-12 11:52 | 2014-08-22 11:52 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730029 | 11" WI Flexible Dynamic Jumper SHR Side Connection General Arrangement Drawing | 0 | 2014-05-22 20:10 | 2014-05-26 20:10 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730030 | 3,5" GL Flexible Dynamic Jumper - FPSO Side Connection - General Arrangement Drawing | 0 | 2014-08-12 11:52 | 2014-08-22 11:52 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730031 | 3,5" GL Flexible Dynamic Jumper SHR Side Connection General Arrangement Drawing | 0 | 2014-05-22 20:10 | 2014-05-26 20:10 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730032 | 12,5" GE Flexible Dynamic Jumper Hang-Off Collar Drawing (General Arrangement + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730033 | 11,9" Production Flexible Dynamic Jumper Hang-Off Collar General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730034 | 11" WI Flexible Dynamic Jumper Hang-Off Collar General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730035 | 3,5" GL Flexible Dynamic Jumper Hang-Off Collar General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730036 | 12,5" GE Flexible Dynamic Jumper Pulling/Test Head General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730037 | 11,9" Production Flexible Dynamic Jumper Pulling/Test Head Drawing (General Arrangement + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730038 | 11" WI Flexible Dynamic Jumper Pulling/Test Head General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730039 | 3,5" GL Flexible Dynamic Jumper Pulling/Test Head General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730040 | 12,5" GE Flexible Dynamic Jumper at FPSO Side End-Fitting Commercial Drawing | 1 | 2014-09-16 16:40 | 2014-09-19 16:40 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730041 | 12,5" GE Flexible Dynamic Jumper at SHR Side End Fitting Commercial Drawing | 2 | 2014-03-20 | 2014-09-29 16:44 | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730042 | 11,9" Production Flexible Dynamic Jumper at FPSO Side End-Fitting Commercial Drawing | 1 | 2014-09-22 10:00 | 2014-10-02 10:00 | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730043 | 11,9" Production Flexible Dynamic Jumper at SHR Side End Fitting Commercial Drawing | 1 | 2014-03-20 | 2014-03-21 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus IFR | 2014-05-15 | 2FC - Reviewed With Comments and Comments on Form | 2014-05-30 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730044 | 11" WI Flexible Dynamic Jumper at FPSO Side End-Fitting Commercial Drawing | 1 | 2014-09-16 16:40 | 2014-09-19 16:40 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730045 | 11" WI Flexible Dynamic Jumper at SHR Side End Fitting Commercial Drawing | 2 | 2014-09-22 10:00 | 2014-10-02 10:00 | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730046 | 3,5" GL Flexible Dynamic Jumper at FPSO Side End-Fitting Commercial Drawing | 1 | 2014-09-16 16:40 | 2014-09-19 16:40 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730047 | 3,5" GL Flexible Dynamic Jumper at SHR Side End Fitting Commercial Drawing | 2 | 2014-09-22 10:00 | 2014-10-02 10:00 | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730048 | Flexible Dynamic Jumper Schematics | 2 | 2014-05-13 19:52 | 2014-05-26 19:50 | AFC | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730054 | Sub component GA & Detail Drawings |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730055 | Flexible Jumpers Thermal Test General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730056 | Flexible Jumpers Coiled Tubing General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730057 | Flexible Dynamic Jumper I-tube Bottom Swivel Flange at FPSO General Arrangement Drawing | 0 | 2013-11-12 | 2013-11-15 | IFR | 2 | CHAUVET Pierre | 3-Rejected_Nextstatus IFR | 2014-01-17 | 3 - Rejected | 2014-02-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730058 | Flexible Dynamic Jumper I-Tube Bottom Swivel Flanges and Top Flanges at FPSO General Arrangement Drawing | 1 | 2014-04-15 18:24 | 2014-04-18 18:25 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730059 | 12.5" GE Flexible Dynamic Jumper SHR Side Connection Mock-Up General Arrangement | 1 | 2014-05-12 17:00 | 2014-05-15 17:00 | IFI | 3 | CHAUVET Pierre | 1-Approved without Comments | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730060 | 11,9" Production Flexible Dynamic Jumper SHR Side Connection Mock-Up General Arrangement | 1 | 2014-05-12 16:58 | 2014-05-15 16:58 | IFI | 3 | CHAUVET Pierre | 1-Approved without Comments | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730061 | 11" WI Flexible Dynamic Jumper SHR Side Connection Mock-Up General Arrangement | 1 | 2014-05-12 17:00 | 2014-05-15 17:00 | IFI | 3 | CHAUVET Pierre | 1-Approved without Comments | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730062 | 3.5" GL Flexible Dynamic Jumper SHR Side Connection Mock-Up General Arrangement | 1 | 2014-05-12 17:00 | 2014-05-15 17:00 | IFI | 3 | CHAUVET Pierre | 1-Approved without Comments | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730063 | 12,5" GE Flexible Dynamic Jumpers at FPSO Side I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730064 | 11,9" Production Flexible Dynamic Jumper at FPSO Side I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730065 | 11" WI01 and WI03 Flexible Dynamic Jumper at FPSO Side I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730066 | 11" WI 02 Flexible Dynamic Jumper at FPSO Side I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730067 | 3,5" GL Flexible Dynamic Jumper at FPSO Side I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730068 | FPSO Umbilical I-Tube and Lower Spool General Arrangement | 0 | 2014-04-15 18:24 | 2014-04-18 18:24 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | 2014-07-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-01 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730069 | 11,9” Production Flexible Dynamic Jumper Sample End Fitting Commercial Drawing | 0 | 2014-05-19 17:47 | 2014-06-04 17:47 | IFR | 2 | CHAUVET Pierre | 1-Approved without Comments_Nextstatus AFC | 2014-09-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-09 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730070 | 12,5" GE Flexible Dynamic Jumper at FPSO Side - BSC Outboard - General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730071 | 11,9" Production Flexible Dynamic Jumper at FPSO Side - BSC Outboard - General Arrangement Drawing | 0 | 2014-08-07 19:17 | 2014-09-05 19:17 | IFR | 2 | CHAUVET Pierre | 3-Rejected_Nextstatus IFR | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730072 | 11" WI Flexible Dynamic Jumper at FPSO Side - BSC Outboard - General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730073 | 3,5" GL Flexible Dynamic Jumper at FPSO Side - BSC Outboard - General Arrangement Drawing | 0 | 2014-08-07 19:17 | 2014-09-05 19:17 | IFR | 2 | CHAUVET Pierre | 3-Rejected_Nextstatus IFR | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730074 | 11,9" Production Flexible Dynamic Jumper Sample Pulling Head - WLL 200t - General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730075 | Riser Annulus Condition Surveillance - Riser Unit Assembly (GA) | 0 | 2014-09-17 17:45 | 2014-09-19 17:45 | IFR | 2 | Vernouillet Philippe | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730076 | BSC Pulling Vertebrae 3.5" GL Flexible Dynamic Jumper at FPSO Side - BSC Pulling Vertebrae - General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730077 | BSC Pulling Vertebrae 11" WI Flexible Dynamic Jumper at FPSO Side - BSC Pulling Vertebrae - General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730078 | BSC Pulling Vertebrae 11.9" Production Flexible Dynamic Jumper at FPSO Side - BSC Pulling Vertebrae - General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-730079 | BSC Pulling Vertebrae 12.5" GE Flexible Dynamic Jumper at FPSO Side - BSC Pulling Vertebrae - General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740001 | 12,5" GE Flexible Dynamic Jumper I-tube Lower Spool at FPSO Detailed Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740003 | 11,9" Production Flexible Dynamic Jumper I-tube Lower Spool at FPSO Detailed Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740005 | 11" WI Flexible Dynamic Jumper I-tube Lower Spool at FPSO Detailed Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740007 | 3,5" GL Flexible Dynamic Jumper I-tube Lower Spool at FPSO Detailed Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740009 | 12,5" GE Flexible Dynamic Jumper at SHR - TECHLOK H14in130 Counter Hub Detailed Drawing | 2 | 2014-07-11 19:25 | 2014-10-02 10:00 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740010 | 11,9" Production Flexible Dynamic Jumper at SHR - TECHLOK H16in120 Counter Hub Detailed Drawing | 2 | 2014-07-11 19:25 | 2014-10-02 10:00 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740011 | 11" WI Flexible Dynamic Jumper at SHR - TECHLOK H14in112 Counter Hub Detailed Drawing | 2 | 2014-07-11 19:25 | 2014-10-02 10:00 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740012 | 3,5" GL Flexible Dynamic Jumper at SHR - TECHLOK 5in34 Counter Hub Detailed Drawing | 2 | 2014-07-11 19:25 | 2014-10-02 10:00 | AFC | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740013 | Flexible Dynamic Jumper I-tube Top Flange at FPSO Detailed Drawing | 1 | 2014-04-15 18:00 | 2014-04-18 18:19 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740014 | Flexible Dynamic Jumper I-Tube Bottom Swivel Flange Ring at FPSO Detailed Drawing | 1 | 2014-04-15 18:00 | 2014-04-18 18:19 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740015 | Flexible Dynamic Jumper I-Tube Bottom Swivel Flange Hub at FPSO Detailed Drawing | 1 | 2014-04-15 18:00 | 2014-04-18 18:19 | IFR | 2 | CHAUVET Pierre | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740016 | 12,5" GE Flexible Dynamic Jumper at FPSO - TECHLOK H14in130 Counter Hub Detailed Drawing | 0 | 2014-09-22 09:53 |  | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740017 | 11,9" Production Flexible Dynamic Jumper at FPSO - TECHLOK H14in120 Counter Hub Detailed Drawing | 0 | 2014-09-22 09:53 |  | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740018 | 11" WI Flexible Dynamic Jumper at FPSO - TECHLOK H14in112 Counter Hub Detailed Drawing | 0 | 2014-09-22 09:53 |  | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740019 | 3,5" GL Flexible Dynamic Jumper at FPSO - TECHLOK 6in52 Counter Hub Detailed Drawing | 0 | 2014-09-22 09:53 |  | IFR | 2 | [7 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740027 | SUP - 11" WI Flexible Dynamic Jumper SHR Spool Piece Mock-Up Detail Drawing (SUPERSEDED BY NG-EGN-23-SV01-730061) |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740032 | Rise Annulus Condition Surveillance - Data Acquisition Unit UCP Wiring and GA | 0 | 2014-09-17 17:45 | 2014-09-19 17:45 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740033 | Riser Annulus Condition Surveillance - Remote IO Unit Wiring and GA | 0 | 2014-09-17 17:45 | 2014-09-19 17:45 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740034 | RACS - Riser Unit Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740035 | Riser Annulus Condition Surveillance - System Interconnect Wiring Diagram | 0 | 2014-09-17 17:47 | 2014-09-19 17:47 | IFR | 2 | Vernouillet Philippe | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-740036 | Riser Annulus Condition Surveillance - System P and ID | 0 | 2014-09-17 17:43 | 2014-09-19 17:43 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750001 | Ancillary Permanent Equipments - Painting Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750002 | Ancillary Temporary Equipments - Painting Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750003 | Ancillary Equipments - Fasteners Coating Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750004 | Ancillary Equipments - Welding Book (WPS, PQR & Welding Map) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750005 | Flexible Jumpers Factory Acceptance Test Procedure | 0 | 2014-08-27 12:57 | 2014-09-08 12:57 | IFR | 2 | CHAUVET Pierre | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750006 | Flexible Jumpers Load Out Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750007 | Dimensional Control Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750008 | Painting Procedure - SUBVENDOR N°1 |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750009 | NDT Procedure - SUBVENDOR N°1 |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750010 | FAT Procedure - SUBVENDOR N°1 (if applicable) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750011 | Manufacturing Procedure - SUBVENDOR N°1 (if applicable) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750012 | Flexible Jumpers Thermal Test Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750013 | Flexible Jumpers Coiled Tubing Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750014 | RACS - Packing, Marking, Handling, Transportation, Storage and Preservation Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750015 | RACS - Installation Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750016 | RACS - Factory Acceptance Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750017 | RACS - Data Validation Test Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750018 | RACS - Site Acceptance Test Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750019 | RACS - Pre-Commissioning Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-750020 | RACS - Commissioning Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760001 | 12,5" Gas Export Flexible Dynamic Jumper Manufacturing Quality Plan | 1 | 2014-08-01 18:42 | 2014-08-01 18:42 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | 2014-10-01 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-16 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760002 | 11,9" Production Flexible Dynamic Jumper Manufacturing Quality Plan | 1 | 2014-08-01 18:42 | 2014-08-01 18:42 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | 2014-10-01 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-16 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760003 | 11" Water Injection Flexible Dynamic Jumper Manufacturing Quality Plan | 1 | 2014-08-01 18:42 | 2014-08-01 18:42 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | 2014-10-01 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-16 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760004 | 3,5" Gas Lift Flexible Dynamic Jumper Manufacturing Quality Plan | 1 | 2014-08-01 18:42 | 2014-08-01 18:42 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | 2014-10-01 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-16 |  | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760005 | Riser Annulus Condition Surveillance - Inspection and Test Plan | 0 | 2014-09-18 17:43 | 2014-09-19 17:43 | IFR | 1 | Vernouillet Philippe | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-760006 | RACS - Factory Acceptance Test Report |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-770001 | Welding Book - SUBVENDOR N°1 |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-770002 | Flexible Jumpers Thermal Test Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-770003 | Flexible Jumpers Coiled Tubing Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-770004 | RACS - Data Validation Test Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-780001 | Flexible Jumpers Operating, Inspection and Maintenance Manual |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-780002 | Packing, Marking and Shipping Instructions | 1 | 2014-08-28 16:10 | 2014-09-19 16:10 | IFR | 2 | Huvet Guillaume | [6 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-780003 | RACS - Operations and Maintenance Manual and Trouble Shooting Loop Diagram |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-780004 | RACS - Software Installation and Administration Guide |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-780005 | RACS - RTAC Software User Manual |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | Flexible Jumpers | 836717 | SV01 | NG-EGN-23-SV01-790001 | Integration, Installation and Commissioning Guidelines for Contractor |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700001 | Vendor Master Document List for OOL | 3 | 2014-06-24 17:42 | 2014-06-26 17:42 | AFC | 2 | Huvet Guillaume | 2-Approved with comments_Nextstatus AFC | 2014-09-10 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-25 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700002 | OOLs Qualification Plan and Criteria | 1 | 2014-02-10 | 2014-02-11 | IFR | 2 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus AFC | 2014-09-25 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-10 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700003 | Vendor Data Book Index for OOLs | 0 | 2014-07-30 16:12 | 2014-08-19 16:12 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-10-02 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-17 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700004 | Vendor Data Book for OOL |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700005 | Monthly Progress Report OOLs | 13 | 2014-09-19 15:42 | 2014-09-22 15:42 | IFR | 2 | Huvet Guillaume | [6 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-700006 | Project Equipment List |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-711001 | OOLs Design Premise | 3 | 2014-07-25 18:29 | 2014-07-29 18:29 | IFA | 1 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus IFA | 2014-10-03 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-18 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-711002 | OOL Ancillary Equipment Design Basis | 0 | 2014-04-14 01:00 | 2014-04-16 19:00 | IFR | 1 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus IFA | 2014-09-25 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-10 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-711003 | OOLs Dynamic Analyses Design Premise | 2 | 2014-09-26 17:28 | 2014-09-30 17:28 | IFA | 1 | [7 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712001 | OOL Design Report | 1 | 2014-08-01 19:58 | 2014-08-01 19:58 | IFR | 2 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus AFC | 2014-10-03 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-18 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712002 | OOLs Dynamic Analysis Report | 1 | 2014-08-14 15:05 | 2014-08-19 15:05 | IFR | 2 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus AFC | 2014-09-18 | 2 - Reviewed With Comments | 2014-10-03 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712003 | OOLs Interference Analysis Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712004 | OOLs Fatigue Analysis Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712005 | Bending Stiffeners Design Report | 0 | 2014-08-14 16:27 | 2014-08-14 16:27 | IFR | 2 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus AFC | 2014-10-03 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-18 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712006 | OOL FPSO Support Structure Design Report | 1 | 2014-09-26 17:27 | 2014-09-30 17:27 | IFR | 2 | [7 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712007 | Mock-up Design Report (including GA) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712008 | OOL BSC Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712009 | OOL End-Fittings Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712010 | OOL FPSO Spool Piece Design Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712011 | OOLs Sample Definition Report | 2 | 2014-01-13 | 2014-01-14 | AFC | 1 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus IFA | 2014-02-25 | 2 - Reviewed With Comments | 2014-03-12 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712012 | OOLs Flow Assurance Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712013 | OOL OLT Support Structure Design Report | 0 | 2014-05-06 18:10 | 2014-05-09 18:05 | IFR | 2 | VOUTIER Marie-Alix | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3FC - Rejected and Comments on Form | 2014-10-10 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-712014 | Failure Mode, Effects and Criticality (FMECA) |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721001 | OOLs Specification | 1 | 2014-05-12 18:37 | 2014-05-14 18:37 | IFA | 1 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721002 | OOL Buoyancy Modules Specification | 0 | 2014-08-01 09:43 | 2014-08-12 09:42 | IFR | 1 | VOUTIER Marie-Alix | 3-Rejected_Nextstatus IFR | [5 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721003 | Ancillary Permanent Equipments - Paint Coating Specification |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721004 | Ancillary Temporary Equipments - Paint Coating Specification |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721005 | Ancillary Equipments - Structural Welding Specification |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-721006 | Ancillary Equipments - Subsea Fasterners Coating Specification |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-722001 | OOLs Data Sheet | 2 | 2014-08-14 18:27 | 2014-08-14 18:27 | AFC | 2 | VOUTIER Marie-Alix | [6 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-722002 | Ancillary Equipments - Steel Products Material Datasheets for Plates and Tubes |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-722003 | Ancillary Equipments - Fasteners Material Datasheets |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-722004 | Ancillary Equipments - Steel Products Material Datasheets for Forged Pieces |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730001 | OOLs Configuration Schematics | 2 | 2014-08-28 18:53 | 2014-09-05 18:53 | IFR | 2 | VOUTIER Marie-Alix | [6 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730002 | OOL BUOY Side Connection Drawing (GA + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730004 | OOL BUOY and FPSO Side Bend Stiffener Commercial Drawing | 0 | 2014-08-27 13:55 | 2014-09-05 13:55 | IFR | 2 | VOUTIER Marie-Alix | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730006 | OOL BSC General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730007 | OOL Pulling/Test Head General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730008 | OOL End-Fitting Commercial Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730009 | OOL Interface Structure Drawing (GA + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730010 | OOL FPSO Spool Drawing (GA + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730011 | Sub-Component Drawing (GA + Detail) |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730012 | OOL BUOY Side Connection 20.5inch Export Line Preliminary Drawing General Arrangement | 0 | 2013-07-30 | 2013-08-07 | IFI | 3 | VOUTIER Marie-Alix | 3-Rejected_Nextstatus IFR | 2013-10-03 | 3 - Rejected | 2013-10-18 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730013 | 20.5" Export Line OOL FPSO Side Connection Preliminary Drawing General Arrangement | 0 | 2013-11-12 | 2013-11-15 | IFR | 2 | VOUTIER Marie-Alix | 3-Rejected_Nextstatus IFR | 2014-01-20 | 3 - Rejected | 2014-02-04 |  | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730014 | OOL Sample Qualification Fatigue Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730015 | OOL Sample Qualification Tension / Bending over a Gutter Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730016 | OOL Sample Qualification Crushing with Tension Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730017 | OOL Sample Qualification Bend Stiffener Connection Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730018 | OOL Sample Qualification Pressure Drop Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730019 | OOL Sample Qualification Burst Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730020 | OOL Sample Qualification Damaging Pull Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730021 | OOL Sample Qualification Bending & Folding Test: General Arrangement Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730022 | OOL Sample Qualification Fatigue Test: Bend Stiffener Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730023 | OOL Sample Qualification Fatigue Test: Simplified BSC Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730024 | OOL Support Structure FPSO Side General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730025 | OOL Support Structure OLT Side General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-730026 | OOL FPSO - Side Connection - General Arrangement | 1 | 2014-08-26 18:25 | 2014-10-03 17:50 | IFR | 2 | [7 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-740001 | OOL Counter Hub Detailed Drawing |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-740002 | OOL FPSO Starboard Side Support Structure Detail Drawing | 1 | 2014-09-26 17:49 | 2014-10-03 17:49 | IFR | 2 | [7 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-740003 | OOL FPSO Port Side Support Structure Detail Drawing | 1 | 2014-09-26 17:49 | 2014-10-03 17:49 | IFR | 2 | [7 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750001 | OOLs Factory Acceptance Test Procedure | 0 | 2014-08-25 17:33 | 2014-08-28 17:33 | IFR | 2 | VOUTIER Marie-Alix | [6 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750002 | OOL Load Out Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750003 | OOL Support Structure NDT Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750004 | OOL Support Structure Painting Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750005 | OOL Support Structure Quality Control Plan |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750006 | OOL Support Structure Weighing Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750007 | OOL FPSO Spool NDT Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750008 | OOL FPSO Spool Painting Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750009 | OOL FPSO Spool Weighing Procedure |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750010 | OOL Sample Qualification Fatigue Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750011 | OOL Sample Qualification Tension/Bending over a gutter Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750012 | OOL Sample Qualification Crushing with Tension Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750013 | OOL Sample Qualification Bend Stiffener Connection Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750014 | OOL Sample Qualification Pressure Drop Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750015 | OOL Sample Qualification Fatigue Dissection Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750016 | Ancillary Permanent Equipments - Painting Procedure |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750017 | Ancillary Temporary Equipments - Painting Procedure |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-750018 | Ancillary Equipments - Fasteners Coating Procedure |  |  |  | not received | 3 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760001 | OOLs Operating, Inspection and Maintenance Manual |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760002 | OOLs Sample Qualification Manufacturing Quality Plan | 2 | 2014-02-24 | 2014-02-25 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760003 | OOLs Manufacturing Quality Plan |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760004 | OOL FPSO Spool Quality control Plan |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760005 | OOL Sample Qualification Tension/Bending over a Gutter Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760006 | OOL Sample Qualification Crushing with Tension Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760007 | OOL Sample Qualification Bend Stiffener Connection Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760008 | OOL Sample Qualification Pressure Drop Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760009 | OOL Sample Qualification Fatigue Dissection Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760010 | OOL Sample Qualification Burst Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760011 | OOL Sample Qualification Burst Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760012 | OOL Sample Qualification Damaging Pull Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760013 | OOL Sample Qualification Damaging Pull Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760014 | OOL Sample Qualification Bending & Folding Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-760015 | OOL Sample Qualification Bending & Folding Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-770001 | OOL Sample Qualification Fatigue Test Report |  |  |  | not received | 1 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-770002 | OOLs Cathodic Protection Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-770003 | OOL Support Structure Welding Book |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-770004 | OOL FPSO Spool Welding Book |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-790001 | OOLs Service Life Assessment Report |  |  |  | not received | 2 | [8 empty] | Y
TECHNIP | OOL | 836720 | SV02 | NG-EGN-25-SV02-790002 | Packing Analysis and Carousel Layout Report |  |  |  | not received | 2 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700001 | Master Document Register | 0 | 2013-09-05 | 2013-11-13 13:35 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2013-10-24 11:38 | 2FC - Reviewed With Comments and Comments on Form | 2013-11-08 11:38 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700002 | Project Organization Chart | 2 | 2014-05-09 10:24 | 2014-05-12 10:23 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus IFR | [5 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700003 | Work Time Schedule | 0 | 2013-09-05 | 2013-11-13 13:36 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2013-10-29 11:26 | 2FC - Reviewed With Comments and Comments on Form | 2013-11-13 11:26 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700004 | Weekly Report | 28 | 2014-09-19 17:10 | 2014-10-07 15:46 | IFR | 2 | [7 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700005 | Monthly Progress Report | 9 | 2014-08-15 12:22 | 2014-08-27 12:22 | IFR | 2 | LE-BOUTEILLER Olivier | [6 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700006 | Weekly and Monthly Reporting Calender | 0 | 2013-09-06 | 2013-11-13 13:36 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2013-10-29 11:26 | 3FC - Rejected and Comments on Form | 2013-11-13 11:26 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700007 | EEW Vendor Data Book Index | 1 | 2014-04-30 14:38 | 2014-04-30 14:38 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-07-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-24 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700008 | EEW Project Quality Plan | 2 | 2014-06-27 11:16 | 2014-06-27 11:16 | IFA | 1 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus IFA | 2014-10-06 | 2 - Reviewed With Comments | 2014-10-21 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700009 | Plug Mill Project Quality Plan | 0 | 2014-07-21 15:46 | 2014-07-25 15:46 | IFR | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus IFA | 2014-10-08 | 2 - Reviewed With Comments | 2014-10-23 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-700010 | Continuous Mandrel Mill Project Quality Plan | 0 | 2014-07-21 12:22 | 2014-07-21 12:22 | IFR | 1 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus IFA | 2014-10-07 | 2 - Reviewed With Comments | 2014-10-22 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-721001 | EEW Manufacturing Procedure Specification (SAWL) | 5 | 2014-06-16 10:35 | 2014-06-17 10:35 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-09-17 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-721002 | Voestalpine Manufacturing Procedure Specification (Plates) | 4 | 2014-04-24 15:24 | 2014-04-25 16:20 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-06-06 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-721003 | EEW Welding Procedure Specification | 6 | 2014-10-08 15:10 | 2014-10-10 15:10 | AFC | 1 | [7 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-721004 | Vallourec Welding Procedure Specification | 2 | 2014-04-16 12:20 | 2014-04-16 12:20 | IFR | 1 | GASTALDI Jean-philippe | 2-Approved with comments_Nextstatus IFR | 2014-06-17 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-02 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750001 | Handling, Loading, Transportation, Storage and Preservation Procedure | 2 | 2014-05-05 17:15 | 2014-05-05 17:15 | AFC | 2 | LE-BOUTEILLER Olivier | 1-Approved without Comments | 2014-05-20 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750002 | EEW Material Control and Traceability Procedure | 3 | 2014-04-24 15:24 | 2014-04-25 16:20 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-06-06 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750003 | EEW Forming Procedure Specification | 3 | 2014-07-28 15:17 | 2014-07-28 15:17 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-08-21 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750004 | EEW Heat Treatment Procedure | 7 | 2014-07-03 14:56 | 2014-10-01 12:54 | AFC | 1 | [7 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750005 | EEW Dimensional Control Procedure | 3 | 2014-07-28 15:17 | 2014-07-28 15:17 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-08-21 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750006 | EEW Visual Inspection Procedure for 24" SAW Pipes | 5 | 2014-05-08 11:45 | 2014-05-08 11:45 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-16 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750007 | EEW Hydrostatic Test Procedure | 3 | 2014-04-23 15:24 | 2014-04-25 16:20 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-06-06 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750008 | EEW Marking Procedure Specification | 3 | 2014-07-28 15:17 | 2014-07-28 15:17 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-08-21 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750009 | EEW Automatic UT Testing Procedure | 4 | 2014-04-29 14:05 | 2014-04-30 14:05 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-16 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750010 | EEW Manual UT Testing Procedure | 4 | 2014-04-29 14:05 | 2014-04-30 14:05 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-16 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750011 | EEW Radiographic Testing Procedure | 3 | 2014-07-28 15:17 | 2014-07-28 15:17 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750012 | EEW Magnetic Particle Testing Procedure for 24" SAW Pipes | 4 | 2014-05-08 11:45 | 2014-05-08 11:45 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-16 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-750013 | EEW Weldability Test Program Procedure | 2 | 2014-06-16 10:35 | 2014-06-17 10:35 | AFC | 1 | GASTALDI Jean-philippe | 1-Approved without Comments | [5 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760001 | Quality Plan STO Rath | 6 | 2014-09-12 18:55 | 2014-09-12 14:52 | AFC | 1 | Lambin Axel | 1-Approved without Comments | [5 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760002 | Quality Plan CMM MH (including ITP, MPS , main procedures) | 5 | 2014-05-06 18:03 | 2014-05-06 18:03 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-06-26 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760003 | EEW Inspection and Test Plan | 6 | 2014-10-08 15:10 | 2014-10-10 15:10 | IFA | 1 | [7 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760004 | EEW MPQ Test Plan | 6 | 2014-07-11 18:24 | 2014-07-11 18:27 | IFA | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-08-05 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-20 |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760005 | EEW Production Test Plan | 3 | 2014-08-07 13:52 | 2014-08-11 13:52 | AFC | 1 | Lambin Axel | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760006 | Voestalpine Inspection and Test Plan (Plates) | 4 | 2014-07-08 17:23 | 2014-07-08 17:23 | AFC | 1 | RAOUL Nicolas | 1-Approved without Comments | 2014-09-17 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760007 | V&M Certificates with results of MPQ Testing and Production Testing |  |  |  | not received | 3 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760008 | EEW MPQ Test Reports |  |  |  | not received | 3 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-760009 | EEW Production Test Reports |  |  |  | not received | 3 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-770001 | V&M Final Documentation |  |  |  | not received | 1 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-770002 | EEW Final Documentation |  |  |  | not received | 1 | [8 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-770003 | EEW Welder List | 3 | 2014-06-16 10:35 | 2014-06-17 10:35 | AFC | 1 | GASTALDI Jean-philippe | 1-Approved without Comments | [5 empty] | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-770004 | EEW NDT Operator List | 3 | 2014-07-28 15:17 | 2014-07-28 15:17 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-21 | 1 - Reviewed Without Comments |  | Y
V&M Deutschland GmbH | CS Linepipes | 856251 | SV03 | NG-EGN-21-SV03-780001 | Health, Safety and Environment Management Manual | 1 | 2014-05-14 18:28 | 2014-05-14 18:27 | IFA | 1 | Poullaouec Anne-Gael | 2-Approved with comments_Nextstatus IFA | 2014-06-20 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-05 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700001 | Vendor Master Document List | 0 | 2013-12-17 | 2013-12-17 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2014-01-22 | 2FC - Reviewed With Comments and Comments on Form | 2014-02-06 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700002 | Project Organization Chart | 0 | 2013-12-17 | 2013-12-17 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2014-01-21 | 2FC - Reviewed With Comments and Comments on Form | 2014-02-05 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700003 | Work Time Schedule | 0 | 2013-12-18 | 2013-12-18 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2014-01-21 | 2FC - Reviewed With Comments and Comments on Form | 2014-02-05 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700004 | Monthly Progress Report |  |  |  | not received | 2 | [8 empty] | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700005 | POSCO HSE Manual | 0 | 2013-12-18 | 2013-12-18 | IFR | 1 | Poullaouec Anne-Gael | 2-Approved with comments_Nextstatus IFA | 2014-04-09 01:00 | 3FC - Rejected and Comments on Form | 2014-04-24 01:00 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700006 | POSCO Project Quality Plan | 0 | 2013-12-18 | 2013-12-18 | IFR | 1 | Agorni Lorenzo | 1-Approved without Comments_Nextstatus IFA | 2014-01-31 | 3FC - Rejected and Comments on Form | 2014-02-15 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700007 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-700008 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-750001 | POSCO Material Control & Traceability Procedure | 0 | 2013-12-18 | 2013-12-18 | IFR | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-02-10 | 2FC - Reviewed With Comments and Comments on Form | 2014-02-25 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-750002 | POSCO NDT Procedure | 2 | 2014-06-25 13:05 | 2014-07-02 13:05 | IFA | 1 | Feuilly Nicolas | 2-Approved with comments_Nextstatus IFA | 2014-08-18 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-02 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-750003 | Handling, Loading, Transportation, Storage and Preservation Procedure | 0 | 2013-12-20 | 2013-12-20 | IFR | 2 | LE-BOUTEILLER Olivier | 3-Rejected_Nextstatus IFR | 2014-07-22 | 3FC - Rejected and Comments on Form | 2014-08-06 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-750004 | POSCO Manufacturing Procedure Specification | 2 | 2014-06-25 14:14 | 2014-07-01 14:14 | IFA | 1 | Lambin Axel | 1-Approved without Comments_Nextstatus AFC | 2014-07-25 | 1FC - Reviewed Without Comments but Comments on Form | 2014-08-09 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-750005 | POSCO Manual NDT Procedure | 1 | 2014-02-25 | 2014-02-25 | IFR | 1 | Feuilly Nicolas | 2-Approved with comments_Nextstatus IFA | 2014-05-22 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-06 01:00 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-760001 | POSCO Quality Control Plan (ITP) | 2 | 2014-06-25 14:14 | 2014-07-01 14:14 | IFA | 1 | Bertrand Sylvain | 1-Approved without Comments_Nextstatus AFC | 2014-07-28 | 1FC - Reviewed Without Comments but Comments on Form | 2014-08-12 |  | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-760002 | Plates Material Certificates + Traceability Sheet |  |  |  | not received | 3 | [8 empty] | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-770001 | POSCO NDT Record (UT RECORD) |  |  |  | not received | 2 | [8 empty] | Y
DAEWOO | STRUCTURAL STEEL | 883892 | SV04 | NG-EGN-20-SV04-770002 | POSCO NDT Operator List + Qualification | 0 | 2013-12-18 | 2013-12-18 | IFR | 1 | Feuilly Nicolas | 3-Rejected_Nextstatus IFR | 2014-01-31 | 3FC - Rejected and Comments on Form | 2014-02-15 |  | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | IN-EGN-20-SV05-770105 | Plate Weldability Test Report (Class 0) | 0 | 2014-02-07 | 2014-02-10 | IFI | 0 | MAS Jeremy | [6 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-700001 | Vendor Master Document List | 1 | 2014-02-07 | 2014-02-10 | AFC | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-700003 | Vendor Data Book Index | 2 | 2014-10-09 10:00 | 2014-10-10 10:00 | IFA | 1 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-700005 | VENDOR Data Book |  |  |  | not received | 1 | [8 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-700006 | List of Items of the Purchase Order | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFR | 3 | Bertrand Sylvain | [6 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-750001 | Manufacturing Procedure Specification for Beams (Including UT Procedure) | 4 | 2014-09-30 10:04 | 2014-10-10 10:00 | AFC | 1 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-750002 | Manufacturing Procedure Specification for Plates (Including UT Procedure) | 4 | 2014-09-30 10:44 | 2014-10-10 10:00 | IFA | 1 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760001 | AM Inspection & Test Plan | 2 | 2014-03-19 | 2014-03-19 | AFC | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760002 | Inspection and Test Plan for Plates | 4 | 2014-10-09 10:00 | 2014-10-10 10:00 | AFC | 1 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760003 | Visual and Dimensional Inspection Records for Beams (After Cutting) | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFI | 3 | Bertrand Sylvain | 1-Approved without Comments | [5 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760004 | Inspection Release Note for Beams (including TPA Certificate) | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFI | 3 | Bertrand Sylvain | [6 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760005 | Inspection Release Note for Plates | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFI | 3 | Bertrand Sylvain | [6 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760006 | Signed off Inspection & Test Plan for Beams |  |  |  | not received | 3 | [8 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-760007 | Signed off Inspection & Test Plan for Plates |  |  |  | not received | 3 | [8 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-770002 | NDT Operators list & Qualification for Plates | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFR | 2 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-770003 | UT Records for Beams | 0 | 2014-06-19 10:00 | 2014-10-10 10:00 | IFI | 3 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-770004 | NDT Operators list & Qualification for Beams | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFR | 2 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-770006 | Material Certificates for Plates | 0 | 2014-05-09 10:00 | 2014-10-10 10:00 | IFI | 3 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-770007 | Material Certificates for Beams | 0 | 2014-05-09 10:00 | 2014-10-10 10:00 | IFI | 3 | [7 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-790001 | Certificate of Conformity | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFI | 3 | Bertrand Sylvain | [6 empty] | Y
ARCELOR | STRUCTURAL STEEL | 884754 | SV05 | NG-EGN-20-SV05-790002 | Non conformity Reports | 0 | 2014-09-16 09:47 | 2014-09-23 09:47 | IFI | 3 | Bertrand Sylvain | [6 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700001 | Vendor Master Document List | 2 | 2014-06-16 15:32 | 2014-06-16 15:32 | AFC | 2 | Huvet Guillaume | 1-Approved without Comments | 2014-07-16 | 2 - Reviewed With Comments |  |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700002 | Manufacturing schedule | 2 | 2014-08-04 14:44 | 2014-08-28 10:10 | AFC | 2 | Huvet Guillaume | 1-Approved without Comments | [5 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700003 | Supplier Progress Report | 7 | 2014-10-03 16:49 |  | IFI | 3 | [7 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700004 | Project Quality Plan (including Project Organization Charts) | 2 | 2014-07-15 10:00 | 2014-07-16 10:00 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | [5 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700005 | Vendor Data Book (VDB) Index | 0 | 2014-05-09 01:00 | 2014-05-15 11:00 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-07-09 01:00 | 2 - Reviewed With Comments | 2014-07-24 01:00 |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-700006 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-730001 | General Arrangement Drawings | 1 | 2014-08-05 16:56 | 2014-08-06 10:00 | AFC | 2 | Bchir Reda | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750001 | Manufacturing Procedure Specification | 3 | 2014-06-11 10:00 | 2014-05-22 11:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-06-12 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750002 | Ultrasonic Examination Procedure | 2 | 2014-06-11 10:00 | 2014-05-26 11:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-06-12 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750003 | Magnetic Particle Examination Procedure | 2 | 2014-06-11 10:00 | 2014-05-26 11:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-06-12 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750004 | FAI - Weld Overlay Procedure WPS/WPQR | 4 | 2014-08-04 10:10 | 2014-08-28 10:10 | IFA | 1 | Bchir Reda | 2-Approved with comments_Nextstatus IFA | 2014-09-23 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-08 |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750005 | CLD - Forging procedure - CANCELLED |  |  |  | not received | 1 | [8 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750006 | CLD - Heat treatment procedure - CANCELLED |  |  |  | not received | 1 | [8 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750007 | Hydrotest Procedure | 0 | 2014-06-16 15:32 | 2014-06-16 15:32 | IFR | 1 | Bchir Reda | 3-Rejected_Nextstatus IFR | 2014-07-23 01:00 | 3 - Rejected | 2014-08-07 01:00 |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750008 | CLD - FAI - NDT procedure - CANCELLED |  |  |  | not received | 1 | [8 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750009 | CLD - WPS/PQR for hydrotest preparation - CANCELLED |  |  |  | not received | 2 | [8 empty] | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750010 | FAI - Weld Overlay NDE Testing Procedure | 4 | 2014-07-22 14:05 | 2014-07-22 11:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-08-25 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750011 | Packing, Handling Transportation, Storage and Preservation Procedure | 1 | 2014-05-26 15:00 | 2014-05-26 11:00 | AFC | 2 | Huvet Guillaume | 1-Approved without Comments | 2014-06-26 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-750012 | Traceabily Procedure (Ringmill and FAI supplies) | 1 | 2014-05-27 | 2014-05-26 11:00 | AFC | 2 | Vernouillet Philippe | 1-Approved without Comments | 2014-07-24 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-760001 | Inspection and Test Plan (ITP) | 3 | 2014-06-16 15:32 | 2014-06-16 15:32 | AFC | 1 | Vernouillet Philippe | 1-Approved without Comments | 2014-07-24 | 1 - Reviewed Without Comments |  | Y
RINGMILL | RBS | 886125 | SV06 | NG-EGN-21-SV06-760002 | FAI - Weld Overlay Inspection and Test Plan (ITP) | 2 | 2014-08-04 10:10 | 2014-08-28 10:10 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700001 | Vendor Master Document List | 1 | 2014-03-19 | 2014-03-19 | IFR | 2 | Bourquouquou Tarik | 1-Approved without Comments_Nextstatus AFC | 2014-05-28 01:00 | 2 - Reviewed With Comments | 2014-06-12 01:00 |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700002 | Monthly Progress Schedule | 7 | 2014-09-15 16:29 | 2014-09-18 16:29 | IFR | 2 | VERDIER Adrien | [6 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700003 | Procurement Plan | 1 | 2014-06-19 18:00 | 2014-06-25 07:54 | IFI | 3 | Bourquouquou Tarik | 2-Approved with comments_Nextstatus IFI | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700004 | Project Quality Plan | 3 | 2014-07-29 13:39 | 2014-07-31 13:39 | IFA | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus AFC | 2014-10-06 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700005 | Work Execution Schedule | 2 | 2014-05-16 | 2014-05-15 01:00 | IFR | 2 | Bourquouquou Tarik | 2-Approved with comments_Nextstatus AFC |  |  |  | Y |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700006 | Final Documentation - Preliminary Table of Content |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-700007 | Final Documentation |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-712001 | Design Report Including FEA | 3 | 2014-07-04 10:00 | 2014-09-18 18:00 | IFR | 2 | Bchir Reda | [6 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-730001 | General Arrangement Drawings | 3 | 2014-09-01 16:26 | 2014-09-02 16:26 | AFC | 2 | Bchir Reda | 1-Approved without Comments | 2014-10-14 | 2 - Reviewed With Comments | 2014-10-29 |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750001 | Traceability Procedure | 1 | 2014-05-03 | 2014-05-05 01:00 | AFC | 2 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750002 | WPQR, WPS |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750003 | RT Procedures | 3 | 2014-09-24 17:21 | 2014-09-24 17:21 | IFA | 1 |  | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750004 | Hydrostatic Testing Procedure | 2 | 2014-06-19 16:45 | 2014-06-20 16:45 | IFA | 1 | Bchir Reda | 1-Approved without Comments_Nextstatus AFC | 2014-07-30 | 1FC - Reviewed Without Comments but Comments on Form | 2014-08-14 |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750005 | Manufacturing Procedure Specification (MPS) | 2 | 2014-07-02 10:00 | 2014-07-02 10:00 | IFR | 1 | Bchir Reda | 2-Approved with comments_Nextstatus IFA | 2014-09-29 | 2 - Reviewed With Comments | 2014-10-14 |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750006 | SUP - Heat Treatment Procedure (SUPERSEDED BY NG-EGN-21-SV07-750005) |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750007 | Handling, Transportation, Storage and Preservation Manual | 0 | 2014-09-27 12:21 | 2014-09-27 12:21 | IFR | 2 | [7 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750008 | Welding Maps |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750009 | UT Procedures | 2 | 2014-08-04 10:00 | 2014-08-04 10:00 | IFA | 1 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus AFC | 2014-08-19 | 1FC - Reviewed Without Comments but Comments on Form | 2014-09-03 |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750010 | MT Procedure | 3 | 2014-09-24 17:21 | 2014-09-24 17:21 | IFA | 1 |  | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750011 | VT Procedure | 1 | 2014-04-05 | 2014-04-24 15:00 | IFA | 1 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus AFC | 2014-05-07 01:00 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-750012 | PT Procedures | 2 | 2014-05-08 17:00 | 2014-05-08 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-06-13 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-760001 | Project Quality Control Plan (ITP) for Tees | 2 | 2014-07-03 10:00 | 2014-07-03 10:00 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-760002 | Project Quality Control Plan (ITP) for Elbows | 2 | 2014-07-03 10:00 | 2014-07-03 10:00 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
BASSI LUIGI | Barred Tees, Elbows and Reducers | 893604 | SV07 | NG-EGN-21-SV07-760003 | Project Quality Control Plan (ITP) for Reducers | 2 | 2014-07-03 10:00 | 2014-07-03 10:00 | IFR | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus IFA | [5 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700001 | VENDOR Master Document Register | 2 | 2014-07-02 13:00 | 2014-07-02 11:00 | AFC | 2 | Bourquouquou Tarik | 1-Approved without Comments | [5 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700002 | WORK Execution Schedule |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700003 | Monthly progress report including 4 weeks look ahead schedule | 1 | 2014-07-21 | 2014-07-21 10:00 | IFI | 3 | Bourquouquou Tarik | [6 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700004 | Project Quality Plan (Including WORK Organization Chart) | 2 | 2014-05-23 15:00 | 2014-05-23 11:00 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-06-18 | 1 - Reviewed Without Comments |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700005 | Vendor Data Book Index | 0 | 2014-04-17 01:00 | 2014-04-22 01:00 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-07-09 01:00 | 2 - Reviewed With Comments | 2014-07-24 01:00 |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-700007 | List of the Items of the Purchase Order |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750002 | NDT Procedure - Europe | 2 | 2014-05-08 | 2014-05-07 01:00 | IFR | 1 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus IFA | 2014-05-16 01:00 | 1 - Reviewed Without Comments | 2014-05-31 01:00 |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750003 | Destructive Test Procedure - Europe | 2 | 2014-06-27 12:15 | 2014-06-27 12:15 | IFA | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-08-22 | 2 - Reviewed With Comments | 2014-09-06 |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750004 | Traceability, marking, and identification procedure | 2 | 2014-05-16 | 2014-05-15 01:00 | AFC | 2 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750005 | Handling. transportation. storage and preservation procedure | 1 | 2014-04-01 | 2014-03-31 01:00 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-05-27 01:00 | 1 - Reviewed Without Comments |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750006 | NDT Procedure - Singapore | 1 | 2014-05-06 17:50 | 2014-05-06 01:00 | IFR | 1 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus IFA | 2014-05-16 01:00 | 1 - Reviewed Without Comments | 2014-05-31 01:00 |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750007 | Destructive Test Procedure - Singapore | 2 | 2014-07-30 15:59 | 2014-07-30 15:59 | AFC | 1 | MAS Jeremy | 1-Approved without Comments | 2014-08-26 | 1 - Reviewed Without Comments |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750008 | NDT procedure - Dubai | 3 | 2014-07-28 12:49 | 2014-07-28 12:49 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-750009 | Destructive Test Procedure - Dubai | 2 | 2014-09-16 10:20 | 2014-09-16 10:20 | IFA | 1 | Lambin Axel | [6 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760001 | Project Quality Control Plan(s) / ITP(s) | 4 | 2014-09-10 10:06 | 2014-09-10 10:06 | IFA | 1 | Desbois Louis | [6 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760003 | Visual & Dimensional Test Reports |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760004 | Inspection Release Notes |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760005 | Project Quality Control Plan(s) / ITP - Signed Off |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760006 | Project Quality Control Plan(s) / ITP(s) for revision 01 and VOR - Signed Off |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-760007 | Project Quality Control Plan(s) / ITP(s) for revision 01 and VOR | 0 | 2014-07-16 10:00 | 2014-07-16 10:00 | IFR | 1 | RAOUL Nicolas | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770001 | Final Material Certificates for batch 1 including certificates for additional tests |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770002 | Final Material Certificates for batch 2 including certificates for additional tests |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770003 | NDT Operators List & Qualifications - Europe |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770004 | NDT Operators List & Qualifications - Singapore |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770005 | NDT Operators List & Qualifications - Dubai |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770006 | NDT Reports - Europe |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770007 | NDT Reports - Singapore |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770008 | NDT Reports - Dubai |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-770009 | Final Material certificates for Revision 01 and VOR |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-790001 | Certificate of Conformity to the PO |  |  |  | not received | 0 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-790002 | Deviation Requests & Register |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Structural Steel | 899503 | SV08 | NG-EGN-21-SV08-790003 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700001 | Vendor Master Document List | 4 | 2014-08-31 14:49 | 2014-09-01 14:29 | AFC | 2 | GICQUEL Severine | 1-Approved without Comments | [5 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700002 | Work Execution Schedule | 2 | 2014-08-01 10:00 | 2014-08-04 01:00 | AFC | 2 | GICQUEL Severine | 2-Approved with comments_Nextstatus AFC | 2014-09-11 | 2 - Reviewed With Comments | 2014-09-26 |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700003 | Monthly Progress Report | 1 | 2014-05-14 | 2014-05-13 11:00 | IFR | 2 | GICQUEL Severine |  | 2014-06-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-24 |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700004 | VENDOR Data Book (VDB) Index | 0 | 2014-03-17 | 2014-03-18 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-07-09 01:00 | 2 - Reviewed With Comments | 2014-07-24 01:00 |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700005 | VENDOR Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-700006 | Project Quality Plan | 2 | 2014-06-16 09:56 | 2014-06-17 07:39 | AFC | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-07-11 01:00 | 1 - Reviewed Without Comments |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-730001 | General Arrangement Drawings | 2 | 2014-08-31 14:49 | 2014-09-01 14:29 | AFC | 1 | Bchir Reda | 1-Approved without Comments | [5 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750001 | Traceability and Marking Procedure | 2 | 2014-09-23 12:15 | 2014-09-24 12:15 | AFC | 1 | [7 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750002 | Manufacturing Procedure Specification | 3 | 2014-09-09 11:52 | 2014-09-11 11:52 | IFA | 1 | Bchir Reda | [6 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750003 | Ultrasonic Testing Procedure | 2 | 2014-04-29 | 2014-04-28 15:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-14 01:00 | 1 - Reviewed Without Comments |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750004 | Magnetic Particle Examination Procedure | 3 | 2014-06-03 | 2014-06-02 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-07-03 | 1FC - Reviewed Without Comments but Comments on Form |  |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750005 | Hydrotest Procedure including Calculation Notes | 2 | 2014-07-02 23:00 | 2014-07-03 11:00 | AFC | 2 | Bchir Reda | 2-Approved with comments_Nextstatus AFC | 2014-08-22 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-06 |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-750006 | Packing, Handling, Loading, Transportation, Storage and Preservation Procedure | 2 | 2014-06-30 11:00 | 2014-06-30 11:00 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-07-30 | 1 - Reviewed Without Comments |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-760001 | Inspection & Test Plan | 3 | 2014-09-23 12:15 | 2014-09-24 12:15 | AFC | 1 | [7 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-760002 | Material Certificates 3.2 + Traceability Sheet |  |  |  | not received | 0 | [8 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-770001 | NDT Records |  |  |  | not received | 0 | [8 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-770002 | NDT Operator List + Qualification | 2 | 2014-04-29 | 2014-04-28 15:00 | AFC | 2 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-14 01:00 | 1 - Reviewed Without Comments |  | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-770003 | Hydrotest Reports (including Calibration Certificates) |  |  |  | not received | 0 | [8 empty] | Y
VILMAR | Forged Anchors | 901777 | SV09 | NG-EGN-21-SV09-790001 | Certificate of Conformity to the PO |  |  |  | not received | 0 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700001 | Vendor Master Document List | 5 | 2014-09-02 17:09 | 2014-09-02 17:09 | AFC | 2 | GICQUEL Severine | 1-Approved without Comments | 2014-09-18 | 2 - Reviewed With Comments | 2014-10-03 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700002 | Work Execution Schedule | 3 | 2014-08-14 16:44 | 2014-08-14 16:44 | AFC | 2 | GICQUEL Severine |  | 2014-10-07 | 2 - Reviewed With Comments | 2014-10-22 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700003 | Sub-vendors List | 3 | 2014-08-07 17:36 | 2014-08-07 17:36 | AFC | 2 | GICQUEL Severine | 1-Approved without Comments | 2014-10-21 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700004 | Part List | 2 | 2014-07-21 17:55 | 2014-07-21 17:55 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700005 | Monthly Progress Report | 5 | 2014-08-11 17:49 | 2014-10-06 12:07 | IFI | 3 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700006 | Project QA Plan (including organization chart) | 1 | 2014-06-26 11:26 | 2014-06-26 11:26 | IFR | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus IFA | 2014-09-29 | 1 - Reviewed Without Comments | 2014-10-14 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700007 | Vendor Data Book Index | 1 | 2014-08-14 16:44 | 2014-08-14 16:44 | IFR | 1 | Quintas Stephane | 2-Approved with comments_Nextstatus IFA | 2014-10-02 | 2 - Reviewed With Comments | 2014-10-17 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700008 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-700009 | List of PO items | 0 | 2014-08-07 09:11 | 2014-08-13 09:11 | IFI | 3 | Breuskin Bruno | 1-Approved without Comments | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-711001 | FBC/FTC Design Report | 1 | 2014-07-01 11:39 | 2014-07-02 11:39 | IFR | 1 | Breuskin Bruno | 2-Approved with comments_Nextstatus IFA | 2014-08-18 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-02 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-712001 | Docking Report | 1 | 2014-06-27 11:39 | 2014-07-02 11:39 | IFR | 2 | Breuskin Bruno | 2-Approved with comments_Nextstatus AFC | 2014-08-08 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-23 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-712002 | Wetted Surface Area Report | 2 | 2014-09-25 08:49 | 2014-09-26 08:49 | IFR | 1 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-712003 | Failures Modes, Effects & Criticality Analysis | 2 | 2014-09-10 11:14 | 2014-09-10 11:14 | AFC | 2 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-721001 | Forging Specification | 4 | 2014-09-01 17:09 | 2014-09-02 17:09 | AFC | 1 | Lambin Axel | 1-Approved without Comments | 2014-10-13 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-721002 | Manufacturing Specification | 2 | 2014-09-02 11:13 | 2014-09-03 11:13 | IFA | 1 | Breuskin Bruno | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-721003 | Painting and coating specification | 1 | 2014-09-18 17:58 | 2014-09-18 17:58 | IFA | 1 | DEBAVELAERE Marc |  | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-730001 | FTC Production SHR General Arrangement Drawing | 2 | 2014-09-01 17:09 | 2014-09-02 17:09 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-730002 | FTC WI/GE SHR General Arrangement Drawing | 2 | 2014-09-01 17:09 | 2014-09-02 17:09 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-730003 | FBC Production / WI / GE SHR General Arrangement Drawing | 2 | 2014-09-01 17:09 | 2014-09-02 17:09 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-740001 | Connection sequence drawing | 2 | 2014-09-04 15:42 | 2014-09-08 15:42 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-740002 | Painting, Coating & Marking Drawing | 0 | 2014-07-21 11:20 | 2014-07-22 11:20 | IFR | 2 | Breuskin Bruno | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750001 | Riser manufacturing procedure specification (including forging procedure and heat treatment) | 2 | 2014-09-08 10:41 | 2014-09-08 10:41 | IFA | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750002 | Ring manufacturing procedure specification (including forging procedure and heat treatment) | 1 | 2014-05-23 17:59 | 2014-05-23 16:59 | IFA | 1 | Breuskin Bruno | 1-Approved without Comments_Nextstatus IFA | 2014-08-20 | 2 - Reviewed With Comments | 2014-09-04 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750003 | FAT LEC Procedure | 1 | 2014-09-15 13:49 | 2014-09-15 13:49 | IFA | 1 | Breuskin Bruno | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750004 | FAT FBC/FTC Procedure | 0 | 2014-05-27 17:56 | 2014-05-27 17:56 | IFR | 1 | Breuskin Bruno | 2-Approved with comments_Nextstatus IFA | 2014-07-23 | 2 - Reviewed With Comments | 2014-08-07 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750005 | Riser NDT Procedures | 2 | 2014-09-10 10:29 | 2014-09-11 10:29 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-10-02 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750006 | Ring NDT Procedures | 2 | 2014-08-11 18:10 | 2014-08-11 18:10 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-27 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750007 | Structure NDT Procedures | 2 | 2014-08-14 16:44 | 2014-08-14 16:44 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-09-01 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750008 | Painting & Coating Procedure | 0 | 2014-10-07 12:03 | 2014-10-08 12:03 | IFR | 1 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750009 | Welding Book | 2 | 2014-09-12 10:30 | 2014-09-15 10:30 | IFA | 1 | KUHN Vincent | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750010 | Cutting & Forming Procedure | 2 | 2014-09-02 11:13 | 2014-09-03 11:13 | AFC | 1 | Breuskin Bruno | 1-Approved without Comments | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750011 | Packing, Handling, Loading, Transportation, Storage and Preservation Procedure | 0 | 2014-09-05 17:29 | 2014-09-05 17:29 | IFR | 2 | Clement Arnaud | 2-Approved with comments_Nextstatus AFC | 2014-10-06 | 2 - Reviewed With Comments | 2014-10-21 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750012 | Dimensional Control Procedure | 0 | 2014-09-03 17:28 | 2014-09-03 19:28 | IFR | 1 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-10-01 | 3 - Rejected | 2014-10-16 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750013 | Traceability & Marking Procedure | 0 | 2014-09-08 15:42 | 2014-09-08 15:42 | IFR | 1 | Breuskin Bruno | 1-Approved without Comments_Nextstatus IFA | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750014 | Weld Consumable Storage and Handling Procedure | 2 | 2014-09-16 10:58 | 2014-09-16 10:58 | IFA | 1 | KUHN Vincent | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750015 | Weld Consumable Storage and Handling Procedure - Bottom shroud | 2 | 2014-09-03 11:13 | 2014-09-03 11:13 | IFA | 1 | KUHN Vincent | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750016 | Welding Book - Bottom Shroud | 2 | 2014-07-29 08:59 | 2014-09-01 08:59 | IFR | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | 2014-09-24 | 2 - Reviewed With Comments | 2014-10-09 |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750017 | Cutting & Forming Procedure - Bottom Shroud | 1 | 2014-06-27 10:59 | 2014-09-24 11:29 | IFA | 1 | Breuskin Bruno | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750018 | Structure NDT Procedures - Bottom Shroud | 2 | 2014-08-28 16:08 | 2014-10-09 17:57 | AFC | 1 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750019 | WPQR LHV/14/B/179 - WPS 27114/1 (AGR) | 0 | 2014-09-18 16:40 | 2014-09-18 17:58 | IFR | 2 | KUHN Vincent | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750020 | WPQR LHV/14/B/180 - WPS 27114/3 (AGR) | 0 | 2014-09-18 16:40 | 2014-09-18 17:58 | IFR | 2 | KUHN Vincent | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750021 | WPQR LVH/14/B/187 - WPS 27114/2-a & 27114/2-b (AGR) | 0 | 2014-10-09 17:57 | 2014-10-09 17:57 | IFR | 2 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750022 | WPQR LHV/14B/186 - WPS 27114/5 (AGR) | 0 | 2014-10-09 17:57 | 2014-10-09 17:57 | IFR | 2 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750023 | WPQR LHV/14/B/188 - WPS 27114/6 (AGR) | 0 | 2014-10-09 17:57 | 2014-10-09 17:57 | IFR | 2 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750024 | WPQR x - WPS x (AGR) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750025 | WPQR x - WPS x (AGR) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750026 | WPQR x - WPS x (AGR) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750027 | WPQR x - WPS x (AGR) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750028 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750029 | PQR W-2039 & PQR W-2040 / WPS 145251 F1B-P (AST) | 0 | 2014-09-23 17:39 | 2014-09-23 17:39 | IFR | 2 | KUHN Vincent | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750030 | PQR W-2041 & PQR W-2042 / WPS 145251 F1B-1 (AST) | 0 | 2014-09-23 17:39 | 2014-09-23 17:39 | IFR | 2 | KUHN Vincent | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750031 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750032 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750033 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750034 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750035 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-750036 | WPQR x - WPS x (AST) |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760001 | Project ITP | 3 | 2014-10-03 16:36 | 2014-10-06 16:36 | AFC | 1 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760002 | Riser Forging ITP | 2 | 2014-09-03 17:28 | 2014-09-03 19:28 | AFC | 1 | RAOUL Nicolas | 1-Approved without Comments | 2014-09-18 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760003 | Ring Forging ITP | 2 | 2014-09-03 17:28 | 2014-09-03 19:28 | AFC | 1 | RAOUL Nicolas | 1-Approved without Comments | 2014-09-18 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760004 | Structure ITP (Welding & Assembly) | 2 | 2014-09-19 13:40 | 2014-09-19 13:40 | IFA | 1 | RAOUL Nicolas | [6 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760005 | NDT Reports |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760006 | Painting Report |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760007 | FAT LEC Report |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760008 | FAT FBC/FTC Report |  |  |  | not received | 2 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760009 | Heat Treatment Report |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760010 | Dimensional Test Report |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760011 | Mechanical Test Report |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760012 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760013 | Painting & Coating ITP | 0 | 2014-10-06 12:03 | 2014-10-08 12:03 | IFR | 1 | [7 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-760014 | Structure ITP (Welding & Assembly) - Bottom shroud | 1 | 2014-09-05 16:43 | 2014-09-05 16:43 | IFA | 1 | RAOUL Nicolas | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-770001 | NDT Operators Qualification and List | 1 | 2014-09-01 17:09 | 2014-09-02 17:09 | AFC | 2 | Feuilly Nicolas | 1-Approved without Comments | 2014-09-29 | 1 - Reviewed Without Comments |  | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-770002 | Material Certificates 3.2 + Summary Sheet |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-780001 | Installation, operation and commissioning manuals (including Secondary locking system GA) |  |  |  | not received | 1 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-790002 | Deviation Requests and Register |  |  |  | not received | 3 | [8 empty] | Y
TECHLAM | Flexible Base and Top Connectors | 903858 | SV10 | NG-EGN-23-SV10-790003 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700001 | Vendor Master Document List | 3 | 2014-07-23 15:00 | 2014-07-23 11:00 | AFC | 2 | GICQUEL Severine | 2-Approved with comments_Nextstatus AFC | 2014-10-07 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-22 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700002 | Schedule | 1 | 2014-04-30 | 2014-05-05 01:00 | AFC | 2 | GICQUEL Severine | 2-Approved with comments_Nextstatus AFC | 2014-05-27 01:00 | 2 - Reviewed With Comments | 2014-06-11 01:00 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700003 | Progress Report | 5 | 2014-08-18 13:38 | 2014-08-22 13:38 | IFI | 3 | GICQUEL Severine | [6 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700005 | WORK Quality Assurance Plan (including organization chart) | 2 | 2014-08-15 13:34 | 2014-08-22 13:34 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | 2014-10-08 | 2 - Reviewed With Comments | 2014-10-23 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700006 | Vendor Data Book Index | 0 | 2014-08-14 15:48 | 2014-09-29 15:48 | IFR | 1 | [7 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700007 | Vendor Data Book (VDB) | 0 | 2014-08-14 15:48 | 2014-09-29 15:48 | IFR | 1 | [7 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-700008 | List of PO items |  |  |  | not received | 3 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750001 | Heat Treatment Procedure | 3 | 2014-06-18 09:58 | 2014-06-23 09:58 | AFC | 1 | Crabbe Marcus | 1-Approved without Comments | 2014-07-22 14:21 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750002 | Mechanical Test Procedure (Production padeyes) | 4 | 2014-10-06 12:56 | 2014-10-08 | AFC | 1 | [7 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750003 | Mechanical Test Procedure (Sacrificial padeyes) | 3 | 2014-08-11 15:40 | 2014-08-18 15:40 | AFC | 1 | Crabbe Marcus | 1-Approved without Comments | 2014-09-24 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750004 | Mechanical Test Procedure (WPQ Test Plates) | 3 | 2014-06-20 09:27 | 2014-06-26 09:27 | AFC | 1 | Crabbe Marcus | 1-Approved without Comments | 2014-07-25 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750005 | Traceability Procedure | 0 | 2014-03-13 | 2014-03-13 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750006 | Manufacturing Procedure Specification | 3 | 2014-08-15 15:40 | 2014-08-18 15:40 | AFC | 1 | Crabbe Marcus | 2-Approved with comments_Nextstatus AFC | 2014-09-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-09 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750007 | Dimensional and Weight Control Procedure | 2 | 2014-06-18 09:58 | 2014-06-23 09:58 | AFC | 1 | Crabbe Marcus | 1-Approved without Comments | 2014-07-25 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750008 | WPS - Casting repair | 2 | 2014-10-09 14:48 | 2014-10-10 16:28 | IFA | 1 | [7 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750009 | WPQ - Casting repair | 1 | 2014-05-26 01:00 | 2014-06-20 11:00 | IFA | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | 2014-08-20 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-04 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750010 | Visual & MPI procedure | 2 | 2014-04-24 | 2014-09-23 09:18 | IFA | 1 |  | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750011 | UT Procedure | 2 | 2014-05-08 14:00 | 2014-05-09 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-05-16 01:00 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750012 | Weighing Procedure | 3 | 2014-06-05 15:11 | 2014-06-12 15:11 | AFC | 1 | Crabbe Marcus | 1-Approved without Comments | 2014-09-24 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750013 | RT Procedure | 2 | 2014-05-26 15:00 | 2014-05-26 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-06-19 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-750014 | Packing, Preservation, Marking and Shipping Procedure | 1 | 2014-09-03 11:10 | 2014-09-05 11:10 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-10-06 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760001 | Inspection & Test Plan (Production padeyes) | 2 | 2014-04-24 | 2014-04-28 15:00 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760002 | Inspection & Test Plan (Sacrificial padeyes) | 2 | 2014-04-25 | 2014-04-28 15:00 | IFA | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760003 | Inspection & Test Plan (WPQ Test Plates) | 2 | 2014-04-30 | 2014-04-29 11:00 | IFA | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760004 | MPI Reports |  |  |  | not received | 3 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760005 | UT Reports |  |  |  | not received | 3 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760006 | RT Reports |  |  |  | not received | 3 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760007 | Heat Treatment Report |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760008 | Dimensional Test Report |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760009 | Hardness Test Report |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760010 | Weighing Test Report |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-760011 | Inspection Release Note |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-770001 | NDE Operators Qualifications | 3 | 2014-06-18 09:58 | 2014-06-23 09:58 | AFC | 2 | Feuilly Nicolas | 1-Approved without Comments | 2014-07-18 01:00 | 1 - Reviewed Without Comments |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-770002 | Welder Qualifications | 1 | 2014-06-09 15:11 | 2014-06-12 15:11 | IFI | 3 | KUHN Vincent | 2-Approved with comments_Nextstatus IFI | 2014-07-04 14:39 | 2 - Reviewed With Comments | 2014-07-19 14:39 |  | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-770003 | Material Certificates 3.2 + Summary Sheet |  |  |  | not received | 0 | [8 empty] | Y
VULCAN SFM | Supply of Casting for Cast Padeyes | 904033 | SV11 | NG-EGN-26-SV11-790001 | Certificate of Conformity |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700001 | Vendor Master Document List (VMDL) | 4 | 2014-06-13 10:35 | 2014-06-13 10:35 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-07-03 | 1FC - Reviewed Without Comments but Comments on Form |  |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700002 | Work Execution Schedule | 1 | 2014-03-17 16:30 | 2014-04-17 12:00 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | 2014-05-16 01:00 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700003 | Project Quality Plan | 1 | 2014-07-02 09:50 | 2014-07-07 09:50 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700004 | Vendor Data Book (VDB) Index |  |  |  | not received | 1 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700005 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700006 | List of subvendors | 1 | 2014-04-10 | 2014-04-10 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | [5 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700007 | Monthly Report (including HSE report) | 6 | 2014-10-01 09:58 |  | IFR | 2 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-700008 | List of items of the Purchase Order | 1 | 2014-05-19 10:48 | 2014-06-03 10:48 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | 2014-07-01 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-730001 | Drawings | 3 | 2014-07-10 11:58 | 2014-07-10 11:58 | AFC | 2 | Lambin Axel | 1-Approved without Comments | [5 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750001 | Plate Manufacturing Procedure Specification | 2 | 2014-06-17 09:07 | 2014-06-17 09:07 | IFA | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-09-25 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-10 |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750002 | Plate NDT UT Procedure | 2 | 2014-05-12 10:46 | 2014-05-12 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-06-02 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750003 | Domes manufacturing procedure specification | 3 | 2014-06-16 15:34 | 2014-10-01 10:00 | IFA | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750004 | Dimensional and weight control procedure | 2 | 2014-07-08 15:17 | 2014-07-08 15:17 | AFC | 2 | Lambin Axel | 1-Approved without Comments_Nextstatus IFA | 2014-09-16 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750007 | WPS | 4 | 2014-10-09 16:49 | 2014-10-09 16:49 | IFA | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750008 | WPQR | 5 | 2014-10-09 16:49 | 2014-10-09 16:49 | IFA | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750009 | UT procedure for domes | 5 | 2014-07-25 16:28 | 2014-09-29 11:01 | AFC | 1 |  | 1-Approved without Comments | [5 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750010 | RT procedure for domes | 4 | 2014-08-05 13:03 | 2014-10-01 10:00 | AFC | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750011 | MPI procedure for domes | 3 | 2014-07-25 16:28 | 2014-08-28 16:28 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-09-16 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750012 | Marking and Packing Procedure | 2 | 2014-07-04 07:03 | 2014-07-15 07:03 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-09-18 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750013 | Heat treatment procedure | 3 | 2014-06-05 12:44 | 2014-10-01 12:00 | AFC | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750015 | Handling & Storage Procedure | 1 | 2014-09-22 11:05 | 2014-09-22 11:05 | AFC | 2 | Clement Arnaud | [6 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750016 | Visual Inspection Procedure | 3 | 2014-07-10 07:03 | 2014-07-10 11:58 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-750017 | Material Traceability Procedure | 1 | 2014-10-03 09:05 | 2014-10-03 09:05 | IFR | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760001 | Plate Inspection and Test Plan | 4 | 2014-08-01 15:10 | 2014-10-07 09:28 | AFC | 1 | [7 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760002 | Plates UT Report |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760003 | ITP for Standard Domes | 4 | 2014-08-01 15:10 | 2014-08-04 13:25 | AFC | 1 | WISEMAN Paul | 1-Approved without Comments | 2014-09-10 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760004 | ITP for sacrificial domes | 4 | 2014-08-01 08:58 | 2014-09-11 08:58 | AFC | 1 | WISEMAN Paul |  | 2014-10-09 | 1 - Reviewed Without Comments | 2014-10-24 | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760005 | ITP for domes with patches | 4 | 2014-08-01 15:10 | 2014-08-04 13:25 | AFC | 1 | WISEMAN Paul | 1-Approved without Comments | 2014-09-10 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760006 | UT report for domes |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760007 | RT report for domes |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760008 | MPI report for domes |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760009 | Dimensional and weight control report for domes |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760010 | Inspection Release Note |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760011 | ITP for Reinforcement Pad | 3 | 2014-07-04 12:10 | 2014-07-14 12:10 | AFC | 1 | WISEMAN Paul | 1-Approved without Comments | 2014-08-26 | 1 - Reviewed Without Comments |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-760012 | Signed ITPs |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-770001 | Material certificates 3.2 for plates |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-770002 | Material certificates 3.2 for domes |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-770003 | NDT operator qualification | 0 | 2014-03-20 | 2014-03-20 | IFR | 1 | Bertrand Sylvain | 2-Approved with comments_Nextstatus IFA | 2014-05-15 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-05-30 01:00 |  | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-770004 | Welding Record |  |  |  | not received | 1 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-770005 | Welder List - Welder Qualification Records | 3 | 2014-09-08 08:37 | 2014-09-08 08:37 | IFA | 1 | WISEMAN Paul | [6 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-790001 | Certificate of Conformity to the PO |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-790002 | Non conformity Reports |  |  |  | not received | 0 | [8 empty] | Y
VOESTALPINE | SHR Buoyancy Tanks Domes | 907757 | SV12 | NG-EGN-23-SV12-790003 | Deviation Requests |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700001 | Vendor Master Document List | 2 | 2014-06-18 10:12 | 2014-06-23 10:12 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700002 | Work Execution Schedule | 1 | 2014-07-15 07:44 | 2014-07-16 07:44 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700003 | Project Quality Plan (including Project Organization Charts) | 2 | 2014-07-16 16:05 | 2014-07-17 16:05 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-09-29 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700004 | Vendor Data Book (VDB) Index | 1 | 2014-09-18 12:40 | 2014-09-24 12:40 | IFR | 1 | Quintas Stephane | [6 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700005 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700006 | Monthly Report (including HSE report) | 5 | 2014-09-30 15:31 | 2014-10-03 12:00 | IFR | 2 | [7 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700007 | List of items of the Purchase Order | 1 | 2014-06-18 15:45 | 2014-06-23 10:12 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | 2014-07-25 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-700008 | List of Subvendors | 1 | 2014-05-28 14:54 | 2014-05-28 14:54 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-06-12 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-730001 | General Arrangement Drawings of Induction Bends and Test Rings | 2 | 2014-09-04 16:17 | 2014-09-04 16:17 | AFC | 2 | Bourry Anthony | [6 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750001 | Induction Bending Procedure | 2 | 2014-06-19 15:45 | 2014-06-20 15:45 | IFA | 1 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-10-10 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750002 | Heat Treatment Procedure | 2 | 2014-06-19 15:45 | 2014-06-20 15:45 | IFA | 1 | Bourry Anthony | 2-Approved with comments_Nextstatus IFA | 2014-10-10 | 2 - Reviewed With Comments | 2014-10-25 |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750003 | Magnetic Particle Examination Procedure | 3 | 2014-07-18 09:54 | 2014-07-18 09:54 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750004 | Visual Examination Procedure | 3 | 2014-07-18 09:54 | 2014-07-18 09:54 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750005 | Ultrasonic Examination Procedure | 3 | 2014-07-18 09:54 | 2014-07-18 09:54 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750006 | Hardness Measurement Procedure | 2 | 2014-06-27 10:58 | 2014-07-01 15:58 | IFA | 1 | Bourry Anthony | 2-Approved with comments_Nextstatus IFA | 2014-09-24 | 2 - Reviewed With Comments | 2014-10-09 |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750007 | Thickness Measurement Procedure | 2 | 2014-06-20 15:45 | 2014-06-20 15:45 | IFA | 1 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-09-24 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750008 | Corrosion Test Procedure (HIC) | 2 | 2014-06-25 09:16 | 2014-06-26 09:16 | AFC | 1 | Bourry Anthony | 1-Approved without Comments | 2014-09-19 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750009 | Corrosion Test Procedure (SSCC) | 2 | 2014-06-25 09:16 | 2014-06-26 09:16 | AFC | 1 | Bourry Anthony | 1-Approved without Comments | 2014-09-19 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750010 | Dimensional Control Procedure | 2 | 2014-06-20 15:45 | 2014-06-20 15:45 | AFC | 2 | Bourry Anthony | 2-Approved with comments_Nextstatus AFC | 2014-09-24 | 2 - Reviewed With Comments | 2014-10-09 |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750011 | Handling, Marking, Packing & Transportation Procedure for bends | 1 | 2014-07-23 15:56 | 2014-07-23 15:56 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-09-01 | 1 - Reviewed Without Comments |  | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-750012 | Traceability and Equipment Identification Procedure | 1 | 2014-05-08 10:56 | 2014-05-19 12:53 | AFC | 2 | Bellamoli Cedric | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760001 | Inspection and Test Plan (ITP) for Hot Induction Bends | 2 | 2014-06-19 15:45 | 2014-06-20 15:45 | AFC | 1 | Vernouillet Philippe | 1-Approved without Comments | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760002 | Production Dimensional Control Report | 0 | 2014-10-06 16:04 | 2014-10-09 | IFR | 0 | [7 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760003 | Inspection Release Note |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760004 | Production Heat Treatment Report | 0 | 2014-10-06 16:04 | 2014-10-09 | IFR | 0 | [7 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760005 | Production Induction Bending Report | 0 | 2014-10-06 16:04 | 2014-10-09 | IFR | 0 | [7 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760006 | Production NDT and Destructive Tests Report | 0 | 2014-10-06 16:04 | 2014-10-09 | IFR | 0 | [7 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760007 | MPQT report | 0 | 2014-07-17 10:15 | 2014-07-28 10:15 | IFR | 2 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-760008 | Signed off Inspection and Test Plan |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-770001 | NDT Operator Qualifications | 0 | 2014-04-04 | 2014-04-09 | IFR | 1 | Bellamoli Cedric | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-770002 | Material Certifcates 3.2 |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-790001 | Certificate of Conformity to the PO |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-790002 | Non Conformity Reports |  |  |  | not received | 0 | [8 empty] | Y
COFELY FABRICOM | CS Induction Bends | 916859 | SV13 | NG-EGN-21-SV13-790003 | Deviation Requests |  |  |  | not received | 0 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700001 | Vendor Master Document List | 2 | 2014-06-17 15:18 | 2014-08-04 10:00 | AFC | 2 | GICQUEL Severine | 2-Approved with comments_Nextstatus AFC | 2014-09-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-24 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700002 | List of sub-vendors | 2 | 2014-09-26 09:43 | 2014-10-08 09:43 | IFI | 3 | [7 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700003 | Work Execution Schedule | 2 | 2014-08-01 15:18 | 2014-08-04 10:00 | IFR | 2 | GICQUEL Severine | 1-Approved without Comments_Nextstatus AFC | 2014-09-08 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-23 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700004 | Monthly Progress Report | 1 | 2014-09-15 17:44 | 2014-09-21 17:44 | IFI | 3 | GICQUEL Severine | [6 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700005 | Project Quality Plan (including Project Organization Charts) | 1 | 2014-06-23 11:00 | 2014-06-23 10:00 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | 2014-09-29 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-14 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700006 | List of PO items |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700007 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-700008 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750001 | Traceability Procedure | 0 | 2014-05-12 01:00 | 2014-05-20 11:00 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750002 | Manufacturing Procedure Specification | 3 | 2014-09-03 16:04 | 2014-09-05 16:04 | IFA | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750003 | Dimensional and Weight Control Procedure |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750004 | Welding Book (including WPS) | 0 | 2014-07-09 11:00 | 2014-07-09 11:00 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-07-30 | 3FC - Rejected and Comments on Form | 2014-08-14 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750005 | Welding Qualification Plan (including WQPp) | 4 | 2014-10-02 09:43 | 2014-10-08 09:43 | IFA | 1 | [7 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750006 | WPQ Records |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750007 | UT Procedure | 3 | 2014-09-22 16:34 | 2014-10-08 16:34 | AFC | 1 | [7 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750008 | MT Procedure | 2 | 2014-07-29 11:00 | 2014-08-05 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750009 | RT Procedure (for WPQT) |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750010 | Hardness Test Procedure | 0 | 2014-08-01 10:00 | 2014-08-04 10:00 | IFR | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | 2014-09-08 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-23 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750011 | Visual Procedure | 2 | 2014-07-29 11:00 | 2014-08-05 11:00 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750012 | Welding Consumable Handling and Storage Procedure |  |  |  | not received | 1 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750013 | Forming Procedure | 0 | 2014-08-20 08:18 | 2014-08-22 08:18 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-09-15 | 3FC - Rejected and Comments on Form | 2014-09-30 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750014 | Packing, Preservation, Marking and Shipping Procedure |  |  |  | not received | 2 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750015 | Transportation Drawings |  |  |  | not received | 2 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-750016 | PT Procedure | 0 | 2014-07-21 10:00 | 2014-07-23 10:00 | IFR | 1 | Feuilly Nicolas | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760001 | Inspection & Test Plan for Production | 1 | 2014-07-11 18:46 | 2014-07-11 18:46 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760002 | Inspection & Test Plan for Qualification (ITP) | 3 | 2014-09-18 09:43 | 2014-10-08 09:43 | IFA | 1 | [7 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760003 | UT Reports |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760004 | MT Reports |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760005 | Hardness Test Reports |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760006 | Visual Reports |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760007 | Dimensional and Weight Control Reports |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-760008 | Inspection Release Note |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-770001 | NDT Operators List and Qualifications | 1 | 2014-06-17 15:18 | 2014-06-23 15:18 | AFC | 2 | Feuilly Nicolas | 1-Approved without Comments | 2014-07-18 | 1 - Reviewed Without Comments |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-770002 | Welder Qualifications | 1 | 2014-06-20 10:00 | 2014-07-03 | IFR | 2 | KUHN Vincent | 2-Approved with comments_Nextstatus AFC | 2014-08-14 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-29 |  | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-770003 | Material Certificates 3.2 (including Traceability Sheet) |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-790002 | Deviation Request Register |  |  |  | not received | 3 | [8 empty] | Y
EIFFAGE | Padeyes Assembly | 927991 | SV14 | NG-EGN-26-SV14-790003 | Clarification Request Register |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700001 | VENDOR Master Document List | 1 | 2014-06-30 11:00 | 2014-06-30 11:00 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-07-25 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700002 | WORK Execution Schedule | 1 | 2014-08-01 11:00 | 2014-08-01 11:00 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | 2014-09-18 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700003 | Project Quality Plan (including Project Organization Charts) | 1 | 2014-07-08 11:00 | 2014-07-08 11:00 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700004 | List of Subvendors | 1 | 2014-06-24 19:20 | 2014-06-24 19:20 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-08-01 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700005 | Vendor Data Book Index | 0 | 2014-09-24 18:55 | 2014-09-24 18:55 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700007 | List of items of the Purchase Order | 0 | 2014-05-19 01:00 | 2014-05-19 11:00 | IFI | 3 | BOIS Benjamin | 2-Approved with comments_Nextstatus IFI | 2014-09-23 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-08 |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-700008 | Monthly Report | 0 | 2014-09-24 19:49 | 2014-09-24 19:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-750001 | Magnetic Particle Examination Procedure | 2 | 2014-07-28 10:48 | 2014-07-30 10:48 | IFA | 1 | Feuilly Nicolas | 2-Approved with comments_Nextstatus IFA | 2014-09-23 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-08 |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-750002 | Ultrasonic Testing Procedure | 3 | 2014-09-22 19:17 | 2014-09-23 16:59 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-750003 | Hydrotesting procedure | 1 | 2014-07-08 11:00 | 2014-07-30 11:00 | IFA | 1 | Lambin Axel | 2-Approved with comments_Nextstatus IFA | 2014-10-13 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-28 |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-750004 | Handling, Marking, Packing & Transportation Procedure | 1 | 2014-06-30 11:00 | 2014-07-01 11:00 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-07-30 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760001 | Inspection and Test Plan | 2 | 2014-07-01 15:21 | 2014-07-02 10:00 | AFC | 1 | WISEMAN Paul | 1-Approved without Comments | 2014-07-25 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760002 | Ultrasonic Testing Report | 0 | 2014-08-28 20:18 | 2014-09-04 20:18 | IFI | 3 | WISEMAN Paul | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760003 | Magnetic Particle Examination Report | 0 | 2014-08-27 20:18 | 2014-09-04 20:18 | IFI | 3 | WISEMAN Paul | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760004 | Hydrotesting Report | 0 | 2014-08-28 20:18 | 2014-09-04 20:18 | IFI | 3 | WISEMAN Paul | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760005 | Inspection Release Note and TPA Completion Certificate | 0 | 2014-09-22 16:53 | 2014-09-23 16:53 | IFI | 3 | WISEMAN Paul | [6 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-760006 | Signed off Inspection and Test Plan | 0 | 2014-08-28 20:18 | 2014-09-04 20:18 | IFI | 3 | WISEMAN Paul | [6 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-770001 | NDT Operator List and Qualifications | 1 | 2014-08-28 20:18 | 2014-09-04 20:18 | IFR | 2 | WISEMAN Paul | [6 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-770002 | Material Certificates 3.1 and 3.2 (additional testing) | 0 | 2014-08-28 20:18 | 2014-09-04 20:18 | IFI | 3 | WISEMAN Paul | [6 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-790001 | Certificate of Conformity to the PO | 0 | 2014-09-22 16:53 | 2014-09-23 16:53 | IFI | 3 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-790002 | Non Conformity Reports |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | 2” piping | 930105 | SV15 | NG-EGN-22-SV15-790003 | Deviation Requests |  |  |  | not received | 0 | [8 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700001 | Vendor Master Document List | 1 | 2014-07-02 10:00 | 2014-07-02 10:00 | AFC | 2 | Huvet Guillaume | 1-Approved without Comments | 2014-09-08 | 2FC - Reviewed With Comments and Comments on Form |  |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700002 | Manufacturing schedule | 1 | 2014-06-23 14:09 | 2014-06-27 14:09 | AFC | 2 | Huvet Guillaume | 1-Approved without Comments | 2014-09-15 | 1 - Reviewed Without Comments |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700003 | Supplier Progress Report | 2 | 2014-08-04 15:32 | 2014-08-06 15:32 | IFI | 3 | Huvet Guillaume | [6 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700004 | Project Quality Plan (including Project Organization Charts) | 1 | 2014-05-14 01:00 | 2014-09-26 14:36 | AFC | 2 | [7 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700005 | Vendor Data Book Index | 0 | 2014-06-18 14:59 | 2014-06-18 14:59 | IFR | 1 | Quintas Stephane | 3-Rejected_Nextstatus IFR | 2014-07-09 01:00 | 2 - Reviewed With Comments | 2014-07-24 01:00 |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-730001 | General Arrangement Drawings |  |  |  | not received | 2 | [8 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750001 | Manufacturing Procedure Specification (including forging and heat treatment) | 1 | 2014-07-08 11:00 | 2014-07-08 11:00 | IFA | 1 | Bchir Reda | 1-Approved without Comments_Nextstatus AFC | 2014-08-07 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-22 |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750002 | Traceability Procedure | 1 | 2014-08-04 15:32 | 2014-08-06 15:32 | AFC | 2 | Vernouillet Philippe | 1-Approved without Comments | [5 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750003 | Ultrasonic Testing Procedure | 2 | 2014-08-04 16:00 | 2014-08-07 16:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | [5 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750004 | Magnetic Particle Examination Procedure | 2 | 2014-07-21 14:34 | 2014-07-21 10:00 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750005 | Visual and Dimensional Control Procedure | 2 | 2014-08-04 15:32 | 2014-08-06 15:32 | AFC | 1 | Bchir Reda | 1-Approved without Comments | 2014-08-20 | 1 - Reviewed Without Comments |  | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750006 | Packing, Handling, Transportation, Storage and Preservation Procedure | 2 | 2014-09-22 09:34 | 2014-09-24 09:34 | AFC | 2 | [7 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-750007 | Production Bulkhead - Manufacturing Procedure Specification (MPS) | 1 | 2014-10-03 17:00 | 2014-10-06 17:00 | IFA | 1 | [7 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-760001 | Inspection and Test Plan | 2 | 2014-08-04 16:00 | 2014-08-07 16:00 | AFC | 1 | Vernouillet Philippe | 1-Approved without Comments | [5 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-760002 | Production Bulkhead - Inspection and Test Plan (ITP) | 2 | 2014-09-22 09:34 | 2014-09-24 09:34 | IFA | 1 | [7 empty] | Y
RINGMILL | Tapered Joints | 929968 | SV16 | NG-EGN-23-SV16-770001 | NDT Operators Qualification (VT, UT, MPI) | 1 | 2014-08-05 15:32 | 2014-08-06 15:32 | AFC | 2 | Bchir Reda | 1-Approved without Comments | 2014-08-20 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700001 | Vendor Master Document List | 1 | 2014-07-03 11:00 | 2014-07-03 11:00 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-08-05 01:00 | 1FC - Reviewed Without Comments but Comments on Form | 2014-08-20 01:00 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700002 | Work Execution Schedule | 1 | 2014-10-09 22:39 | 2014-10-11 22:39 | IFI | 3 | [7 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700003 | Project Quality Plan (including Project Organization Charts) | 1 | 2014-07-14 10:00 | 2014-07-11 11:00 | IFR | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus AFC | 2014-10-08 | 3FC - Rejected and Comments on Form | 2014-10-23 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700004 | List of Subvendors | 1 | 2014-07-11 11:00 | 2014-07-11 11:00 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | 2014-09-17 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700005 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700007 | List of items of the Purchase Order | 0 | 2014-05-26 01:00 | 2014-05-26 11:00 | IFI | 3 | BOIS Benjamin | 1-Approved without Comments | 2014-06-13 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-700008 | Monthly Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750001 | EBK - Manufacturing Procedure Specification for Structural Welded Tubulars (including mechanical tests) | 2 | 2014-07-22 10:00 | 2014-10-01 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750002 | EBK - Magnetic Particle Examination Procedure for welded tubulars | 3 | 2014-09-17 12:14 | 2014-09-17 12:14 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750003 | EBK - Ultrasonic Testing Procedure for welded tubulars | 2 | 2014-07-30 21:24 | 2014-07-30 21:24 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750004 | EBK - Radiographic Testing Procedure for Welded Tubulars | 2 | 2014-07-30 21:24 | 2014-07-30 21:24 | AFC | 1 | Feuilly Nicolas | 1-Approved without Comments | 2014-08-19 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750005 | EBK - Welding Procedure Specification (including Welding Map) | 1 | 2014-07-29 11:10 | 2014-07-30 11:10 | IFR | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | 2014-10-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-24 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750006 | EBK - Welding Procedure Qualification Record | 1 | 2014-07-30 21:24 | 2014-07-30 21:24 | IFR | 1 | KUHN Vincent | 2-Approved with comments_Nextstatus IFA | 2014-10-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-24 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750007 | EBK - Handling & Transportation Procedure | 0 | 2014-08-08 13:14 | 2014-08-08 13:14 | IFR | 2 | Clement Arnaud | 2-Approved with comments_Nextstatus AFC | 2014-09-17 | 2 - Reviewed With Comments | 2014-10-02 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750008 | EBK - Material Marking and Traceability Procedure | 0 | 2014-06-02 01:00 | 2014-06-02 11:00 | IFR | 1 | BOIS Benjamin | 1-Approved without Comments_Nextstatus IFA | 2014-10-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-24 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-750009 | EBK - Dimensional Control Procedure for Welded Tubulars | 2 | 2014-09-17 12:14 | 2014-09-17 12:14 | AFC | 2 | Lambin Axel | 1-Approved without Comments | 2014-10-13 | 2 - Reviewed With Comments |  |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760001 | EBK - Inspection and Test Plan for Welded Tubulars | 2 | 2014-07-18 11:00 | 2014-10-01 | IFR | 1 |  | 2-Approved with comments_Nextstatus IFA | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760002 | EBK - Magnetic Particle Examination Report for Tubulars |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760003 | EBK - Ultrasonic Testing Report for Tubulars |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760004 | EBK - Radiographic Testing Record for Tubulars |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760005 | EBK - Dimensional Control Report for Tubulars (including PO item 5) |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760006 | EBK - Inspection and Test Plan for Welded Tubulars - As Built/Signed |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-760007 | Inspection Release Note and TPA Completion Certificate |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-770001 | EBK - NDT Operators List and Qualifications for Tubulars | 1 | 2014-07-03 11:00 | 2014-07-03 11:00 | AFC | 1 | WISEMAN Paul | 1-Approved without Comments | 2014-07-24 | 1 - Reviewed Without Comments |  | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-770002 | VA - Material Certificates 3.1 for Plates (including UT report and qualifications) |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-770003 | EBK - Material Certificates 3.2 for Welded Tubulars |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-770004 | EBK - Welder List - Welder Qualification Records | 1 | 2014-09-17 12:14 | 2014-09-17 12:14 | IFA | 1 | KUHN Vincent | [6 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-770005 | EBK - Welding Record |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-790001 | Certificate of Conformity to the PO |  |  |  | not received | 0 | [8 empty] | Y
PROJECT MATERIALS | Main Steel Tubular | 934277 | SV17 | NG-EGN-23-SV17-790002 | Non Conformity Reports and Deviation Requests |  |  |  | not received | 0 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700001 | Vendor Master Document List | 0 | 2014-06-03 10:00 | 2014-06-11 10:00 | IFR | 2 | Bourquouquou Tarik | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700002 | Monthly Progress Schedule |  |  |  | not received | 2 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700003 | Procurement Plan |  |  |  | not received | 3 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700004 | Project Quality Plan | 0 | 2014-05-28 10:00 | 2014-06-11 10:00 | IFI | 3 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus IFI | 2014-07-08 01:00 | 3 - Rejected | 2014-07-23 01:00 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700005 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-730001 | General Arrangement Drawings | 1 | 2014-10-02 15:05 | 2014-10-03 15:08 | AFC | 2 | [7 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750001 | Traceability Procedure for Bends | 0 | 2014-05-23 10:00 | 2014-06-11 10:00 | IFR | 2 | Vernouillet Philippe | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750002 | Traceability Procedure for mother Pipes | 0 | 2014-08-11 16:43 | 2014-08-20 16:43 | IFR | 2 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750003 | NDT Procedure for Bends | 2 | 2014-09-01 15:45 | 2014-09-01 15:45 | AFC | 1 | MONNIER Alban | 1-Approved without Comments | 2014-09-23 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750004 | NDT Procedure for Pipes | 0 | 2014-08-14 16:16 | 2014-08-22 16:16 | IFR | 1 | MONNIER Alban | 2-Approved with comments_Nextstatus IFA | 2014-09-23 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-08 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750005 | Manufacturing Procedure Specification for Mother Pipes | 1 | 2014-08-11 11:03 | 2014-08-20 16:43 | IFA | 1 | Bourry Anthony | 2-Approved with comments_Nextstatus IFA | 2014-09-10 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-25 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750006 | Manufacturing Procedure Specification for Bends (including Dimensional Procedure for bends) | 2 | 2014-09-15 15:08 | 2014-10-03 15:08 | IFA | 1 | [7 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750007 | Hydrostatic Testing Procedure for Mother Pipes | 1 | 2014-08-06 12:42 | 2014-08-20 12:42 | IFA | 1 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-09-17 | 1FC - Reviewed Without Comments but Comments on Form | 2014-10-02 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750008 | Heat Treatment Procedure for Bends | 1 | 2014-08-04 17:25 | 2014-08-25 17:25 | IFA | 1 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-09-17 | 2 - Reviewed With Comments | 2014-10-02 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750009 | Pickling and Passivation Procedure for Mother Pipes | 0 | 2014-08-11 16:43 | 2014-08-20 16:43 | IFR | 2 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-09-11 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-26 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750010 | Pickling and Passivation Procedure for Bends | 0 | 2014-09-04 14:45 | 2014-09-05 14:45 | IFR | 2 | Bourry Anthony | 1-Approved without Comments_Nextstatus AFC | 2014-10-13 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750011 | Handling, Transportation, Storage and Preservation Manual | 0 | 2014-09-04 14:45 | 2014-09-05 14:45 | IFR | 2 | Clement Arnaud | 3-Rejected_Nextstatus IFR | 2014-10-10 | 3 - Rejected | 2014-10-25 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750012 | Visual Procedure for Bends | 2 | 2014-09-10 11:56 | 2014-09-10 11:56 | AFC | 1 | Bourry Anthony | 1-Approved without Comments | [5 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750013 | Procedure for Wall Thickness Measurement | 1 | 2014-08-04 10:29 | 2014-08-20 12:42 | AFC | 2 | Bourry Anthony | 1-Approved without Comments | 2014-09-17 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750014 | Procedure for Manual Hardness Examination | 1 | 2014-07-23 10:29 | 2014-08-20 12:42 | AFC | 2 | Bourry Anthony | 1-Approved without Comments | 2014-09-17 | 1 - Reviewed Without Comments |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750015 | Procedure for Ferrite Determination | 1 | 2014-08-04 10:29 | 2014-08-20 12:42 | IFR | 2 | Bourry Anthony | 3-Rejected_Nextstatus IFR | 2014-09-15 | 3FC - Rejected and Comments on Form | 2014-09-30 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-750016 | Procedure for Pigging (Drift) Test of Bends | 1 | 2014-08-04 10:29 | 2014-08-20 12:42 | AFC | 2 | Bourry Anthony | 2-Approved with comments_Nextstatus AFC | 2014-09-17 | 2 - Reviewed With Comments | 2014-10-02 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-760001 | Inspection and Test Plan (ITP) for Mother Pipes | 0 | 2014-07-25 16:05 | 2014-09-08 16:05 | IFR | 1 | Vernouillet Philippe |  | 2014-10-10 | 2 - Reviewed With Comments | 2014-10-25 |  | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-760002 | Inspection and Test Plan (ITP) for Bends | 1 | 2014-09-15 17:29 | 2014-09-17 17:29 | IFR | 1 | Vernouillet Philippe | [6 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-760003 | MPQT Report for Mother Pipes |  |  |  | not received | 2 | [8 empty] | Y
BASSI LUIGI | Supply of Duplex Hot Induction Bends | 934363 | SV18 | NG-EGN-23-SV18-760004 | MPQT Report for Bends |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700001 | Vendor Master Document List | 1 | 2014-09-11 01:47 | 2014-09-12 01:47 | AFC | 2 | BOIS Benjamin | [6 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700002 | Project Schedule | 1 | 2014-07-01 23:41 | 2014-10-30 00:15 | IFR | 3 | [7 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700003 | Project Quality Plan (Including Project Organization Chart) | 0 | 2014-07-01 19:07 | 2014-07-04 19:07 | IFR | 2 | Blanco Rodriguez Juan Antonio | 3-Rejected_Nextstatus IFR | 2014-10-09 | 3 - Rejected | 2014-10-24 |  | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700004 | Vendor Data Book (VDB) Index |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700005 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700006 | Monthly Report | 2 | 2014-09-20 17:58 | 2014-09-24 17:58 | IFR | 2 | [7 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700007 | List of items of the purchase order | 0 | 2014-09-20 00:15 | 2014-10-30 00:15 | IFI | 3 | [7 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700008 | Commissioning, Start up and Performance Test Spare Parts List | 0 | 2014-09-22 00:15 | 2014-10-30 00:15 | IFR | 2 | [7 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700009 | Spare parts list for 2 years continuous operation | 0 | 2014-09-22 17:58 | 2014-09-24 17:58 | IFR | 2 | [7 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-700010 | List of Major Sub-Vendors | 0 | 2014-07-01 23:41 | 2014-07-03 23:41 | IFR | 2 | BOIS Benjamin | 1-Approved without Comments_Nextstatus AFC | 2014-08-05 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-20 |  | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-711001 | RIMS Design basis | 0 | 2014-10-06 02:29 | 2014-10-08 02:29 | IFR | 1 |  |  | 2014-10-13 | 3FC - Rejected and Comments on Form | 2014-10-28 |  | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712001 | Design report - RCC Console |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712002 | Design report - MRU |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712003 | Design report - PTMS |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712004 | Design report - Strain Sensor |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712005 | Design report - SDAM |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712006 | Design report - Riser Cable |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712007 | Design report - Corrosion Protection |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-712008 | Design report - Data Aquistion and HMI Software |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-722001 | Material Safety Datasheets |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730001 | System Block Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730002 | System Single Line Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730003 | Subsea Cable Summary |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730004 | MRU Coordinate System and Reference Frame |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730005 | Strain Sensor Coordinate System and Reference Frame |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730006 | RTMS Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730007 | RTMS General Arrangment and Equipment Location |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730008 | MRU Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730009 | MRU Receptacle and Hanger Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730010 | SBM Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730011 | SBM Receptacle and Hanger Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730012 | SBM EFL Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730013 | MRU and SBM General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730014 | PTMS Interface |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730015 | PTMS Sub-Vendor Item Control Drawing |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730016 | SSSA Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730017 | SSSA Protection Cage Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730018 | SSSA ROV-Installation Tool Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730019 | SSSA EFL Chafing Protection Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730020 | SSSA Interface |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730021 | SSSA As-built Calibration Pipe Fabrication |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730022 | SDAM Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730023 | SDAM Receptacle and Hanger Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730024 | CTA to SDAM EFL Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730025 | Riser Cable and CTA Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730026 | Riser Cable and Slack Management General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730027 | CTA Hanger Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730028 | Riser Cable Clamp Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730029 | Riser Cable Reel General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730030 | Riser Cable Reel Spreader Bar Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730031 | RCC Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730032 | RCC General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730033 | RCC Power Distribution Unit Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730034 | RCC Interface Specification |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730035 | Parking Position 1 Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730036 | Parking Position 1 General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730037 | Parking Position 2 Assembly |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-730038 | Parking Position 2 General Arrangement |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740001 | MRU Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740002 | SBM Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740003 | SDAM Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740004 | RCC Power Distribution Unit Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740005 | RCC Wiring Diagram |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-740006 | Seafloor Wiring Diagram |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750001 | Utility Load List of All Equipment |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750002 | Marking and Tagging Plan | 0 | 2014-09-11 01:47 | 2014-09-12 01:47 | IFR | 2 | GALLAGHER Brian | [6 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750003 | Pickling and Passivation Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750004 | Welding Procedure Specification (Including Welding Map) |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750005 | Welding Procedure Qualification |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750006 | Riser Cable Clamp ROV-Serviceability Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750007 | SSSA Temperature and Hydrostatic Pressure Calibration Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750008 | Painting/Coating Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750009 | Subsea Equipment Hydrostatic Test Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750010 | Factory Acceptance Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750011 | SSSA Full Scale Calibration and Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750012 | Packing, Handling, Transportation, Storage and Preservation Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750013 | Site Integration Test Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750014 | Installation and Commissioning Procedures |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750015 | Performance Test Procedures |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750016 | Welds Non-Destructive Examination Procedure |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-750017 | Material Traceability Procedure |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760001 | Pickling and Passivation Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760002 | Riser Cable Clamp ROV-Serviceability Test Report |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760003 | SSSA Temperature and Hydrostatic Pressure Calibration Report |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760004 | Painting/Coating Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760005 | Subsea Equipment Hydrostatic Test Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760006 | Factory Acceptance Test Report |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760007 | SSSA Full Scale Calibration and Test Report |  |  |  | not received | 2 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760008 | Weights and Dimensions Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760009 | FMECA Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760010 | RAM Analysis Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760011 | Inspection and Test Plan | 0 | 2014-09-11 01:47 | 2014-09-12 01:47 | IFR | 1 | WISEMAN Paul | [6 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760012 | Welds Non-Destructive Examination Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760013 | Signed-off Inspection and Test Plan |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760014 | Site Integration Test Report (will be part of the service PO for the requisition scope) |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760015 | Installation and Commissioning Report (will be part of the service PO for the requisition scope) |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-760016 | Performance Test Report (will be part of the service PO for the requisition scope) |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-770001 | Material Certificates (EN 10204) |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-770002 | Welding Record |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-770003 | Shipping Crate Heat Treatment Certificates |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-770004 | Welder List - Welder Qualification Records |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-770005 | NDT Operators List and Qualifications |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-780001 | Operation, Maintenance and Troubleshooting Manual |  |  |  | not received | 1 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-790002 | Non-Conformity Report |  |  |  | not received | 3 | [8 empty] | Y
BMT | Riser Integrity Monitoring System | 940818 | SV20 | NG-EGN-23-SV20-790003 | Deviation Request |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700001 | Vendor Master Document List | 1 | 2014-08-14 11:36 | 2014-08-14 11:36 | AFC | 2 | ZAGNI Jean-charles | 1-Approved without Comments | [5 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700002 | Production Schedule | 0 | 2014-06-26 18:25 | 2014-06-26 18:25 | IFR | 2 | ZAGNI Jean-charles | 1-Approved without Comments_Nextstatus AFC | 2014-08-12 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-27 |  | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700003 | Sub Vendor List | 1 | 2014-08-06 09:27 | 2014-08-07 09:27 | AFC | 2 | ZAGNI Jean-charles | 1-Approved without Comments | [5 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700004 | Project Quality Plan | 0 | 2014-07-15 10:00 | 2014-07-15 10:00 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700005 | Recommended Spare Parts List | 1 | 2014-10-01 12:51 | 2014-10-07 12:51 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700006 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700007 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700008 | Monthly Progress Report | 0 | 2014-07-22 15:10 | 2014-07-28 15:10 | IFI | 3 | ZAGNI Jean-charles | [6 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-700009 | List of the items of the Purchase Order |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730001 | 2" Parking Receptacle - General Arrangement Drawing | 2 | 2014-08-12 11:36 | 2014-09-25 16:32 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730002 | 2" NB SS Female Receptacle - General Arrangement Drawing | 2 | 2014-10-01 12:51 | 2014-10-07 12:51 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730003 | 2" NB Blind Stab - General Arrangement Drawing | 2 | 2014-08-12 11:36 | 2014-09-25 16:32 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730004 | 2" NB Dummy Plug Assembly - General Arrangement Drawing | 2 | 2014-08-12 15:38 | 2014-09-25 16:32 | AFC | 2 |  |  | 2014-10-13 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-28 |  | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730005 | 2" SS Male Stab c/w Integral female 1502 - General Arrangement Drawing | 2 | 2014-08-12 15:38 | 2014-09-25 16:32 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-730006 | 2" Female Receptacle c/w 9/16" Autoclave - General Arrangement Drawing | 2 | 2014-10-01 12:51 | 2014-10-07 12:51 | AFC | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-750002 | Welding Book | 1 | 2014-09-13 09:35 | 2014-09-19 09:35 | IFR | 1 | Balma Pascal | [6 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-750003 | NDT Procedures | 1 | 2014-09-13 09:35 | 2014-09-19 09:35 | IFA | 1 | Feuilly Nicolas | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-750004 | Hydrotest Procedure | 1 | 2014-09-17 11:16 | 2014-09-22 11:16 | IFR | 2 | Balma Pascal | [6 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-750005 | Paint Procedure | 1 | 2014-10-07 11:44 | 2014-10-10 11:44 | IFR | 2 | [7 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-750006 | Marking, Handling, Storage and Preservation Procedure | 0 | 2014-07-23 10:00 | 2014-07-18 | IFR | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-09-01 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-16 |  | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760001 | Inspection and Test Plan | 1 | 2014-09-15 09:50 | 2014-09-23 09:50 | IFA | 1 | WISEMAN Paul | 1-Approved without Comments_Nextstatus AFC | 2014-10-14 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-29 |  | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760002 | NDT Reports |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760003 | Hydrotest Reports |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760004 | Paint Report |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760005 | Inspection Release Note (including TPA completion certificate) |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-760006 | Signed off ITP |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-770001 | List of Welder Qualifications and Certificate | 0 | 2014-07-28 15:54 | 2014-07-28 15:54 | IFR | 2 | WISEMAN Paul | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-770002 | List of NDT Operators and Certificates |  |  |  | not received | 2 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-770003 | Production Weld Records |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-770004 | Material Certificates - UNS N06625 | 0 | 2014-09-15 09:09 | 2014-09-16 09:09 | IFR | 2 | Lambin Axel | [6 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
MOFFAT | System G - PLEM & SIV Hot Stabs | 942320 | SV21 | NG-EGN-22-SV21-790002 | NCR/DR List and reports |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700001 | VENDOR Master Document List | 0 | 2014-07-15 10:00 | 2014-07-15 10:00 | IFR | 2 | Bourquouquou Tarik | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700002 | WORK Execution Schedule |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700003 | Monthly progress report including 4 weeks look ahead schedule |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700004 | Project Quality Plan (Including WORK Organization Chart) | 0 | 2014-08-05 10:50 | 2014-08-11 10:50 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700005 | Vendor data book Index |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700006 | Vendor data book |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-700007 | List of the Items of the Purchase Order | 0 | 2014-10-01 11:46 | 2014-10-02 11:46 | IFR | 3 | [7 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-750001 | Manufacturing Procedure Specification | 1 | 2014-09-01 16:48 | 2014-09-01 16:48 | IFA | 1 | MAS Jeremy | 2-Approved with comments_Nextstatus IFA | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-750002 | Handling. transportation. storage and preservation procedure | 0 | 2014-10-01 | 2014-10-03 08:50 | IFR | 2 | [7 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-760001 | Inspection and Test Plan | 2 | 2014-09-30 16:25 | 2014-10-01 16:25 | AFC | 1 | [7 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-760002 | Visual & Dimensional Test Reports |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-760003 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-770001 | Material certificates |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-770002 | NDT Operators List & Qualifications - Europe |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-770003 | NDT Reports |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Buoyancy Tank - Plates Supply | 945176 | SV22 | NG-EGN-23-SV22-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700001 | VENDOR Master Document List | 1 | 2014-09-09 11:14 | 2014-09-11 11:14 | AFC | 2 | BOIS Benjamin | 1-Approved without Comments | [5 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700002 | WORK Execution Schedule | 0 | 2014-08-06 11:09 | 2014-08-07 11:09 | IFI | 3 | BOIS Benjamin | 2-Approved with comments_Nextstatus IFI | [5 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700003 | Project Quality Plan (including Project Organization Charts) | 0 | 2014-08-05 17:49 | 2014-08-07 17:49 | IFR | 2 | Blanco Rodriguez Juan Antonio |  | 2014-10-08 | 3FC - Rejected and Comments on Form | 2014-10-23 |  | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700004 | List of Subvendors | 1 | 2014-09-09 11:14 | 2014-09-11 11:14 | AFC | 2 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700005 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700006 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700007 | List of items of the Purchase Order | 1 | 2014-09-09 11:14 | 2014-09-11 11:14 | IFI | 3 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-700008 | Monthly Report | 0 | 2014-10-02 15:11 | 2014-10-03 15:11 | IFI | 3 | [7 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-750001 | Manufacturing Procedure Specification | 1 | 2014-08-28 11:14 | 2014-09-11 11:14 | IFA | 1 | MAS Jeremy | 2-Approved with comments_Nextstatus IFA | 2014-10-13 | 2 - Reviewed With Comments | 2014-10-28 |  | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-760001 | Inspection and Test Plan | 2 | 2014-09-08 11:14 | 2014-10-02 10:09 | IFA | 1 | [7 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-760002 | Inspection Release Note and TPA Completion Certificate |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-760003 | Inspection and Test Plan - As Built/Signed |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-770003 | Material Certificates 3.2 |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-790002 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Buoyancy Tank - Beams Supply | 945177 | SV23 | NG-EGN-23-SV23-790003 | Deviation Requests |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700001 | Vendor Master Document List | 1 | 2014-10-08 11:01 | 2014-10-09 11:01 | AFC | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700002 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700003 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700004 | Project Execution Plan | 0 | 2014-09-19 14:56 | 2014-09-26 13:23 | IFI | 3 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700005 | Project Quality Plan | 0 | 2014-09-17 14:56 | 2014-09-26 13:23 | IFR | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700006 | Monthly Progress Report | 1 | 2014-09-05 12:37 | 2014-09-08 12:37 | IFI | 3 | Huvet Guillaume | [6 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700007 | Project Schedule | 0 | 2014-09-03 10:35 | 2014-09-04 10:35 | IFR | 2 | Huvet Guillaume | [6 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700008 | Scope of Supply | 0 | 2014-08-08 16:46 | 2014-08-08 16:47 | IFI | 3 | GRIEVE James-Peter | 2-Approved with comments_Nextstatus IFI | 2014-09-10 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-25 |  | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700009 | Installation and pre-commissioning spare parts list |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700010 | Ship loose items list - Static RM |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-700011 | Ship loose items list - Dynamic |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-711001 | Design Basis - Static RM Umbilical | 0 | 2014-10-03 10:59 | 2014-10-03 11:00 | IFR | 1 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712001 | Design Calculation - UTA Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712002 | Cathodic Protection Calculation - UTA Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712003 | Design Calculation - UTA Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712004 | Cathodic Protection Calculation - UTA Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712005 | Design Calculation - Mudmat Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712006 | Cathodic Protection Calculation - Mudmat Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712007 | Design Calculation - Mudmat Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712008 | Cathodic Protection Calculation - Mudmat Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712009 | Design Calculation - Subsea Arch Clamp |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712010 | Cathodic Protection Calculation - Subsea Arch Clamp |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712011 | Design Calculation - Hang Off |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712012 | Installation Load Calculation - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712013 | Design Report - Static RM Umbilical |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712014 | Umbilical Historical Qualification Report |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-712015 | Bend Restrictor Sizing Report - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-721001 | Electrical Cable Requirements 2.5mm2 Screened Quad | 1 | 2014-09-30 17:31 | 2014-10-01 17:31 | AFC | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-721002 | Electrical Cable Design (ECD) 2.5mm2 Screened Quad | 0 | 2014-10-06 12:59 | 2014-10-06 12:59 | IFI | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-721003 | Material Purchasing Specification - Low Voltage Electrical Cables | 0 | 2014-10-06 12:59 | 2014-10-06 12:59 | IFI | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730001 | Hang-Off Collar General Arrangement - SIV/RIMS Dynamic | 0 | 2014-09-19 14:56 | 2014-09-26 13:23 | IFR | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730002 | GA Umbilical Termination Assembly - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730003 | GA Umbilical Termination Assembly - Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730004 | GA Subsea Arch Clamp |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730005 | GA Mudmat - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730006 | GA Mudmat - Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730007 | Reel Packing Arrangement - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730008 | Reel Packing Arrangement - Static RM Samples |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730009 | GA Bend Restrictors |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730010 | Hang-Off Collar General Arrangement - Main Dynamic | 0 | 2014-09-19 14:56 | 2014-09-26 13:23 | IFR | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730011 | GA Subsea Arch Clamp - Main Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-730012 | GA Umbilical Termination Assembly - Static RM (UTA 2) |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-740001 | Umbilical Cross Section - Static RM | 0 | 2014-08-12 15:23 | 2014-09-26 13:23 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-740002 | Electrical Schematic - Static RM | 0 | 2014-09-11 13:23 | 2014-09-26 13:23 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-740003 | Electro / Hydraulic Schematic - SIV/RIMS Dynamic Umbilical | 0 | 2014-09-19 14:56 | 2014-09-26 13:23 | IFR | 2 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750001 | Termination Procedure - Static RM |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750002 | Termination Procedure - Dynamic |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750003 | Loadout Procedure |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750004 | Tensile Test Procedure - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750005 | Crush / Friction Test Procedure - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750006 | Bend Stiffeness Test Procedure - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750007 | Reverse Bend (Flex) Test Procedure - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750008 | Umbilical Length Specification - Static RM | 0 | 2014-09-11 15:23 | 2014-09-11 15:23 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750009 | Subsea Arch Clamp Friction Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750010 | Traceability Procedure |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750011 | Welding Book - UTA |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750012 | Welding Book - Mudmat |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750013 | Welding Book - Subsea Arch Clamp |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750014 | Welding Book - UTA integration SIV umbilical |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750015 | Welding Book - Steel Bend Restrictors |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750016 | NDT Procedure - UTA |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750017 | NDT Procedure - Mudmat |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750018 | NDT Procedure - Subsea Arch Clamp |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750019 | NDT Procedure - UTA integration SIV umbilical |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750020 | NDT Procedure - Steel Bend Restrictors |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750021 | Pre & Post Loadout Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750022 | Packing, Marking, Handling and Preservation Procedure |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-750023 | Installation, Operation, Maintenance & Repair Procedure |  |  |  | not received | 2 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760001 | ITP - Umbilical Manufacture Static RM | 0 | 2014-09-19 14:56 | 2014-09-26 13:23 | IFR | 1 | [7 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760002 | ITP - Termination and Testing Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760003 | ITP - Termination and Testing Dynamic RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760004 | ITP - Manufacture of Electrical Cables |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760005 | ITP - Manufacture of UTA - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760006 | ITP - Manufacture of UTA - Dynamic |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760007 | ITP - Manufacture of Hang Off |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760008 | ITP - Manufacture of Subsea Arch Clamp |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760009 | ITP - Manufacture of Mudmat - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760010 | ITP - Manufacture of Mudmat - Dynamic |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760011 | ITP - Manufacture of Bend Restrictors - Static RM |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-760012 | ITP - Manufacture of Electrical Connectors |  |  |  | not received | 1 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-770001 | NDT Operators Qualifications - UTA |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-770002 | NDT Operators Qualifications - Mudmat |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-770003 | NDT Operators Qualifications - Subsea Arch Clamp |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-770004 | NDT Operators Qualifications - UTA integration SIV umbilical |  |  |  | not received | 3 | [8 empty] | Y
DUCO | RM Umbilical | 942733 | SV24 | NG-EGN-24-SV24-770005 | NDT Operators Qualifications - Steel Bend Restrictors |  |  |  | not received | 3 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700001 | Vendor Master Document List | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | ZAGNI Jean-charles | 2-Approved with comments_Nextstatus AFC | 2014-09-19 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-04 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700002 | Work Execution Schedule | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | ZAGNI Jean-charles | 3-Rejected_Nextstatus IFR | 2014-09-26 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-11 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700003 | Project Quality Assurance Plan (Including Project Organization Chart) | 0 | 2014-09-18 17:55 | 2014-09-18 17:55 | IFR | 2 | Blanco Rodriguez Juan Antonio | [6 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700004 | Procurement Plan - Riganti | 0 | 2014-10-09 17:32 | 2014-10-09 17:32 | IFR | 1 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700005 | List of Sub Vendors | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | ZAGNI Jean-charles | 2-Approved with comments_Nextstatus AFC | 2014-10-14 | 2 - Reviewed With Comments | 2014-10-29 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700006 | Monthly Progress Report | 0 | 2014-09-30 11:21 | 2014-10-09 11:21 | IFI | 3 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700007 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700008 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700009 | List of Items of the Purchase Order |  |  |  | not received | 3 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-700010 | Procurement Plan - San Giorgio | 0 | 2014-10-09 17:32 | 2014-10-09 17:32 | IFR | 1 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-712001 | Detail design report including FEA |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721001 | Material Purchase Specification - A182-F51 | 0 | 2014-09-03 08:16 | 2014-09-05 08:16 | IFI | 3 | Lambin Axel | 3-Rejected_Nextstatus IFR | 2014-10-06 | 3FC - Rejected and Comments on Form | 2014-10-21 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721002 | Material Purchase Specification - A479-S31803 | 0 | 2014-09-03 08:16 | 2014-09-05 08:16 | IFI | 3 | Lambin Axel | 3-Rejected_Nextstatus IFR | 2014-10-06 | 3FC - Rejected and Comments on Form | 2014-10-21 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721003 | Material Purchase Specification - ASTM A320 L7M | 0 | 2014-09-03 08:16 | 2014-09-05 08:16 | IFI | 3 | Lambin Axel | 3-Rejected_Nextstatus IFR | 2014-10-01 | 3FC - Rejected and Comments on Form | 2014-10-16 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721004 | Material Purchase Specification - ASTM A194 Gr.7M | 0 | 2014-09-03 08:16 | 2014-09-05 08:16 | IFI | 3 | Lambin Axel | 3-Rejected_Nextstatus IFR | 2014-10-01 | 3FC - Rejected and Comments on Form | 2014-10-16 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721006 | Material Purchase Specification - UNS S31803 / UNS J92205 - 22% Cr NORSOK | 0 | 2014-09-05 11:58 | 2014-09-05 11:58 | IFI | 3 | Lambin Axel | 3-Rejected_Nextstatus IFR | 2014-10-10 | 3FC - Rejected and Comments on Form | 2014-10-25 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-721007 | Material Purchase Specification - ASTM A240- S31803 + Nace | 0 | 2014-09-26 17:46 | 2014-09-30 18:26 | IFR | 3 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-722001 | Completed data sheet - Valves |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-730001 | General Assembly Drawing 1/2" 300 S.E. Ball Valve | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3 - Rejected | 2014-10-10 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-730002 | General Assembly Drawing 3" 300 S.E. Ball Valve | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3 - Rejected | 2014-10-10 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-730003 | General Assembly Drawing 4" 300 S.E. Ball Valve | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3 - Rejected | 2014-10-10 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-730004 | General Assembly Drawing 8" 300 S.E. Ball Valve | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 2 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-25 | 3 - Rejected | 2014-10-10 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750001 | Sub-Supplier Manufacturing Procedure - Riganti | 0 | 2014-09-26 18:26 | 2014-09-30 18:26 | IFR | 2 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750002 | FAT Procedure S.E Ball valve lever operated | 0 | 2014-10-13 12:01 | 2014-10-14 | IFR | 1 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750003 | FAT Procedure S.E Ball valve ROV operated | 0 | 2014-10-13 12:01 | 2014-10-14 | IFR | 1 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750004 | Valve Qualification Procedure for soft seal valves (1 1/2" - 3" - 4") | 0 | 2014-09-05 11:58 | 2014-09-05 11:58 | IFR | 1 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-23 | 3 - Rejected | 2014-10-08 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750005 | Valve Qualification Procedure for metal/metal seal valves (8") | 0 | 2014-09-05 11:58 | 2014-09-05 11:58 | IFR | 1 | Breuskin Bruno | 3-Rejected_Nextstatus IFR | 2014-09-23 | 3 - Rejected | 2014-10-08 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750006 | Procedure for Handling, Storage & Preservation |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750007 | Paint Procedure (including Qualification Reports) |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750008 | NDT Procedure - Dye Penetrant Inspection | 1 | 2014-09-12 17:42 | 2014-09-12 17:42 | IFA | 1 | MONNIER Alban | 1-Approved without Comments_Nextstatus AFC | 2014-10-06 | 1 - Reviewed Without Comments |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750009 | NDT Procedure - Ultrasonic Test Inspection | 1 | 2014-09-12 17:42 | 2014-09-12 17:42 | IFR | 1 | MONNIER Alban | 2-Approved with comments_Nextstatus IFA | 2014-10-06 | 2 - Reviewed With Comments | 2014-10-21 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750010 | Welding Procedure Specification and Qualification Record - pup pieces (3" - 8" 300) | 0 | 2014-09-11 12:58 | 2014-09-11 12:58 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-10-14 | 3 - Rejected | 2014-10-29 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750012 | Welding Procedure Specification and Qualification Record - plug | 0 | 2014-09-02 15:22 | 2014-09-02 15:22 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-10-14 | 3FC - Rejected and Comments on Form | 2014-10-29 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750013 | Welding Procedure Specification and Qualification Record - valve support | 0 | 2014-09-02 15:22 | 2014-09-02 15:22 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-10-14 | 3FC - Rejected and Comments on Form | 2014-10-29 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750014 | Welding Procedure Specification and Qualification Record - Inconel Overlay | 0 | 2014-10-07 19:01 | 2014-10-07 19:01 | IFR | 1 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750015 | Forging procedure (including heat treatment) |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750016 | TCC Procedure | 0 | 2014-09-15 17:18 | 2014-09-15 17:18 | IFR | 1 | Lambin Axel | [6 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750017 | Traceability Procedure | 0 | 2014-09-18 18:00 | 2014-09-23 18:00 | IFR | 1 | Breuskin Bruno | [6 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750018 | Welding Procedure Specification and Qualification Record - pup pieces for 1" - 3" and 4" |  |  |  | not received | 1 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-750019 | Sub-supplier manufacturing procedure - San Giorgio | 0 | 2014-09-26 18:26 | 2014-09-30 18:26 | IFR | 2 | [7 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-760001 | ITP for Soft Seal Valve | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 1 | GILLAN David | 3-Rejected_Nextstatus IFR | 2014-09-18 | 3FC - Rejected and Comments on Form | 2014-10-03 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-760002 | ITP for metal/metal Seal Valves | 0 | 2014-08-14 09:09 | 2014-08-14 09:09 | IFR | 1 | GILLAN David | 3-Rejected_Nextstatus IFR | 2014-09-19 | 3FC - Rejected and Comments on Form | 2014-10-04 |  | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-760003 | Sub Supplier ITP Riganti | 0 | 2014-09-30 11:27 | 2014-09-30 11:27 | IFR | 1 |  | 3-Rejected_Nextstatus IFR | [5 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-760004 | Inspection Release Notes (including TPA completion certificate) |  |  |  | not received | 3 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-760005 | Sub Supplier ITP (San Giorgio) | 0 | 2014-09-30 11:27 | 2014-09-30 11:27 | IFR | 1 |  | 3-Rejected_Nextstatus IFR | [5 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-770001 | Raw Bar Material Certificates |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-770002 | Ingots Material Certificates |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-770003 | List of NDT Operators and Certificates | 0 | 2014-09-18 17:55 | 2014-09-18 17:55 | IFR | 2 | GILLAN David | 3-Rejected_Nextstatus IFR | [5 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-770004 | Welder's Certificates |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-780001 | Installation, Operating & Maintenance Manual S.E Ball valve lever operated |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-780002 | Installation, Operating & Maintenance Manual S.E Ball valve ROV operated |  |  |  | not received | 2 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-790002 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
ADVANCED TECHNOLOGY VALVE SPA | Buoyancy Tanks Valves | 955596 | SV25 | NG-EGN-23-SV25-790003 | Deviations Request and Register |  |  |  | not received | 3 | [8 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700001 | Vendor Master Document List | 0 | 2014-09-10 18:03 | 2014-09-10 18:03 | IFR | 2 | ZAGNI Jean-charles | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700002 | Work Execution Schedule | 0 | 2014-09-11 17:06 | 2014-09-11 17:06 | IFR | 2 | ZAGNI Jean-charles | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700003 | Installation. Operation & Maintenance Manual Index | 0 | 2014-09-12 17:09 | 2014-09-12 17:09 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700004 | Project Quality Assurance Plan | 0 | 2014-09-09 18:03 | 2014-09-10 18:03 | IFR | 2 | Blanco Rodriguez Juan Antonio | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700005 | Monthly Progress Report | 0 | 2014-09-16 16:18 | 2014-09-16 16:18 | IFI | 3 | ZAGNI Jean-charles | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700006 | BSC Installation & Operational Spare Parts List (IOSPL) | 0 | 2014-09-11 17:06 | 2014-09-11 17:06 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700007 | BSC Approved Vendors List (AVL) | 0 | 2014-09-10 12:11 | 2014-09-10 17:53 | IFR | 2 | ZAGNI Jean-charles | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700008 | BSC Despatch Dossier |  |  |  | not received | 3 | [8 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700009 | Vendor Data Book Index | 0 | 2014-09-11 17:06 | 2014-09-11 17:06 | IFR | 1 | Quintas Stephane | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-700010 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-712001 | BSC Design Report (including Fatigue Analysis) | 0 | 2014-09-09 18:03 | 2014-09-10 18:03 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-712002 | BSC Material Selection Report | 0 | 2014-09-09 18:03 | 2014-09-10 18:03 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-730001 | General Assembly Drawing - BSC | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-740001 | Detail Drawing - BSC Male | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-740002 | Detail Drawing - BSC Female | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-740003 | Detail Drawing - End Fitting/ EFRS Adaptor Sleeve | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 2 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750001 | Manufacturing Procedure Specification (Forging) | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750002 | FAT Procedure | 0 | 2014-09-26 12:40 |  | IFR | 1 | [7 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750003 | Load Test Procedure | 0 | 2014-09-24 16:29 | 2014-09-24 16:29 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750004 | SIT Procedure | 0 | 2014-09-24 16:29 | 2014-09-24 16:29 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750005 | Coating Procedure (Epoxy) | 0 | 2014-09-10 17:53 | 2014-09-10 17:53 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750006 | Marking and Traceability Procedure |  |  |  | not received | 1 | [8 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-750007 | Coating Procedure (DNP) | 0 | 2014-09-12 17:09 | 2014-09-12 17:09 | IFR | 1 | GRIEVE James-Peter | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-760001 | Inspection & Testing Plan (Overall Project) | 0 | 2014-09-10 12:11 | 2014-09-11 12:11 | IFR | 1 | GILLAN David | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-760002 | Inspection & Testing Plan (Bruck Forging) | 0 | 2014-09-10 12:11 | 2014-09-11 12:11 | IFR | 1 | GILLAN David | [6 empty] | Y
FLEXIBLE ENGINEERED SOLUTIONS Ltd | Supply of Bend Stiffener Connector | 956127 | SV26 | NG-EGN-24-SV26-780001 | Installation. Operation & Maintenance Manual |  |  |  | not received | 2 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700001 | Vendor Master Document List | 0 | 2014-09-16 11:59 | 2014-09-18 11:59 | IFR | 2 | ZAGNI Jean-charles | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700002 | Work Execution Schedule | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFR | 2 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700003 | Project Quality Plan | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFR | 2 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700004 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700005 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700006 | Monthly Report |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700007 | Anodes and Accessories Supply List | 0 | 2014-09-16 13:05 | 2014-09-25 13:05 | IFI | 3 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-700008 | Manufacturing Weekly Report |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-722001 | Technical Data Sheet of Paint and Accessories | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFI | 3 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-740001 | FM-71 Anode Drawing | 0 | 2014-09-19 18:24 | 2014-09-19 18:24 | IFR | 2 | Ogunsola Abiodun | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-740002 | FM-17 Anode Drawing | 0 | 2014-09-19 18:24 | 2014-09-19 18:24 | IFR | 2 | Ogunsola Abiodun | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-750001 | Anode Manufacturing Procedure for flush mounted anodes | 0 | 2014-09-19 18:24 | 2014-09-19 18:24 | IFR | 2 | Ogunsola Abiodun | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-750002 | Anode Factory Acceptance Test for flush mounted anodes | 0 | 2014-09-19 18:24 | 2014-09-19 18:24 | IFR | 2 | Ogunsola Abiodun | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-750003 | Handling, Transportation, Storage and Preservation Procedure | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFR | 2 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-750004 | Identification, Traceability and Marking Procedure | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFR | 1 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760001 | Inspection and Test Plan for flush mounted Anodes | 0 | 2014-09-19 18:24 | 2014-09-19 18:24 | IFR | 1 | Desbois Louis | [6 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760002 | Long Term Performance Justification Report/Certificate | 0 | 2014-09-25 13:05 | 2014-09-25 13:05 | IFI | 3 | [7 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760003 | PQT Report for FM-71 Anodes |  |  |  | not received | 2 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760004 | PQT Report for FM-17 Anodes |  |  |  | not received | 2 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760005 | Raw Material Certificates |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760006 | Other Test Reports |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760007 | Visual / Dimensional Test Reports |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760008 | Signed Off ITP for flushed mounted Anodes |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-760009 | Inspection Release Note |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-790001 | Certificates of Conformity |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-790002 | Non Conformity Report |  |  |  | not received | 3 | [8 empty] | Y
BAC CORROSION CONTROL | Anodes for IMS Structure | 964350 | SV27 | NG-EGN-23-SV27-790003 | Deviation Request |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700001 | Vendor Master Document List | 0 | 2014-09-09 16:05 | 2014-09-09 | IFR | 2 | VERDIER Adrien | [6 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700002 | VENDOR Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700003 | VENDOR Data Book |  |  |  | not received | 1 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700004 | Delivery Time Schedule |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700005 | List of subvendors |  |  |  | not received | 2 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700006 | Monthly Progress Report |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-700007 | List of Items of the PO |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-750001 | Traceability, marking and identification Procedure |  |  |  | not received | 2 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-750002 | Handling, Transportation, Storage and preservation procedure |  |  |  | not received | 2 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-750003 | LMBS Manufacturing Procedure Specification (option) |  |  |  | not received | 1 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-760001 | AM Inspection & Test Plan | 0 | 2014-09-09 16:05 | 2014-09-09 16:05 | IFR | 1 | Desbois Louis | [6 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-760002 | LMBS Inspection and Test Plan (option) |  |  |  | not received | 1 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-760003 | Signed off Inspection and Test Plan |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-760004 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-770001 | Arcelor Material test certificates incl additional test |  |  |  | not received | 3 | [8 empty] | Y
ARCELORMITTAL | Structural Steel | 964762 | SV28 | NG-EGN-21-SV28-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700001 | Vendor Master Document List | 0 | 2014-08-26 14:07 | 2014-09-02 14:07 | IFR | 2 | VERDIER Adrien | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700002 | Project Quality Plan including HSE | 0 | 2014-08-26 14:07 | 2014-09-02 14:07 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700003 | Project Schedule | 0 | 2014-08-26 14:07 | 2014-09-02 14:07 | IFR | 2 | VERDIER Adrien | [6 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700004 | Monthly Report |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700005 | VENDOR Data Book Index | 0 | 2014-09-11 15:57 | 2014-09-11 15:57 | IFR | 1 | Quintas Stephane | [6 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700006 | VENDOR Data Book |  |  |  | not received | 1 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700007 | List of Sub-Vendors | 0 | 2014-09-11 15:57 | 2014-09-11 15:57 | IFR | 2 | VERDIER Adrien | [6 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-700008 | List of Items of the PO |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-730001 | General Arrangement Drawings | 0 | 2014-08-26 14:07 | 2014-09-02 14:07 | IFR | 2 | Lambin Axel | [6 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750001 | Manufacturing Procedure Specification | 1 | 2014-10-06 10:07 | 2014-10-09 10:00 | IFR | 1 | [7 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750002 | Ultrasonic Examination Procedure | 1 | 2014-09-26 16:01 | 2014-09-30 16:01 | IFA | 1 |  | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750003 | Magnetic Particle Examination Procedure | 1 | 2014-09-24 14:47 | 2014-09-24 14:47 | IFR | 1 |  | 1-Approved without Comments_Nextstatus IFA | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750004 | Visual Examination Procedure | 1 | 2014-09-24 14:47 | 2014-09-24 14:47 | IFR | 1 |  | 1-Approved without Comments_Nextstatus IFA | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750005 | Handling, Transportation, Storage and Preservation Procedure | 1 | 2014-10-10 15:46 | 2014-10-14 15:46 | AFC | 2 | [7 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-750006 | Traceability & Identification Procedure | 0 | 2014-09-11 15:24 | 2014-09-11 15:57 | IFR | 2 | Lambin Axel | [6 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-760001 | Inspection and Test Plan | 1 | 2014-09-24 14:47 | 2014-09-24 14:47 | IFA | 1 | [7 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-760002 | Signed off Inspection and Test Plan |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-760003 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-760004 | Visual Reports |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-760005 | NDT Reports |  |  |  | not received | 3 | [8 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-770001 | NDT Operators List & Qualification | 0 | 2014-09-11 15:57 | 2014-09-11 15:57 | IFR | 2 | MONNIER Alban | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
M.E.G.A. | Riser Structural Forging | 966069 | SV29 | NG-EGN-23-SV29-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700001 | VENDOR Master Document List | 0 | 2014-09-11 14:53 | 2014-09-16 15:02 | IFR | 2 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700002 | WORK Execution Schedule | 0 | 2014-09-11 15:02 | 2014-09-16 15:02 | IFI | 3 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700003 | Project Quality Plan (including Project Organization Charts) |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700004 | List of Subvendors | 0 | 2014-09-11 17:26 | 2014-09-16 15:02 | IFR | 2 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700005 | Vendor Data Book (VDB) Index |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700006 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700007 | List of items of the Purchase Order | 0 | 2014-09-11 15:02 | 2014-09-16 15:02 | IFI | 3 | BOIS Benjamin | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700008 | Monthly report (including HSE report) |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700009 | Procurement Plan |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-700010 | Weekly report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-730001 | COFELY FABRICOM - General Arrangement Drawings of Pipes, Induction Bends and Test Rings |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-730002 | COFELY FABRICOM - ASB Drawings of Pipes and Bends |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750001 | VOEST - Manufacturing Procedure Specification for Clad Plates (Including Heat Treatment and Dimensional and Weight Control Procedure) | 0 | 2014-09-30 11:53 | 2014-10-01 11:53 | IFR | 1 |  |  | 2014-10-14 | 3 - Rejected | 2014-10-29 |  | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750002 | VOEST - Ultrasonic Testing Procedure for Clad Plates | 0 | 2014-09-18 15:48 | 2014-09-19 15:48 | IFR | 1 | Feuilly Nicolas | 2-Approved with comments_Nextstatus IFA | 2014-10-10 | 2 - Reviewed With Comments | 2014-10-25 |  | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750003 | VOEST - Traceability and Equipment Identification Procedure for Clad Plates |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750004 | VOEST - Packing, handling and shipping procedure for Clad Plates |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750006 | BUTTING - Ultrasonic Testing Procedure for Clad Pipes | 0 | 2014-09-22 14:38 | 2014-09-22 14:38 | IFR | 1 | Feuilly Nicolas | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750007 | BUTTING - Magnetic Particle Testing Procedure for Clad Pipes and Clad Plates | 0 | 2014-09-18 15:48 | 2014-09-19 15:48 | IFR | 1 | Feuilly Nicolas | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750008 | BUTTING - Radiographic Testing Procedure for Clad Pipes | 0 | 2014-09-18 15:48 | 2014-09-19 15:48 | IFR | 1 | Feuilly Nicolas | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750009 | BUTTING - Dye Penetrant Testing Procedure for Clad Pipes and Clad Plates | 0 | 2014-09-16 17:33 | 2014-09-18 16:59 | IFR | 1 | Feuilly Nicolas | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750010 | COFELY FABRICOM - Thickness Measurement Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750011 | BUTTING - Visual, Dimensional and Weight Control Procedure for Clad Pipes |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750012 | BUTTING - WPS (Including Welding Map) | 0 | 2014-09-18 15:48 | 2014-09-19 15:48 | IFR | 1 | KUHN Vincent | 3-Rejected_Nextstatus IFR | 2014-10-10 | 3 - Rejected | 2014-10-25 |  | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750013 | BUTTING - WPQR |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750014 | BUTTING - Traceability and Equipment Identification Procedure for Clad Pipes | 0 | 2014-09-11 15:48 | 2014-09-19 15:48 | IFR | 2 | Lambin Axel | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750015 | BUTTING - Packing, Handling and Shipping Procedure for Clad Pipes | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750016 | COFELY FABRICOM - Induction Bending Procedure | 0 | 2014-09-16 17:33 | 2014-09-18 16:59 | IFR | 1 | Lambin Axel | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750017 | COFELY FABRICOM - Heat treatment Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750018 | COFELY FABRICOM - Ultrasonic Examination Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750019 | COFELY FABRICOM - Magnetic Particle Testing Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750020 | COFELY FABRICOM - Liquid Penetrant Testing Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750021 | COFELY FABRICOM - Visual Inspection Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750022 | COFELY FABRICOM - Dimensional Control and Pigging Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750023 | COFELY FABRICOM - Traceability and Equipment Identification Procedure | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750024 | COFELY FABRICOM - Handling, Marking, Packing & Transportation Procedure |  |  |  | not received | 2 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750025 | BUTTING - Hydrotest Procedure | 0 | 2014-09-23 15:28 | 2014-09-23 15:28 | IFR | 2 | Lambin Axel | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750026 | BUTTING - Pickling and Passivation Procedure | 0 | 2014-09-23 15:28 | 2014-09-23 15:28 | IFR | 2 | Lambin Axel | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-750027 | FABRICOM - Radiographic Testing Procedure for Clad Bends | 0 | 2014-10-01 16:23 |  | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760001 | VOEST - Inspection and Test Plan for Clad Plates | 0 | 2014-09-30 11:53 | 2014-10-01 11:53 | IFR | 1 |  |  | 2014-10-14 | 3 - Rejected | 2014-10-29 |  | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760002 | BUTTING - Inspection and Test Plan for Clad Pipes | 0 | 2014-09-17 16:15 | 2014-09-17 16:15 | IFR | 1 | QUESNE Alain | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760003 | COFELY FABRICOM - Inspection and Test Plan for Clad Bends | 0 | 2014-09-16 16:59 | 2014-09-18 16:59 | IFR | 1 | QUESNE Alain | [6 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760004 | BUTTING - Inspection and Test Plan for Final Sizing and Machining of Bends | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760005 | BUTTING - Ultrasonic Testing Report for Clad Pipes |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760006 | BUTTING - Magnetic Particle Testing Report for Clad Pipes |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760007 | BUTTING - Radiographic Testing Report for Clad Pipes |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760008 | COFELY FABRICOM - Ultrasonic Testing Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760009 | COFELY FABRICOM - Magnetic Particle Testing Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760010 | COFELY FABRICOM - Production Dimensional Control Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760011 | COFELY FABRICOM - Liquid Penetrant Testing Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760012 | Signed off Inspection and Test Plans |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760013 | Inspection Release Note including TPA completion certificate |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-760014 | FABRICOM - Radiographic Testing Report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770001 | VOEST - NDT Operators list and Qualifications | 0 | 2014-09-23 15:28 | 2014-09-23 15:28 | IFR | 2 | QUESNE Alain | 3-Rejected_Nextstatus IFR | 2014-10-10 | 3 - Rejected | 2014-10-25 |  | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770002 | BUTTING - Welders list and Qualifications | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 1 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770003 | BUTTING - NDT Operators list and Qualifications | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770004 | COFELY FABRICOM - NDT Operators list and Qualifications | 0 | 2014-10-01 10:49 | 2014-10-07 10:49 | IFR | 2 | [7 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770005 | BUTTING - Manufacturing Production Qualification Test report |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770006 | COFELY FABRICOM - Production Induction Bending report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770007 | BUTTING - Hydrotest report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770008 | COFELY FABRICOM - Production Heat treatment report |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770009 | COFELY FABRICOM - Manufacturing Production Qualification Test report |  |  |  | not received | 1 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770010 | Material certifcates 3.2 for Cladded Plates |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770011 | Material certifcates 3.2 for Cladded Pipes |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-770012 | Material certifcates 3.2 for Cladded Bends |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-790002 | Deviation Requests |  |  |  | not received | 3 | [8 empty] | Y
PROJECT MATERIALS | Pipes and Bends | 969181 | SV31 | NG-EGN-21-SV31-790003 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700001 | Vendor Master Document List |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700002 | List of Sub-vendors |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700003 | Work Execution Schedule |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700004 | Weekly Progress Report |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700005 | Monthly Progress Report |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700006 | Project HSE Plan |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700007 | Project Quality Assurance Plan |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700008 | List of Items of the PO |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700009 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-700010 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-712001 | Design Report |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-722001 | Technical Data Sheet and Material Safety Data Sheet of raw materials |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-730001 | General Arrangement and Detailed Drawings of North Buoyancy modules |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-730002 | General Arrangement and Detailed Drawings of Central Buoyancy modules |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-730003 | General Arrangement and Detailed Drawings of South Buoyancy modules |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-730004 | General Arrangement and detailed Drawings of Steel works |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-730005 | General Arrangement Drawings of Assembly |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750001 | Traceability Procedure |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750002 | Manufacturing Procedure Specification |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750003 | Test Procedures |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750004 | Welding Book (including WPS, WPQR and Welding maps) |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750005 | Non Destructive Testing Procedure |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750006 | Painting Procedure |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-750007 | Packing, Preservation, Marking and Shipping Procedure |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760001 | Inspection & Test Plan for Buoyancy modules |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760002 | Inspection & Test Plan for Steel works |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760003 | Inspection & Test Plan for Painting |  |  |  | not received | 1 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760004 | Painting Pre Qualification Test Report |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760005 | Non Destructive Testing Reports |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760006 | Painting Report |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760007 | Inspection Release Note |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-760008 | Production test report |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-770001 | NDT Operators List and Qualifications |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-770002 | Welder list and Qualifications |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-770003 | Pre Qualification Test Report of Buoyancy modules |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-770004 | Material Certificates 3.1 + Summary Sheet |  |  |  | not received | 3 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-780001 | Operation, Installation, Maintenance and Repair Manual |  |  |  | not received | 2 | [8 empty] | Y
BALMORAL | Umbilical Arches Buoyancy Modules | 971635 | SV32 | NG-EGN-24-SV32-790001 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700001 | Vendor Master Document List | 0 | 2014-09-23 13:54 | 2014-09-24 13:54 | IFR | 2 | VENGEON Germain | [6 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700002 | Work Execution Schedule | 0 | 2014-09-23 14:49 | 2014-09-24 13:54 | IFI | 3 | VENGEON Germain | [6 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700003 | List of sub-vendors | 0 | 2014-09-23 13:54 | 2014-09-24 13:54 | IFR | 2 | VENGEON Germain | [6 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700004 | Project Quality Plan | 0 | 2014-10-02 14:32 | 2014-10-09 14:32 | IFR | 2 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700005 | Monthly Progress Report |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700006 | VENDOR Data book index |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700007 | VENDOR Data book |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-700008 | List of Items of the PO |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750001 | Factory Acceptance Test Procedure for Plug |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750002 | Factory Acceptance Test Procedure for Locking Arm |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750003 | Marking and Traceability Procedure | 0 | 2014-09-26 20:55 |  | IFR | 2 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750004 | Handling, Transportation Storage preservation Procedure |  |  |  | not received | 2 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750005 | Welding Book | 0 | 2014-09-25 20:55 | 2014-10-20 20:55 | IFR | 1 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750006 | Welding Qualification Dossier |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750007 | NDT procedure (including List of Operator + Qualification) |  |  |  | not received | 1 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-750008 | Welding Qualification Plan | 0 | 2014-09-22 20:55 | 2014-09-30 20:55 | IFR | 1 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760001 | Inspection and Test Plan for Production | 0 | 2014-09-26 20:55 | 2014-09-30 20:55 | IFR | 1 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760002 | Inspection and Test Plan for Qualification | 0 | 2014-09-26 20:55 | 2014-09-30 20:55 | IFR | 1 | [7 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760003 | NDT Report |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760004 | Dimensional Control Report (including As Built DWG) |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760005 | Signed off Inspection and Test Plan |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-760006 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-770001 | Material certificates and Material certificates summary |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-770002 | Factory Accepatance Test Reports for Plug |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-770003 | Factory Accepatance Test Reports for Locking Arm |  |  |  | not received | 3 | [8 empty] | Y
ERM-S | Subsea structures pre-fabricated items | 961218 | SV33 | NG-EGN-21-SV33-790001 | Certificate of Conformity of the PO |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700001 | Vendor Master Document List | 0 | 2014-10-01 10:00 | 2014-10-03 18:11 | IFR | 2 | [7 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700002 | Work Execution Schedule | 0 | 2014-10-03 09:08 | 2014-10-03 18:11 | IFI | 3 | [7 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700003 | Project Quality Plan |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700004 | List of Subvendors | 0 | 2014-10-01 10:00 | 2014-10-03 | IFR | 2 | [7 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700005 | Monthly progress report |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700006 | Spare part list |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700007 | Vendor Data Book |  |  |  | not received | 1 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700008 | Vendor Data Book Index |  |  |  | not received | 1 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-700009 | List of PO items |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-711001 | Design basis | 0 | 2014-10-10 | 2014-10-10 14:48 | IFR | 1 | [7 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-712001 | Design report |  |  |  | not received | 1 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-722001 | Technical Data Sheet and Material Safety Data Sheet of raw material |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-730001 | General Arrangement Drawing for CHOC insulation cover |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-730002 | General Arrangement Drawing for Hanger spool Insulation Cover |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-740001 | Detailed Drawing for CHOC insulation half shell |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-740002 | Detailed Drawing for Hanger spool half shell |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-750001 | Manufacturing Procedure |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-750002 | Factory Acceptance Test Procedure |  |  |  | not received | 1 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-750003 | Installation, Handling, Repair, Transportation, Storage and Preservation Procedure |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-750004 | Identification, Traceability and Marking Procedure |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-760001 | Inspection and Test Plan |  |  |  | not received | 1 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-760002 | Inspection release note |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-760003 | Signed off Inspection and Test Plan |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-770001 | PQT test report |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-770002 | FAT test report |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-770003 | Raw material certificates 3.1 |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-770004 | Production test reports |  |  |  | not received | 2 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-790001 | Non conformity reports |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-790002 | Deviation requests and Register |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-790003 | Certificate of Conformity to the PO |  |  |  | not received | 3 | [8 empty] | Y
TRELLEBORG | Insulation Covers | 972220 | SV34 | NG-EGN-23-SV34-790004 | Clarification requests and Register |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700001 | VENDOR Master Document List |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700002 | WORK Execution Schedule |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700003 | Monthly progress report including 4 weeks look ahead schedule |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700004 | Project Quality Plan (Including WORK Organization Chart) |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700005 | Vendor data book Index |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700006 | Vendor data book |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-700007 | List of Subvendors |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750001 | Welding Book - EBK (Welded Pipes) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750002 | Manufacturing Procedure Specification (including NDT Procedure and Tracebility and Marking Procedure) - Voest Alpine (Plates) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750003 | Manufacturing Procedure Specification (including NDT Procedure and Tracebility and Marking Procedure) - Arcelor Mittal (Seamless Pipes) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750004 | Manufacturing Procedure Specification - EBK (Welded pipes) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750005 | Manufacturing Procedure Specification (including NDT Procedure and Tracebility and Marking Procedure)) - TATA (RHS) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750006 | Handling, transportation, storage and preservation procedure - Voest Alpine (Plates) |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750007 | Handling, transportation, storage and preservation procedure - Arcelor Mittal (Seamless Pipes) |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750008 | Handling, transportation, storage and preservation procedure - EBK (Welded pipes) |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750009 | Handling, transportation, storage and preservation procedure - TATA (RHS) |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750010 | Handling, transportation, storage, preservation and marking procedure - Stock Materials |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750011 | NDT Procedure - Europe |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750012 | NDT Procedure - Singapore |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750013 | NDT Procedure for Welded Pipes - EBK |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750014 | Destructive Test - Europe |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-750015 | Destructive Test - Singapore |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760001 | Inspection and Test Plan - Voest Alpine (Plates) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760002 | Inspection and Test Plan - Arcelor Mittal (Seamless Pipes) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760003 | Inspection and Test Plan - EBK (Welded pipes) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760004 | Inspection and Test Plan - TATA (RHS) |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760005 | Inspection and Test Plan - Stock Materials |  |  |  | not received | 1 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-760006 | Inspection Release Notes |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770001 | Material certificates (including tracability register) - Voest Alpine (Plates) |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770002 | Material certificates (including tracability register) - Arcelor Mittal (Seamless Pipes) |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770003 | Material certificates (including tracability register) - EBK (Welded pipes) |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770004 | Material certificates (including tracability register) - TATA (RHS) |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770005 | Material certificates (including tracability register and NDT Reports) - Stock Materials |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770006 | NDT Operators List & Qualifications - Europe |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-770007 | NDT Operators List & Qualifications - Singapore |  |  |  | not received | 2 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-790001 | Certificate of Conformity of the PO |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-790002 | Deviation Request |  |  |  | not received | 3 | [8 empty] | Y
EDGEN MURRAY | Miscellaneous - PO 973979 | 973979 | SV35 | NG-EGN-21-SV35-790003 | Non Conformity Reports |  |  |  | not received | 3 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800001 | Vendor Master Document List (VMDL) | 3 | 2014-05-08 | 2014-05-07 14:24 | IFR | 1 | MARC Herve | 2-Approved with comments_Nextstatus IFA | 2014-08-05 15:21 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-20 15:21 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800002 | Project Execution Plan (includes project organisation and coordination procedure) | 2 | 2014-09-02 01:00 |  | IFR | 2 | MARC Herve | 2-Approved with comments_Nextstatus IFA | 2014-10-13 15:42 | 3 - Rejected | 2014-10-28 15:42 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800003 | Project Quality Plan | 4 | 2014-07-24 23:00 | 2014-08-06 13:12 | IFA | 1 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus IFA | 2014-08-14 16:58 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-29 16:58 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800004 | Project Quality Audit Procedure | 5 | 2014-09-22 | 2014-09-25 13:18 | IFA | 2 |  | 1-Approved without Comments_Nextstatus AFC | 2014-10-13 12:18 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800005 | Project HSE Plan | 6 | 2014-10-03 23:00 | 2014-10-09 15:31 | AFC | 1 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800006 | Work Scope Execution Schedule for Pig Launcher and Receivers fabrication |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800007 | Procurement Plan for Pig Launcher and Receivers |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800008 | Project Risk Management Plan | 4 | 2014-08-27 23:00 | 2014-09-03 16:29 | AFC | 1 | MANTOUX Florian | [6 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800009 | Manufacturer's Data Record Index for Pig Launcher and Receivers |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800010 | PROJECT PROCUREMENT PLAN |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-800011 | PROJECT SECURITY BRIDGING DOCUMENT | 2 | 2014-08-25 01:00 | 2014-08-29 11:33 | IFA | 1 | MARC Herve | [6 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-822002 | Pig Launcher And Receivers Material Datasheet |  |  |  | not received | 3 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-840002 | Detail Fabrication Drawings For Pig Launcher And Receivers |  |  |  | not received | 3 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850001 | Change Management Procedure | 3 | 2014-08-21 | 2014-08-25 15:08 | IFA | 2 | Ejarune Blessing | 2-Approved with comments_Nextstatus IFA | 2014-10-10 15:31 | 2 - Reviewed With Comments | 2014-10-25 15:31 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850002 | Drawing & Document Control Procedure | 4 | 2014-05-16 | 2014-05-19 11:59 | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | 2014-06-12 16:53 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850003 | Quality Control Inspection Documentation Procedure |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850004 | Non-Conformance Management Procedure | 4 | 2014-09-08 23:00 | 2014-09-08 16:57 | IFA | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus AFC | 2014-10-13 12:18 | 1FC - Reviewed Without Comments but Comments on Form | 2014-10-28 12:18 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850005 | Material Receiving Inspection Procedure | 3 | 2014-08-27 23:00 | 2014-09-03 16:29 | AFC | 2 | Quarta Giulio | 2-Approved with comments_Nextstatus AFC | 2014-10-14 12:46 | 2 - Reviewed With Comments | 2014-10-29 12:46 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850006 | Material Identification and Traceability Procedure | 5 | 2014-09-27 | 2014-09-26 17:58 | AFC | 1 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850007 | Non-Destructive Examination (NDE) Procedure | 3 | 2014-06-25 | 2014-06-25 10:42 | AFC | 1 | MONNIER Alban | 1-Approved without Comments | 2014-07-25 16:05 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850008 | Calibration Procedure | 2 | 2014-04-26 |  | AFC | 2 |  | 1-Approved without Comments | 2014-06-03 12:57 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850009 | Welding Consumable Control Procedure | 5 | 2014-07-11 | 2014-07-14 17:13 | AFC | 1 | ROUSLANS Gens | 2-Approved with comments_Nextstatus AFC | 2014-08-13 10:43 | 1 - Reviewed Without Comments | 2014-08-28 10:43 | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850010 | Weight Control and Weighing Procedure |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850011 | Lifting Procedure | 2 | 2014-04-08 | 2014-04-08 12:49 | IFA | 2 | Blin Nicolas | 2-Approved with comments_Nextstatus IFA | 2014-05-30 16:29 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-14 16:29 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850012 | Fabrication & Construction Plan for Pig Launcher and Receivers fabrication | 0 | 2013-11-19 |  | IFI | 3 | MARC Herve | 2-Approved with comments_Nextstatus IFI | 2014-05-21 10:29 | 3FC - Rejected and Comments on Form | 2014-06-05 10:29 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850013 | Painting & Marking Procedure for Pig Launcher and Receivers fabrication |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850014 | Welding Book (WPS,PQR Weld Map) for Pig Launcher and Receivers |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850015 | Welding Repair Procedure for Pig Launcher and Receivers |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850016 | Dimensional Control Procedure for Pig Launcher and Receivers |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850017 | Handling, Packing, Preservation & Storage Procedure for Pig Launcher and Receivers |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850018 | Load out Procedure for Pig Launcher and Receivers |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850019 | Factory Acceptance Test Procedure for Pig Launcher and Receivers |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850020 | Liquid Penetrant Examination Procedure |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850021 | Radiographic Testing Procedure |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850022 | Ultrasonic Testing Procedure |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850023 | Managetic Particle Examination Procedure |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-850024 | Visual Testing Procedure |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-860001 | Inspection & Test Plan for Pig Launcher and Receivers fabrication |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-870001 | Manufacturer's Data Record for Pig Launcher and Receivers |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-890001 | Paint System Qualification Plan | 4 | 2014-09-18 23:00 | 2014-09-19 16:17 | AFC | 2 | DEBAVELAERE Marc | [6 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-890002 | Paint Operators Qualification Plan | 4 | 2014-09-18 23:00 | 2014-09-19 16:17 | AFC | 2 | DEBAVELAERE Marc | [6 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-890003 | NDE Operator Qualification Records | 4 | 2014-07-20 | 2014-08-06 13:11 | AFC | 1 | MONNIER Alban | 1-Approved without Comments | 2014-08-26 15:29 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-890004 | Welder Performance Qualification Records | 2 | 2014-07-08 01:00 | 2014-07-14 16:52 | AFC | 2 | ROUSLANS Gens | 2-Approved with comments_Nextstatus AFC | 2014-08-21 12:21 | 2 - Reviewed With Comments | 2014-09-05 12:21 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-20-SX01-890005 | Weld Procedure Qualification Plan (WPQP) for Pig Launcher and Receivers |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-800001 | Work Scope Execution Schedule for LBL array frame fabrication | 4 | 2014-10-10 23:00 | 2014-10-10 17:12 | AFC | 2 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-800002 | Project Procurement Plan | 2 | 2014-09-22 | 2014-09-25 13:18 | AFC | 2 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-800003 | Manufacturer's Data Record Index for LBL array frame fabrication | 1 | 2014-08-22 | 2014-08-25 15:08 | IFR | 1 | Quarta Giulio | 2-Approved with comments_Nextstatus IFA | 2014-09-12 11:21 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-27 11:21 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-822001 | LBL Array Frame Material Datasheet | 2 | 2014-09-24 | 2014-09-25 13:18 | IFI | 3 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-822002 | Pig Launcher And Receivers Material Datasheet |  |  |  | not received | 3 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-840001 | Detail Fabrication Drawings for LBL Array Frame Fabrication | 4 | 2014-09-11 |  | AFC | 2 | MARC Herve |  | 2014-10-02 10:34 | 2 - Reviewed With Comments | 2014-10-17 10:34 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-840003 | LBL Array Frame – Electrical Continuity Check Method Statement | 0 | 2014-09-11 01:00 |  | IFR | 2 | MARC Herve | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850001 | Fabrication & Construction Plan for LBL array frame fabrication | 3 | 2014-06-21 23:00 | 2014-06-25 10:41 | IFA | 2 | DE-FRANCO Ernesto | 2-Approved with comments_Nextstatus IFA | 2014-08-22 20:27 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-06 20:27 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850002 | Painting & Marking Procedure for LBL array frame fabrication | 3 | 2014-08-21 | 2014-08-25 15:08 | AFC | 2 | MARC Herve | 1-Approved without Comments | 2014-09-22 15:04 | 1 - Reviewed Without Comments |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850003 | Welding Book (WPS,PQR Weld Map) for LBL array frame fabrication | 6 | 2014-10-11 01:00 | 2014-10-13 15:08 | AFC | 1 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850004 | Welding Repair Procedure for LBL array frame fabrication |  |  |  | not received | 2 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850005 | Dimensional Control Procedure for LBL array frame fabrication | 4 | 2014-10-09 | 2014-10-09 11:55 | AFC | 2 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850006 | Handling, Packing, Preservation & Storage Procedure for LBL array frame fabrication | 5 | 2014-10-14 | 2014-10-13 15:36 | AFC | 2 | [7 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850007 | Load out & Seafastening Procedure for LBL array frame fabrication | 0 | 2014-03-06 | 2014-03-17 09:58 | IFR | 2 | Blanco Rodriguez Juan Antonio | 3-Rejected_Nextstatus IFR | 2014-04-24 15:49 | 3 - Rejected | 2014-05-09 15:49 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-850008 | Factory Acceptance Test Procedure for LBL array frame fabrication | 0 | 2014-09-17 01:00 | 2014-09-22 16:20 | IFR | 1 | MARC Herve | 3-Rejected_Nextstatus IFR | [5 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-860001 | Inspection & Test Plan for LBL array frame fabrication | 5 | 2014-05-24 |  | AFC | 1 | Quarta Giulio | 2-Approved with comments_Nextstatus AFC | 2014-08-11 14:11 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-26 14:11 |  | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-860002 | Painting Inspection and Test Plan for LBL Array Frame Fabrication | 1 | 2014-09-18 01:00 | 2014-09-25 13:18 | IFA | 1 |  | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-870001 | Manufacturer's Data Record for LBL array frame fabrication |  |  |  | not received | 1 | [8 empty] | Y
EWT | Fab Struct Ass | 836297 | SX01 | NG-EGN-21-SX01-890001 | Weld Procedure Qualification Plan (WPQP) for LBL array frame fabrication | 5 | 2014-08-13 23:00 | 2014-08-25 15:03 | AFC | 1 | ROUSLANS Gens | 1-Approved without Comments | 2014-09-18 14:14 | 1 - Reviewed Without Comments |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700001 | Vendor Master Document List | 4 | 2014-07-14 23:00 | 2014-07-14 16:28 | AFC | 2 | Sinteh Chinakwe Kelechi | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700002 | Work Execution Schedule for EQT | 0 | 2014-07-24 01:00 | 2014-07-25 19:01 | IFR | 2 | MAUBERT Thomas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700003 | Project Quality Plan for EQT | 2 | 2014-06-16 23:00 | 2014-06-24 13:33 | AFC | 2 |  | 2-Approved with comments_Nextstatus AFC | 2014-09-01 12:29 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-16 12:29 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700004 | Organization and Mobilization Plan of the QA/QC department for EQT | 1 | 2014-04-26 | 2014-04-28 13:33 | AFC | 2 | Quarta Giulio | 1-Approved without Comments | 2014-05-20 16:11 | 1 - Reviewed Without Comments |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700006 | Health, Safety and Environmental Plan (including Risk assessment plan and emergency response plan) | 1 | 2014-05-06 | 2014-05-06 15:54 | IFA | 1 | Sodde Andrea | 2-Approved with comments_Nextstatus AFC | 2014-09-03 10:17 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-18 10:17 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700007 | Final Documentation - Preliminary Table of Content | 1 | 2014-07-14 01:00 | 2014-07-07 15:55 | IFA | 1 | Quintas Stephane | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700008 | Final Documentation - (First issue) |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700009 | PCNL - TRACEABILITY AND MARKING MATRIX FOR SAMPLE FOR EQT | 1 | 2014-08-09 23:00 | 2014-08-25 13:51 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700101 | PCNL - VENDOR MASTER DOCUMENT LIST FOR PQT | 0 | 2014-04-30 01:00 | 2014-05-06 14:49 | IFR | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | 2014-09-11 17:28 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-26 17:28 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700102 | PCNL - Work Execution Schedule | 1 | 2014-07-16 01:00 |  | AFC | 2 | Sinteh Chinakwe Kelechi | 2-Approved with comments_Nextstatus AFC | 2014-08-22 17:50 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-06 17:50 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700103 | PCNL - Project Quality Plan | 1 | 2014-07-04 01:00 | 2014-07-08 12:38 | AFC | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700104 | PCNL - Mobilization Plan of the QA/QC department | 0 | 2014-06-19 01:00 | 2014-06-24 14:00 | IFR | 2 | Singling Nicolas | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700105 | PCNL - Health Safety and Environmental Plan for PQT | 2 | 2014-08-29 01:00 | 2014-09-03 16:28 | IFA | 1 | Akanni Olukayode | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700106 | PCNL - Health Safety and Environmental Plan for PPT and Production | 0 | 2014-06-10 01:00 | 2014-06-12 17:38 | IFR | 1 | Sodde Andrea | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700107 | PCNL - Weekly report for 5-LPP | 10 | 2014-10-10 01:00 | 2014-10-13 16:29 | IFI | 3 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700108 | PCNL - Monthly report for 5-LPP | 1 | 2014-09-18 01:00 | 2014-09-26 12:01 | IFI | 3 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700109 | PCNL - Final Documentation - Preliminary table of content | 1 | 2014-07-17 01:00 | 2014-07-17 16:23 | IFA | 1 | Quintas Stephane | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700110 | PCNL - Final Documentation |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700111 | PCNL - Project Execution Plan | 1 | 2014-08-16 01:00 | 2014-08-25 13:56 | AFC | 2 | Sinteh Chinakwe Kelechi | 2-Approved with comments_Nextstatus AFC | 2014-09-15 11:27 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-30 11:27 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700201 | PCNL - Vendor Master Document List | 0 | 2014-06-02 01:00 |  | IFR | 2 | Quintas Stephane | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700202 | PCNL - Work Execution Schedule for 3-LPP | 0 | 2014-07-24 01:00 |  | IFR | 2 | Bellamoli Cedric | 3-Rejected_Nextstatus IFR | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700203 | PCNL - Project Quality Plan | 1 | 2014-07-03 01:00 |  | IFA | 1 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700204 | PCNL - Mobilization Plan of the QA/QC department | 1 | 2014-07-10 01:00 |  | AFC | 2 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700205 | PCNL - Health Safety and Environmental Plan | 0 | 2014-06-03 01:00 |  | IFR | 1 | Sodde Andrea | 1-Approved without Comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700207 | PCNL - Weekly report of 3-LPP | 11 | 2014-10-10 01:00 |  | IFI | 3 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700208 | PCNL - Monthly report for 3-LPP | 1 | 2014-09-18 01:00 |  | IFI | 3 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700209 | PCNL - Final Documentation - Preliminary table of content | 2 | 2014-08-19 01:00 |  | IFA | 1 | Quintas Stephane | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-700210 | PCNL - Final Documentation |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710001 | PCNL - 3 LPP AND 5LPP REPORT FOR EQT | 2 | 2014-07-17 | 2014-07-17 12:18 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | 2014-09-22 12:55 | 2 - Reviewed With Comments | 2014-10-07 12:55 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710002 | PCNL - Themal Insulation Design Report for EQT | 2 | 2014-08-12 | 2014-08-25 13:53 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710003 | PCNL - UV TEST PROCEDURE OF SOLID PP TOP COAT | 1 | 2014-08-08 | 2014-08-08 13:38 | AFC | 2 | Singling Nicolas | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710004 | PCNL - SST REPORT OF EQT | 1 | 2014-06-16 01:00 | 2014-06-24 13:54 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | 2014-08-19 15:49 | 2 - Reviewed With Comments | 2014-09-03 15:49 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710005 | PCNL – INSULATION OFFLINE TEST AT KORROSIONSTECHINK |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-710006 | PCNL – INSULATION OFFLINE TEST AT REDE |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-711101 | PCNL - Thermal Design report for 14" PQT | 2 | 2014-08-05 01:00 | 2014-08-06 12:43 | IFR | 1 | BONNARD Sebastien | 2-Approved with comments_Nextstatus IFA | 2014-10-09 10:45 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-24 10:45 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-711102 | PCNL - Thermal Design report for 18" PQT |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-711103 | PCNL - Thermal Design report for Production |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-722001 | TDS and MSDS of raw material for EQT | 1 | 2014-08-08 23:00 | 2014-08-25 13:47 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-722101 | PCNL - TDS and MSDS of raw materials for PQT, PPT and Production | 1 | 2014-06-10 01:00 | 2014-06-12 17:29 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-722201 | PCNL - TDS and MSDS of raw materials for PQT, PPT and Production | 2 | 2014-08-28 01:00 |  | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750001 | PCNL - Anticorrosion Coating Application Procedure for EQT | 1 | 2014-08-02 23:00 | 2014-08-06 12:37 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750003 | PCNL - Insulation Coating Application Procedure for EQT | 1 | 2014-08-05 23:00 | 2014-08-06 12:42 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750005 | Test procedures for laboratory test control (on-line and off-line), SST and FST | 2 | 2014-06-10 | 2014-06-12 13:59 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | 2014-08-04 17:39 | 1 - Reviewed Without Comments |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750006 | Handling, transportation, storage and preservation procedure | 1 | 2014-02-07 | 2014-02-07 12:23 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | 2014-06-05 16:52 | 1 - Reviewed Without Comments | 2014-06-20 16:52 | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750007 | PCNL - Long term ageing test, non-standard temperature mechanical and thernal tests for EQT | 2 | 2014-08-08 | 2014-08-25 13:48 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750008 | PCNL - SST, Creep Test and Static Bending test procedure for EQT | 1 | 2014-08-08 | 2014-08-08 13:43 | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750101 | PCNL - Marking and traceability for PQT | 2 | 2014-10-07 01:00 | 2014-10-10 11:02 | AFC | 2 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750102 | PCNL - Marking and traceability for PPT and Production |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750103 | PCNL - Handling, transportation, storage and preservation procedure for PQT | 2 | 2014-07-05 01:00 | 2014-07-07 15:55 | AFC | 2 | Clement Arnaud | 1-Approved without Comments | 2014-09-19 09:49 | 1 - Reviewed Without Comments |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750104 | PCNL - Handling, transportation, storage and preservation procedure for PPT and Production |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750105 | PCNL - Application procedure of 3-LPP for PQT, PPT and Production | 1 | 2014-06-06 01:00 | 2014-06-12 14:09 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750106 | PCNL - Repair procedure of 3-LPP for PQT, PPT and Production | 1 | 2014-06-05 01:00 | 2014-06-12 14:09 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750107 | PCNL - Application procedure of 5-LPP syn. for PQT, PPT and Production | 1 | 2014-06-09 01:00 | 2014-06-12 15:26 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750108 | PCNL - Repair & partial stripping procedure of 5-LPP syn. for PQT, PPT and Production | 1 | 2014-06-06 01:00 | 2014-06-12 14:09 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750109 | PCNL - Test procedures for quality control (on-line and off-line) for PQT, PPT and Production | 1 | 2014-06-12 01:00 | 2014-06-16 13:05 | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750110 | PCNL - Wet and dry ageing test procedures for PQT | 0 | 2014-08-28 01:00 | 2014-09-03 16:23 | IFR | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | 2014-10-09 10:45 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-24 10:45 |  | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750111 | PCNL - Full Scale Test procedures (Static Bending Test, Simulated Service Test, Tri-axial creep test) for PQT |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750112 | PCNL - UV ageing test procedure for PQT |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750113 | PCNL - Test Procedures (Simulated Service Test) for PQT | 1 | 2014-09-18 01:00 | 2014-09-22 11:12 | AFC | 2 | BONNARD Sebastien | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750114 | PCNL - Test Procedures (Static Bending Test) for PQT | 1 | 2014-09-18 01:00 | 2014-09-22 11:12 | AFC | 2 | Singling Nicolas | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750115 | PCNL - Test Procedures (Tri - Axial Creep Test) for PQT | 1 | 2014-09-18 01:00 | 2014-09-22 11:12 | AFC | 2 | Singling Nicolas | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750201 | PCNL - Marking and traceability Procedure | 1 | 2014-08-22 01:00 |  | AFC | 2 | Singling Nicolas | [6 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750203 | PCNL - Handling, transportation, storage and preservation procedure | 2 | 2014-09-23 01:00 |  | AFC | 2 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750204 | PCNL - Application procedure of 3-LPP for PQT, PPT and Production | 2 | 2014-10-07 01:00 |  | AFC | 2 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750205 | PCNL - Repair procedure of 3-LPP for PQT, PPT and Production | 1 | 2014-07-30 01:00 |  | AFC | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750206 | PCNL - Application procedure of temporary protection (Zincoprim) for PQT, PPT and Production |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750207 | PCNL - Repair & stripping procedure of temporary protection (Zincoprim) for PQT, PPT and Production |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750208 | PCNL - Test procedures for quality control (on-line and off-line) for PQT, PPT and Production | 1 | 2014-08-26 01:00 |  | AFC | 2 | Singling Nicolas | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-750209 | PCNL - Technical Querries / Devaition & Concession request Management Procedure | 1 | 2014-10-02 01:00 |  | IFR | 2 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760001 | Inspection and Test Plan of the Anticorrosion Coating | 2 | 2014-06-23 23:00 | 2014-06-24 14:01 | AFC | 1 | Quarta Giulio | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760002 | Inspection and Test Plan of the Insulation Coating | 2 | 2014-06-24 | 2014-06-24 14:01 | AFC | 1 | Quarta Giulio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760101 | PCNL - Inspection and Test Plan of 3-LPP for PQT | 2 | 2014-07-03 01:00 | 2014-07-04 13:37 | AFC | 1 | Bellamoli Cedric | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760102 | PCNL - Inspection and Test Plan of 3-LPP for PPT and Production |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760103 | PCNL - Inspection and Test Plan of 5-LPP syn. for PQT | 2 | 2014-08-04 01:00 | 2014-08-08 13:13 | AFC | 1 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760104 | PCNL - Inspection and Test Plan of 5-LPP syn. for PPT and Production |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760105 | PCNL - PQT report for 14" 5-LPP syn. |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760106 | PCNL - PQT report for 18" 5-LPP syn. |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760107 | PCNL - SST report for 14" 5-LPP syn. |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760108 | PCNL - SST report for 18" 5-LPP syn. |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760201 | PCNL - Inspection and Test Plan of 3-LPP for PQT | 2 | 2014-08-23 01:00 |  | AFC | 1 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760202 | PCNL - Inspection and Test Plan of 3-LPP for PPT and Production | 3 | 2014-10-11 01:00 |  | AFC | 1 | [7 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760203 | PCNL - Inspection and Test Plan of temporary protection (Zincoprim) for PQT |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760204 | PCNL - Inspection and Test Plan of temporary protection (Zincoprim) for PPT and Production |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760205 | PCNL - PQT report for 14" line pipes 3-LPP coated | 0 | 2014-10-07 01:00 |  | IFR | 2 |  | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760206 | PCNL - PQT report for 12" line pipes 3-LPP coated |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760207 | PCNL - PQT report for 6" line pipes 3-LPP coated |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760208 | PCNL - PQT report for temporary protection (Zincoprim) |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760209 | PCNL - Specific PPT report for 12'' line pipes 3-LPP coated (WI buckle arrestor) |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760210 | PCNL - Specific PPT report for 14'' (GE buckle arrestor) |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760211 | PCNL - Specific PPT report for 14'' (GE String pipe) |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760212 | PCNL - PPT Report for 14" line pipes 3-LPP coated |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760213 | PCNL - PPT Report for 12" line pipes 3-LPP coated |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760214 | PCNL - PPT Report for 6" line pipes 3-LPP coated |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-760215 | PCNL - PPT report for temporary protection (Zincoprim) |  |  |  | not received | 2 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-770201 | PCNL - Production Test Reports for 14" line pipes |  |  |  | not received | 3 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-770202 | PCNL - Production Test Reports for 12" line pipes |  |  |  | not received | 3 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-770203 | PCNL - Production Test Reports for 6" line pipes |  |  |  | not received | 3 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-770204 | PCNL - Production Test Reports for Temporary Protection (Zincoprim) |  |  |  | not received | 3 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-770205 | PCNL - Production Management Plan for Anticorrosion Coating |  |  |  | not received | 1 | [8 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-790101 | PCNL - Corrective and Preventive Actions Management | 0 | 2014-08-13 01:00 | 2014-08-25 13:54 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-790102 | PCNL - Non-Conformance Management Procedure | 0 | 2014-06-11 01:00 | 2014-06-16 13:05 | IFR | 2 | Singling Nicolas | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-790201 | PCNL - Corrective and Preventive Actions Management Procedure | 0 | 2014-08-13 01:00 |  | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
PCNL | EQT 5LPP | 927513 | SX02 | NG-EGN-21-SX02-790202 | PCNL - Non Conformance Management Procedure | 0 | 2014-06-11 01:00 |  | IFR | 2 | Singling Nicolas | 3-Rejected_Nextstatus IFR | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700001 | MWA - Vendor Master Document List for Anodes of LBL Array | 2 | 2014-08-01 |  | AFC | 2 | WILLIAMS Opetunde | 1-Approved without Comments | 2014-09-05 12:23 | 2FC - Reviewed With Comments and Comments on Form |  |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700002 | MWA - Subvendor List for Anodes of LBL Array | 0 | 2014-02-14 | 2014-02-18 09:08 | IFR | 2 | WILLIAMS Opetunde | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700003 | MWA - Work Execution Schedule for Anodes of LBL Array | 3 | 2014-09-19 | 2014-09-19 12:36 | AFC | 2 | WILLIAMS Opetunde | [6 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700004 | MWA - Project Quality Plan for Anodes of LBL Array | 1 | 2014-05-23 | 2014-05-27 12:33 | IFA | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | 2014-06-20 17:13 | 2 - Reviewed With Comments | 2014-07-05 17:13 |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700005 | MWA - Organisation Chart for Anodes of LBL Array | 1 | 2014-06-17 | 2014-06-24 14:34 | IFR | 2 | Blanco Rodriguez Juan Antonio | 2-Approved with comments_Nextstatus AFC | 2014-07-14 12:50 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-29 12:50 |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700006 | MWA - Health, Safety and Environmental Plan for Anodes of LBL Array | 1 | 2014-07-17 | 2014-07-21 11:32 | IFA | 1 | Akanni Olukayode | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700007 | MWA - VENDOR Data Book (VDB) Index for Anodes of LBL Array |  |  |  | not received | 1 | [8 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-700008 | MWA - VENDOR Data Book (VDB) for Anodes of LBL Array |  |  |  | not received | 1 | [8 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-740001 | MWA - FM-17 Anode Drawing | 2 | 2014-05-24 | 2014-05-27 12:33 | AFC | 2 | Njoku Chukwudi | 1-Approved without Comments | 2014-06-20 17:13 | 1 - Reviewed Without Comments |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-750001 | MWA - Anode Manufacturing Procedure for LBL Array | 2 | 2014-05-23 | 2014-05-27 12:33 | AFC | 2 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-750002 | MWA - Anode Factory Acceptance Test Procedure for LBL Array | 2 | 2014-06-03 | 2014-06-05 14:08 | AFC | 2 | Njoku Chukwudi | 1-Approved without Comments | 2014-07-08 13:50 | 1 - Reviewed Without Comments |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-750003 | MWA - Handling, Transportation, Storage and Preservation Procedure for Anodes of LBL Array | 1 | 2014-06-03 | 2014-06-05 14:08 | AFC | 2 | Bertrand Sylvain | 1-Approved without Comments | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-750004 | MWA - Identification, Tracability and Marking Procedure for Anodes of LBL Array | 1 | 2014-06-03 | 2014-06-05 14:08 | IFA | 1 | Bertrand Sylvain | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760001 | MWA - Long Term Performance Justification Report for Anodes of LBL Array | 0 | 2014-05-23 01:00 | 2014-05-27 12:33 | IFI | 3 | Njoku Chukwudi | 1-Approved without Comments | 2014-06-20 17:13 | 1 - Reviewed Without Comments |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760002 | MWA - Inspection and Test Plan for Anodes of LBL Array | 2 | 2014-05-24 | 2014-05-27 12:33 | IFA | 1 | Bertrand Sylvain | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760003 | MWA - PQT Report for Anodes of LBL Array | 1 | 2014-05-23 01:00 | 2014-05-27 12:33 | IFR | 2 | Njoku Chukwudi | 2-Approved with comments_Nextstatus AFC | 2014-06-20 17:13 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-05 17:13 |  | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760004 | MWA - RAW MATERIAL CERTIFICATE | 0 | 2014-08-05 01:00 |  | IFI | 3 | [7 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760005 | MWA - OTHER TEST REPORT | 0 | 2014-08-05 01:00 |  | IFI | 3 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760006 | MWA - VISUAL/DIMENSIONAL TEST REPORT | 0 | 2014-08-05 01:00 |  | IFI | 3 | Bellamoli Cedric | 3-Rejected_Nextstatus IFR | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760007 | MWA - PAINTING TEST REPORT | 0 | 2014-08-05 01:00 |  | IFI | 3 | Bellamoli Cedric | 1-Approved without Comments | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760008 | MWA - Calibration Certificate |  |  |  | IFR | 3 | [7 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-760009 | MWA - Certificate of Conformity of the PO |  |  |  | not received | 3 | [8 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-770001 | MWA - INSPECTION RELEASE NOTE | 1 | 2014-08-05 01:00 |  | IFI | 3 | [7 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-770002 | MWA - PRODUCTION TEST REPORT | 0 | 2014-06-10 01:00 | 2014-06-12 17:26 | IFI | 3 | Bertrand Sylvain | 1-Approved without Comments | [5 empty] | Y
METEC | ANODES FOR PERMANENT LBL ARRAY | 892951 | SX03 | NG-EGN-21-SX03-790001 | DEVIATION REQUEST |  |  |  | not received | 3 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700001 | Vendor Master Document List | 0 | 2014-04-16 09:00 | 2014-04-16 09:00 | IFR | 2 | LE-BOUTEILLER Olivier | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700002 | Work Execution Schedule (Bar Chart) | 1 | 2014-05-14 16:13 | 2014-05-14 16:13 | AFC | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700003 | Project Quality Plan | 2 | 2014-07-21 14:35 | 2014-07-21 14:35 | IFA | 1 | Blanco Rodriguez Juan Antonio | 1-Approved without Comments_Nextstatus AFC | 2014-10-13 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700004 | Monthly Progress Report | 3 | 2014-09-16 10:50 | 2014-09-22 10:50 | IFI | 3 | LE-BOUTEILLER Olivier | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700005 | List of sub-vendors | 0 | 2014-04-04 | 2014-04-07 | IFR | 2 | LE-BOUTEILLER Olivier | 2-Approved with comments_Nextstatus AFC | 2014-05-07 | 2FC - Reviewed With Comments and Comments on Form | 2014-05-22 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700006 | Recommended Spare Parts Lists (final) |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700007 | Vendor Data Book Index | 2 | 2014-08-20 10:46 | 2014-08-20 10:46 | IFA | 1 | Quintas Stephane | 1-Approved without Comments_Nextstatus AFC | 2014-10-02 | 2 - Reviewed With Comments | 2014-10-17 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-700008 | Vendor Data Book (VDB) |  |  |  | not received | 1 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-712001 | Structural Integrity Evaluation of 2.1/16" 517bar Side Entry Ball Valve | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 2 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-712002 | Structural Integrity Evaluation of 5.1/8" 690bar Side Entry Ball Valve | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 2 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-712003 | Structural Integrity Evaluation of 11" 690bar Side Entry Ball Valve | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 2 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-712004 | Structural Integrity Evaluation of 13.5/8" 517bar Side Entry Ball Valve | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 2 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-712005 | Handling & Lifting Point Calculation Note |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721001 | Material Specification for F60 Sour Service | 2 | 2014-07-14 11:13 | 2014-07-14 11:13 | IFA | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721002 | Material Specification for F60 no Sour Service | 2 | 2014-07-14 11:13 | 2014-07-14 11:13 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-08-26 | 1FC - Reviewed Without Comments but Comments on Form | 2014-09-10 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721003 | Material Specification for F65 Sour Service | 3 | 2014-10-07 18:52 |  | AFC | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721004 | Material Specification for F65 no Sour Service | 2 | 2014-07-14 11:13 | 2014-07-14 11:13 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-08-26 | 1FC - Reviewed Without Comments but Comments on Form | 2014-09-10 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721005 | Material Specification for F55 | 3 | 2014-09-11 18:29 | 2014-09-11 18:29 | IFA | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721006 | Material Specification for F51 | 3 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-721007 | Material Specification for Inconel 718 | 2 | 2014-07-17 14:03 | 2014-07-17 14:03 | AFC | 1 | Balma Pascal | 1-Approved without Comments | 2014-08-26 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-722001 | Valve Data Sheet - 2.1/16" 517bar Subsea Ball Valves ROV | 1 | 2014-08-22 18:42 | 2014-09-01 12:30 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-09-16 | 2 - Reviewed With Comments | 2014-10-01 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-722002 | Valve Data Sheet - 5.1/8" 10000psi Subsea Ball Valves GEAR | 1 | 2014-09-01 12:30 | 2014-09-01 12:30 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-10-07 | 2 - Reviewed With Comments | 2014-10-22 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-722003 | Valve Data Sheet - 11" 10000psi Subsea Ball Valves GEAR | 1 | 2014-09-01 12:30 | 2014-09-01 12:30 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-10-07 | 2 - Reviewed With Comments | 2014-10-22 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-722004 | Valve Data Sheet - 13.5/8" Subsea Ball Valves GEAR | 1 | 2014-09-01 18:52 | 2014-09-01 12:30 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-10-07 | 2 - Reviewed With Comments | 2014-10-22 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-722005 | Valve Data Sheet - 13.5/8" Subsea Ball Valve FSC Hydraulic Actuated | 1 | 2014-09-01 12:30 | 2014-09-01 12:30 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-10-01 | 2 - Reviewed With Comments | 2014-10-16 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730001 | General Assembly Drawing and Bill of Materials Subsea Side Entry Ball Valve 2.1/16" - 7500 PSI | 2 | 2014-05-30 13:42 | 2014-05-30 13:42 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-07-04 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-19 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730002 | General Assembly Drawing and Bill of Material Subsea Side Entry Ball Valve Gear Operated 5.1/8" - 10000 PSI | 2 | 2014-06-19 16:09 | 2014-06-23 16:09 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-07-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-08 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730003 | General Assembly Drawing and Bill of Materials Subsea Side Entry Ball Valve Gear Operated 11" - 10000 PSI | 2 | 2014-06-19 16:09 | 2014-06-23 16:09 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-07-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-08 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730004 | General Assembly Drawing and Bill of Materials Subsea Side Entry Ball Valve Gear Operated 13.5/8" - 7500 PSI | 2 | 2014-06-19 16:09 | 2014-06-23 16:09 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-07-24 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-08 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730005 | General Assembly Drawing and bill of materials Subsea Side Entry Ball Valve + FSC Hydraulic Actuated 13.5/8" - 7500 PSI | 3 | 2014-08-22 18:52 | 2014-09-01 18:52 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-10-09 | 2 - Reviewed With Comments | 2014-10-24 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730006 | General Assembly Drawing for FSC Actuator | 0 | 2014-04-03 01:00 | 2014-04-08 01:00 | IFR | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-04-30 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-05-15 01:00 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730007 | General Assembly Drawing and Bill of Materials Actuator Stop for Subsea Side Entry Ball Valve 13" - 7500 PSI | 1 | 2014-05-12 10:54 | 2014-05-21 09:28 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-06-11 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730008 | General Assembly Drawing and Bill of Materials Gear for Subsea Side Entry Ball Valve 13" - 7500 PSI | 1 | 2014-05-12 09:28 | 2014-05-21 09:28 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-06-11 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730009 | General Assembly Drawing and Bill of Materials Gear for Subsea Side Entry Ball Valve 11" - 10000 PSI | 1 | 2014-05-12 09:28 | 2014-05-21 09:28 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-06-11 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730010 | General Assembly Drawing and Bill of Materials Gear for Subsea Side Entry Ball Valve 5.1/8" - 10000 PSI | 1 | 2014-05-12 09:28 | 2014-05-21 09:28 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-06-11 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730011 | General Assembly Drawing for Protection Cap | 0 | 2014-04-03 01:00 | 2014-04-08 01:00 | IFR | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-04-30 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-05-15 01:00 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730012 | Overall Dimension Drawing Subsea Side Entry Ball Valve 2.1/16" - 7500 PSI | 2 | 2014-06-10 15:13 | 2014-06-11 15:13 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-07-08 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730013 | Overall Dimension Drawing Subsea Side Entry Ball Valve - Water Injection System 5.1/8" - 10000 PSI | 1 | 2014-05-15 11:44 | 2014-05-19 11:44 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-06-06 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-21 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730014 | Overall Dimension Drawing Subsea Side Entry Ball Valve Manually ROV Operated 11" - 10000 PSI | 1 | 2014-06-10 09:03 | 2014-06-16 09:03 | IFR | 2 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-07-24 | 1FC - Reviewed Without Comments but Comments on Form | 2014-08-08 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730015 | Overall Dimension Drawing Subsea Side Entry Ball Valve Gear Operated - Isolation Valve for Gas Export - 13.5/8" - 7500 PSI | 1 | 2014-05-08 19:02 | 2014-05-14 15:10 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-06-04 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-19 01:00 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730016 | Overall Dimension Drawing Subsea Side Entry Ball Valve + FSC - Gas Export Isolation Valve - 13.5/8" - 7500 PSI | 1 | 2014-05-08 15:10 | 2014-05-14 15:10 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-06-04 01:00 | 2FC - Reviewed With Comments and Comments on Form | 2014-06-19 01:00 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730017 | 3D Model for 2.1/16" 7500psi Ball Valves | 0 | 2014-09-24 16:53 | 2014-09-25 16:53 | IFR | 2 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730018 | 3D Model for 5.1/8" 10000psi Ball Valves |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730019 | 3D Model for 11" 10000psi Ball Valves | 0 | 2014-09-24 16:53 | 2014-09-25 16:53 | IFR | 2 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730020 | 3D Model for 13.5/8" 7500psi Ball Valves + Gear | 0 | 2014-09-24 16:53 | 2014-09-25 16:53 | IFR | 2 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730021 | 3D Model for 13.5/8" 7500psi Ball Valves + FSC |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730022 | General Assembly Drawing for Test Ring - Subsea Side Entry Ball Valve | 1 | 2014-06-04 20:22 | 2014-06-04 20:22 | AFC | 2 | Balma Pascal | 2-Approved with comments_Nextstatus AFC | 2014-07-15 | 2FC - Reviewed With Comments and Comments on Form | 2014-07-30 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730023 | Torque Tool for Receptacle ISO 13628-8 Class 4 - General Assembly Drawing and Bill of Materials | 1 | 2014-07-21 16:08 | 2014-07-28 16:08 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-09-02 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-730024 | Overall Dimension Drawing Subsea Side Entry Ball Valve 5.1/8" - 10000 PSI |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-740001 | Wiring Diagram For Actuator Position Sensor Drawing For Subsea Side Entry Ball Valve 13" - 7500 PSI | 3 | 2014-09-11 18:29 | 2014-09-11 18:29 | AFC | 2 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750001 | Tungsten Carbide Coating Procedure | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750002 | Localized PWHT Procedure | 0 | 2014-09-29 14:54 | 2014-09-25 16:53 | IFR | 1 |  | 3-Rejected_Nextstatus IFR | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750003 | Surface Preparation and Painting Procedure for Subsea Ball Valves | 4 | 2014-09-12 19:08 | 2014-09-15 19:08 | IFA | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750004 | Positive Material Identification Procedure | 2 | 2014-09-16 14:34 | 2014-09-16 14:34 | AFC | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750005 | Dye Penetrant Inspection Procedure | 2 | 2014-08-20 11:55 | 2014-08-20 11:55 | AFC | 1 | Balma Pascal | 1-Approved without Comments | 2014-09-08 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750006 | Magnetic Particle Inspection Procedure | 2 | 2014-08-20 11:55 | 2014-08-20 11:55 | AFC | 1 | Balma Pascal | 1-Approved without Comments | 2014-09-08 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750007 | Ultrasonic Inspection Procedure (forgings) | 2 | 2014-08-20 11:55 | 2014-08-20 11:55 | AFC | 1 | Balma Pascal | 1-Approved without Comments | 2014-09-08 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750008 | Ultrasonic Inspection Procedure (welding overlay) | 2 | 2014-08-20 11:55 | 2014-08-20 11:55 | AFC | 1 | Balma Pascal | 1-Approved without Comments | 2014-09-08 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750009 | Ultrasonic Inspection Procedure (welds) | 2 | 2014-10-07 18:52 |  | AFC | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750010 | Radiographic Test Procedure | 2 | 2014-10-07 18:36 |  | AFC | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750011 | FAT Procedure for 13.5/8" 7500psi Ball Valves + FSC including simulated Hyperbaric Procedure | 0 | 2014-09-05 09:46 | 2014-09-05 09:46 | IFR | 1 | Balma Pascal | 3-Rejected_Nextstatus IFR | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750012 | FAT Procedure for Ball Valves + Gear including Hyperbaric Procedure | 0 | 2014-09-02 18:53 | 2014-09-02 18:53 | IFR | 1 | Balma Pascal | 3-Rejected_Nextstatus IFR | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750013 | Actuator Factory Acceptance for Test Procedure | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFR | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750014 | Subsea Gearbox Factory Acceptance Test Procedure | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFR | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750015 | Cleaning and Flushing Procedure for Subsea Hydraulic Actuators | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFA | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750016 | Cleaning and Preservation Shipping, Handling & Storage Procedure |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750017 | Manufacturing Process Specification for ASTM A694 F60/F65 for 11" (sweet service) | 2 | 2014-09-23 12:04 | 2014-09-23 12:04 | AFC | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750018 | Manufacturing Process Specification for ASTM A694 F60/F65 for 5.1/8" (sweet service) | 1 | 2014-07-29 16:53 | 2014-08-08 16:53 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus IFA | 2014-08-28 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-12 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750019 | Manufacturing Process Specification for F51 for 2" (sour service) - Forge Fedriga | 1 | 2014-08-05 11:51 | 2014-08-05 11:51 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-08-28 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-12 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750020 | Welding Book for Overlay, Inconel rods into bodies and Overlay repairs for sour | 3 | 2014-09-16 17:52 | 2014-09-16 17:52 | IFR | 1 | Blin Nicolas | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750021 | Welding Procedure and Repair for Pups to Body 5.1/8" (non sour service) | 2 | 2014-09-16 17:52 | 2014-09-16 17:52 | IFA | 1 | Balma Pascal | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750022 | Welding Book for fabrication welds and plugs sealing | 3 | 2014-09-16 08:38 | 2014-09-16 14:34 | AFC | 1 | Blin Nicolas | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750023 | Welding Procedure and Repair for Pups to Body 11" (non sour service) | 0 | 2014-09-15 19:08 | 2014-09-15 19:08 | IFR | 1 | Balma Pascal | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750024 | Pickling and Passivation Procedure | 1 | 2014-06-23 09:10 | 2014-06-25 09:10 | AFC | 2 | Balma Pascal | 1-Approved without Comments | 2014-07-21 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750025 | Welding Book for Overlay, Inconel rods into bodies and Overlay repairs for Non Sour | 2 | 2014-09-16 17:52 | 2014-09-16 17:52 | IFA | 1 | Blin Nicolas | [6 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750026 | Welding Procedure and Repair for Pups to Body 13.5/8" (sour service) | 0 | 2014-09-15 19:08 | 2014-09-15 19:08 | IFR | 1 | Balma Pascal | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750027 | Welding Procedure and Repair for Pups to Body 2.1/6" (sour service) | 1 | 2014-08-13 14:40 | 2014-08-13 14:40 | IFA | 1 | Balma Pascal | 2-Approved with comments_Nextstatus IFA | 2014-09-09 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-24 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750028 | Manufacturing Process Specification for ASTM A694 F60/F65 for 13" (sour service) | 1 | 2014-08-06 09:08 | 2014-08-06 09:08 | IFA | 1 | Balma Pascal | 2-Approved with comments_Nextstatus IFA | 2014-08-28 | 2 - Reviewed With Comments | 2014-09-12 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750029 | Manufacturing Process Specification for A182 F55 Forge Fedriga | 1 | 2014-08-05 11:51 | 2014-08-05 11:51 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-08-28 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-12 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750030 | Manufacturing Process Specification for Inconel 718 - Forge Fedriga | 1 | 2014-08-05 11:51 | 2014-08-05 11:51 | IFA | 1 | Balma Pascal | 1-Approved without Comments_Nextstatus AFC | 2014-08-28 | 2FC - Reviewed With Comments and Comments on Form | 2014-09-12 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-750031 | Procedure for Phased Array Ultrasonic Examination of (body end to pipe end butt weld) | 0 | 2014-07-18 09:07 | 2014-07-18 09:07 | IFR | 2 | Balma Pascal | 2-Approved with comments_Nextstatus IFA | 2014-09-18 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-03 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760001 | Inspection & Test Plan for Ball valves 2.1/16" 7500psi | 4 | 2014-09-26 18:29 | 2014-09-29 | IFA | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760002 | Inspection & Test Plan (Hydraulic actuator for 13.5/8" Ball valve) | 4 | 2014-10-07 18:52 |  | AFC | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760003 | Inspection & Test Plan for Ball valves 5.1/8" 10000psi | 2 | 2014-09-26 18:29 | 2014-09-29 | IFA | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760004 | Inspection & Test Plan for Ball valves 11" 10000psi | 3 | 2014-09-26 18:29 | 2014-09-29 | IFA | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760005 | Inspection & Test Plan for Ball valves 13.5/8" 7500psi SIV | 3 | 2014-09-26 18:29 | 2014-09-29 | IFA | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760006 | Quality Control Plan Painting Activities | 1 | 2014-09-26 18:29 | 2014-09-29 | IFR | 1 | [7 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760007 | Inspection & Test Plan for Ball valves 13.5/8" 7500psi Gearbox | 0 | 2014-04-29 16:09 | 2014-04-29 17:00 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | 2014-09-23 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-08 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760008 | ITP - Forgiatura Marcora - for ASTM A694 F60/F65 for 11" (sweet service) | 0 | 2014-06-12 16:52 | 2014-06-12 16:52 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | 2014-08-11 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-26 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760009 | ITP - Valforge - for ASTM A694 F60/F65 for 5.1/8" (sweet service) | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFA | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760010 | ITP - Forge Fedriga for 2" (sour service) | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFA | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760011 | ITP - Forgiatura Marcora - for ASTM A694 F60/F65 for 13" (sour service) | 0 | 2014-07-03 16:54 | 2014-07-03 16:54 | IFR | 1 | Vernouillet Philippe | 2-Approved with comments_Nextstatus IFA | 2014-08-11 | 2FC - Reviewed With Comments and Comments on Form | 2014-08-26 |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760012 | ITP - Forge Fedriga - for A182 F55 | 1 | 2014-09-12 15:49 | 2014-09-15 19:14 | IFA | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-760013 | ITP- Forge Fedriga - for Inconel 718 | 1 | 2014-09-12 19:14 | 2014-09-15 19:14 | IFA | 1 | Vernouillet Philippe | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-770001 | NDT Operators List & Qualifications | 1 | 2014-05-15 15:12 | 2014-05-15 15:12 | AFC | 2 | Feuilly Nicolas | 1-Approved without Comments | 2014-06-19 | 1 - Reviewed Without Comments |  | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-770002 | List of Welders and Welding Operators Performance Qualifications applicable to Egina Project for Weld Metal Overlay | 0 | 2014-05-14 10:55 | 2014-05-14 10:55 | IFR | 2 | Vernouillet Philippe | 3-Rejected_Nextstatus IFR | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-770003 | 3.2 Material Certificate with Traceability Sheet |  |  |  | not received | 0 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-770004 | List of Welders and Welding Operators Performance Qualifications applicable to Egina Project for Fabrication | 0 | 2014-05-14 10:55 | 2014-05-14 10:55 | IFR | 2 | Vernouillet Philippe | 3-Rejected_Nextstatus IFR | [5 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-780001 | Operating and Maintenance Manual for Ball Valves with FSC |  |  |  | not received | 2 | [8 empty] | Y
CAMERON | Supply of Subsea Ball Valves | 914144 | SX04 | NG-EGN-21-SX04-780002 | Operating and Maintenance Manual for Ball Valves Gear operated |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700001 | MWA - Vendor Master Document List for Anodes of SCNL and EWT structures and linepipes | 0 | 2014-08-20 01:00 | 2014-09-03 16:22 | IFR | 2 | WILLIAMS Opetunde | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700002 | MWA - Work Execution Schedule for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700003 | MWA - Project Quality Plan for Anodes of SCNL and EWT structures and linepipes | 0 | 2014-08-22 01:00 | 2014-09-03 16:23 | IFR | 2 | Aaron Philip | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700004 | MWA - Health, Safety and Environmental Plan for Anodes of SCNL and EWT structures and linepipes | 0 | 2014-08-22 01:00 | 2014-09-03 16:23 | IFR | 1 | Ohiaeri Ijeoma | 2-Approved with comments_Nextstatus AFC | 2014-09-18 15:12 | 2FC - Reviewed With Comments and Comments on Form | 2014-10-03 15:12 |  | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700005 | MWA - Health, Safety and Environmental risk Assessment for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700006 | MWA - Final Documentation - Table of Content for flush mounted and stand off Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700007 | MWA - Final Documentation - Data Record for flush mounted and stand off Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700008 | MWA - Final Documentation - Table of Content for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700009 | MWA - Final Documentation - Data Record for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700010 | MWA - Coordination and execution plan for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700011 | MWA - Emergency Response Plan for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-700012 | MWA - Monthly Report for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740001 | MWA - FM-92 Anode Drawing | 1 | 2014-08-20 01:00 | 2014-09-08 16:40 | AFC | 2 | Ogunsola Abiodun | 1-Approved without Comments | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740002 | MWA - FM-86 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740003 | MWA - FM-71 Anode Drawing | 0 | 2014-08-29 01:00 | 2014-09-03 16:24 | IFR | 2 | Ogunsola Abiodun | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740004 | MWA - FM-55 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740005 | MWA - FM-38 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740006 | MWA - FM-17 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740007 | MWA - FM-14 Anode Drawing | 0 | 2014-08-20 01:00 | 2014-09-03 16:22 | IFR | 2 | Ogunsola Abiodun | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740008 | MWA - FM-12 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740009 | MWA - FM-06 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740010 | MWA - FM-01 Anode Drawing | 0 | 2014-08-29 01:00 | 2014-09-03 16:24 | IFR | 2 | Ogunsola Abiodun | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740011 | MWA - ST-235 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740012 | MWA - ST-140 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740013 | MWA - ST-100 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740014 | MWA - ST-90 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740015 | MWA - BR-P35 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740016 | MWA - BR-P36 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740017 | MWA - BR-W42 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740018 | MWA - BR-W17 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740019 | MWA - BR-G52 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-740020 | MWA - BR-G50 Anode Drawing |  |  |  | not received | 2 | [8 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750001 | MWA - Anode Manufacturing Procedure for flush mounted and stand off anodes | 0 | 2014-08-20 01:00 | 2014-09-03 16:22 | IFR | 2 | Ogunsola Abiodun | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750002 | MWA - Anode Manufacturing Procedure for bracelet anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750003 | MWA - Anode Factory Acceptance Test Procedure for flush mounted and stand off anodes | 0 | 2014-08-20 01:00 | 2014-09-03 16:22 | IFR | 2 | Ogunsola Abiodun | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750004 | MWA - Anode Factory Acceptance Test Procedure for bracelet anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750005 | MWA - Handling, Transportation, Storage and Preservation Procedure for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-750006 | MWA - Identification, Traceability and Marking Procedure for Anodes of SCNL and EWT structures and linepipes | 0 | 2014-09-02 01:00 | 2014-09-03 16:25 | IFR |  | Bellamoli Cedric | 2-Approved with comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760001 | MWA - Inspection and Test Plan for flush mounted and stand off Anodes | 0 | 2014-08-20 01:00 | 2014-09-03 16:22 | IFR | 1 | Bellamoli Cedric | 2-Approved with comments_Nextstatus IFA | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760002 | MWA - Inspection and Test Plan for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760003 | MWA - Long Term Performance Justification Report for Anodes of SCNL and EWT structures and linepipes | 0 | 2014-09-06 01:00 | 2014-09-08 16:40 | IFI | 3 | Ogunsola Abiodun | 1-Approved without Comments | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760004 | MWA - PQT Report for FM-92 Anodes | 0 | 2014-09-09 01:00 | 2014-09-10 14:44 | IFR | 2 | Ogunsola Abiodun | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760005 | MWA - PQT Report for FM-86 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760006 | MWA - PQT Report for FM-71 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760007 | MWA - PQT Report for FM-55 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760008 | MWA - PQT Report for FM-38 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760009 | MWA - PQT Report for FM-17 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760010 | MWA - PQT Report for FM-14 Anodes | 0 | 2014-09-09 01:00 | 2014-09-10 14:44 | IFR | 2 | Ogunsola Abiodun | 1-Approved without Comments_Nextstatus AFC | [5 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760011 | MWA - PQT Report for FM-12 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760012 | MWA - PQT Report for FM-06 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760013 | MWA - PQT Report for FM-01 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760014 | MWA - PQT Report for ST-235 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760015 | MWA - PQT Report for ST-140 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760016 | MWA - PQT Report for ST-100 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760017 | MWA - PQT Report for ST-90 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760018 | MWA - PQT Report for BR-P35 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760019 | MWA - PQT Report for BR-P36 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760020 | MWA - PQT Report for BR-W42 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760021 | MWA - PQT Report for BR-W17 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760022 | MWA - PQT Report for BR-G52 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760023 | MWA - PQT Report for BR-G50 Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760024 | MWA - RAW MATERIAL CERTIFICATES FOR FLUSH MOUNTED AND STAND OFF ANODES | 0 | 2014-09-11 01:00 | 2014-09-12 16:56 | IFI | 3 | Bellamoli Cedric | [6 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760025 | MWA- Other Test Reports for flush mounted and stand off Anodes | 0 | 2014-09-12 01:00 | 2014-09-12 16:23 | IFI | 3 | Bellamoli Cedric | [6 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760026 | MWA - Visual / Dimensional Test Reports for flush mounted and stand off Anodes | 0 | 2014-09-11 01:00 | 2014-09-12 16:56 | IFI | 3 | Bellamoli Cedric | [6 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760027 | MWA - Painting Test Reports for flush mounted and stand off Anodes | 0 | 2014-09-12 01:00 | 2014-09-12 16:23 | IFI | 3 | Bellamoli Cedric | [6 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760028 | MWA- Raw Material Certificates for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760029 | MWA- Other Test Reports for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760030 | MWA - Visual / Dimensional Test Reports for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-760031 | MWA - Painting Test Reports for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770001 | MWA - Anodes and Accessories Supply List |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770002 | MWA - Welder List and Qualifications |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770003 | MWA - NDT Operators List and Qualification |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770004 | MWA - Inspection Release Note for flush mounted and stand off Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770005 | MWA - Welding Books for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770006 | MWA - NDT Records for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770007 | MWA - Inspection Release Note for Bracelet Anodes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-770008 | MWA - Technical Data Sheet of Paint and Accessories for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
METEC | BLANKET ORDER FOR ANODES | 5000024922 | SX05 | NG-EGN-20-SX05-790001 | MWA - Deviation Request for Anodes of SCNL and EWT structures and linepipes |  |  |  | not received | [9 empty] | Y
Afficher tout