## Assembly board
1
ZASE | [5 empty] | FY 16 | [57 empty] | FY 17 | [51 empty] | FY 18 | [51 empty] | STUB | [16 empty] | FY 19 | [51 empty] | FY 20 | [47 empty] | FY 21
| Month | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Janv. |  |  |  | Févr. |  |  |  | Mars |  |  |  | Avr. |  |  |  | Mai |  |  |  | Juin |  |  |  | Juil. |  |  |  | Août |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  | Déc. |  |  |  | Janv.
| Date |  |  |  |  | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24
| Week Number | 4 | 11 | 18 | 25 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
| Material due | 18: Type 5 Belge (frein); 22: PIV Belge; 36: ATLAS France
| Firm | 3: M6 France 1; 4: Type Bangla; 5: Type 5 Czech 1.2; 9: WT NLD 1; 12: M6 France Filtres; 17: WT NLD 3; 22: 500S Belge; 23: Type 5 Belge (pieces); 29: 500S Belge; 32: 500S Belge
| Not Firm / TBC | 3: M6 France 2; 5: Type 5 Czech 3.4; 9: WT NLD 2; 18: Bangladesh PR14858; 22: Italy; 29: Colombie; 32: Czech Rep; 37: M6 France; 38: WT
| Shipping | 5: 500S France
NEW | M6 | 19: Poulies France 631251 Qty: 8-1; 25: Poulies France Qty: 8-1
| TYPE H | 10: USAF H45-200 Qty:2 P/N: 218402 UBO:829281 - 2; 15: Getafe Montage TYPE H - 1; 38: Belgique Montage TYPE H - 1
BFB
| TYPE 5 | 14: DUBAI type 5 qty: 4 ET:71471A CO:826773 -2; 44: Bengladesh Montage Type 5 -1 - 1
61QS
OVERHAUL | M6 | 4: FRANCE M6 P/N:905163 S/N:37-38 CO: - 2; 13: FRANCE M6 P/N:905163 S/N:31-32 CO: - 2; 2: FRANCE MCO ATLAS CO: 687481 - 2; 12: ATLAS -2; 10: REP TCHEQUE Demont M6 - 1; 15: ST; 18: Montage M6 - 1; 33: REP TCHEQUE Demont M6 - 1; 38: ST; 41: Montage M6 - 1
[61 empty] | PB Cazaux -2 | [6 empty] | Poulies M6 PN: 905159 Qty: 18 -2 | [125 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1 | [14 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
[194 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1 | [14 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
[194 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1 | [14 empty] | REP TCHEQUE Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
[220 empty] | Belgique Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1 | [12 empty] | Belgique Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
[220 empty] | Belgique Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1 | [12 empty] | Belgique Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
| PIV | 17: PIV BELGIUM S/N:Tr555/556 P/N: 905321 CO:704280 - 2; 27: PIV BELGIUM S/N:Tr555/556 P/N: 905321 CO:704280 - 2; 20: Belgique Demont PIV - 1; 24: ST; 27: Montage PIV - 1; 36: Belgique Demont PIV - 1; 40: ST; 43: Montage PIV - 1
[61 empty] | PIV P/N: 905321 - 2 | [10 empty] | PIV P/N: 905321 - 2 | [131 empty] | Belgique Demont PIV - 1 |  |  |  | ST |  |  | Montage PIV - 1 | [8 empty] | Belgique Demont PIV - 1 |  |  |  | ST |  |  | Montage PIV - 1
| 500S | 10: FRANCE Stock état - 1; 30: FRANCE Stock état - 1; 37: France MCO Stock Etat P/N: 905262 CO: - 2; 2: France MCO pour installation NANCY P/N: 905262 CO: - 1; 17: 500S -1; 47: Tours Demont 500S - 1; 49: ST; 52: Montage 500S - 1
[32 empty] | FRANCE Stock état - 1 | [20 empty] | FRANCE Stock état - 1 | [10 empty] | France MCO Stock Etat P/N: 905262 CO: - 2 | [17 empty] | France MCO pour installation NANCY P/N: 905262 CO: - 1 | [14 empty] | 500S -1 | [81 empty] | Tours Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 | [24 empty] | Belgique Demont 500S - 1 |  | ST |  |  | Montage 500S - 1
Poulies de renvoie 500S fosse 905322 Qty 2 -1
[61 empty] | PB Peinture FMX -2 |  |  | PB Peinture FMX -2
[13 empty] | BELGIUM - 2 | [5 empty] | FRANCE MCO ISTRES - 2 | [32 empty] | FRANCE MCO ISTRES - 2 | [129 empty] | Solenzarra Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 | [8 empty] | Djibouti Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 | [16 empty] | Stock etat Demont 500S - 1 |  | ST |  |  | Montage 500S - 1
[182 empty] | Solenzarra Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 | [8 empty] | Djibouti Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 |  |  |  |  | Djibouti Demont 500S - 1 |  | ST |  |  | Montage 500S - 1 | [6 empty] | Stock etat Demont 500S - 1 |  | ST |  |  | Montage 500S - 1
| Type 5 | 4: BELGIUM P/N: 905327 Mov: 679076- 1; 24: BELGIUM P/N: 905327 cdv: 679102- 1; 3: Belgique Demont Type5 - 1; 4: ST; 7: Montage Type 5 - 1
[46 empty] | CZECH REP P/N:905189 Qty:2 Cdv :679120 - 1 |  |  |  | CZECH REP P/N:905189 Qty:2 Cdv :679120 - 1 | [143 empty] | Demont Type5 - 1 | ST |  |  | Montage Type 5 - 1
[194 empty] | Demont Type5 - 1 | ST |  |  | Montage Type 5 - 1
[27 empty] | Proof L T BANGLADESH CDV: 602888 1 - 1 | [18 empty] | CZECH REP P/N:905189 Qty:2 Cdv :679120 - 1 |  |  |  | CZECH REP P/N:905189 Qty:2 Cdv :679120 - 1
| WT | 14: WT NETHERLAND P/N: 905305 CDV: 704237- 2; 20: WT NETHERLAND P/N: 905305 CDV: 704237- 2; 32: WT NETHERLAND P/N: 905305 CDV: 704237- 2; 51: Pays Bas Demont WT - 1; 2: ST; 5: Montage WT - 1
[37 empty] | WT NETHERLAND P/N: 905305 CDV: 704237- 2 |  |  |  |  | WT NETHERLAND P/N: 905305 CDV: 704237- 2 | [11 empty] | WT NETHERLAND P/N: 905305 CDV: 704237- 2 | [15 empty] | WT NETHERLAND SN: 005 P/N: 905305 - 2 | [112 empty] | Pays Bas Demont WT - 1 |  |  | ST |  |  | Montage WT - 1
[47 empty] | WT NETHERLAND P/N: 905305 CDV: 724290 - 2 | [16 empty] | WT NETHERLAND SN: 004 P/N: 905305- 2
BAK 12
TRAINING |  | 43: MOROCCO 500S - 1; 27: Solenzara - 1; 32: Cazaux - 1; 36: iran; 47: WT NLD; 18: ATLAS ISTRES; 20: Solenzarra - 1; 25: Tours -1; 46: Djibouti - 1
| ManPower Req |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 4 | 4 | 4 | 4 | 3 | 5 | 2 | 2 | 2 | 4 | 6 | 6 | 8 | 6 | 5 | 7 | 5 | 4 | 4 | 7 | 4 | 2 | 5 | 8 | 7 | 10 | 9 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 8 | 6 | 6 | 8 | 4 | 6 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | -2 | -2 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 4 | 4 | 4 | 2 | 5 | 2 | 4 | 4 | 3 | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 6 | 6 | 9 | 7 | 7 | 7 | 4 | 6 | 2 | 3 | 3 | 3 | 4 | 3 | 3 | 7 | 8 | 8 | 8 | 8 | 4 | 6 | 4 | 6 | 6 | 6 | 8 | 8 | 9 | 9 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | bar: 17; 28; 30 to 32; 37 to 38; 41; 20; 34 to 37; 44 to 48
7 | bar: 17; 20; 24; 28 to 32; 37 to 38; 41; 20 to 23; 33 to 37; 44 to 48
6 | bar: 15 to 18; 20; 24; 28 to 32; 37 to 41; 43; 10; 12 to 14; 18 to 23; 25; 33 to 37; 39; 41 to 48
5 | bar: 4; 10; 15 to 21; 24; 27 to 33; 37 to 41; 43; 3; 10; 12 to 14; 18 to 23; 25; 33 to 37; 39; 41 to 48
4 | bar: 4 to 8; 10; 14 to 25; 27 to 33; 37 to 44; 2 to 11; 51 to 1; 3; 5 to 6; 10 to 14; 18 to 25; 30; 33 to 51
3 | bar: 4 to 10; 14 to 25; 27 to 33; 37 to 44; 2 to 11; 51 to 1; 3; 5 to 25; 27 to 51
2 | bar: 49 to 34; 34 to 49; 2 to 14; 47 to 48; 50 to 51; 57 to 61; 65 to 72
1 | bar: 49 to 34; 34 to 49; 53; 2 to 14; 47 to 48; 50 to 51; 57 to 61; 65 to 72

## Templates
| Week Number | N°1 | N°2 | N°3 | N°4 | N°5 | N°6 | N°7 | N°8 | N°9 | N°10 | N°11 | N°12 | N°13 | N°14 | N°15 | N°16
NEW | M6 | N°1: Montage M6 - 1; N°9: 7s; N°11: 1 frein
|  | Montage M6 - 1 | [9 empty] | 1 frein
|  | Montage M6 - 1 | [9 empty] | 1 frein
| TYPE H | N°1: Montage TYPE H - 1; N°9: 3s; N°11: 1 dispo
|  | Montage TYPE H - 1 | [9 empty] | 1 dispo
|  | Montage TYPE H - 1 | [9 empty] | 1 dispo
| BFB | N°1: Montage BFB - 1; N°9: 2s; N°11: 1 frein
|  | Montage BFB - 1 | [9 empty] | 1 frein
|  | Montage BFB - 1 | [9 empty] | 1 frein
| TYPE 5 | N°1: Montage Type 5 - 1; N°9: 3s; N°11: 1 mât
|  | Montage Type 5 - 1 | [9 empty] | 1 mât
|  | Montage Type 5 - 1 | [9 empty] | 1 mât
| TYPE 5-1 | N°1: Montage Type 5-1 - 1; N°9: 3s; N°11: 1 mât
|  | Montage Type 5-1 - 1 | [9 empty] | 1 mât
|  | Montage Type 5 -1 - 1 | [9 empty] | 1 mât
OVERHAUL | M6 | N°1: Demont M6 - 1; N°6: ST; N°9: Montage M6 - 1 | 16s | 5s | 8s | Pour un frein |  | 477,94 heures | 79.6667 | jours
|  | Demont M6 - 1 |  |  |  |  | ST |  |  | Montage M6 - 1
M6 : - 1
| PIV | N°1: Demont PIV - 1; N°5: ST; N°8: Montage PIV - 1 | 16s | 4s | 9s | Pour un frein |  | 488 heures | 81.3333 | jours
|  | Demont PIV - 1 |  |  |  | ST |  |  | Montage PIV - 1
PIV : - 1
| 500S | N°1: Demont 500S - 0,5; N°3: ST; N°6: Montage 500S - 0,5; N°12: 16s; N°13: 5s; N°14: 8s |  |  |  |  | Pour un frein | 175,5 heures | 29.25 | jours
|  | Demont 500S - 0,5 |  | ST |  |  | Montage 500S - 0,5
500S : - 1
| Type 5 | N°1: Demont Type5 - 0,5; N°2: ST; N°5: Montage Type 5 - 0,5; N°13: 13s; N°14: 3s; N°15: 7s |  |  |  |  | Pour un mât | 107,45 heures | 17.9083 | jours
|  | Demont Type5 - 0,5 | ST |  |  | Montage Type 5 - 0,5
Type 5 : - 1
| WT | N°1: Demont WT - 1; N°4: ST; N°7: Montage WT - 1; N°14: 16s; N°15: 5s; N°16: 7s |  |  |  |  | Pour un frein | 260 heures | 43.3333 | jours
|  | Demont WT - 1 |  |  | ST |  |  | Montage WT - 1
WT : - 1
| BAK 12 | N°1: Demont BAK12 - 1; N°3: ST; N°6: Montage BAK12 - 1; N°12: 9s; N°13: 2s; N°14: 4s | [5 empty] | 250 heures
|  | Demont BAK12 - 2 |  | ST |  |  | Montage BAK12 - 1