## Feuil1
Project No. | Time | Place | Inspection Item | Insp. Characteristic | Inspector | M.P. | GTT | GTT | GTT
2298 | 09:10 | "3L" | NO.2 C.T "3L" REMOVAL OF MAIN SCAFFOLD | CONFIRMATION INSP. | Gyeong In Park | 010-2648-1538
2298 | 09:30 | "9L" | NO.1 TK "P" MEMB" CLEANING INSP.(9L) | CARGO P/P TOWER MAST GUIDE FIT-UP | SEUNG GU KWON | 010-6674-4355
2298 | 09:30 | "9L" | NO.1 C.T."S" 'MEME 'STRENGTH TEST | MEMB. MECHANICAL STRENGTH TEST | SEUNG GU KWON | 010-6674-4355
2298 | 14:30 | "J" WALL | NO. 3 C.T S/OPENING AREA SEC' BOX FIT UP | SEC.S/OPENING BOX FIT-UP INSP. | Gyeong In Park | 010-2648-1538
2298 | 15:30 | "J" WALL | NO. 3 C.T S/OPENING AREA SEC' BOX FINAL. | SEC.S/OPENING BOX FINAL INSP. | Gyeong In Park | 010-2648-1538
2400 | 8:50 | "BG" T/CORNER | NO.1 C.T (BD/GKC 1~0L) A/BAR FIT-UP(IPI) | A/BAR FIT-UP INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 09:00 | "6L" | NO. 3 C.T ( "B/F" 6~1L) 1B BOX. | 1B/E/F BOX INST. | HYUN WOO KIM | 010-9280-4901
2400 | 09:10 | "1L" | NO. 3 C.T ( "B/GKC" 1~0L) 1B BOX. | 1B/E/F BOX INST. | HYUN WOO KIM | 010-9280-4901
2400 | 09:20 | "BF" T/CORNER | NO.4 C.T(B/FJ 6~1L)789B BOX(IPI) | 7,8,9B BOX INST. INSP | HYUN WOO KIM | 010-9280-4901
2400 | 09:30 | "DK" T/CORNER | NO.4 C.T(D/K 1~0L)I/TUBE FIT-UP(IPI) | INVAR TUBE FIT-UP INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 09:40 | "BA" T/CORNER | NO.2 C.T(B/A 9L)I/TUBE FIT-UP(IPI) | INVAR TUBE FIT-UP INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 09:50 | "DA" T/CORNER | NO.2 C.T(D/AEH 9~6L)5B BOX | (A)5B - BOX FIT-UP INST. | HYUN WOO KIM | 010-9280-4901
2400 | 09:50 | "B" WALL | NO.2 C.T(BD/A WALL 9L)N2 SLEEVE FINAL | N2 PIPE INST. INSP | HYUN WOO KIM | 010-9280-4901
2400 | 10:00 | BOX SHOP | X4H45-01 | INSULATION BOX FINAL FAB.INSP. | Dae Hyeong Kim | 010-9667-6563
2400 | 10:00 | "BG" T/CORNER | NO.4 C.T(B/GKC 1~0L)I/TUBE FINAL | INVAR TUBE INST. INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 10:20 | "9L" | NO 3 C.T ("9L") I/BEAM "END" INST INSP'. | SEC. INVAR BEAM INST. INSP | HYUN WOO KIM | 010-9280-4901
2400 | 10:30 | "8L" | NO 3 C.T("B,D 8L") STANDARD BOX FIT-UP. | SEC. STANDARD BOX INST. INSP | Dong Gil Hwang | 010-9511-1632
2400 | 10:40 | "8L" | NO 3 C.T(BD/EH 8~7L)T/BORDER BOX FIT-UP. | SEC. BORDER BOX. FIT-UP INSP | HYUN WOO KIM | 010-9280-4901
2400 | 10:50 | "BFG" CORNER | NO.2 C.T(BFG/BJK 1L)T/RON FINAL | TRIHEDRON INST. INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 11:00 | MATERIAL STOCK CENTER | NO.2 C.T BASE SUPPORT He-LEAK TEST | BASE SUPPORT FIT-UP. INSP | Yeongho Bak | 010-6876-5429
2400 | 13:30 | INVAR SHOP | TRIHEDRON FAB(T02) | FINAL FAB. INSP. | Dong Jin Kim | 010-9209-8040
2400 | 13:40 | INVAR SHOP | INVAR TUBE FAB(6B03) | FINAL FAB. INSP. | Dong Jin Kim | 010-9209-8040
2400 | 14:30 | "BE" T/CORNER | NO.2 C.T(B/EH 9~6L)I/TUBE FIT-UP(IPI) | INVAR TUBE FIT-UP INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 14:40 | "DGC" CORNER | NO.2 C.T(DGC/DKC 0L)T/RON FIT-UP(IPI) | TRIHEDRON FIT-UP INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 14:40 | "BGC" CORNER | NO.2 C.T(BGC/BKC 0L)T/RON FIT-UP(IPI) | TRIHEDRON FIT-UP INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 14:50 | "A" WALL | NO.4 C.T(A WALL 9L)G/DOME CONPENSATOR | SEC/PRI GAS DOME COMPENSATOR INST. INSP | HYUN WOO KIM | 010-9280-4901
2400 | 15:00 | "DF" T/CORNER | NO.4 C.T(D/FJ 6~1L)I/STRIP FINAL | INVAR STRIP INST. INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 15:20 | "BE" T/CORNER | NO.1 C.T (B/EH 9~6L) A/BAR FINAL | A/BAR INST. INSP. | HYUN WOO KIM | 010-9280-4901
2401 | 09:00 | ANJEONG | x2h7102 | INSULATION BOX FINAL FAB.INSP. | Hyun Jun An | 010-5188-4519
2401 | 10:00 | BOX SHOP | 1B12-01 | INSULATION BOX FINAL FAB.INSP. | Dae Hyeong Kim | 010-9667-6563
2401 | 14:00 | ANJEONG | k2s0101 | INSULATION BOX FINAL FAB.INSP. | Hyun Jun An | 010-5188-4519