## Feuil1
Project No. | Time | Place | Inspection Item | Insp. Characteristic | Inspector | M.P. | GTT | GTT | GTT
2298 | 09:10 | "2L" | NO.2 C.T "2L" REMOVAL OF MAIN SCAFFOLD | CONFIRMATION INSP. | Gyeong In Park | 010-2648-1538
2298 | 15:00 | "1L" | NO.2 C.T "1L" REMOVAL OF MAIN SCAFFOLD | CONFIRMATION INSP. | Gyeong In Park | 010-2648-1538
2400 | 09:00 | "BG" T/CORNER | NO.4 C.T(B/GKC 1~0L)789B BOX(IPI) | 7,8,9B BOX INST. INSP | Manjin Kim | 010-3135-6905
2400 | 09:10 | "1L" | NO3C.T(D/GKC 1~0L)1B BOX INST. INSP. | 1A BOX FIT-UP INSP. | Dong Gil Hwang | 010-9511-1632
2400 | 09:20 | "A" WALL | NO.2 C.T (A WALL 9L)L/DOME CHAIR FIT-UP | LIQUID DOME CHAIR FIT-UP. INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 09:30 | "DA" T/CORNER | NO.2 C.T(D/A 9L)I/TUBE FIT-UP(IPI) | INVAR TUBE FIT-UP INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 09:40 | "DF" T/CORNER | NO.2 C.T(D/FJ 6~1L)5B BOX | (A)5B - BOX FIT-UP INST. | HYUN WOO KIM | 010-9280-4901
2400 | 10:00 | BOX SHOP | X4H13-01 | INSULATION BOX FINAL FAB.INSP. | Dae Hyeong Kim | 010-9667-6563
2400 | 10:00 | "DGC" CORNER | NO.2 C.T(DGC/DKC 0L)T/RON FINAL | TRIHEDRON INST. INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 10:00 | "BGC" CORNER | NO.2 C.T(BGC/BKC 0L)T/RON FINAL | TRIHEDRON INST. INSP. | HYUN WOO KIM | 010-9280-4901
2400 | 10:10 | "9L" | NO3C.T("9~1L")TEMP. S/CABLE INST. INSP. | TEMPERATURE SENSOR CABLE INST. INSP | Dong Gil Hwang | 010-9511-1632
2400 | 10:30 | "1L" | NO3C.T("1L")I/BEAM STANDARD INST. INSP. | SEC. INVAR BEAM INST. INSP | Dong Gil Hwang | 010-9511-1632
2400 | 10:50 | "DG" T/CORNER | NO.4 C.T(D/GC 1~0L)I/TUBE FINAL | INVAR TUBE INST. INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 11:00 | LNGC S/CENTER | OBLIQUE PILLAR FAB(PRSS02) | WELDING INSP. | Dong Jin Kim | 010-9209-8040
2400 | 13:30 | INVAR SHOP | TRIHEDRON FAB(T03) | FINAL FAB. INSP. | Dong Jin Kim | 010-9209-8040
2400 | 13:40 | INVAR SHOP | INVAR TUBE FAB(A6B01) | FINAL FAB. INSP. | Dong Jin Kim | 010-9209-8040
2400 | 14:10 | "BAE" CORNER | NO.1 C.T(BAE/BAH 9L)T/RON FIT-UP(IPI) | TRIHEDRON FIT-UP INSP. | WANG HEE LEE | 010-9213-8284
2400 | 14:20 | "DE" T/CORNER | NO.2 C.T(D/EH 9~6L)I/TUBE FIT-UP(IPI) | INVAR TUBE FIT-UP INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 14:30 | "6L" | NO.3C.T(BD/EHFJ 6~2L) T/BORDER BOX INSP. | SEC. BORDER BOX. FIT-UP INSP | Dong Gil Hwang | 010-9511-1632
2400 | 14:50 | "6L" | NO.3C.T(E/F,H/J6L)1A END BOX FIT-UP INSP | 1A BOX FIT-UP INSP. | Dong Gil Hwang | 010-9511-1632
2400 | 15:00 | "DK" T/CORNER | NO.2 C.T(D/K 1~0L)I/TUBE FINAL | INVAR TUBE INST. INSP.(A6/6-TYPE) | HYUN WOO KIM | 010-9280-4901
2400 | 15:20 | "DA" T/CORNER | NO.1 C.T (D/AEH 9~6L) A/BAR FINAL | A/BAR INST. INSP. | WANG HEE LEE | 010-9213-8284
2400 | 15:40 | "BA" T/CORNER | NO.4 C.T(B/AEH 9~6L)I/STRIP FINAL | INVAR STRIP INST. INSP. | Manjin Kim | 010-3135-6905
2400 | 16:00 | LNGC S/CENTER | PILLAR HAT 제작(PRSS03) | WELDING INSP. | Dong Jin Kim | 010-9209-8040
2401 | 10:00 | BOX SHOP | 1B12-01 | INSULATION BOX FINAL FAB.INSP. | Dae Hyeong Kim | 010-9667-6563
2401 | 14:00 | "BA" T/CORNER | NO.3 C.T (B/A 9L) A/BAR FIT-UP(IPI) | A/BAR FIT-UP INSP. | Joon Yeong Park | 010-4464-9185
2401 | 14:00 | "A" WALL | NO.3 C.T (A WALL 9L) L/DOME A/BAR FIT-UP | A/BAR FIT-UP INSP. | Joon Yeong Park | 010-4464-9185