## Dwg List Schedule
DRAWING LIST SCHEDULE
Partname | Drawing No. |  |  |  | Revision | Drawing Name | Ship General | CATEGORIE | Scheduled AAAA-MM-DD | Received AAAA-MM-DD | Comments sent AAAA-MM-DD | Status | Milestone | delivery for approval | Email date | Status | <36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | Email n° for macro | #REF! | Part name | #REF! |  | Date | 2014-09-18
GENERAL | D.103. | SD. | 100 | .01 | .REV_A | D.103.SD.100.01.REV_A | General arrangement | 1 | 2014-08-19 | 2014-04-24 | ???? Ne trouve pas |  | 0 | 36 | 2014-08-19 |  | X
| D.103. | SD. | 100 | .01 | .REV_B | D.103.SD.100.01.REV_B | General arrangement | 1 | 2014-08-19 | 2014-08-19 | ????
GENERAL | D.103. | SD. | 100 | .02 | .REV_A | D.103.SD.100.02.REV_A | Contract specification | 1 | 2014-11-10 |  |  |  | 0 | 46 | [12 empty] | X | [15 empty] | Already Received
GENERAL | D.103. | SD. | 100 | .03 | .REV_A | D.103.SD.100.03.REV_A | Basic design drawing list | 1 | 2014-06-16 | 2014-06-16 |  |  | 0 | 36 | 2014-06-16 |  | X
GENERAL | D.103. | SD. | 101 | .01 | .REV_A | D.103.SD.101.01.REV_A | Collision bulkhead calculation | 1 | 2014-06-16 | 2014-05-21 | 2014-06-16 |  | 0 | 36 | 2014-06-16 |  | X
GENERAL | D.103. | SD. | 102 | .01 | .REV_A | D.103.SD.102.01.REV_A | Geometrical definition | 2 | 2014-11-24 |  |  |  | 0 | 48 | [14 empty] | X
GENERAL | D.103. | SD. | 102 | .02 | .REV_A | D.103.SD.102.02.REV_A | Lines plan | 2 | [33 empty] | GENERAL
GENERAL | D.103. | SD. | 102 | .03 | .REV_A | D.103.SD.102.03.REV_A | Offset table | 2 | [33 empty] | 1 | GENERAL ARRANGEMENT & CAPACITY PLAN
GENERAL | D.103. | SD. | 102 | .04 | .REV_A | D.103.SD.102.04.REV_A | Hydrostatic table | 2 | 2014-09-15 | 2014-09-19 | 2014-09-24 |  | 0 | 38 | 2014-09-19 |  |  |  | X | [22 empty] | 2 | HULL LINES DRAWINGS
GENERAL | D.103. | SD. | 102 | .05 | .REV_A | D.103.SD.102.05.REV_A | Propeller definition | 6 | [33 empty] | 3 | FINAL DRAWINGS
GENERAL | D.103. | SD. | 102 | .06 | .REV_A | D.103.SD.102.06.REV_A | Propeller strength calculation | 6 | [33 empty] | 4 | PRELIMINARY STABILITY
GENERAL | D.103. | SD. | 102 | .07 | .REV_A | D.103.SD.102.07.REV_A | Definition of propulsion improvement devices | 6 | 2014-12-22 |  |  |  | 0 | 52 | [18 empty] | X | [8 empty] | 5 | VARIOUS CALCULATIONS
GENERAL | D.103. | SD. | 102 | .08 | .REV_A | D.103.SD.102.08.REV_A | EEDI calculation (preliminary) | 5 | 2014-06-16 | 2014-06-16 | Plus tard il a ete dit |  | 0 | 36 | 2014-06-16 |  | X | [24 empty] | 6 | VARIOUS (ANCHOR, DAVIT, MAST, ETC)
GENERAL | D.103. | SD. | 102 | .08 | .REV_A | D.103.SD.102.08.REV_A | EEDI calculation (final) | 5
GENERAL | D.103. | SD. | 103 | .01 | .REV_A | D.103.SD.103.01.REV_A | Calculation of bending moments | 5 |  |  |  |  | 0 | 36 | ??? |  | X | [24 empty] | HULL
GENERAL | D.103. | SD. | 103 | .02 | .REV_A | D.103.SD.103.02.REV_A | Estimation of lightweight and lightweight distribution incl. COG | 3 | 2014-08-14 | 2014-08-14 | A renvoyer |  | 0 | 36 | 2014-08-14 |  | X | [24 empty] | 1 | MIDSHIP
GENERAL | D.103. | SD. | 103 | .03 | .REV_A | D.103.SD.103.03.REV_A | Tonnage calculation | 5 | 2014-10-20 |  |  |  | 0 | 43 | [9 empty] | X | [17 empty] | 2 | CARGO AREA
GENERAL | D.103. | SD. | 105 | .01 | .REV_A | D.103.SD.105.01.REV_A | Tank plan | 1 | 2014-07-25 | 2014-07-21 | 2014-09-10 |  | 0 | 36 | 2014-07-25 |  | X | [24 empty] | 3 | FWD AND AFT (ER, ACCOMMODATION, ETC)
GENERAL | D.103. | SD. | 105 | .02 | .REV_A | D.103.SD.105.02.REV_A | Sounding table | 1 | 2014-12-08 |  |  |  | 0 | 50 | [16 empty] | X | [10 empty] | 4 | VARIOUS (FOUNDATION, WELDING SPEC, ETC)
GENERAL | D.103. | SD. | 105 | .03 | .REV_A | D.103.SD.105.03.REV_A | Preliminary capacity plan incl. deadweight scale | 1
GENERAL | D.103. | SD. | 105 | .03 | .REV_A | D.103.SD.105.03.REV_A | Final capacity plan incl. deadweight scale | 1 | [33 empty] | MACHINERY
GENERAL | D.103. | SD. | 105 | .04 | .REV_A | D.103.SD.105.04.REV_A | Preliminary stability booklet (incl. loading sequence) | 3 | 2014-09-29 | 2014-09-16 |  |  | 0 | 40 | [6 empty] | X | [19 empty] | Clarify, need details BT | 1 | ROOM ARRANGEMENT
GENERAL | D.103. | SD. | 105 | .04 | .REV_A | D.103.SD.105.04.REV_A | Final stability booklet (incl. loading sequence) | 3 | [33 empty] | 2 | VARIOUS CALCULATIONS
GENERAL | D.103. | SD. | 105 | .05 | .REV_A | D.103.SD.105.05.REV_A | Preliminary grain stability manual | 4 | 2014-09-22 | 2014-09-16 |  |  | 0 | 39 | [5 empty] | X | [20 empty] | Clarify, need details from BT | 3 | PIPING SYSTEMS
GENERAL | D.103. | SD. | 105 | .05 | .REV_A | D.103.SD.105.05.REV_A | Final grain stability manual | 4 | [33 empty] | 4 | SHAFTING
GENERAL | D.103. | SD. | 105 | .06 | .REV_A | D.103.SD.105.06.REV_A | Preliminary damage stability calculation | 4 | 2014-09-15 | 2014-09-18 | 2014-09-24 |  | 0 | 38 | 2014-09-18 |  |  |  | X | [21 empty] | Comments by Florian | 5 | VARIOUS (EQUIPMENT MOUNTING PLAN, HOISTING BEAM, ETC)
GENERAL | D.103. | SD. | 105 | .06 | .REV_A | D.103.SD.105.06.REV_A | Final damage stability calculation | 4 | [33 empty] | 6 | SHIP SYST. CALCULATIONS & DIAGRAMS
GENERAL | D.103. | SD. | 105 | .07 | .REV_A | D.103.SD.105.07.REV_A | Preliminary cargo loading manual | 4 | [33 empty] | 7 | SHIP SYST. ARRANGEMENTS & VARIOUS
GENERAL | D.103. | SD. | 105 | .07 | .REV_A | D.103.SD.105.07.REV_A | Final cargo loading manual | 4 | [33 empty] | 8 | SYST. MACHIERY ARRANG & Various
GENERAL | D.103. | SD. | 105 | .08 | .REV_A | D.103.SD.105.08.REV_A | Prelimininary damage control plan | 3 | [33 empty] | 9 | FO / WATER / COOLING / HEATING
GENERAL | D.103. | SD. | 105 | .08 | .REV_A | D.103.SD.105.08.REV_A | Final damage control plan | 3
GENERAL | D.103. | SD. | 105 | .09 | .REV_A | D.103.SD.105.09.REV_A | Preliminary damage control manual | Redondant
GENERAL | D.103. | SD. | 105 | .09 | .REV_A | D.103.SD.105.09.REV_A | Final damage control manual | Redondant
GENERAL | D.103. | SD. | 105 | .10 | .REV_A | D.103.SD.105.10.REV_A | Freeboard calculation | 5 | 2014-07-01 | 2014-08-15 | 2014-08-15 |  | 0 | 36 | 2014-07-01 |  | X | [23 empty] | Comments by Florian
GENERAL | D.103. | SD. | 105 | .11 | .REV_A | D.103.SD.105.11.REV_A | Freeboard mark | 3
GENERAL | D.103. | SD. | 105 | .12 | .REV_A | D.103.SD.105.12.REV_A | Freeboard plan | 3
GENERAL | D.103. | SD. | 105 | .13 | .REV_A | D.103.SD.105.13.REV_A | Cargo list
GENERAL | D.103. | SD | 105 | .14 | .REV_A | D.103.SD105.14.REV_A | CALCULATION OF FILLING TIME FOR PROTECTION FLOODING | 2
GENERAL | D.103. | SD. | 106 | .01 | .REV_A | D.103.SD.106.01.REV_A | Speed power prediction | 5 | 2014-12-22 |  |  |  | 1 | 52 | [18 empty] | X
GENERAL | D.103. | SD. | 107 | .01 | .REV_A | D.103.SD.107.01.REV_A | Visibility plan | 6 | 2014-09-15 | 2014-08-08 | A renvoyer |  | 1 | 38 | 2014-08-08 |  |  |  | X
GENERAL | D.103. | SD. | 107 | .02 | .REV_A | D.103.SD.107.02.REV_A | Dangereous area arrangement | 6 | 2014-10-20 |  |  |  | 0 | 43 | [9 empty] | X
GENERAL | D.103. | SD. | 107 | .03 | .REV_A | D.103.SD.107.03.REV_A | List of dangerous cargoes | 6
GENERAL | D.103. | SD. | 107 | .04 | .REV_A | D.103.SD.107.04.REV_A | Preliminary ballast water management plan | 5
GENERAL | D.103. | SD. | 107 | .04 | .REV_A | D.103.SD.107.04.REV_A | Final ballast water management plan | 3
GENERAL | D.103. | SD. | 107 | .05 | .REV_A | D.103.SD.107.05.REV_A | Cargo securing manual | 3
GENERAL | D.103. | SD. | 108 | .01 | .REV_A | D.103.SD.108.01.REV_A | Preliminary fire control and safety plan | 1
GENERAL | D.103. | SD. | 109 | .01 | .REV_A | D.103.SD.109.01.REV_A | Equipment number calculation | 5
GENERAL | D.103. | SD. | 109 | .02 | .REV_A | D.103.SD.109.02.REV_A | Calculation of freeing ports | 5
GENERAL | D.103. | SD. | 144 | .01 | .REV_A | D.103.SD.144.01.REV_A | Docking plan | 3
GENERAL | D.103. | SD. | 152 | .01 | .REV_A | D.103.SD.152.01.REV_A | Inclining test survey procedure | 3
GENERAL | D.103. | SD. | 152 | .02 | .REV_A | D.103.SD.152.02.REV_A | Inclining test survey report | 3
GENERAL | D.103. | SD. | 154 | .03 | .REV_A | D.103.SD.154.03.REV_A | Quay trial program | 3
GENERAL | D.103. | SD. | 154 | .04 | .REV_A | D.103.SD.154.04.REV_A | Sea trial program | 3
GENERAL | D.103. | SD | 192 | .01 | .REV_A | D.103.SD192.01.REV_A | ESTIMATION OF ENDURANCE | 5
GENERAL | D.103. | SD | 192 | .02 | .REV_A | D.103.SD192.02.REV_A | PRELIMINARY EEDI CALCULATION | 5
GENERAL | D.103. | SD | 192 | .03 | .REV_A | D.103.SD192.03.REV_A | FINAL EEDI CALCULATION | 3
GENERAL | D.103. | SD | 195 | .01 | .REV_A | D.103.SD195.01.REV_A | IN-WATER SURVEY MANUAL | 6
HULL | D.103. | SD. |  |  | .REV_A | D.103.SD..REV_A | 3-D model | 3
HULL | D.103. | SD. | 200 | .01 | .REV_A | D.103.SD.200.01.REV_A | Midship section | 1 | 2014-06-08 | 2014-08-15 | 2014-07-29 |  | 0 | 36 | 2014-08-15 |  | X | X | [22 empty] | Comments by Florian
| D.103. | SD. | 200 | .01 | .REV_B | D.103.SD.200.01.REV_B | Shell expansion | 2 | 2014-08-15 | Il semblerait qu'aucun nouveau commentaire ai ete fait, HICHAM peux tu verifier sur le reseau
HULL | D.103. | SD. | 200 | .02 | .REV_A | D.103.SD.200.02.REV_A | Shell expansion | 2 | 2014-12-01 |  |  |  | 0 | 49 | [16 empty] | X
HULL | D.103. | SD. | 200 | .03 | .REV_A | D.103.SD.200.03.REV_A | Ice regions
HULL | D.103. | SD. | 200 | .04 | .REV_A | D.103.SD.200.04.REV_A | Typical structural details | 4 |  |  |  |  | 1
HULL | D.103. | SD. | 200 | .05 | .REV_A | D.103.SD.200.05.REV_A | Welding table | [5 empty] | 1
HULL | D.103. | SD. | 200 | .06 | .REV_A | D.103.SD.200.06.REV_A | Section scantling calculations | 4 | 2014-11-24 |  |  |  | 0 | 48 | [15 empty] | X
HULL | D.103. | SD. | 200 | .07 | .REV_A | D.103.SD.200.07.REV_A | CSR FE-calculation |  | 2014-11-24 |  |  |  | 0 | 48 | [15 empty] | X
HULL | D.103. | SD. | 200 | .08 | .REV_A | D.103.SD.200.08.REV_A | Fatigue strength calculation | 4 | 2014-11-24 |  |  |  | 0 | 48 | [15 empty] | X
HULL | D.103. | SD. | 200 | .08 | .REV_A | D.103.SD.200.08.REV_A | Structural scantling calculation | 4 | 2014-11-24 |  |  |  | 0 | 48 | [15 empty] | X
HULL | D.103. | SD | 200 | .10 | .REV_A | D.103.SD200.10.REV_A | CARGO HOLD FLOODED STRENGTH CALCULATION | 4
HULL | D.103. | SD | 200 | .11 | .REV_A | D.103.SD200.11.REV_A | OIL FUEL TANK PROTECTION CALCULATION | 2
HULL | D.103. | SD. | 201 | .01 | .REV_A | D.103.SD.201.01.REV_A | Steel purchase estimate | 2 | 2014-12-22 |  |  |  | 0 | 52 | [19 empty] | X
HULL | D.103. | SD. | 210 | .01 | .REV_A | D.103.SD.210.01.REV_A | Aft ship | 3
HULL | D.103. | SD. | 216 | .01 | .REV_A | D.103.SD.216.01.REV_A | Aft sterntube outer boss | 3
HULL | D.103. | SD. | 216 | .02 | .REV_A | D.103.SD.216.02.REV_A | Frw sterntube outer boss | 3
HULL | D.103. | SD. | 216 | .03 | .REV_A | D.103.SD.216.03.REV_A | Pre-swirl stator construction | 4
HULL | D.103. | SD. | 218 | .01 | .REV_A | D.103.SD.218.01.REV_A | Rudder horn (incl. castings) | 4
HULL | D.103. | SD. | 220 | .01 | .REV_A | D.103.SD.220.01.REV_A | Transverse sections in engine room | 2
HULL | D.103. | SD. | 220 | .02 | .REV_A | D.103.SD.220.02.REV_A | Engine room front bulkhead | 3
HULL | D.103. | SD. | 223 | .01 | .REV_A | D.103.SD.223.01.REV_A | Double bottom in engine room | 3
HULL | D.103. | SD. | 223 | .02 | .REV_A | D.103.SD.223.02.REV_A | Main engine foundation | 4
HULL | D.103. | SD. | 223 | .03 | .REV_A | D.103.SD.223.03.REV_A | Aux. engine foundation | 4
HULL | D.103. | SD. | 223 | .04 | .REV_A | D.103.SD.223.04.REV_A | Intermediate shaft bearing seating | 4
HULL | D.103. | SD | 223 | .05 | .REV_A | D.103.SD223.05.REV_A | Emergency generator foundation | 4
HULL | D.103. | SD. | 224 | .01 | .REV_A | D.103.SD.224.01.REV_A | Tween decks | 4 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 226 | .01 | .REV_A | D.103.SD.226.01.REV_A | Longitudinal sections in engine room | 3 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 232 | .01 | .REV_A | D.103.SD.232.01.REV_A | Double bottom in cargo area | 2 | 2014-09-29 | 2014-09-23 | A envoyer |  | 0 | 39 | 2014-09-23 | [5 empty] | X
HULL | D.103. | SD. | 234 | .01 | .REV_A | D.103.SD.234.01.REV_A | Side stringers | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 234 | .02 | .REV_A | D.103.SD.234.02.REV_A | Upper deck | 2 | 2014-09-29 | 2014-09-23 | A envoyer |  | 0 | 39 | 2014-09-23 | [5 empty] | X
HULL | D.103. | SD. | 234 | .03 | .REV_A | D.103.SD.234.03.REV_A | Miscellaneous stores abobe upper deck in cargo area | 2
HULL | D.103. | SD. | 236 | .01 | .REV_A | D.103.SD.236.01.REV_A | Transverse sections in way of cargo hold #1 | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 236 | .02 | .REV_A | D.103.SD.236.02.REV_A | Transverse bulkhead btw CH1 & CH2 | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 236 | .03 | .REV_A | D.103.SD.236.03.REV_A | Transverse bulkhead btw CH2 & CH3 | 2 | 2014-09-29 | 2014-09-23 | A envoyer |  | 0 | 39 | 2014-09-23 | [5 empty] | X
HULL | D.103. | SD. | 236 | .04 | .REV_A | D.103.SD.236.04.REV_A | Transverse bulkhead btw CH3 & CH4 | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 236 | .05 | .REV_A | D.103.SD.236.05.REV_A | Transverse bulkhead btw CH4 & CH5 | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 236 | .06 | .REV_A | D.103.SD.236.06.REV_A | Transverse sections in way of cargo hold #5 | 2 | 2014-10-27 |  |  |  | 0 | 44 | [11 empty] | X
HULL | D.103. | SD. | 237 | .01 | .REV_A | D.103.SD.237.01.REV_A | Inner side | 2 | 2014-10-06 | 2014-10-06 |  |  | 0 | 40 | 2014-10-06 | [6 empty] | X
HULL | D.103. | SD. | 240 | .01 | .REV_A | D.103.SD.240.01.REV_A | Fore ship | 4 |  |  |  |  | 0 | 49 | [16 empty] | X
HULL | D.103. | SD. | 241 | .01 | .REV_A | D.103.SD.241.01.REV_A | Bulwark construction | 3
HULL | D.103. | SD | 242 | .01 | .REV_A | D.103.SD242.01.REV_A | HATCH COAMING STRUCTURE | 4
HULL | D.103. | SD. | 243 | .01 | .REV_A | D.103.SD.243.01.REV_A | Forecastle deck and bulkheads below | 3
HULL | D.103. | SD. | 246 | .01 | .REV_A | D.103.SD.246.01.REV_A | Collision bulkhead | 2
HULL | D.103. | SD. | 251 | .01 | .REV_A | D.103.SD.251.01.REV_A | Deck house decks and bulkheads below | 3 | 2014-12-01 |  |  |  | 0 | 49 | [16 empty] | X
HULL | D.103. | SD | 253 | .01 | .REV_A | D.103.SD253.01.REV_A | SUPERSTRUCTURE & DECK HOUSE STRUCTURE | 3 | 2014-12-01 |  |  |  | 0 | 49 | [16 empty] | X
HULL | D.103. | SD. | 261 | .01 | .REV_A | D.103.SD.261.01.REV_A | Draught mark and paint line
HULL | D.103. | SD | 261 | .02 | .REV_A | D.103.SD261.02.REV_A | DECK AND HULL MARK PLAN
HULL | D.103. | SD | 261 | .03 | .REV_A | D.103.SD261.03.REV_A | ARRANGEMENT OF PORT AND SHIPNAME
HULL | D.103. | SD. | 262 | .01 | .REV_A | D.103.SD.262.01.REV_A | Arrangement of bottom plugs
HULL | D.103. | SD. | 263 | .01 | .REV_A | D.103.SD.263.01.REV_A | Crane foundations | 4
HULL | D.103. | SD. | 263 | .02 | .REV_A | D.103.SD.263.02.REV_A | Windlass seating | 4
HULL | D.103. | SD. | 263 | .03 | .REV_A | D.103.SD.263.03.REV_A | Mooring winch seating | 4
HULL | D.103. | SD. | 263 | .04 | .REV_A | D.103.SD.263.04.REV_A | Steering gear seating | 4
HULL | D.103. | SD. | 263 | .05 | .REV_A | D.103.SD.263.05.REV_A | Boiler seating | 4
HULL | D.103. | SD. | 264 | .01 | .REV_A | D.103.SD.264.01.REV_A | Bilge keel | 4
HULL | D.103. | SD. | 266 | .01 | .REV_A | D.103.SD.266.01.REV_A | Anchor excess | 4
HULL | D.103. | SD. | 266 | .02 | .REV_A | D.103.SD.266.02.REV_A | Hawse pipe
HULL | D.103. | SD. | 268 | .01 | .REV_A | D.103.SD.268.01.REV_A | Funnel | 4
HULL | D.103. | SD. | 278 | .01 | .REV_A | D.103.SD.278.01.REV_A | Arrangement of anodes | 4
HULL | D.103. | SD | 278 | .02 | .REV_A | D.103.SD278.02.REV_A | SACRIFICIAL ANODE CALCULATION | 4
MACHINERY | D.103. | SD. | 600 | .01 | .REV_A | D.103.SD.600.01.REV_A | Machinery arrangement (preliminary) | 1 | 2014-09-15 | 2014-08-14 | A envoyer |  | 0 | 38 | 2014-08-14
MACHINERY | D.103. | SD. | 600 | .01 | .REV_A | D.103.SD.600.01.REV_A | Machinery arrangement (final) | 1
MACHINERY | D.103. | SD. | 600 | .02 | .REV_A | D.103.SD.600.02.REV_A | List of machinery equipment | 1 | 2014-09-15 | 2014-09-21 | A envoyer |  | 1 | 38 | 2014-09-21
MACHINERY | D.103. | SD. | 600 | .03 | .REV_A | D.103.SD.600.03.REV_A | Equipment capacity calculation | 2
MACHINERY | D.103. | SD. | 600 | .04 | .REV_A | D.103.SD.600.04.REV_A | Tank capacity calculation | 2 | 2014-10-03 | 2014-09-29 | A envoyer |  | 0 | 40 | 2014-10-03
MACHINERY | D.103. | SD. | 600 | .05 | .REV_A | D.103.SD.600.05.REV_A | Calculation of friction loss for exhaust gas piping | 2 | 2014-10-03 | 2014-09-29 | A envoyer |  | 1 | 40 | 2014-10-03
MACHINERY | D.103. | SD. | 600 | .06 | .REV_A | D.103.SD.600.06.REV_A | Calculation of duct pessure loss in accommodation | 2
MACHINERY | D.103. | SD. | 600 | .07 | .REV_A | D.103.SD.600.07.REV_A | Engine casing and funnel arrangement | 1
MACHINERY | D.103. | SD. | 600 | .08 | .REV_A | D.103.SD.600.08.REV_A | Arrangement of exhaust gas piping in ER | 1
MACHINERY | D.103. | SD. | 600 | .09 | .REV_A | D.103.SD.600.09.REV_A | Arrangement of steering gear room | 1
MACHINERY | D.103. | SD. | 600 | .10 | .REV_A | D.103.SD.600.10.REV_A | Arrangement of Ox & acetylene room | 1 |  | ``
MACHINERY | D.103. | SD. | 600 | .11 | .REV_A | D.103.SD.600.11.REV_A | Arrangement of hydraulic power pack room | 1
MACHINERY | D.103. | SD | 600 | .12 | .REV_A | D.103.SD600.12.REV_A | ENGINE CONTROL ROOM ARRANGEMENT | 1
MACHINERY | D.103. | SD. | 601 | .01 | .REV_A | D.103.SD.601.01.REV_A | Main engine installation | 4
MACHINERY | D.103. | SD | 601 | .02 | .REV_A | D.103.SD601.02.REV_A | M/E TOP BRACING ARRANGEMENT | 1
MACHINERY | D.103. | SD. | 630 | .01 | .REV_A | D.103.SD.630.01.REV_A | Torsional vibration calculation report | 2
MACHINERY | D.103. | SD. | 630 | .02 | .REV_A | D.103.SD.630.02.REV_A | Whirling vibration calculation report | 2
MACHINERY | D.103. | SD. | 630 | .03 | .REV_A | D.103.SD.630.03.REV_A | Shafting strength calculation | 2
MACHINERY | D.103. | SD. | 631 | .01 | .REV_A | D.103.SD.631.01.REV_A | Propulsion shafting arrangement | 4
MACHINERY | D.103. | SD | 631 | .02 | .REV_A | D.103.SD631.02.REV_A | SHAFT EARTHING DEVICE MOUNTING PLAN | 5
MACHINERY | D.103. | SD | 631 | .03 | .REV_A | D.103.SD631.03.REV_A | PULLING ARRANGEMENT OF PROPELLER SHAFT | 1
MACHINERY | D.103. | SD | 631 | .04 | .REV_A | D.103.SD631.04.REV_A | TECHNICAL REQUIREMENT FOR SHAFT CASTING AND FORGING | 4
MACHINERY | D.103. | SD | 631 | .05 | .REV_A | D.103.SD631.05.REV_A | SHAFTING ALIGNMENT CALCULATION | 4
MACHINERY | D.103. | SD. | 640 | .01 | .REV_A | D.103.SD.640.01.REV_A | Heat balance calculation (steam) | 2
MACHINERY | D.103. | SD. | 665 | .01 | .REV_A | D.103.SD.665.01.REV_A | Emergency generator room arrangement | 1
MACHINERY | D.103. | SD. | 700 | .01 | .REV_A | D.103.SD.700.01.REV_A | Piping & fittings symbol | 3
MACHINERY | D.103. | SD. | 700 | .02 | .REV_A | D.103.SD.700.02.REV_A | Arrangement of shipside valves | 8
MACHINERY | D.103. | SD. | 701 | .01 | .REV_A | D.103.SD.701.01.REV_A | Fuel oil transfer system diagram | 9
MACHINERY | D.103. | SD. | 701 | .02 | .REV_A | D.103.SD.701.02.REV_A | Fuel oil drain system diagram | 9
MACHINERY | D.103. | SD. | 702 | .01 | .REV_A | D.103.SD.702.01.REV_A | Fuel oil purifying system diagram | 9
MACHINERY | D.103. | SD. | 703 | .01 | .REV_A | D.103.SD.703.01.REV_A | Fuel oil service system diagram | 9
MACHINERY | D.103. | SD. | 703 | .02 | .REV_A | D.103.SD.703.02.REV_A | Incinerator piping system diagram | 3
MACHINERY | D.103. | SD | 703 | .03 | .REV_A | D.103.SD703.03.REV_A | FUEL OIL CHANGE-OVER PROCEDURE | 8
MACHINERY | D.103. | SD. | 704 | .01 | .REV_A | D.103.SD.704.01.REV_A | Calculation of heating coils surface/length | 9
MACHINERY | D.103. | SD. | 711 | .01 | .REV_A | D.103.SD.711.01.REV_A | LO transfer and purifying system diagram | 9
MACHINERY | D.103. | SD. | 711 | .02 | .REV_A | D.103.SD.711.02.REV_A | LO drain system diagram | 9
MACHINERY | D.103. | SD. | 713 | .01 | .REV_A | D.103.SD.713.01.REV_A | LO service system diagram | 9
MACHINERY | D.103. | SD | 713 | .02 | .REV_A | D.103.SD713.02.REV_A | STERN TUBE L.O. PIPING SYSTEM | 3
MACHINERY | D.103. | SD | 713 | .03 | .REV_A | D.103.SD713.03.REV_A | M.E L.O. SUMP ARRANGMENT | 8
MACHINERY | D.103. | SD | 713 | .04 | .REV_A | D.103.SD713.04.REV_A | M/E DRAIN PIPING SYSTEM | 3
MACHINERY | D.103. | SD. | 720 | .01 | .REV_A | D.103.SD.720.01.REV_A | Cooling system calculations (heat flow) | 9
MACHINERY | D.103. | SD. | 721 | .01 | .REV_A | D.103.SD.721.01.REV_A | Sea water cooling system diagram | 9
MACHINERY | D.103. | SD. | 721 | .02 | .REV_A | D.103.SD.721.02.REV_A | HT and LT fresh water cooling system diagram | 9
MACHINERY | D.103. | SD. | 721 | .03 | .REV_A | D.103.SD.721.03.REV_A | Arrangement of sea chest and board valves | 8
MACHINERY | D.103. | SD. | 731 | .01 | .REV_A | D.103.SD.731.01.REV_A | Starting and service compressed air diagram and capacity calculation | 9
MACHINERY | D.103. | SD. | 734 | .01 | .REV_A | D.103.SD.734.01.REV_A | Oil tanks quick-closing valve control system diagram | 9
MACHINERY | D.103. | SD. | 734 | .02 | .REV_A | D.103.SD.734.02.REV_A | Diagram of pneumatically remote controlled valves | 9
MACHINERY | D.103. | SD. | 740 | .01 | .REV_A | D.103.SD.740.01.REV_A | Calculation of pressure losses in exhaust gas piping | 3
MACHINERY | D.103. | SD. | 743 | .01 | .REV_A | D.103.SD.743.01.REV_A | Engine casing and funnel arrangement | 9
MACHINERY | D.103. | SD. | 743 | .02 | .REV_A | D.103.SD.743.02.REV_A | Exhaust gas system diagram | 9
MACHINERY | D.103. | SD. | 751 | .01 | .REV_A | D.103.SD.751.01.REV_A | Steam heating diagram | 9
MACHINERY | D.103. | SD. | 751 | .02 | .REV_A | D.103.SD.751.02.REV_A | Emergency control device of safety valve for boiler arrangement | 8
MACHINERY | D.103. | SD. | 756 | .01 | .REV_A | D.103.SD.756.01.REV_A | Boiler feed water and condensate water system diagram | 9
MACHINERY | D.103. | SD | 761 | .01 | .REV_A | D.103.SD761.01.REV_A | F.W. GENERATOR PIPING SYSTEM | 3
MACHINERY | D.103. | SD | 771 | .01 | .REV_A | D.103.SD771.01.REV_A | ME TC WASHING PIPING SYSTEM | 3
MACHINERY | D.103. | SD. | 790 | .01 | .REV_A | D.103.SD.790.01.REV_A | Arrangement of automation equipment | 8
MACHINERY | D.103. | SD. | 793 | .01 | .REV_A | D.103.SD.793.01.REV_A | List for control, monitoring, alarming points & separate instruments | 9
MACHINERY | D.103. | SD. | 798 | .01 | .REV_A | D.103.SD.798.01.REV_A | Wiring diagram of automation system | 9
MACHINERY | D.103. | SD. | 801 | .01 | .REV_A | D.103.SD.801.01.REV_A | Ballast water diagram | 6
MACHINERY | D.103. | SD. | 803 | .01 | .REV_A | D.103.SD.803.01.REV_A | Bilge water diagram and calculation | 6
MACHINERY | D.103. | SD. | 803 | .02 | .REV_A | D.103.SD.803.02.REV_A | Diagram of oily water separating system | 6
MACHINERY | D.103. | SD. | 804 | .01 | .REV_A | D.103.SD.804.01.REV_A | Scuppers and drain water diagram | 6
MACHINERY | D.103. | SD | 811 | .01 | .REV_A | D.103.SD811.01.REV_A | ARRANGEMENT OF FIRE DETECTING AND ALARM EQUIPMENT | 7
MACHINERY | D.103. | SD | 811 | .02 | .REV_A | D.103.SD811.02.REV_A | FIRE CONTROL STATION ARRANGEMENT | 7
MACHINERY | D.103. | SD. | 813 | .01 | .REV_A | D.103.SD.813.01.REV_A | Calculation of fire water system | 6
MACHINERY | D.103. | SD. | 813 | .02 | .REV_A | D.103.SD.813.02.REV_A | Fire and deck washing diagram | 6
MACHINERY | D.103. | SD. | 813 | .03 | .REV_A | D.103.SD.813.03.REV_A | Cargo washing diagram | 6
MACHINERY | D.103. | SD | 813 | .04 | .REV_A | D.103.SD813.04.REV_A | EMERGENCY FIRE PUMP ARRANGEMENT & PIPING SYSTEM | 7
MACHINERY | D.103. | SD. | 815 | .01 | .REV_A | D.103.SD.815.01.REV_A | CO2 system diagram and calculation (Machinery, galley and C/H) | 6
MACHINERY | D.103. | SD. | 815 | .02 | .REV_A | D.103.SD.815.02.REV_A | Arrangement of CO2-room | 7
MACHINERY | D.103. | SD. | 817 | .01 | .REV_A | D.103.SD.817.01.REV_A | ER local water mist system diagram | 6
MACHINERY | D.103. | SD | 817 | .02 | .REV_A | D.103.SD817.02.REV_A | ARRANGEMENT OF FIXED WATER LOCAL FIRE FIGTHING ELE EQUIP | 7
MACHINERY | D.103. | SD. | 821 | .01 | .REV_A | D.103.SD.821.01.REV_A | Air, sounding and overflow diagram | 6
MACHINERY | D.103. | SD. | 823 | .01 | .REV_A | D.103.SD.823.01.REV_A | Level monitoring system diagram | 6
MACHINERY | D.103. | SD. | 830 | .01 | .REV_A | D.103.SD.830.01.REV_A | Diagram of hydraulically remote controlled valves | 6
MACHINERY | D.103. | SD. | 837 | .01 | .REV_A | D.103.SD.837.01.REV_A | Oxygen & acetylene piping diagram | 6
MACHINERY | D.103. | SD. | 860 | .01 | .REV_A | D.103.SD.860.01.REV_A | Electric load balance | 6
MACHINERY | D.103. | SD. | 860 | .02 | .REV_A | D.103.SD.860.02.REV_A | Arrangement of electric power equipments | 7
MACHINERY | D.103. | SD. | 860 | .03 | .REV_A | D.103.SD.860.03.REV_A | Battery calculation | 6
MACHINERY | D.103. | SD | 866 | .01 | .REV_A | D.103.SD866.01.REV_A | ARRANGEMENT OF BATTERY ROOM | 7
MACHINERY | D.103. | SD. | 870 | .01 | .REV_A | D.103.SD.870.01.REV_A | Electric power short circuit calculation | 6
MACHINERY | D.103. | SD. | 871 | .01 | .REV_A | D.103.SD.871.01.REV_A | Wiring diagram of main power circuit | 6
MACHINERY | D.103. | SD. | 871 | .02 | .REV_A | D.103.SD.871.02.REV_A | Single line electrical diagram | 6
MACHINERY | D.103. | SD. | 881 | .01 | .REV_A | D.103.SD.881.01.REV_A | Cable trays E/R | 7
MACHINERY | D.103. | SD. | 882 | .01 | .REV_A | D.103.SD.882.01.REV_A | Cable trays accommodation | 7
MACHINERY | D.103. | SD. | 883 | .01 | .REV_A | D.103.SD.883.01.REV_A | Cable trays open decks & cargo holds | 7
MACHINERY | D.103. | SD. | 886 | .01 | .REV_A | D.103.SD.886.01.REV_A | Wiring diagram of interior communication system | 6
MACHINERY | D.103. | SD. | 886 | .02 | .REV_A | D.103.SD.886.02.REV_A | Wiring diagram of GMDSS and navigation system | 6
MACHINERY | D.103. | SD. | 890 | .01 | .REV_A | D.103.SD.890.01.REV_A | Arrangement of electric equipment on exposed weather decks | 7
MACHINERY | D.103. | SD. | 891 | .01 | .REV_A | D.103.SD.891.01.REV_A | Lighting diagram E/R | 6
MACHINERY | D.103. | SD. | 892 | .01 | .REV_A | D.103.SD.892.01.REV_A | Lighting diagram accommodation | 6
MACHINERY | D.103. | SD. | 893 | .01 | .REV_A | D.103.SD.893.01.REV_A | Lighting diagram open decks, cargo holds | 6
MACHINERY | D.103. | SD. | 894 | .01 | .REV_A | D.103.SD.894.01.REV_A | Arrangement of transducer and echo sounder log | 7
OUTFITTING | D.103. | SD. | 400 | .01 | .REV_A | D.103.SD.400.01.REV_A | Arrangement of 1st accommodation deck | 6
OUTFITTING | D.103. | SD. | 400 | .02 | .REV_A | D.103.SD.400.02.REV_A | Arrangement of 2nd accommodation deck | 6
OUTFITTING | D.103. | SD. | 400 | .03 | .REV_A | D.103.SD.400.03.REV_A | Arrangement of 3rd accommodation deck | 6
OUTFITTING | D.103. | SD. | 400 | .04 | .REV_A | D.103.SD.400.04.REV_A | Arrangement of 4th accommodation deck | 6
OUTFITTING | D.103. | SD. | 400 | .05 | .REV_A | D.103.SD.400.05.REV_A | Arrangement of bridge deck incl. window washing platform | 6
OUTFITTING | D.103. | SD. | 401 | .01 | .REV_A | D.103.SD.401.01.REV_A | Rudder arrangement | 2 | 2014-08-14 | 2014-08-14 | 2014-08-18 |  | 0 | 36 | 2014-08-14 |  | X | [23 empty] | Comment sent by mail
OUTFITTING | D.103. | SD. | 401 | .02 | .REV_A | D.103.SD.401.02.REV_A | Calculation of rudder | 2
OUTFITTING | D.103. | SD. | 401 | .03 | .REV_A | D.103.SD.401.03.REV_A | Rudder construction (incl. castings) | 2
OUTFITTING | D.103. | SD. | 401 | .04 | .REV_A | D.103.SD.401.04.REV_A | Rudder stock | 2
OUTFITTING | D.103. | SD. | 401 | .05 | .REV_A | D.103.SD.401.05.REV_A | Rudder pintle | 2
OUTFITTING | D.103. | SD. | 401 | .06 | .REV_A | D.103.SD.401.06.REV_A | Rudder stock bearing | 2
OUTFITTING | D.103. | SD. | 401 | .07 | .REV_A | D.103.SD.401.07.REV_A | Rudder pintle bearing | 2
OUTFITTING | D.103. | SD. | 401 | .08 | .REV_A | D.103.SD.401.08.REV_A | Rudder stock nut | 2
OUTFITTING | D.103. | SD. | 401 | .09 | .REV_A | D.103.SD.401.09.REV_A | Rudder pintle nut | 2
OUTFITTING | D.103. | SD. | 402 | .01 | .REV_A | D.103.SD.402.01.REV_A | Steering gear room arrangement | 3
OUTFITTING | D.103. | SD. | 409 | .01 | .REV_A | D.103.SD.409.01.REV_A | Ship structure access manual | 1
OUTFITTING | D.103. | SD. | 409 | .02 | .REV_A | D.103.SD.409.02.REV_A | Arrangement of Permanent means of access | 3
OUTFITTING | D.103. | SD. | 410 | .01 | .REV_A | D.103.SD.410.01.REV_A | Arrangement of navigation equipment | 5
OUTFITTING | D.103. | SD. | 418 | .01 | .REV_A | D.103.SD.418.01.REV_A | Arrangement of navigation lights | 5
OUTFITTING | D.103. | SD. | 418 | .02 | .REV_A | D.103.SD.418.02.REV_A | Fore mast construction | 5
OUTFITTING | D.103. | SD. | 418 | .03 | .REV_A | D.103.SD.418.03.REV_A | Radar mast construction | 5
OUTFITTING | D.103. | SD. | 420 | .01 | .REV_A | D.103.SD.420.01.REV_A | Arrangement of communication equipment | 5
OUTFITTING | D.103. | SD. | 420 | .02 | .REV_A | D.103.SD.420.02.REV_A | Arrangement of antenna system | 5
OUTFITTING | D.103. | SD. | 431 | .01 | .REV_A | D.103.SD.431.01.REV_A | Anchor and chain locker arrangement | 5
OUTFITTING | D.103. | SD. | 433 | .01 | .REV_A | D.103.SD.433.01.REV_A | Mooring arrangement (aft & fwd) | 1
OUTFITTING | D.103. | SD | 435 | .01 | .REV_A | D.103.SD435.01.REV_A | MOORING EQUIPEMENT STRENGTHEN STRUCTURE | 1
OUTFITTING | D.103. | SD | 437 | .01 | .REV_A | D.103.SD437.01.REV_A | EMERGENCY TOWING PROCEDURE | 3
OUTFITTING | D.103. | SD | 438 | .01 | .REV_A | D.103.SD438.01.REV_A | HYD. PUMP ARRANGEMENT | 6
OUTFITTING | D.103. | SD | 439 | .01 | .REV_A | D.103.SD439.01.REV_A | HYDRAULIC CIRCUIT DIGRAM OF STEERING GEAR | 5
OUTFITTING | D.103. | SD | 445 | .01 | .REV_A | D.103.SD445.01.REV_A | INCINERATOR MDO TANK | 5
OUTFITTING | D.103. | SD | 452 | .01 | .REV_A | D.103.SD452.01.REV_A | E/R CRANE INSTALLATION | 5
OUTFITTING | D.103. | SD. | 501 | .01 | .REV_A | D.103.SD.501.01.REV_A | Rescue boat arrangement | 3
OUTFITTING | D.103. | SD. | 501 | .02 | .REV_A | D.103.SD.501.02.REV_A | Life boat and davit arrangement | 3
OUTFITTING | D.103. | SD. | 501 | .03 | .REV_A | D.103.SD.501.03.REV_A | Arrangement of provision crane | 5
OUTFITTING | D.103. | SD. | 503 | .01 | .REV_A | D.103.SD.503.01.REV_A | Life saving equipment arrangement | 3
OUTFITTING | D.103. | SD. | 511 | .01 | .REV_A | D.103.SD.511.01.REV_A | Handrail & storm rail arrangement | 3
OUTFITTING | D.103. | SD. | 514 | .01 | .REV_A | D.103.SD.514.01.REV_A | Arrangement of external doors | 3
OUTFITTING | D.103. | SD | 514 | .02 | .REV_A | D.103.SD514.02.REV_A | LIST OF FIRE PROOF DOOR | 3
OUTFITTING | D.103. | SD | 514 | .03 | .REV_A | D.103.SD514.03.REV_A | ARRANGEMENT OF FIRE PROOF DOOR | 3
OUTFITTING | D.103. | SD | 514 | .04 | .REV_A | D.103.SD514.04.REV_A | LIST OF STEEL DOOR | 3
OUTFITTING | D.103. | SD | 514 | .05 | .REV_A | D.103.SD514.05.REV_A | ARRANGEMENT OF STEEL DOOR | 3
OUTFITTING | D.103. | SD. | 515 | .01 | .REV_A | D.103.SD.515.01.REV_A | Arrangement of windows in supertructure & wheelhouse | 6
OUTFITTING | D.103. | SD. | 517 | .01 | .REV_A | D.103.SD.517.01.REV_A | Structural fire protection plan | 3
OUTFITTING | D.103. | SD. | 517 | .02 | .REV_A | D.103.SD.517.02.REV_A | Insulation plan | 5
OUTFITTING | D.103. | SD | 517 | .03 | .REV_A | D.103.SD517.03.REV_A | TYPICAL DETAIL FOR FIRE-PROOF CONSTRUCTION | 3
OUTFITTING | D.103. | SD. | 520 | .01 | .REV_A | D.103.SD.520.01.REV_A | Deck covering arrangement | 6
OUTFITTING | D.103. | SD. | 524 | .01 | .REV_A | D.103.SD.524.01.REV_A | Arrangement of interior stairs and ladders | 6
OUTFITTING | D.103. | SD | 525 | .01 | .REV_A | D.103.SD525.01.REV_A | E/R CHECKERED PLATE. LADDER & GRATING ARR'T | 5
OUTFITTING | D.103. | SD. | 526 | .01 | .REV_A | D.103.SD.526.01.REV_A | Arrangement of ladders in double hull | 6
OUTFITTING | D.103. | SD. | 528 | .01 | .REV_A | D.103.SD.528.01.REV_A | Stairs and ladders in cargo holds | 5
OUTFITTING | D.103. | SD. | 534 | .01 | .REV_A | D.103.SD.534.01.REV_A | Arrangement of exterior stairs and ladders | 6
OUTFITTING | D.103. | SD. | 551 | .01 | .REV_A | D.103.SD.551.01.REV_A | Arrangement of galley and pantries | 6
OUTFITTING | D.103. | SD | 557 | .01 | .REV_A | D.103.SD557.01.REV_A | ARRANGEMENT OF CHANGING ROOM | 6
OUTFITTING | D.103. | SD | 558 | .01 | .REV_A | D.103.SD558.01.REV_A | ARRANGEMENT OF LAUNDRY & DRY ROOM | 6
OUTFITTING | D.103. | SD | 563 | .01 | .REV_A | D.103.SD563.01.REV_A | JIB REST FOR PROVISION CRANE
OUTFITTING | D.103. | SD. | 564 | .01 | .REV_A | D.103.SD.564.01.REV_A | Arrangement of accommodation & pilot ladder | 6
OUTFITTING | D.103. | SD. | 571 | .01 | .REV_A | D.103.SD.571.01.REV_A | Arrangement of AC-rooms | 6
OUTFITTING | D.103. | SD. | 571 | .02 | .REV_A | D.103.SD.571.02.REV_A | Air conditioning sharing scheme | 6
OUTFITTING | D.103. | SD. | 572 | .01 | .REV_A | D.103.SD.572.01.REV_A | Arrangement of provision stores | 6
OUTFITTING | D.103. | SD. | 572 | .02 | .REV_A | D.103.SD.572.02.REV_A | Refrigeration of provision stores | 6
OUTFITTING | D.103. | SD. | 574 | .01 | .REV_A | D.103.SD.574.01.REV_A | Calculation of ventilation
OUTFITTING | D.103. | SD. | 574 | .02 | .REV_A | D.103.SD.574.02.REV_A | Ventilation routing scheme of machinery spaces | 6
OUTFITTING | D.103. | SD. | 576 | .01 | .REV_A | D.103.SD.576.01.REV_A | Ventilation routing scheme of deck stores etc. | 6
OUTFITTING | D.103. | SD. | 581 | .01 | .REV_A | D.103.SD.581.01.REV_A | Fresh water supply system diagram | 6
OUTFITTING | D.103. | SD. | 582 | .01 | .REV_A | D.103.SD.582.01.REV_A | Sewage treatment system
OUTFITTING | D.103. | SD. | 582 | .02 | .REV_A | D.103.SD.582.02.REV_A | Grey water routing diagram | 6
OUTFITTING | D.103. | SD. | 582 | .03 | .REV_A | D.103.SD.582.03.REV_A | Black water routing diagram | 6
OUTFITTING | D.103. | SD. | 582 | .04 | .REV_A | D.103.SD.582.04.REV_A | Sanitary discharge system diagram | 6
OUTFITTING | D.103. | SD. | 591 | .01 | .REV_A | D.103.SD.591.01.REV_A | Arrangement of paint and bosun store | 6
OUTFITTING | D.103. | SD. | 591 | .02 | .REV_A | D.103.SD.591.02.REV_A | Arrangement of deck stores | 6
OUTFITTING | D.103. | SD. | 591 | .03 | .REV_A | D.103.SD.591.03.REV_A | Arrangement of cherry picker room | 6
OUTFITTING | D.103. | SD. | 591 | .04 | .REV_A | D.103.SD.591.04.REV_A | Arrangement of upper deck | 6
ELECTRICAL | D.103. | SD.9. | 278 | .01 | .REV_A | D.103.SD.9.278.01.REV_A | ICCP ELEC. SYSTEM DIAGRAM | 4 | [35 empty] | MACHINERY SYSTEMS
ELECTRICAL | D.103. | SD.9. | 288 | .01 | .REV_A | D.103.SD.9.288.01.REV_A | ENGINEER CALL.EXTENSION ALARM ELE. SYSTEM DIAGRAM | [36 empty] | ELECTRICAL WIRING DIAGRAMS
ELECTRICAL | D.103. | SD.9. | 288 | .02 | .REV_A | D.103.SD.9.288.02.REV_A | MARINE GROWTH PREVENTING PLANT ELE. SYSTEM DIAGRAM | [36 empty] | SHIP SYSTEMS
ELECTRICAL | D.103. | SD.9. | 381 | .01 | .REV_A | D.103.SD.9.381.01.REV_A | CARGO HOLD WATER LEVEL ALARM ELE. SYSTEM DIAGRAM | [36 empty] | EQUIPMENT FOR CARGO
ELECTRICAL | D.103. | SD.9. | 403 | .01 | .REV_A | D.103.SD.9.403.01.REV_A | RUDDER ANGLE INDICATOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 403 | .02 | .REV_A | D.103.SD.9.403.02.REV_A | STEERING GEAR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 412 | .01 | .REV_A | D.103.SD.9.412.01.REV_A | DGPS RECEIVER ELE. SYSTEM DIAGRAM$
ELECTRICAL | D.103. | SD.9. | 417 | .01 | .REV_A | D.103.SD.9.417.01.REV_A | CLOCK ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 417 | .02 | .REV_A | D.103.SD.9.417.02.REV_A | NAVTEX RECEIVER ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 417 | .03 | .REV_A | D.103.SD.9.417.03.REV_A | WEATHER FAX RECEIVER ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 419 | .01 | .REV_A | D.103.SD.9.419.01.REV_A | ECDIS ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 419 | .02 | .REV_A | D.103.SD.9.419.02.REV_A | BRIDGE WATCH ALARM ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 421 | .01 | .REV_A | D.103.SD.9.421.01.REV_A | RADIO EQUIPEMENT ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 421 | .02 | .REV_A | D.103.SD.9.421.02.REV_A | INMARSAT-FBB ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 423 | .01 | .REV_A | D.103.SD.9.423.01.REV_A | Network (LAN)
ELECTRICAL | D.103. | SD.9. | 423 | .02 | .REV_A | D.103.SD.9.423.02.REV_A | VDR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 424 | .01 | .REV_A | D.103.SD.9.424.01.REV_A | VHF RADIO TELEPHONE ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 427 | .01 | .REV_A | D.103.SD.9.427.01.REV_A | WHISTLE ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 433 | .01 | .REV_A | D.103.SD.9.433.01.REV_A | COMB. WINDLASS/MOORING WINCH ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 452 | .01 | .REV_A | D.103.SD.9.452.01.REV_A | ER OVERHEAD CRANE ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 571 | .01 | .REV_A | D.103.SD.9.571.01.REV_A | AIR COND AND REFRIGERTING PLANT ELE. DIAGRAM
ELECTRICAL | D.103. | SD.9. | 582 | .01 | .REV_A | D.103.SD.9.582.01.REV_A | SEWAGE TREATMENT PLANT ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 601 | .01 | .REV_A | D.103.SD.9.601.01.REV_A | M/E AUX. BLOWER ELE. DIAGRAM
ELECTRICAL | D.103. | SD.9. | 601 | .02 | .REV_A | D.103.SD.9.601.02.REV_A | M/E TURNING GEAR ELE DIAGRAM
ELECTRICAL | D.103. | SD.9. | 625 | .01 | .REV_A | D.103.SD.9.625.01.REV_A | TRANSFORMER CAPACITY CALCULATION
ELECTRICAL | D.103. | SD.9. | 665 | .01 | .REV_A | D.103.SD.9.665.01.REV_A | EM'CY GENERATOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 703 | .01 | .REV_A | D.103.SD.9.703.01.REV_A | H.F.O. PURIFIER ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 712 | .01 | .REV_A | D.103.SD.9.712.01.REV_A | L.O. PURIFIER ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 731 | .01 | .REV_A | D.103.SD.9.731.01.REV_A | MAIN AIR COMPRESSOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 731 | .02 | .REV_A | D.103.SD.9.731.02.REV_A | EMERGENCY AIR COMPRESSOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 733 | .01 | .REV_A | D.103.SD.9.733.01.REV_A | SERVICE AIR COMPRESSOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 734 | .01 | .REV_A | D.103.SD.9.734.01.REV_A | VALVE REMOTE CONTROL ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 761 | .01 | .REV_A | D.103.SD.9.761.01.REV_A | FRESH WATER GENERATOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 791 | .01 | .REV_A | D.103.SD.9.791.01.REV_A | E/R CONTROL CONSOLE ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 791 | .02 | .REV_A | D.103.SD.9.791.02.REV_A | WHEELHOUSE CONTROL CONSOLE ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 791 | .03 | .REV_A | D.103.SD.9.791.03.REV_A | AIS ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 792 | .01 | .REV_A | D.103.SD.9.792.01.REV_A | MONITORING AND ALARM ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 792 | .02 | .REV_A | D.103.SD.9.792.02.REV_A | CLOSED CIRCUIT TELEVISION (CCTV) ELE SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 793 | .01 | .REV_A | D.103.SD.9.793.01.REV_A | M/E REMOTE CONTROL ELE. SYS DIAGRAM
ELECTRICAL | D.103. | SD.9. | 794 | .01 | .REV_A | D.103.SD.9.794.01.REV_A | BOILER ELE. CONTROL SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 801 | .01 | .REV_A | D.103.SD.9.801.01.REV_A | BALLAST WATER TREATMENT PLANT ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 803 | .01 | .REV_A | D.103.SD.9.803.01.REV_A | OILY WATER SEPARATOR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 811 | .01 | .REV_A | D.103.SD.9.811.01.REV_A | FIRE STATION CONTROL PANEL
ELECTRICAL | D.103. | SD.9. | 811 | .02 | .REV_A | D.103.SD.9.811.02.REV_A | FIRE DETECTION AND ALARM ELE. SYTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 815 | .01 | .REV_A | D.103.SD.9.815.01.REV_A | CO2 RELEASE ALAMR ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 817 | .01 | .REV_A | D.103.SD.9.817.01.REV_A | FIXED WATER-BASED LOCAL FIRE FIGHTING ELE. SYSTEM DIAGRAM
ELECTRICAL | D.103. | SD.9. | 866 | .01 | .REV_A | D.103.SD.9.866.01.REV_A | DC24V BATTERY CHARGING/DISCHARGING PANEL SYSTEM
ELECTRICAL | D.103. | SD.9. | 872 | .01 | .REV_A | D.103.SD.9.872.01.REV_A | EMERGENCY DISCONNECT ELE. SYSTEM DIAGRAM
EQUIPMENT FOR CARGO | D.103. | SD | 300 | .01 | .REV_A | D.103.SD300.01.REV_A | Cargo securing manual | redondant en general
EQUIPMENT FOR CARGO | D.103. | SD | 301 | .01 | .REV_A | D.103.SD301.01.REV_A | Arrangement of hatch covers
EQUIPMENT FOR CARGO | D.103. | SD | 302 | .01 | .REV_A | D.103.SD302.01.REV_A | Arrangement and support of lashing points in cargo holds
EQUIPMENT FOR CARGO | D.103. | SD | 304 | .01 | .REV_A | D.103.SD304.01.REV_A | Arrangement of manholes
EQUIPMENT FOR CARGO | D.103. | SD | 304 | .02 | .REV_A | D.103.SD304.02.REV_A | Arrangement of small hatches
EQUIPMENT FOR CARGO | D.103. | SD | 331 | .01 | .REV_A | D.103.SD331.01.REV_A | Arrangement of cargo cranes
EQUIPMENT FOR CARGO | D.103. | SD | 373 | .01 | .REV_A | D.103.SD373.01.REV_A | Cargo hold ventilation system
EQUIPMENT FOR CARGO | D.103. | SD | 381 | .01 | .REV_A | D.103.SD381.01.REV_A | ARRANGEMENT OF CARGO HOLD WATER LEVEL ALARM EQUIPMENT
EQUIPMENT FOR CARGO | D.103. | SD | 382 | .01 | .REV_A | D.103.SD382.01.REV_A | Arrangement of cargo hold washing system

## Recap
DRAWINS LIST SCHEDULE
| DRAWINGS | TOTAL | RECEIVED | DONE | DELAY (DAYS) **
GENERAL | GENERAL ARRANGEMENT & CAPACITY PLAN | 0 |  | #REF!
| HULL LINES DRAWINGS | 0 |  | #DIV/0!
| FINAL DRAWINGS | 0 |  | #DIV/0!
| PRELIMINARY STABILITY | 0 |  | #DIV/0! |  | #REF!
| VARIOUS CALCULATIONS | 0 |  | #DIV/0!
| VARIOUS (ANCHOR, DAVIT, MAST, ETC) | 0 |  | #DIV/0!
| TOTAL | 57 |  | 0%
ELECTRICAL | POWER SYSTEM - ELECTRICAL LOAD BALANCE |  |  | #DIV/0!
| VARIOUS CALCULATIONS |  |  | #DIV/0!
| EQUIPMENT SYSTEM ELECTRICAL DIAGRAM |  |  | #DIV/0!
| ARRANGEMENT OF ELECTRICAL |  |  | #DIV/0!
| TOTAL | 48 |  | 0%
HULL | MIDSHIP |  |  | #DIV/0!
| CARGO AREA |  |  | #DIV/0!
| FWD AND AFT (ER, ACCOMMODATION, ETC) |  |  | #DIV/0!
| VARIOUS (FOUNDATION, WELDING SPEC, ETC) |  |  | #DIV/0!
| TOTAL | 72 |  | 0%
OUTFITTING | MOORING |  |  | #DIV/0!
| RUDDER SYSTEM |  |  | #DIV/0!
| RAIL, HANDRAIL, LADDER & MANHOLE |  |  | #DIV/0!
| SAFETY |  |  | #DIV/0!
| ICCP, ANODE |  |  | #DIV/0!
| VARIOUS (ANCHOR, DAVIT, MAST, ETC) |  |  | #DIV/0!
| TOTAL | 61 |  | 0%
MACHINERY | ROOM ARRANGEMENT |  |  | #DIV/0!
| VARIOUS CALCULATIONS |  |  | #DIV/0!
| PIPING SYSTEMS |  |  | #DIV/0!
| SHAFTING |  |  | #DIV/0!
| VARIOUS (EQUIPMENT MOUNTING PLAN, HOISTING BEAM, ETC) |  |  | #DIV/0!
| TOTAL | 93 |  | 0%
OVERALL | TOTAL | 331 | 0 | 0%
* Nb of settled is based on the "sent" column (when drawings received and comments sent back)
** Delay calculation is based on difference between planned date and drawing issued date

## Workload
DRAWINS LIST SCHEDULE
| 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2014-01-01
| June | July | August | September | Ocotber | November | December | January | February | March | TOTAL
GENERAL | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 57
HULL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72
MACHINERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93
ELECTRICAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
OUTFITTING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 331
TOTAL GS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0

## Mymacro
Enter your date : | 2014-09-18
Remarks : | Choose a received dwg date and start the macro.
If there are many files on the same day, then as many differents comments sheet would be created