## Feuil1
Discipline | DBS | DBS Description | WBS | WBS Description | CLIENT REFERENCE | DELIVERABLE REFERENCE | CAT | TITLE | WEIGHT | REVIEW CLASS | CWA | MILESTONE CHAIN | MSCODE | CUM% | PLAN DATE | FORECAST DATE | ACTUAL DATE | Weight% | Achieved Weight%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00001-00-D | 61402S-000-CN-0007-00001 | [D] | Process Basis of Design | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-11-30 | 2013-12-05 | 2013-12-05 | 0.03802% | 0.03802%
E357 | E357P17 | CIVIL WORKS | P | Power Generation | 3300-E-000-CS-DRW-57055-01-D | 61404U-000-DW-1741-57055 | [D] | Foundations Concrete Drawings - Pipe Rack 000-SPP-521 | 50 | 2-Document for CPY Comment | P01-Power Generation Interconnecting | E0310 | IFRE | 70 | 2014-10-24 | 2014-10-24 |  | 0.004962% | 0%
E357 | E357P14 | UNDERGROUND PIPING | T1 | LNG Train 1 | 3300-E-114-CS-DRW-04503-01-D | 61404U-114-DW-1432-04503 | [D] | Piles Layout for 114-PAU-012 | 30 | 2-Document for CPY Comment |  | E0310 | IFCE | 100 | 2014-05-23 | 2014-05-30 |  | 0.001259% | 0%
E357 | E357P18 | STRUCTURAL STEEL | W | West Interconnecting Piperack | 3300-E-000-CS-CAL-38110-00-D | 61404U-000-CN-1832-38110 | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-323 | 70 | 2-Document for CPY Comment | W01-West Interconnecting | E0310 | IFRE | 70 | 2014-03-21 | 2014-04-25 |  | 0.004476% | 0%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00002-00-D | 61402S-000-CN-0008-00002 | [D] | Drainage Philosophy | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 0.03802% | 0.03802%