## Somme PDBc PDB vs WP03_TEST
Database | Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Discipline | DBS | DBS Description | WBS | WBS Description | CAT | TITLE | WEIGHT | REVIEW CLASS | CWA | MILESTONE CHAIN | CUM% | PLAN DATE | FORECAST DATE | ACTUAL DATE | Weight% | Achieved Weight% | CLIENT REFERENCE | DELIVERABLE REFERENCE | MSCODE | MSCODE Procedure | WP03 Delv Ref + MSCode ok | Résultats Macro | Bonjour, Objectif recherché :
PDBc | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 01R | 2013-08-16 | IFR | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2013-09-19 | 61402S-TN-P332-00421 | 61402S-CTPJ-YLNG-TN-00420, 61402S-TP-JGC-TN-00241 | IFA | 2013-10-04 |  | Transmitted | E349 | E349M | ROTATING EQUIPMENT DESIGN | 0 | General ISBL | [DS] | Material Requistion Submerged Motor Pumps | 780 | 2-FCPY-COM | F00 | E0808 | 95 | 2014-05-15 | 2015-03-24 | 2015-03-24 | 0.2935% | 0.2935% |  | 61402S-000-MR-0910-00002 | VDW4 | TBTE | ROTATING EQUIPMENT DESIGN General ISBL | 61402S-000-MR-0910-00002
PDBc | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 02U | 2014-03-25 | PUR | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-04-24 | 61402S-TN-P332-04531 | 61402S-CTPJ-YLNG-TN-04421, 61402S-TP-JGC-TN-04490, 61402S-TP-Chiyoda-TN-00825 | IFR | 2014-05-09 | 2014-05-15 | Commented | E349 | E349L | ROTATING EQUIPMENT DESIGN | 0 | General ISBL | [DS] | MR Heavy Duty Amine Pumps | 813 |  | T15 | E0809 | 95 | 2015-02-03 | 2015-06-22 | 2015-06-22 | 0.8404% | 0.8404% | 3300-E-000-ME-REQ-91004-00-D | 61402S-000-MR-0910-00004 | VDW4 | TBTE | ROTATING EQUIPMENT DESIGN General ISBL |  | En colonne AP -> Si valeur colonne B trouvée en colonne AI, on recherche la valeur dans colonne AI et on la colle en face de la 1ère valeur de colonne B en colonne AP
PDBc | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 03U | 2014-08-05 | PUR | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-08-20 | 61402S-TN-P332-07621 | 61402S-CTPJ-YLNG-TN-07383, 61402S-TP-Chiyoda-TN-03859, 61402S-TP-JGC-TN-07659 | IFR | 2014-09-04 | 2014-09-17 | Transmitted | E392 | E392P | INSTRUMENTATION & SYSTEMS DESIGN | 0 | General ISBL | [D] | Material Requisition for Instrument Surge Protection | 1 | 2-FCPY-COM | SEVERAL | E0721 | 80 | 2015-06-19 | 2015-08-25 | 2015-08-25 | 8.896e-05% | 8.896e-05% | 3300-E-000-IC-REQ-00043-00-D | 61402S-000-MR-1573-00021 | VDWI1 | TBTE | INSTRUMENTATION & SYSTEMS DESIGN General ISBL
PDBc | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 04U | 2014-10-15 | PUR | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-10-24 | 61402S-TN-P332-09821 | 61402S-CTPJ-YLNG-TN-09504, 61402S-TP-JGC-TN-09822, 61402S-TP-Chiyoda-TN-06022 | IFR | 2014-11-08 | 2014-11-27 | Accepted | E392 | E392P | INSTRUMENTATION & SYSTEMS DESIGN | 0 | General ISBL | [D] | Material Requisition for Instrumentation Cables | 280 | 2-FCPY-COM | SEVERAL | E0721 | 95 | 2014-12-23 | 2015-08-25 | 2015-08-25 | 0.01868% | 0.01868% | 3300-E-000-IC-REQ-00026-00-D | 61402S-000-MR-1574-00001 | VDWI3 | TBTE | INSTRUMENTATION & SYSTEMS DESIGN General ISBL
PDBc | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 05U | 2015-04-28 | PUR | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2015-05-06 | 61402S-TN-P333-05917 | 61402S-CTPJ-YLNG-TN-16243, 61402S-TP-JGC-TN-16680, 61402S-TP-Chiyoda-TN-12879 | IFR | 2015-05-21 |  | Transmitted | E346 | E346P | ELECTRICAL DESIGN | 0 | General ISBL | [D] | Material Requisition for Local Distribution Boards | 306 | 2-FCPY-COM | 0 | E0715 | 100 | 2014-12-01 | 2015-08-19 | 2015-08-19 | 0.01246% | 0.01246% | 3300-E-000-EL-REQ-00003-00-D | 61402S-000-MR-1628-00001 | VDWI3 | TBTE | ELECTRICAL DESIGN General ISBL
PDB Dir | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 03U | 2014-06-19 | PURE | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-06-24 01:00 | 61404U-TN-MK332-00585 | 61404U-MKOC-TRADEST-TN-00070 | IFT |  |  | Transmitted | E348 | E348P | PACKAGES DESIGN | 0 | General ISBL | [DS] | Material Requisition for Essential Diesel Generator | 1500 |  |  | E0810 | 65 | 2014-05-02 | 2014-10-30 | 2014-10-30 | 8.296% | 8.296% |  | 61402S-000-MR-4123-00001 | VDWI2 | TBTE | PACKAGES DESIGN General ISBL
PDB Dir | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 02 | 2014-03-25 | PURE | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-03-10 01:00 | 61404U-TN-MK332-00316 | 61404U-MKOC-TRADEST-TN-00026 | IFT | 2014-04-07 01:00 |  | Transmitted | E348 | E348P | PACKAGES DESIGN | 0 | General ISBL | [DS] | Material Requisition for Essential Diesel Generator | 1500 |  |  | E0810 | 80 | 2014-09-01 | 2014-11-28 | 2014-11-28 | 4.978% | 4.978% |  | 61402S-000-MR-4123-00001 | VDWI4 | TBTE | PACKAGES DESIGN General ISBL
PDB Dir | 61402S-000-MR-0910-00002 | Material Requisition for Canned Submerged Motor Pumps | 03 | 2014-06-19 | PURE | 3300-E-000-ME-REQ-91002-00-D | 349-Rotating | 2014-06-24 01:00 | 61404U-TN-MK332-00585 | 61404U-MKOC-TRADEST-TN-00070 | IFT | 2014-07-01 01:00 | 2014-07-21 | Translated | E392 | E392P | INSTRUMENTATION & SYSTEMS DESIGN | 0 | General ISBL | [D] | Flexible Protection for Valves and Instrumentation | 150 | 3-DOCFINFO | SEVERAL | E0506 | 100 | 2015-04-24 | 2015-08-25 | 2015-08-25 | 0.01001% | 0.01001% | 3300-E-000-IC-MTO-00051-00-D | 61402S-000-MTO-1577-00051 | IFP3E | PURE | INSTRUMENTATION & SYSTEMS DESIGN General ISBL
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 01R | 2013-10-08 | ENQ | 3300-E-000-ME-REQ-91004-00-D | 349-Packages | 2013-10-30 | 61402S-TN-P332-00884 | 61402S-CTPJ-YLNG-TN-00878, 61402S-TP-JGC-TN-00699 | IFA | 2013-11-14 |  | Transmitted | E353 | E353P | PIPING & LAYOUT DESIGN | 0 | General ISBL | [D] | Piping Interface Drawing POC/EDG | 1 |  |  | E0510 | 80 | 2015-03-11 | 2015-07-01 | 2015-07-01 | 4.541e-05% | 4.541e-05% | 3300-E-040-MP-DRW-00011 | 61402S-040-DW-0052-00011 | IFCE | AFCE | PIPING & LAYOUT DESIGN General ISBL | #N/A
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 02R | 2013-11-06 | ENQ | 3300-E-000-ME-REQ-91004-00-D | 349-Packages | 2013-12-10 | 61402S-TN-P332-01614 | 61402S-CTPJ-YLNG-TN-01593, 61402S-TP-JGC-TN-01422 | IFA | 2013-12-25 |  | Transmitted | E353 | E353P | PIPING & LAYOUT DESIGN | 0 | General ISBL | [D] | Piping Interface Drawing POC/ DAILY TANK | 1 |  |  | E0510 | 80 | 2015-03-11 | 2015-07-01 | 2015-07-01 | 4.541e-05% | 4.541e-05% | 3300-E-040-MP-DRW-00012 | 61402S-040-DW-0052-00012 | IFCE | AFCE | PIPING & LAYOUT DESIGN General ISBL
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 03U | 2014-02-12 | PUR | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2014-02-27 | 61402S-TN-P332-03177 | 61402S-CTPJ-YLNG-TN-03112, 61402S-TP-JGC-TN-03037 | IFA | 2014-03-14 | 2014-04-09 | Commented | E357 | E357P18 | STRUCTURAL STEEL | 0 | General ISBL | [D] | Calculation Note for Typical Transportation Frame (12M Span) | 50 |  |  | E0311 | 100 | 2015-02-13 | 2015-08-10 | 2015-08-10 | 0.000611% | 0.000611% | 3300-E-000-CS-CAL-08100-00-D | 61404U-000-CN-1800-08100 | IFDE | AFDE | STRUCTURAL STEEL General ISBL
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 04U | 2014-10-10 | PUR | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2014-10-21 | 61402S-TN-P332-09692 | 61402S-CTPJ-YLNG-TN-09380, 61402S-TP-JGC-TN-09694, 61402S-TP-Chiyoda-TN-05894 | IFA | 2014-11-05 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-505 | 70 | 2-FCPY-COM | P01 | E0310 | 100 | 2014-09-05 | 2015-08-03 | 2015-08-03 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58015-00-D | 61404U-000-CN-1832-58015 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 05U | 2015-02-16 | PUR | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2015-02-27 | 61402S-TN-P333-03960 | 61402S-CTPJ-YLNG-TN-13900, 61402S-TP-JGC-TN-14291, 61402S-TP-Chiyoda-TN-10491 | IFA | 2015-03-14 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-517 | 70 | 2-FCPY-COM | P04 | E0310 | 100 | 2014-09-19 | 2015-08-03 | 2015-08-03 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58035-00-D | 61404U-000-CN-1832-58035 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDBc | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 06U | 2015-04-21 | PUR | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2015-04-29 | 61402S-TN-P333-05793 | 61402S-CTPJ-YLNG-TN-16109, 61402S-TP-JGC-TN-16536, 61402S-TP-Chiyoda-TN-12735 | IFA | 2015-05-14 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Steel Structure - Pipe Rack 000-SPP-531 | 70 |  |  | E0310 | 100 | 2015-03-09 | 2015-08-10 | 2015-08-10 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58180-00-D | 61404U-000-CN-1832-58180 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDB Dir | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 03 | 2014-02-12 | PURE | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2014-02-17 | 61404U-TN-L332-00931 | 61404U-LOC-TRADEST-TN-00094 | IFT | 2014-02-20 | 2014-02-21 | Translated | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Steel Structure - Pipe Rack 000-SPP-535 | 70 |  |  | E0310 | 100 | 2015-04-24 | 2015-08-10 | 2015-08-10 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58200-00-D | 61404U-000-CN-1832-58200 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDB Dir | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 02 | 2013-11-06 | ENQE | 3300-E-000-ME-REQ-91004-00-D | 349-Packages | 2013-11-21 | 61404U-TN-L332-00399 | 61404U-LOC-TRADEST-TN-00028 | IFT | 2013-11-27 | 2013-11-27 | Translated | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Steel Structure - Pipe Rack 000-SPP-536 | 70 |  |  | E0310 | 100 | 2015-04-24 | 2015-08-10 | 2015-08-10 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58205-00-D | 61404U-000-CN-1832-58205 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDB Dir | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 01 | 2013-10-08 | ENQE | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2013-10-09 | 61404U-TN-L332-00215 | 61404U-LOC-TRADEST-TN-00011 | IFT | 2013-10-16 | 2013-10-23 | Translated | E357 | E357P18 | STRUCTURAL STEEL | P | Power Generation | [D] | Calculation Note for Steel Structure - Pipe Rack 000-SPP-537 | 70 |  |  | E0310 | 100 | 2015-04-24 | 2015-08-10 | 2015-08-10 | 0.007171% | 0.007171% | 3300-E-000-CS-CAL-58210-00-D | 61404U-000-CN-1832-58210 | IFCE | AFCE | STRUCTURAL STEEL Power Generation
PDB Dir | 61402S-000-MR-0910-00004 | Material Requisition for Heavy Duty Amine Pumps | 04 | 2014-09-12 | PURE | 3300-E-000-ME-REQ-91004-00-D | 349-Rotating | 2014-10-13 | 61404U-TN-L332-02601 | 61404U-LOC-TRADEST-TN-00343 | IFT | 2014-10-17 | 2014-10-15 | Translated | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-601 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68001-00-D | 61404U-000-CN-1832-68001 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1573-00021 | Material Requisition for Instrument Field Surge Protection | 01R | 2015-02-10 | ENQ | 3300-E-000-IC-REQ-00043-00-D | 392-Instrumentation and Telecom | 2015-03-03 | 61402S-TN-P333-04046 | 61402S-CTPJ-YLNG-TN-14008, 61402S-TP-JGC-TN-14400, 61402S-TP-Chiyoda-TN-10600 | IFR | 2015-03-18 | 2015-03-13 | Accepted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-602 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68005-00-D | 61404U-000-CN-1832-68005 | IFCE | AFCE | STRUCTURAL STEEL HP Flares | #N/A
PDBc | 61402S-000-MR-1573-00021 | Material Requisition for Instrument Field Surge Protection | 02U | 2015-05-26 | PUR | 3300-E-000-IC-REQ-00043-00-D | 392-Instrumentation and Telecom | 2015-05-29 | 61402S-TN-P333-06541 | 61402S-CTPJ-YLNG-TN-16998, 61402S-TP-JGC-TN-17450, 61402S-TP-Chiyoda-TN-13649 | IFR | 2015-06-13 | 2015-06-04 | Commented | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-603 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68010-00-D | 61404U-000-CN-1832-68010 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1573-00021 | Material Requisition for Instrument Field Surge Protection | 03U | 2015-07-08 | PUR | 3300-E-000-IC-REQ-00043-00-D | 392-Instrumentation and Telecom | 2015-09-11 | 61402S-TN-P333-08852 | 61402S-CTPJ-YLNG-TN-19758, 61402S-TP-JGC-TN-20259, 61402S-TP-Chiyoda-TN-16459 | IFR | 2015-09-26 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-604 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68015-00-D | 61404U-000-CN-1832-68015 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDB Dir | 61402S-000-MR-1573-00021 | Material Requisition for Instrument Field Surge Protection | 01 | 2015-02-10 | ENQE | 3300-E-000-IC-REQ-00043-00-D | 392-Instrumentation and Telecom | 2015-02-12 | 61404U-TN-P333-03037 | 61404U-POC-TRADEST-TN-02509 | IFT | 2015-02-16 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-607 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68030-00-D | 61404U-000-CN-1832-68030 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1574-00001 | Material Requisition for Instrumentation Cables | 01R | 2014-07-02 | ENQ | 3300-E-000-IC-REQ-00026-00-D | 392-Instrumentation and Telecom | 2014-08-21 | 61402S-TN-P332-07668 | 61402S-CTPJ-YLNG-TN-07430, 61402S-TP-JGC-TN-07706, 61402S-TP-Chiyoda-TN-03906 | IFR | 2014-09-05 | 2014-09-15 | Commented | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-609 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68040-00-D | 61404U-000-CN-1832-68040 | IFCE | AFCE | STRUCTURAL STEEL HP Flares | #N/A
PDBc | 61402S-000-MR-1574-00001 | Material Requisition for Instrumentation Cables | 02U | 2015-01-29 | PUR | 3300-E-000-IC-REQ-00026-00-D | 392-Instrumentation and Telecom | 2015-02-04 | 61402S-TN-P333-03159 | 61402S-CTPJ-YLNG-TN-12967, 61402S-TP-JGC-TN-13351, 61402S-TP-Chiyoda-TN-09552 | IFR | 2015-02-19 | 2015-03-09 | Accepted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-610 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68045-00-D | 61404U-000-CN-1832-68045 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1574-00001 | Material Requisition for Instrumentation Cables | 03U | 2015-07-08 | PUR | 3300-E-000-IC-REQ-00026-00-D | 392-Instrumentation and Telecom | 2015-09-11 | 61402S-TN-P333-08852 | 61402S-CTPJ-YLNG-TN-19758, 61402S-TP-JGC-TN-20259, 61402S-TP-Chiyoda-TN-16459 | IFR | 2015-09-26 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-611 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68050-00-D | 61404U-000-CN-1832-68050 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDB Dir | 61402S-000-MR-1574-00001 | Material Requisition for Instrumentation Cables | 01 | 2014-07-02 | ENQE | 3300-E-000-IC-REQ-00026-00-D | 392-Instrumentation and Telecom | 2014-07-07 | 61404U-TN-P332-06641 | 61404U-POC-TRADEST-TN-01274 | IFT | 2014-07-14 | 2014-08-13 | Translated | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-612 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68055-00-D | 61404U-000-CN-1832-68055 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 01R | 2014-04-03 | ENQ | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2014-05-15 | 61402S-TN-P332-05012 | 61402S-CTPJ-YLNG-TN-04886, 61402S-TP-JGC-TN-05025, 61402S-TP-Chiyoda-TN-01299 | IFR | 2014-05-30 | 2014-06-16 | Commented | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-613 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68060-00-D | 61404U-000-CN-1832-68060 | IFCE | AFCE | STRUCTURAL STEEL HP Flares | #N/A
PDBc | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 02U | 2014-10-22 | PUR | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2014-11-24 | 61402S-TN-P333-00905 | 61402S-CTPJ-YLNG-TN-10539, 61402S-TP-JGC-TN-10887, 61402S-TP-Chiyoda-TN-07087 | IFR | 2014-12-09 | 2014-12-18 | Accepted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-614 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68065-00-D | 61404U-000-CN-1832-68065 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 03U | 2015-06-18 | PUR | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2015-09-11 | 61402S-TN-P333-08856 | 61402S-CTPJ-YLNG-TN-19764, 61402S-TP-JGC-TN-20265, 61402S-TP-Chiyoda-TN-16465 | IFR | 2015-09-26 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-615 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-09-26 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68070-00-D | 61404U-000-CN-1832-68070 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDBc | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 04U | 2015-07-09 | PUR | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2015-09-11 | 61402S-TN-P333-08857 | 61402S-CTPJ-YLNG-TN-19765, 61402S-TP-JGC-TN-20266, 61402S-TP-Chiyoda-TN-16466 | IFI |  |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-653 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-08-01 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68085-00-D | 61404U-000-CN-1832-68085 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDB Dir | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 01 | 2014-04-03 | ENQE | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2014-04-07 | 61404U-TN-P332-04533 | 61404U-POC-TRADEST-TN-00768, 61404U-LOC-CHIYODA-TN-00032 | IFT | 2014-04-14 | 2014-04-18 | Translated | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-654 | 70 | 2-FCPY-COM | H02 | E0310 | 100 | 2014-08-01 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68090-00-D | 61404U-000-CN-1832-68090 | IFCE | AFCE | STRUCTURAL STEEL HP Flares
PDB Dir | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 02 | 2014-10-22 | PURE | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2014-11-14 | 61404U-TN-P333-00749 | 61404U-POC-TRADEST-TN-02089 | IFT | 2014-11-18 | 2014-11-18 | Translated | E357 | E357P18 | STRUCTURAL STEEL | W | West Interconnecting Piperack | [D] | Calculation Note for Primary Steel Structure - Pipe Rack 000-SPP-655 | 70 | 2-FCPY-COM |  | E0310 | 100 | 2014-08-01 | 2015-08-03 | 2015-08-03 | 0.002156% | 0.002156% | 3300-E-000-CS-CAL-68100-00-D | 61404U-000-CN-1832-68100 | IFCE | AFCE | STRUCTURAL STEEL West Interconnecting Piperack
PDB Dir | 61402S-000-MR-1628-00001 | Material Requisition for Local Distribution Boards (Hazardous Area) | 03 | 2015-06-18 | PURE | 3300-E-000-EL-REQ-00003-00-D | 346-Electrical Design | 2015-06-19 | 61404U-TN-P333-05745 | 61404U-POC-TRADEST-TN-03033 | IFT | 2015-06-23 |  | Transmitted | E357 | E357P18 | STRUCTURAL STEEL | H | HP Flares | [D] | Calculation Note for Steel Structure - Pipe Rack 000-SPP-616 | 70 |  |  | E0310 | 100 | 2014-12-17 | 2015-08-03 | 2015-08-03 | 0.003133% | 0.003133% | 3300-E-000-CS-CAL-68145-00-D | 61404U-000-CN-1832-68145 | IFCE | AFCE | STRUCTURAL STEEL HP Flares