## Yq_ProgressBackupWP3
Discipline | DBS | DBS Description | WBS | WBS Description | CLIENT REFERENCE | DELIVERABLE REFERENCE | CAT | TITLE | WEIGHT | REVIEW CLASS | CWA | MILESTONE CHAIN | MSCODE | CUM% | PLAN DATE | FORECAST DATE | ACTUAL DATE | Weight% | Achieved Weight%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00001-00-D | 61402S-000-CN-0007-00001 | [D] | Process Basis of Design | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-11-30 | 2013-12-05 | 2013-12-05 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00001-00-D | 61402S-000-CN-0007-00001 | [D] | Process Basis of Design | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2014-01-15 | 2014-04-24 | 2014-04-24 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00002-00-D | 61402S-000-CN-0007-00002 | [D] | Process Sizing Criteria | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-06-28 | 2013-06-28 | 2013-06-28 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00002-00-D | 61402S-000-CN-0007-00002 | [D] | Process Sizing Criteria | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2013-09-23 | 2013-09-26 | 2013-09-26 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00004-00-D | 61402S-000-CN-0008-00004 | [D] | Emergency Shutdown Philosophy | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-07-05 | 2013-07-03 | 2013-07-03 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00004-00-D | 61402S-000-CN-0008-00004 | [D] | Emergency Shutdown Philosophy | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2013-10-26 | 2013-12-06 | 2013-12-06 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00008-00-D | 61402S-000-CN-0008-00008 | [D] | Overall Operating and Control philosophy (including transient, start-up, degraded case, ESD cases) | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-11-15 | 2014-02-28 | 2014-02-28 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00008-00-D | 61402S-000-CN-0008-00008 | [D] | Overall Operating and Control philosophy (including transient, start-up, degraded case, ESD cases) | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2014-01-15 | 2014-04-22 |  | 0.01462% | 0%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00009-00-D | 61402S-000-CN-0008-00009 | [D] | Sparing Philosophy | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-07-12 | 2013-07-12 | 2013-07-12 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PHI-00009-00-D | 61402S-000-CN-0008-00009 | [D] | Sparing Philosophy | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2013-10-12 | 2013-10-04 | 2013-10-04 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-LST-00102-00-D | 61402S-000-NM-0021-00102 | [D] | PID Index | 77 | 2-Document for CPY Comment | Several CWA | E0304 | IFRE | 75 | 2013-12-07 | 2013-12-29 | 2013-12-29 | 0.0287% | 0.0287%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-LST-00102-00-D | 61402S-000-NM-0021-00102 | [D] | PID Index | 77 | 2-Document for CPY Comment | Several CWA | E0304 | IFDE | 100 | 2015-01-30 | 2014-06-30 |  | 0.01104% | 0%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PRO-00002-00-D | 61404U-000-CN-0007-00004 | [D] | Line List Preparation Standards | 102 | 3-Document for Information | Several CWA | E0304 | IFRE | 75 | 2013-10-15 | 2013-10-28 | 2013-10-28 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-PRO-00002-00-D | 61404U-000-CN-0007-00004 | [D] | Line List Preparation Standards | 102 | 3-Document for Information | Several CWA | E0304 | IFDE | 100 | 2013-11-15 | 2013-11-15 | 2013-11-15 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00003-00-D | 61404U-000-CN-0007-00006 | [D] | Process Simulation Design Basis | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-11-15 | 2013-12-20 | 2013-12-20 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-BOD-00003-00-D | 61404U-000-CN-0007-00006 | [D] | Process Simulation Design Basis | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2013-12-20 | 2014-03-21 | 2014-03-21 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-SOW-00001-00-D | 61404U-000-CN-0008-00001 | [D] | Hot Air recirculation study - Scope of work | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2013-08-08 | 2013-07-22 | 2013-07-22 | 0.03802% | 0.03802%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-SOW-00001-00-D | 61404U-000-CN-0008-00001 | [D] | Hot Air recirculation study - Scope of work | 102 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2013-09-27 | 2013-09-04 | 2013-09-04 | 0.01462% | 0.01462%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-SOW-00002-00-D | 61404U-000-CN-0008-00012 | [D] | Hot Air recirculation study 2 Scope of Work | 100 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2014-03-28 | 2014-03-07 | 2014-03-07 | 0.03727% | 0.03727%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-SOW-00002-00-D | 61404U-000-CN-0008-00012 | [D] | Hot Air recirculation study 2 Scope of Work | 100 | 1-Document for CPY Approval | Several CWA | E0304 | IFDE | 100 | 2014-04-30 | 2014-04-24 | 2014-04-24 | 0.01433% | 0.01433%
E312 | E312P | PROCESS DESIGN | 0 | General ISBL | 3300-E-000-PR-REP-00004-00-D | 61404U-000-CN-0008-00013 | [D] | Hot Air recirculation study 2 | 100 | 1-Document for CPY Approval | Several CWA | E0304 | IFRE | 75 | 2014-05-30 | 2014-06-20 |  | 0.03727% | 0%