## Planning
ID | Ref | Type | MSN | Completion Date | Defect Code | Plannification | Comment | Type
474657582493 | 91 | LB | 00146 | 2017-11-02 | Adjustment | D2 | Rework pipe | Mecanic
474681582645 | 106 | LB | 00146 | 2017-11-01 | Floor Pan | D1 | Impact paint | Paint
474683582644 | 107 | LB | 00146 | 2017-11-01 | Floor Pan | D1 | Impact paint | Paint
455709534017 | 525 | GN | 00146 | 2017-10-30 | Shroud | Out | Scratchs | Mecanic
aaaa | 100 | zzz | zzzz | zzzzz | zzz | zzz | zzzz | Counter-Top
bbbb | 200 | zzz | zzzz | zzzzz | zzz | zzz | zzzz | Elec
cccc | 300 | zzz | zzzz | zzzzz | zzz | zzz | zzzz | Deco

## Calendar
PLAN
Task exceeded |  | 2017-10-31 | 2017-10-31 | 2017-11-01 | 2017-11-01 | 2017-11-02 | 2017-11-02 | 2017-11-03 | 2017-11-03 | 2017-11-04 | 2017-11-04 | 2017-11-05 | 2017-11-05
|  | Total Time: | 4 | Total Time: | 4 | Total Time: | 2 | Total Time: | 0 | Total Time: | 0 | Total Time: | 0
|  | Worker Needed: | 0.66667 | Worker Needed: | 0.66667 | Worker Needed: | 0.33333 | Worker Needed: | 0 | Worker Needed: | 0 | Worker Needed: | 0
|  |  | #N/A |  | #N/A |  | #N/A | Visit | Engine Run | Test Elec | RTO | Test structure | First Flight
|  | 106 107 |  | 106 107 |  | 91
2017-11-06 | 2017-11-06 | 2017-11-07 | 2017-11-07 | 2017-11-08 | 2017-11-08 | 2017-11-09 | 2017-11-09 | 2017-11-10 | 2017-11-10 | 2017-11-11 | 2017-11-11 | 2017-11-12 | 2017-11-12
Total Time: | 0 | Total Time: | 0 | Total Time: | 2 | Total Time: | 0 | Total Time: | 0 | Total Time: | 0 | Total Time: | 0
Worker Needed: | 0 | Worker Needed: | 0 | Worker Needed: | 1 | Worker Needed: | 0 | Worker Needed: | 0 | Worker Needed: | 0 | Worker Needed: | 0
| #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
|  |  |  | 525 |  | 100 200 106 300 |  | 200 106 107 200
2017-11-13 | 2017-11-13 | Out Scope
Total Time: | 0
Worker Needed: | 0
#N/A
100 200 106 300
Legend color text:
Elec / Deco / Paint / Counter-Top
Test