## Suivi
Info commande | [7 empty] | Enregistrement | [5 empty] | Etude
N° devis | Client | N° cde client | N° cde SEI | N° de ligne cde | Commercial | Date de cde | Delai rendu client | Type de convoyeur | Type de dossier E / RM /R | Date d'enregistrement | Nom de celui qui a fait l'enregistrement | N° Plan SEI | Commentaire | Nom du dessinateur | Date debut | Etat | Date envoi approbation | Accord le : | Detail du projet (debit et nomenclature) | Lancement du dossier à l'atelier
COXXXX1 | YIY1 | 1 | Jxxx1 | 01 | - | 2017-02-02 | 2017-03-30 | ESSAI1 | E1 | 2017-08-20 | ADE | xxxx1 | note1 | FDO
COXXXX2 | YIY2 | 2 | Jxxx2 | 02 | - | 2017-02-03 | 2017-03-31 | ESSAI2 | E2 | 2017-08-21 | ADE | xxxx2 | note2
COXXXX3 | YIY3 | 3 | Jxxx3 | 03 | - | 2017-02-04 | 2017-04-01 | ESSAI3 | E3 | 2017-08-22 | ADE | xxxx3 | note3
COXXXX4 | YIY4 | 4 | Jxxx4 | 04 | - | 2017-02-05 | 2017-04-02 | ESSAI4 | E4 | 2017-08-23 | ADE | xxxx4 | note4
COXXXX5 | YIY5 | 5 | Jxxx5 | 05 | - | 2017-02-06 | 2017-04-03 | ESSAI5 | E5 | 2017-08-24 | ADE | xxxx5 | note5
COXXXX6 | YIY6 | 6 | Jxxx6 | 06 | - | 2017-02-07 | 2017-04-04 | ESSAI6 | E6 | 2017-08-25 | ADE | xxxx6 | note6
COXXXX7 | YIY7 | 7 | Jxxx7 | 07 | - | 2017-02-08 | 2017-04-05 | ESSAI7 | E7 | 2017-08-26 | ADE | xxxx7 | note7
COXXXX8 | YIY8 | 8 | Jxxx8 | 08 | - | 2017-02-09 | 2017-04-06 | ESSAI8 | E8 | 2017-08-27 | ADE | xxxx8 | note8
COXXXX9 | YIY9 | 9 | Jxxx9 | 09 | - | 2017-02-10 | 2017-04-07 | ESSAI9 | E9 | 2017-08-28 | ADE | xxxx9 | note9
COXXXX10 | YIY10 | 10 | Jxxx10 | 10 | - | 2017-02-11 | 2017-04-08 | ESSAI10 | E10 | 2017-08-29 | ADE | xxxx10 | note10
COXXXX11 | YIY11 | 11 | Jxxx11 | 11 | - | 2017-02-12 | 2017-04-09 | ESSAI11 | E11 | 2017-08-30 | ADE | xxxx11 | note11
COXXXX12 | YIY12 | 12 | Jxxx12 | 12 | - | 2017-02-13 | 2017-04-10 | ESSAI12 | E12 | 2017-08-31 | ADE | xxxx12 | note12
Bouton 1

## BD
Nom du commercial | Nom du dessinateur
JPC | ADE
EL | FDO
DG | LBO
- | SLE
-- | -
--- | --
---

## Exemple
PREPARATION | PROJECT DEFINITION | ANALYSIS | DESIGN | DEVELOPMENT | TESTING | IMPLEMENTATION | ACCEPTANCE | REVIEW | CLOSE-DOWN | OPERATIONAL SUPPORT | * | Color | PROJECT PHASES | PUBLIC HOLIDAYS
Perform feasibility study | Define Project | Document high-level business requirements | Document current state design | Build IT Infrastructure | Build test packs and scripts | Schedule implementation | Perform final user acceptance | Document post implementation review | Document project closedown report | Manage operational schedule (facilities) | * |  | PREPARATION
Perform risk & impact assessment | Document project definition report | Document high-level technology requirements | Define process model | Build prototype | Perform system testing | Implement IT Infrastructure | Perform final operational acceptance |  | Release resources | Manage availability | * |  | PROJECT DEFINITION
Document business case | Document project plan | Document detailed business requirements | Define organisational chart | Design physical prototype | Perform integration testing | Implement data migration | Signoff implementation completion |  | Perform contract close-out / change-over | Manage capacity | * |  | ANALYSIS
Document umbrella contract | Document quality plan | Document detailed technology requirements | Define location chart | Build physical prototype | Perform user acceptance testing | Perform data extraction routines |  |  |  | Manage performance | * |  | DESIGN
Obtain interim funding | Document resource terms of reference |  | Define data architecture | Test physical prototype | Perform regression testing | Perform data scrubbing & migration routines |  |  |  | Manage backup and recovery | * |  | DEVELOPMENT
| Project definition approved |  | Define application architecture | Implement prototype | Review implementation readiness | Perform data loading routines |  |  |  | Manage disaster recovery | * |  | TESTING
| Agree Contract |  | Define technical architecture | Market and approve prototype |  | Check data validity |  |  |  | Manage against SLAs | * |  | IMPLEMENTATION
| Document vendor/client contract |  | Current state design approved | Prototype authorised |  | Implement application software |  |  |  | Manage security | * |  | ACCEPTANCE
|  |  | Document future state design | Build database |  | Distribute and install application software |  |  |  | Manage data | * |  | REVIEW
|  |  | Define process model | Develop database |  | Test installed application software |  |  |  | Manage on-going training | * |  | CLOSE-DOWN
|  |  | Define organisational chart | Produce database design |  | Implement technology hardware |  |  |  | Support solution (1st/2nd/3rd level) | * |  | OPERATIONAL SUPPORT
|  |  | Define location chart | Build database |  | Distribute and install technology hardware |  |  |  |  | *
|  |  | Define data architecture | Build database testing routines |  | Test installed technology hardware |  |  |  |  | * | E-MAIL TEXTS
|  |  | Define application architecture | Perform database unit testing |  | Implement Business Infrastructure |  |  |  |  | * | Sending Task List to participants:
|  |  | Define technical architecture | Develop data migration |  | Implement processes |  |  |  |  | * | Please find below a list of project tasks for which you have been identified as responsible for. The timing and deliverables for each task reflect those defined in the project plan. Please advise of any issues that you may have regarding this list. Furthermore, regular updates on reporting the progress of these tasks would be greatly appreciated.
|  |  | Future state design approved | Produce data migration design |  | Distribute process & procedural documentation |  |  |  |  | *
|  |  | Perform detailed planning | Build data migration components |  | Check distribution complete |  |  |  |  | *
|  |  | Define organisational change strategy | Build data migration testing routines |  | Implement organisational changes |  |  |  |  | *
|  |  | Define development strategy | Perform data migration unit testing |  | Undertake actual org. changes |  |  |  |  | *
|  |  | Define testing strategy | Database development complete | [6 empty] | *
|  |  | Define implementation strategy | Build application software | [6 empty] | *
|  |  | Define acceptance strategy | Design software configuration | [6 empty] | *
|  |  | Define operational support strategy | Install and configure software components | [6 empty] | *
|  |  |  | Build software testing routines | [6 empty] | *
|  |  |  | Unit test software components | [6 empty] | *
|  |  |  | Software development complete | [6 empty] | *
|  |  |  | Build technology hardware | [6 empty] | *
|  |  |  | Design hardware configuration | [6 empty] | * | Requesting Progress reports:
|  |  |  | Install and configure hardware components | [6 empty] | * | Please find below a list of your outstanding project tasks. In order to monitor the status of the overall project, your co-operation is required to report on the progress of each task. Where possible, please provide the exact number of units completed to date. If the the task has been fully completed, please provide the completion date.
|  |  |  | Build hardware testing routines | [6 empty] | *
|  |  |  | Unit test hardware components | [6 empty] | *
|  |  |  | Hardware development complete | [6 empty] | *
|  |  |  | Build Business Infrastructure | [6 empty] | *
|  |  |  | Build business processes | [6 empty] | *
|  |  |  | Document detailed process model | [6 empty] | *
|  |  |  | Document detailed procedures | [6 empty] | *
|  |  |  | Unit test processes and procedures | [6 empty] | *
|  |  |  | Process development complete | [6 empty] | *
|  |  |  | Undertake communications | [6 empty] | *
|  |  |  | Document communications plan | [6 empty] | *
|  |  |  | Communicate organisational changes | [6 empty] | *
|  |  |  | Communicate system changes | [6 empty] | *
|  |  |  | Measure communications effectiveness | [6 empty] | *
|  |  |  | Communications plan implemented | [6 empty] | *
|  |  |  | Undertake training | [6 empty] | *
|  |  |  | Document training procedures & handbook | [6 empty] | *
|  |  |  | Perform organisational training / re-skilling | [6 empty] | *
|  |  |  | Measure training effectiveness | [6 empty] | *
|  |  |  | Traininng complete | [6 empty] | *
|  |  |  | Build physical locations | [6 empty] | *
|  |  |  | Produce physical location design | [6 empty] | *
|  |  |  | Purchase / build locations | [6 empty] | *
|  |  |  | Unit test locations | [6 empty] | *
|  |  |  | Location development complete | [6 empty] | *
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*