## Cover Page
SHELL PROJECT & TECHNOLOGY
REDIIGreen
MASTER DOCUMENT REGISTER
Project Name | REDIIGreen
Project Number | 09173H60
Plant Code | HVO
Document Number | 09173H60-0000-FA-0005
PCAP ID
Discipline Code | PRJ
Document Type | FA
Originator / Author | JC ROOSSENS
Company Code
Revision | 5
Status | IFR
Issue Date | 2026-04-16
ECCN
Information Security Classification
JPI Document Number

## Feuil1
CRITERE
|  |  |  | double clic sur une cellule de cette colonne | CNI
PERMIS
bidule | 0/4 | effectué | restante | Document à fournir ( menu deroulant) | ASSURANCE
abc | FALSE | 0 | 0 | CNI;ASSURANCE | CONTRÔLE
def | FALSE | 0%
ghi | FALSE
jkl | FALSE |  |  |  | cette colonne
peut être
masquée

## PROGRESS (hidden)
WORLEY PROJECT
2026-04-16
PROGRESS - ALL DOCUMENTS LATEST REVISION
WEEK | Total Docs MDL | Total Docs.MDL Due (livrable) | Total Dispatched Documents | Total APPROVED Documents | Total COMMENTED Documents | Document to be Returned by Client | General Progress Docs. DUE APPROVED | General Progress Docs. APPROVED | General Progress Docs COMMENTED | General Progress Docs DUE - Client | GENERAL PROGRESS TOTAL
S41 | 184 | 127 | 11 | 0 | 0 | 11 | 0% | 0% | 0% | 100% | 100%
S42 | 209 | 128 | 39 | 0 | 0 | 39 | 0% | 0% | 0% | 100% | 100%
S43 | 213 | 137 | 48 | 0 | 0 | 48 | 0% | 0% | 0% | 100% | 100%
S44 | 224 | 137 | 54 | 0 | 0 | 54 | 0% | 0% | 0% | 100% | 100%
S45 | 277 | 159 | 65 | 0 | 8 | 57 | 0% | 0% | 12.31% | 87.69% | 100%
S46 | 277 | 159 | 65 | 0 | 8 | 57 | 0% | 0% | 12.31% | 87.69% | 100%
S47 | 322 | 152 | 65 | 1 | 34 | 30 | 0.6579% | 1.538% | 52.31% | 46.15% | 100%
S48 | 328 | 152 | 74 | 5 | 52 | 17 | 3.289% | 6.757% | 70.27% | 22.97% | 100%
S49 | 328 | 154 | 77 | 4 | 54 | 19 | 2.597% | 5.195% | 70.13% | 24.68% | 100%
S50 | 344 | 155 | 97 | 4 | 48 | 45 | 2.581% | 4.124% | 49.48% | 46.39% | 100%
S01 | 358 | 164 | 110 | 7 | 47 | 56 | 4.268% | 6.364% | 42.73% | 50.91% | 100%
S02 | 375 | 175 | 113 | 6 | 36 | 71 | 3.429% | 5.31% | 31.86% | 62.83% | 100%
S04 | 404 | 199 | 127 | 14 | 49 | 64 | 7.035% | 11.02% | 38.58% | 50.39% | 100%
S05 | 414 | 208 | 130 | 14 | 49 | 67 | 6.731% | 10.77% | 37.69% | 51.54% | 100%
S06 | 423 | 212 | 135 | 14 | 49 | 72 | 6.604% | 10.37% | 36.3% | 53.33% | 100%
S07 | 430 | 216 | 138 | 14 | 49 | 75 | 6.481% | 10.14% | 35.51% | 54.35% | 100%
S08 | 438 | 220 | 142 | 19 | 70 | 53 | 8.636% | 13.38% | 49.3% | 37.32% | 100%
S09 | 442 | 224 | 150 | 19 | 70 | 61 | 8.482% | 12.67% | 46.67% | 40.67% | 100%
S10 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S11 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S12 | 457 | 235 | 161 | 25 | 68 | 68 | 10.64% | 15.53% | 42.24% | 42.24% | 100%
S13 | 460 | 239 | 167 | 25 | 68 | 74 | 10.46% | 14.97% | 40.72% | 44.31% | 100%
S14 | 463 | 244 | 188 | 25 | 78 | 85 | 10.25% | 13.3% | 41.49% | 45.21% | 100%
S15 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S16 | 471 | 249 | 198 | 43 | 58 | 97 | 17.27% | 21.72% | 29.29% | 48.99% | 100%
S17 | 476 | 251 | 196 | 47 | 61 | 88 | 18.73% | 23.98% | 31.12% | 44.9% | 100%
S18 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S19 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S20 | 481 | 256 | 204 | 65 | 69 | 70 | 25.39% | 31.86% | 33.82% | 34.31% | 100%
S21 | 485 | 259 | 207 | 66 | 64 | 77 | 25.48% | 31.88% | 30.92% | 37.2% | 100%
S22 | 498 | 257 | 202 | 70 | 69 | 63 | 27.24% | 34.65% | 34.16% | 31.19% | 100%
S27 | 583 | 264 | 209 | 67 | 69 | 73 | 25.38% | 32.06% | 33.01% | 34.93% | 100%
S28 | 589 | 266 | 210 | 81 | 69 | 60 | 30.45% | 38.57% | 32.86% | 28.57% | 100%
S31 | 592 | 267 | 211 | 83 | 64 | 64 | 31.09% | 39.34% | 30.33% | 30.33% | 100%
S32 | 598 | 268 | 212 | 83 | 69 | 60 | 30.97% | 39.15% | 32.55% | 28.3% | 100%
S33 | 624 | 269 | 211 | 93 | 77 | 41 | General Progress Docs. DUE APPROVED | General Progress Docs. APPROVED | General Progress Docs COMMENTED | General Progress Docs DUE - Client | 0%
S34 | 624 | 269 | 211 | 87 | 73 | 51 | 32.34% | 41.23% | 34.6% | 24.17% | 100%
S35 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S36 | 626 | 269 | 219 | 88 | 74 | 57 | 32.71% | 40.18% | 33.79% | 26.03% | 100%
S37 | 634 | 275 | 221 | 101 | 49 | 71 | 36.73% | 45.7% | 22.17% | 32.13% | 100%
S38 | 637 | 275 | 229 | 105 | 53 | 71 | 38.18% | 45.85% | 23.14% | 31% | 100%
S39 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S40 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S41 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S42 | 652 | 274 | 233 | 128 | 59 | 46 | 46.72% | 54.94% | 25.32% | 19.74% | 100%
S43 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S44 | 652 | 274 | 234 | 133 | 60 | 41 | 48.54% | 56.84% | 25.64% | 17.52% | 100%
S45 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S46 | 652 | 273 | 238 | 136 | 65 | 37 | 49.82% | 57.14% | 27.31% | 15.55% | 100%
S47 |  | 274 |  |  |  | 0 | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S48 | 660 | 275 | 241 | 139 | 68 | 34 | 50.55% | 57.68% | 28.22% | 14.11% | 100%
S01 | 669 | 290 | 259 | 151 | 51 | 57 | 52.07% | 58.3% | 19.69% | 22.01% | 100%
S02 | 674 | 295 | 266 | 155 | 50 | 61 | 52.54% | 58.27% | 18.8% | 22.93% | 100%
S03 | 679 | 295 | 265 | 165 | 56 | 44 | 55.93% | 62.26% | 21.13% | 16.6% | 100%
S04 | 699 | 300 | 264 | 171 | 36 | 57 | 57% | 64.77% | 13.64% | 21.59% | 100%
S05 | 701 | 304 | 275 | 188 | 33 | 54 | 61.84% | 68.36% | 12% | 19.64% | 100%
S06 | 701 | 306 | 279 | 195 | 17 | 67 | 63.73% | 69.89% | 6.093% | 24.01% | 100%
S07 | 702 | 306 | 280 | 196 | 17 | 67 | 64.05% | 70% | 6.071% | 23.93% | 100%
S08 | 711 | 313 | 286 | 199 | 22 | 65 | 63.58% | 69.58% | 7.692% | 22.73% | 100%
S09 | 715 | 318 | 295 | 201 | 16 | 78 | 63.21% | 68.14% | 5.424% | 26.44% | 100%
S12 | 717 | 319 | 296 | 231 | 31 | 34 | 72.41% | 78.04% | 10.47% | 11.49% | 100%
S13 | 717 | 319 | 296 | 237 | 31 | 28 | 74.29% | 80.07% | 10.47% | 9.459% | 100%
S14 | 722 | 325 | 299 | 240 | 27 | 32 | 73.85% | 80.27% | 9.03% | 10.7% | 100%
S19 | 722 | 324 | 300 | 242 | 16 | 42 | 74.69% | 80.67% | 5.333% | 14% | 100%
S20 | 724 | 324 | 300 | 241 | 13 | 46 | 74.38% | 80.33% | 4.333% | 15.33% | 100%
S24 | 735 | 329 | 300 | 244 | 9 | 47 | 74.16% | 81.33% | 3% | 15.67% | 100%
S01 | 742 | 326 | 305 | 274 | 3 | 28 | 84.05% | 89.84% | 0.9836% | 9.18% | 100%
S02 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S03 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S04 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S05 | [5 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## ValueList_Helper (hidden)
TPS | 3DCOLL
CALLIDUS | CONS
HPM | DCC
HPR | ELE
HPS | GEN
INTERNAL | HSE
CLIENT | INS
INSP
MEC
PCS
PIP
PL
PRJ
PVS
QC
STR
SUP
WSH