## Sheet1
Project OTD Performance
Deliveries of 2011
Month | Project Name | Project Number | Project Manager | Planned Drawing Approval | Actual Drawing Approval | Planned Delivery Date | Actual Delivery Date | On time Drawing Approval | On Time Delivery | Cumulative Month | Delay | Cumulative Year
April |  |  |  | 2011-09-02 | 2011-09-25 | 2011-09-02 | 2011-09-01 | 0% | 100% |  | 1
January | [5 empty] | 2011-09-09 | 2011-09-10 |  | 0%
January | [5 empty] | 2011-01-09 | 2011-01-09 |  | 100%
January | [5 empty] | 2011-03-10 | 2011-03-10 |  | 100%
July | [5 empty] | 2011-04-09 | 2011-04-07 |  | 100% |  | 2
June | [5 empty] | 2011-01-11 | 2011-01-11 |  | 100%
March | [5 empty] | 2011-05-02 | 2011-02-02 |  | 100% |  | 89
May | [5 empty] | 2011-06-25 | 2011-05-09 |  | 100% |  | 47
September | [5 empty] | 2011-07-02 | 2011-06-02 |  | 100% |  | 30
September | [5 empty] | 2011-01-14 | 2011-01-15 |  | 0%
0.33333
Month | Cumulative Month | Cumulative Year
January | 33.33%
February | 0%
March | 0%
April | 0%
May | 0%
June | 0%
July | 0%
August | 0%
September | 50%
October | 0%
November | 0%
December | 0%
Total |  | 0%
Month | Cumulative Month | Cumulative Year
January | 1
February | 0
March | 0
April | 0
May | 0
June | 0
July | 0
August | 0
September | 1
October | 0
November | 0
December | 0
Total |  | 0%
J ai un fichier excel contenant des dates de livraison ( date prévut et date actuelle),
Avec ses date je doit creer deux graphiques, un premier qui affichera le retard accumulé ( en pourcentage) pour chaque mois et un second qui affichera le nombre de jour de retard pour chaque mois.
Mai je ne sais pas comment selectionner les donnée pour chauqe moi.