## Action list
|  | SEA Change - Incidents - Non conformances Register |  |  |  | Updated - | 2016-03-30
Date | No. | Type | Where | Non Conformance/Hazard identified/Action required | What reported | Action to take | By Whom | Review Period (days) | By when | Status | Additional measures taken/needed | Reasons for deadline not being met | New deadline | Status | Measures implemented sufficient (YES or NO) | Complete
2016-03-29 | 16/23 | Safety | U18 | Housekeeping | Bikes in corridor encroaching onto fire escape route | Provide an alternate place for storage (Bike shelter) | JOC |  | 2016-06-29 | 91 |  |  |  |  | NO | NO
2016-03-18 | L1_Demo_1603_01 | Observation | U16 Warehouse | Fire Risk | Pallets of cardboard stored in first aisle next to production, under light units | Relocate/ store in racking | JOC |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
2016-03-18 | L1_Demo_1603_02 | Observation | Demo Room | Inspections | No evidence to show that eye wash station is regularly flushed | Instigate use of log / record sheet and check the eye wash station weekly | AL |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
2016-03-18 | L1_Demo_1603_03 | Observation | Demo Room | Inspections | Demo room very untidy | Tidy up and remove/ unpack pallets | AL |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
2016-03-18 | L1_Demo_1603_04 | Observation | U16 Warehouse | Inspections | Unit 16 floor 'dirty' | Sweep | JOC |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
2016-03-10 | INT NCR 16 07 | Internal NCR | U16 -Pigments | Workplace design | Large pallet balance fouling on nearby stand causing incorrect weighing. Approx 60Kg (Setathane D1150 and Desmophen C1200) of MasterSeal CR460 Red batch 0014999898 was scrapped as a result. | Affix to ground/install preventative measure. | JOC |  | 2016-04-10 | 11 |  |  |  |  | YES | YES | Completed
2016-03-07 | SC 16/19 | Safety | Lab/ mezzanine | Access issue | Door closer on door to mezzanine is worn and periodically jams which may lead to spills if someone drops what they are carrying as a result. | Repair/ replace or refit door closer | DW |  | 2016-06-07 | 69 |  |  |  |  | NO | NO
2016-02-26 | L1_Office_20160226_02 | Observation | CSD Office | Workplace temperature | Air conditioning unit overshoots target temperature making it too hot in winter and too cold in summer | Service/ repair the unit | DW |  | 2016-05-31 | 62 |  |  |  |  | NO | NO
2016-02-26 | L1_Office_20160226_01 | Observation | Production Coordinator Office | No natural light | Broken window blind permanently down cuuting out all natural light | Repair/ replace | DW |  | 2016-04-30 | 31 |  |  |  |  | NO | NO
2016-02-25 | L1_U16_1602_01 | Observation | U16 - Pigments | Housekeeping | Drums of pigment waste (full) and 'in use' (half full) located within racking | Transfer full container to waste area, question if 'in use' drum is in best place for access. | JOC |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
2016-02-24 | L1_WRK_1624_01 | Observation | Workshop | Labelling | Cupboard containing hazardous material is unmarked | Does it need to be? | DW |  | 2016-03-24 | -6 |  |  |  |  | YES | YES | Completed
2016-02-24 | L1_WRK_1624_02 | Observation | Jet wash room | Labelling | IBC containg Vestan/ Santiciser mix is marked as non hazardous and displays stencil for original contents. | Check hazards for mixture, prepare a better suited label and blank out stencil | JOC |  | 2016-02-29 | -30 |  |  |  |  | YES | YES | Completed
2016-02-24 | L1_WRK_1624_03 | Observation | Jet wash room | Slip | floor greasy/ slippery | Clean | JOC |  | 2016-03-24 | -6 |  |  |  |  | YES | YES | Completed
2016-02-24 | L1_WRK-1624_04 | Observation | Workshop+ stores | Slip/ trip | Floor prone to getting wet from rain water and is peeling up | Repair damp coarse and roof. Install new floor | DW |  | 2016-10-31 | 215 |  |  |  |  | NO | NO
2016-02-24 | INT 16 06 | Internal NCR | Powders (PP1) | Incorrect procedure | Sample bags not brought up promptly | Operative training | JOC |  | 2016-03-31 | 1 |  |  |  |  | YES | YES | Completed
DW
SR
GB
TB
BP
DB
MC
LF
LO
AL
| R |  |  |  |  | JOC
ALL
RB

## Completed
Date | No. | Type | Where | Non Conformance/Hazard identified | What reported | Action to take | By Whom | By when | Status | Complete | Measures implemented sufficient (Y or N) | Additional measures taken/needed | Reasons for deadline not being met | New deadline | Measures impemented sufficient (Y or N) | Complete