## Projects list
QUALITY ROADMAP INFORMATION | [9 empty] | ROADMAP ITEMS PRIORITIZATION
[10 empty] | PRIORITY | [6 empty] | EASE OF IMPLEMENTATION
Roadmap item n° | ROADMAP item | Priority | Actions description | Responsible | Cost | Starting date | Due date | Completion% | Roadmap Item Status | Source | Source scoring | Severity | Severity scoring | Organizational impact | Organizational impact scoring | Total Priority | Resources: financial | Resources financial Scoring | Resources: human (on action duration) | Resources Human Scoring | Resources: expertise | Resources expertise scoring | Action duration | Action duration scoring | Total Ease of implementation
1 | Project 1 | P4 | Description |  |  | 2015-01-01 | 2016-12-31 | 25% | Delayed | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 12 | Budget supported by site direction | 2 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Strictly greater than 1 year | 1 | 8
2 | Project 2 | P2 | Description |  |  | 2014-01-01 | 2016-06-30 | 50% | On-Time | Inspection / Regulatory / IRT origin | 4 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with impacts beyond site | 4 | 48 | Budget supported by the group | 1 | Strictly greater than 100% of a person | 1 | expertise available externally | 1 | Strictly greater than 1 year | 1 | 1
3 | Project 3 | P4 | Description |  |  | 2016-07-01 | 2017-12-31 | 75% | On-Time | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with wider organization changes (site scale) | 3 | 18 | Budget supported by the group | 1 | Strictly greater than 100% of a person | 1 | expertise available externally | 1 | Strictly greater than 1 year | 1 | 1
4 | Project 4 | P4 | Description |  |  | 2015-07-01 | 2017-12-31 | 75% |  | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 12 | Budget supported by site direction | 2 | Strictly greater than 100% of a person | 1 | expertise available internally | 2 | Strictly greater than 1 year | 1 | 4
5 | Project 5 | P4 | Description |  |  | 2015-04-01 | 2017-03-31 |  |  | Site origin | 2 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with wider organization changes (site scale) | 3 | 18 | Budget supported by the group | 1 | Strictly greater than 100% of a person | 1 | expertise available externally | 1 | Strictly greater than 1 year | 1 | 1
6 | Project 6 | P2 | Description |  |  | 2015-01-01 | 2016-12-31 |  |  | Group / Audit / SQSR origin | 3 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with wider organization changes (site scale) | 3 | 27 | Budget supported by site direction | 2 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Strictly greater than 1 year | 1 | 8
7 | Project 7 | P3 | Description |  |  | 2015-03-01 | 2015-12-31 |  |  | Site origin | 2 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with wider organization changes (site scale) | 3 | 12 | Budget supported by site entity concerned by the action | 3 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Less or equal to 1 year | 2 | 24
8 | Project 8 | P3 | Description |  |  | 2015-02-01 | 2015-07-31 |  |  | Group / Audit / SQSR origin | 3 | Minor finding of audit or inspection – Low and located risk | 1 | Action with isolated changes (only one organization of the site) | 2 | 6 | Budget supported by site entity concerned by the action | 3 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Less or equal to 1 year | 2 | 24
9 | Project 9 | P1 | Description |  |  | 2015-01-01 | 2015-03-31 |  |  | Inspection / Regulatory / IRT origin | 4 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with wider organization changes (site scale) | 3 | 36 | Budget supported by site direction | 2 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Less or equal to 1 semester | 3 | 24
10 | Project 10 | P3 | Description |  |  | 2015-01-01 | 2015-01-31 |  |  | Site origin | 2 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 8 | No budget needed | 4 | Less or equal to 50% of a person | 3 | expertise available internally | 2 | Strictly greater than 1 year | 1 | 24
11 | Project 11 | P4 | Description |  |  | 2015-01-01 | 2015-07-31 |  |  | Group / Audit / SQSR origin | 3 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with isolated changes (only one organization of the site) | 2 | 18 | Budget supported by site entity concerned by the action | 3 | Strictly greater than 100% of a person | 1 | expertise available internally | 2 | Less or equal to 1 year | 2 | 12
12 | Project 12 | P3 | Description |  |  | 2014-11-15 | 2015-04-30 |  |  | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 12 | No budget needed | 4 | Less or equal to 50% of a person | 3 | expertise available internally | 2 | Less or equal to 1 year | 2 | 48
13 | Project 13 | P4 | Description |  |  | 2015-07-01 | 2016-12-31 |  |  | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 12 | Budget supported by site direction | 2 | Strictly greater than 100% of a person | 1 | expertise available internally | 2 | Less or equal to 1 year | 2 | 8
14 | Project 14 | P4 | Description |  |  | 2015-10-01 | 2015-12-30 |  |  | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | 12 | Budget supported by site direction | 2 | Strictly greater than 100% of a person | 1 | expertise available externally | 1 | Less or equal to 1 year | 2 | 4
15 | Project 15 | P4 | Description |  |  | 2015-04-01 | 2015-07-31 |  |  | Group / Audit / SQSR origin | 3 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with wider organization changes (site scale) | 3 | 18 | No budget needed | 4 | Strictly greater than 100% of a person | 1 | expertise available internally | 2 | Less or equal to 1 year | 2 | 16
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
[11 empty] | #N/A |  | #N/A |  | #N/A | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A | #N/A
Note on G5: Abujamra, Fernanda AH/BR: This project started as a structured project 1 year ago.

## Table of Prioritization
TABLE OF PRIORITIZATION
PRIORITY | [5 empty] | EASE OF IMPLEMENTATION
Source |  | Severity |  | Organizational impact |  | Resources: financial |  | Resources: human (on action duration) |  | Resources: expertise |  | Action duration
Optimization | 1 | Minor finding of audit or inspection – Low and located risk | 1 | No impact on organization | 1 | Budget supported by the group | 1 | Strictly greater than 100% of a person | 1 | expertise available externally | 1 | Strictly greater than 1 year | 1
Site origin | 2 | Risk with potential impact on the productivity of the site / entity concerned by the action | 2 | Action with isolated changes (only one organization of the site) | 2 | Budget supported by site direction | 2 | Less or equal to 100% of a person | 2 | expertise available internally | 2 | Less or equal to 1 year | 2
Group / Audit / SQSR origin | 3 | Major finding of audit or inspection – Risk on image, markets loss | 3 | Action with wider organization changes (site scale) | 3 | Budget supported by site entity concerned by the action | 3 | Less or equal to 50% of a person | 3 |  |  | Less or equal to 1 semester | 3
Inspection / Regulatory / IRT origin | 4 | Critical finding of audit or inspection – Risk on public health or regulation | 4 | Action with impacts beyond site | 4 | No budget needed | 4 |  |  |  |  | Less or equal to 1 month | 4
[12 empty] | Less or equal to 1 week | 0
Total Priority = Source*Severity*Organizationnal Impact | [5 empty] | Total Ease Of Implementation = Resources(Financial)*Resources(Human)*Resources(Expertise)*Action Duration
PRIORITY 1 | = | 24<Total Priority<64 | and | 19<Total Ease of implementation<96 | Items with a priority equal to 1,2 or 3 will always appear in the roadmap
PRIORITY 2 | = | 24<Total Priority<64 | and | 1<Total Ease of implementation<18
PRIORITY 3 | = | 1<Total Priority<23 | and | 19<Total Ease of implementation<96
PRIORITY 4 | = | 1<Total Priority<23 | and | 1<Total Ease of implementation<18 | As Items with a Priority 4 ar less significant, they can be hidden from the roadmap
Priority

## Eisenhower Matrix
Project priority matrix
PRIORITY | PRIORITY 2 |  |  | PRIORITY 1
| Project n° | Project Name | % Completion | Project n° | Project Name | % Completion
| PRIORITY 4 |  |  | PRIORITY 3
| Project n° | Project Name | % Completion | Project n° | Project Name | % Completion
EASE OF IMPLEMENTATION

## Data (hidden)
This sheet is used to implement formulas - Please do not modify any cells
USED FOR first Date Of Quality Roadmap | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Used to workout month (line 8) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35