## Report
NON CONFORMING MATERIAL REPORT |  |  |  |  | NCMR N°: | 1903
Assignee: | Finnian | Supplier ID N°: | 0 | Initiation Date: |  | 2014-05-20
Company: | FinCo |  |  | Initiator: | Tom Treacy
Adress: | Monaghan |  |  | Position: | QA Manager
e-mail: | 0 |  |  | e-mail: | 0
Phone: | 0 |  |  | Phone: | 00353(0)599721729
Part name: | Cylinder end | Part N°: | 3J-423693 | Decision | 0
|  | PB PO N°: | 0
Batch Quantity: | 217 | Quantity Wrong: | 2 | on Parts:
Invoice N°: | B071
Severity of Non Conformance: (Rated1-10 with 10 the highest and 1 the lowest) Severity Rating | [5 empty] | 5
Problem Identification: (Attach photo if relevant)
|  |  |  | 0 |  |  | IMAGE
Saw finish on base of cylinder end. When clevis is welded onto cylinder end problems could occur if base was not completely flat and parallel to weld prep of no more than 0.15. Saw finish is not permitted and surface finish is 3.5 Ra maximum.
Your reply to the actions below is required within 24 hours unless otherwise notified by initiator of complaint
Immediate Corrective Actions:
1 | 0
2 | 0
3 | 0
4 | 0
Person Responsible for Corrective Action: |  |  |  |  | Date: | 0
Root Cause of Problem: (List all know root causes)
1 | 0
2 | 0
3 | 0
4 | 0
Preventive Action(s): (List all preventive actions)
1 | 0
2 | 0
3 | 0
4 | 0
Person Responsible for Preventive Action(s): | 0 |  | Position: |  | Date Implemented:
|  |  | 0 |  | 0
To be completed by initiator of complaint
| PB Machine Tech QA Verify Actions: |  | 0 | Date: | 0
| PB Machine Tech QA Closure of Actions: |  | 0 | Date: | 0

## Organised record
[22 empty] | Immediate Corrective Action |  |  |  |  | Root cause Problem |  |  |  | Preventive Actions
NCMR | Iniation Date | Initiator | Position | e-mail | Phone | Assignee | Company | Address | e-mail | Phone | Supplier ID N | Part Name | Part N | PB PO N | Batch Quantity | Invoice N | Quantity Wrong | Decision on Parts | Severity Rating | Problem identification | Picture | 1 | 2 | 3 | 4 | Date | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Responsible for P.A | Position | Date implemented | QA V.A | Date | QA C.A | Date | Comment | Cost involving | How the claim was Resulted | Closed ?
1903 | 2014-05-20 | Tom Treacy | QA Manager |  | 00353(0)599721729 | Finnian | FinCo | Monaghan |  |  |  | Cylinder end | 3J-423693 |  | 217 | B071 | 2 |  | 5 | Saw finish on base of cylinder end. When clevis is welded onto cylinder end problems could occur if base was not completely flat and parallel to weld prep of no more than 0.15. Saw finish is not permitted and surface finish is 3.5 Ra maximum.
1931 | 2015-01-21 | [5 empty] | Terex Benford |  |  |  | Cell 1 | Screwed gland | 1g080045A-02 |  | 60 |  | 6 | Reject |  | will not screw into tube. Go gauge will not screw on to gland. | [14 empty] | Alan / Ray. | [9 empty] | No
1932 | 2015-02-02 | [5 empty] | TEREX |  |  |  | Kelly Precision | Cyl End valve Block | 824184-6 |  | 20 |  | 6 | Reject. |  | 7/16UNF thread oversize. | [14 empty] | liam Fennely | [9 empty] | Yes
1933 | 2015-02-04 | [5 empty] | Terex Benford |  |  |  | Cell 1 | CLEVIS | 3j-423701 |  |  |  | 64 | Reject |  | Dia 46.975 - 47 mm is 46.45. | [14 empty] | Ray / Alan | [9 empty] | No
1934 | 2015-02-09 | [5 empty] | Terex Italy |  |  |  | Kelly Precision | Cyl End valve Block | 824186-6 |  | 89 |  | 38 | KP to send someone to check. |  | Koneig plug will not fit in Ø6 H12 | [14 empty] | James / Liam. | [5 empty] | 2015-02-10 |  |  |  | Yes
1935 | 2015-02-11 | [5 empty] | Terex Benford |  |  |  | Distag | Cylinder end forging. | 3J-423764 |  | 696 |  | 347 | Reject back to supplier. |  | Forgings formed badly. | [14 empty] | Tommy Hickey | [7 empty] | Cost for reworking in PB to be sent to Distag. |  | No
1936 | 2015-02-11 | [5 empty] | Kaiser |  |  |  | Cell 1 | Cyl End | 1C055053B-01 |  |  |  | 2 | Scrap. |  | Dimension 23 mm is 25 mm | [14 empty] | Ray / Alan
1937 | 2015-02-11 | [5 empty] | Terex Benford |  |  |  | Cell 1 | Gland | 3J-423766 |  |  |  | 6 | Return to supplier. |  | Bore undersize. | [14 empty] | Ray / Alan
1938 | 2015-02-11 | [5 empty] | Farid |  |  |  | Cell 1 | Gland | KA070050A |  |  |  | 1 | Return to supplier |  | Bore undersize. | [14 empty] | Ray / Alan
1939 | 2015-02-11 | [5 empty] | Farid |  |  |  | Cell 1 | Profiled port | 1M101140A-02 |  |  |  | 2 | Scrap. |  | leaking after been welded. | [14 empty] | Ray / Alan
1940 | 2015-02-11 | [5 empty] | Terex Italy |  |  |  | Cell 1 | Profiled mounting bracket | 824188-6 |  |  |  |  | Return to supplier. |  | Profiled at an angle, slag not removed. | [14 empty] | Ray / Alan
1941 | 2015-02-11 | [5 empty] | Terex Benford |  |  |  | Distag | Cylinder end forging. | 3J-323651/A |  |  |  |  | Inform supplier. |  | Forging not uniform. After welding one side has to be ground. | [14 empty] | Tommy Hickey | [7 empty] | Cost for reworking in PB to be sent to Distag. |  | No
1942 | 2015-02-11 | [5 empty] | Snorkel |  |  |  | Cell 1 | Piston | 1P045080A-01 |  |  |  | 2 | Reject |  | Ø40.4 h9 IS Ø 44.8 | [14 empty] | Alan / Ray.
1943 | 2015-02-12 | [5 empty] | TURKEY |  |  |  | DOGANLAR | U-CLEVIS | 1J022036B-02 |  | 1500 |  |  | Reject |  | Milling is not parallell to center line. | [21 empty] | No reply from supplier. |  |  | No
1944 | 2015-02-19 | [5 empty] | Snorkel |  |  |  | Kelly Precision | Valve block | 15644 |  | 63 |  | 63 | Oilpipe modified to suit. |  | Ø11.5 is Ø12.02. | [14 empty] | liam Fennely | [5 empty] | 2015-02-26 |  |  | New oilpipes from KP | Yes
1945 | 2015-02-19 | [5 empty] | Snorkel |  |  |  | Kelly Precision | Valve Block | 15644 |  | 116 |  | 116 | Oilpipe modified to suit. |  | Ø 11.5 is Ø 12.02 | [14 empty] | liam Fennely | [5 empty] | 2015-02-26 |  |  | New oilpipes from KP | Yes
1946 | 2015-02-25 | [5 empty] | lehnhoff |  |  |  | Cell 1 | GLAND | 1G050025A-04 |  |  |  | 26 | Return for rework. |  | Bore undersize. | [14 empty] | Ray / Alan | [5 empty] | 2015-02-26 |  |  |  | Yes
1948 | 2015-03-04 | [5 empty] | Farid |  |  |  | Cell 1 | SPACER | 1E020030W-02 |  | 207 |  | % | REWORK IN CELL 1 |  | NOT ALL DE-BURRED. | [14 empty] | Alan / Ray. | [5 empty] | 2015-04-09 |  |  | Spacers de-burred. | Yes
1949 | 2015-02-20 | [5 empty] | KUHN |  |  |  | PONCIAL | Cyl End machined Forging. | H0406640 |  | 43 |  | 10 | Reject, supplier to collect. |  | 3/8" BSP thread, no/go screwing in. | [14 empty] | Giselle. | [6 empty] | 10 replacements required. |  |  | No
1950 | 2015-04-02 | [5 empty] | KUHN |  |  |  | Finco | Boss | 1D040080A-01 |  | 20 |  | 16 | reject. |  | Bore Ø 44 H7 undersize | [14 empty] | Finnian. | [5 empty] | 2015-04-07 |  |  | New bosses delivered. | Yes
1951 | 2015-04-03 | [5 empty] | Farid |  |  |  | Cell 1 | Gland. | kA125090 |  | 50 |  | 50 | Rework. |  | Thread oversize. | [14 empty] | Ray / Alan | [5 empty] | 2015-04-08 |  |  | Parts reworked in cell 1. | YES
1952 | 2015-04-10 | [5 empty] | Various |  |  |  | Wiederholt | TUBE. | 3A063075b-03 |  |  |  | 25 | REJECT. |  | SEAM IN TUBE. | [24 empty] | NO
1953 | 2015-04-16 | [5 empty] | Snorkel. |  |  |  | ST-Koneistus | Cyl End. | 1C090115G-01 |  | 10 |  | 10 | reject. |  | Ø 8 H12 is Ø 12. | [14 empty] | Teemu | [9 empty] | No
1954 | 2015-04-22 | [5 empty] | Various |  |  |  | Uraine. | Ø 70 CK45 |  |  |  |  | 7 meters | Reject |  | Defect in base material. | [14 empty] | GENC Gülsen. | [9 empty] | No
1955 | 2015-04-22 | [5 empty] | Terex |  |  |  | Kelly Precision | CYL END VALVE BLOCK | 1C045051C-01 |  | 76 |  | 76 | Return to supplier for re-work. |  | No radius on corners. | [14 empty] | James / Liam. | [9 empty] | No
1956 | 2015-04-22 | [5 empty] | Terex |  |  |  | Kelly Precision | Cyl end valve block | 1C45051C-01 |  |  |  | 1 | Return to supplier for re-work. |  | Koneig plug will not fit in Ø6 H12 | [14 empty] | James / Liam. | [9 empty] | No
1957 | 2015-04-22 | [5 empty] | Terex |  |  |  | Kelly Precision | Cyl end valve block | 824186-6 |  |  |  | 2 | Return to supplier for re-work. |  | Koneig plug will not fit in Ø6 H12 | [14 empty] | James / Liam. | [9 empty] | No
1958 | 2015-04-24 | [5 empty] | Snorkel |  |  |  | Cell 1 | Port block. | 116373-000-5 |  |  |  | 39 | return to Cell 1 for rework. |  | 58 mm milled slot is 54 mm. | [14 empty] | Ray / Alan | [9 empty] | No
1959 | 2015-05-18 | [5 empty] | Miedema |  |  |  | Cell 1 | Gland | 1G080075A-01 |  |  |  | 1 | reject |  | No spanner slot. | [14 empty] | Ray / Alan | [9 empty] | NO
1960 | 2015-05-19 | [5 empty] | lehnhoff |  |  |  | Cell 1 | Piston | 102579/3 |  |  |  | 5 | Reject. |  | Bore not concentric. | [14 empty] | Ray / Alan | [9 empty] | NO
1961 | 2015-05-20 | [5 empty] | KUHN |  |  |  | Rosco Eng. | Piston | 1P040041B-01 |  | 82 |  | 82 | Reject |  | thread oversize. | [14 empty] | Stephen. | [9 empty] | No
1962 | 2015-06-15 | [5 empty] | Snorkel |  |  |  | Finco | CYL END | 1C030045A-01 |  | 25 |  | 25 | REJECT |  | Ø40 IS Ø38. | [14 empty] | Finnian. | [9 empty] | NO
1963 | 2015-06-15 | [5 empty] | KUHN |  |  |  | DNC | BRACKET | 1J025065M-01 |  | 30 |  | 30 | REJECT |  | M10 X 1.5 IS M12 X 1.5. BAD FINISH | [14 empty] | LEO | [9 empty] | NO
1964 | 2015-06-11 | [5 empty] | Snorkel |  |  |  | Nimet | 38 mm 20mnv6 |  |  |  |  | 275 meters | Reject |  | Base material defective. | [14 empty] | Samy Numan.
1965 | 2015-06-16 | [5 empty] | Snorkel |  |  |  | Kelly Precision | Cylinder end | 1c050080c-01 |  |  |  | 1 | Reject |  | 9/16 port not machined. Link hole inot full bore not machined, not stamped. | [14 empty] | liam Fennely
1966 | 2015-06-16 | [5 empty] | Snorkel |  |  |  | Cell 1 | Piston. | 1P045080A-01 |  |  |  | 4 | REJECT |  | Run out in bore. | [14 empty] | Ray / Alan
1967 | 2015-06-16 | [5 empty] | SNORKEL |  |  |  | Cell 1 | GLAND | 1G045038A-01 |  |  |  | 4 | REJECT |  | Run out in bore, BORE UNDERSIZE. | [14 empty] | Ray / Alan
1968 | 2015-06-16 | [5 empty] | BENFORD |  |  |  | CELL 1 | GLAND | 1G115055A-01 |  |  |  | 1 | REJECT |  | Bore undersize. | [14 empty] | Ray / Alan
1969 | 2015-06-16 | [5 empty] | STILL |  |  |  | Cell 1 | GLAND | G03022A2 |  |  |  | 2 | REJECT |  | Bore undersize. | [14 empty] | Ray / Alan
1970 | 2015-06-16 | [5 empty] | SNORKEL |  |  |  | Cell 1 | PISTON | 1P030040B-01 |  |  |  | 1 | REJECT |  | FINISH ON END IS BAD. | [14 empty] | Ray / Alan
1971 | 2015-06-22 | [5 empty] | TEREX MPS |  |  |  | Nimet | Ø65 MACHINED ROD. | T133002-2 |  |  |  | 35 | Reject. |  | M45 x 3No Go gauge screwing in. | [14 empty] | Gabriela / Samy
1972 | 2015-06-22 | [9 empty] | Nimet | Ø 50 |  |  |  |  | 5 | reject |  | Grinding marks. | [14 empty] | Gabriela / Samy
1973 | 2015-06-26 | [5 empty] | Footpump |  |  |  | Kelly Precision | Valve block | Gruse28 |  |  |  | 228 | Reject |  | Plunger cavity is tapered. | [14 empty] | liam Fennely
1974 | 2015-07-07 | [5 empty] | Terex UK |  |  |  | ST-Koneistus | GLAND | 1G080045A-02 |  |  |  | 2 | REJECT |  | BORE UNDER SIZE | [14 empty] | Teemu
1975 | 2015-07-15 | [5 empty] | SNORKEL |  |  |  | Kelly Precision | Cyl End valve Block | 1C050080C-01 |  |  |  | 2 | REJECT |  | 1 PORT NOT TAPPED, Ø0.344" NOT DRILLED X 2 | [14 empty] | James / Liam.
1976 | 2015-07-23 | [5 empty] | HAND ENG |  |  |  | Finco | BOSS | 1D020040A-02 |  |  |  | 66 | REJECT 46 , REWORK 20 |  | BORE UNDER SIZE. | [14 empty] | Finnian.