## Orders
Important Information to Order |  |  | Date | 2016-11-21 |  | BBBB |  |  |  |  | S. | Surface
[11 empty] | P. | Position
[11 empty] | Dr. | Drawing |  |  | KiKi Plan
Project reference |  | BBBB - QWERTY | [8 empty] | Pre order | Date Pre Order
Address |  | Address - City | [8 empty] | N° Dorma | Number reference
Type of wall |  | Variflex - 38 dB 100 U | [8 empty] | WB | Week Booked
Finish description |  | HPL | [8 empty] | FD. | Final Dimensions
Number position |  | 6 | [8 empty] | B.Track | Beginning installation track |  |  | Marque déposé
Track installation |  | Begin Week / Not Started / Finished | [8 empty] | E.Track | End installation track
Type of track |  | R-Track with rack 9010 | [8 empty] | Order | Date Order
Delivery date |  | 2 | [8 empty] | OC. | State Order Confirmation
Drawing |  | Attached | [8 empty] | DD. | Delivery Date
Dorma offer |  | Attached | [8 empty] | I. | Installation elements
Order form |  | Attached | [8 empty] | F. | Finished
PRE ORDER
N° SBI | Client | Project | Type | Model | S. | P. | Dr. | Pre Order | N°Dorma | WB. | FD. | B.Track | E.Track | Order | Comments
5678 | BBBB | QWERTY | Variflex | 38 dB 100 U | HPL | 6 | Oui | 2016-01-02 | 91234567 | 2 |  | 3
ORDER
N° SBI | Client | Project | Type | Model | S. | P. | Dr. | Pre Order | N°Dorma | WB. | FD. | B.Track | E.Track | Order | OC. | DD. | I. | F. | Comments
1234 | CCCC | ASDFG
5678 | DDDD | ZXCVB
2345 | EEEE | QAZWS
Supprimer Projet
Projet Terminé
Nouveau Projet
PreOrder_Order

## Terminé
ORDER
N° SBI | Client | Project | Type | Model | S. | P. | Dr. | Pre Order | N°Dorma | WB. | FD. | B.Track | E.Track | Order | OC. | DD. | I. | F. | Comments
1234 | AAAA | AZERTY | Moveo | 42 dB Smart Line K/U | CPL | 4 | Oui | 2016-01-01 | 12345678 | 1 | 2011-02-01 | 2 | 3 | 2016-02-13 |  |  |  | oui

## Eléments
Moveo | 140 | 260 | 400 |  | Classic | Design | Functional |  | NC | HPL | CPL |  | Standard | CF30 | M1
Variflex | 120 | 260 | 450 | [6 empty] | HPL | CPL | [24 empty] | 0
[36 empty] | 1 | Position 1
Oui | En attente | [34 empty] | 2 | Position 2
Non | Vérifié | [34 empty] | 3 | Position 3
| Réfusé | [34 empty] | 4 | Position 4
[36 empty] | 5 | Position 5
[36 empty] | 6 | Position 6
1P = | 1 Point Suspension |  |  | R-Track |  | ST14-Track |  | K-Track | [5 empty] | R-Track |  | K-Track | [19 empty] | 7 | Position 7
Course TE |  | Variflex |  | 120 |  | 120 |  | 120 | [27 empty] | 8 | Position 8
|  | Moveo |  | 140 |  | 140 |  | 140 |  |  |  | Moveo |  | 140 |  | 140 | [19 empty] | 9 | Position 9
|  | Moduline |  | 120 | [31 empty] | 10 | Position 10
11
TE 1 POINT SUSPENSION | [11 empty] | TEF 1 POINT SUSPENSION | [9 empty] | AWA 1 POINT SUSPENSION | [5 empty] | KE 1 POINT SUSPENSION | [7 empty] | 12 | Sans
Type | Operation | LH* |  | R-Track 1P |  | S14-Track 1P |  | K-Track 1P |  | CD-Track 1P |  | LH* |  | R-Track 1P |  | S14-Track 1P |  | K-Track 1P |  | CD-Track 1P |  | LH* |  | R-Track 1P |  | K-Track 1P |  | LH* |  | R-Track 1P |  | K-Track 1P |  |  |  | 13 | TE 1 Point Suspension
|  | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max |  |  | 14 | TEF 1 Point Suspension | Sans
[36 empty] | 15 | TE 2 Point Suspension | TE 2 Point Suspension
Moveo | ComforTronic | 2000 | 3500 | 860 | 1480 | 860 | 1480 | 860 | 1480 | [12 empty] | 2000 | 3500 | 350 | 1390 | 350 | 1390 | 2000 | 3500 | 765 | 1415 | 765 | 1415 |  |  |  | TEF 2 Point Suspension | TEF 2 Point Suspension
[37 empty] | AWA | AWA
| Manual | 2000 | 5000 | 765 | 1400 | 765 | 1400 | 765 | 1400 |  |  | 2000 | 4100 | 850 | 1400 | 850 | 1400 | 850 | 1400
Variflex 100 | Semi-auto | 2000 | 5000 | 950 | 1400 | 950 | 1400 | 950 | 1400 |  |  | 2000 | 4100 | 1020 | 1400 | 1020 | 1400 | 1020 | 1400 | [17 empty] | 1P de suspension
| Manual B1 | 2000 | 5000 | 765 | 1380 | 765 | 1380 | 765 | 1380 |  |  | 2000 | 4100 | 850 | 1380 | 850 | 1380 | 850 | 1380 | [17 empty] | 2P de suspension
| Semi-auto B1 | 2000 | 5000 | 950 | 1380 | 950 | 1380 | 950 | 1380 |  |  | 2000 | 4100 | 1020 | 1380 | 1020 | 1380 | 1020 | 1380
| Manual | 2000 | 5000 | 765 | 1400 | 765 | 1400 | 765 | 1400 |  |  | 2000 | 4100 | 850 | 1400 | 850 | 1400 | 850 | 1400
Variflex 120 | Semi-auto | 2000 | 5000 | 950 | 1400 | 950 | 1400 | 950 | 1400 |  |  | 2000 | 4100 | 1020 | 1400 | 1020 | 1400 | 1020 | 1400
| Manual B1 | 2000 | 5000 | 765 | 1380 | 765 | 1380 | 765 | 1380 |  |  | 2000 | 4100 | 850 | 1380 | 850 | 1380 | 850 | 1380
| Semi-auto B1 | 2000 | 5000 | 950 | 1380 | 950 | 1380 | 950 | 1380 |  |  | 2000 | 4100 | 1020 | 1380 | 1020 | 1380 | 1020 | 1380
Variflex F30 | Manual | 2000 | 5000 | 765 | 1350 | 765 | 1350
| Semi-auto | 2000 | 5000 | 950 | 1350 | 950 | 1350
Variflex F60 | Manual | 2000 | 5000 | 765 | 1350 | 765 | 1350
Variflex F90 | Manual | 2000 | 5000 | 765 | 1350 | 765 | 1350
2P = | 2 Point Suspension |  |  | R-Track |  | ST14-Track |  | K-Track |  | CD-Track | [13 empty] | R-Track |  | K-Track |  | CD-Track
Course TE |  | Variflex |  | 120 |  | 450 |  | 260
|  | Moveo |  | 140 |  | 400 |  | 260 |  | 260 | [11 empty] | Moveo |  | 140 |  | 260 |  | 260
|  | Moduline |  | 120 | [5 empty] | 260
TE 2 POINT SUSPENSION | [11 empty] | TEF 2 POINT SUSPENSION | [9 empty] | AWA 2 POINT SUSPENSION | [7 empty] | KE 2 POINT SUSPENSION
Type | Operation | LH* |  | R-Track 2P |  | S14-Track 2P |  | K-Track 2P |  | CD-Track 2P |  | LH* |  | R-Track 2P |  | S14-Track 2P |  | K-Track 2P |  | CD-Track 2P |  | LH* |  | R-Track 2P |  | K-Track 2P |  | CD-Track 2P |  | LH* |  | R-Track 2P |  | K-Track 2P
|  | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
Moveo | ComforTronic | 2000 | 4500 | 860 | 1480 | 1520 | 1770 | 980 | 1600 | 980 | 1600 | [10 empty] | 2000 | 4500 | 350 | 1390 | 590 | 1510 | 590 | 1510
| ComforTronic | 4501 | 9000 | 940 | 1480 | 1520 | 1770 | 1060 | 1600 | 1060 | 1600 | [18 empty] | 2000 | 4500 | 765 | 1415 | 765 | 1415
| Manual | 2000 | 14500 | 765 | 1400 | 765 | 1400 | 1045 | 1540 |  |  | 2000 | 4100 | 850 | 1400
Variflex 100 | Semi-auto | 2000 | 9000 | 950 | 1400 | 950 | 1400 | 1230 | 1540 |  |  | 2000 | 4100
| Manual B1 | 2000 | 14500 | 765 | 1380 | 765 | 1380 | 1045 | 1520 |  |  | 2000 | 4100 | 850 | 1380
| Semi-auto B1 | 2000 | 9000 | 950 | 1380 | 950 | 1380 | 1230 | 1520 |  |  | 2000 | 4100 | 1020 | 1380
| Manual | 2000 | 14500 | 765 | 1400 | 1590 | 1730 | 1045 | 1540 |  |  | 2000 | 4100 | 850 | 1400
Variflex 120 | Semi-auto | 2000 | 9000 | 950 | 1400 | 1610 | 1730 | 1230 | 1540 |  |  | 2000 | 4100 | 1020 | 1400
| Manual B1 | 2000 | 14500 | 765 | 1380 | 1590 | 1730 | 1045 | 1520 |  |  | 2000 | 4100 | 850 | 1380
| Semi-auto B1 | 2000 | 9000 | 950 | 1380 | 1610 | 1730 | 1230 | 1520 |  |  | 2000 | 4100 | 1020 | 1380
Variflex F30 | Manual | 2000 | 7000 | 765 | 1350 | 1590 | 1680
| Semi-auto | 2000 | 7000 | 950 | 1350 | 1610 | 1680
Variflex F60 | Manual | 2000 | 9500 | 765 | 1350 | 1590 | 1680
Variflex F90 | Manual | 2000 | 6400 | 765 | 1350 | 1590 | 1680
ELEMENT DIMENSION
Type | Operation | LH* |  | VE |  | FE |  | EE |  | WE |  | SL |  | WA |  | SL OF EE |  | TA |  | FT |  | MONTANT |  | GE |  | GE-EX-Y/Z |  | GE-EX-E
|  | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
Moveo | ComforTronic | 2000 | 4500 | 600 | 1250 |  |  | 610 | 1250 | 800 | 1200 | 80 | 1250 | 60 | 1250 | 43 | 43 | [6 empty] | 600 | 12500 | 760 | 1410 | 770 | 1420
| ComforTronic | 4501 | 9000 | 800 | 1250 |  |  | 800 | 1250 |  |  | 80 | 1250 | 60 | 1250 | 43 | 43 | 600 | 1230 | 800 | 1250 | 90 | 1200
| Manual | 2000 | 14500 | 600 | 1250 | 600 | 1250 | 620 | 1250 | 600 | 1220 | 80 | 1250 | 60 | 1250 | 46 | 46 | 600 | 1220 | 600 | 1200 | 600 | 1200
Variflex 100 | Semi-auto | 2000 | 9000 | 750 | 1250 | 750 | 1250 | 770 | 1250 | 750 | 1220 | 80 | 1250 | 60 | 1250 | 46 | 46 | 750 | 1220 | 600 | 1200 | 600 | 1200
| Manual B1 | 2000 | 14500 | 600 | 1230 | 600 | 1230 | 620 | 1230 | 600 | 1200 | 80 | 1230 | 60 | 1230 | 46 | 46 | 600 | 1200 | 600 | 1200 | 600 | 1200
| Semi-auto B1 | 2000 | 9000 | 750 | 1230 | 750 | 1230 | 770 | 1230 | 750 | 1200 | 80 | 1230 | 60 | 1230 | 46 | 46 | 750 | 1200 | 600 | 1200 | 600 | 1200
| Manual | 2000 | 14500 | 600 | 1250 | 600 | 1250 | 620 | 1250 | 600 | 1220 | 80 | 1250 | 60 | 1250 | 46 | 46 | 600 | 1220 | 600 | 1200 | 600 | 1200
Variflex 120 | Semi-auto | 2000 | 9000 | 750 | 1250 | 750 | 1250 | 770 | 1250 | 750 | 1220 | 80 | 1250 | 60 | 1250 | 46 | 46 | 750 | 1220 | 600 | 1200 | 600 | 1200
| Manual B1 | 2000 | 14500 | 600 | 1230 | 600 | 1230 | 620 | 1230 | 600 | 1200 | 80 | 1230 | 60 | 1230 | 46 | 46 | 600 | 1200 | 600 | 1200 | 600 | 1200
| Semi-auto B1 | 2000 | 9000 | 750 | 1230 | 750 | 1230 | 770 | 1230 | 750 | 1200 | 80 | 1230 | 60 | 1230 | 46 | 46 | 750 | 1200 | 600 | 1200 | 600 | 1200
Variflex F30 | Manual | 2000 | 7000 | 600 | 1200 |  |  | 620 | 1200 | 600 | 1170 | 80 | 1200 | 60 | 1200 | 46 | 46 | 600 | 1170 | 600 | 1200 | 600 | 1200
| Semi-auto | 2000 | 7000 | 750 | 1200 |  |  | 770 | 1200 | 750 | 1170 | 80 | 1200 | 60 | 1200 | 46 | 46 | 750 | 1170 | 600 | 1200 | 600 | 1200
Variflex F60 | Manual | 2000 | 9500 | 600 | 1200 | [6 empty] | 80 | 1200 | 60 | 1200 | 46 | 46
Variflex F90 | Manual | 2000 | 6400 | 600 | 1200 | [6 empty] | 80 | 1200 | 60 | 1200 | 46 | 46
ELEMENT DIMENSION
Type | Operation | LH* |  | LDH |  |  |  | DT | DTZ |  |  | DT-EX-Y/Z |  |  | DT-EX-E |  |  | DT-EX-W
|  | Min | Max | Min | Max | 820 | 920 | 1000 | 820 | 920 | 1000 | 820 | 920 | 1000 | 820 | 920 | 1000 | 820 | 920 | 1000
Moveo | ComforTronic
| ComforTronic | 2440 | 9000 | 2100 |  | 1070 | 1170 | 1250 | 957 | 1057 | 1137 | 1230 | 1330 | 1410 | 1230 | 1340 | 1420
| Manual | 2402 | 14500 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
Variflex 100 | Semi-auto | 2631 | 9000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Manual B1 | 2402 | 14500 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Semi-auto B1 | 2631 | 9000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Manual | 2402 | 14500 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
Variflex 120 | Semi-auto | 2631 | 9000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Manual B1 | 2402 | 14500 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Semi-auto B1 | 2631 | 9000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
Variflex F30 | Manual | 2402 | 7000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
| Semi-auto | 2631 | 7000 | 2050 |  | 1110 | 1210 | 1290 | 976 | 1076 | 1156
Variflex F60 | Manual | 2402 | 9500 | 2050
Variflex F90 | Manual
MOVEO K/U Max. LH without joint : 4100 mm
VARIFLEX K/U Max. LH without joint : 4100 mm
VARIFLEX S Max. LH without joint : 3200 mm
VARIFLEX F30/B1 Max. LH without joint : 3650 mm
VARIFLEX F60/A2 Max. LH without joint : 2950 mm
1 Point Suspension Sealingstroke Top : 30 mm / Bottom : 30 mm
2 Point Suspension Sealingstroke Top / Bottom : 20 mm

## Poids
| POIDS DES ELEMENTS | [8 empty] | POIDS SUSPENSION
Moveo
| Cloison | Type | Cover Plate | Rw (dB) | Poids | Profile | Note | Variflex | TYPE DE RAIL |  | K-Track | R-Track | R-Track avec ailettes | ST-Track | MR-Track | CD-Track
[8 empty] | Moduline |  |  | 4 | 3.5 | 3.5 | 8.6 | 11.5 | 6.5
38 dB Smart Line K/U | Moveo | Smart Line K/U | 10 mm MDF | 38 | 16 |  | 38 dB TE / AWA / KE |  |  |  |  | K-Track | R-Track | ST-Track | MR-Track | CD-Track
42 dB Smart Line K/U | Moveo | Smart Line K/U | 10 mm MDF | 42 | 20 |  | 42 Db TE / 43 dB AWA |  |  | Poids (kg/m) |  | 4 | 3.5 | 8.6 | 11.5 | 6.5
49 dB Business K/U | Moveo | Business K/U | 10 mm MDF | 49 | 30 |  | 49 dB TE / 50 dB AWA
55 dB Design Line K/U | Moveo | Design Line K/U | 10 mm MDF | 55 | 40 |  |  |  |  | 1P de suspension |  | MAX. DISTANCES SUSPENSION
[10 empty] | Max. Poids (kg/elt) |  | K-Track | R-Track | ST-Track | MR-Track | CD-Track
44 dB Glass | Moveo | Glass | 6 + 6 mm Glass | 44 | 34 |  |  |  |  | 150 |  | 600
50 dB Glass | Moveo | Glass | 8 + 10 Glass | 50 | 49 |  |  |  |  | 165 |  |  | 600
[10 empty] | 180 |  |  | 550
51 dB Acoustic 1-Side interior | Moveo | Acoustic 1-Side interior | MDF Acoustic | 51 | 50 |  |  |  |  | 200 |  |  | 500
47 dB Acoustic 2-Side interior | Moveo | Acoustic 2-Side interior | MDF Acoustic | 47 | 67 |  |  |  |  | 220 |  |  | 450 **
[10 empty] | 250 |  |  | 400 **
| POIDS ADDITIONNEL | [8 empty] | 300 |  |  |  | 400 | 500 *
| LH ≥ 4500 mm avec les éléments de connexion |  |  | kg / élément | 15.5 |  |  |  |  | 150 |  |  |  |  | 500 *
| TE |  |  | kg / élément | 60
| DT |  |  | kg / élément | 60 |  |  |  |  | 2P de suspension |  | MAX. DISTANCES SUSPENSION
| DTZ |  |  | kg / élément | 60 |  |  |  |  | Max. Poids (kg/elt) |  | K-Track | R-Track | ST-Track | MR-Track | CD-Track
[10 empty] | 250 |  |  | 700 |  |  | 250
[10 empty] | 265 |  |  | 700 |  |  | 265 ***
38 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 38 | 36 | Solid |  |  |  | 285 |  |  | 700 |  |  | 285 ***
44 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 44 | 38 | Solid |  |  |  | 310 |  |  | 650 |  |  | 310 ***
49 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 49 | 45 | Solid |  |  |  | 330 |  |  | 600 |  |  | 330 ***
52 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 52 | 52 | Solid |  |  |  | 360 |  |  | 550 |  |  | 360 ***
55 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 55 | 52 | Top |  |  |  | 400 |  |  | 500 |  |  | 400 ***
57 dB 100 K | Variflex | 100 K | 16 mm Chipboard | 57 | 59 | Top |  |  |  | 440 |  |  | 450 ** |  |  | 440 ***
[10 empty] | 500 |  |  | 400 ** |  |  | 500 ***
38 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 38 | 38 | Solid |  |  |  | 900 |  |  |  |  | 500
45 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 45 | 38 | Solid
50 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 50 | 45 | Solid
52 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 52 | 52 | Solid |  |  |  | * Moveo: LH max.=3500 / Variflex: LH max.=5000
55 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 55 | 52 | Top |  |  |  | ** Rail anodisé et renforcé, zone de parking recouvert avec un angle métallique
57 dB 100 U | Variflex | 100 U | 16 mm Chipboard | 57 | 59 | Top |  |  |  | *** Avec steel insert
38 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 38 | 46 | Top |  |  |  | SUPPORT
44 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 44 | 46 | Top |  |  |  | Béton | Bois | Métallique | Spécial
48 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 48 | 46 | Top
52 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 52 | 46 | Top |  |  |  | BARRIERE PHONIQUE | [5 empty] | kg/m²
56 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 56 | 58 | Top |  |  |  | 38/45 dB - Acoustimass 80mm | [5 empty] | 6.4
58 dB 100 S | Variflex | 100 S | 1,0 mm Steel | 58 | 65 | Top |  |  |  | 49/50 dB - 2 BA 13 + 45 mm | [5 empty] | 25
[10 empty] | 52/57 dB - 4 BA 13 + 45 mm | [5 empty] | 46
52 dB EI 30 K | Variflex | EI 30 K | 16 mm A2 Particles | 52 | 48 | Top |  |  |  | 58/60 dB - 6 BA 13 + 45 mm | [5 empty] | 66
57 dB EI 30 K | Variflex | EI 30 K | 16 mm A2 Particles | 57 | 71 | Top
[10 empty] | SUSUSPENSION | [5 empty] | kg/ml
58 dB 120 K/ U | Variflex | 120 K/ U | 16 mm Chipboard | 58 | 54 | Top |  |  |  | Tige filetée
60 dB 120 K/ U | Variflex | 120 K/ U | 16 mm Chipboard | 60 | 61 | Top |  |  |  | Platine joue de poutre
Rail KMT
| POIDS ADDITIONNEL | [8 empty] | Consoles
| TE |  |  | kg / élément | 50 |  |  |  |  | Spéciale
| DT |  |  | kg / élément | 80
| DTZ |  |  | kg / élément | 80
41 dB 88 K | Moduline | ML88 | 10 mm MDF | 41 | 23 | ML
46 dB 88 K | Moduline | ML88 | 10 mm MDF | 46 | 24 | ML |  |  |  | MATERIEL | [5 empty] | kg/m²
53 dB 88 K | Moduline | ML88 | 10 mm MDF | 53 | 32 | ML |  |  |  | BA 13 mm | [5 empty] | 10.2
55 dB 88 K | Moduline | ML88 | 10 mm MDF | 55 | 41 | ML |  |  |  | MDF 16 mm | [5 empty] | 12.16
58 dB 88 K | Moduline | ML88 | 10 mm MDF | 58 | 49 | ML |  |  |  | Agglo 16 mm | [5 empty] | 10.4
[10 empty] | Laine minérale 45 mm | [5 empty] | 4.5
| POIDS ADDITIONNEL | [8 empty] | Acoustimass 80 mm | [5 empty] | 6.4
| TE |  |  | kg / élément | 50
| DT |  |  | kg / élément | 70
| DTZ |  |  | kg / élément | 70 |  |  |  |  | Platine de fixation 180 x 60 x 8 | 0.7 | U
[10 empty] | Platine à souder 170 x 30 x 8 | 0.51 | U
[10 empty] | Tige filetée M10 x 1000 | 0.46 | U
[10 empty] | Rail KMT | 4.12 | kg/ml
[10 empty] | CACHE RAIL | [5 empty] | kg/m²
[10 empty] | Sans | Hors lot SBI | Lot SBI | Dorma