## Allocation_overview
Allocation Overview |  | Current Number of MSN :
Team | FCM | MSN/FCM | Backup | Own/OP
1 | Sébastien ASSE | 1 | 0
1 | Diego ALONSO | 0 | 0
1 | Alain HAMON | 0 | 0
1 | Sandra BERGER | 0 | 0
1 | Rodrigo GONZALEZ | 0 | 0
1 | Julien CAREJE | 0 | 0
1 | Raoul JOGUET | 0 | 0
1 | John RUSSELL | 0 | 0
1 | NOT KNOWN | 0 | 0
1 | Alain AUBINEAU | 0 | 0
2 | Christelle COQUELLE | 0 | 0
2 | Bruno COUBES | 0 | 0
2 | Patrick CLANET | 0 | 0
2 | Nicolas CURTY | 1 | 0
2 | Rodrigo CAZORLA | 0 | 0
2 | Adam SHAW | 0 | 0
2 | Cecile AMADIEU | 0 | 0
2 | Georges RUIZ | 0 | 0
3 | Adam DEAN | 0 | 0
3 | NOT KNOWN | 0 | 0
3 | Chris BARBER | 0 | 0
3 | Francis BONNEVILLE | 0 | 0
3 | Sandra QUONIAM | 0 | 0
3 | Philippe ERNOT | 0 | 0
3 | Eugenio CORONADO | 0 | 0
3 | Luis VARGAS | 0 | 0
3 | Jeremy RACHER | 0 | 0
| Pascal ADVENIER | 0 | 0
Count MSN/FCM

## FCM_alloc
Initials | FCM | Team | Tel | Remark
SA | Sébastien ASSE | 1 | 06.85.32.18.60
EC | Eugenio CORONADO | 3 | /
EC | Eugenio CORONADO | 3 | /
EC | Eugenio CORONADO | 3 | /
EC | Eugenio CORONADO | 3 | /
EC | Eugenio CORONADO | 3 | /
PC | Patrick CLANET | 2 | 06.87.76.54.38
NC | Nicolas CURTY | 2 | 06.10.67.59.07
Refresh MSN
Colore FCM
SendPDF
Intern
Conversion dates tactical planning

## Team_info
Intitial | FCM | Team | Tel
/ | NOT ALLOCATED | / | /
SA | Sébastien ASSE | 1 | 06.85.32.18.60
DA | Diego ALONSO | 1 | 06.31.88.79.18
AH | Alain HAMON | 1 | 06.07.46.79.22
SB | Sandra BERGER | 1 | 06.14.80.41.86
RG | Rodrigo GONZALEZ | 1 | 06.24.55.11.58
JC | Julien CAREJE | 1 | 06.82.25.09.93
RJ | Raoul JOGUET | 1 | 06.19.65.71.13
JR | John RUSSELL | 1 | 06.89.16.02.32
NOT KNOWN
AA | Alain AUBINEAU | 1 | 06.07.34.60.91
CC | Christelle COQUELLE | 2 | 06.14.80.37.02
BC | Bruno COUBES | 2 | 06.73.99.37.29
PC | Patrick CLANET | 2 | 06.87.76.54.38
NC | Nicolas CURTY | 2 | 06.10.67.59.07
RC | Rodrigo CAZORLA | 2 | 06.38.70.30.69
AS | Adam SHAW | 2 | 06.86.68.60.14
CA | Cecile AMADIEU | 2 | 06.19.65.71.35
GR | Georges RUIZ | 2 | 06.79.93.25.40
AD | Adam DEAN | 3 | 06.22.94.80.71
NK | NOT KNOWN | 3 | 06.38.79.76.22
CB | Chris BARBER | 3 | 07.86.83.75.08
FB | Francis BONNEVILLE | 3 | 06.87.80.74.35
SQ | Sandra QUONIAM | 3 | 06.37.95.98.36
PE | Philippe ERNOT | 3 | 06.26.37.07.41
LV | Luis VARGAS | 3 | 06.72.05.80.02
EC | Eugenio CORONADO | 3 | /
JER | Jeremy RACHER | 3 | 06.14.80.39.19
PA | Pascal ADVENIER |  | 06.16.18.51.97
LD | Les DAVEY
FSB | Fabienne SALGUES-BRUNELLI

## tactical_planning
|  |  | 2016-07-28 04:53 | 2016-08-05 13:04 |  |  |  | 2016-07-25 12:00 | 2016-09-06 12:00 | 2016-09-07 07:00 | 2016-09-09 20:00 | 2016-09-09 20:00 | 2016-09-12 12:00
|  |  | 2016-10-12 12:00 | 2016-10-21 12:00 |  |  | 2016-09-30 12:00 | 2016-10-10 12:00 | 2016-10-27 12:00 | 2016-10-28 07:00 | 2016-11-03 20:00 | 2016-11-03 20:00 | 2016-11-04 12:00
[9 empty] | 2016-09-02 12:00 | 2016-09-05 10:56 | 2016-09-07 10:43 | 2016-09-07 10:39 | 2016-09-08 07:22
|  |  | 2016-12-12 12:00 | 2016-12-21 12:00 |  |  | 2016-12-05 12:00 | 2016-12-08 12:00 | 2016-12-26 12:00 | 2016-12-27 07:00 | 2016-12-29 20:00 | 2016-12-29 20:00 | 2016-12-30 12:00
|  |  | 2016-09-13 12:00 | 2016-09-19 12:00 |  |  | 2016-09-06 12:00 | 2016-09-09 12:00 | 2016-09-22 12:00 | 2016-09-23 07:00 | 2016-09-27 20:00 | 2016-09-27 20:00 | 2016-09-28 12:00
|  |  | 2016-09-02 12:00 | 2016-09-08 12:00 |  |  | 2016-08-26 12:00 | 2016-08-31 12:00 | 2016-09-13 12:00 | 2016-09-15 14:00 | 2016-09-19 09:18 | 2016-09-19 12:30 | 2016-09-20 12:48
|  |  | 2016-12-06 12:00 | 2016-12-14 12:00 |  |  | 2016-11-29 12:00 | 2016-12-02 12:00 | 2016-12-21 12:00 | 2016-12-22 07:00 | 2016-12-26 20:00 | 2016-12-23 20:00 | 2016-12-26 12:00
|  |  | 2016-08-24 09:27 | 2016-08-30 18:12 |  |  | 2016-08-17 12:00 | 2016-08-22 12:00 | 2016-09-02 12:00 | 2016-09-05 08:41 | 2016-09-07 21:41 | 2016-09-07 13:41 | 2016-09-08 13:41
|  |  | 2016-10-07 12:00 | 2016-10-12 12:00 |  |  | 2016-09-30 12:00 | 2016-10-05 12:00 | 2016-10-17 12:00 | 2016-10-18 07:00 | 2016-10-20 20:00 | 2016-10-20 20:00 | 2016-10-21 12:00
|  |  | 2016-07-05 12:00 | 2016-07-13 12:00 |  |  |  |  | 2016-07-22 08:24 | 2016-07-26 08:00 | 2016-07-28 20:00 | 2016-07-28 10:26 | 2016-07-29 03:43
|  |  | 2016-09-23 12:00 | 2016-09-28 12:00 |  |  | 2016-09-12 12:00 | 2016-09-16 12:00 | 2016-10-03 12:00 | 2016-10-04 07:00 | 2016-10-06 20:00 | 2016-10-06 20:00 | 2016-10-07 12:00
[7 empty] | 2016-08-31 12:00 |  | 2016-09-12 12:00 | 2016-09-14 09:27 | 2016-09-16 18:41 | 2016-09-16 09:43 | 2016-09-19 15:43
|  |  | 2016-10-14 12:00 | 2016-10-19 12:00 |  |  | 2016-10-07 12:00 | 2016-10-12 12:00 | 2016-10-24 12:00 | 2016-10-25 07:00 | 2016-10-27 20:00 | 2016-10-27 20:00 | 2016-10-28 12:00
|  |  | 2016-10-20 12:00 | 2016-10-31 12:00 |  |  | 2016-10-13 12:00 | 2016-10-18 12:00 | 2016-11-04 12:00 | 2016-11-07 07:00 | 2016-11-09 20:00 | 2016-11-09 20:00 | 2016-11-10 12:00
|  |  | 2016-11-23 12:00 | 2016-12-01 12:00 |  |  | 2016-11-16 12:00 | 2016-11-21 12:00 | 2016-12-07 12:00 | 2016-12-08 07:00 | 2016-12-12 20:00 | 2016-12-12 20:00 | 2016-12-13 12:00
|  |  | 2016-11-07 12:00 | 2016-11-10 12:00 |  |  | 2016-10-27 12:00 | 2016-11-03 12:00 | 2016-11-16 12:00 | 2016-11-17 07:00 | 2016-11-21 20:00 | 2016-11-21 20:00 | 2016-11-22 12:00
|  |  | 2016-10-07 12:00 | 2016-10-18 12:00 | 2016-08-31 07:00 | 2016-09-07 20:00 | 2016-09-30 12:00 | 2016-10-05 12:00 | 2016-10-21 12:00 | 2016-10-24 07:00 | 2016-10-26 20:00 | 2016-10-26 20:00 | 2016-10-27 12:00
|  |  | 2016-09-19 12:00 | 2016-09-28 12:00 |  |  | 2016-09-09 12:00 | 2016-09-15 12:00 | 2016-10-03 12:00 | 2016-10-05 07:00 | 2016-10-07 20:00 | 2016-10-07 20:00 | 2016-10-10 12:00
|  |  | 2016-09-27 12:00 | 2016-10-04 12:00 |  |  | 2016-09-20 12:00 | 2016-09-23 12:00 | 2016-10-10 12:00 | 2016-10-11 07:00 | 2016-10-13 20:00 | 2016-10-13 20:00 | 2016-10-14 12:00
|  |  | 2016-07-29 12:12 | 2016-08-09 13:55 |  |  | 2016-07-18 12:00 | 2016-07-27 12:00 | 2016-08-23 12:00 | 2016-08-24 07:00 | 2016-08-26 20:00 | 2016-08-26 20:00 | 2016-08-29 12:00
|  |  | 2016-09-27 12:00 | 2016-09-30 12:00 | 2016-07-23 07:00 | 2016-07-29 20:00 | 2016-09-20 12:00 | 2016-09-23 12:00 | 2016-10-05 12:00 | 2016-10-06 07:00 | 2016-10-10 20:00 | 2016-10-10 20:00 | 2016-10-11 12:00
|  |  | 2016-07-20 12:00 | 2016-08-02 12:00 |  |  |  |  | 2016-08-23 12:00 | 2016-09-02 13:54 | 2016-09-06 07:51 | 2016-09-06 07:54 | 2016-09-07 10:43
|  |  | 2016-07-14 05:09 | 2016-07-20 15:03 |  |  |  | 2016-07-12 12:00 | 2016-08-12 13:45 | 2016-08-16 14:51 | 2016-08-18 18:51 | 2016-08-18 13:00 | 2016-08-19 13:00
|  |  | 2016-09-05 12:00 | 2016-09-13 12:00 |  |  | 2016-08-23 12:00 | 2016-09-01 12:00 | 2016-09-21 12:00 | 2016-09-22 07:00 | 2016-09-26 20:00 | 2016-09-26 20:00 | 2016-09-27 12:00
[12 empty] | 2016-07-22 02:55 | 2016-07-22 11:01
|  |  | 2016-08-02 12:00 | 2016-08-09 12:00 |  |  | 2016-07-13 12:00 | 2016-07-22 12:00 | 2016-08-22 12:00 | 2016-08-23 07:00 | 2016-08-25 20:00 | 2016-08-25 20:00 | 2016-08-26 12:00
|  |  | 2016-10-20 12:00 | 2016-11-01 12:00 |  |  | 2016-10-13 12:00 | 2016-10-18 12:00 | 2016-11-07 12:00 | 2016-11-08 07:00 | 2016-11-10 20:00 | 2016-11-10 20:00 | 2016-11-11 12:00
|  |  | 2016-09-14 12:00 | 2016-09-23 12:00 | 2016-09-02 07:00 | 2016-09-12 20:00 | 2016-08-22 12:00 | 2016-08-31 12:00 | 2016-09-30 12:00 | 2016-10-03 11:50 | 2016-10-05 16:15 | 2016-10-05 13:51 | 2016-10-06 13:51
|  |  | 2016-09-15 12:00 | 2016-09-20 12:00 | 2016-07-30 07:00 | 2016-08-08 20:00 | 2016-09-02 12:00 | 2016-09-13 12:00 | 2016-09-28 12:00 | 2016-09-29 07:00 | 2016-10-03 20:00 | 2016-10-03 20:00 | 2016-10-04 12:00
|  | 2016-07-07 13:23 | 2016-09-14 12:00 | 2016-09-22 12:00 | 2016-08-13 07:00 | 2016-08-22 20:00 | 2016-09-07 12:00 | 2016-09-12 12:00 | 2016-09-27 12:00 | 2016-09-28 07:00 | 2016-09-30 20:00 | 2016-09-30 20:00 | 2016-10-03 12:00
2016-07-07 13:23 | 2016-07-11 21:03 | 2016-07-11 21:03 | 2016-11-28 12:00 | 2016-12-06 12:00 | 2016-08-18 07:00 | 2016-08-25 20:00 | 2016-11-21 12:00 | 2016-11-24 12:00 | 2016-12-09 12:00 | 2016-12-12 07:00 | 2016-12-14 20:00 | 2016-12-14 20:00 | 2016-12-15 12:00
2016-07-08 13:13 | 2016-07-12 21:53 | 2016-07-12 21:53 | 2016-09-16 11:00 | 2016-09-21 11:00 | 2016-08-20 07:00 | 2016-08-26 20:00 | 2016-09-08 12:00 | 2016-09-13 12:00 | 2016-09-26 12:00 | 2016-10-03 07:44 | 2016-10-05 20:44 | 2016-10-05 09:59 | 2016-10-06 07:51
2016-07-12 21:53 | 2016-07-19 08:11 | 2016-07-19 08:11 | 2016-10-17 12:00 | 2016-10-20 12:00 | 2016-08-25 07:00 | 2016-08-31 20:00 | 2016-10-10 12:00 | 2016-10-13 12:00 | 2016-10-28 12:00 | 2016-10-31 07:00 | 2016-11-03 20:00 | 2016-11-03 20:00 | 2016-11-04 12:00
2016-07-20 10:48 | 2016-07-22 16:01 | 2016-07-22 16:01 | 2016-11-04 12:00 | 2016-11-11 12:00 | 2016-08-31 07:00 | 2016-09-07 20:00 | 2016-10-26 12:00 | 2016-11-02 12:00 | 2016-11-17 12:00 | 2016-11-18 07:00 | 2016-11-22 20:00 | 2016-11-22 20:00 | 2016-11-23 12:00
[10 empty] | 2016-07-08 07:00 | 2016-07-12 20:00 | 2016-07-12 20:00 | 2016-07-13 12:00
|  |  | 2016-07-12 12:00 | 2016-07-18 12:00 |  |  |  |  | 2016-07-21 12:00 | 2016-07-22 07:00 | 2016-07-26 20:00 | 2016-07-26 20:00 | 2016-07-27 12:00
[10 empty] | 2016-07-20 09:43 | 2016-07-22 13:09 | 2016-07-22 13:09 | 2016-07-25 11:31
|  |  | 2016-07-18 04:17 | 2016-07-22 18:32 |  |  | 2016-07-12 12:00 | 2016-07-15 12:00 | 2016-07-29 12:00 | 2016-08-01 18:06 | 2016-08-03 17:43 | 2016-08-03 07:51 | 2016-08-04 12:01
|  |  | 2016-07-06 12:00 | 2016-07-11 12:00 |  |  |  |  | 2016-07-18 12:00 | 2016-07-21 07:00 | 2016-07-25 20:00 | 2016-07-25 20:00 | 2016-07-26 12:00
|  |  | 2016-07-11 12:00 | 2016-07-15 12:00 |  |  |  |  | 2016-07-21 12:00 | 2016-07-22 11:02 | 2016-07-26 14:58 | 2016-07-26 08:52 | 2016-07-27 13:58
[10 empty] | 2016-07-07 07:00 | 2016-07-11 20:00 |  | 2016-07-11 11:35
[9 empty] | 2016-07-12 12:00 | 2016-07-25 10:55 | 2016-07-27 14:05 | 2016-07-27 14:07 | 2016-07-28 10:54
|  |  | 2016-07-19 12:00 | 2016-07-26 12:00 |  |  | 2016-07-11 12:00 | 2016-07-18 12:00 | 2016-08-03 08:56 | 2016-08-05 12:04 | 2016-08-09 13:24 | 2016-08-09 10:46 | 2016-08-10 10:46
|  |  | 2016-07-07 14:11 | 2016-07-11 12:00 |  |  |  |  | 2016-07-19 12:00 | 2016-07-20 07:00 | 2016-07-22 20:00 | 2016-07-22 14:30 | 2016-07-22 14:30
|  |  | 2016-07-13 12:00 | 2016-07-19 12:00 |  |  |  | 2016-07-11 12:00 | 2016-07-22 12:00 | 2016-07-25 14:47 | 2016-07-27 11:44 | 2016-07-27 11:16 | 2016-07-28 10:33
2016-07-21 14:24 | 2016-08-17 13:00 | 2016-08-17 13:00 | 2016-09-29 12:00 | 2016-10-04 12:00 | 2016-09-09 07:00 | 2016-09-16 20:00 | 2016-09-22 12:00 | 2016-09-27 12:00 | 2016-10-07 12:00 | 2016-10-10 07:00 | 2016-10-12 20:00 | 2016-10-12 20:00 | 2016-10-13 12:00
|  |  | 2016-07-22 05:42 | 2016-07-28 15:55 |  |  | 2016-07-13 12:00 | 2016-07-20 12:00 | 2016-08-05 12:00 | 2016-08-25 10:29 | 2016-08-29 12:45 | 2016-08-29 11:27 | 2016-08-30 09:57
|  |  | 2016-07-20 04:46 | 2016-07-28 16:44 | 2016-07-05 07:00 | 2016-07-18 20:00 |  |  | 2016-08-05 12:00 | 2016-08-08 11:11 | 2016-08-11 00:11 | 2016-08-10 16:11 | 2016-08-11 16:11
|  |  | 2016-07-26 07:02 | 2016-08-01 17:58 |  |  | 2016-07-20 12:00 | 2016-07-22 12:00 | 2016-08-18 12:00 | 2016-08-25 09:39 | 2016-08-29 08:12 | 2016-08-29 14:46 | 2016-08-30 14:41
|  |  | 2016-08-23 12:00 | 2016-08-30 12:00 |  |  | 2016-07-22 12:00 | 2016-08-19 12:00 | 2016-09-02 11:02 | 2016-09-14 13:49 | 2016-09-16 17:08 | 2016-09-16 12:11 | 2016-09-19 11:52
|  |  | 2016-08-08 06:15 | 2016-08-12 16:17 |  |  | 2016-07-19 12:00 | 2016-08-04 12:00 | 2016-08-26 12:00 | 2016-08-30 10:30 | 2016-09-01 15:29 | 2016-09-01 14:13 | 2016-09-02 14:13
|  |  | 2016-08-30 12:00 | 2016-09-07 12:00 |  |  | 2016-08-23 12:00 | 2016-08-26 12:00 | 2016-09-12 12:00 | 2016-09-13 14:07 | 2016-09-15 15:10 | 2016-09-15 14:13 | 2016-09-16 11:09
|  |  | 2016-08-22 04:59 | 2016-08-26 13:50 | 2016-07-12 07:00 | 2016-07-21 20:00 |  | 2016-08-18 12:00 | 2016-08-31 12:00 | 2016-09-01 12:12 | 2016-09-05 18:14 | 2016-09-05 18:48 | 2016-09-06 18:48
2016-08-22 14:29 | 2016-08-24 22:38 | 2016-08-24 22:38 | 2016-11-17 12:00 | 2016-11-23 12:00 | 2016-09-09 07:00 | 2016-09-15 20:00 | 2016-11-09 12:00 | 2016-11-15 12:00 | 2016-11-28 12:00 | 2016-11-29 07:00 | 2016-12-01 20:00 | 2016-12-01 20:00 | 2016-12-02 12:00
|  |  | 2016-08-23 10:37 | 2016-08-29 19:12 | 2016-07-07 07:00 | 2016-07-16 20:00 | 2016-08-17 12:00 | 2016-08-19 12:00 | 2016-09-01 12:00 | 2016-09-05 08:29 | 2016-09-07 21:29 | 2016-09-07 13:29 | 2016-09-08 13:29
|  |  | 2016-08-01 12:00 | 2016-08-05 12:00 | 2016-08-08 07:00 | 2016-08-19 20:00 | 2016-07-25 12:00 | 2016-07-29 12:00 | 2016-08-26 12:00 | 2016-08-29 07:00 | 2016-08-31 20:00 | 2016-08-31 20:00 | 2016-09-01 12:00
2016-08-23 18:10 | 2016-08-26 09:18 | 2016-08-26 09:18 | 2016-09-30 12:00 | 2016-10-07 12:00 | 2016-09-10 07:00 | 2016-09-16 20:00 | 2016-09-23 12:00 | 2016-09-28 12:00 | 2016-10-12 12:00 | 2016-10-13 07:00 | 2016-10-17 20:00 | 2016-10-17 20:00 | 2016-10-18 12:00
|  |  | 2016-08-26 09:46 | 2016-09-05 12:18 | 2016-07-07 07:00 | 2016-07-18 20:00 | 2016-08-19 12:00 | 2016-08-24 12:00 | 2016-09-08 12:00 | 2016-09-09 08:57 | 2016-09-13 21:57 | 2016-09-13 13:57 | 2016-09-14 13:57
2016-08-24 22:38 | 2016-08-29 19:10 | 2016-08-29 19:10 | 2016-10-05 12:00 | 2016-10-11 12:00 | 2016-09-13 07:00 | 2016-09-20 20:00 | 2016-09-27 12:00 | 2016-09-30 12:00 | 2016-10-14 12:00 | 2016-10-17 07:00 | 2016-10-19 20:00 | 2016-10-19 20:00 | 2016-10-20 12:00
|  |  | 2016-08-31 06:27 | 2016-09-05 18:02 | 2016-08-13 07:00 | 2016-08-29 20:00 | 2016-07-21 12:00 | 2016-08-11 12:00 | 2016-09-09 12:00 | 2016-09-12 11:06 | 2016-09-15 00:06 | 2016-09-14 16:06 | 2016-09-15 16:06
2016-08-30 23:38 | 2016-09-02 13:58 | 2016-09-02 13:58 | 2016-10-07 12:00 | 2016-10-12 12:00 | 2016-09-17 07:00 | 2016-09-26 20:00 | 2016-09-30 12:00 | 2016-10-05 12:00 | 2016-10-17 12:00 | 2016-10-19 07:00 | 2016-10-21 20:00 | 2016-10-21 20:00 | 2016-10-24 12:00
|  |  | 2016-09-01 12:00 | 2016-09-06 12:00 | 2016-07-12 07:00 | 2016-07-22 20:00 | 2016-08-25 12:00 | 2016-08-30 12:00 | 2016-09-09 12:00 | 2016-09-13 09:33 | 2016-09-16 20:06 | 2016-09-16 13:23 | 2016-09-19 13:23
|  |  | 2016-08-31 12:00 | 2016-09-05 12:00 | 2016-07-16 20:00 | 2016-07-23 20:00 | 2016-08-24 12:00 | 2016-08-29 12:00 | 2016-09-08 12:00 | 2016-09-09 11:17 | 2016-09-13 19:54 | 2016-09-13 16:17 | 2016-09-14 10:58
|  |  | 2016-09-06 12:01 | 2016-09-09 12:01 | 2016-08-04 07:00 | 2016-08-12 20:00 | 2016-08-30 12:00 | 2016-09-02 12:00 | 2016-09-14 12:00 | 2016-09-15 07:00 | 2016-09-19 20:00 | 2016-09-19 20:00 | 2016-09-20 12:00
2016-09-05 22:15 | 2016-09-07 23:55 | 2016-09-07 23:55 | 2016-10-14 12:00 | 2016-10-19 12:00 | 2016-09-22 07:00 | 2016-09-28 20:00 | 2016-10-07 12:00 | 2016-10-12 12:00 | 2016-10-24 12:00 | 2016-10-25 07:00 | 2016-10-27 20:00 | 2016-10-27 20:00 | 2016-10-28 12:00
2016-09-07 23:55 | 2016-09-12 14:47 | 2016-09-12 14:47 | 2016-10-20 12:00 | 2016-10-25 12:00 | 2016-09-24 07:00 | 2016-09-30 20:00 | 2016-10-12 12:00 | 2016-10-17 12:00 | 2016-10-28 12:00 | 2016-10-31 07:00 | 2016-11-03 20:00 | 2016-11-03 20:00 | 2016-11-04 12:00
|  |  | 2016-09-06 12:00 | 2016-09-12 12:00 | 2016-07-26 07:00 | 2016-08-01 20:00 | 2016-08-26 12:00 | 2016-09-01 12:00 | 2016-09-15 12:00 | 2016-09-16 07:00 | 2016-09-20 20:00 | 2016-09-20 20:00 | 2016-09-21 12:00
2016-09-09 07:45 | 2016-09-13 15:37 | 2016-09-13 15:37 |  |  | 2016-09-27 07:00 | 2016-10-03 20:00 | 2016-10-12 12:00 | 2016-10-17 12:00 | 2016-10-19 12:00 | 2016-10-21 07:00 | 2016-10-25 20:00 | 2016-10-25 20:00 | 2016-10-26 12:00
2016-09-12 14:47 | 2016-09-14 16:27 | 2016-09-14 16:27 | 2016-10-24 12:00 | 2016-10-27 12:00 | 2016-09-29 07:00 | 2016-10-05 20:00 | 2016-10-17 12:00 | 2016-10-20 12:00 | 2016-11-03 12:00 | 2016-11-04 07:00 | 2016-11-08 20:00 | 2016-11-08 20:00 | 2016-11-09 12:00
2016-09-14 16:27 | 2016-09-19 07:07 | 2016-09-19 07:07 | 2016-11-30 12:00 | 2016-12-07 12:00 | 2016-10-01 07:00 | 2016-10-07 20:00 | 2016-11-23 12:00 | 2016-11-28 12:00 | 2016-12-13 12:00 | 2016-12-14 07:00 | 2016-12-16 20:00 | 2016-12-16 20:00 | 2016-12-19 12:00
2016-09-15 17:17 | 2016-09-20 07:57 | 2016-09-20 07:57 |  |  | 2016-10-04 07:00 | 2016-10-10 20:00 | 2016-11-09 12:00 | 2016-11-15 12:00 | 2016-11-17 12:00 | 2016-11-21 07:00 | 2016-11-23 20:00 | 2016-11-23 20:00 | 2016-11-24 12:00
|  | 2016-07-08 13:13 | 2016-09-08 12:00 | 2016-09-13 12:00 | 2016-08-01 07:00 | 2016-08-16 20:00 | 2016-09-01 12:00 | 2016-09-06 12:00 | 2016-09-16 12:00 | 2016-09-19 07:00 | 2016-09-21 20:00 | 2016-09-21 20:00 | 2016-09-22 12:00
2016-07-11 21:03 | 2016-07-13 22:43 | 2016-07-13 22:43 | 2016-09-13 12:00 | 2016-09-20 12:00 | 2016-08-23 07:00 | 2016-08-30 20:00 | 2016-09-06 12:00 | 2016-09-09 12:00 | 2016-09-23 12:00 | 2016-09-26 07:00 | 2016-09-28 20:00 | 2016-09-28 20:00 | 2016-09-29 12:00
2016-09-19 07:07 | 2016-09-21 08:47 | 2016-09-21 08:47 | 2016-11-22 12:00 | 2016-11-25 12:00 | 2016-10-05 07:00 | 2016-10-11 20:00 | 2016-11-15 12:00 | 2016-11-18 12:00 | 2016-11-30 12:00 | 2016-12-01 07:00 | 2016-12-05 20:00 | 2016-12-05 20:00 | 2016-12-06 12:00
2016-07-13 22:43 | 2016-07-20 10:48 | 2016-07-20 10:48 | 2016-09-19 09:12 | 2016-09-22 18:53 | 2016-08-26 07:00 | 2016-09-01 20:00 | 2016-09-09 12:00 | 2016-09-15 12:00 | 2016-09-27 12:00 | 2016-09-28 07:00 | 2016-09-30 20:00 | 2016-09-30 20:00 | 2016-10-03 12:00
2016-07-19 08:11 | 2016-07-21 14:24 | 2016-07-21 14:24 | 2016-09-21 12:00 | 2016-09-26 12:00 | 2016-08-27 07:00 | 2016-09-02 20:00 | 2016-09-13 12:00 | 2016-09-19 12:00 | 2016-09-29 12:00 | 2016-09-30 07:00 | 2016-10-04 20:00 | 2016-10-04 20:00 | 2016-10-05 12:00
2016-07-22 16:01 | 2016-08-18 19:10 | 2016-08-18 19:10 | 2016-09-23 13:20 | 2016-09-28 17:37 | 2016-09-02 07:00 | 2016-09-08 20:00 | 2016-09-15 12:00 | 2016-09-20 12:00 | 2016-10-03 12:00 | 2016-10-05 07:00 | 2016-10-07 20:00 | 2016-10-07 20:00 | 2016-10-10 12:00
2016-09-20 07:57 | 2016-09-22 09:37 | 2016-09-22 09:37 | 2016-10-27 12:00 | 2016-11-01 12:00 | 2016-10-06 07:00 | 2016-10-12 20:00 | 2016-10-20 12:00 | 2016-10-25 12:00 | 2016-11-07 12:00 | 2016-11-08 07:00 | 2016-11-10 20:00 | 2016-11-10 20:00 | 2016-11-11 12:00
2016-08-17 13:00 | 2016-08-22 14:29 | 2016-08-22 14:29 | 2016-09-26 10:52 | 2016-10-04 10:52 | 2016-09-03 07:00 | 2016-09-09 20:00 | 2016-09-15 12:00 | 2016-09-21 12:00 | 2016-10-07 12:00 | 2016-10-10 07:00 | 2016-10-12 20:00 | 2016-10-12 20:00 | 2016-10-13 12:00
2016-09-26 17:29 | 2016-09-28 19:09 | 2016-09-28 19:09 | 2016-11-03 12:00 | 2016-11-08 12:00 | 2016-10-13 07:00 | 2016-10-18 20:00 | 2016-10-25 12:00 | 2016-10-28 12:00 | 2016-11-14 12:00 | 2016-11-15 07:00 | 2016-11-17 20:00 | 2016-11-17 20:00 | 2016-11-18 12:00
2016-08-18 19:10 | 2016-08-23 18:10 | 2016-08-23 18:10 | 2016-09-28 11:18 | 2016-10-10 18:01 | 2016-09-07 07:00 | 2016-09-13 20:00 | 2016-09-19 12:00 | 2016-09-22 12:00 | 2016-10-13 12:00 | 2016-10-14 07:00 | 2016-10-18 20:00 | 2016-10-18 20:00 | 2016-10-19 12:00
2016-08-26 09:18 | 2016-08-30 23:38 | 2016-08-30 23:38 |  |  | 2016-09-14 07:00 | 2016-09-23 20:00 | 2016-10-05 12:00 | 2016-10-10 12:00 | 2016-10-12 12:00 | 2016-10-14 07:00 | 2016-10-18 20:00 | 2016-10-18 20:00 | 2016-10-19 12:00
2016-09-28 19:09 | 2016-10-03 09:49 | 2016-10-03 09:49 |  |  | 2016-10-16 07:00 | 2016-10-25 20:00 | 2016-11-04 12:00 | 2016-11-09 12:00 | 2016-11-14 12:00 | 2016-11-15 07:00 | 2016-11-17 20:00 | 2016-11-17 20:00 | 2016-11-18 12:00
2016-08-29 19:10 | 2016-09-01 10:18 | 2016-09-01 10:18 | 2016-10-11 12:00 | 2016-10-18 12:00 | 2016-09-27 07:00 | 2016-10-07 20:00 | 2016-09-20 12:00 | 2016-09-22 12:00 | 2016-10-24 12:00 | 2016-10-26 07:00 | 2016-10-28 20:00 | 2016-10-28 20:00 | 2016-10-31 12:00
2016-09-01 10:18 | 2016-09-05 22:15 | 2016-09-05 22:15 | 2016-10-13 12:00 | 2016-10-20 12:00 | 2016-09-30 07:00 | 2016-10-11 20:00 | 2016-09-26 12:00 | 2016-09-28 12:00 | 2016-10-26 12:00 | 2016-10-27 07:00 | 2016-11-02 20:00 | 2016-11-02 12:00 | 2016-11-02 13:00
2016-09-02 13:58 | 2016-09-06 23:05 | 2016-09-06 23:05 |  |  | 2016-09-21 07:00 | 2016-09-26 20:00 | 2016-10-05 12:00 | 2016-10-10 12:00 | 2016-10-12 12:00 | 2016-10-14 07:00 | 2016-10-18 20:00 | 2016-10-18 20:00 | 2016-10-19 12:00
2016-09-06 23:05 | 2016-09-09 07:45 | 2016-09-09 07:45 | 2016-10-17 12:00 | 2016-10-20 12:00 | 2016-09-24 07:00 | 2016-10-03 20:00 | 2016-10-10 12:00 | 2016-10-13 12:00 | 2016-10-25 12:00 | 2016-10-26 07:00 | 2016-10-28 20:00 | 2016-10-28 20:00 | 2016-10-31 12:00
2016-10-03 09:49 | 2016-10-05 11:29 | 2016-10-05 11:29 | 2016-11-15 12:00 | 2016-11-18 12:00 | 2016-10-19 07:00 | 2016-10-25 20:00 | 2016-11-07 12:00 | 2016-11-10 12:00 | 2016-11-23 12:00 | 2016-11-24 07:00 | 2016-11-28 20:00 | 2016-11-28 20:00 | 2016-11-29 12:00
2016-09-13 15:37 | 2016-09-15 17:17 | 2016-09-15 17:17 | 2016-10-25 12:00 | 2016-10-31 12:00 | 2016-09-30 07:00 | 2016-10-06 20:00 | 2016-10-17 12:00 | 2016-10-20 12:00 | 2016-11-07 12:00 | 2016-11-08 07:00 | 2016-11-10 20:00 | 2016-11-10 20:00 | 2016-11-11 12:00
2016-10-05 11:29 | 2016-10-07 13:09 | 2016-10-07 13:09 |  |  | 2016-10-21 07:00 | 2016-10-27 20:00 | 2016-11-10 12:00 | 2016-11-16 12:00 | 2016-11-18 12:00 | 2016-11-22 07:00 | 2016-11-24 20:00 | 2016-11-24 20:00 | 2016-11-25 12:00
2016-09-21 08:47 | 2016-09-23 10:27 | 2016-09-23 10:27 | 2016-10-28 12:00 | 2016-11-02 12:00 | 2016-10-07 07:00 | 2016-10-15 20:00 | 2016-10-21 12:00 | 2016-10-26 12:00 | 2016-11-09 12:00 | 2016-11-10 07:00 | 2016-11-15 20:00 | 2016-11-15 20:00 | 2016-11-16 12:00
2016-10-06 13:19 | 2016-10-10 20:59 | 2016-10-10 20:59 | 2016-11-16 12:00 | 2016-11-21 12:00 | 2016-10-22 07:00 | 2016-10-28 20:00 | 2016-11-08 12:00 | 2016-11-14 12:00 | 2016-11-24 12:00 | 2016-11-25 07:00 | 2016-11-29 20:00 | 2016-11-29 20:00 | 2016-11-30 12:00
2016-09-22 09:37 | 2016-09-26 17:29 | 2016-09-26 17:29 |  |  | 2016-10-11 07:00 | 2016-10-19 20:00 | 2016-10-27 12:00 | 2016-11-03 12:00 | 2016-11-07 12:00 | 2016-11-09 07:00 | 2016-11-14 20:00 | 2016-11-14 20:00 | 2016-11-15 12:00
2016-10-07 13:09 | 2016-10-11 21:49 | 2016-10-11 21:49 | 2016-11-21 12:00 | 2016-11-24 12:00 | 2016-10-26 07:00 | 2016-11-03 20:00 | 2016-11-14 12:00 | 2016-11-17 12:00 | 2016-11-29 12:00 | 2016-11-30 07:00 | 2016-12-02 20:00 | 2016-12-02 20:00 | 2016-12-05 12:00
2016-10-11 21:49 | 2016-10-13 23:29 | 2016-10-13 23:29 |  |  | 2016-10-28 07:00 | 2016-11-04 20:00 | 2016-11-17 12:00 | 2016-11-22 12:00 | 2016-11-24 12:00 | 2016-11-28 07:00 | 2016-11-30 20:00 | 2016-11-30 20:00 | 2016-12-01 12:00
2016-09-23 10:27 | 2016-09-27 18:19 | 2016-09-27 18:19 | 2016-11-01 12:00 | 2016-11-04 12:00 | 2016-10-12 07:00 | 2016-10-18 20:00 | 2016-10-24 12:00 | 2016-10-27 12:00 | 2016-11-09 12:00 | 2016-11-10 07:00 | 2016-11-15 20:00 | 2016-11-15 20:00 | 2016-11-16 12:00
2016-09-27 18:19 | 2016-09-29 20:47 | 2016-09-29 20:47 | 2016-11-09 12:00 | 2016-11-15 12:00 | 2016-10-25 07:00 | 2016-11-07 20:00 | 2016-10-19 12:00 | 2016-10-21 12:00 | 2016-11-21 12:00 | 2016-11-22 07:00 | 2016-11-24 20:00 | 2016-11-24 20:00 | 2016-11-25 12:00
2016-09-29 20:47 | 2016-10-04 10:39 | 2016-10-04 10:39 | 2016-11-09 12:00 | 2016-11-17 12:00 | 2016-10-19 07:00 | 2016-10-24 20:00 | 2016-11-02 12:00 | 2016-11-07 12:00 | 2016-11-23 12:00 | 2016-11-24 07:00 | 2016-11-28 20:00 | 2016-11-28 20:00 | 2016-11-29 12:00
2016-10-18 14:21 | 2016-10-20 16:01 | 2016-10-20 16:01 |  |  | 2016-11-09 07:00 | 2016-11-16 20:00 | 2016-11-24 12:00 | 2016-11-29 12:00 | 2016-12-01 12:00 | 2016-12-05 07:00 | 2016-12-07 20:00 | 2016-12-07 20:00 | 2016-12-08 12:00
2016-10-04 10:39 | 2016-10-06 13:19 | 2016-10-06 13:19 | 2016-11-11 12:00 | 2016-11-17 12:00 | 2016-10-27 07:00 | 2016-11-04 20:00 | 2016-10-26 12:00 | 2016-11-09 12:00 | 2016-11-22 12:00 | 2016-11-23 07:00 | 2016-11-25 20:00 | 2016-11-25 20:00 | 2016-11-28 12:00
2016-10-10 20:59 | 2016-10-12 22:39 | 2016-10-12 22:39 | 2016-11-23 12:00 | 2016-11-29 12:00 | 2016-11-09 07:00 | 2016-11-21 20:00 | 2016-11-03 12:00 | 2016-11-07 12:00 | 2016-12-05 12:00 | 2016-12-06 07:00 | 2016-12-08 20:00 | 2016-12-08 20:00 | 2016-12-09 12:00
2016-10-20 16:01 | 2016-10-25 08:20 | 2016-10-25 08:20 | 2016-12-02 12:00 | 2016-12-07 12:00 | 2016-11-15 07:00 | 2016-11-21 20:00 | 2016-11-25 12:00 | 2016-11-30 12:00 | 2016-12-12 12:00 | 2016-12-13 07:00 | 2016-12-15 20:00 | 2016-12-15 20:00 | 2016-12-16 12:00
2016-10-12 22:39 | 2016-10-17 13:31 | 2016-10-17 13:31 | 2016-11-23 12:00 | 2016-11-28 12:00 | 2016-10-29 07:00 | 2016-11-08 20:00 | 2016-11-16 12:00 | 2016-11-21 12:00 | 2016-12-01 12:00 | 2016-12-02 07:00 | 2016-12-06 20:00 | 2016-12-06 20:00 | 2016-12-07 12:00
2016-10-13 23:29 | 2016-10-18 14:21 | 2016-10-18 14:21 | 2016-11-29 10:20 | 2016-12-02 13:39 | 2016-11-04 07:00 | 2016-11-15 20:00 | 2016-11-22 12:00 | 2016-11-25 12:00 | 2016-12-07 12:00 | 2016-12-08 07:00 | 2016-12-12 20:00 | 2016-12-12 20:00 | 2016-12-13 12:00
2016-10-17 13:31 | 2016-10-19 15:11 | 2016-10-19 15:11 | 2016-11-29 12:00 | 2016-12-02 12:00 | 2016-11-08 07:00 | 2016-11-15 20:00 | 2016-11-22 12:00 | 2016-11-25 12:00 | 2016-12-07 12:00 | 2016-12-08 07:00 | 2016-12-12 20:00 | 2016-12-12 20:00 | 2016-12-13 12:00
2016-10-25 08:20 | 2016-10-27 14:33 | 2016-10-27 14:33 |  |  | 2016-11-17 07:00 | 2016-11-22 20:00 | 2016-11-30 12:00 | 2016-12-05 12:00 | 2016-12-07 12:00 | 2016-12-09 07:00 | 2016-12-13 20:00 | 2016-12-13 20:00 | 2016-12-14 12:00
2016-10-19 15:11 | 2016-10-21 15:51 | 2016-10-21 15:51 | 2016-12-02 06:44 | 2016-12-08 20:12 | 2016-11-10 07:00 | 2016-11-17 20:00 | 2016-11-25 12:00 | 2016-11-30 12:00 | 2016-12-13 12:00 | 2016-12-14 07:00 | 2016-12-16 20:00 | 2016-12-16 20:00 | 2016-12-19 12:00
2016-10-21 15:51 | 2016-10-26 10:57 | 2016-10-26 10:57 | 2016-12-05 12:00 | 2016-12-09 12:00 | 2016-11-16 07:00 | 2016-11-22 20:00 | 2016-11-28 12:00 | 2016-12-01 12:00 | 2016-12-14 12:00 | 2016-12-15 07:00 | 2016-12-19 20:00 | 2016-12-19 20:00 | 2016-12-20 12:00
2016-10-26 10:57 | 2016-10-28 16:10 | 2016-10-28 16:10 | 2016-12-08 09:31 | 2016-12-15 13:32 | 2016-11-18 07:00 | 2016-11-24 20:00 | 2016-12-01 12:00 | 2016-12-06 12:00 | 2016-12-20 12:00 | 2016-12-21 07:00 | 2016-12-23 20:00 | 2016-12-23 20:00 | 2016-12-26 12:00
2016-10-27 14:33 | 2016-11-03 14:39 | 2016-11-03 14:39 | 2016-12-09 12:00 | 2016-12-15 12:00 | 2016-11-19 07:00 | 2016-11-25 20:00 | 2016-12-01 12:00 | 2016-12-06 12:00 | 2016-12-20 12:00 | 2016-12-21 07:00 | 2016-12-23 20:00 | 2016-12-23 20:00 | 2016-12-26 12:00
2016-10-28 16:10 | 2016-11-07 10:23 | 2016-11-07 10:23 | 2016-12-13 12:00 | 2016-12-19 12:00 | 2016-11-22 07:00 | 2016-11-28 20:00 | 2016-12-02 12:00 | 2016-12-07 12:00 | 2016-12-22 12:00 | 2016-12-23 07:00 | 2016-12-27 20:00 | 2016-12-27 20:00 | 2016-12-28 12:00
2016-11-03 14:39 | 2016-11-08 14:00 | 2016-11-08 14:00 |  |  | 2016-11-23 07:00 | 2016-11-29 20:00 | 2016-12-07 12:00 | 2016-12-12 12:00 | 2016-12-14 12:00 | 2016-12-16 07:00 | 2016-12-20 20:00 | 2016-12-20 20:00 | 2016-12-21 12:00
2016-11-07 10:23 | 2016-11-09 16:36 | 2016-11-09 16:36 | 2016-12-14 12:00 | 2016-12-19 12:00 | 2016-11-24 07:00 | 2016-11-30 20:00 | 2016-12-06 12:00 | 2016-12-09 12:00 | 2016-12-22 12:00 | 2016-12-23 07:00 | 2016-12-27 20:00 | 2016-12-27 20:00 | 2016-12-28 12:00
2016-11-08 14:00 | 2016-11-10 19:13 | 2016-11-10 19:13 |  |  | 2016-11-25 07:00 | 2016-12-01 20:00 | 2016-12-09 12:00 | 2016-12-14 12:00 | 2016-12-16 12:00 | 2016-12-20 07:00 | 2016-12-22 20:00 | 2016-12-22 20:00 | 2016-12-23 12:00
2016-11-09 16:36 | 2016-11-14 21:15 | 2016-11-14 21:15 | 2016-12-19 09:56 | 2017-01-04 18:09 | 2016-11-26 07:00 | 2016-12-05 20:00 | 2016-12-12 12:00 | 2016-08-18 12:00: 2016-12-15 12:00
2016-11-10 19:13 | 2016-11-15 22:05 | 2016-11-15 22:05 |  |  | 2016-11-30 07:00 | 2016-12-06 20:00 | 2016-12-13 12:00 | 2016-12-16 12:00 | 2016-12-20 12:00 | 2016-12-22 07:00 | 2016-12-26 20:00 | 2016-12-26 20:00 | 2016-12-27 12:00
2016-11-14 21:15 | 2016-11-16 22:55 | 2016-11-16 22:55 | 2016-12-20 12:00 | 2017-01-06 12:00 | 2016-12-01 07:00 | 2016-12-07 20:00 | 2016-12-13 12:00 | 2016-08-18 12:00: 2016-12-16 12:00
2016-11-15 22:05 | 2016-11-17 23:45 | 2016-11-17 23:45 |  |  | 2016-12-02 07:00 | 2016-12-08 20:00 | 2016-12-14 12:00 | 2016-12-19 12:00 | 2016-12-21 12:00 | 2016-12-23 07:00 | 2016-12-27 20:00 | 2016-12-27 20:00 | 2016-12-28 12:00
2016-11-16 22:55 | 2016-11-21 13:47 | 2016-11-21 13:47 |  |  | 2016-12-14 07:00 | 2016-12-22 20:00 | 2016-12-08 12:00 | 2016-08-18 12:00: 2016-12-12 12:00
2016-11-17 23:45 | 2016-11-22 14:37 | 2016-11-22 14:37 |  |  | 2016-12-06 07:00 | 2016-12-14 20:00 | 2016-12-20 12:00 | 2016-08-18 12:00: 2016-12-23 12:00
2016-11-21 13:47 | 2016-11-23 15:27 | 2016-11-23 15:27 |  |  | 2016-12-08 07:00 | 2016-12-14 20:00 | 2016-12-21 12:00
2016-11-22 14:37 | 2016-11-24 16:17 | 2016-11-24 16:17 |  |  | 2016-12-09 07:00 | 2016-12-15 20:00 | 2016-12-22 12:00
2016-11-23 15:27 | 2016-11-25 16:07 | 2016-11-25 16:07 |  |  | 2016-12-10 07:00 | 2016-12-17 20:00 | 2016-12-23 12:00
2016-11-24 16:17 | 2016-11-28 23:57 | 2016-11-28 23:57 |  |  | 2016-12-15 07:00 | 2016-12-21 20:00
2016-11-25 16:07 | 2016-11-30 07:47 | 2016-11-30 07:47 |  |  |  |  | 2016-12-19 12:00 | 2016-08-18 12:00: 2016-12-21 12:00
2016-11-28 23:57 | 2016-12-01 08:37 | 2016-12-01 08:37 |  |  | 2016-12-15 07:00 | 2016-12-21 20:00
2016-11-30 07:47 | 2016-12-02 09:27 | 2016-12-02 09:27 |  |  | 2016-12-16 07:00 | 2016-12-22 20:00
2016-12-01 08:37 | 2016-12-05 16:29 | 2016-12-05 16:29
2016-12-02 09:27 | 2016-12-06 17:19 | 2016-12-06 17:19
2016-12-06 17:19 | 2016-12-08 18:59 | 2016-12-08 18:59
2016-12-12 08:49 | 2016-12-14 10:29 | 2016-12-14 10:29
2016-12-13 09:39 | 2016-12-15 11:19 | 2016-12-15 11:19
2016-12-05 16:29 | 2016-12-07 18:09 | 2016-12-07 18:09
2016-12-15 11:19 | 2016-12-19 21:22 | 2016-12-19 21:22
2016-12-16 12:09 | 2016-12-21 07:10 | 2016-12-21 07:10
2016-12-14 10:29 | 2016-12-16 12:09 | 2016-12-16 12:09
2016-12-21 07:10 | 2016-12-23 14:34 | 2016-12-23 14:34
2016-12-23 14:34 | 2017-01-05 15:31
2016-12-19 21:22 | 2016-12-22 09:59 | 2016-12-22 09:59
2016-12-07 18:09 | 2016-12-12 08:49 | 2016-12-12 08:49
2016-12-08 18:59 | 2016-12-13 09:39 | 2016-12-13 09:39
2016-12-22 09:59 | 2017-01-04 07:42