## Settings
Update the orange cells below ↓
| Team Name | Team Manager
Team 1 | Alpha | Adam
Team 2 | Bravo | Bill
Team 3 | Charlie | Charlene
Team 4 | Delta | Daryl
Team 5 | Echo | Elizabeth
Team 6 | Fox | Frank
All | Portfolio | ← Top level organization.
Current Year | 2017
Setup
Rename the "Team 1", "Team 2", "Team …" fields on the Summary Table sheets (Excel doesn't allow formulas in PivotTables).
Rename the Team sheets.
Hide this sheet when not in use.
Tips
When filling out the team sheets, never include resources who no longer work for the company. They will be included in your head count and your team will appear to have more bandwidth than they actually do.
Keep the Totals row on the team sheets visible. You can use the filters
Advanced: there's a hidden data sheet that is very hidden - research how to unhide sheets that are xlSheetVeryHidden.
Advanced: to modify the underlying data in the PivotTables, bring up the PivotTable Wizard by clcking anywhere in the pivot table and press Alt + D, P.
How to fill out the Team Sheets
Fill out the Team sheets with the resource allocation as shown below. Then reset the PivotTables by going to Data → Refresh All.

## Data
Portfolio | Description | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Total Unique Resources: | 14
Active | Alpha | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bravo | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Charlie | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Delta | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Echo | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fox | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Active Subtotal | 12.25 | 14 | 16.75 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | Up to Bat - Needs Resource | 1.5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 3 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 3 | 0 | 3 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pending Subtotal | 10.5 | 12 | 15 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 22.75 | 26 | 31.75 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alpha | Team 1 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Alpha Workload | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 5.25 | 6 | 6.75 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bravo | Team 2 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Bravo Workload | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Charlie | Team 3 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Charlie Workload | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | Team 4 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Delta Workload | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Echo | Team 5 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Echo Workload | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fox | Team 6 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar +
| Fox Workload | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Up to Bat - Needs Resource | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| On Deck - Going To Happen | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In The Dugout - May Happen | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bench | 0.5 | 0 | 0.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3.5 | 4 | 5 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
You shouldn't have to edit this sheet... but if you do, save a backup of the entire workbook first.
Password: goodplusfast
Lock it when you're finished.

## Team Summary
Somme de Valeur | Étiquettes de colonnes
Étiquettes de lignes | Sept | Oct | Nov | Dec | Mar | Apr | Aug | Feb | Feb + | Jan | Jan+ | Jul | Jun | Mar + | May | Year: 2017 | Refresh pivot table by going to Data >> Refresh All
Team1 | Étiquettes de colonnes Mar: 6.75; Étiquettes de colonnes Apr: 0.02; Étiquettes de colonnes Feb: 6 |  | 5.25 | [5 empty] | Legend: | Allocation < 100% | Allocation = 100% | Allocation > 100%
Active | Étiquettes de colonnes Mar: 4.25; Étiquettes de colonnes Apr: 0.01; Étiquettes de colonnes Feb: 4 |  | 3.5
Resource A (Overallocated) | Étiquettes de colonnes Mar: 1.25; Étiquettes de colonnes Apr: 0.01; Étiquettes de colonnes Feb: 1.25 |  | 1.25
Resource B (Underallocated) | Étiquettes de colonnes Mar: 0.75; Étiquettes de colonnes Feb: 0.75 |  | 0.75
Resource C (Optimally Allocated) | [9 empty] | 1 | bar: Étiquettes de colonnes Mar; Étiquettes de colonnes Feb
Resource D | Étiquettes de colonnes Mar: 1.25; Étiquettes de colonnes Feb: 1 |  | 0.5
Pending | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.01; Étiquettes de colonnes Feb: 2 |  | 1.75
Team2 | Étiquettes de colonnes Mar: 5; Étiquettes de colonnes Apr: 0.04; Étiquettes de colonnes Feb: 4 |  | 3.5
Team3 | Étiquettes de colonnes Mar: 5; Étiquettes de colonnes Apr: 0.06; Étiquettes de colonnes Feb: 4 |  | 3.5
Team4 | Étiquettes de colonnes Mar: 5; Étiquettes de colonnes Apr: 0.08; Étiquettes de colonnes Feb: 4 |  | 3.5
Team5 | Étiquettes de colonnes Mar: 5; Étiquettes de colonnes Apr: 0.1; Étiquettes de colonnes Feb: 4 |  | 3.5
Team6 | Étiquettes de colonnes Mar: 5; Étiquettes de colonnes Apr: 0.12; Étiquettes de colonnes Feb: 4 |  | 3.5
Total général | Étiquettes de colonnes Mar: 31.75; Étiquettes de colonnes Apr: 0.42; Étiquettes de colonnes Feb: 26 |  | 22.75

## Status Summary
Somme de Valeur | Étiquettes de colonnes
Étiquettes de lignes | Sept | Oct | Nov | Dec | Mar | Apr | Aug | Feb | Feb + | Jan | Jan+ | Jul | Jun | Mar + | May | Year: 2017 | Refresh pivot table by going to Data >> Refresh All
Active | Étiquettes de colonnes Mar: 16.75; Étiquettes de colonnes Apr: 0.21; Étiquettes de colonnes Feb: 14 |  | 12.25 | [5 empty] | Legend: | Allocation < 100% | Allocation = 100% | Allocation > 100%
Team1 | Étiquettes de colonnes Mar: 4.25; Étiquettes de colonnes Apr: 0.01; Étiquettes de colonnes Feb: 4 |  | 3.5
Resource A (Overallocated) | Étiquettes de colonnes Mar: 1.25; Étiquettes de colonnes Apr: 0.01; Étiquettes de colonnes Feb: 1.25 |  | 1.25
Resource B (Underallocated) | Étiquettes de colonnes Mar: 0.75; Étiquettes de colonnes Feb: 0.75 |  | 0.75
Resource C (Optimally Allocated) | [9 empty] | 1 | bar: Étiquettes de colonnes Mar; Étiquettes de colonnes Feb
Resource D | Étiquettes de colonnes Mar: 1.25; Étiquettes de colonnes Feb: 1 |  | 0.5
Team2 | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.02; Étiquettes de colonnes Feb: 2 |  | 1.75
Team3 | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.03; Étiquettes de colonnes Feb: 2 |  | 1.75
Team4 | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.04; Étiquettes de colonnes Feb: 2 |  | 1.75
Team5 | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.05; Étiquettes de colonnes Feb: 2 |  | 1.75
Team6 | Étiquettes de colonnes Mar: 2.5; Étiquettes de colonnes Apr: 0.06; Étiquettes de colonnes Feb: 2 |  | 1.75
Pending | Étiquettes de colonnes Mar: 15; Étiquettes de colonnes Apr: 0.21; Étiquettes de colonnes Feb: 12 |  | 10.5
Total général | Étiquettes de colonnes Mar: 31.75; Étiquettes de colonnes Apr: 0.42; Étiquettes de colonnes Feb: 26 |  | 22.75

## Summary Table
This table is pasted as a linked image from a very hidden sheet. Update the Settings and Team sheets to modify this table.

## Team 1
Adam | ← Manager ¦ Team → | Alpha | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A (Overallocated) | Project Manager I | Project A | 2017 Jan: 75%; 2017 Feb: 75%; 2017 Mar: 75%; 2017 Apr: 1%
Resource A (Overallocated) | Project Manager I | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B (Underallocated) | Project Manager II | Project C | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B (Underallocated) | Project Manager II | Project D | 2017 Jan: 25%; 2017 Feb: 25%; 2017 Mar: 25%
Resource C (Optimally Allocated) | Project Manager III | Project E | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource C (Optimally Allocated) | Project Manager III | Project E | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Resource D | Project Manager III | Project F | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 125%
Unique Resources: | 4 | Active Project Subtotal | 3.5 | 4 | 4.25 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 1%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 5.25 | 6 | 6.75 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 2
Bill | ← Manager ¦ Team → | Bravo | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 2%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 2%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 3
Charlene | ← Manager ¦ Team → | Charlie | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 3%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 3%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 4
Daryl | ← Manager ¦ Team → | Delta | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 4%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 4%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 5
Elizabeth | ← Manager ¦ Team → | Echo | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 5%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 5%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team 6
Frank | ← Manager ¦ Team → | Fox | 2017 | [11 empty] | 2018
Resource | Role | Active Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Mar: 50%; 2017 Apr: 6%
Resource A | Role1 | Project A | 2017 Jan: 50%; 2017 Feb: 100%; 2017 Mar: 100%
Resource B | Role2 | Project B | 2017 Jan: 25%; 2017 Feb: 50%; 2017 Mar: 50%
Resource B | Role2 | Project B | 2017 Jan: 50%; 2017 Feb: 50%; 2017 Mar: 50%
Unique Resources: | 2 | Active Projects Subtotal | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status (no blanks) | Role | Prospective Projects | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan+ | Feb + | Mar + | Comments
Bench |  |  | Jan: 50%; Mar: 50%; Apr: 6%
In the Dugout - May Happen |  |  | Jan: 50%; Feb: 100%; Mar: 100%
Up to Bat - Needs Resource |  |  | Jan: 25%; Feb: 50%; Mar: 50%
On Deck - Going to Happen |  |  | Jan: 50%; Feb: 50%; Mar: 50%
|  | Prospective Project Subtotal | 1.75 | 2 | 2.5 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 3.5 | 4 | 5 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0