## Tableau
| Temps Prévu: | 88 | [7 empty] | Temps réel : | 30
| Budget Prévu: | 358000 | [7 empty] | Coût constaté : | 249000
|  | Etapes | Etapes antérieurs | Temps cummulés | Temps | Budgets | Budgets/u |  | 1 | Etapes | Etapes antérieurs | Semaines réalisés | % réel d’avancement | Coûts réel constaté | Coûts/u
|  | ESQ | 0 | 3 | 3 | 24000 | 8000 |  | 2 | ESQ | 0 | 4 | 100% | 24000 | 6000 | ESQ
|  | APS/PC | ESQ | 7 | 4 | 30000 | 7500 |  | 3 | APS/PC | ESQ | 10 | 100% | 65000 | 6500 | APS/PC
|  | PRO | APS/PC | 12 | 5 | 20000 | 4000 |  | 4 | PRO | APS/PC | 16 | 100% | 160000 | 10000 | PRO
|  | ACT | PRO | 18 | 6 | 100000 | 16666.6667 |  | 5 | ACT | PRO |  |  |  | #DIV/0! | PRO
|  | VISA/DET | ACT | 28 | 10 | 70000 | 7000 |  | 6 | VISA/DET | ACT |  |  |  | #DIV/0! | PRO
|  | AOR | VISA/DET | 36 | 8 | 60000 | 7500 |  | 7 | AOR | VISA/DET |  |  |  | #DIV/0! | PRO
|  | PA | AOR | 88 | 52 | 54000 | 1038.4615 |  | 8 | PA | AOR |  |  |  | #DIV/0! | PRO
[7 empty] | #DIV/0! |  | 0 | [5 empty] | #DIV/0! | PRO
[15 empty] | #DIV/0! | PRO
[7 empty] | #DIV/0! | [7 empty] | #DIV/0! | PRO
[7 empty] | #DIV/0! | [7 empty] | #DIV/0!
|  | Etape | Temps cumulé | Temps | Budgets/u | Budget cumulé |  |  |  | Etape | Temps cumulé | Temps | Coût/u | Coût total
0 | ESQ1 | ESQ | 1 | 1 | 8000 | 8000 |  | ESQ | ESQ1 | ESQ | 1 | 1 | 6000 | 6000
0 | ESQ2 | ESQ | 2 | 1 | 8000 | 16000 |  | ESQ | ESQ2 | ESQ | 2 | 1 | 6000 | 12000
ESQ | ESQ3 | ESQ | 3 | 1 | 8000 | 24000 |  | 0 | ESQ3 | ESQ | 3 | 1 | 6000 | 18000
0 | APS/PC 4 | APS/PC | 4 | 1 | 7500 | 31500 |  | APS/PC | ESQ4 | ESQ | 4 | 1 | 6000 | 24000
0 | APS/PC 5 | APS/PC | 5 | 1 | 7500 | 39000 |  | APS/PC | APS/PC 5 | APS/PC | 5 | 1 | 6500 | 30500
0 | APS/PC 6 | APS/PC | 6 | 1 | 7500 | 46500 |  | APS/PC | APS/PC 6 | APS/PC | 6 | 1 | 6500 | 37000
APS/PC | APS/PC 7 | APS/PC | 7 | 1 | 7500 | 54000 |  | 0 | APS/PC 7 | APS/PC | 7 | 1 | 6500 | 43500
0 | PRO 8 | PRO | 8 | 1 | 4000 | 58000 |  | PRO | APS/PC 8 | APS/PC | 8 | 1 | 6500 | 50000
0 | PRO 9 | PRO | 9 | 1 | 4000 | 62000 |  | PRO | APS/PC 9 | APS/PC | 9 | 1 | 6500 | 56500
0 | PRO 10 | PRO | 10 | 1 | 4000 | 66000 |  | PRO | APS/PC 10 | APS/PC | 10 | 1 | 6500 | 63000
0 | PRO 11 | PRO | 11 | 1 | 4000 | 70000 |  | PRO | APS/PC 11 | APS/PC | 11 | 1 | 6500 | 69500
PRO | PRO 12 | PRO | 12 | 1 | 4000 | 74000 |  | 0 | APS/PC 12 | APS/PC | 12 | 1 | 6500 | 76000
0 | ACT 13 | ACT | 13 | 1 | 16666.6667 | 90666.6667 |  | ACT | APS/PC 13 | APS/PC | 13 | 1 | 6500 | 82500
0 | ACT 14 | ACT | 14 | 1 | 16666.6667 | 107333.3333 |  | ACT | APS/PC 14 | APS/PC | 14 | 1 | 6500 | 89000
0 | ACT 15 | ACT | 15 | 1 | 16666.6667 | 124000 |  | ACT | PRO 15 | PRO | 15 | 1 | 10000 | 99000
0 | ACT 16 | ACT | 16 | 1 | 16666.6667 | 140666.6667 |  | ACT | PRO 16 | PRO | 16 | 1 | 10000 | 109000
0 | ACT 17 | ACT | 17 | 1 | 16666.6667 | 157333.3333 |  | ACT | PRO 17 | PRO | 17 | 1 | 10000 | 119000
ACT | ACT 18 | ACT | 18 | 1 | 16666.6667 | 174000 |  | 0 | PRO 18 | PRO | 18 | 1 | 10000 | 129000
0 | VISA/DET19 | VISA/DET | 19 | 1 | 7000 | 181000 |  | VISA/DET | PRO 19 | PRO | 19 | 1 | 10000 | 139000
0 | VISA/DET20 | VISA/DET | 20 | 1 | 7000 | 188000 |  | VISA/DET | PRO 20 | PRO | 20 | 1 | 10000 | 149000
0 | VISA/DET21 | VISA/DET | 21 | 1 | 7000 | 195000 |  | VISA/DET | PRO 21 | PRO | 21 | 1 | 10000 | 159000
0 | VISA/DET22 | VISA/DET | 22 | 1 | 7000 | 202000 |  | VISA/DET | PRO 22 | PRO | 22 | 1 | 10000 | 169000
0 | VISA/DET23 | VISA/DET | 23 | 1 | 7000 | 209000 |  | VISA/DET | PRO 23 | PRO | 23 | 1 | 10000 | 179000
0 | VISA/DET24 | VISA/DET | 24 | 1 | 7000 | 216000 |  | VISA/DET | PRO 24 | PRO | 24 | 1 | 10000 | 189000
0 | VISA/DET25 | VISA/DET | 25 | 1 | 7000 | 223000 |  | VISA/DET | PRO 25 | PRO | 25 | 1 | 10000 | 199000
0 | VISA/DET26 | VISA/DET | 26 | 1 | 7000 | 230000 |  | VISA/DET | PRO 26 | PRO | 26 | 1 | 10000 | 209000
0 | VISA/DET27 | VISA/DET | 27 | 1 | 7000 | 237000 |  | VISA/DET | PRO 27 | PRO | 27 | 1 | 10000 | 219000
VISA/DET | VISA/DET28 | VISA/DET | 28 | 1 | 7000 | 244000 |  | 0 | PRO 28 | PRO | 28 | 1 | 10000 | 229000
0 | AOR29 | AOR | 29 | 1 | 7500 | 251500 |  | AOR | PRO 29 | PRO | 29 | 1 | 10000 | 239000
0 | AOR30 | AOR | 30 | 1 | 7500 | 259000 |  | AOR | PRO 30 | PRO | 30 | 1 | 10000 | 249000
0 | AOR31 | AOR | 31 | 1 | 7500 | 266500 |  | AOR
0 | AOR32 | AOR | 32 | 1 | 7500 | 274000 |  | AOR
0 | AOR33 | AOR | 33 | 1 | 7500 | 281500 |  | AOR
0 | AOR34 | AOR | 34 | 1 | 7500 | 289000 |  | AOR
0 | AOR35 | AOR | 35 | 1 | 7500 | 296500 |  | AOR
AOR | AOR36 | AOR | 36 | 1 | 7500 | 304000 |  | 0
0 | PA37 | PA | 37 | 1 | 1038.4615 | 305038.4615 |  | PA
0 | PA38 | PA | 38 | 1 | 1038.4615 | 306076.9231 |  | PA
0 | PA39 | PA | 39 | 1 | 1038.4615 | 307115.3846 |  | PA
0 | PA40 | PA | 40 | 1 | 1038.4615 | 308153.8462 |  | PA
0 | PA41 | PA | 41 | 1 | 1038.4615 | 309192.3077 |  | PA
0 | PA42 | PA | 42 | 1 | 1038.4615 | 310230.7692 |  | PA
0 | PA43 | PA | 43 | 1 | 1038.4615 | 311269.2308 |  | PA
0 | PA44 | PA | 44 | 1 | 1038.4615 | 312307.6923 |  | PA
0 | PA45 | PA | 45 | 1 | 1038.4615 | 313346.1538 |  | PA
0 | PA46 | PA | 46 | 1 | 1038.4615 | 314384.6154 |  | PA
0 | PA47 | PA | 47 | 1 | 1038.4615 | 315423.0769 |  | PA
0 | PA48 | PA | 48 | 1 | 1038.4615 | 316461.5385 |  | PA
0 | PA49 | PA | 49 | 1 | 1038.4615 | 317500 |  | PA
0 | PA50 | PA | 50 | 1 | 1038.4615 | 318538.4615 |  | PA
0 | PA51 | PA | 51 | 1 | 1038.4615 | 319576.9231 |  | PA
0 | PA52 | PA | 52 | 1 | 1038.4615 | 320615.3846 |  | PA
0 | PA53 | PA | 53 | 1 | 1038.4615 | 321653.8462 |  | PA
0 | PA54 | PA | 54 | 1 | 1038.4615 | 322692.3077 |  | PA
0 | PA55 | PA | 55 | 1 | 1038.4615 | 323730.7692 |  | PA
0 | PA56 | PA | 56 | 1 | 1038.4615 | 324769.2308 |  | PA
0 | PA57 | PA | 57 | 1 | 1038.4615 | 325807.6923 |  | PA
0 | PA58 | PA | 58 | 1 | 1038.4615 | 326846.1538 |  | PA
0 | PA59 | PA | 59 | 1 | 1038.4615 | 327884.6154 |  | PA
0 | PA60 | PA | 60 | 1 | 1038.4615 | 328923.0769 |  | PA
0 | PA61 | PA | 61 | 1 | 1038.4615 | 329961.5385 |  | PA
0 | PA62 | PA | 62 | 1 | 1038.4615 | 331000 |  | PA
0 | PA63 | PA | 63 | 1 | 1038.4615 | 332038.4615 |  | PA
0 | PA64 | PA | 64 | 1 | 1038.4615 | 333076.9231 |  | PA
0 | PA65 | PA | 65 | 1 | 1038.4615 | 334115.3846 |  | PA
0 | PA66 | PA | 66 | 1 | 1038.4615 | 335153.8462 |  | PA
0 | PA67 | PA | 67 | 1 | 1038.4615 | 336192.3077 |  | PA
0 | PA68 | PA | 68 | 1 | 1038.4615 | 337230.7692 |  | PA
0 | PA69 | PA | 69 | 1 | 1038.4615 | 338269.2308 |  | PA
0 | PA70 | PA | 70 | 1 | 1038.4615 | 339307.6923 |  | PA
0 | PA71 | PA | 71 | 1 | 1038.4615 | 340346.1538 |  | PA
0 | PA72 | PA | 72 | 1 | 1038.4615 | 341384.6154 |  | PA
0 | PA73 | PA | 73 | 1 | 1038.4615 | 342423.0769 |  | PA
0 | PA74 | PA | 74 | 1 | 1038.4615 | 343461.5385 |  | PA
0 | PA75 | PA | 75 | 1 | 1038.4615 | 344500 |  | PA
0 | PA76 | PA | 76 | 1 | 1038.4615 | 345538.4615 |  | PA
0 | PA77 | PA | 77 | 1 | 1038.4615 | 346576.9231 |  | PA
0 | PA78 | PA | 78 | 1 | 1038.4615 | 347615.3846 |  | PA
0 | PA79 | PA | 79 | 1 | 1038.4615 | 348653.8462 |  | PA
0 | PA80 | PA | 80 | 1 | 1038.4615 | 349692.3077 |  | PA
0 | PA81 | PA | 81 | 1 | 1038.4615 | 350730.7692 |  | PA
0 | PA82 | PA | 82 | 1 | 1038.4615 | 351769.2308 |  | PA
0 | PA83 | PA | 83 | 1 | 1038.4615 | 352807.6923 |  | PA
0 | PA84 | PA | 84 | 1 | 1038.4615 | 353846.1538 |  | PA
0 | PA85 | PA | 85 | 1 | 1038.4615 | 354884.6154 |  | PA
0 | PA86 | PA | 86 | 1 | 1038.4615 | 355923.0769 |  | PA
0 | PA87 | PA | 87 | 1 | 1038.4615 | 356961.5385 |  | PA
PA | PA88 | PA | 88 | 1 | 1038.4615 | 358000 |  | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
Insertion
Effacer
Insertion
Effacer

## Calcul
EAA |  | CBA |  | CRTE |  | CBTE |  | CBTP
1204621.6216 |  | 358000 |  | 249000 |  | 74000 |  | 259000
E/total
-10000
| VAC |  | FRAD |  | E/coût |  | E/délai
| 846621.6216 |  | 109000 |  | 175000 |  | 185000
[5 empty] | IPC |  | IPP
[5 empty] | 0.29719 |  | 0.28571
K= | 2.1275 | [7 empty] | K = 0,43 + 0,604 /IPP – 0,034 /IPP²
Jours restants prévus | 58
123.395
Jours restants réels | 124
Jours passés | 30
Totals de jours éstimés | 154

## Planning
| Prévi' |  | Réel
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
ESQ | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ESQ | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
APS/PC | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
APS/PC | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PRO | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PRO | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ACT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ACT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
VISA/DET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
VISA/DET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
AOR | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
AOR | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Budget Prévu | 8000 | 8000 | 8000 | 7500 | 7500 | 7500 | 7500 | 4000 | 4000 | 4000 | 4000 | 4000 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | 1038.4615 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Budget cum' | 8000 | 16000 | 24000 | 31500 | 39000 | 46500 | 54000 | 58000 | 62000 | 66000 | 70000 | 74000 | 90666.6667 | 107333.3333 | 124000 | 140666.6667 | 157333.3333 | 174000 | 181000 | 188000 | 195000 | 202000 | 209000 | 216000 | 223000 | 230000 | 237000 | 244000 | 251500 | 259000 | 266500 | 274000 | 281500 | 289000 | 296500 | 304000 | 305038.4615 | 306076.9231 | 307115.3846 | 308153.8462 | 309192.3077 | 310230.7692 | 311269.2308 | 312307.6923 | 313346.1538 | 314384.6154 | 315423.0769 | 316461.5385 | 317500 | 318538.4615 | 319576.9231 | 320615.3846 | 321653.8462 | 322692.3077 | 323730.7692 | 324769.2308 | 325807.6923 | 326846.1538 | 327884.6154 | 328923.0769 | 329961.5385 | 331000 | 332038.4615 | 333076.9231 | 334115.3846 | 335153.8462 | 336192.3077 | 337230.7692 | 338269.2308 | 339307.6923 | 340346.1538 | 341384.6154 | 342423.0769 | 343461.5385 | 344500 | 345538.4615 | 346576.9231 | 347615.3846 | 348653.8462 | 349692.3077 | 350730.7692 | 351769.2308 | 352807.6923 | 353846.1538 | 354884.6154 | 355923.0769 | 356961.5385 | 358000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A