## Settings
SETTINGS
Project
Name of the Project
Team
Project Manager
| NAME | RESSOURCE TYPE | E-MAIL | PHONE
Project Owner 1
Project Owner 2
Project Owner 3
Project Owner 4
Project Owner 5
Project Owner 6
Project Owner 7
Project Owner 8
Project Owner 9
Project Owner 10
Project Owner 11
Project Owner 12
Project Owner 13
Project Owner 14
Project Owner 15
Project Owner 16
Insert new row above this line
Main Task Name
TASK NAME
X
X
X
X
X
X
X
X
X
Insert new row above this line
INTERFACE
X
X
X
Insert new row above this line

## Project
RoadMap |  | Version | Update Date |  | ■
|  | T1 | 2016-10-11
Today's Date | 2016-10-13
Week Starts from | Monday | [5 empty] | Start Delay | Start Delay |  |  | Remaining |  |  | Achieved
Project Start Date | 2016-04-01
[7 empty] | Completed Later than Planned | Completed earlier than Planned |  |  | Available |  |  | Completed later than Planned
0
[5 empty] | ‼ Do not modify the informations in the shaded cells | [14 empty] | avr |  |  |  | mai |  |  |  |  | juin |  |  |  | juil |  |  |  | août |  |  |  |  | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | déc |  |  |  | janv |  |  |  |  | févr |  |  |  | mars |  |  |  | avr |  |  |  | mai |  |  |  |  | juin |  |  |  | juil |  |  |  |  | août |  |  |  | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | déc |  |  |  | janv |  |  |  |  | févr |  |  |  | mars |  |  |  | avr |  |  |  |  | mai |  |  |  | juin |  |  |  | juil |  |  |  |  | août |  |  |  | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | déc
Environments | Project Name/Phase | Project Owner | Priority Level | Initial % | Progress % | Objective % | Complete % | Progress bar % | Planned Start Use Date | Planned End Use Date | Real Start Use Date | Estimated End Use Date | Planned Duration | Duration update (delta +/-) | Start Delay |  |  | Total Planned Use in Working Days | time axis 2016-03-28 to 2018-12-31
2016-03-28
ACCEPTATION (ACC) |  |  |  | 0% |  |  |  |  | 2016-05-12 | 2016-07-20 | 2016-05-12 | 2016-07-20 | [6 empty] | 2016-04-04: Environment Availabilty
| X | Project Owner 1 | P1 | 0% | 100% | 100% | 100% | ■■■■■■■■■■ | 2016-05-03 | 2016-05-10 | 2016-05-03 | 2016-05-10 | 7 |  | 0 | 7 | 7 | 6
| X | Project Owner 1 | P1 | 0% | 100% | 100% | 100% | ■■■■■■■■■■ | 2016-07-22 | 2016-07-31 | 2016-07-22 | 2016-07-31 | 9 |  | 0 | 9 | 9 | 6
0%
HOMOLOGATION (HML) |  |  |  | 0% |  |  |  |  | 2016-10-19 | 2017-03-30 | 2016-10-19 | 2017-03-30 | [6 empty] | 2016-04-04: Environment Availabilty
| X | Project Owner 1 | P1 | 0% | 90% | 100% | 90% | ■■■■■■■■■□ | 2016-05-11 | 2016-10-17 | 2016-05-11 | 2016-10-17 | 159 |  | 0 | 159 | 159 | 114
| X | Project Owner 1 | P1 | 0% | 90% | 100% | 90% | ■■■■■■■■■□ | 2016-08-01 | 2016-10-17 | 2016-08-01 | 2016-10-17 | 77 |  | 0 | 77 | 77 | 56
| X | Project Owner 1 | P1 | 0% | 90% | 100% | 90% | ■■■■■■■■■□ | 2016-09-30 | 2016-11-15 | 2016-09-30 | 2016-11-15 | 46 |  | 0 | 46 | 46 | 33
| X | Project Owner 1 | P1 | 0% | 0% | 100% | 0% | □□□□□□□□□□ | 2017-04-01 | 2017-06-30 | 2017-04-01 | 2017-06-30 | 90 |  | 0 | 90 | 90 | 65
| X | Project Owner 1 | P1 |  | 0% | 100% | 0% | □□□□□□□□□□ | 2017-04-01 | 2017-06-30 | 2017-04-01 | 2017-06-30 | 90 |  | 0 | 90 | 90 | 65
RECETTE (REC) |  |  |  | 0% |  |  |  |  | 2016-10-07 | 2016-10-15 | 2016-10-07 | 2016-10-15 | [6 empty] | 2016-04-04: Environment Availabilty
| X | Project Owner 1 | P1 | 0% | 0% | 100% | 0% | □□□□□□□□□□ | 2016-10-17 | 2017-03-10 | 2016-10-17 | 2017-03-10 | 144 |  | 0 | 144 | 144 | 105
| X | Project Owner 1 | P1 | 0% | 100% | 100% | 100% | ■■■■■■■■■■ | 2016-07-01 | 2016-10-05 | 2016-07-01 | 2016-10-05 | 96 |  | 0 | 96 | 96 | 69
PREPRODUCTION (PREPROD) |  |  |  | 0% |  |  |  |  | 2016-10-14 | 2016-10-04 | 2016-10-14 | 2016-10-04 | [6 empty] | 2016-04-04: Environment Availabilty
| X | Project Owner 1 | P1 | 0% | 100% | 100% | 100% | ■■■■■■■■■■ | 2016-10-06 | 2016-10-12 | 2016-10-06 | 2016-10-12 | 6 |  | 0 | 6 | 6 | 5
PRODUCTION (PROD) |  |  |  | 0% |  |  |  |  | 2016-10-19 | 2016-10-11 | 2016-10-19 | 2016-10-11 | [6 empty] | 2016-04-04: Environnement Availability
| X | Project Owner 1 | P1 | 0% | 50% | 100% | 50% | ■■■■■□□□□□ | 2016-10-13 | 2016-10-17 | 2016-10-13 | 2016-10-17 | 4 |  | 0 | 4 | 4 | 3
0%
0%
0%
0%