## Indicators
[5 empty] | Udpate: | 2016-06-16
TOP 25 PROGRESSION OVERVIEW
ALL PROJECT PROGRESSION OVERVIEW
1-Planning/Engineering/MOC | 2-Procurement | 3-Project Execution and QA/QC
Comments & work in focus: | Comments & work in focus: | Comments & work in focus: | Comments & work in focus: | Comments & work in focus:
Comments & work in focus: | Comments & work in focus: | Comments & work in focus: | Comments & work in focus: (MTD)
#REF!

## Indicators_Data (hidden)
TOP 25
1-Planning and Engineering in progress / MOC | [5 empty] | 166.6667 | 1-Planning and Engineering in progress / MOC
Valeur atteinte 2 | #REF! | #REF! | Target | 100 | 100% |  | 100 | #REF! | 100
Valeur ecart 2 | #REF! |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | #REF! | 99
2-Procurement
Valeur atteinte 2 | #REF! | #REF! | Target | 100 | 100% |  | 100 | #REF! | 100
Valeur ecart 2 | #REF! |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | #REF! | 99
3-Project Execution and QA/QC
Valeur atteinte 2 | #REF! | #REF! | Target | 100 | 100% |  | 100 | #REF! | 100
Valeur ecart 2 | #REF! |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | #REF! | 99
Number of status
Procurement in progress | #REF!
Engeneering in progress | #REF!
Planning in progress | #REF!
Canceled | #REF!
Execution in progress | #REF!
Approved | #REF!
Ready to complete | #REF!
Closed | #REF!
Child WO's Not Closed | #REF!
ALL
1- Engineering | [5 empty] | 166.6667 | 1-Planning and Engineering in progress / MOC
Valeur atteinte 2 | 4773% | 47.73% | Target | 100 | 100% |  | 100 | 47.7296 | 100
Valeur ecart 2 | 52.2704 |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | 151.2704 | 99
2-Procurement
Valeur atteinte 2 | 3125% | 31.25% | Target | 100 | 100% |  | 100 | 31.25 | 100
Valeur ecart 2 | 68.75 |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | 167.75 | 99
3- Execution
Valeur atteinte 2 | 2041% | 20.41% | Target | 100 | 100% |  | 100 | 20.41 | 100
Valeur ecart 2 | 79.59 |  | épaisseur | 1 | 1% |  | 100 | 1 | 1
Valeur fixe 2 | 66.6667 |  | Valeur fixe 2 | 65.6667 | 65.67% |  |  | 178.59 | 99

## 3100.3200_Tab
Area | (Plusieurs éléments)
Étiquettes de lignes | 3- Execution | 2- Procurement | 1- Engineering
31-PU-11/21/31/41/51 upgrade | 0% | 0% | 7.018% | 31-PU-11/21/31/41/51 upgrade | 2017-08-24 | 2017-09-07 | 2017-04-02
3200 Blast spools LP flash steam | 0% | 0% | 52.63% | 3200 Blast spools LP flash steam | 2016-05-26 | 2016-10-28 | 2016-10-07
Alternative triple pumps | 0% | 0% | 21.05% | Alternative triple pumps | 2017-05-02 | 2017-06-22 | 2017-12-29
GEHO maintenance platforms | 0% | 0% | 24.56% | GEHO maintenance platforms | 2017-06-17 | 2017-08-08 | 2017-10-24
Recycle H2S from 3500 to 3400 | 0% | 0% | 29.82% | Recycle H2S from 3500 to 3400 | 0 | 0 | 0
Review 52-PU-05 caustic pump | 0% | 0% | 29.82% | Review 52-PU-05 caustic pump | 0 | 0 | 0
Spare agitator gearbox assemblies | 0% | 0% | 31.58% | Spare agitator gearbox assemblies | 2017-04-30 | 2017-07-22 | 2017-06-13
Triple Pumps Reliability | 0% | 0% | 0% | Triple Pumps Reliability | 2017-06-06 | 2017-05-18 | 2017-04-28
Total général | 0% | 0% | 24.56% | Total général
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## T_Data_Arun (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Arun | Execution in progress | Replacement of rubber lined piping at the tailings discharge pumps in PAL | 33-PU-41/42/43/44 | 3300 | [30 empty] | 0 | 0 | 0 | 2017-08-25 | 2017-11-22 | 2017-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arun | Execution in progress | Common line from 35-PU-14/24 A/B to 35TK75 replacement (3500) | 35-TK-75 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-07-21 | 2017-06-30 | 2017-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arun | Execution in progress | Train 1&2 inlet and outlet piping replacement | 3400 | 3400 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  | 0.96491 | 1 | 0.9697 | 2017-12-29 | 2017-06-09 | 2017-10-04 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0

## T_Data_Denis (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Denis | Engineering in progress | ICAM: Validate Existing Pre-heater Instrumentation and Final Control Elements | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | [15 empty] | 0.92982 | 0 | 0 | 2017-10-30 | 2017-06-13 | 2017-11-23 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Denis | Engineering in progress | ICAM:Pre-heater Feed Pump Discharge Pressure Indication | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | 0.96491 | 1 | 0.48485 | 2017-06-17 | 2017-08-08 | 2017-10-24 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0 | 0 | 0 | 0 | 0 | 0
| Denis | Engineering in progress | ICAM: Pre-heater Pressure Indication | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-04-23 | 2017-05-16 | 2017-07-30 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0.030303
| Denis | Engineering in progress | 3300 MOL addition improved controls | 3300 | 3300 | [30 empty] | 0 | 0 | 0 | 2017-10-08 | 2017-12-16 | 2017-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Elisa (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Elisa | Engineering in progress | GEHO maintenance platforms | 32-PU-15/25/35/45/55 | 3200 | Permanent platforms to be installed for Maintenance |  |  | x | x | x | x | [23 empty] | 0.24561 | 0 | 0 | 2017-06-17 | 2017-08-08 | 2017-10-24 | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Gueorgui (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Gueorgui | Engineering in progress | Modification of the piping header to measure dilution in CCD | 33-TH-01/02/03/04/06/07 | 3300 | Defect Elimination action 33-DE-02 |  |  | x | x | x | x | [23 empty] | 0.24561 | 0 | 0 | 2017-04-23 | 2017-05-16 | 2017-07-30 | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Guillaume (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Guillaume | Engineering in progress | 36-TK-19 bypass | 36-TK-19 | 3600 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-04-29 | 2017-11-05 | 2017-05-10 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0.030303
| Guillaume | Engineering in progress | 35-TK-01 bypass | 35-TK-01 | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | 0.96491 | 1 | 0 | 2017-06-24 | 2017-05-05 | 2017-12-25 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | ICAM: 3500 Train Feed Tank Level | 35-TK-01/02 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-05-24 | 2017-11-13 | 2017-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | ICAM:Valve Travel Times | 35-PU-11B | 3500 | [30 empty] | 0 | 0 | 0 | 2017-10-07 | 2017-07-02 | 2017-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | Pump back long term solution | 96-PU | 9600 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-08-12 | 2017-12-13 | 2017-08-17 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Not started | 3500 Sulphide Precipitation area improvement 2017 | 3500 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-08-04 | 2017-08-01 | 2017-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Miandry (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Miandry | Engineering in progress | Assessment if HDPE can be used for TMF distribution line | 9600 | 9600 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | 1 | 1 | 0.24242 | 2017-11-09 | 2017-06-13 | 2017-05-27 | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Miandry | Engineering in progress | 35-FN-03 Drain | 35-FN-03 | 3500 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1 | 1 | 1 | 2017-06-04 | 2017-08-07 | 2017-04-16 | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0.030303
2003553 | Miandry | Engineering in progress | Recycle H2S from 3500 to 3400 | 3200 | 3200 | Proper control of the reactor vent is crucial. Managing the right level of inert gas recirculating around prevents lossof efficiency |  |  | x | x | x | x | x | [22 empty] | 0.29825 | 0 | 0 |  |  |  | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2003554 | Miandry | Engineering in progress | Reduce sour water spill | 35-TK-90 | 3500 |  |  |  | x | x | x |  |  | x | [21 empty] | 0.19298 | 0 | 0 |  |  |  | 0.035088 | 0.070175 | 0.035088 | 0 | 0 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2003555 | Miandry | Engineering in progress | Transfer 35-VE-70 to 35-VE-05 | 35-VE-70 / 35-VE-05 | 3500 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [13 empty] | 1 | 0.3 | 0 |  |  |  | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Miandry | Engineering in progress | Review 52-PU-05 caustic pump | 52-PU-05 | 3200 |  |  |  | x | x | x | x | x | [22 empty] | 0.29825 | 0 | 0 |  |  |  | 0.035088 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Nambin (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Nambin | Engineering in progress | Modification of the flexible hose by rigid piping for Floc Injection | 33-TH-01/02/03/04/06/07 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-07-30 | 2017-09-26 | 2017-04-30 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0.030303
| Nambin | Engineering in progress | Facilitate the Pump access in the Floc Preparation Area | 51-PU-206 | 5100 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | 0.96491 | 1 | 0.24242 | 2017-06-14 | 2017-12-30 | 2017-04-28 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Oleg (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Oleg | Engineering in progress | Restart H2S compressors including a recirculation philosophy | 35-CP-01/02 | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-09-20 | 2017-07-19 | 2017-05-15 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0.030303

## T_Data_Patrick (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Patrick | Not started | 3400 Raw Liquor Neutralization area improvement 2017 | 34-TH-01 and 02 | 3400 | [30 empty] | 0 | 0 | 0 | 2017-10-23 | 2017-07-01 | 2017-11-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | PAL sump pump replacement | 33-PU-02/28/35-PU-02/36-PU-22 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x |  | x | x | [12 empty] | 0.92982 | 0.5 | 0 | 2017-08-20 | 2017-06-13 | 2017-06-10 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | 31-PU-11/21/31/41/51 upgrade | 31-PU-11/21/31/41/51 | 3100 |  |  |  |  | x | [25 empty] | 0.070175 | 0 | 0 | 2017-08-24 | 2017-09-07 | 2017-04-02 | 0 | 0.070175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | Spare agitator gearbox assemblies | 32-AG-21/22 | 3200 |  |  |  |  | x | x | x | x | x | [21 empty] | 0.31579 | 0 | 0 | 2017-04-30 | 2017-07-22 | 2017-06-13 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Engineering in progress | 3200 Blast spools LP flash steam |  | 3200 |  |  |  |  | x | x | x | x | x | x | x | [19 empty] | 0.52632 | 0 | 0 | 2016-05-26 | 2016-10-28 | 2016-10-07 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Roelof (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Roelof | Engineering in progress | Alternative triple pumps | 32-PU-11 | 3200 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-05-02 | 2017-06-22 | 2017-12-29 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roelof | Execution in progress | 36-TK-19 relining | 36-TK-19 | 3600 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-11-26 | 2017-08-11 | 2017-09-08 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roelof | Execution in progress | 33-TK-29 relining | 33-TK-29 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | [16 empty] | 0.82456 | 0 | 0 | 2017-04-23 | 2017-07-08 | 2017-08-28 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T_Data_Vien (hidden)
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27
| Vien | Procurement in progress | Triple Pumps Reliability | 32-PU-11 | 3200 | [30 empty] | 0 | 0 | 0 | 2017-06-06 | 2017-05-18 | 2017-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vien | Execution in progress | Floc Preparation Plant improvements | 5100 | 5100 | [30 empty] | 0 | 0 | 0 | 2017-05-26 | 2017-11-08 | 2017-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 3300_Tab
Area | 3300
Étiquettes de lignes | 3- Execution | 2- Procurement | 1- Engineering
3300 MOL addition improved controls | 0% | 0% | 0% | 3300 MOL addition improved controls | 2017-10-08 | 2017-12-16 | 2017-11-22
33-TK-29 relining | 0% | 0% | 82.46% | 33-TK-29 relining | 2017-04-23 | 2017-07-08 | 2017-08-28
Modification of the flexible hose by rigid piping for Floc Injection | 100% | 100% | 96.49% | Modification of the flexible hose by rigid piping for Floc Injection | 2017-07-30 | 2017-09-26 | 2017-04-30
Modification of the piping header to measure dilution in CCD | 0% | 0% | 24.56% | Modification of the piping header to measure dilution in CCD | 2017-04-23 | 2017-05-16 | 2017-07-30
PAL sump pump replacement | 0% |  | 92.98% | PAL sump pump replacement | 2017-08-20 | 2017-06-13 | 2017-06-10
Replacement of rubber lined piping at the tailings discharge pumps in PAL | 0% | 0% | 0% | Replacement of rubber lined piping at the tailings discharge pumps in PAL | 2017-08-25 | 2017-11-22 | 2017-07-04
Total général | 16.67% | 20% | 49.42% | Total général
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 3400_Tab
Area | 3400
Étiquettes de lignes | 3- Execution | 2- Procurement | 1- Engineering
3400 Raw Liquor Neutralization area improvement 2017 | 0% | 0% | 0% | 3400 Raw Liquor Neutralization area improvement 2017 | 2017-10-23 | 2017-07-01 | 2017-11-19
Train 1&2 inlet and outlet piping replacement | 96.97% | 100% | 96.49% | Train 1&2 inlet and outlet piping replacement | 2017-12-29 | 2017-06-09 | 2017-10-04
Total général | 48.48% | 50% | 48.25% | Total général
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 3500.3600_Tab
Area | (Plusieurs éléments)
Étiquettes de lignes | 3- Execution | 2- Procurement | 1- Engineering
3500 Sulphide Precipitation area improvement 2017 | 0% | 0% | 0% | 3500 Sulphide Precipitation area improvement 2017 | 2017-08-04 | 2017-08-01 | 2017-04-29
35-FN-03 Drain | 100% | 100% | 100% | 35-FN-03 Drain | 2017-06-04 | 2017-08-07 | 2017-04-16
35-TK-01 bypass | 0% | 100% | 96.49% | 35-TK-01 bypass | 2017-06-24 | 2017-05-05 | 2017-12-25
36-TK-19 bypass | 100% | 100% | 96.49% | 36-TK-19 bypass | 2017-04-29 | 2017-11-05 | 2017-05-10
36-TK-19 relining | 0% | 0% | 21.05% | 36-TK-19 relining | 2017-11-26 | 2017-08-11 | 2017-09-08
Common line from 35-PU-14/24 A/B to 35TK75 replacement (3500) | 0% | 0% | 0% | Common line from 35-PU-14/24 A/B to 35TK75 replacement (3500) | 2017-07-21 | 2017-06-30 | 2017-10-29
ICAM: 3500 Train Feed Tank Level | 0% | 0% | 0% | ICAM: 3500 Train Feed Tank Level | 2017-05-24 | 2017-11-13 | 2017-09-24
ICAM: Pre-heater Pressure Indication | 100% | 100% | 96.49% | ICAM: Pre-heater Pressure Indication | 2017-04-23 | 2017-05-16 | 2017-07-30
ICAM: Validate Existing Pre-heater Instrumentation and Final Control Elements | 0% | 0% | 92.98% | ICAM: Validate Existing Pre-heater Instrumentation and Final Control Elements | 2017-10-30 | 2017-06-13 | 2017-11-23
ICAM:Pre-heater Feed Pump Discharge Pressure Indication | 48.48% | 100% | 96.49% | ICAM:Pre-heater Feed Pump Discharge Pressure Indication | 2017-06-17 | 2017-08-08 | 2017-10-24
ICAM:Valve Travel Times | 0% | 0% | 0% | ICAM:Valve Travel Times | 2017-10-07 | 2017-07-02 | 2017-11-08
Reduce sour water spill | 0% | 0% | 19.3% | Reduce sour water spill | 0 | 0 | 0
Restart H2S compressors including a recirculation philosophy | 100% | 100% | 96.49% | Restart H2S compressors including a recirculation philosophy | 2017-09-20 | 2017-07-19 | 2017-05-15
Transfer 35-VE-70 to 35-VE-05 | 0% |  | 100% | Transfer 35-VE-70 to 35-VE-05 | 0 | 0 | 0
Total général | 32.03% | 46.15% | 58.27% | Total général
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 5100.9600_Tab
Area | (Plusieurs éléments)
Étiquettes de lignes | 3- Execution | 2- Procurement | 1- Engineering
Assessment if HDPE can be used for TMF distribution line | 24.24% | 100% | 100% | Assessment if HDPE can be used for TMF distribution line | 2017-11-09 | 2017-06-13 | 2017-05-27
Facilitate the Pump access in the Floc Preparation Area | 24.24% | 100% | 96.49% | Facilitate the Pump access in the Floc Preparation Area | 2017-06-14 | 2017-12-30 | 2017-04-28
Floc Preparation Plant improvements | 0% | 0% | 0% | Floc Preparation Plant improvements | 2017-05-26 | 2017-11-08 | 2017-11-22
Pump back long term solution | 0% | 0% | 21.05% | Pump back long term solution | 2017-08-12 | 2017-12-13 | 2017-08-17
Total général | 12.12% | 50% | 54.39% | Total général
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Data
Work Order | Leader | Status | Description | Equipment | Area | Comments | Commissioning Start date | Commissioning Completion date | Marked-Up Document | Identify Options | Scope Def. | Pre. Design | TECH Review | Pre Cost Estimate Approved | Package completed | Initial Design Review | Design Risk Review | Final Design Review | Design Issued | Approved Cost Estimate | MOC Created/Not Needed | BOM Done | PR Sent | PO Issued | PO Delivered | Construction Package Sent | Pick Tickets Done | Installation Scheduled | Installation in Progress | PSSR Done | Start-up Done | Punch List | Objectives achieved? | Close MOC | Close Project | 1- Engineering | 2- Procurement | 3- Execution | Estimated date 1- Engineering | Estimated date 2-Procurement | Estimated date 3- Execution | Marked-Up Document2 | Identify Options2 | Scope Def.3 | Pre. Design4 | TECH Review5 | Pre Cost Estimate Approved6 | Package given to TS7 | Initial Design Review8 | Design Risk Review9 | Final Design Review10 | TS Design Issued11 | Approved Cost Estimate12 | MOC Created/Not Needed13 | BOM Done14 | PR Sent15 | PO Issued16 | PO Delivered17 | Construction Package Sent18 | Pick Tickets Done19 | Installation Scheduled20 | Installation in Progress21 | PSSR Done22 | Start-up Done23 | Punch List24 | Objectives achieved?25 | Close MOC26 | Close Project27 | Commissioning Start date | Commissioning Completion date
| Arun | Execution in progress | Replacement of rubber lined piping at the tailings discharge pumps in PAL | 33-PU-41/42/43/44 | 3300 | [30 empty] | 0 | 0 | 0 | 2017-08-25 | 2017-11-22 | 2017-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arun | Execution in progress | Common line from 35-PU-14/24 A/B to 35TK75 replacement (3500) | 35-TK-75 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-07-21 | 2017-06-30 | 2017-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arun | Execution in progress | Train 1&2 inlet and outlet piping replacement | 3400 | 3400 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  | 0.96491 | 1 | 0.9697 | 2017-12-29 | 2017-06-09 | 2017-10-04 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606 | 0
| Denis | Engineering in progress | ICAM: Validate Existing Pre-heater Instrumentation and Final Control Elements | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | [15 empty] | 0.92982 | 0 | 0 | 2017-10-30 | 2017-06-13 | 2017-11-23 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Denis | Engineering in progress | ICAM:Pre-heater Feed Pump Discharge Pressure Indication | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | 0.96491 | 1 | 0.48485 | 2017-06-17 | 2017-08-08 | 2017-10-24 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0 | 0 | 0 | 0 | 0 | 0
| Denis | Engineering in progress | ICAM: Pre-heater Pressure Indication | 35-PU-11B | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-04-23 | 2017-05-16 | 2017-07-30 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606
| Denis | Engineering in progress | 3300 MOL addition improved controls | 3300 | 3300 | [30 empty] | 0 | 0 | 0 | 2017-10-08 | 2017-12-16 | 2017-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Elisa | Engineering in progress | GEHO maintenance platforms | 32-PU-15/25/35/45/55 | 3200 | Permanent platforms to be installed for Maintenance |  |  | x | x | x | x | [23 empty] | 0.24561 | 0 | 0 | 2017-06-17 | 2017-08-08 | 2017-10-24 |  | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gueorgui | Engineering in progress | Modification of the piping header to measure dilution in CCD | 33-TH-01/02/03/04/06/07 | 3300 | Defect Elimination action 33-DE-02 |  |  | x | x | x | x | [23 empty] | 0.24561 | 0 | 0 | 2017-04-23 | 2017-05-16 | 2017-07-30 |  | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | 36-TK-19 bypass | 36-TK-19 | 3600 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-04-29 | 2017-11-05 | 2017-05-10 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606
| Guillaume | Engineering in progress | 35-TK-01 bypass | 35-TK-01 | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | 0.96491 | 1 | 0 | 2017-06-24 | 2017-05-05 | 2017-12-25 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | ICAM: 3500 Train Feed Tank Level | 35-TK-01/02 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-05-24 | 2017-11-13 | 2017-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | ICAM:Valve Travel Times | 35-PU-11B | 3500 | [30 empty] | 0 | 0 | 0 | 2017-10-07 | 2017-07-02 | 2017-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Engineering in progress | Pump back long term solution | 96-PU | 9600 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-08-12 | 2017-12-13 | 2017-08-17 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Guillaume | Not started | 3500 Sulphide Precipitation area improvement 2017 | 3500 | 3500 | [30 empty] | 0 | 0 | 0 | 2017-08-04 | 2017-08-01 | 2017-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Miandry | Engineering in progress | Assessment if HDPE can be used for TMF distribution line | 9600 | 9600 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | 1 | 1 | 0.24242 | 2017-11-09 | 2017-06-13 | 2017-05-27 |  | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Miandry | Engineering in progress | 35-FN-03 Drain | 35-FN-03 | 3500 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1 | 1 | 1 | 2017-06-04 | 2017-08-07 | 2017-04-16 |  | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606
2003553 | Miandry | Engineering in progress | Recycle H2S from 3500 to 3400 | 3200 | 3200 | Proper control of the reactor vent is crucial. Managing the right level of inert gas recirculating around prevents lossof efficiency |  |  | x | x | x | x | x | [22 empty] | 0.29825 | 0 | 0 |  |  |  |  | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2003554 | Miandry | Engineering in progress | Reduce sour water spill | 35-TK-90 | 3500 |  |  |  | x | x | x |  |  | x | [21 empty] | 0.19298 | 0 | 0 |  |  |  |  | 0.070175 | 0.035088 | 0 | 0 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2003555 | Miandry | Engineering in progress | Transfer 35-VE-70 to 35-VE-05 | 35-VE-70 / 35-VE-05 | 3500 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [13 empty] | 1 |  | 0 |  |  |  |  | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Miandry | Engineering in progress | Review 52-PU-05 caustic pump | 52-PU-05 | 3200 |  |  |  | x | x | x | x | x | [22 empty] | 0.29825 | 0 | 0 |  |  |  |  | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nambin | Engineering in progress | Modification of the flexible hose by rigid piping for Floc Injection | 33-TH-01/02/03/04/06/07 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-07-30 | 2017-09-26 | 2017-04-30 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606
| Nambin | Engineering in progress | Facilitate the Pump access in the Floc Preparation Area | 51-PU-206 | 5100 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | 0.96491 | 1 | 0.24242 | 2017-06-14 | 2017-12-30 | 2017-04-28 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Oleg | Engineering in progress | Restart H2S compressors including a recirculation philosophy | 35-CP-01/02 | 3500 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0.96491 | 1 | 1 | 2017-09-20 | 2017-07-19 | 2017-05-15 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0.035088 | 0.3 | 0.2 | 0.2 | 0.3 | 0.060606 | 0.060606 | 0.12121 | 0.24242 | 0.090909 | 0.18182 | 0.060606 | 0.090909 | 0.060606
| Patrick | Not started | 3400 Raw Liquor Neutralization area improvement 2017 | 34-TH-01 and 02 | 3400 | [30 empty] | 0 | 0 | 0 | 2017-10-23 | 2017-07-01 | 2017-11-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | PAL sump pump replacement | 33-PU-02/28/35-PU-02/36-PU-22 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x |  | x | x | [12 empty] | 0.92982 |  | 0 | 2017-08-20 | 2017-06-13 | 2017-06-10 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0.10526 | 0 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | 31-PU-11/21/31/41/51 upgrade | 31-PU-11/21/31/41/51 | 3100 |  |  |  |  | x | [25 empty] | 0.070175 | 0 | 0 | 2017-08-24 | 2017-09-07 | 2017-04-02 | 0 | 0.070175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Procurement in progress | Spare agitator gearbox assemblies | 32-AG-21/22 | 3200 |  |  |  |  | x | x | x | x | x | [21 empty] | 0.31579 | 0 | 0 | 2017-04-30 | 2017-07-22 | 2017-06-13 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Patrick | Engineering in progress | 3200 Blast spools LP flash steam |  | 3200 |  |  |  |  | x | x | x | x | x | x | x | [19 empty] | 0.52632 | 0 | 0 | 2016-05-26 | 2016-10-28 | 2016-10-07 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roelof | Engineering in progress | Alternative triple pumps | 32-PU-11 | 3200 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-05-02 | 2017-06-22 | 2017-12-29 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roelof | Execution in progress | 36-TK-19 relining | 36-TK-19 | 3600 |  |  |  |  | x | x | x | [23 empty] | 0.21053 | 0 | 0 | 2017-11-26 | 2017-08-11 | 2017-09-08 | 0 | 0.070175 | 0.035088 | 0.10526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roelof | Execution in progress | 33-TK-29 relining | 33-TK-29 | 3300 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | [16 empty] | 0.82456 | 0 | 0 | 2017-04-23 | 2017-07-08 | 2017-08-28 | 0 | 0.070175 | 0.035088 | 0.10526 | 0.052632 | 0.052632 | 0.035088 | 0.17544 | 0.070175 | 0.17544 | 0.052632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vien | Procurement in progress | Triple Pumps Reliability | 32-PU-11 | 3200 | [30 empty] | 0 | 0 | 0 | 2017-06-06 | 2017-05-18 | 2017-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vien | Execution in progress | Floc Preparation Plant improvements | 5100 | 5100 | [30 empty] | 0 | 0 | 0 | 2017-05-26 | 2017-11-08 | 2017-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0