## Front_sheet
MRL PROC STATUS MASTER v2
Date | Modified by | Description of change
2017-02-14 | Olivier Nossa | Improved new format

## STATUS
PROC STATUS FOLLOW-UP v2
ITB |  |  |  | PROGRESS | CRITICALITY /Delay for delivery | MRL | [17 empty] | NOC |  | PO
[6 empty] | MRL identification |  |  |  | Requested delivery |  | Link I:\ | Link Outlook | RFQ |  |  | MRL completion
Number | Status | Hold | Cancel |  |  | Number | Rev | Requestor | Title | date | location |  |  | issue date | calculated due date | Supplier | Quoted price € | Lead time (days) | Acceptable offer ? | PRODUCTION ORDER Date | Calculated delivery date | Comments | Buyer | Number | Date | Number | Amendt
546-112 | RFQ issued |  |  | 50 |  | 5325-2188 | A | JBO | Dande Seafastening | 2017-03-20 | Tarragona (Schwartz Hautmont) | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-112_MRL-5325-2188_Dande Seafastening | ITB-546-112_MRL-5325-2188-A Dande Seafastening | 2017-03-01 | 2017-03-06 | RIGMARINE
546-113 | Quotation on clarif |  |  | 70 |  | 5329-2189 | A | FZA | Mooring ropes and tyres for CB | 2017-03-24 | Tarragona (Schwartz Hautmont) | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-113_MRL-5329-2189_Mooring ropes and tyres for CB | ITB-546-113_MRL-5329-2189-A Mooring ropes and tyres for CB | 2017-03-01 | 2017-03-06 | RIGMARINE |  | 21
546-114 | RFQ issued |  |  | 50 |  | 5329-2191 | A | MWK | NSA Spares picker - TTS | 2017-03-20 | TP Angola | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-114_MRL-5329-2191_NSA Spares picker - TTS | ITB-546-114_MRL-5329-2191-A NSA Spares picker - TTS | 2017-03-06 | 2017-03-11 | RIGMARINE
546-115 | Quotation on clarif |  |  | 70 |  | 5850-2192 | A | SLE | BM Lifting Rigging | 2017-03-20 | New Castle | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-115_MRL-5850-2192_BM Lifting Rigging | ITB-546-115_MRL-5850-2192-A BM Lifting Rigging | 2017-03-06 | 2017-03-11 | RIGMARINE |  | 7
546-116 | Quotation on clarif |  |  | 70 |  | 5850-2194 | A | SLE | Additional wires for pile SKAF | 2017-03-16 | New Castle | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-116_MRL-5850-2194_Additional wires for pile SKAF | ITB-546-116_MRL-5850-2194-A Additional wires for pile SKAF | 2017-03-07 | 2017-03-12 | RIGMARINE |  | 7
546-117 | Quotation on clarif |  |  | 70 |  | 5850-2195 | A | SLE | Rigging for stack up test | 2017-03-16 | Reel SAS - Imeca La Rochelle | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-117_MRL-5850-2195_Rigging for stack up test | ITB-546-117_MRL-5850-2195-A Rigging for stack up test | 2017-03-08 | 2017-03-13 | RIGMARINE |  | 7
546-118 | RFQ issued |  |  | 50 |  | 5870-2197 | A | SLE | Misc Material for Dande | 2017-03-16 | Tarragona (Schwartz Hautmont) | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-118_MRL-5870-2197_Misc Material for Dande | ITB-546-118_MRL-5870-2197-A Misc Material for Dande | 2017-03-09 | 2017-03-14 | RIGMARINE
546-119 | RFQ issued |  |  | 50 |  | 5870-2198 | A | SLE | Consumables for operations NSA | 2017-03-16 | Tarragona (Schwartz Hautmont) | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-119_MRL-5870-2198_Consumables for operations NSA | ITB-546-119_MRL-5870-2198-A Consumables for operations NSA | 2017-03-09 | 2017-03-14 | RIGMARINE
546-120 | RFQ issued |  |  | 50 |  | 5850-2199 | A | SLE | Miscellaneous Install Rigging SKAF | 2017-03-20 | Tarragona (Schwartz Hautmont) | I:\063950C001-KAOMBO\10-Restricted-Procurement\03_ITBs IA OPERATIONS\ITB-546-120_MRL-5850-2199_Miscellaneous Install Rigging SKAF | ITB-546-120_MRL-5850-2199-A Miscellaneous Install Rigging SKAF | 2017-03-09 | 2017-03-14 | RIGMARINE
Formulas:
calculated due date = IF(ISBLANK([RFQ]),"",[RFQ]+5)

## choice_lists
STATUS | PROGRESS | REQUISITOR | BUYER | ACCEPTABLE ? | SUPPLIER | DELIVERY PLACE | TODAY | MRL REV | DELAY CRITICALITY | PO NUMBER
MRL received | 20 | FZA | LFI | YES | RIGMARINE | Aberdeen | 2017-03-09 | A | 7 | S1578
RFQ issued | 50 | JBO | ONO | NO | EMM | OSLT (Le Trait) |  | B | 21
Quotation on clarif | 70 | SLE | FMO |  | Other | Tarragona (Schwartz Hautmont) |  | C | 100
NOC Issued | 85 | WAU |  |  |  | Moffat UK |  | D
PO Placed | 100 | HTS |  |  |  | New Castle |  | E
HOLD | 0 | FJL |  |  |  | Bintan |  | F
Cancelled | 0 | APE |  |  |  | Asturfeito (Spain) |  | 0
|  | MWK |  |  |  | TP Angola |  | 1
[6 empty] | Reel SAS - Imeca La Rochelle |  | 2
3
4
5

## Statistics
Total amount (quotations) | 0
MRL quantity since 01/03/2017 | 7
Average price per MRL | 0