## FIFI
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
[19 empty] | PLANNED WORKLOAD FUNCT | PLANNED WORKLOAD DEV | [11 empty] | PLANNED WORKLOAD FUNCT | PLANNED WORKLOAD DEV | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [11 empty] | TOTAL PLANNED WORKLOAD FUNCT. HORS M3 |  | TOTAL PLANNED WORKLOAD DEV. HORS M3 | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [9 empty] | 296 | 533
ID | LOT | Outils | SOURCE | TARGET | TOPIC | DELIVERABLE GENERAL NAME | COMMENT | TYPE | COMPLEXITY | OTHER | WORKSHOP | RESPONSIBLE | DATE | WORKLOAD | ATTENDEES | STATUS | FUNCTIONAL SPECIFICATION | Funct. Resp. | PLANNED WORKLOAD FUNCT. | PLANNED WORKLOAD DEV. | DURATION | PLANNED START DATE | PLANNED DUE DATE | ACTUALS | ETC | ESTIMATED END DATE | STATUS2 | EAC | % WORKLOAD COMPLETED | TECHNICAL SPECIFICATION | Dev. Resp. | PLANNED WORKLOAD FUNCT. | PLANNED WORKLOAD DEV. | DURATION3 | PLANNED START DATE4 | PLANNED DUE DATE5 | ACTUALS6 | ETC7 | ESTIMATED END DATE2 | STATUS9 | EAC8 | % WORK COMPLETED | DETAILED TECHNICAL SPECIFICATION | Funct. Resp.10 | PLANNED WORKLOAD FUNCT.11 | Dev. Resp.12 | PLANNED WORKLOAD DEV.13 | DURATION14 | PLANNED START DATE15 | PLANNED DUE DATE16 | ACTUALS17 | ETC18 | ESTIMATED END DATE22 | STATUS21 | EAC19 | % WORK COMPLETE20 | DETAILED TECHNICAL SPECIFICATION NOT IN M3 | Funct. Resp. Hors M3 | PLANNED WORKLOAD FUNCT. HORS M3 | Dev. Resp. HORS M3 | PLANNED WORKLOAD DEV. HORS M3 | DURATION22 | PLANNED START DATE23 | PLANNED DUE DATE24 | ACTUALS25 | ETC26 | ESTIMATED END DATE222 | STATUS29 | EAC27 | % WORK COMPLETE28 | UNIT TESTS | Funct. Resp | PLANNED WORKLOAD FUNCT.30 | Dev. Resp.31 | PLANNED WORKLOAD DEV.32 | DURATION323 | PLANNED START DATE33 | PLANNED DUE DATE34 | ACTUALS35 | ETC36 | ESTIMATED END DATE2222 | STATUS39 | EAC37 | % WORK COMPLETE38 | INTEGRATION TESTS | Funct. Resp40 | PLANNED WORKLOAD FUNCT.41 | Dev. Resp.42 | PLANNED WORKLOAD DEV.43 | DURATION44 | PLANNED START DATE45 | PLANNED DUE DATE46 | ACTUALS47 | ETC48 | ESTIMATED END DATE22222 | STATUS51 | EAC372 | % WORK COMPLETE50 | PLANNED WORKLOAD FUNCT | PLANNED WORKLOAD DEV | LOT2 | TOTAL PLANNED WORKLOAD FUNCT. HORS M3 | TOTAL PLANNED WORKLOAD DEV. HORS M3 | [6 empty] | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
1 | 2 | PRICING | Pricing | M3 | Sales price | FIFI - PRICING - Sales price |  | INTERFACE | LOW |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Sales price - Functional Specification | Maxime | 1 | 0 | 1.3 | 2018-10-01 | 2018-10-02 |  |  | 2018-10-02 | Not Started | 1 | 0% | FIFI - PRICING - Sales price - Technical Specification | 3Kles | 0 | 0.5 | 0.65 | 2018-10-05 | 2018-10-05 |  |  | 2018-10-05 | Not Started | 0.5 | 0% | FIFI - PRICING - Sales price - DETAILED TECH SPECIFICATION | Maxime | 0.5 | 3Kles | 3 | 3.9 | 2018-10-10 | 2018-10-15 |  |  | 2018-10-15 | Not Started | 3 | 0% | FIFI - PRICING - Sales price - DTS not in M3 | Maxime | 2.5 | TBD | 4 | 5.2 | 2019-01-01 | 2019-01-15 |  |  | 2019-01-15 | Not Started | 4 | 0% | FIFI - PRICING - Sales price - Unit Tests | Maxime | 1 | 3Kles | 1 | 1.3 | 2018-10-17 | 2018-10-18 |  |  | 2018-10-18 | Not Started | 1 | 0% | FIFI - PRICING - Sales price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 2 | 2.5 | 4 | 1 | LOT | PLANNED WORKLOAD FUNCT | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
2 | 2 | PRICING | Pricing | M3 | Retail price | FIFI - PRICING - Retail price |  | INTERFACE | LOW |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Retail price - Functional Specification | Maxime | 1 | 0 | 1.3 | 2018-10-02 | 2018-10-03 |  |  | 2018-10-03 | Not Started | 1 | 0% | FIFI - PRICING - Retail price - Technical Specification | 3Kles | 0 | 0.5 | 0.65 | 2018-10-08 | 2018-10-08 |  |  | 2018-10-08 | Not Started | 0.5 | 0% | FIFI - PRICING - Retail price - DETAILED TECH SPECIFICATION | Maxime | 0.5 | 3Kles | 3 | 3.9 | 2018-10-11 | 2018-10-16 |  |  | 2018-10-16 | Not Started | 3 | 0% | FIFI - PRICING - Retail price - DTS not in M3 | Maxime | 2.5 | TBD | 4 | 5.2 | 2019-01-02 | 2019-01-16 |  |  | 2019-01-16 | Not Started | 4 | 0% | FIFI - PRICING - Retail price - Unit Tests | Maxime | 1 | 3Kles | 1 | 1.3 | 2018-10-18 | 2018-10-19 |  |  | 2018-10-19 | Not Started | 1 | 0% | FIFI - PRICING - Retail price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 2 | 2.5 | 4 | 2 | 1 | 128.5 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 21.4167; 2018-08-01: 14.2778; 2018-09-01: 21.4167; 2018-10-01: 21.4167; 2018-11-01: 21.4167; 2018-12-01: 21.4167
3 | 2 | PRICING | M3 | Pricing | Master Client | FIFI - PRICING - Master Client |  | INTERFACE | MEDIUM |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Master Client - Functional Specification | Maxime | 2 | 0 | 2.6 | 2018-10-03 | 2018-10-05 |  |  | 2018-10-05 | Not Started | 2 | 0% | FIFI - PRICING - Master Client - Technical Specification | CL TBD | 0 | 1.5 | 1.95 | 2018-10-10 | 2018-10-11 |  |  | 2018-10-11 | Not Started | 1.5 | 0% | FIFI - PRICING - Master Client - DETAILED TECH SPECIFICATION | Maxime | 1.5 | CL TBD | 6 | 7.8 | 2018-10-15 | 2018-10-24 |  |  | 2018-10-24 | Not Started | 6 | 0% | FIFI - PRICING - Master Client - DTS not in M3 | Maxime | 4.5 | TBD | 8.5 | 11.05 | 2019-01-03 | 2019-01-17 |  |  | 2019-01-17 | Not Started | 8.5 | 0% | FIFI - PRICING - Master Client - Unit Tests | Maxime | 1 | CL TBD | 1 | 1.3 | 2018-10-22 | 2018-10-23 |  |  | 2018-10-23 | Not Started | 1 | 0% | FIFI - PRICING - Master Client - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 3 | 2 | 125 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 20.8333; 2018-08-01: 13.8889; 2018-09-01: 20.8333; 2018-10-01: 20.8333; 2018-11-01: 20.8333; 2018-12-01: 20.8333
4 | 2 | PRICING | M3 | Pricing | Client Order | FIFI - PRICING - Client Order |  | INTERFACE | MEDIUM |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Client Order - Functional Specification | Maxime | 2 | 0 | 2.6 | 2018-10-08 | 2018-10-10 |  |  | 2018-10-10 | Not Started | 2 | 0% | FIFI - PRICING - Client Order - Technical Specification | CL TBD | 0 | 1.5 | 1.95 | 2018-10-15 | 2018-10-16 |  |  | 2018-10-16 | Not Started | 1.5 | 0% | FIFI - PRICING - Client Order - DETAILED TECH SPECIFICATION | Maxime | 1.5 | CL TBD | 6 | 7.8 | 2018-10-18 | 2018-10-29 |  |  | 2018-10-29 | Not Started | 6 | 0% | FIFI - PRICING - Client Order - DTS not in M3 | Maxime | 4.5 | TBD | 8.5 | 11.05 | 2019-01-04 | 2019-01-18 |  |  | 2019-01-18 | Not Started | 8.5 | 0% | FIFI - PRICING - Client Order - Unit Tests | Maxime | 1 | CL TBD | 1 | 1.3 | 2018-10-25 | 2018-10-26 |  |  | 2018-10-26 | Not Started | 1 | 0% | FIFI - PRICING - Client Order - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 4 | 3 | 42.5 | 5 | 2018-09-01 | 2019-02-01 | 2018-09-01: 8.5; 2018-10-01: 8.5; 2018-11-01: 8.5; 2018-12-01: 8.5; 2019-01-01: 8.5
5 | 1 | PLM | PLM | M3 | Item+attributes (weight, dimension, etc..) | FIFI - PLM - Item+attributes (weight, dimension, etc..) |  | INTERFACE | VERY COMPLEX |  |  | JY |  |  |  | Not Started | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-10 | 2018-10-18 |  |  | 2018-10-18 | Not Started | 5 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Technical Specification | Centric/3Kles | 0 | 4 | 5.2 | 2018-10-23 | 2018-10-30 |  |  | 2018-10-30 | Not Started | 4 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | Centric/3Kles | 12 | 15.6 | 2018-10-26 | 2018-11-19 |  |  | 2018-11-19 | Not Started | 12 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-05 | 2019-01-19 |  |  | 2019-01-19 | Not Started | 19 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Unit Tests | 3Kles (TBD) | 4 | Centric/3Kles | 4 | 5.2 | 2018-11-05 | 2018-11-12 |  |  | 2018-11-12 | Not Started | 4 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 5 |  | TOTAL |  |  |  | 0 | 0 | 0 | 42.25 | 28.1667 | 50.75 | 50.75 | 50.75 | 50.75 | 8.5 | 0
6 | 1 | PLM | PLM | M3 | Purchase Price | FIFI - PLM - Purchase Price |  | INTERFACE | VERY COMPLEX |  |  | JY |  |  |  | Not Started | FIFI - PLM - Purchase Price - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-22 | 2018-10-30 |  |  | 2018-10-30 | Not Started | 5 | 0% | FIFI - PLM - Purchase Price - Technical Specification | Centric/3Kles | 0 | 4 | 5.2 | 2018-11-05 | 2018-11-12 |  |  | 2018-11-12 | Not Started | 4 | 0% | FIFI - PLM - Purchase Price - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | Centric/3Kles | 12 | 15.6 | 2018-11-08 | 2018-11-29 |  |  | 2018-11-29 | Not Started | 12 | 0% | FIFI - PLM - Purchase Price - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-06 | 2019-01-20 |  |  | 2019-01-20 | Not Started | 19 | 0% | FIFI - PLM - Purchase Price - Unit Tests | 3Kles (TBD) | 4 | Centric/3Kles | 4 | 5.2 | 2018-11-15 | 2018-11-22 |  |  | 2018-11-22 | Not Started | 4 | 0% | FIFI - PLM - Purchase Price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 6 |  | ETP |  |  |  | 0 | 0 | 0 | 2.3472 | 1.5648 | 2.8194 | 2.8194 | 2.8194 | 2.8194 | 0.47222 | 0
7 | 1 | PLM | PLM | M3 | Product, poids, grilles, Madein, etc… | FIFI - PLM - Madein |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Madein - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-01 | 2018-10-09 |  |  | 2018-10-09 | Not Started | 5 | 0% | FIFI - PLM - Madein - Technical Specification | 3Kles | 0 | 4 | 5.2 | 2018-10-12 | 2018-10-19 |  |  | 2018-10-19 | Not Started | 4 | 0% | FIFI - PLM - Madein - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-10-17 | 2018-11-08 |  |  | 2018-11-08 | Not Started | 12 | 0% | FIFI - PLM - Madein - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-07 | 2019-01-21 |  |  | 2019-01-21 | Not Started | 19 | 0% | FIFI - PLM - Madein - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-10-24 | 2018-10-31 |  |  | 2018-10-31 | Not Started | 4 | 0% | FIFI - PLM - Madein - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 7
8 | 1 | PLM | PLM | M3 | Drop | FIFI - PLM - HS Code |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - HS Code - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-09 | 2018-10-17 |  |  | 2018-10-17 | Not Started | 5 | 0% | FIFI - PLM - HS Code - Technical Specification | 3Kles | 0 | 4 | 5.2 | 2018-10-22 | 2018-10-29 |  |  | 2018-10-29 | Not Started | 4 | 0% | FIFI - PLM - HS Code - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-10-25 | 2018-11-16 |  |  | 2018-11-16 | Not Started | 12 | 0% | FIFI - PLM - HS Code - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-08 | 2019-01-22 |  |  | 2019-01-22 | Not Started | 19 | 0% | FIFI - PLM - HS Code - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-02 | 2018-11-09 |  |  | 2018-11-09 | Not Started | 4 | 0% | FIFI - PLM - HS Code - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 8
9 | 1 | PLM | PLM | M3 | Composition | FIFI - PLM - Composition |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Composition - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-17 | 2018-10-25 |  |  | 2018-10-25 | Not Started | 5 | 0% | FIFI - PLM - Composition - Technical Specification | 3Kles | 0 | 4 | 5.2 | 2018-10-30 | 2018-11-07 |  |  | 2018-11-07 | Not Started | 4 | 0% | FIFI - PLM - Composition - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-05 | 2018-11-26 |  |  | 2018-11-26 | Not Started | 12 | 0% | FIFI - PLM - Composition - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-09 | 2019-01-23 |  |  | 2019-01-23 | Not Started | 19 | 0% | FIFI - PLM - Composition - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-12 | 2018-11-19 |  |  | 2018-11-19 | Not Started | 4 | 0% | FIFI - PLM - Composition - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 9
10 | 1 | PLM | PLM | M3 | Offer | FIFI - PLM - Offer |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Offer - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-10-25 | 2018-11-05 |  |  | 2018-11-05 | Not Started | 5 | 0% | FIFI - PLM - Offer - Technical Specification | 3Kles | 0 | 4 | 5.2 | 2018-11-08 | 2018-11-15 |  |  | 2018-11-15 | Not Started | 4 | 0% | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-13 | 2018-12-04 |  |  | 2018-12-04 | Not Started | 12 | 0% | FIFI - PLM - Offer - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-10 | 2019-01-24 |  |  | 2019-01-24 | Not Started | 19 | 0% | FIFI - PLM - Offer - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-20 | 2018-11-27 |  |  | 2018-11-27 | Not Started | 4 | 0% | FIFI - PLM - Offer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 10
11 | 1 | PLM | PLM | M3 | Modification/Desactivation | FIFI - PLM - Offer |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Offer - Functional Specification | 3Kles (TBD) | 5 | 0 | 6.5 | 2018-11-05 | 2018-11-13 |  |  | 2018-11-13 | Not Started | 5 | 0% | FIFI - PLM - Offer - Technical Specification | 3Kles | 0 | 4 | 5.2 | 2018-11-16 | 2018-11-23 |  |  | 2018-11-23 | Not Started | 4 | 0% | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-21 | 2018-12-12 |  |  | 2018-12-12 | Not Started | 12 | 0% | FIFI - PLM - Offer - DTS not in M3 | Centric | 12 | TBD | 19 | 24.7 | 2019-01-11 | 2019-01-25 |  |  | 2019-01-25 | Not Started | 19 | 0% | FIFI - PLM - Offer - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-28 | 2018-12-05 |  |  | 2018-12-05 | Not Started | 4 | 0% | FIFI - PLM - Offer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 11
Formulas:
ESTIMATED END DATE = +[PLANNED DUE DATE]
ESTIMATED END DATE2 = +[PLANNED DUE DATE5]
ESTIMATED END DATE22 = +[PLANNED DUE DATE16]
ESTIMATED END DATE2222 = +[PLANNED DUE DATE34]
UPDATE
Note on AR3: Sophie Boisseau: 1/2 FLOW IN M3

## AGGREGATE
DELIVERABLE | COMPLEXITY | TYPE | ID | Funct. Resp. | PLANNED WORKLOAD FUNCT. | Dev. Resp. | PLANNED WORKLOAD DEV. | PLANNED START DATE | ESTIMATED END DATE | STATUS | EAC | % WORKLOAD COMPLETED

## REF
FUNCTIONAL SPECIFICATION | 18
TECHNICAL SPECIFICATION | 30
DETAILED TECH SPECIFICATION | 42
DTS NOT IN M3 | 50
UNIT TESTS | 70
Note on A3: Sophie Boisseau: 1/2 FLOW IN M3