## REPORTING_SEPTEMBRE
BU | Region | Entity | Measure ID | Priority | Target status | Target scope | Target justification (if<100%) | Status | Implementation progress rate | CISO assessment | CISO Comments | Resource allocated | Main actor | Kick-off | Initial end | Re-estimated end | <Local use 1> | <Local use 2>
AFMO | Maroc | EQDOM | OPS_ACM_01 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% | No alert |  | Not secured | Local | 4392200% | 4393600%
AFMO | Maroc | EQDOM | OPS_ACM_02 | P1 | FULL IMPLEMENTATION | 100% | - | DONE | 100% | No alert |  | Not secured | NC |  |  | 4394300%
AFMO | Maroc | EQDOM | OPS_ACM_03 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% | Alert |  |  | Hub SSI |  |  | 4394400%
AFMO | Maroc | EQDOM | OPS_ACM_04 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% | Alert | 20% déjà réalisés avant début du projet donc to be started est cohérent |  | Hub SSI |  |  | 4394500%
AFMO | Maroc | EQDOM | OPS_ACM_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 90% | Warning | Pas de projet donc pas de suivi |  | Local |  |  | 4394600%
AFMO | Maroc | EQDOM | OPS_ACM_06 | P0 | NOT APPLICABLE | - | <required> | TO BE STARTED | 0% | Warning | Pas de projet donc pas de suivi |  | Local |  |  | 4394600%
AFMO | Maroc | EQDOM | OPS_EYS_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  | Pas de projet donc pas de suivi |  | NC |  |  | 4394800%
AFMO | Maroc | EQDOM | OPS_IMN_01 | P2 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4394800%
AFMO | Maroc | EQDOM | OPS_IMN_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4395000%
AFMO | Maroc | EQDOM | OPS_IMN_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4395100%
AFMO | Maroc | EQDOM | OPS_KYI_01 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | OPS_KYI_02 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_KYI_03 | P2 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | OPS_KYI_04 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | OPS_KYI_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | VERIFIED | 100% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_KYI_06 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_02 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_04 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_06 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_07 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_08 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_09 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_01 | P2 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | VERIFIED | 100% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_04 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_05 | P2 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_06 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_01 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_02 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_03 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_04 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_05 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_06 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_07 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_08 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_09 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 70% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYE_01 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_01 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_02 | P2 | PARTIAL IMPLEMENTATION + RA | 40% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_03 | P2 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_04 | P2 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_05 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_06 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_07 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_08 | P3 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | TAA_AWA_01 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_AWA_02 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | TAA_AWA_03 | P2 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_AWA_04 | P0 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 40% |  |  |  | Local |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_AWA_05 | P0 | NOT APPLICABLE | - | <required> | VERIFIED | 100% |  |  |  | Hub SSI |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_CAW_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_GOV_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | TAA_GOV_02 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | TAA_SPC_01 | P2 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 60% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_TPT_01 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 60% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | TAA_TRN_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | DTP_ANO_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | SG ABS
AFMO | Maroc | EQDOM | DTP_ANO_02 | P2 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_BDT_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | DTP_BDT_02 | P1 | NOT APPLICABLE | - | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | DTP_BDT_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_BDT_04 | P1 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_BDT_05 | P1 | NOT APPLICABLE | - | <required> | CHECKED CISO | 100% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_BDT_06 | P1 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCT_01 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% |  |  |  | Local |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCT_02 | P2 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_DCT_03 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | DTP_DCT_04 | P2 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCL_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DCL_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_01 | P2 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_02 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | DTP_DLK_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 60% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_04 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 60% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_06 | P1 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_07 | P3 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_ENC_01 | P2 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_02 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_03 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_04 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_05 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_06 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | DTP_ENC_07 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_MON_01 | P1 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_MON_02 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | IFP_DET_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | IFP_DET_02 | P2 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | IFP_DET_03 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | Hub SSI |  |  | 4399100%
AFMO | Maroc | EQDOM | IFP_DET_04 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 80% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_02 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 40% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | IFP_PRV_01 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 30% |  |  |  | Hub SSI |  |  | 4435600%
Note on J1: (Done = 100%)

## REPORTING_DECEMBRE
BU | Region | Entity | Measure ID | Priority | Target status | Target scope | Target justification (if<100%) | Status | Implementation progress rate | CISO assessment | CISO Comments | Resource allocated | Main actor | Kick-off | Initial end | Re-estimated end | <Local use 1> | <Local use 2>
AFMO | Maroc | EQDOM | OPS_ACM_01 | P0 | PARTIAL IMPLEMENTATION + RA | 40% | BUDGET | IN PROGRESS | 20% | Warning | Ressources | Not secured |  | 4392200% | 4393600% | 4394600% | CP : Ahmad
AFMO | Maroc | EQDOM | OPS_ACM_02 | P1 |  |  | <required> | DONE | 100% | No alert |  | Not secured | NC |  |  | 4394300% |  | CP : Ahmad
AFMO | Maroc | EQDOM | OPS_ACM_03 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% | Alert |  |  | Hub SSI |  |  | 4394400%
AFMO | Maroc | EQDOM | OPS_ACM_04 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% | Alert | 20% déjà réalisés avant début du projet donc to be started est cohérent |  | Hub SSI |  |  | 4394500%
AFMO | Maroc | EQDOM | OPS_ACM_05 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% | No alert | Double checked of proof done | Secured | Local |  |  | 4394600%
AFMO | Maroc | EQDOM | OPS_ACM_06 | P0 | NOT APPLICABLE | - | <required> | TO BE STARTED | 0% | Warning | Pas de projet donc pas de suivi |  | Local |  |  | 4394600%
AFMO | Maroc | EQDOM | OPS_EYS_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  | Pas de projet donc pas de suivi |  | NC |  |  | 4394800%
AFMO | Maroc | EQDOM | OPS_IMN_01 | P2 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4394800%
AFMO | Maroc | EQDOM | OPS_IMN_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4395000%
AFMO | Maroc | EQDOM | OPS_IMN_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4395100%
AFMO | Maroc | EQDOM | OPS_KYI_01 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 50% | No alert |  |  | Local
AFMO | Maroc | EQDOM | OPS_KYI_02 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_KYI_03 | P2 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | OPS_KYI_04 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | OPS_KYI_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | VERIFIED | 100% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_KYI_06 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_02 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_04 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_05 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_06 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_07 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_08 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MIS_09 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Local |  |  | 4431700% | CF : Mohammed | CF : Mohammed
AFMO | Maroc | EQDOM | OPS_MON_01 | P2 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  | Check done | Secured | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 80% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | VERIFIED | 100% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_04 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_05 | P2 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_MON_06 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | NC |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_01 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_02 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Local |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_03 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4431700%
AFMO | Maroc | EQDOM | OPS_PAM_04 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_05 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_06 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_07 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_08 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_PAM_09 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 70% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYE_01 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_01 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_02 | P2 | PARTIAL IMPLEMENTATION + RA | 40% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_03 | P2 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_04 | P2 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 0% |  |  |  | NC |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_05 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_06 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | Local |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_07 | P0 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4470600%
AFMO | Maroc | EQDOM | OPS_SYI_08 | P3 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | TAA_AWA_01 | P0 | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_AWA_02 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | TAA_AWA_03 | P2 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_AWA_04 | P0 | PARTIAL IMPLEMENTATION + RA | 20% | <required> | IN PROGRESS | 40% |  |  |  | Local |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_AWA_05 | P0 | NOT APPLICABLE | - | <required> | VERIFIED | 100% |  |  |  | Hub SSI |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_CAW_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | TAA_GOV_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | TAA_GOV_02 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | TAA_SPC_01 | P2 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 60% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | TAA_TPT_01 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | IN PROGRESS | 60% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | TAA_TRN_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | DTP_ANO_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | SG ABS
AFMO | Maroc | EQDOM | DTP_ANO_02 | P2 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_BDT_01 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | DTP_BDT_02 | P1 | NOT APPLICABLE | - | <required> | DONE | 100% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | DTP_BDT_03 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_BDT_04 | P1 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_BDT_05 | P1 | NOT APPLICABLE | - | <required> | CHECKED CISO | 100% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_BDT_06 | P1 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCT_01 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% |  |  |  | Local |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCT_02 | P2 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_DCT_03 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | DTP_DCT_04 | P2 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | NC |  |  | 4435600%
AFMO | Maroc | EQDOM | DTP_DCL_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DCL_02 | P1 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | TO BE STARTED | 0% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_01 | P2 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_02 | P0 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | Local
AFMO | Maroc | EQDOM | DTP_DLK_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 60% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_04 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_05 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_06 | P1 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_DLK_07 | P3 | NOT APPLICABLE | - | <required> | NO PROJECT | 0% |  |  |  | NC
AFMO | Maroc | EQDOM | DTP_ENC_01 | P2 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_02 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_03 | P0 | FULL IMPLEMENTATION | 100% | - | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_04 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_05 | P0 | FULL IMPLEMENTATION | 100% | - | VERIFIED | 100% |  | LOD2 done |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_ENC_06 | P0 | PARTIAL IMPLEMENTATION + RA | 40% | <required> | IN PROGRESS | 10% |  |  | Secured | Local | 4447600% | 4453700%
AFMO | Maroc | EQDOM | DTP_ENC_07 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | CHECKED CISO | 100% |  |  |  | Local |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_MON_01 | P1 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4472100%
AFMO | Maroc | EQDOM | DTP_MON_02 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  |  |  | SG ABS |  |  | 4472100%
AFMO | Maroc | EQDOM | IFP_DET_01 | P0 | RISK ACCEPTED | 0% | <required> | NO PROJECT | 0% |  |  |  | Hub SSI
AFMO | Maroc | EQDOM | IFP_DET_02 | P2 | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  |  |  | NC |  |  | 4399100%
AFMO | Maroc | EQDOM | IFP_DET_03 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | DONE | 100% |  |  |  | Hub SSI |  |  | 4399100%
AFMO | Maroc | EQDOM | IFP_DET_04 | P0 | PARTIAL IMPLEMENTATION + RA | 80% | <required> | CHECKED CISO | 100% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_01 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 80% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_02 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | TO BE STARTED | 0% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | IFP_GOV_03 | P0 | PARTIAL IMPLEMENTATION + RA | 60% | <required> | IN PROGRESS | 40% |  |  |  | Hub SSI |  |  | 4472100%
AFMO | Maroc | EQDOM | IFP_PRV_01 | P0 | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 30% |  |  |  | Hub SSI |  |  | 4435600%
AFMO | Maroc | EQDOM | SPL_PMD_07 | P1 | PARTIAL IMPLEMENTATION + RA | 60% | edezc | IN PROGRESS | 20% |  |  |  | Hub SSI |  |  | 4399800%
Note on J1: (Done = 100%)

## DATA
C2-Confidential
File_Version | Security packs EN | Security packs FR | Acronym / Acronyme | Status_Choice | Rank | Months overdelay | # | Entity | BU | Region | Country | Level | Language | Pack EN | Pack FR | Theme EN | Theme FR | Acronym theme | Acronym combined | ID
5.0 | Advanced protection | Protection avancée | ADP | NO PROJECT | 1 | 3 | 1 | BDK | EURO | - | Allemagne | 3 | EN | Advanced protection | Protection avancée | Analytic security | Sécurité analytique | ANS | ADP_ANS | Advanced protectionAnalytic security
| Cloud | Cloud | CLD | TO BE STARTED | 2 |  | 2 | BDP | AFMO | Outre-mer | Polynésie française | 3 | FR | Advanced protection | Protection avancée | Cyber Incident | Incident cyber | CYI | ADP_CYI | Advanced protectionCyber Incident
| Data protection | Protection des données | DTP | IN PROGRESS | 3 | Ressources | 3 | BFCOI | AFMO | Outre-mer | La Réunion | 3 | FR | Advanced protection | Protection avancée | Endpoint security | Sécurité des terminaux | ENS | ADP_ENS | Advanced protectionEndpoint security
| Exposed services | Services exposés | EXS | DONE | 4 | Not secured | 4 | BRD | EURO | - | Roumanie | 1 | EN | Advanced protection | Protection avancée | Filtering security | Sécurité des flux | FLS | ADP_FLS | Advanced protectionFiltering security
| Internal fraud protection | Protection contre la fraude interne | IFP | CHECKED CISO | 5 | Secured | 5 | BRD Finance | EURO | - | Roumanie | 3 | EN | Advanced protection | Protection avancée | Sensitive Assets | Actifs sensibles | SEA | ADP_SEA | Advanced protectionSensitive Assets
| Operational security | Sécurité opérationnelle | OPS | VERIFIED | 6 |  | 6 | CGI Finance | EURO | - | France | 2 | FR | Advanced protection | Protection avancée | User Security | Sécurité des utilisateurs | UZS | ADP_UZS | Advanced protectionUser Security
| Security in product lifecycle | Sécurité dans le cycle de vie produit | SPL |  |  |  | 7 | EQDOM | AFMO | Maroc | Maroc | 3 | FR | Cloud | Cloud | Cloud Management | Gestion du Cloud | MNG | CLD_MNG | CloudCloud Management
| Third parties and supply chain | Tiers et supply chain | TPS |  |  |  | 8 | Essox | EURO | - | République Tchèque | 3 | EN | Cloud | Cloud | Availability | Disponibilité | AVA | CLD_AVA | CloudAvailability
| Training and awareness | Formation et sensibilisation | TAA | Target_Status_Choice | Value | Target of scope | 9 | Fiditalia | EURO | - | Italie | 2 | EN | Cloud | Cloud | IAM | IAM | IAM | CLD_IAM | CloudIAM
|  |  |  | RISK ACCEPTED | 0% | - | 10 | Hanseatic Bank | EURO | - | Allemagne | 3 | EN | Cloud | Cloud | Data Protection | Protection des données | DTP | CLD_DTP | CloudData Protection
|  |  |  | PARTIAL IMPLEMENTATION + RA | 1% | 0% | 11 | KB | EURO | - | République Tchèque | 1 | EN | Cloud | Cloud | Incident management | Gestion des incidents | IMN | CLD_IMN | CloudIncident management
CISO assessment | Pack | Acronyme | Order index | FULL IMPLEMENTATION | 100% | 20% | 12 | ROSBANK | RUSS | - | Russie | 1 | EN | Cloud | Cloud | Services access | Accès aux services | SAC | CLD_SAC | CloudServices access
No alert | Operational security | OPS | 1 | NOT APPLICABLE | - | 40% | 13 | Rusfinance | RUSS | - | Russie | 2 | EN | Cloud | Cloud | Architecture | Architecture | ARC | CLD_ARC | CloudArchitecture
Warning | Training and awareness | TAA | 2 |  |  | 60% | 14 | SGA | AFMO | Méditerranée | Algérie | 2 | FR | Cloud | Cloud | Access filtering | Filtrage d'accès | ACF | CLD_ACF | CloudAccess filtering
Alert | Data protection | DTP | 3 | RAF_Status_Choice | Rank | 80% | 15 | SGABS | AFMO | COO | Maroc | 1 | FR | Cloud | Cloud | Infrastructure security | Sécurité de l'infrastructure | IFS | CLD_IFS | CloudInfrastructure security
| Internal fraud protection | IFP | 4 | NOT APPLICABLE | 1 | 100% | 16 | SGB | AFMO | Afrique de l'ouest | Bénin | 3 | FR | Cloud | Cloud | Log management | Gestion des traces | LGM | CLD_LGM | CloudLog management
| Advanced protection | ADP | 5 | TO BE DONE | 2 |  | 17 | SGBF | AFMO | Afrique de l'ouest | Burkina Faso | 3 | FR | Data protection | Protection des données | Data cartography | Cartographie des données | DCT | DTP_DCT | Data protectionData cartography
| Exposed services | EXS | 6 | TO BE UPDATED | 3 |  | 18 | SGBGE | AFMO | Afrique centrale et Australie | Guinée équatoriale | 3 | FR | Data protection | Protection des données | Data classification | Classification des données | DCL | DTP_DCL | Data protectionData classification
| Cloud | CLD | 7 | IN PROGRESS | 4 |  | 19 | SGC | AFMO | Afrique centrale et Australie | Congo | 3 | FR | Data protection | Protection des données | Monitoring | Monitoring | MON | DTP_MON | Data protectionMonitoring
| Third parties and supply chain | TPS | 8 | SUBMITTED | 5 |  | 20 | SGCAM | AFMO | Afrique centrale et Australie | Cameroun | 3 | FR | Data protection | Protection des données | Data leakage | Fuite de données | DLK | DTP_DLK | Data protectionData leakage
| Security in product lifecycle | SPL | 9 | VALIDATED | 6 |  | 21 | SGCB | AFMO | Outre-mer | Nouvelle Calédonie | 3 | FR | Data protection | Protection des données | Encryption | Chiffrement | ENC | DTP_ENC | Data protectionEncryption
[7 empty] | 22 | SGCI | AFMO | Afrique de l'ouest | SGCI | 3 | FR | Data protection | Protection des données | Anonymisation | Anonymisation | ANO | DTP_ANO | Data protectionAnonymisation
[7 empty] | 23 | SGGH | AFMO | Afrique de l'ouest | Ghana | 3 | EN | Data protection | Protection des données | Big Data | Big data | BDT | DTP_BDT | Data protectionBig Data
[7 empty] | 24 | SGGN | AFMO | Afrique de l'ouest | Guinée | 3 | FR | Exposed services | Services exposés | Secure Hosting Baseline | Hébergement de référence sécurisé | SHB | EXS_SHB | Exposed servicesSecure Hosting Baseline
[7 empty] | 25 | SGM | AFMO | Afrique de l'ouest | Mauritanie | 3 | FR | Exposed services | Services exposés | Customer Identity Mangement | Gestion de l'identité des clients | CIM | EXS_CIM | Exposed servicesCustomer Identity Mangement
[7 empty] | 26 | SGMA | AFMO | Maroc | Maroc | 2 | FR | Exposed services | Services exposés | DNS security | Sécurité du DNS | DNS | EXS_DNS | Exposed servicesDNS security
[7 empty] | 27 | SGMADA | AFMO | Afrique centrale et Australie | Madagascar | 2 | FR | Exposed services | Services exposés | E-fraud | E-fraud | EFD | EXS_EFD | Exposed servicesE-fraud
[7 empty] | 28 | SGMZ | AFMO | Afrique centrale et Australie | Mozambique | 3 | EN | Exposed services | Services exposés | Internet application security | Sécurité des applications web | IAS | EXS_IAS | Exposed servicesInternet application security
[7 empty] | 29 | SGSN | AFMO | Afrique de l'ouest | Sénégal | 3 | FR | Exposed services | Services exposés | Mobile Banking Security | Sécurité des services bancaires mobile | MBS | EXS_MBS | Exposed servicesMobile Banking Security
[7 empty] | 30 | SGT | AFMO | Afrique centrale et Australie | Tchad | 3 | FR | Exposed services | Services exposés | Open Banking and API security | Open Banking et sécurité des API | OBS | EXS_OBS | Exposed servicesOpen Banking and API security
[7 empty] | 31 | SGTG | AFMO | Afrique de l'ouest | Togo | 3 | FR | Exposed services | Services exposés | Secure usage of internet services | Utilisation sécurisée des services web | SUI | EXS_SUI | Exposed servicesSecure usage of internet services
[7 empty] | 32 | UIB | AFMO | Méditerranée | Tunisie | 3 | FR | Internal fraud protection | Protection contre la fraude interne | Governance | Gouvernance | GOV | IFP_GOV | Internal fraud protectionGovernance
[14 empty] | Internal fraud protection | Protection contre la fraude interne | Prevention | Prévention | PRV | IFP_PRV | Internal fraud protectionPrevention
[8 empty] | 32 | 3 | 7 | 26 |  |  | Internal fraud protection | Protection contre la fraude interne | Detection | Détection | DET | IFP_DET | Internal fraud protectionDetection
[14 empty] | Operational security | Sécurité opérationnelle | Know your IT | Connaître son SI | KYI | OPS_KYI | Operational securityKnow your IT
[14 empty] | Operational security | Sécurité opérationnelle | Incident management | Gestion des incidents | IMN | OPS_IMN | Operational securityIncident management
[14 empty] | Operational security | Sécurité opérationnelle | Access management | Gestion des accès | ACM | OPS_ACM | Operational securityAccess management
[14 empty] | Operational security | Sécurité opérationnelle | Privileged Access management | Gestion des accès à privilèges | PAM | OPS_PAM | Operational securityPrivileged Access management
[14 empty] | Operational security | Sécurité opérationnelle | Secure your IT | Sécuriser son SI | SYI | OPS_SYI | Operational securitySecure your IT
[14 empty] | Operational security | Sécurité opérationnelle | Secure your Endpoints | Protéger ces postes de travail | SYE | OPS_SYE | Operational securitySecure your Endpoints
[14 empty] | Operational security | Sécurité opérationnelle | Maintain IT Security | Maintenance de la sécurité du SI | MIS | OPS_MIS | Operational securityMaintain IT Security
[14 empty] | Operational security | Sécurité opérationnelle | Monitoring | Monitoring | MON | OPS_MON | Operational securityMonitoring
[14 empty] | Operational security | Sécurité opérationnelle | Evaluate your Security | Evaluer la sécurité | EYS | OPS_EYS | Operational securityEvaluate your Security
[14 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Project Methodology | Méthodologie Projet | PMD | SPL_PMD | Security in product lifecycleProject Methodology
[14 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Agile Project Methodology | Méthodologie Projet Agile | APM | SPL_APM | Security in product lifecycleAgile Project Methodology
[14 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Dev. Security | Sécurité des développements | DVS | SPL_DVS | Security in product lifecycleDev. Security
[14 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Devops | Devops | DVO | SPL_DVO | Security in product lifecycleDevops
[14 empty] | Third parties and supply chain | Tiers et supply chain | Third Parties Management | Gestion des tiers | TPM | TPS_TPM | Third parties and supply chainThird Parties Management
[14 empty] | Third parties and supply chain | Tiers et supply chain | Third Parties Access | Accès des tiers | TPA | TPS_TPA | Third parties and supply chainThird Parties Access
[14 empty] | Third parties and supply chain | Tiers et supply chain | Monitoringand control | Suivi et contrôle | MNC | TPS_MNC | Third parties and supply chainMonitoringand control
[14 empty] | Third parties and supply chain | Tiers et supply chain | End of the contract | Fin de contrat | EOC | TPS_EOC | Third parties and supply chainEnd of the contract
[14 empty] | Training and awareness | Formation et sensibilisation | Governance | Gouvernance | GOV | TAA_GOV | Training and awarenessGovernance
[14 empty] | Training and awareness | Formation et sensibilisation | Training | Formation | TRN | TAA_TRN | Training and awarenessTraining
[14 empty] | Training and awareness | Formation et sensibilisation | Awareness | Sensibilisation | AWA | TAA_AWA | Training and awarenessAwareness
[14 empty] | Training and awareness | Formation et sensibilisation | Specific comunication | Communication spécifique | SPC | TAA_SPC | Training and awarenessSpecific comunication
[14 empty] | Training and awareness | Formation et sensibilisation | Customer awareness | Sensibilisation du client | CAW | TAA_CAW | Training and awarenessCustomer awareness
[14 empty] | Training and awareness | Formation et sensibilisation | Third Parties | Tiers | TPT | TAA_TPT | Training and awarenessThird Parties
[14 empty] | 9 |  | 57

## CALCULATION
C2-Confidential
PACK | END | Before DARWIN² | NO PROJECT P0 | NO PROJECT P1 | NO PROJECT P2&P3 | NO PROJECT | TO BE STARTED P0 | TO BE STARTED P1 | TO BE STARTED P2&P3 | TO BE STARTED | IN PROGRESS P0 | IN PROGRESS P1 | IN PROGRESS P2&P3 | IN PROGRESS | DONE P0 | DONE P1 | DONE P2&P3 | DONE | CHECKED CISO P0 | CHECKED CISO P1 | CHECKED CISO P2&P3 | CHECKED CISO | VERIFIED P0 | VERIFIED P1 | VERIFIED P2&P3 | VERIFIED | PR_EX P0 | PR_EX P1 | PR_EX P2&P3 | TOTAL PR_EX | RISK ACCEPTED P0 | RISK ACCEPTED P1 | RISK ACCEPTED P2&3 | RISK ACCEPTED (FULL MEASURE) | PARTIAL IMPLEMENTATION + RA P0 | PARTIAL IMPLEMENTATION + RA P1 | PARTIAL IMPLEMENTATION + RA P2&P3 | PARTIAL IMPLEMENTATION + RA | RISK ACCEPTANCE | FULL IMPLEMENTATION | NOT APPLICABLE | LEFT P0 | LEFT P1 | LEFT P2&3 | TOTAL Impl | WIP | COMPLETED P0 | COMPLETED P1 | COMPLETED P2&3 | COMPLETED | COMPLETED % | IN SCOPE | IN SCOPE % | % RISK ACCEPTED | Risk situation comment | RISK STATUS (Alert/Warning) | DELTA (No risk/empty) | TARGET IMPL | CURRENT IMPL DONE | CURRENT IMPL CHECKED CISO & VERIFIED | WIP % | CURRENT IMPL | 2020 IMLP | 2020 COMMITTED | % 2020 COMMITTED | 2021 IMPL | 2021 COMMITTED | % 2021 COMMITTED | 2022 IMPL | 2022 COMMITTED | % 2022 COMMITTED | COMMITTED | Total IMPLEMENTED | DELTA
Operational security | 100% | 20% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Training and awareness | 100% | 15% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Data protection | 100% | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Internal fraud protection | 100% | 7% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Advanced protection | 100% | 8% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Exposed services | 100% | 9% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Cloud | 100% | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Third parties and supply chain | 100% | 11% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Security in product lifecycle | 100% | 12% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | 0% | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0% | 0%
Overview |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! |  | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | #REF! | #REF! | 0% | 0% | 0 | 0%
PACK |  | Target Nb | Target Global Status | 2020 | 2021 | 2022
Operational security | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Operational security | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Training and awareness | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Training and awareness | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Data protection | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Data protection | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Internal fraud protection | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Internal fraud protection | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Advanced protection | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Advanced protection | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Exposed services | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Exposed services | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Cloud | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Cloud | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Third parties and supply chain | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Third parties and supply chain | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Security in product lifecycle | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Security in product lifecycle | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Total | P0 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope
Total | P1 | #REF! | 0 in scope | 0 in scope | 0 in scope | 0 in scope

## DASHBOARD_2 (hidden)
VER 5.0
#REF!
Operational security |  |  |  | Training and awareness |  |  |  | Operational security |  |  |  | Training and awareness |  |  |  | Global rollout of security packs
Global progress |  |  |  | Global progress |  |  |  | Global progress |  |  |  | Global progress
Certified |  |  | #REF! | Certified |  |  | #REF! | Certified |  |  | #REF! | Certified |  |  | #REF!
Completed |  |  | #NAME? | Completed |  |  | #NAME? | Completed |  |  | #REF! | Completed |  |  | #NAME?
In progress |  |  | #NAME? | In progress |  |  | #NAME? | In progress |  |  | #REF! | In progress |  |  | #NAME?
To be started |  |  | #NAME? | To be started |  |  | #NAME? | To be started |  |  | #REF! | To be started |  |  | #NAME?
Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF!
#REF! | / | #REF! |  | #REF! | / | #REF! |  | #REF! | / | #REF! |  | #REF! | / | #REF!
Measures distribution |  |  |  | Measures distribution |  |  |  | Measures distribution |  |  |  | Measures distribution
Current situation |  |  |  | Current situation |  |  |  | Current situation |  |  |  | Current situation |  |  |  |  | Entity remarks
#REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF!
#REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0
0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Data protection |  |  |  | Internal fraud protection |  |  |  | Advanced protection |  |  |  | Exposed services
Global progress |  |  |  | Global progress |  |  |  | Global progress |  |  |  | Global progress
Certified |  |  | #REF! | Certified |  |  | #REF! | Certified |  |  | #REF! | Certified |  |  | #REF!
Completed |  |  | #REF! | Completed |  |  | #REF! | Completed |  |  | #NAME? | Completed |  |  | #NAME?
In progress |  |  | #REF! | In progress |  |  | #REF! | In progress |  |  | #NAME? | In progress |  |  | #NAME?
To be started |  |  | #REF! | To be started |  |  | #REF! | To be started |  |  | #NAME? | To be started |  |  | #NAME?
Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF! | Risk accepted by entity |  |  | #REF!
#REF! | / | #REF! |  | #REF! | / | #REF! |  | #REF! | / | #REF! |  | #REF! | / | #REF!
Measures distribution |  |  |  | Measures distribution |  |  |  | Measures distribution |  |  |  | Measures distribution
Current situation |  |  |  | Current situation |  |  |  | Current situation |  |  |  | Current situation
#REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF!
#REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF!
0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0

## Feuil1
Measure ID | Target status | Target scope | Target justification (if<100%) | Status | Implementation progress rate | CISO assessment | CISO Comments | Main actor | Re-estimated end | <Local use 1> | <Local use 2> | Resource allocated | Kick-off | Initial end | BU | Region | Entity | Priority
DTP_DLK_05 | PARTIAL IMPLEMENTATION + RA --> FULL IMPLEMENTATION | Evolution 20,00% | <required> --> -
DTP_ENC_05 |  |  |  | CHECKED CISO --> VERIFIED |  |  | --> LOD2 done
DTP_ENC_06 | NOT APPLICABLE --> PARTIAL IMPLEMENTATION + RA | Evolution 40,00% |  | NO PROJECT --> IN PROGRESS | Evolution 10,00% | [6 empty] | --> Secured | --> 07/10/2021 | --> 07/12/2021
OPS_ACM_01 | NOT APPLICABLE --> PARTIAL IMPLEMENTATION + RA | Evolution 40,00% | <required> --> BUDGET | NO PROJECT --> IN PROGRESS | Evolution 20,00% | No alert --> Warning | --> Ressources | Local --> | --> 25/04/2020 | --> CP : Ahmad
OPS_ACM_02 | FULL IMPLEMENTATION --> | Evolution -100,00% | - --> <required> | [7 empty] | --> CP : Ahmad
OPS_ACM_05 | PARTIAL IMPLEMENTATION + RA --> FULL IMPLEMENTATION | Evolution 20,00% | <required> --> - | IN PROGRESS --> DONE | Evolution 10,00% | Warning --> No alert | Pas de projet donc pas de suivi --> Double checked of proof done |  |  |  |  | --> Secured
OPS_KYI_01 | NOT APPLICABLE --> FULL IMPLEMENTATION | Evolution 100,00% | <required> --> - | NO PROJECT --> IN PROGRESS | Evolution 50,00% | --> No alert
OPS_MIS_09 | [9 empty] | --> CF : Mohammed | --> CF : Mohammed
OPS_MON_01 |  |  |  | DONE --> CHECKED CISO |  |  | --> Check done |  |  |  |  | --> Secured
SPL_PMD_07 | Nouvelle ligne - PARTIAL IMPLEMENTATION + RA | Nouvelle ligne - 60,00% | Nouvelle ligne - edezc | Nouvelle ligne - IN PROGRESS | Nouvelle ligne - 20,00% |  |  | Nouvelle ligne - Hub SSI | Nouvelle ligne - 16/06/2020 | [5 empty] | Nouvelle ligne - AFMO | Nouvelle ligne - Maroc | Nouvelle ligne - EQDOM | Nouvelle ligne - P1