## QC Lab domain migration
Project name | [5 empty] | Project start date | Project duration | Project end date
[6 empty] | 2021-06-21 | 193 | 2021-12-31
System | Server(s) | Change number | System analysis date | SOP Update request date | SOP Effective date | Start date | Duration | End date | VSI Contact | IT Tech | SME | PC Name | System ID | Retirement Plan (RP) | Status | Action | Comment | Risk/Impact | Semaine | Durée
|  |  | 2021-06-24 | 30-Aug-2021 | 2021-09-07 | 2021-09-07 | 1 | 2021-09-08 | [7 empty] | See above |  |  | 202136 | 0.14286
|  |  | 2021-06-08 | 2021-06-21 | 2021-07-19 | 2021-09-27 | 2 | 2021-09-29 | [7 empty] | 0 |  |  | 202139 | 0.28571
|  |  | 2021-06-24 | 2021-09-09 | 2021-09-27 | 2021-10-11 | 4 | 2021-10-15 | [10 empty] | 202141 | 0.57143
|  |  | 2021-06-24 | 2021-09-09 | 2021-09-27 | 2021-10-11 | 4 | 2021-10-15 | [7 empty] | 0 |  |  | 202141 | 0.57143
|  |  | 2021-06-29 | 2021-09-30 | 2021-10-18 | 2021-10-18 | 2 | 2021-10-20 | [7 empty] | #REF! |  |  | 202142 | 0.28571
|  |  | 2021-07-08 | 2021-09-29 | 2021-10-18 | 2021-10-20 | 2 | 2021-10-22 | [7 empty] | #REF! |  |  | 202142 | 0.28571
|  |  | 2021-10-14 | 2021-09-29 | 2021-10-18 | 2021-10-25 | 2 | 2021-10-27 | [7 empty] | 0 |  |  | 202143 | 0.28571
|  |  | 2021-10-20 | 2021-10-18 | 2021-11-03 | 2021-11-03 | 2 | 2021-11-05 | [7 empty] | 0 |  |  | 202144 | 0.28571
|  |  | 2021-06-25 | 2021-10-25 | 2021-11-05 | 2021-11-08 | 2 | 2021-11-10 | [7 empty] | 0 |  |  | 202145 | 0.28571
|  |  | 2021-11-03 | 2021-11-03 | 2021-11-15 | 2021-11-16 | 3 | 2021-11-19 | [7 empty] | #REF! |  |  | 202146 | 0.42857
|  |  | 2021-11-08 | 2021-11-10 | 2021-11-19 | 2021-11-22 | 1 | 2021-11-23 | [10 empty] | 202147 | 0.14286
|  |  | 2021-11-10 | 2021-11-17 | 2021-11-29 | 2021-11-23 | 3 | 2021-11-26 | [10 empty] | 202147 | 0.42857
|  |  | 2021-11-08 | 2021-11-10 | 2021-11-19 | 2021-11-25 | 1 | 2021-11-26 | [7 empty] | 0 |  |  | 202147 | 0.14286
|  |  | 2021-11-18 |  |  | 2021-11-29 | 2 | 2021-12-01 | [10 empty] | 202148 | 0.28571
|  |  | 2021-11-09 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2 | 2021-12-03 | [10 empty] | 202148 | 0.28571
|  |  | 2021-11-24 | 2021-11-29 | 2021-12-06 | 2021-12-06 | 4 | 2021-12-10 | [7 empty] | 0 |  |  | 202149 | 0.57143
|  |  | 2021-11-24 | 2021-11-29 | 2021-12-06 | 2021-12-06 | 4 | 2021-12-10 | [10 empty] | 202149 | 0.57143
|  |  | 2021-06-28 | 2021-10-15 | 2021-10-26 | 2021-12-08 | 2 | 2021-12-10 | [7 empty] | 0 |  |  | 202149 | 0.28571
|  |  | 2021-11-18 |  |  | 2021-12-13 | 4 | 2021-12-17 | [7 empty] | 0 |  |  | 202150 | 0.57143
|  |  | 2021-11-18 |  |  | 2021-12-13 | 4 | 2021-12-17 | [7 empty] | 0 |  |  | 202150 | 0.57143
|  |  | 2021-11-08 |  |  | 2022-01-03 | 2 | 2022-01-05 | [7 empty] | 0 |  |  | 202201 | 0.28571
|  |  | 2021-11-08 |  |  | 2022-01-05 | 2 | 2022-01-07 | [10 empty] | 202201 | 0.28571
|  |  | N/A | N/A | N/A | N/A | #VALUE! | N/A | [11 empty] | #VALUE!
|  |  | N/A | N/A | N/A | N/A | #VALUE! | N/A | [11 empty] | #VALUE!
[7 empty] | 0 | [8 empty] | #REF! |  |  |  | 0
[7 empty] | 0 | [12 empty] | 0
[7 empty] | 0 | [8 empty] | #REF! |  |  |  | 0
[7 empty] | 0 | [12 empty] | 0
0.14286
Formulas:
Semaine = IF(OR(Tableau24[[#This Row],[Start date]]="N/A",Tableau24[[#This Row],[Start date]]<=0),"",(YEAR(Tableau24[[#This Row],[Start date]])*100)+ISOWEEKNUM(Tableau24[[#This Row],[Start date]]))
Note on C6: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Attention le pôle Change a fait une erreur en donnant le numéro (-04 au lieu de _04)

## Liste déroulante (hidden)
Done
Not started
Postponed
On going

## Feuil1 (hidden)
EMS Lab B80 | 2021-07-07 | 31 | 2021-08-07 | Linnea Nilsson | Dima Hussein | Philippe Tourlonias | N/A | Not started | #REF!

## Request - Issue log (hidden)
Request description | Ticket # | Raised by | Assigned to | Open date | Close date | Status | Resolution | Comment