## Feuil1
| Job/ Project | ACC | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
| OSN - World of Sport | Megan | November | Amends being made as per clients feedback. | Client meeting 1st week Dec | Awaiting feedback
closed | BANG & OLUFSEN | Jon | Novmber | Davie to pick up furniture | Live
| HAUTLETIC x SoleDXB | Farah |  | Renders shared with client… | Awaiting client feedback with regards to budget and 3rd party supplying some design elements
| Pringles - Redfest | Lynsey | February | RENDERS SHARED WITH CLIENT | AWAITING FEEDBACK | DAVIE HAS THE LEAD ON IT
closed | OSN - Race to Dubai | Megan | 18.02.18 | 1st round concept being shared with client.
| DAVIDOFF | Anna | TBC | Account won | Acc Team to share debrief and amends | DAVIE OUT TILL TUESDAY
| W HOTEL | Joseph | TBC | AMENDING ACCORDING TO FEEDBACK | AWAITING FEEDBACK | DAVIE HAS THE LEAD ON IT - AWAITING CONTENT BRIEF
| H41 BRUNCH STATIONS | johny | TBC | AWAITING FEEDBACK | SEND BRIEF TO DESIGN
| SAN DISK/WD | Anna | TBC | BRIEF SHARED WITH CE TEAM | JON TO SHARE QUESTIONS | JON TO TAKE LEAD
| HARVEY NICHOLS | JO | 27.11.17 | JOB SENT | CLIENT CANCELED
LEVI'S STRAUSS
SOLE DXB
| Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
| BOOTH DESIGN | DAVIE | 30.11.17 | AWAITING CLIENT FEEDBACK
| PATCHES & CUSTOMISATION | PATTI | 30.11.17 | JON TO PROVIDE CONTACTS FOR LACOMEDI | AWAITING CLIENT FEEDBACK | LACOMEDI IS HAPPY TO JOIN - RETURNING FROM EUR. 23.11.17
SOCIAL MEDIA
| NATIONAL DAY CAMPAIGN | SARAH | 24.11.17 | CREATIVE IDEA SHARED | WAITING CLIENT FEEDBACK | ON HOLD FOR LPO
| SKINNY CAMPAIGN | SARAH | 26.11.17 | SHOOT & PRODUCTION | COORDINATE WITH LIZZIE | ON HOLD FOR LPO
| SKINNY CAMPAIGN | SARAH | 27.11.17 | INFLUENCER SEEDING REPORT | VALIDATE BY JON
| COMPETITOR REPORT | SARAH | 30.11.17 | SARAH TO SUBMIT WORK BY 27.11.17 | VALIDATE BY JON | APPROACH SHARED WITH JON
closed | TAPPER SHOOT | SARAH | TBD | INFLUENCER SEEDING REPORT | VALIDATE BY JON
| OCTOBER CALENDAR | SARAH | TBD | APPROVED
| NOVEMBER CALENDAR | SARAH | 27.11.17 | SARAH TO LIZZIE
| DECEMBER CALENDAR | SARAH | 7.11.17 | SARAH TO SUBMIT TO LIZZIE
THE BAKERY
CONTENT
| Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
| VIDEO MANIFESTO | JON/FARAH | 1.11.17 | EDIT STARTED | ABRAAJ TO CHECK IN | VINAY MADE AWARE OF POTENTIAL 2 VIDEOS
| BKRYDLY | JON | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
| COFFEE WITH | JON/FARAH | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
closed | NINE 7 ONE | FARAH | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
EVENTS
HAPPINESS & INNOVATION
| STRUCTURAL | JON | 1.11.17 | PATTY ON-BOARDING |  | SET UP MEETING WITH ABRAAJ FOR CLARITY ON SCOPE
LIGHTBLUE
| Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
| LB- MEDIA | JON | 24.10.17 | HASHTAGS SENT | SOCIAL MEDIA STRATEGY WITH DAVID & CRAIG | CONFIRM DATE OF AIR FOR SOCIAL PLATFORMS
| PR LB MEDIA | FARAH |  |  |  | NEED FEEDBACK ON MEDIA PARTNERSHIP
closed | PR 10th YEAR | FARAH
| PR APPOINTEMENTS | FARAH

## Feuil2
FALSE

## Sheet2 (hidden)
Job/ Project | ACC | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
OSN - World of Sport | Megan | November | Amends being made as per clients feedback. | Client meeting 1st week Oct
BANG & OLUFSEN | Jon | Novmber | Acc shared feedback | Re-work in process
HAUTLETIC x SoleDXB | Farah | November | Renders shared with client… | Awaiting client feedback with regards to budget and 3rd party supplying some design elements
Pringles - Redfest | Lynsey | February | RENDERS SHARED WITH CLIENT | AWAITING FEEDBACK | DAVIE HAS THE LEAD ON IT
OSN - Race to Dubai | Megan | 18.02.18 | 1st round concept being shared with client.
DAVIDOFF | Anna | TBC | Account won | Acc Team to share debrief and amends | DAVIE OUT TILL TUESDAY
W HOTEL | Joseph | TBC | AMENDING ACCORDING TO FEEDBACK | AWAITING FEEDBACK | DAVIE HAS THE LEAD ON IT - AWAITING CONTENT BRIEF
H41 BRUNCH STATIONS | johny | TBC | AWAITING FEEDBACK | SEND BRIEF TO DESIGN
SAN DISK/WD | Lucie | TBC | LUCIE TO COME BACK TO US
HARVEY NICHOLS | JO | 27.11.17 | JOB SENT | CLIENT CANCELED
LEVI'S STRAUSS
SOLE DXB
Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
BOOTH DESIGN | DAVIE | 30.11.17 | AWAITING CLIENT FEEDBACK
PATCHES & CUSTOMISATION | PATTI | 30.11.17 | JON TO PROVIDE CONTACTS FOR LACOMEDI | AWAITING CLIENT FEEDBACK | LACOMEDI IS HAPPY TO JOIN - RETURNING FROM EUR. 23.11.17
SOCIAL MEDIA
NATIONAL DAY CAMPAIGN | SARAH | 24.11.17 | CREATIVE IDEA SHARED | WAITING CLIENT FEEDBACK | ON HOLD FOR LPO
SKINNY CAMPAIGN | SARAH | 26.11.17 | SHOOT & PRODUCTION | COORDINATE WITH LIZZIE | ON HOLD FOR LPO
SKINNY CAMPAIGN | SARAH | 27.11.17 | INFLUENCER SEEDING REPORT | VALIDATE BY JON
COMPETITOR REPORT | SARAH | 30.11.17 | SARAH TO SUBMIT WORK BY 27.11.17 | VALIDATE BY JON | APPROACH SHARED WITH JON
TAPPER SHOOT | SARAH | TBD | INFLUENCER SEEDING REPORT | VALIDATE BY JON
OCTOBER CALENDAR | SARAH | TBD | APPROVED
NOVEMBER CALENDAR | SARAH | 27.11.17 | SARAH TO LIZZIE
DECEMBER CALENDAR | SARAH | 7.11.17 | SARAH TO SUBMIT TO LIZZIE
THE BAKERY
CONTENT
Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
VIDEO MANIFESTO | JON/FARAH | 1.11.17 | EDIT STARTED | ABRAAJ TO CHECK IN | VINAY MADE AWARE OF POTENTIAL 2 VIDEOS
BKRYDLY | JON | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
COFFEE WITH | JON/FARAH | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
NINE 7 ONE | FARAH | 1.01.18 | PLANNING - DESIGN LANGUAGE | VALIDATE CONCEPT WITH ABRAAJ TEAM | GET JAMES ON-BOARD
EVENTS
HAPPINESS & INNOVATION
STRUCTURAL | JON | 1.11.17 | PATTY ON-BOARDING |  | SET UP MEETING WITH ABRAAJ FOR CLARITY ON SCOPE
LIGHTBLUE
Job/ Project | OWNER | DATES | CURRENT STATUS | NEXT STEP | COMMENTS
LB- MEDIA | JON | 24.10.17 | HASHTAGS SENT | SOCIAL MEDIA STRATEGY WITH DAVID & CRAIG | CONFIRM DATE OF AIR FOR SOCIAL PLATFORMS
PR LB MEDIA | FARAH |  |  |  | NEED FEEDBACK ON MEDIA PARTNERSHIP
PR 10th YEAR | FARAH
PR APPOINTEMENTS | FARAH