## NameDB
Full Name | Name | Surname | Category | Sub-Category | Occupation | Origin | Cpy | Activity | POB | Scope | PTW | Shift | Date | Week | NPT1 | NPT2 | NPT3a | NPT3p | NPT3 | NPT4 | NPT5 | NPT6 | NPT7 | NPT8 | NPT9 | NPT10 | NPT11 | NPT12 | NPT13 | Worked
aaa 111 | aaa | 111 | [8 empty] | WP 02 |  | 2017-07-18 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
yyy 222 | yyy | 222 | Non Prod |  |  |  |  | Mob | in | SoW | WP 02 |  | 2017-06-28 | 26 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | 12
zzz 333 | zzz | 333 | Prod Indirect |  |  |  |  | Mob | in | SoW | WP 03 |  | 2017-06-27 | 26 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | 12
xxx 111 | xxx | 111 | Prod Indirect | SubCat |  | Origin | Cpy | Mob | in |  | WP 04 |  | 2017-06-04 | 23 |  |  |  |  | 0 | [10 empty] | 12
yyy 222 | yyy | 222 | Prod Indirect |  |  |  |  | Mob | in | SoW | WP 05 |  | 2017-06-25 | 26 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | 12
aaa 333 | aaa | 333 | Prod Indirect |  |  |  |  | Mob | in | SoW | WP 06 |  | 2017-06-12 | 24 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | 12
yyy 222 | yyy | 222 | Prod Indirect | Scaffold | Scaffolder |  | Ponticelli |  |  |  | WP 06 | Day | 2017-06-12 | 24 | 30 | 15 | 15 | 20 | 35 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
aaa 222 | aaa | 222 |  |  |  |  | SPIE |  |  |  | WP 06 | Day |  |  | 25 | 15 | 20 | 20 | 40 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
zzz 333 | zzz | 333 | Prod Direct | PVV | CS Piping Welder |  | Ponticelli |  |  |  | WP 06 | Day |  |  | 0 | 0 |  |  | #VALUE! | 0 | 0 | 0 | [7 empty] | #VALUE!
aaa 111 | aaa | 111 | Prod Direct | PVV | CS Piping Welder |  | Ponticelli |  |  |  | WP 06 | Day |  |  | 25 | 15 | 20 | 15 | 35 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
aaa 111 | aaa | 111 | Prod Direct | STR | Fitter |  | Ponticelli |  |  |  | WP 06 | Day |  |  | 15 | 20 | 20 | 25 | 45 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
xxx 222 | xxx | 222 | Prod Direct | E&I | Electrician Tech. |  | Ponticelli |  |  |  |  | Day |  |  | 30 | 20 | 25 | 25 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
xxx 222 | xxx | 222 | Prod Direct | E&I | Electrician Tech. |  | Ponticelli |  |  |  |  | Day |  |  | 30 | 20 | 25 | 25 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
xxx 222 | xxx | 222 | Prod Direct | E&I | Electrician Tech. |  | Ponticelli |  |  |  |  | Day |  |  | 30 | 20 | 25 | 25 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Formulas:
Week = IF([Date]="","",(WEEKNUM([Date])))

## SubCat
Shift | Cat | Origin | Cpy | Non Prod List SubCat1 | Prod Direct List SubCat2 | Prod Indirect List SubCat3 | Activity | Scope | Management Trade1 | HSE Trade2 | Preparation Trade3 | QC Trade4 | NDT Trade5 | PCC Trade6 | Other Trade7 | PVV Trade8 | STR Trade9 | E&I Trade10 | ICSS Trade11 | Scaffold Trade12 | Coating Trade13 | MEC Trade14 | HVAC Trade15 | Other Prod Trade16
Day | Non Prod | Local | Ponticelli | MNGT | PVV | Scaffold | Mob | SoW | HU Manager | HSE Spdt | Doc Control | QC Superintendant | NDT Inspector | PCC Officer | Hold | Foreman | Foreman | Foreman | Engineer | Foreman | Foreman Painter | Mechanic Foreman | Hold | Hold
Night | Prod Direct | TCN | SPIE | HSE | STR | Coating | Crew Change | Rework | E&I Manager | HSE Officer | Quantity Surveyor | QC Inspector | NDT Assistant | E&I PCC Officer |  | CS Piping Welder | Fitter | Electrician Tech. | Technician | Scaffolder | Painter | Mechanic
| Prod Indirect | Expat | Prezioso | PREP | E&I | MEC | Demob | Carry Over | Admin. Officer | Fire Watch | Work Permit Officer | QC E&I Inspector |  | PCC Assistant |  | SS Piping Welder | Rigger | Instrum. Tech. | Assistant | Rope Access/RAT | PFP Foreman | Mechanic Helper
| Vendor |  | Actemium | QC | ICSS | Other | PTW | CTR Stand-by | Field Engineer |  | Work Preparation | QC Assistant |  |  |  | Pipe Fitter | Welder | E&I Helper |  |  | PFP Applicator | Fork-lift Operator
|  |  | Yokogawa | NDT | MEC |  | Sickness | Com Assist. | Welding Spdt |  | Job Cards Officer | QC Painting/PFP |  |  |  | Fiber Glass Piping | Assistant/Labor | E&I Assistant/Labor |  |  | PFP Helper
|  |  |  | PCC | HVAC |  |  | SURF Assist. | Supervisor |  | Follow-up Leader |  |  |  |  | Rigging / Lifting Foreman | Load Testing Technician |  |  |  | Insulator
|  |  |  | Other_NP | Other |  |  | CPY Request | Lifting/Rigging Supervisor |  | Mec Preparator |  |  |  |  | Assistant / Labor
[8 empty] | FPSO Request | Pre-Comm Manager |  | E&I Preparator |  |  |  |  | Helper
[11 empty] | Material Controler |  |  |  |  | Torquing
[11 empty] | E&I Material Controler |  |  |  |  | PWHT Operator
[11 empty] | Mec Storekeeper |  |  |  |  | PWHT Assistant
[11 empty] | E&I Storekeeper |  |  |  |  | Leak Testing

## NameCheck
Full Name | Name | Surname | Mob Demob | Date | PTW Number | NPTs | Worked Hours | Check | Check Date
aaa 111 | aaa | 111
yyy 222 | yyy | 222
zzz 333 | zzz | 333
xxx 111 | xxx | 111
aaa 333 | aaa | 333
aaa 222 | aaa | 222
xxx 222 | xxx | 222
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname
Full Name | Name | Surname

## DailyDB
DAILY PERSONNEL MONITORING (Based on Productive Personnel List) - Data Base
Clé | Category | Discipline | Worker Trade | Worker Name | Origin | Week | PTW # | D Date | NPT10 Induction | Crew Change In | Crew Change Out | NPT1 Tool Box | NPT2 WP Open | NPT3 Tea Breaks | NPT4 Lunch Break | NPT5 Transfer | NPT6 Gangway | NPT7 Drills | NPT8 Weather | NPT9 CPY Stand-by | NPT10 Sunday Safety (5.75 h) | Total Hours per day | NPT12 Slack Period | NPT12 Event
L001 | Non Prod | MNGT | HU Manager | Christophe MOREL | Expat. | 0 | none | 2017-02-05 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | none
L0X1 | Non Prod | MNGT | E&I Manager | AAA | Expat. | 0 | none | 2017-02-05 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | none
L0X2 | Non Prod | Prep. | Work Permit Officer | BBB | Expat. | 0 | none | 2017-02-05 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | none
L0X3 | Prod. Direct | PIP | Piping Foreman | CCC | Expat. | 0 | PIP-004 | 2017-02-05 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | none
L0X4 | Prod. Direct | STR | Structure Foreman | DDD | Expat. | 0 | STR-005 | 2017-02-05 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | none
L0X5 | Prod. Direct | STR | Structure Fitter | EEE | Local | 0 | none | 2017-02-12 | 5 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | ???
input | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | Formule | RechercheV | input | input | input | input | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | RechercheV | Formule | Formule | input
Formulas:
Week = IF([NPT9 CPY Stand-by]="","",(WEEKNUM([NPT9 CPY Stand-by])))

## PermitDB
PERMIT TO WORK PROCESS MONITORING (Daily Input by Permit) - Data Base | [18 empty] | PERMIT TO WORK PROCESS MONITORING - CODE LIST
Clé | Number | Type | Discipline | Activity | Phase | Service | System | Sub-System | Tag | Planned Duration (h) | Man Power | Submission Date | Submission Week | Validation Date | Validation Week | Valid up to (+48h) | Rejection Date | Warning Validation | PERMIT TO WORK PROCESS MONITORING - CODE LIST
P0X1 | STR-001 | C | STR | Rigging | 1 | EHT | xx | xx | xxx | 12 | Rigger | 2017-02-10 | 6 | 2017-04-04 | 14 | 2017-04-06 |  | WARNING | Service | Phase | State | PTW | Type | Disc | PVV Activity | STR Activity | E&I Activity | ICSS Activity
P0X1 | STR-001 | C | STR | Habitat | 1 | EHT | xx | xx | xxx | 6 | Helper | 2017-02-10 | 6 | 2017-02-12 | 7 | 2017-02-14 |  |  | Gas Lift | 1 | Base Scope | 001 | A | PVV | Rigging | Rigging | Scaffolding | Connection
P0X1 | STR-003 | A | STR | Welding | 1 | EHT | xx | xx | xxx | 6 | Welder | 2017-02-10 | 6 |  | 0 |  | 2017-02-11 |  | Umbilical | 2 | Rework | 002 | B | STR | Fit-up | Fit-up/Install | Support | Test
P0X4 | STR-004 | Rout. | STR | Scaffolding | 1 | Gas Lift | xx | xx | yyy | 24 | Scaffolder | 2017-02-05 | 6 | 2017-02-07 | 6 | 2017-02-09 |  |  | EHT | 3a | Carry Over | 003 | C | ELE | Torquing | Bolting | Tray | Download
P0X5 | PIP-001 | C | PIP | Rigging | 3a | Gas Lift | xx | xx | yyy | 12 | Rigger | 2017-02-05 | 6 | 2017-02-07 | 6 | 2017-02-09 |  |  | Water Inj. | 3b | Dismantling | 004 | Rout. | INS | Welding | Welding | Pulling | Cable Pulling
P0X6 | PIP-002 | C | PIP | Torquing | 3a | Water Inj. | xx | xx | zzz | 12 | Torquing | 2017-02-12 | 7 | 2017-02-14 | 7 | 2017-02-16 |  |  | Chemical | 4a | Decommissioning | 005 |  | ICSS | NDT | NDT | Connection
[20 empty] | 4b | Reinstatement | 006 |  | TEL | TTH | Painting | Test
Auto | Input | combolist sur colonne | Combolist | Combobox based on Discipline on "Codes List" | Combolist | Combolist | Combolist | Combolist | Combolist | input | Combobox based on Discipline on "Codes List" | input | Formule | input | Formule | Formule | input | Formule |  | 5 | Change by CPY | 007 |  | PFP | Hydrotest | PFP | Eqp. Install
[20 empty] | Start-up | Extra Work | 009 |  |  | Flushing | Test | Tubing
[22 empty] | 010 |  |  | Chem. Cleaning | Scaffolding | Pre-Com
[22 empty] | 011 |  |  | Support
[22 empty] | 012 |  |  | Pre-Com
[22 empty] | 013 |  |  | Painting
[22 empty] | 014 |  |  | Insulation
Scaffolding
Formulas:
Submission Week = WEEKNUM([Submission Date])
Validation Week = IF([Validation Date]="rejected","",WEEKNUM([Validation Date]))
Valid up to (+48h) = IF([Validation Date]="","",[Validation Date]+2)
Warning Validation = IF(TODAY()>[Valid up to (+48h)],"WARNING","")

## ProgressDB
PHYSICAL PROGRESS MONITORING (Daily Input) - Data Base | [21 empty] | TAG ITEM - CODE LIST | [9 empty] | PHYSICAL PROGRESS - CODE LIST
Clé | PTW # | Discipline | Phase | Service | System | Sub-System | PID | ND | Fluid | Sector | Syst. | Seq. | Class | Item Type | Tag | Weight (kg) | Date | Week | Step | Erection Progress (on step) | Disc. Progress (on item) | TAG ITEM - CODE LIST | [9 empty] | PHYSICAL PROGRESS - CODE LIST
W0X1 | STR-001 | STR | 1 | EHT | xx | xx | xxx | xxx | xxx | TO | xxx | xxx | xxx | valve | xxx | 251 | 2017-04-08 | 14 | NDT/joint |  | 35.7675 | System | Sub-System | PID | ND | Fluid | Sector | Syst. | Seq. | Class | Tag | PVV item | PVV Scale | Step Spool | Scale Spool | Step Valve | Scale Valve | Step Pre-Com | Scale Pre-Com | STR item | STR Scale | Step Struct. | Scale Struct. | ELE item | ELE Scale | Step Trays | Scale Trays | Step Cable | Scale Cable | Step Eqp. | Scale Eqp. | INS item | INS Scale | Step Trays | Scale Trays | Step Cable | Scale Cable | Step Instrum. | Scale Instrum. | Step Cabinet | Scale Cabinet | Step Valve | Scale Valve
W0X2 | STR-001 | STR | 1 | EHT | xx | xx | xxx | xxx | xxx | HU | xxx | xxx | xxx | valve | xxx | 251 | 2017-04-07 | 14 | weld/bolt | 125.5 | 95.38 | xx | xx | 339011 | 0.5 | BI | TO | 20 | 000 | B01 | Spool | Spool | 40% | Rigging Handling | 20% | Rigging Handling | 25% | Hydro Test | 25% | All | 85% | Rigging Handling | 25% | Trays & Supports | 10% | Support Comp. | 30% | Pulled | 60% | Rigging Install | 20% | Trays & Supports | 5% | Support Comp. | 30% | Pulled | 60% | Install. | 30% | Support Compl. | 30% | Control Panel | 30%
W0X3 | STR-003 | STR | 1 | EHT | xx | xx | xxx | xxx | xxx |  | xxx | xxx | xxx | valve | xxx | 251 | 2017-04-06 | 14 | fit-up | 50.2 | 45.18 | xx | xx |  | 0.75 | CD | HU | 27 | 000 | B03 | Manual Valve | Valve/PSV | 30% | Fit-up / Pos. | 15% | Fit-up / Pos. | 15% | Air Leak Test | 25% | Pre-Com Check | 5% | Fit-up / Pos. | 20% | Cable | 20% | Trays Inst. | 50% | JB Inst. | 15% | Ass. Completed | 70% | Cable | 20% | Trays Inst. | 50% | JB Inst. | 15% | Process Connect. | 30% | Install | 60% | Air Manifold | 30%
W0X4 | STR-004 | STR | 1 | Gas Lift | xx | xx | yyy | yyy | yyy |  | yyy | yyy | yyy | valve | xxx | 251 | 2017-04-05 | 14 | rigging | 62.75 | 25.1 | xx | xx |  | 1 | CI |  | 28 | 000 | B23 |  | Instrum. | 5% | Weld/Bolt | 45% | Ass. Complt. | 60% | Int. Chem. Cleaning | 25% | Punch List Cleared | 5% | Weld/Bolt | 50% | Equipment | 40% | Earthing | 15% | Connected | 20% | Earthing | 10% | Instruments | 15% | Earthing | 15% | Connected | 20% | Calibration | 30% | Earthing | 10% | Process Connect. | 30%
W0X5 | PIP-001 | PIP | 3a | Gas Lift | xx | xx | yyy | yyy | yyy |  | yyy | yyy | yyy | valve | yyy | 176 | 2017-04-04 | 14 |  |  | 0 | xx | xx |  | 1.5 | DE |  | 29 | 000 | B49 |  | Pre-Com Check | 10% | NDT/Joint | 5% |  |  | Flushing | 25% | RFC Signed | 5% | NDT/Joint | 5% | Pre-Com Check | 15% | Covers Inst. | 5% | Tightened | 5% |  |  | Cabinet | 15% | Covers Inst. | 5% | Tightened | 5% | Earthing | 10% |  |  | Leak Test | 10%
W0X6 | PIP-002 | PIP | 3a | Water Inj. | xx | xx | zzz | zzz | zzz |  | zzz | zzz | zzz | zzz | zzz | 18 | 2017-04-01 | 13 |  |  | 0 |  |  |  | 2 | FC |  | 31 |  | B91 |  | Punch List Cleared | 10% | Support | 15% | [8 empty] | Punch List Cleared | 10% | [6 empty] | Auto. Valve | 15%
[25 empty] | 3 | FH |  | 54 |  | D50 |  | RFC Signed | 5% | [10 empty] | RFC Signed | 5% | [6 empty] | Pre-Com Check | 15%
Auto | Input | RechercheV | RechercheV | RechercheV | Combolist | Combolist | Combolist | Combolist | Combolist | Combolist | Combolist | Combolist | Combolist | Combolist | input | input | input | Auto | Combolist | Formule | Formule |  |  |  | 4 | HC |  | 71 |  | F50 | [21 empty] | Punch List Cleared | 10%
[25 empty] | 6 | HG |  | 75 |  | H03Z | [21 empty] | RFC Signed | 5%
[25 empty] | 8 | HI |  |  |  | H21P
[25 empty] | 10 | HL |  |  |  | H21Z
[25 empty] | 12 | ME |  |  |  | J03P
[25 empty] | 14 | OD |  |  |  | J03Z
[25 empty] | 16 | SI |  |  |  | J49Z
[25 empty] | 18 | SW |  |  |  | J50Z
[25 empty] | 20 | XX
24
Formulas:
Week = WEEKNUM([Date])

## Logistic Process DB
PERSONNEL LOGISTIC DATA BASE - TABLES & RELATIONS |  |  |  | EXAMPLE PERSONNEL LOGISTIC DATA BASE
| Category | saisie | Clé | Name | Category | Sub-Category | Occupation | Company | Origin | Mob Date | Mob Week | Demob Date | Demob Week
| Category | (Prod Direct, Prod Indirect….) | 01 | AAA | Non Prod | Management | HU Leader | Ponticelli | Expat | 2017-05-02 | 18 |  | 0
|  |  | 02 | BBB | Non Prod | Management | E&I HU Leader | SPIE | Expat | 2017-05-03 | 18 |  | 0
|  |  | 03 | CCC | Non Prod | HSE | HSE Spdt | Ponticelli | Expat | 2017-05-04 | 18 |  | 0
| Sub-Category | saisie | 04 | DDD | Non Prod | HSE | HSE Officer | Ponticelli | Expat | 2017-05-05 | 18 |  | 0
PERSONNEL | Prod Direct | (worker discipline list) | 05 | EEE | Non Prod | HSE | Fire watch | Ponticelli | Local | 2017-05-06 | 18 |  | 0
Name | Prod Indirect |  | 06 | FFF | Non Prod | Preparation | WP Coordinator | Ponticelli | Expat | 2017-05-07 | 19 |  | 0
Category | Non Prod |  | 07 | GGG | Non Prod | Preparation | Work Preparation | Ponticelli | Expat | 2017-05-08 | 19 |  | 0
Sub-Category |  |  | 08 | HHH | Non Prod | Logistic | Materiel Logistic | Ponticelli | Local | 2017-05-09 | 19 |  | 0
Occupation | Occupation | saisie | 09 | III | Non Prod | Logistic | E&I Materiel Logistic | SPIE | Local | 2017-05-10 | 19 |  | 0
Company | Management | (worker function list) | 10 | JJJ | Non Prod | Preparation | Welding Chief | Ponticelli | Expat | 2017-05-11 | 19 |  | 0
Origin | Preparation |  | 11 | KKK | Non Prod | QC & NDT | Pre-Com Leader | Ponticelli | Expat | 2017-05-12 | 19 |  | 0
Mob date | HSE |  | 12 | LLL | Non Prod | Management | Supervisor E&I | SPIE | Expat | 2017-05-13 | 19 |  | 0
Demob date | QC & NDT |  | 13 | MMM | Non Prod | Management | Spdt Mechanical | Ponticelli | Expat | 2017-05-14 | 20 |  | 0
| Logistic |  | 14 | NNN | Non Prod | Management | Piping Supervisor | Ponticelli | Expat | 2017-05-15 | 20 |  | 0
| Supervision |  | 15 | OOO | Prod Direct | PIP | Piping Foreman | Ponticelli | Local | 2017-05-16 | 20 |  | 0
| ….. |  | 16 | PPP | Prod Direct | PIP | Cs Welder | Ponticelli | Local | 2017-05-17 | 20 |  | 0
|  |  | 17 | QQQ | Prod Direct | PIP | SS Welder | Ponticelli | Local | 2017-05-18 | 20 |  | 0
| Company | saisie | 18 | RRR | Prod Direct | PIP | Pipe Fitter | Ponticelli | Local | 2017-05-19 | 20 |  | 0
| cpy | (Ponticelli, SPIE, Prezioso…) | 19 | SSS | Prod Direct | PIP | Helper | Ponticelli | Local | 2017-05-20 | 20 |  | 0
|  |  | 20 | TTT | Prod Direct | E&I | Foreman E&I | SPIE | Expat | 2017-05-21 | 21 |  | 0
|  |  | 21 | UUU | Prod Direct | INS | Instrum Techn. | SPIE | Expat | 2017-05-22 | 21 |  | 0
| Origin | saisie | 22 | VVV | Prod Direct | INS | E&I Helper | SPIE | Local | 2017-05-23 | 21 |  | 0
| Origin | (Local, TCN, Expat) | 23 | WWW | Prod Indirect | Scaffolding | Scaffolder | Prezioso | Local | 2017-05-24 | 21 |  | 0
|  |  | 24 | XXX | Prod Indirect | Painting | Painter | Prezioso | Local | 2017-05-25 | 21 |  | 0
EXAMPLE PERSONNEL LOGISTIC Reporting per Day and Week
|  |  | Category | (Tous)
|  |  | Week | 21
|  |  | POB per Day | Days
|  |  | By Occupation / Trade | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | Total POB
|  |  | E&I | 1 |  |  |  |  | 1
|  |  | INS |  | 1 | 1 |  |  | 2
|  |  | Painting |  |  |  |  | 1 | 1
|  |  | Scaffolding |  |  |  | 1 |  | 1
|  |  | Total POB | 1 | 1 | 1 | 1 | 1 | 5
|  |  | POB by Category | Categories
|  |  | Week | Non Prod | Prod Direct | Prod Indirect | Total POB
|  |  | 18 | 5 |  |  | 5
|  |  | 19 | 7 |  |  | 7
|  |  | 20 | 2 | 5 |  | 7
|  |  | 21 |  | 3 | 2 | 5
|  |  | Total POB | 14 | 8 | 2 | 24
Formulas:
Mob Week = WEEKNUM([Mob Date])
Demob Week = WEEKNUM([Demob Date])

## PTW Process DB
| PTW Validation Process DATA BASE - TABLES & RELATIONS |  |  |  | EXAMPLE of PTW Validation Process DATA BASE | [20 empty] | 2017-07-18 | 2017-07-01 | 1900-01-05 | année | 2017 | 2017-05-15
[27 empty] | 2017-07-31 |  | format | nombre
|  |  |  | Clé | Number | Scope | Type | Discipline | Description | Phase | Service | System | Sub-System | Tag | Quantity | Duration | Review Date | Review Week | Submit Date | Submit Week | Return Date | Return Week | Status | Open Date | Open Week | format | jj | jjjj | WEEK | 20 | 2017-05-15 | 2017-05-16 | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2017-05-20
|  | Type | saisie | 01 | PTW-001 | Base sow | C | SCF | scaffold | 1 | EHT | 61 | 6101 | xxxxxxxxxxx | 300 | 172 | [6 empty] | under review
|  | PTW type | (type A, type B, Cold) | 02 | PTW-002 | Base sow | C | ELE | cable trays install | 1 | EHT | 61 | 6101 | xxxxxxxxxxx | 150 | 224 | [6 empty] | Submitted | [5 empty] | PTW under review with CONTRACTOR
|  |  |  | 03 | PTW-003 | Base sow | C | ELE | cable pulling | 1 | EHT | 61 | 6101 | xxxxxxxxxxx | 450 | 450 | [6 empty] | Submitted | [5 empty] | Type A (Hot Work Naked Flame) |  | 1 | 1 | 0 | 0 | 1 | 0
Scope | PTW Validation Process | Phase | saisie | 04 | PTW-004 | Base sow | C | SCF | scaffold | 1 | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 25 | 80 | [6 empty] | Submitted | [5 empty] | Type B (Hot Work) |  | 0 | 0 | 0 | 0 | 0 | 0
Scope | Number | Offshore Phase | (1, 2, 3a, 3b, 4a, 4b, 5) | 05 | PTW-005 | Base sow | C | SCF | habitacle | 1 | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 20 | 40 | [6 empty] | Submitted | [5 empty] | Type C (Cold Work) |  | 2 | 3 | 1 | 2 | 3 | 2
| Scope |  |  | 06 | PTW-006 | Base sow | A | STR | piping penetration | 1 | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 15 | 120 | [6 empty] | Submitted | [5 empty] | Total PTW under Review |  | 3 | 4 | 1 | 2 | 4 | 2
saisie | Type |  |  | 07 | PTW-007 | Base sow | C | PIP | spool erection | 3a | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 45 | 75 | [6 empty] | Accepted
SoW | Phase | Service | saisie | 08 | PTW-008 | Base sow | C | PIP | spool erection | 3a | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 32 | 56 | [6 empty] | Accepted | [5 empty] | PTW submitted to FPSO
CTR stand-by | Service | Service | (Water Inj., Gas Lift, Chemical, EHT…) | 09 | PTW-009 | Base sow | C | PIP | spool erection | 3a | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 65 | 90 | [6 empty] | Accepted | [5 empty] | Type A (Hot Work Naked Flame) |  | 1 | 0 | 1 | 1 | 0 | 0
Rework | System |  |  | 10 | PTW-010 | Base sow | C | PIP | support | 3a | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 12 | 24 | [6 empty] | Accepted | [5 empty] | Type B (Hot Work) |  | 1 | 0 | 0 | 0 | 0 | 0
Carry Over | Sub-System |  |  | 11 | PTW-011 | Rework | C | PIP | support | 3a | Gas Lift | 31 | 3101 | xxxxxxxxxxx | 12 | 12 | [6 empty] | Accepted | [5 empty] | Type C (Cold Work) |  | 3 | 2 | 2 | 3 | 1 | 2
COM Assist. | Discipline | System | saisie | 12 | PTW-012 | Base sow | C | PIP | spool erection | 4a | Water Inj. | 54 | 5401 | xxxxxxxxxxx | 38 | 60 | [6 empty] | Accepted | [5 empty] | Total PTW submitted |  | 5 | 2 | 3 | 4 | 1 | 2
SURF Assist. | Tag | System | (20, 27, 28, 29, 31, 54, 71, 75))
CPY Request | Weight | Description | [26 empty] | PTW validated
FPSO Request | Planned Duration | [27 empty] | Type A (Hot Work Naked Flame) |  | 1 | 1 | 1 | 0 | 1 | 1
| Review Date | Sub-System | saisie | [25 empty] | Type B (Hot Work) |  | 0 | 0 | 1 | 0 | 0 | 0
| Submit Date | Sub-System | to be defined with commissioning team | [25 empty] | Type C (Cold Work) |  | 1 | 2 | 3 | 2 | 2 | 3
| Return Date | [27 empty] | Total validated |  | 2 | 3 | 5 | 2 | 3 | 4
Return Status
| Open Date | Discipline | saisie | [25 empty] | PTW open
|  | Discipline | (PIP, STR, ELE, INS, ICSS, PAI, SCF...) | [25 empty] | Type A (Hot Work Naked Flame) |  | 1 | 0 | 1 | 1 | 1 | 0 | 4
|  | Description | [26 empty] | Type B (Hot Work) |  | 1 | 0 | 0 | 0 | 1 | 0 | 2
[29 empty] | Type C (Cold Work) |  | 4 | 6 | 5 | 4 | 3 | 2 | 24
|  | Item Data | (Refer to Data Base "Tag & Weight") | [25 empty] | Total open |  | 6 | 6 | 6 | 5 | 5 | 2
EXAMPLE of PTW Validation Process Reporting per Day and Week
[29 empty] | Week | 15 | 16 | 17 | 18 | 19 | 20 | 21
[29 empty] | Type A | 2 | 0 | 0 | 1 | 2 | 4 | 0
[29 empty] | Type B | 0 | 0 | 0 | 1 | 0 | 2 | 0
[29 empty] | Type C | 8 | 10 | 11 | 9 | 8 | 6 | 10

## Daily Activity DB
NPT Time DATA BASE - TABLES & RELATIONS |  |  |  | EXAMPLE of NPT Time DATA BASE | [19 empty] | Année = | 2017
|  |  | Clé | Number | Date | Week Number | Name | NPT3am | NPT3pm | NPT1 | NPT2 | NPT3 | NPT4 | NPT5 | NPT6 | NPT7 | NPT8 | NPT9 | NPT10 | NPT11 | NPT12 | NPT13 | Worked | WEEK | 18 | 01 mai | 02 mai | 03 mai | 04 mai | 05 mai | 06 mai
|  | available information: | 01 | B PTW-01 | 2017-05-01 | 18 | B Name01 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | NPT1 - Tool Box Talk | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | PTW Number | 02 | B PTW-01 | 2017-05-01 | 18 | B Name02 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | NPT2 - WP Opening | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Scope | 03 | B PTW-01 | 2017-05-01 | 18 | B Name03 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6.25 | NPT3 - Tea Breaks | 0.69167 | 0.75 | 0.75 | 0.75 | 0.4 | 0.75 | 0.75
NPT Time |  | PTW Type | 04 | B PTW-01 | 2017-05-01 | 18 | B Name04 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6.25 | NPT4 - Lunch Break | 1 | 1 | 1 | 1 | 1 | 1 | 1
PTW Number |  | Phase | 05 | B PTW-01 | 2017-05-02 | 18 | B Name01 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | no NPT5 - Transfer
Date | PTW Data | Service | 06 | B PTW-01 | 2017-05-02 | 18 | B Name02 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | no NPT6 - Disconnection
Name |  | System | 07 | B PTW-01 | 2017-05-02 | 18 | B Name03 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8.25 | no NPT7 - Drills
NPT1 |  | Sub-System | 08 | B PTW-01 | 2017-05-02 | 18 | B Name04 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8.25 | no NPT8 - Weather
NPT2 |  | Discipline | 09 | B PTW-02 | 2017-05-03 | 18 | B Name05 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | no NPT9 - CPY stand-by
NPT3 |  | Tag | 10 | B PTW-02 | 2017-05-03 | 18 | B Name06 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | no NPT10 - Induction
NPT4 |  |  | 11 | B PTW-02 | 2017-05-04 | 18 | B Name05 | 0 | 0.4 | 0.5 | 0.5 | 0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 3.6 | NPT11 - Sunday Safety | 6 |  |  |  | 6
NPT5 |  | available information: | 12 | B PTW-02 | 2017-05-04 | 18 | B Name06 | 0 | 0.4 | 0.5 | 0.5 | 0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 3.6 | no NPT12 - Crew Change
NPT6 |  | Name | 13 | B PTW-03 | 2017-05-05 | 18 | B Name07 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | NPT13 - Slack period | 1 | 1.5 | 0.5
NPT7 |  | Category | 14 | B PTW-03 | 2017-05-05 | 18 | B Name08 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | Worked Hours | 7.975 | 7.75 | 8.75 | 9.25 | 3.6 | 9.25 | 9.25
NPT8 | Name Data | Sub-Category | 15 | B PTW-03 | 2017-05-05 | 18 | B Name09 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25
NPT9 |  | Occupation | 16 | B PTW-03 | 2017-05-06 | 18 | B Name07 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25 | Total NPT per day |  | 4.25 | 3.25 | 2.75 | 8.4 | 2.75 | 2.75
NPT10 |  | Company | 17 | B PTW-03 | 2017-05-06 | 18 | B Name08 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25
NPT11 |  | Origin | 18 | B PTW-03 | 2017-05-06 | 18 | B Name09 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.25
NPT12 |  |  | 19 | B PTW-04 | 2017-05-14 | 20 | B Name10 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 8.75
NPT13 |  |  | 20 | B PTW-04 | 2017-05-14 | 20 | B Name11 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 8.75
Worked |  |  | 21 | B PTW-04 | 2017-05-14 | 20 | B Name12 | 0.35 | 0.4 | 0.5 | 0.5 | 0.75 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 8.75
|  |  | 22 | No | 2017-05-15 | 20 | B Name13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0
|  |  | 23 | No | 2017-05-15 | 20 | B Name14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0