## Administration and General
Hotel Live Date | 2017-11-17
ADMINISTRATION & GENERAL | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Insurance
Determine Insurance Needs | Completed | 0 | 2012-11-19 | 2012-12-19 | KB
Confirm Insurance Providers | Completed | 0 | 2012-11-12 | 2012-11-15 | KB
Ensure Insurance is activated | Completed | 0 | 2012-10-10 | 2012-10-11 | KB
Purchasing & Receiving
Identify Primary Suppliers | Completed | 0 |  |  | All HOD's /P Dept
Establish Credit with Suppliers | Completed | 0 |  |  | KB
Implement purchase order system | Completed | 0 |  |  | KB
Develop Inventory Procedure | Completed | 0 |  |  | KB
Develop Requisition Procedures | Completed | 0 |  |  | KB
Leases
Confirm lease in place and copies available |  | 0
Printing and Stationery
Business Cards ordered | In Progress | 0 |  |  | CB/HR
Resorts Letterheads | Completed | 0 |  |  | CB
PMS Stationery | In Progress | 0
GUEST Account Stationery | Completed | 0
Purchasing Order Forms | Completed | 0
Payroll & Personnel Forms | Completed | 0
Uniforms
Finalise Specifications and Quantities | In Progress | 0 |  |  | CB/AR
Order Uniforms | Pending | 0 |  |  | CB/AR
Order STAFF Name Badges | Pending | 0 |  |  | CB/AR
Transportation
Finalise Requirements | Completed | 0 |  |  | KB
Affiliations & Memberships
Establish Membership | In Progress | 0 |  |  | CB/Sales
0
Opening Offices
Locate and Prepare Opening offices | In Progress | 0 |  |  | LN
0
Note on A4: F&B Royal Park: Swan
Note on A5: F&B Royal Park: Swan

## FINANCIAL PLAN
FINANCIAL PLAN | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Accounting Procedures
Obtain copy of Financial Plan Manual | Pending |  |  |  | KB
Order Accounting Packagesoftware | Pending | 0 |  |  | KB
Establish Resorts credit policy and procedures | Completed | 0 |  |  | KB
Set-up Accounts Procedures | Completed | 0
Obtain reporting formats |  | 0
Obtain Accounting Procedures Manuals | Completed | 0
Schedule training on Accounting Software | Pending | 0
Set-up Accounts STAFFING | Pending | 0
Recruit Key Accounts STAFF | In Progress | 0
Payroll
Set-up salaries bank account | Completed | 0 |  |  | KS
Register to Bank Account | Completed | 0
Order Payroll software | Pending | 0 |  |  | KS
Order Payroll Stationery | Pending | 0
General Manager Checklist Completed post-opening |  | 0
Pre-opening Budget
Draft pre-opening budget |  | 0
Pre-opening budget approval |  | 0
Operating Forecasts completed |  | 0
Hotel Budgets
12 mth Operating Budget | In Progress | 0 |  |  | KS
Capex Budget | Completed | 0 |  |  | KS
Banking
Set-up Bank Accounts incl. Salary Account |  | 0
Arrange Overdraft Facilities | Completed | 0
Set-up credit card agreements | Completed | 0
Arrange Security Cash collection | Completed | 0
Determine Operating Cash requirements | Pending | 0
Asset Management
Open Fixed Asset Register | Pending | 0
Complete pre-opening asset stock takes | In Progress | 12 | 2017-11-01 | 2017-11-13
See Admin & General |  | 0
See Risk Management |  | 0
See Legal Compliance |  | 0
Note on A27: F&B Royal Park: OD from Current Account
Note on A29: F&B Royal Park: Cash collection procedures in place KB

## IT & SYSTEMS
IT & SYSTEMS | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Property Management System
Order placed | In Progress | 237 | 2011-01-07 | 2011-09-01
Service Level Agreement finalised | Completed | 0
Installation dates confirmed | In Progress | 0
Data configuration set-up | In Progress | 0
Data input and configuration | In Progress | 0
Set restrictions in PMS | In Progress | 0
Implement Rate Codes In PMS | In Progress | 0
Enter Packages Into PMS | In Progress | 0
System Installed & Tested | Pending | 0
Training dates confirmed | Pending | 0
Backup Systems & Protocol | In Progress | 0
F&B Outlet POS Systems
One Unit at Main Bar | In Progress | 0
0
Server & LAN Network
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Backup Systems & Protocol |  | 0
Workstations
Requirements determined |  | 0
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Training dates confirmed |  | 0
Printers/Scanner/ Fax
Requirements determined |  | 0
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Training dates confirmed |  | 0
Software Requirements
Requirements determined |  | 0
Orders placed |  | 0
Licencing
Software Licences obtained | In Progress | 0
TV Licence application | In Progress | 0
Internet Service Provider
Determine ISP | Completed | 0
Service Level Agreement finalised | In Progress | 0
Domain registered | Completed | 0
e-mail accounts set-up | Completed | 0
Internet connectivity | Pending | 0
Telephone System
Confirm Switchboard Specifications | Pending | 0
Training dates confirmed | Pending | 0
Arrange Telkom Application |  | 0
Finalise Hotel Phone Number | Pending | 0
Finalise Hotel Fax Number | Pending | 0
Arrange Fax to Mail Facility |  | 0
Complete On-Hold Message Recording | Pending | 0
In-Room Entertainment
Specify requirements |  | 0
Order Decoders |  | 0
Installation & Testing |  | 0
Determine Bouquet |  | 0
Obtain licencing |  | 0
Source Public Area Music |  | 0
Timekeeping System
Requirements determined | In Progress | 0
System specifications agreed |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Note on A13: F&B Royal Park: Back up through Firewall system
Note on A48: F&B Royal Park: As pe rcontract
Note on A68: F&B Royal Park: SICORAX proposed

## LEGAL COMPLIANCE
LEGAL COMPLIANCE | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Business Registration
Obtain business trading number- BRN | Completed | 237 | 2011-01-07 | 2011-09-01 | KB
Licensing
Trading licence | In Progress | 0 |  |  | KB
0
Promotion of Access to Information Act
Fire Clearance Certificate obtained | In Progress | 0 |  |  | KB
Skills Development
Skills Development Facilitator appointed |  | 0
Training Committee established |  | 0
Health and Safety
Health & Safety Representatives appointed | In Progress | 0 |  |  | LN/JM
First Aiders trained and appointed | In Progress | 0 |  |  | LN/JM
Health & Safety Committee established | Pending | 0 |  |  | LN/JM
First Aid Boxes equipped and available | In Progress | 0 |  |  | LN/JM

## MARKETING PLAN
MARKETING PLAN | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Hotel Positioning
Complete Competitor Analysis | Completed | 0 | 2011-09-01 | 2011-09-01 | CB
Complete SWOT Analysis | Completed | 0 |  |  | CB
Hotel Sales Collateral
Develop facilities guide/presentation folder | In Progress | 156 | 2017-06-06 | 2017-11-09 | CB
Develop Permanent Brochure | In Progress | 156 | 2017-06-06 | 2017-11-09 | CB
Develop ancillary sales collateral/stationery | In Progress | 164 | 2017-06-06 | 2017-11-17 | CB
Develop Press Kit | Pending | 0 |  |  | CB
Develop Property Maps | Pending | 0 |  |  | CB
Photography/Video | In Progress | 164 | 2017-06-06 | 2017-11-17 | CB
Coordinate photo shoot for permanent brochure | In Progress | 0 |  |  | CB
Photography available | Completed | 0 |  |  | CB
Marketing Plan
Appoint Project Lead | Completed | 0
Appoint Sales Executive | Completed | 0
Rates Structure
Complete and Submit Rate Builder | In Progress | 0 |  |  | RL
Rate Grid to be approved |  | 0
Soft Opening Programme
Determine Target Groups |  | 0
Determine pre-opening programmes |  | 0
Hotel Opening Programme
Determine official opening date |  | 0
Determine Target Groups |  | 0
Determine Programme |  | 0
Hotel Branding
Minimum Branding Requirements ascertained |  | 0
Minimum Branding Requirements ordered |  | 0
Hotel Brochure finalised |  | 0
Hotel Signage finalised |  | 0
Corporate Flags ordered |  | 0
Rates Board ordered |  | 0
Brochure Rack and Brochures ordered |  | 0
Hotel Stationery finalised and ordered |  | 0
Key Cards designed |  | 0
Internal Signage agreed |  | 0
Marketing Material ordered |  | 0
Branding Checklist Completed |  | 0
Hotel Web Page
Hotel.com Web Entry |  | 0
Hotel Fact Sheet submitted |  | 0
Pictures submitted |  | 0
MEMBERSHIP
0
0
0
0
0
0
Note on A15: F&B Royal Park: CB
Note on A21: F&B Royal Park: See Annex Group Target

## BOAT PARKING
BOAT PARKING | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
PARKING SPACE
Identifying area for Boat parking | Completed | 0 | 2011-09-01 | 2011-09-01 | CB
Completion of Parking project | Completed | 0 |  |  | CB
Marketing of Boat Parking Space
Proper communication for promoting parking | In Progress | 156 | 2017-06-06 | 2017-11-09 | CB
Agreement for Boat parking | In Progress | 156 | 2017-06-06 | 2017-11-09 | CB
Appropriate insurance for Boat parking in case of Cyclone | In Progress | 164 | 2017-06-06 | 2017-11-17 | CB
Develop Press Kit | Pending | 0 |  |  | CB
Develop Property Maps | Pending | 0 |  |  | CB
Photography/Video | In Progress | 164 | 2017-06-06 | 2017-11-17 | CB
Coordinate photo shoot for permanent brochure | In Progress | 0 |  |  | CB
Photography available | Completed | 0 |  |  | CB
0
0
0
0
0
0

## QUALITY PLAN - F&B
QUALITY PLAN - F&B | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Contract GUEST Valet/ Laundry | Completed | 237 | 2011-01-07 | 2011-09-01
Contract GUEST Transport | Completed | 0 |  |  | CC
Develop F&B Outlet Concepts | In Progress | 0 | 2011-01-07 | 2011-01-07 | CB/Chef/JM/BM
Restaurant Concept | In Progress | 0
Restaurant Theme | In Progress | 0
STAFFING LEVELS |  | 0
Service Levels | Completed | 0
Menu Planning | In Progress | 0
Menu Tastings | In Progress | 0
Menu Costings | In Progress | 0
Develop Standard Recipes | In Progress | 0
Menu Pricing finalised | In Progress | 0
Menus to Print | Pending | 1 | 1899-12-31 | 1900-01-01
Table Layouts | Completed | 0
Centrepieces | Completed | 0
Linen/ Table Mats | Completed | 0
Bar Concept
Operating Hours | Completed | 0
STAFFING Levels | Completed | 0
Wine List Finalised | In Progress | 0
Wine List Costed | In Progress | 0
Drinks Pricing | In Progress | 0
Service Levels | In Progress | 0
Restaurant Service
Operating Hours | Completed | 0
STAFFING Levels | Completed | 0
Service Levels |  | 0
Menu Planning | Completed | 0
Menu Costings |  | 0
Menu Pricing finalised |  | 0
Menus to Print |  | 0
Equipment specifications | Completed | 0
Equipment ordered (see Purchasing) |  | 0
Equipment commissioning complete |  | 0
Kitchen
Determine Kitchen smallwares | Completed | 0
Specify kitchen smallwares | Completed | 0
Order kitchen smallwares | Completed | 0
Delivery date confirmed |  | 0
Equipment commissioning complete | Completed | 0
Purchasing
Linen |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Cutlery |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Crockery |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Glassware |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Equipment |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
F&B Inventories |  | 0
Develop Kitchen par stock |  | 0
Develop master beverage/bar par stock and wine list |  | 0
Procure opening F&B inventories |  | 0
Conferencing
Conferencing Layouts |  | 0
Conferencing Packages |  | 0
Specify Conferencing Equipment |  | 0
Order Conferencing Equipment |  | 0
Delivery Dates Confirmed |  | 0
Equipment commissioning complete |  | 0
Technical support available |  | 0
Storage and Control
Arrange suitably secured storage | In Progress | 0
Complete Asset Register |  | 0
Complete Opening Stock Inventories |  | 0
Obtain Quality Operating Standards Manual |  | 0
Issue Minimum Operating Standards to Heads of Departments |  | 0
Customise Minimum GUEST Service Standards |  | 0
Communicate Minimum GUEST Service Standards |  | 0
Schedule Pre-opening Quality Assurance Assessment |  | 0
Obtain required SA Grading |  | 0
Implement "Hot or Not" GUEST Feedback System |  | 0

## QUALITY PLAN - Housekeeping
QUALITY PLAN - Housekeeping | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Obtain Quality Operating Standards Manual | In Progress | 237 | 2011-01-07 | 2011-09-01
Issue Minimum Operating Standards to Heads of Departments |  | 0
Customise Minimum GUEST Service Standards |  | 0
Communicate Minimum GUEST Service Standards |  | 0
Schedule Pre-opening Quality Assurance Assessment |  | 0
Obtain required Standard Assessment Grading |  | 0
Implement GUEST Feedback System |  | 0
HOUSEKEEPING
Equipment |  | 0
Requirements Specified |  | 0
Housekeeping Trolleys |  | 0
Vacuum Cleaners |  | 0
Cleaning Smalls |  | 0
Quantities and Specifications established |  | 0
Delivery Dates Confirmed |  | 0
Asset Register opened |  | 0
Linen
Quanities Specified |  | 0
Par Stock Established |  | 0
Quality Specifications Set |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Secure Storage |  | 0
Opening Inventory Taken |  | 0
GUEST Supplies
GUEST Bathroom Amenities |  | 0
GUEST Stationery |  | 0
GUEST Beverage Supplies |  | 0
Quanities Specified |  | 0
Par Stock Established |  | 0
Quality Specifications Set |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Secure Storage |  | 0
Opening Inventory Taken |  | 0
Minimum Branding
Checklist Completed |  | 0
Outsourcing |  | 0
Housekeeping Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
Laundry |  | 0
Service Level Agreement finalised |  | 0
Public Area Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
All Contractors to undergo Induction Training |  | 0

## RISK MANAGEMENT
RISK MANAGEMENT | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Obtain Risk Management Manual | Completed | 25 | 2011-01-07 | 2011-02-01
Complete Risk Management Plan |  | 0
Insurance
Determine Insurance Needs |  | 0
Confirm Insurance Providers | Completed | 0
Ensure Insurance is activated | Completed | 0
Arrange Risk Audit post opening | Completed | 0
Emergency Planning
Draft Emergency Procedures |  | 0
Draft Evacuation Procedures |  | 0
Obtain Emergency Services Contact Numbers |  | 0
Appoint Fire Station Officers |  | 0
Train STAFF in Emergency Procedures |  | 0
Hold Fire & Evacuation Drill |  | 0
Health & Safety
Order First Aid Boxes |  | 0
Order Emergency Equipment |  | 0
Megaphones |  | 0
Hard Helmets |  | 0
Vests |  | 0
2-way radios |  | 0
Torches |  | 0
Verify proper operation of all Life Safety equipment/systems |  | 0
GUEST Security
Check CCTV installation & monitoring |  | 0
Key Register & Monitoring System in place |  | 0
Computer Security |  | 0
Backup Systems & Procedures in place |  | 0
Electronic Communication Policy in Place |  | 0
Note on A6: F&B Royal Park: Swan
Note on A8: F&B Royal Park: See annexed reports from Health n Safety

## STAFFING
STAFFING | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Finalise STAFFING Numbers | Completed | 31 | 2017-10-01 | 2017-11-01 | LN
Finalise Salary & Benefits Budget | Completed | 0 |  |  | LN
Obtain HR Operating Standards Manual | Completed | 0 |  |  | LN
Establish Conditions of Employment | Completed | 0 |  |  | LN
Draw up Contracts of Employment | Completed | 0 |  |  | LN
Confirm Employment Policies | Completed | 0 |  |  | LN
Finalise Employee Handbook | Pending | 0 |  |  | LN
Establish Performance Expectations
Issue Job Descriptions | Pending | 0 |  |  | LN/JM
Issue GUEST Service Standards | In Progress | 0 |  |  | LN/JM
Arrange for Probationary Performance Reviews | In Progress | 0 |  |  | LN/HOD's
Determine Outsourcing Requirements
Housekeeping |  | 0
Service Level Agreement finalised |  | 0
Laundry |  | 0
Service Level Agreement finalised |  | 0
Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
Maintenance |  | 0
Service Level Agreement finalised |  | 0
Security |  | 0
Service Level Agreement finalised |  | 0
STAFF Transport | Completed | 0
Service Level Agreement finalised |  | 0
Customise Position Specifications |  | 0
Develop Hiring Schedule |  | 0
Develop Training Schedules | Pending | 0
Confirm Training Dates & Providers |  | 0
Hire Senior Management Team
Operation Manager | Completed | 0
Asst.Operation Manager | Completed | 0
Hire Department Heads
Accounting Spv | Completed | 0
FO Spv | Pending | 0
HK Spv | Completed | 0
Sales Executive | Completed | 0
Eng Spv | Pending | 0
Hire Junior Management
Hire Service and Support STAFF | Completed | 0 |  |  | KB
Schedule Training
Induction Training | Pending | 0
Skills Training | In Progress | 0 |  |  | HOD's
Systems Training (OBI & POS) | Pending | 0 |  |  | All
Emergency Procedures | Pending | 0 |  |  | LN/JM