## FIFI
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102
[31 empty] | PLANNED WORKLOAD DEV | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [11 empty] | TOTAL PLANNED WORKLOAD FUNCT. HORS M3 |  | TOTAL PLANNED WORKLOAD DEV. HORS M3 | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [11 empty] | PLANNED WORKLOAD FUNCT |  | PLANNED WORKLOAD DEV | [9 empty] | 296 | 533
ID | LOT | Outils | SOURCE | TARGET | TOPIC | DELIVERABLE GENERAL NAME | COMMENT | TYPE | COMPLEXITY | OTHER | WORKSHOP | RESPONSIBLE | DATE | WORKLOAD | ATTENDEES | STATUS | FUNCTIONAL SPECIFICATION | Funct. Resp. | PLANNED WORKLOAD FUNCT. | DURATION | PLANNED START DATE | PLANNED DUE DATE | ACTUALS | ETC | ESTIMATED END DATE | STATUS2 | EAC | % WORKLOAD COMPLETED | TECHNICAL SPECIFICATION | Dev. Resp. | PLANNED WORKLOAD DEV. | DURATION3 | PLANNED START DATE4 | PLANNED DUE DATE5 | ACTUALS6 | ETC7 | ESTIMATED END DATE2 | STATUS9 | EAC8 | % WORK COMPLETED | DETAILED TECHNICAL SPECIFICATION | Funct. Resp.10 | PLANNED WORKLOAD FUNCT.11 | Dev. Resp.12 | PLANNED WORKLOAD DEV.13 | DURATION14 | PLANNED START DATE15 | PLANNED DUE DATE16 | ACTUALS17 | ETC18 | ESTIMATED END DATE22 | STATUS21 | EAC19 | % WORK COMPLETE20 | DETAILED TECHNICAL SPECIFICATION NOT IN M3 | Funct. Resp. Hors M3 | PLANNED WORKLOAD FUNCT. HORS M3 | Dev. Resp. HORS M3 | PLANNED WORKLOAD DEV. HORS M3 | DURATION22 | PLANNED START DATE23 | PLANNED DUE DATE24 | ACTUALS25 | ETC26 | ESTIMATED END DATE222 | STATUS29 | EAC27 | % WORK COMPLETE28 | UNIT TESTS | Funct. Resp | PLANNED WORKLOAD FUNCT.30 | Dev. Resp.31 | PLANNED WORKLOAD DEV.32 | DURATION323 | PLANNED START DATE33 | PLANNED DUE DATE34 | ACTUALS35 | ETC36 | ESTIMATED END DATE2222 | STATUS39 | EAC37 | % WORK COMPLETE38 | INTEGRATION TESTS | Funct. Resp40 | PLANNED WORKLOAD FUNCT.41 | Dev. Resp.42 | PLANNED WORKLOAD DEV.43 | DURATION44 | PLANNED START DATE45 | PLANNED DUE DATE46 | ACTUALS47 | ETC48 | ESTIMATED END DATE22222 | STATUS51 | EAC372 | % WORK COMPLETE50 | PLANNED WORKLOAD FUNCT | PLANNED WORKLOAD DEV | LOT2 | TOTAL PLANNED WORKLOAD FUNCT. HORS M3 | TOTAL PLANNED WORKLOAD DEV. HORS M3 | [6 empty] | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
1 | 2 | PRICING | Pricing | M3 | Sales price | FIFI - PRICING - Sales price |  | INTERFACE | LOW |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Sales price - Functional Specification | Maxime | 1 | 1.3 | 2018-10-01 | 2018-10-02 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Sales price - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-10-05 | 2018-10-05 |  |  |  | Not Started | 0.5 | 0% | FIFI - PRICING - Sales price - DETAILED TECH SPECIFICATION | Maxime | 0.5 | 3Kles | 3 | 3.9 | 2018-10-10 | 2018-10-15 |  |  |  | Not Started | 3 | 0% | FIFI - PRICING - Sales price - DTS not in M3 | Maxime | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - PRICING - Sales price - Unit Tests | Maxime | 1 | 3Kles | 1 | 1.3 | 2018-10-17 | 2018-10-18 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Sales price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 2 | 2.5 | 4 | 1 | LOT | PLANNED WORKLOAD FUNCT | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
2 | 2 | PRICING | Pricing | M3 | Retail price | FIFI - PRICING - Retail price |  | INTERFACE | LOW |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Retail price - Functional Specification | Maxime | 1 | 1.3 | 2018-10-02 | 2018-10-03 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Retail price - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-10-08 | 2018-10-08 |  |  |  | Not Started | 0.5 | 0% | FIFI - PRICING - Retail price - DETAILED TECH SPECIFICATION | Maxime | 0.5 | 3Kles | 3 | 3.9 | 2018-10-11 | 2018-10-16 |  |  |  | Not Started | 3 | 0% | FIFI - PRICING - Retail price - DTS not in M3 | Maxime | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - PRICING - Retail price - Unit Tests | Maxime | 1 | 3Kles | 1 | 1.3 | 2018-10-18 | 2018-10-19 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Retail price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 2 | 2.5 | 4 | 2 | 1 | 128.5 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 21.4167; 2018-08-01: 14.2778; 2018-09-01: 21.4167; 2018-10-01: 21.4167; 2018-11-01: 21.4167; 2018-12-01: 21.4167
3 | 2 | PRICING | M3 | Pricing | Master Client | FIFI - PRICING - Master Client |  | INTERFACE | MEDIUM |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Master Client - Functional Specification | Maxime | 2 | 2.6 | 2018-10-03 | 2018-10-05 |  |  |  | Not Started | 2 | 0% | FIFI - PRICING - Master Client - Technical Specification | CL TBD | 1.5 | 1.95 | 2018-10-10 | 2018-10-11 |  |  |  | Not Started | 1.5 | 0% | FIFI - PRICING - Master Client - DETAILED TECH SPECIFICATION | Maxime | 1.5 | CL TBD | 6 | 7.8 | 2018-10-15 | 2018-10-24 |  |  |  | Not Started | 6 | 0% | FIFI - PRICING - Master Client - DTS not in M3 | Maxime | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - PRICING - Master Client - Unit Tests | Maxime | 1 | CL TBD | 1 | 1.3 | 2018-10-22 | 2018-10-23 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Master Client - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 3 | 2 | 125 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 20.8333; 2018-08-01: 13.8889; 2018-09-01: 20.8333; 2018-10-01: 20.8333; 2018-11-01: 20.8333; 2018-12-01: 20.8333
4 | 2 | PRICING | M3 | Pricing | Client Order | FIFI - PRICING - Client Order |  | INTERFACE | MEDIUM |  |  | Maxime |  |  |  | Not Started | FIFI - PRICING - Client Order - Functional Specification | Maxime | 2 | 2.6 | 2018-10-08 | 2018-10-10 |  |  |  | Not Started | 2 | 0% | FIFI - PRICING - Client Order - Technical Specification | CL TBD | 1.5 | 1.95 | 2018-10-15 | 2018-10-16 |  |  |  | Not Started | 1.5 | 0% | FIFI - PRICING - Client Order - DETAILED TECH SPECIFICATION | Maxime | 1.5 | CL TBD | 6 | 7.8 | 2018-10-18 | 2018-10-29 |  |  |  | Not Started | 6 | 0% | FIFI - PRICING - Client Order - DTS not in M3 | Maxime | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - PRICING - Client Order - Unit Tests | Maxime | 1 | CL TBD | 1 | 1.3 | 2018-10-25 | 2018-10-26 |  |  |  | Not Started | 1 | 0% | FIFI - PRICING - Client Order - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 4 | 3 | 42.5 | 5 | 2018-09-01 | 2019-02-01 | 2018-09-01: 8.5; 2018-10-01: 8.5; 2018-11-01: 8.5; 2018-12-01: 8.5; 2019-01-01: 8.5
5 | 1 | PLM | PLM | M3 | Item+attributes (weight, dimension, etc..) | FIFI - PLM - Item+attributes (weight, dimension, etc..) |  | INTERFACE | VERY COMPLEX |  |  | JY |  |  |  | Not Started | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-10 | 2018-10-18 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Technical Specification | Centric/3Kles | 4 | 5.2 | 2018-10-23 | 2018-10-30 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | Centric/3Kles | 12 | 15.6 | 2018-10-26 | 2018-11-19 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Unit Tests | 3Kles (TBD) | 4 | Centric/3Kles | 4 | 5.2 | 2018-11-05 | 2018-11-12 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Item+attributes (weight, dimension, etc..) - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 5 |  | TOTAL |  |  |  | 0 | 0 | 0 | 42.25 | 28.1667 | 50.75 | 50.75 | 50.75 | 50.75 | 8.5 | 0
6 | 1 | PLM | PLM | M3 | Purchase Price | FIFI - PLM - Purchase Price |  | INTERFACE | VERY COMPLEX |  |  | JY |  |  |  | Not Started | FIFI - PLM - Purchase Price - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-22 | 2018-10-30 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Purchase Price - Technical Specification | Centric/3Kles | 4 | 5.2 | 2018-11-05 | 2018-11-12 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Purchase Price - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | Centric/3Kles | 12 | 15.6 | 2018-11-08 | 2018-11-29 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Purchase Price - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Purchase Price - Unit Tests | 3Kles (TBD) | 4 | Centric/3Kles | 4 | 5.2 | 2018-11-15 | 2018-11-22 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Purchase Price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 6 |  | ETP |  |  |  | 0 | 0 | 0 | 2.3472 | 1.5648 | 2.8194 | 2.8194 | 2.8194 | 2.8194 | 0.47222 | 0
7 | 1 | PLM | PLM | M3 | Product, poids, grilles, Madein, etc… | FIFI - PLM - Madein |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Madein - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-01 | 2018-10-09 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Madein - Technical Specification | 3Kles | 4 | 5.2 | 2018-10-12 | 2018-10-19 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Madein - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-10-17 | 2018-11-08 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Madein - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Madein - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-10-24 | 2018-10-31 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Madein - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 7
8 | 1 | PLM | PLM | M3 | Drop | FIFI - PLM - HS Code |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - HS Code - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-09 | 2018-10-17 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - HS Code - Technical Specification | 3Kles | 4 | 5.2 | 2018-10-22 | 2018-10-29 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - HS Code - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-10-25 | 2018-11-16 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - HS Code - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - HS Code - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-02 | 2018-11-09 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - HS Code - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 8
9 | 1 | PLM | PLM | M3 | Composition | FIFI - PLM - Composition |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Composition - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-17 | 2018-10-25 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Composition - Technical Specification | 3Kles | 4 | 5.2 | 2018-10-30 | 2018-11-07 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Composition - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-05 | 2018-11-26 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Composition - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Composition - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-12 | 2018-11-19 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Composition - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 9
10 | 1 | PLM | PLM | M3 | Offer | FIFI - PLM - Offer |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Offer - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-10-25 | 2018-11-05 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Offer - Technical Specification | 3Kles | 4 | 5.2 | 2018-11-08 | 2018-11-15 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-13 | 2018-12-04 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Offer - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Offer - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-20 | 2018-11-27 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Offer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 10
11 | 1 | PLM | PLM | M3 | Modification/Desactivation | FIFI - PLM - Offer |  | INTERFACE | VERY COMPLEX | [6 empty] | Not Started | FIFI - PLM - Offer - Functional Specification | 3Kles (TBD) | 5 | 6.5 | 2018-11-05 | 2018-11-13 |  |  |  | Not Started | 5 | 0% | FIFI - PLM - Offer - Technical Specification | 3Kles | 4 | 5.2 | 2018-11-16 | 2018-11-23 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | 3Kles (TBD) | 3 | 3Kles | 12 | 15.6 | 2018-11-21 | 2018-12-12 |  |  |  | Not Started | 12 | 0% | FIFI - PLM - Offer - DTS not in M3 | Centric | 12 |  | 19 | 24.7 | [5 empty] | Not Started | 19 | 0% | FIFI - PLM - Offer - Unit Tests | 3Kles (TBD) | 4 | 3Kles | 4 | 5.2 | 2018-11-28 | 2018-12-05 |  |  |  | Not Started | 4 | 0% | FIFI - PLM - Offer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 12 | 20 | 1 | 12 | 19 | 11
12 |  | N/A | M3 | Colombus | Items | FIFI - N/A - Items | Can we maintain the PLM -> Colombus | INTERFACE | [7 empty] | Not Started | FIFI - N/A - Items - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - N/A - Items - Technical Specification | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Items - DETAILED TECH SPECIFICATION | 0 |  | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Items - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - N/A - Items - Unit Tests | 0 |  | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Items - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 12
13 |  | N/A | M3 | Colombus | Retail price | FIFI - N/A - Retail price | Can be manual once a season | INTERFACE | [7 empty] | Not Started | FIFI - N/A - Retail price - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - N/A - Retail price - Technical Specification | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Retail price - DETAILED TECH SPECIFICATION | 0 |  | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Retail price - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - N/A - Retail price - Unit Tests | 0 |  | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - N/A - Retail price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 13 |  | 296
14 | 3 | OSO | M3 | OSO | Items | FIFI - OSO - Items |  | INTERFACE | COMPLEX | [6 empty] | Not Started | FIFI - OSO - Items - Functional Specification | TBConfirmed | 3 | 3.9 | 2019-01-03 | 2019-01-08 |  |  |  | Not Started | 3 | 0% | FIFI - OSO - Items - Technical Specification | 3Kles | 2 | 2.6 | 2019-01-11 | 2019-01-15 |  |  |  | Not Started | 2 | 0% | FIFI - OSO - Items - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 8 | 10.4 | 2019-01-16 | 2019-01-30 |  |  |  | Not Started | 8 | 0% | FIFI - OSO - Items - DTS not in M3 | ACS2I | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - OSO - Items - Unit Tests | TBConfirmed | 2 | 3Kles | 2 | 2.6 | 2019-01-23 | 2019-01-25 |  |  |  | Not Started | 2 | 0% | FIFI - OSO - Items - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 3 | 6.5 | 11.5 | 14
15 | 3 | OSO | M3 | OSO | Prices | FIFI - OSO - Prices |  | INTERFACE | MEDIUM | [6 empty] | Not Started | FIFI - OSO - Prices - Functional Specification | TBConfirmed | 2 | 2.6 | 2019-01-03 | 2019-01-07 |  |  |  | Not Started | 2 | 0% | FIFI - OSO - Prices - Technical Specification | 3Kles | 1.5 | 1.95 | 2019-01-10 | 2019-01-11 |  |  |  | Not Started | 1.5 | 0% | FIFI - OSO - Prices - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2019-01-15 | 2019-01-24 |  |  |  | Not Started | 6 | 0% | FIFI - OSO - Prices - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - OSO - Prices - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2019-01-22 | 2019-01-23 |  |  |  | Not Started | 1 | 0% | FIFI - OSO - Prices - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 15 | LOT | PLANNED WORKLOAD DEV | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
16 | 3 | OSO | M3 | OSO | Client List | FIFI - OSO - Client List |  | INTERFACE | MEDIUM | [6 empty] | Not Started | FIFI - OSO - Client List - Functional Specification | TBConfirmed | 2 | 2.6 | 2019-01-03 | 2019-01-07 |  |  |  | Not Started | 2 | 0% | FIFI - OSO - Client List - Technical Specification | 3Kles | 1.5 | 1.95 | 2019-01-10 | 2019-01-11 |  |  |  | Not Started | 1.5 | 0% | FIFI - OSO - Client List - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2019-01-15 | 2019-01-24 |  |  |  | Not Started | 6 | 0% | FIFI - OSO - Client List - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - OSO - Client List - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2019-01-22 | 2019-01-23 |  |  |  | Not Started | 1 | 0% | FIFI - OSO - Client List - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 16 | 1 | 220 | 6 | 2018-08-01 | 2019-02-01 | 2018-08-01: 24.4444; 2018-09-01: 36.6667; 2018-10-01: 36.6667; 2018-11-01: 36.6667; 2018-12-01: 36.6667; 2019-01-01: 36.6667
17 | 3 | OSO | OSO | M3 | Boutique Order | FIFI - OSO - Boutique Order | Might already exist with CLUSD ? | INTERFACE | MEDIUM | [6 empty] | Not Started | FIFI - OSO - Boutique Order - Functional Specification | TBConfirmed | 2 | 2.6 | 2019-01-03 | 2019-01-07 |  |  |  | Not Started | 2 | 0% | FIFI - OSO - Boutique Order - Technical Specification | 3Kles | 1.5 | 1.95 | 2019-01-10 | 2019-01-11 |  |  |  | Not Started | 1.5 | 0% | FIFI - OSO - Boutique Order - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2019-01-15 | 2019-01-24 |  |  |  | Not Started | 6 | 0% | FIFI - OSO - Boutique Order - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - OSO - Boutique Order - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2019-01-22 | 2019-01-23 |  |  |  | Not Started | 1 | 0% | FIFI - OSO - Boutique Order - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 17 | 2 | 233.5 | 6 | 2018-08-01 | 2019-02-01 | 2018-08-01: 25.9444; 2018-09-01: 38.9167; 2018-10-01: 38.9167; 2018-11-01: 38.9167; 2018-12-01: 38.9167; 2019-01-01: 38.9167
18 | 1 | WSH | M3 | WSH | Items | FIFI - WSH - Items | Could be from PLM ? | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Items - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-09-10 | 2018-09-12 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - Items - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-17 | 2018-09-18 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - Items - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-09-20 | 2018-10-01 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - Items - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - Items - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-09-27 | 2018-09-28 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Items - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 18 | 3 | 79.5 | 5 | 2018-10-01 | 2019-03-01 | 2018-10-01: 15.9; 2018-11-01: 15.9; 2018-12-01: 15.9; 2019-01-01: 15.9; 2019-02-01: 15.9
19 | 1 | WSH | M3 | WSH | Offer | FIFI - WSH - Offer | Could be from PLM ? | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Offer - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-09-14 | 2018-09-18 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - Offer - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-21 | 2018-09-24 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - Offer - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-09-26 | 2018-10-05 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - Offer - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - Offer - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-10-03 | 2018-10-04 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Offer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 19 |  | TOTAL |  |  |  | 0 | 0 | 0 | 0 | 50.3889 | 75.5833 | 91.4833 | 91.4833 | 91.4833 | 91.4833 | 15.9
20 | 1 | WSH | M3 | WSH | Prices | FIFI - WSH - Prices |  | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Prices - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-09-16 | 2018-09-18 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - Prices - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-21 | 2018-09-24 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - Prices - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-09-26 | 2018-10-05 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - Prices - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - Prices - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-10-03 | 2018-10-04 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Prices - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 20 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 2.7994 | 4.1991 | 5.0824 | 5.0824 | 5.0824 | 5.0824 | 0.88333
21 | 1 | WSH | M3 | WSH | Client | FIFI - WSH - Client |  | INTERFACE | LOW |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Client - Functional Specification | TBConfirmed | 1 | 1.3 | 2018-09-18 | 2018-09-19 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Client - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-09-24 | 2018-09-24 |  |  |  | Not Started | 0.5 | 0% | FIFI - WSH - Client - DETAILED TECH SPECIFICATION | TBConfirmed | 0.5 | 3Kles | 3 | 3.9 | 2018-09-27 | 2018-10-02 |  |  |  | Not Started | 3 | 0% | FIFI - WSH - Client - DTS not in M3 | ACS2I | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - WSH - Client - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-10-04 | 2018-10-05 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Client - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 1 | 2.5 | 4 | 21 |  | 533
22 | 1 | WSH | M3 | WSH | Stock ? | FIFI - WSH - Stock ? |  | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Stock ? - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-09-10 | 2018-09-12 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - Stock ? - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-17 | 2018-09-18 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - Stock ? - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-09-20 | 2018-10-01 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - Stock ? - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - Stock ? - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-09-27 | 2018-09-28 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Stock ? - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 22
23 | 1 | WSH | M3 | WSH | Exclusivity + Drops | FIFI - WSH - Exclusivity + Drops |  | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Exclusivity + Drops - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-09-20 | 2018-09-24 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - Exclusivity + Drops - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-27 | 2018-09-28 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - Exclusivity + Drops - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-10-02 | 2018-10-11 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - Exclusivity + Drops - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - Exclusivity + Drops - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-10-09 | 2018-10-10 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Exclusivity + Drops - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 23
24 | 1 | WSH | WSH | M3 | Client Order | FIFI - WSH - Client Order | Confirmed Orders | INTERFACE | LOW |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - Client Order - Functional Specification | TBConfirmed | 1 | 1.3 | 2018-09-17 | 2018-09-18 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Client Order - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-09-21 | 2018-09-21 |  |  |  | Not Started | 0.5 | 0% | FIFI - WSH - Client Order - DETAILED TECH SPECIFICATION | TBConfirmed | 0.5 | 3Kles | 3 | 3.9 | 2018-09-26 | 2018-10-01 |  |  |  | Not Started | 3 | 0% | FIFI - WSH - Client Order - DTS not in M3 | ACS2I | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - WSH - Client Order - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-10-03 | 2018-10-04 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - Client Order - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 1 | 2.5 | 4 | 24 |  | WORKLOAD CUSTO | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
25 | 1 | WSH | WSH | LINELIST | LINELIST | FIFI - WSH - LINELIST |  | INTERFACE | MEDIUM |  |  | Emmanuelle/3Kles |  |  |  | Not Started | FIFI - WSH - LINELIST - Functional Specification | TBConfirmed | 2 | 2.6 | 2018-11-15 | 2018-11-19 |  |  |  | Not Started | 2 | 0% | FIFI - WSH - LINELIST - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-22 | 2018-11-23 |  |  |  | Not Started | 1.5 | 0% | FIFI - WSH - LINELIST - DETAILED TECH SPECIFICATION | TBConfirmed | 1.5 | 3Kles | 6 | 7.8 | 2018-11-27 | 2018-12-06 |  |  |  | Not Started | 6 | 0% | FIFI - WSH - LINELIST - DTS not in M3 | ACS2I | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - WSH - LINELIST - Unit Tests | TBConfirmed | 1 | 3Kles | 1 | 1.3 | 2018-12-04 | 2018-12-05 |  |  |  | Not Started | 1 | 0% | FIFI - WSH - LINELIST - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 1 | 4.5 | 8.5 | 25 |  | INTERNE | 6 | 2018-07-01 | 2019-01-01 | 2.7077 | 1.0192 | 2.0385 | 3.0385 | 0.66667 | 3.5385 | 8.8462 | 8.8038 | 12.3846
26 | 3 | PIGALLE | M3 | Pigalle | Client Order/DO | FIFI - PIGALLE - Client Order/DO |  | INTERFACE | COMPLEX |  |  | JC/3Kles |  |  |  | Not Started | FIFI - PIGALLE - Client Order/DO - Functional Specification | JC 3Kles TBD | 3 | 3.9 | 2018-09-25 | 2018-09-28 |  |  |  | Not Started | 3 | 0% | FIFI - PIGALLE - Client Order/DO - Technical Specification | 3Kles | 2 | 2.6 | 2018-10-03 | 2018-10-05 |  |  |  | Not Started | 2 | 0% | FIFI - PIGALLE - Client Order/DO - DETAILED TECH SPECIFICATION | JC 3Kles TBD | 1.5 | 3Kles | 8 | 10.4 | 2018-10-08 | 2018-10-22 |  |  |  | Not Started | 8 | 0% | FIFI - PIGALLE - Client Order/DO - DTS not in M3 | OHWEE | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - PIGALLE - Client Order/DO - Unit Tests | JC 3Kles TBD | 2 | 3Kles | 2 | 2.6 | 2018-10-15 | 2018-10-17 |  |  |  | Not Started | 2 | 0% | FIFI - PIGALLE - Client Order/DO - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 3 | 6.5 | 11.5 | 26 |  | EXTERNE | 6 | 2018-07-01 | 2019-01-01 | 19.75 | 17.5385 | 34.5218 | 41.7733 | 49.076 | 52.6667 | 77 | 113.5836 | 129.6667
27 | 3 | PIGALLE | M3 | Pigalle | Stock | FIFI - PIGALLE - Stock |  | INTERFACE | LOW |  |  | JC/3Kles |  |  |  | Not Started | FIFI - PIGALLE - Stock - Functional Specification | JC 3Kles TBD | 1 | 1.3 | 2018-09-17 | 2018-09-18 |  |  |  | Not Started | 1 | 0% | FIFI - PIGALLE - Stock - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-09-21 | 2018-09-21 |  |  |  | Not Started | 0.5 | 0% | FIFI - PIGALLE - Stock - DETAILED TECH SPECIFICATION | JC 3Kles TBD | 0.5 | 3Kles | 3 | 3.9 | 2018-09-26 | 2018-10-01 |  |  |  | Not Started | 3 | 0% | FIFI - PIGALLE - Stock - DTS not in M3 | OHWEE | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - PIGALLE - Stock - Unit Tests | JC 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-10-03 | 2018-10-04 |  |  |  | Not Started | 1 | 0% | FIFI - PIGALLE - Stock - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 3 | 2.5 | 4 | 27 |  | EXTERNE BI | 5 | 2018-09-01 | 2019-02-01 | 0 | 0 | 0 | 0 | 4.2857 | 22.5974 | 6.8182 | 0 | 29.4156
28 | 3 | PIGALLE | M3 | Pigalle | Master Client | FIFI - PIGALLE - Master Client |  | INTERFACE | MEDIUM |  |  | JC/3Kles |  |  |  | Not Started | FIFI - PIGALLE - Master Client - Functional Specification | JC 3Kles TBD | 2 | 2.6 | 2018-09-18 | 2018-09-20 |  |  |  | Not Started | 2 | 0% | FIFI - PIGALLE - Master Client - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-25 | 2018-09-26 |  |  |  | Not Started | 1.5 | 0% | FIFI - PIGALLE - Master Client - DETAILED TECH SPECIFICATION | JC 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-09-28 | 2018-10-09 |  |  |  | Not Started | 6 | 0% | FIFI - PIGALLE - Master Client - DTS not in M3 | OHWEE | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - PIGALLE - Master Client - Unit Tests | JC 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-10-05 | 2018-10-08 |  |  |  | Not Started | 1 | 0% | FIFI - PIGALLE - Master Client - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 28 |  | TOTAL |  |  |  | 22.4577 | 18.5577 | 36.5603 | 44.8118 | 54.0284 | 78.8025 | 92.6643 | 122.3874 | 171.4669 | 0 | 0
29 | 3 | PIGALLE | M3 | Pigalle | Assortment | FIFI - PIGALLE - Assortment |  | INTERFACE | MEDIUM |  |  | JC/3Kles |  |  |  | Not Started | FIFI - PIGALLE - Assortment - Functional Specification | JC 3Kles TBD | 2 | 2.6 | 2018-09-20 | 2018-09-24 |  |  |  | Not Started | 2 | 0% | FIFI - PIGALLE - Assortment - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-09-27 | 2018-09-28 |  |  |  | Not Started | 1.5 | 0% | FIFI - PIGALLE - Assortment - DETAILED TECH SPECIFICATION | JC 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-10-02 | 2018-10-11 |  |  |  | Not Started | 6 | 0% | FIFI - PIGALLE - Assortment - DTS not in M3 | OHWEE | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - PIGALLE - Assortment - Unit Tests | JC 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-10-09 | 2018-10-10 |  |  |  | Not Started | 1 | 0% | FIFI - PIGALLE - Assortment - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 29 |  | ETP |  |  |  | 1.2476 | 1.031 | 2.0311 | 2.4895 | 3.0016 | 4.3779 | 5.148 | 6.7993 | 9.5259 | 0 | 0
30 | 3 | PIGALLE | Pigalle | M3 | Allocation/Unallocation | FIFI - PIGALLE - Allocation/Unallocation |  | INTERFACE | MEDIUM |  |  | JC/3Kles |  |  |  | Not Started | FIFI - PIGALLE - Allocation/Unallocation - Functional Specification | JC 3Kles TBD | 2 | 2.6 | 2018-10-01 | 2018-10-03 |  |  |  | Not Started | 2 | 0% | FIFI - PIGALLE - Allocation/Unallocation - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-10-08 | 2018-10-09 |  |  |  | Not Started | 1.5 | 0% | FIFI - PIGALLE - Allocation/Unallocation - DETAILED TECH SPECIFICATION | JC 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-10-11 | 2018-10-22 |  |  |  | Not Started | 6 | 0% | FIFI - PIGALLE - Allocation/Unallocation - DTS not in M3 | OHWEE | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - PIGALLE - Allocation/Unallocation - Unit Tests | JC 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-10-18 | 2018-10-19 |  |  |  | Not Started | 1 | 0% | FIFI - PIGALLE - Allocation/Unallocation - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 3 | 4.5 | 8.5 | 30
31 | 2 | LOUIS | M3 | Louis | Purchase Order | FIFI - LOUIS - Purchase Order | Creation/Update/Cancellation | INTERFACE | COMPLEX |  |  | Arnaud+CL |  |  |  | Not Started | FIFI - LOUIS - Purchase Order - Functional Specification | Arnaud | 3 | 3.9 | 2018-07-27 | 2018-08-01 |  |  |  | Not Started | 3 | 0% | FIFI - LOUIS - Purchase Order - Technical Specification | 3Kles | 2 | 2.6 | 2018-08-06 | 2018-08-08 |  |  |  | Not Started | 2 | 0% | FIFI - LOUIS - Purchase Order - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 8 | 10.4 | 2018-08-09 | 2018-08-24 |  |  |  | Not Started | 8 | 0% | FIFI - LOUIS - Purchase Order - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - LOUIS - Purchase Order - Unit Tests | Arnaud | 2 | 3Kles | 2 | 2.6 | 2018-08-17 | 2018-08-21 |  |  |  | Not Started | 2 | 0% | FIFI - LOUIS - Purchase Order - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 31 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.026235 | 0.026235 | 0.026235 | 0.026235 | 0.026235 | 0
32 | 2 | LOUIS | Louis | M3 | PO Confirmation | FIFI - LOUIS - PO Confirmation | Creation/Update | INTERFACE | COMPLEX |  |  | Arnaud+CL |  |  |  | Not Started | FIFI - LOUIS - PO Confirmation - Functional Specification | Arnaud | 3 | 3.9 | 2018-07-27 | 2018-08-01 |  |  |  | Not Started | 3 | 0% | FIFI - LOUIS - PO Confirmation - Technical Specification | 3Kles | 2 | 2.6 | 2018-08-06 | 2018-08-08 |  |  |  | Not Started | 2 | 0% | FIFI - LOUIS - PO Confirmation - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 8 | 10.4 | 2018-08-09 | 2018-08-24 |  |  |  | Not Started | 8 | 0% | FIFI - LOUIS - PO Confirmation - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - LOUIS - PO Confirmation - Unit Tests | Arnaud | 2 | 3Kles | 2 | 2.6 | 2018-08-17 | 2018-08-21 |  |  |  | Not Started | 2 | 0% | FIFI - LOUIS - PO Confirmation - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 32 |  | 42.5
33 | 2 | EXPERIENCE | M3 | Experience | Product | FIFI - EXPERIENCE - Product | Creation/Update | INTERFACE | MEDIUM |  |  | 3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Product - Functional Specification | Arnaud | 2 | 2.6 | 2018-07-30 | 2018-08-01 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Product - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-08-06 | 2018-08-07 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Product - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 6 | 7.8 | 2018-08-09 | 2018-08-21 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Product - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Product - Unit Tests | Arnaud | 1 | 3Kles | 1 | 1.3 | 2018-08-17 | 2018-08-20 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Product - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 33 | 3 | 42.5 | 5 | 2018-09-01 | 2019-02-01 | 2018-09-01: 8.5; 2018-10-01: 8.5; 2018-11-01: 8.5; 2018-12-01: 8.5; 2019-01-01: 8.5
34 | 2 | EXPERIENCE | M3 | Experience | Master Supplier | FIFI - EXPERIENCE - Master Supplier | Creation/Update | INTERFACE | MEDIUM |  |  | 3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Master Supplier - Functional Specification | Arnaud | 2 | 2.6 | 2018-08-03 | 2018-08-07 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Master Supplier - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-08-10 | 2018-08-13 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Master Supplier - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 6 | 7.8 | 2018-08-16 | 2018-08-27 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Master Supplier - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Master Supplier - Unit Tests | Arnaud | 1 | 3Kles | 1 | 1.3 | 2018-08-23 | 2018-08-24 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Master Supplier - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 34 |  | TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 0
35 | 2 | EXPERIENCE | M3 | Experience | Master Customer | FIFI - EXPERIENCE - Master Customer | Creation/Update | INTERFACE | MEDIUM |  |  | 3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Master Customer - Functional Specification | Arnaud | 2 | 2.6 | 2018-08-08 | 2018-08-10 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Master Customer - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-08-16 | 2018-08-17 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Master Customer - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 6 | 7.8 | 2018-08-21 | 2018-08-30 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Master Customer - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Master Customer - Unit Tests | Arnaud | 1 | 3Kles | 1 | 1.3 | 2018-08-28 | 2018-08-29 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Master Customer - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 35 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.47222 | 0.47222 | 0.47222 | 0.47222 | 0.47222 | 0
36 | 2 | EXPERIENCE | Experience | M3 | PO Reception | FIFI - EXPERIENCE - PO Reception | Creation | INTERFACE | COMPLEX |  |  | Arnaud+CL |  |  |  | Not Started | FIFI - EXPERIENCE - PO Reception - Functional Specification | Arnaud | 3 | 3.9 | 2018-08-15 | 2018-08-20 |  |  |  | Not Started | 3 | 0% | FIFI - EXPERIENCE - PO Reception - Technical Specification | 3Kles | 2 | 2.6 | 2018-08-23 | 2018-08-27 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - PO Reception - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 8 | 10.4 | 2018-08-28 | 2018-09-11 |  |  |  | Not Started | 8 | 0% | FIFI - EXPERIENCE - PO Reception - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - EXPERIENCE - PO Reception - Unit Tests | Arnaud | 2 | 3Kles | 2 | 2.6 | 2018-09-04 | 2018-09-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - PO Reception - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 36 |  | 42.5
37 | 2 | EXPERIENCE | M3 | Experience | Supplier Return | FIFI - EXPERIENCE - Supplier Return | Creation | INTERFACE | COMPLEX |  |  | Arnaud+CL |  |  |  | Not Started | FIFI - EXPERIENCE - Supplier Return - Functional Specification | Arnaud | 3 | 3.9 | [5 empty] | Not Started | 3 | 0% | FIFI - EXPERIENCE - Supplier Return - Technical Specification | 3Kles | 2 | 2.6 | [5 empty] | Not Started | 2 | 0% | FIFI - EXPERIENCE - Supplier Return - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 8 | 10.4 | [5 empty] | Not Started | 8 | 0% | FIFI - EXPERIENCE - Supplier Return - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - EXPERIENCE - Supplier Return - Unit Tests | Arnaud | 2 | 3Kles | 2 | 2.6 | [5 empty] | Not Started | 2 | 0% | FIFI - EXPERIENCE - Supplier Return - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 37 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 2 | EXPERIENCE | M3 | Experience | DO | FIFI - EXPERIENCE - DO |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - DO - Functional Specification | Arnaud | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - DO - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - DO - DETAILED TECH SPECIFICATION | Arnaud | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - DO - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - DO - Unit Tests | Arnaud | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - DO - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 38 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | EXPERIENCE | Experience | M3 | DO Reception | FIFI - EXPERIENCE - DO Reception |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - DO Reception - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - DO Reception - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - DO Reception - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - DO Reception - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - DO Reception - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - DO Reception - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 39
40 | 2 | EXPERIENCE | M3 | Experience | Picking List | FIFI - EXPERIENCE - Picking List |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Picking List - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Picking List - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Picking List - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Picking List - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Picking List - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Picking List - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 40 | LOT | WORKLOAD DEV. HORS M3 | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
41 | 2 | EXPERIENCE | Experience | M3 | Pick&packing | FIFI - EXPERIENCE - Pick&packing |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Pick&packing - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Pick&packing - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Pick&packing - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Pick&packing - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Pick&packing - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Pick&packing - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 41 | LOT | WORKLOAD DEV. HORS M3 | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
42 | 2 | EXPERIENCE | Experience | M3 | Releasing the stock | FIFI - EXPERIENCE - Releasing the stock |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Releasing the stock - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Releasing the stock - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Releasing the stock - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Releasing the stock - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Releasing the stock - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Releasing the stock - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 42 | 1 | 192 | 6 | 2018-08-01 | 2019-02-01 | 2018-08-01: 21.3333; 2018-09-01: 32; 2018-10-01: 32; 2018-11-01: 32; 2018-12-01: 32; 2019-01-01: 32
43 | 2 | EXPERIENCE | Experience | M3 | Expedition creation | FIFI - EXPERIENCE - Expedition creation |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Expedition creation - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Expedition creation - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Expedition creation - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Expedition creation - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Expedition creation - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Expedition creation - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 43 |  | 127.5
44 | 2 | EXPERIENCE | M3 | Experience | Customer Return | FIFI - EXPERIENCE - Customer Return |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Customer Return - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Customer Return - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Customer Return - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Customer Return - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Customer Return - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Customer Return - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 44 |  | 127.5
45 | 2 | EXPERIENCE | Experience | M3 | Reception+QC of Customer Return | FIFI - EXPERIENCE - Reception+QC of Customer Retunr |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 45 | 2 | 228.5 | 6 | 2018-08-01 | 2019-02-01 | 2018-08-01: 25.3889; 2018-09-01: 38.0833; 2018-10-01: 38.0833; 2018-11-01: 38.0833; 2018-12-01: 38.0833; 2019-01-01: 38.0833
46 | 2 | EXPERIENCE | Experience | M3 | Inventory+variance | FIFI - EXPERIENCE - Inventory+variance |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Inventory+variance - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Inventory+variance - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Inventory+variance - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Inventory+variance - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Inventory+variance - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 46 | 3 | 78 | 5 | 2018-10-01 | 2019-03-01 | 2018-10-01: 15.6; 2018-11-01: 15.6; 2018-12-01: 15.6; 2019-01-01: 15.6; 2019-02-01: 15.6
47 | 2 | EXPERIENCE | M3 | Experience | Inventory+variance | FIFI - EXPERIENCE - Inventory+variance |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Inventory+variance - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Inventory+variance - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Inventory+variance - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Inventory+variance - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Inventory+variance - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 47 |  | TOTAL |  |  |  | 0 | 0 | 0 | 0 | 46.7222 | 70.0833 | 85.6833 | 85.6833 | 85.6833 | 85.6833 | 15.6
48 | 2 | EXPERIENCE | M3 | Experience | Retail Price | FIFI - EXPERIENCE - Retail Price |  | INTERFACE | MEDIUM |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Retail Price - Functional Specification | Anne-Marie 3Kles TBD | 2 | 2.6 | 2018-11-02 | 2018-11-06 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Retail Price - Technical Specification | 3Kles | 1.5 | 1.95 | 2018-11-09 | 2018-11-12 |  |  |  | Not Started | 1.5 | 0% | FIFI - EXPERIENCE - Retail Price - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 6 | 7.8 | 2018-11-14 | 2018-11-23 |  |  |  | Not Started | 6 | 0% | FIFI - EXPERIENCE - Retail Price - DTS not in M3 | Sysdat | 4.5 |  | 8.5 | 11.05 | [5 empty] | Not Started | 8.5 | 0% | FIFI - EXPERIENCE - Retail Price - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-21 | 2018-11-22 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Retail Price - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 4.5 | 8.5 | 2 | 4.5 | 8.5 | 48 |  | TOTAL |  |  |  | 0 | 0 | 0 | 0 | 72.1111 | 108.1667 | 139.3667 | 139.3667 | 139.3667 | 139.3667 | 31.2
49 | 2 | EXPERIENCE | Experience | M3 | Stock Adjustment | FIFI - EXPERIENCE - Stock Adjustment |  | INTERFACE | COMPLEX |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Stock Adjustment - Functional Specification | Anne-Marie 3Kles TBD | 3 | 3.9 | 2018-11-02 | 2018-11-07 |  |  |  | Not Started | 3 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Technical Specification | 3Kles | 2 | 2.6 | 2018-11-12 | 2018-11-14 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 8 | 10.4 | 2018-11-15 | 2018-11-29 |  |  |  | Not Started | 8 | 0% | FIFI - EXPERIENCE - Stock Adjustment - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Unit Tests | Anne-Marie 3Kles TBD | 2 | 3Kles | 2 | 2.6 | 2018-11-22 | 2018-11-26 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 49 |  | ETP |  |  |  | 0 | 0 | 0 | 0 | 2.5957 | 3.8935 | 4.7602 | 4.7602 | 4.7602 | 4.7602 | 0.86667
50 | 2 | EXPERIENCE | M3 | Experience | Stock Adjustment | FIFI - EXPERIENCE - Stock Adjustment |  | INTERFACE | COMPLEX |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Stock Adjustment - Functional Specification | Anne-Marie 3Kles TBD | 3 | 3.9 | 2018-11-02 | 2018-11-07 |  |  |  | Not Started | 3 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Technical Specification | 3Kles | 2 | 2.6 | 2018-11-12 | 2018-11-14 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 8 | 10.4 | 2018-11-15 | 2018-11-29 |  |  |  | Not Started | 8 | 0% | FIFI - EXPERIENCE - Stock Adjustment - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Unit Tests | Anne-Marie 3Kles TBD | 2 | 3Kles | 2 | 2.6 | 2018-11-22 | 2018-11-26 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Stock Adjustment - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 50 |  | 753.5
51 | 2 | EXPERIENCE | M3 | Experience | Sending Printout (Invoice, proforma, etc..) | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) |  | INTERFACE | LOW |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Functional Specification | Anne-Marie 3Kles TBD | 1 | 1.3 | 2018-11-02 | 2018-11-05 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-11-08 | 2018-11-08 |  |  |  | Not Started | 0.5 | 0% | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 0.5 | 3Kles | 3 | 3.9 | 2018-11-13 | 2018-11-16 |  |  |  | Not Started | 3 | 0% | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - DTS not in M3 | Sysdat | 2.5 |  | 4 | 5.2 | [5 empty] | Not Started | 4 | 0% | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Unit Tests | Anne-Marie 3Kles TBD | 1 | 3Kles | 1 | 1.3 | 2018-11-20 | 2018-11-21 |  |  |  | Not Started | 1 | 0% | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4.5 | 2 | 2.5 | 4 | 51
52 | 2 | EXPERIENCE | Experience | M3 | Other | FIFI - EXPERIENCE - Other |  | INTERFACE | COMPLEX |  |  | AMB+3Kles |  |  |  | Not Started | FIFI - EXPERIENCE - Other - Functional Specification | Anne-Marie 3Kles TBD | 3 | 3.9 | 2019-01-03 | 2019-01-08 |  |  |  | Not Started | 3 | 0% | FIFI - EXPERIENCE - Other - Technical Specification | 3Kles | 2 | 2.6 | 2019-01-11 | 2019-01-15 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Other - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1.5 | 3Kles | 8 | 10.4 | 2019-01-16 | 2019-01-30 |  |  |  | Not Started | 8 | 0% | FIFI - EXPERIENCE - Other - DTS not in M3 | Sysdat | 6.5 |  | 11.5 | 14.95 | [5 empty] | Not Started | 11.5 | 0% | FIFI - EXPERIENCE - Other - Unit Tests | Anne-Marie 3Kles TBD | 2 | 3Kles | 2 | 2.6 | 2019-01-23 | 2019-01-25 |  |  |  | Not Started | 2 | 0% | FIFI - EXPERIENCE - Other - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 6.5 | 12 | 2 | 6.5 | 11.5 | 52
53 | 1 | M3 | M3 | M3 | PURCHASE ORDER FORM | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM |  | FORMS | MEDIUM | [6 empty] | Not Started | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Functional Specification | Arnaud | 1 | 1.3 | [5 empty] | Not Started | 1 | 0% | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Technical Specification | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - DETAILED TECH SPECIFICATION | Arnaud | 1 | 3Kles | 3 | 3.9 | [5 empty] | Not Started | 3 | 0% | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - DTS not in M3 | [10 empty] | Not Started | 0 | 0% | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Unit Tests | Arnaud | 0.5 | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4 | 1 | 0 | 0 | 53
53 | 1 | M3 | M3 | M3 | PROFORMA FIRST COST FORM | FIFI - M3 PRINTOUT - PROFORMA First Cost |  | FORMS | MEDIUM | [6 empty] | Not Started | FIFI - M3 PRINTOUT - PROFORMA First Cost - Functional Specification | Eric | 1 | 1.3 | [5 empty] | Not Started | 1 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Technical Specification | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION | Eric | 1 | 3Kles | 3 | 3.9 | [5 empty] | Not Started | 3 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - DTS not in M3 | [10 empty] | Not Started | 0 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Unit Tests | Eric | 0.5 | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4 | 1 | 0 | 0 | 53
54 | 1 | M3 | M3 | M3 | PROFORMA OUTBOUND CLINT FORM | FIFI - M3 PRINTOUT - PROFORMA First Cost |  | FORMS | MEDIUM | [6 empty] | Not Started | FIFI - M3 PRINTOUT - PROFORMA First Cost - Functional Specification | Anne-Marie 3Kles TBD | 1 | 1.3 | [5 empty] | Not Started | 1 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Technical Specification | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1 | 3Kles | 3 | 3.9 | [5 empty] | Not Started | 3 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - DTS not in M3 | [10 empty] | Not Started | 0 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Unit Tests | Anne-Marie 3Kles TBD | 0.5 | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PROFORMA First Cost - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4 | 1 | 0 | 0 | 54
55 | 1 | M3 | M3 | M3 | PACKING LIST FORM | FIFI - M3 PRINTOUT - PACKING LIST FORM |  | FORMS | MEDIUM | [6 empty] | Not Started | FIFI - M3 PRINTOUT - PACKING LIST FORM - Functional Specification | Anne-Marie 3Kles TBD | 1 | 1.3 | [5 empty] | Not Started | 1 | 0% | FIFI - M3 PRINTOUT - PACKING LIST FORM - Technical Specification | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PACKING LIST FORM - DETAILED TECH SPECIFICATION | Anne-Marie 3Kles TBD | 1 | 3Kles | 3 | 3.9 | [5 empty] | Not Started | 3 | 0% | FIFI - M3 PRINTOUT - PACKING LIST FORM - DTS not in M3 | [10 empty] | Not Started | 0 | 0% | FIFI - M3 PRINTOUT - PACKING LIST FORM - Unit Tests | Anne-Marie 3Kles TBD | 0.5 | 3Kles | 0.5 | 0.65 | [5 empty] | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - PACKING LIST FORM - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4 | 1 | 0 | 0 | 55
56 | 1 | M3 | M3 | M3 | INVOICE/CREDIT NOTE FORM (rep fiscale) | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM |  | FORMS | MEDIUM | [6 empty] | Not Started | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Functional Specification | Rodolph (3Kles) | 1 | 1.3 | 2018-06-26 | 2018-06-27 | 7 | 2 | 2018-07-10 | Not Started | 9 | 77.78% | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Technical Specification | 3Kles | 0.5 | 0.65 | 2018-07-02 | 2018-07-02 |  |  |  | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - DETAILED TECH SPECIFICATION | Rodolph (3Kles) | 1 | 3Kles | 3 | 3.9 | 2018-07-05 | 2018-07-10 |  |  |  | Not Started | 3 | 0% | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - DTS not in M3 | [10 empty] | Not Started | 0 | 0% | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Unit Tests | Rodolph (3Kles) | 0.5 | 3Kles | 0.5 | 0.65 | 2018-07-12 | 2018-07-12 |  |  |  | Not Started | 0.5 | 0% | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 2.5 | 4 | 1 | 0 | 0 | 56
57 | 1 | PALOMA | M3 | Datawarehouse | TBC | FIFI - PALOMA - TBC |  | INTERFACE |  |  |  | Atef |  |  |  | Not Started | FIFI - PALOMA - TBC - Functional Specification | Atef | [7 empty] | Not Started |  | 0% | FIFI - PALOMA - TBC - Technical Specification | Atef | [7 empty] | Not Started |  | 0% | FIFI - PALOMA - TBC - DETAILED TECH SPECIFICATION | Atef |  | Atef | [7 empty] | Not Started |  | 0% | FIFI - PALOMA - TBC - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - PALOMA - TBC - Unit Tests | Atef |  | Atef | [7 empty] | Not Started |  | 0% | FIFI - PALOMA - TBC - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 1 | 0 | 0 | 57
58 | 2 | GETPAID | GetPaid | M3 | TBD | FIFI - GETPAID - |  | INTERFACE | [7 empty] | Not Started | FIFI - GETPAID - - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - GETPAID - - Technical Specification | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - GETPAID - - DETAILED TECH SPECIFICATION | 0 |  | 3Kles | [7 empty] | Not Started |  | 0% | FIFI - GETPAID - - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - GETPAID - - Unit Tests | 0 | [9 empty] | Not Started |  | 0% | FIFI - GETPAID - - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 2 | 0 | 0 | 58
59 | 2 | GETPAID | M3 | GetPaid | TBD | FIFI - GETPAID - |  | INTERFACE | [7 empty] | Not Started | FIFI - GETPAID - - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - GETPAID - - Technical Specification | [8 empty] | Not Started |  | 0% | FIFI - GETPAID - - DETAILED TECH SPECIFICATION | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - GETPAID - - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - GETPAID - - Unit Tests | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - GETPAID - - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 2 | 0 | 0 | 59 | [5 empty] | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497
60 | 3 | Y2 | M3 | Y2 | TBC | FIFI - Y2 - TBC |  | INTERFACE | [7 empty] | Not Started | FIFI - Y2 - TBC - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Technical Specification | [8 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Unit Tests | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 3 | 0 | 0 | 60 | LOT | WORKLOAD FUNCT. HORS M3 | Durée | Mois départ | Mois Fin | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01
61 | 3 | Y2 | Y2 | M3 | TBC | FIFI - Y2 - TBC |  | INTERFACE | [7 empty] | Not Started | FIFI - Y2 - TBC - Functional Specification | [8 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Technical Specification | [8 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - DTS not in M3 | [10 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Unit Tests | 0 |  | 0 | [7 empty] | Not Started |  | 0% | FIFI - Y2 - TBC - Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 3 | 0 | 0 | 61 | 1 | 116 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 19.3333; 2018-08-01: 12.8889; 2018-09-01: 19.3333; 2018-10-01: 19.3333; 2018-11-01: 19.3333; 2018-12-01: 19.3333
61 | 3 | TEST | TEST | TEST | TBC | TEST |  | INTERFACE | [7 empty] | Not Started | TEST - Functional Specification |  | 1 | 1.3 | 2018-06-26 | 2018-06-27 | 7 | 2 | 2018-07-10 | On Going | 9 | 90% | TEST - Technical Specification |  | 0.5 | 0.65 | 2018-07-02 | 2018-07-02 |  |  |  | On Going | 0.5 | 0% | test - DETAILED TECH SPECIFICATION | 0 |  | 0 | [7 empty] | Not Started |  | 0% | test- DTS not in M3 | [10 empty] | Not Started |  | 0% | test - Unit Tests | 0 |  | 0 | [7 empty] | Not Started |  | 0% | test- Integration Tests | [8 empty] | 0 |  | Not Started | 0 | #REF! | 0 | 0 | 3 | 0 | 0 | 61 | 1 | 116 | 6 | 2018-07-01 | 2019-01-01 | 2018-07-01: 19.3333; 2018-08-01: 12.8889; 2018-09-01: 19.3333; 2018-10-01: 19.3333; 2018-11-01: 19.3333; 2018-12-01: 19.3333
UPDATE
Note on AP3: Sophie Boisseau: 1/2 FLOW IN M3

## AGGREGATE
DELIVERABLE | TYPE | ID | Funct. Resp. | PLANNED WORKLOAD FUNCT. | Dev. Resp. | PLANNED WORKLOAD DEV. | PLANNED START DATE | ESTIMATED END DATE | STATUS | EAC | % WORKLOAD COMPLETED
FIFI - PRICING - Sales price - Functional Specification | FUNCTIONAL SPECIFICATION | 1 | Maxime |  | 3Kles |  | 2018-10-01 |  | Not Started | 1 | 0%
FIFI - PRICING - Retail price - Functional Specification | FUNCTIONAL SPECIFICATION | 2 | Maxime |  | 3Kles |  | 2018-10-02 |  | Not Started | 1 | 0%
FIFI - PRICING - Master Client - Functional Specification | FUNCTIONAL SPECIFICATION | 3 | Maxime |  | CL TBD |  | 2018-10-03 |  | Not Started | 2 | 0%
FIFI - PRICING - Client Order - Functional Specification | FUNCTIONAL SPECIFICATION | 4 | Maxime |  | CL TBD |  | 2018-10-08 |  | Not Started | 2 | 0%
FIFI - PLM - Item+attributes (weight, dimension, etc..) - Functional Specification | FUNCTIONAL SPECIFICATION | 5 | 3Kles (TBD) |  | Centric/3Kles |  | 2018-10-10 |  | Not Started | 5 | 0%
FIFI - PLM - Purchase Price - Functional Specification | FUNCTIONAL SPECIFICATION | 6 | 3Kles (TBD) |  | Centric/3Kles |  | 2018-10-22 |  | Not Started | 5 | 0%
FIFI - PLM - Madein - Functional Specification | FUNCTIONAL SPECIFICATION | 7 | 3Kles (TBD) |  | 3Kles |  | 2018-10-01 |  | Not Started | 5 | 0%
FIFI - PLM - HS Code - Functional Specification | FUNCTIONAL SPECIFICATION | 8 | 3Kles (TBD) |  | 3Kles |  | 2018-10-09 |  | Not Started | 5 | 0%
FIFI - PLM - Composition - Functional Specification | FUNCTIONAL SPECIFICATION | 9 | 3Kles (TBD) |  | 3Kles |  | 2018-10-17 |  | Not Started | 5 | 0%
FIFI - PLM - Offer - Functional Specification | FUNCTIONAL SPECIFICATION | 10 | 3Kles (TBD) |  | 3Kles |  | 2018-10-25 |  | Not Started | 5 | 0%
FIFI - PLM - Offer - Functional Specification | FUNCTIONAL SPECIFICATION | 11 | 3Kles (TBD) |  | 3Kles |  | 2018-11-05 |  | Not Started | 5 | 0%
FIFI - N/A - Items - Functional Specification | FUNCTIONAL SPECIFICATION | 12 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - N/A - Retail price - Functional Specification | FUNCTIONAL SPECIFICATION | 13 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - OSO - Items - Functional Specification | FUNCTIONAL SPECIFICATION | 14 | TBConfirmed |  | 3Kles |  | 2019-01-03 |  | Not Started | 3 | 0%
FIFI - OSO - Prices - Functional Specification | FUNCTIONAL SPECIFICATION | 15 | TBConfirmed |  | 3Kles |  | 2019-01-03 |  | Not Started | 2 | 0%
FIFI - OSO - Client List - Functional Specification | FUNCTIONAL SPECIFICATION | 16 | TBConfirmed |  | 3Kles |  | 2019-01-03 |  | Not Started | 2 | 0%
FIFI - OSO - Boutique Order - Functional Specification | FUNCTIONAL SPECIFICATION | 17 | TBConfirmed |  | 3Kles |  | 2019-01-03 |  | Not Started | 2 | 0%
FIFI - WSH - Items - Functional Specification | FUNCTIONAL SPECIFICATION | 18 | TBConfirmed |  | 3Kles |  | 2018-09-10 |  | Not Started | 2 | 0%
FIFI - WSH - Offer - Functional Specification | FUNCTIONAL SPECIFICATION | 19 | TBConfirmed |  | 3Kles |  | 2018-09-14 |  | Not Started | 2 | 0%
FIFI - WSH - Prices - Functional Specification | FUNCTIONAL SPECIFICATION | 20 | TBConfirmed |  | 3Kles |  | 2018-09-16 |  | Not Started | 2 | 0%
FIFI - WSH - Client - Functional Specification | FUNCTIONAL SPECIFICATION | 21 | TBConfirmed |  | 3Kles |  | 2018-09-18 |  | Not Started | 1 | 0%
FIFI - WSH - Stock ? - Functional Specification | FUNCTIONAL SPECIFICATION | 22 | TBConfirmed |  | 3Kles |  | 2018-09-10 |  | Not Started | 2 | 0%
FIFI - WSH - Exclusivity + Drops - Functional Specification | FUNCTIONAL SPECIFICATION | 23 | TBConfirmed |  | 3Kles |  | 2018-09-20 |  | Not Started | 2 | 0%
FIFI - WSH - Client Order - Functional Specification | FUNCTIONAL SPECIFICATION | 24 | TBConfirmed |  | 3Kles |  | 2018-09-17 |  | Not Started | 1 | 0%
FIFI - WSH - LINELIST - Functional Specification | FUNCTIONAL SPECIFICATION | 25 | TBConfirmed |  | 3Kles |  | 2018-11-15 |  | Not Started | 2 | 0%
FIFI - PIGALLE - Client Order/DO - Functional Specification | FUNCTIONAL SPECIFICATION | 26 | JC 3Kles TBD |  | 3Kles |  | 2018-09-25 |  | Not Started | 3 | 0%
FIFI - PIGALLE - Stock - Functional Specification | FUNCTIONAL SPECIFICATION | 27 | JC 3Kles TBD |  | 3Kles |  | 2018-09-17 |  | Not Started | 1 | 0%
FIFI - PIGALLE - Master Client - Functional Specification | FUNCTIONAL SPECIFICATION | 28 | JC 3Kles TBD |  | 3Kles |  | 2018-09-18 |  | Not Started | 2 | 0%
FIFI - PIGALLE - Assortment - Functional Specification | FUNCTIONAL SPECIFICATION | 29 | JC 3Kles TBD |  | 3Kles |  | 2018-09-20 |  | Not Started | 2 | 0%
FIFI - PIGALLE - Allocation/Unallocation - Functional Specification | FUNCTIONAL SPECIFICATION | 30 | JC 3Kles TBD |  | 3Kles |  | 2018-10-01 |  | Not Started | 2 | 0%
FIFI - LOUIS - Purchase Order - Functional Specification | FUNCTIONAL SPECIFICATION | 31 | Arnaud |  | 3Kles |  | 2018-07-27 |  | Not Started | 3 | 0%
FIFI - LOUIS - PO Confirmation - Functional Specification | FUNCTIONAL SPECIFICATION | 32 | Arnaud |  | 3Kles |  | 2018-07-27 |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - Product - Functional Specification | FUNCTIONAL SPECIFICATION | 33 | Arnaud |  | 3Kles |  | 2018-07-30 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Master Supplier - Functional Specification | FUNCTIONAL SPECIFICATION | 34 | Arnaud |  | 3Kles |  | 2018-08-03 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Master Customer - Functional Specification | FUNCTIONAL SPECIFICATION | 35 | Arnaud |  | 3Kles |  | 2018-08-08 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - PO Reception - Functional Specification | FUNCTIONAL SPECIFICATION | 36 | Arnaud |  | 3Kles |  | 2018-08-15 |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - Supplier Return - Functional Specification | FUNCTIONAL SPECIFICATION | 37 | Arnaud |  | 3Kles |  |  |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - DO - Functional Specification | FUNCTIONAL SPECIFICATION | 38 | Arnaud |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - DO Reception - Functional Specification | FUNCTIONAL SPECIFICATION | 39 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Picking List - Functional Specification | FUNCTIONAL SPECIFICATION | 40 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Pick&packing - Functional Specification | FUNCTIONAL SPECIFICATION | 41 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Releasing the stock - Functional Specification | FUNCTIONAL SPECIFICATION | 42 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Expedition creation - Functional Specification | FUNCTIONAL SPECIFICATION | 43 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Customer Return - Functional Specification | FUNCTIONAL SPECIFICATION | 44 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Functional Specification | FUNCTIONAL SPECIFICATION | 45 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Inventory+variance - Functional Specification | FUNCTIONAL SPECIFICATION | 46 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Inventory+variance - Functional Specification | FUNCTIONAL SPECIFICATION | 47 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Retail Price - Functional Specification | FUNCTIONAL SPECIFICATION | 48 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Functional Specification | FUNCTIONAL SPECIFICATION | 49 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Functional Specification | FUNCTIONAL SPECIFICATION | 50 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Functional Specification | FUNCTIONAL SPECIFICATION | 51 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-02 |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Other - Functional Specification | FUNCTIONAL SPECIFICATION | 52 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2019-01-03 |  | Not Started | 3 | 0%
FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Functional Specification | FUNCTIONAL SPECIFICATION | 53 | Arnaud |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Functional Specification | FUNCTIONAL SPECIFICATION | 54 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Functional Specification | FUNCTIONAL SPECIFICATION | 55 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - M3 PRINTOUT - PACKING LIST FORM - Functional Specification | FUNCTIONAL SPECIFICATION | 56 | Rodolph (3Kles) |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Functional Specification | FUNCTIONAL SPECIFICATION | 57 | Atef |  | Atef |  | 2018-06-26 | 2018-07-10 | Not Started | 9 | 77.78%
FIFI - PALOMA - TBC - Functional Specification | FUNCTIONAL SPECIFICATION | 58 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - Functional Specification | FUNCTIONAL SPECIFICATION | 59 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - Functional Specification | FUNCTIONAL SPECIFICATION | 60 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - Functional Specification | FUNCTIONAL SPECIFICATION | 61 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - Functional Specification | FUNCTIONAL SPECIFICATION | 62 | #N/A |  | #N/A |  |  |  | Not Started |  | 0%
TEST - Functional Specification | FUNCTIONAL SPECIFICATION | 63 | #N/A |  | #N/A |  | 2018-06-26 | 2018-07-10 | On Going | 9 | 90%
FIFI - PRICING - Sales price - Technical Specification | TECHNICAL SPECIFICATION | 1 | Maxime |  | 3Kles |  | 2018-10-05 |  | Not Started | 0.5 | 0%
FIFI - PRICING - Retail price - Technical Specification | TECHNICAL SPECIFICATION | 2 | Maxime |  | 3Kles |  | 2018-10-08 |  | Not Started | 0.5 | 0%
FIFI - PRICING - Master Client - Technical Specification | TECHNICAL SPECIFICATION | 3 | Maxime |  | CL TBD |  | 2018-10-10 |  | Not Started | 1.5 | 0%
FIFI - PRICING - Client Order - Technical Specification | TECHNICAL SPECIFICATION | 4 | Maxime |  | CL TBD |  | 2018-10-15 |  | Not Started | 1.5 | 0%
FIFI - PLM - Item+attributes (weight, dimension, etc..) - Technical Specification | TECHNICAL SPECIFICATION | 5 | 3Kles (TBD) |  | Centric/3Kles |  | 2018-10-23 |  | Not Started | 4 | 0%
FIFI - PLM - Purchase Price - Technical Specification | TECHNICAL SPECIFICATION | 6 | 3Kles (TBD) |  | Centric/3Kles |  | 2018-11-05 |  | Not Started | 4 | 0%
FIFI - PLM - Madein - Technical Specification | TECHNICAL SPECIFICATION | 7 | 3Kles (TBD) |  | 3Kles |  | 2018-10-12 |  | Not Started | 4 | 0%
FIFI - PLM - HS Code - Technical Specification | TECHNICAL SPECIFICATION | 8 | 3Kles (TBD) |  | 3Kles |  | 2018-10-22 |  | Not Started | 4 | 0%
FIFI - PLM - Composition - Technical Specification | TECHNICAL SPECIFICATION | 9 | 3Kles (TBD) |  | 3Kles |  | 2018-10-30 |  | Not Started | 4 | 0%
FIFI - PLM - Offer - Technical Specification | TECHNICAL SPECIFICATION | 10 | 3Kles (TBD) |  | 3Kles |  | 2018-11-08 |  | Not Started | 4 | 0%
FIFI - PLM - Offer - Technical Specification | TECHNICAL SPECIFICATION | 11 | 3Kles (TBD) |  | 3Kles |  | 2018-11-16 |  | Not Started | 4 | 0%
FIFI - N/A - Items - Technical Specification | TECHNICAL SPECIFICATION | 12 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - N/A - Retail price - Technical Specification | TECHNICAL SPECIFICATION | 13 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - OSO - Items - Technical Specification | TECHNICAL SPECIFICATION | 14 | TBConfirmed |  | 3Kles |  | 2019-01-11 |  | Not Started | 2 | 0%
FIFI - OSO - Prices - Technical Specification | TECHNICAL SPECIFICATION | 15 | TBConfirmed |  | 3Kles |  | 2019-01-10 |  | Not Started | 1.5 | 0%
FIFI - OSO - Client List - Technical Specification | TECHNICAL SPECIFICATION | 16 | TBConfirmed |  | 3Kles |  | 2019-01-10 |  | Not Started | 1.5 | 0%
FIFI - OSO - Boutique Order - Technical Specification | TECHNICAL SPECIFICATION | 17 | TBConfirmed |  | 3Kles |  | 2019-01-10 |  | Not Started | 1.5 | 0%
FIFI - WSH - Items - Technical Specification | TECHNICAL SPECIFICATION | 18 | TBConfirmed |  | 3Kles |  | 2018-09-17 |  | Not Started | 1.5 | 0%
FIFI - WSH - Offer - Technical Specification | TECHNICAL SPECIFICATION | 19 | TBConfirmed |  | 3Kles |  | 2018-09-21 |  | Not Started | 1.5 | 0%
FIFI - WSH - Prices - Technical Specification | TECHNICAL SPECIFICATION | 20 | TBConfirmed |  | 3Kles |  | 2018-09-21 |  | Not Started | 1.5 | 0%
FIFI - WSH - Client - Technical Specification | TECHNICAL SPECIFICATION | 21 | TBConfirmed |  | 3Kles |  | 2018-09-24 |  | Not Started | 0.5 | 0%
FIFI - WSH - Stock ? - Technical Specification | TECHNICAL SPECIFICATION | 22 | TBConfirmed |  | 3Kles |  | 2018-09-17 |  | Not Started | 1.5 | 0%
FIFI - WSH - Exclusivity + Drops - Technical Specification | TECHNICAL SPECIFICATION | 23 | TBConfirmed |  | 3Kles |  | 2018-09-27 |  | Not Started | 1.5 | 0%
FIFI - WSH - Client Order - Technical Specification | TECHNICAL SPECIFICATION | 24 | TBConfirmed |  | 3Kles |  | 2018-09-21 |  | Not Started | 0.5 | 0%
FIFI - WSH - LINELIST - Technical Specification | TECHNICAL SPECIFICATION | 25 | TBConfirmed |  | 3Kles |  | 2018-11-22 |  | Not Started | 1.5 | 0%
FIFI - PIGALLE - Client Order/DO - Technical Specification | TECHNICAL SPECIFICATION | 26 | JC 3Kles TBD |  | 3Kles |  | 2018-10-03 |  | Not Started | 2 | 0%
FIFI - PIGALLE - Stock - Technical Specification | TECHNICAL SPECIFICATION | 27 | JC 3Kles TBD |  | 3Kles |  | 2018-09-21 |  | Not Started | 0.5 | 0%
FIFI - PIGALLE - Master Client - Technical Specification | TECHNICAL SPECIFICATION | 28 | JC 3Kles TBD |  | 3Kles |  | 2018-09-25 |  | Not Started | 1.5 | 0%
FIFI - PIGALLE - Assortment - Technical Specification | TECHNICAL SPECIFICATION | 29 | JC 3Kles TBD |  | 3Kles |  | 2018-09-27 |  | Not Started | 1.5 | 0%
FIFI - PIGALLE - Allocation/Unallocation - Technical Specification | TECHNICAL SPECIFICATION | 30 | JC 3Kles TBD |  | 3Kles |  | 2018-10-08 |  | Not Started | 1.5 | 0%
FIFI - LOUIS - Purchase Order - Technical Specification | TECHNICAL SPECIFICATION | 31 | Arnaud |  | 3Kles |  | 2018-08-06 |  | Not Started | 2 | 0%
FIFI - LOUIS - PO Confirmation - Technical Specification | TECHNICAL SPECIFICATION | 32 | Arnaud |  | 3Kles |  | 2018-08-06 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Product - Technical Specification | TECHNICAL SPECIFICATION | 33 | Arnaud |  | 3Kles |  | 2018-08-06 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Master Supplier - Technical Specification | TECHNICAL SPECIFICATION | 34 | Arnaud |  | 3Kles |  | 2018-08-10 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Master Customer - Technical Specification | TECHNICAL SPECIFICATION | 35 | Arnaud |  | 3Kles |  | 2018-08-16 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - PO Reception - Technical Specification | TECHNICAL SPECIFICATION | 36 | Arnaud |  | 3Kles |  | 2018-08-23 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Supplier Return - Technical Specification | TECHNICAL SPECIFICATION | 37 | Arnaud |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - DO - Technical Specification | TECHNICAL SPECIFICATION | 38 | Arnaud |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - DO Reception - Technical Specification | TECHNICAL SPECIFICATION | 39 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Picking List - Technical Specification | TECHNICAL SPECIFICATION | 40 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Pick&packing - Technical Specification | TECHNICAL SPECIFICATION | 41 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Releasing the stock - Technical Specification | TECHNICAL SPECIFICATION | 42 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Expedition creation - Technical Specification | TECHNICAL SPECIFICATION | 43 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Customer Return - Technical Specification | TECHNICAL SPECIFICATION | 44 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Technical Specification | TECHNICAL SPECIFICATION | 45 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Inventory+variance - Technical Specification | TECHNICAL SPECIFICATION | 46 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Inventory+variance - Technical Specification | TECHNICAL SPECIFICATION | 47 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Retail Price - Technical Specification | TECHNICAL SPECIFICATION | 48 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-09 |  | Not Started | 1.5 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Technical Specification | TECHNICAL SPECIFICATION | 49 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-12 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Technical Specification | TECHNICAL SPECIFICATION | 50 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-12 |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Technical Specification | TECHNICAL SPECIFICATION | 51 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2018-11-08 |  | Not Started | 0.5 | 0%
FIFI - EXPERIENCE - Other - Technical Specification | TECHNICAL SPECIFICATION | 52 | Anne-Marie 3Kles TBD |  | 3Kles |  | 2019-01-11 |  | Not Started | 2 | 0%
FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Technical Specification | TECHNICAL SPECIFICATION | 53 | Arnaud |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Technical Specification | TECHNICAL SPECIFICATION | 54 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Technical Specification | TECHNICAL SPECIFICATION | 55 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PACKING LIST FORM - Technical Specification | TECHNICAL SPECIFICATION | 56 | Rodolph (3Kles) |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Technical Specification | TECHNICAL SPECIFICATION | 57 | Atef |  | Atef |  | 2018-07-02 |  | Not Started | 0.5 | 0%
FIFI - PALOMA - TBC - Technical Specification | TECHNICAL SPECIFICATION | 58 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - Technical Specification | TECHNICAL SPECIFICATION | 59 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - Technical Specification | TECHNICAL SPECIFICATION | 60 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - Technical Specification | TECHNICAL SPECIFICATION | 61 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - Technical Specification | TECHNICAL SPECIFICATION | 62 | #N/A |  | #N/A |  |  |  | Not Started |  | 0%
TEST - Technical Specification | TECHNICAL SPECIFICATION | 63 | #N/A |  | #N/A |  | 2018-07-02 |  | On Going | 0.5 | 0%
FIFI - PRICING - Sales price - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 1 | Maxime |  | 3Kles |  | FIFI - PRICING - Sales price - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - PRICING - Retail price - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 2 | Maxime |  | 3Kles |  | FIFI - PRICING - Retail price - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - PRICING - Master Client - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 3 | Maxime |  | CL TBD |  | FIFI - PRICING - Master Client - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - PRICING - Client Order - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 4 | Maxime |  | CL TBD |  | FIFI - PRICING - Client Order - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - PLM - Item+attributes (weight, dimension, etc..) - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 5 | 3Kles (TBD) |  | Centric/3Kles |  | FIFI - PLM - Item+attributes (weight, dimension, etc..) - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - Purchase Price - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 6 | 3Kles (TBD) |  | Centric/3Kles |  | FIFI - PLM - Purchase Price - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - Madein - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 7 | 3Kles (TBD) |  | 3Kles |  | FIFI - PLM - Madein - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - HS Code - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 8 | 3Kles (TBD) |  | 3Kles |  | FIFI - PLM - HS Code - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - Composition - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 9 | 3Kles (TBD) |  | 3Kles |  | FIFI - PLM - Composition - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 10 | 3Kles (TBD) |  | 3Kles |  | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - PLM - Offer - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 11 | 3Kles (TBD) |  | 3Kles |  | FIFI - PLM - Offer - DETAILED TECH SPECIFICATION |  | Not Started | 12 | 0%
FIFI - N/A - Items - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 12 | 0 |  | 3Kles |  | FIFI - N/A - Items - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - N/A - Retail price - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 13 | 0 |  | 3Kles |  | FIFI - N/A - Retail price - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - OSO - Items - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 14 | TBConfirmed |  | 3Kles |  | FIFI - OSO - Items - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - OSO - Prices - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 15 | TBConfirmed |  | 3Kles |  | FIFI - OSO - Prices - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - OSO - Client List - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 16 | TBConfirmed |  | 3Kles |  | FIFI - OSO - Client List - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - OSO - Boutique Order - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 17 | TBConfirmed |  | 3Kles |  | FIFI - OSO - Boutique Order - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Items - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 18 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Items - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Offer - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 19 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Offer - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Prices - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 20 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Prices - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Client - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 21 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Client - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - WSH - Stock ? - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 22 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Stock ? - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Exclusivity + Drops - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 23 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Exclusivity + Drops - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - WSH - Client Order - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 24 | TBConfirmed |  | 3Kles |  | FIFI - WSH - Client Order - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - WSH - LINELIST - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 25 | TBConfirmed |  | 3Kles |  | FIFI - WSH - LINELIST - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - PIGALLE - Client Order/DO - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 26 | JC 3Kles TBD |  | 3Kles |  | FIFI - PIGALLE - Client Order/DO - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - PIGALLE - Stock - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 27 | JC 3Kles TBD |  | 3Kles |  | FIFI - PIGALLE - Stock - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - PIGALLE - Master Client - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 28 | JC 3Kles TBD |  | 3Kles |  | FIFI - PIGALLE - Master Client - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - PIGALLE - Assortment - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 29 | JC 3Kles TBD |  | 3Kles |  | FIFI - PIGALLE - Assortment - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - PIGALLE - Allocation/Unallocation - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 30 | JC 3Kles TBD |  | 3Kles |  | FIFI - PIGALLE - Allocation/Unallocation - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - LOUIS - Purchase Order - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 31 | Arnaud |  | 3Kles |  | FIFI - LOUIS - Purchase Order - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - LOUIS - PO Confirmation - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 32 | Arnaud |  | 3Kles |  | FIFI - LOUIS - PO Confirmation - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - EXPERIENCE - Product - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 33 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - Product - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Master Supplier - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 34 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - Master Supplier - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Master Customer - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 35 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - Master Customer - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - PO Reception - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 36 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - PO Reception - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - EXPERIENCE - Supplier Return - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 37 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - Supplier Return - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - EXPERIENCE - DO - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 38 | Arnaud |  | 3Kles |  | FIFI - EXPERIENCE - DO - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - DO Reception - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 39 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - DO Reception - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Picking List - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 40 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Picking List - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Pick&packing - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 41 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Pick&packing - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Releasing the stock - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 42 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Releasing the stock - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Expedition creation - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 43 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Expedition creation - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Customer Return - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 44 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Customer Return - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Reception+QC of Customer Retunr - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 45 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Reception+QC of Customer Retunr - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 46 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 47 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Inventory+variance - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Retail Price - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 48 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Retail Price - DETAILED TECH SPECIFICATION |  | Not Started | 6 | 0%
FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 49 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 50 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Stock Adjustment - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 51 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - EXPERIENCE - Other - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 52 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - EXPERIENCE - Other - DETAILED TECH SPECIFICATION |  | Not Started | 8 | 0%
FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 53 | Arnaud |  | 3Kles |  | FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 54 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 55 | Anne-Marie 3Kles TBD |  | 3Kles |  | FIFI - M3 PRINTOUT - PROFORMA First Cost - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - M3 PRINTOUT - PACKING LIST FORM - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 56 | Rodolph (3Kles) |  | 3Kles |  | FIFI - M3 PRINTOUT - PACKING LIST FORM - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 57 | Atef |  | Atef |  | FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - DETAILED TECH SPECIFICATION |  | Not Started | 3 | 0%
FIFI - PALOMA - TBC - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 58 | 0 |  | 3Kles |  | FIFI - PALOMA - TBC - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - GETPAID - - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 59 | 0 |  | 0 |  | FIFI - GETPAID - - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - GETPAID - - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 60 | 0 |  | 0 |  | FIFI - GETPAID - - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 61 | 0 |  | 0 |  | FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 62 | #N/A |  | #N/A |  | FIFI - Y2 - TBC - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
test - DETAILED TECH SPECIFICATION | DETAILED TECH SPECIFICATION | 63 | #N/A |  | #N/A |  | test - DETAILED TECH SPECIFICATION |  | Not Started |  | 0%
FIFI - PRICING - Sales price - DTS not in M3 | DTS NOT IN M3 | 1 | Maxime |  | 0 |  | 2018-10-10 |  | Not Started | 4 | 0%
FIFI - PRICING - Retail price - DTS not in M3 | DTS NOT IN M3 | 2 | Maxime |  | 0 |  | 2018-10-11 |  | Not Started | 4 | 0%
FIFI - PRICING - Master Client - DTS not in M3 | DTS NOT IN M3 | 3 | Maxime |  | 0 |  | 2018-10-15 |  | Not Started | 8.5 | 0%
FIFI - PRICING - Client Order - DTS not in M3 | DTS NOT IN M3 | 4 | Maxime |  | 0 |  | 2018-10-18 |  | Not Started | 8.5 | 0%
FIFI - PLM - Item+attributes (weight, dimension, etc..) - DTS not in M3 | DTS NOT IN M3 | 5 | Centric |  | 0 |  | 2018-10-26 |  | Not Started | 19 | 0%
FIFI - PLM - Purchase Price - DTS not in M3 | DTS NOT IN M3 | 6 | Centric |  | 0 |  | 2018-11-08 |  | Not Started | 19 | 0%
FIFI - PLM - Madein - DTS not in M3 | DTS NOT IN M3 | 7 | Centric |  | 0 |  | 2018-10-17 |  | Not Started | 19 | 0%
FIFI - PLM - HS Code - DTS not in M3 | DTS NOT IN M3 | 8 | Centric |  | 0 |  | 2018-10-25 |  | Not Started | 19 | 0%
FIFI - PLM - Composition - DTS not in M3 | DTS NOT IN M3 | 9 | Centric |  | 0 |  | 2018-11-05 |  | Not Started | 19 | 0%
FIFI - PLM - Offer - DTS not in M3 | DTS NOT IN M3 | 10 | Centric |  | 0 |  | 2018-11-13 |  | Not Started | 19 | 0%
FIFI - PLM - Offer - DTS not in M3 | DTS NOT IN M3 | 11 | Centric |  | 0 |  | 2018-11-21 |  | Not Started | 19 | 0%
FIFI - N/A - Items - DTS not in M3 | DTS NOT IN M3 | 12 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - N/A - Retail price - DTS not in M3 | DTS NOT IN M3 | 13 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - OSO - Items - DTS not in M3 | DTS NOT IN M3 | 14 | ACS2I |  | 0 |  | 2019-01-16 |  | Not Started | 11.5 | 0%
FIFI - OSO - Prices - DTS not in M3 | DTS NOT IN M3 | 15 | ACS2I |  | 0 |  | 2019-01-15 |  | Not Started | 8.5 | 0%
FIFI - OSO - Client List - DTS not in M3 | DTS NOT IN M3 | 16 | ACS2I |  | 0 |  | 2019-01-15 |  | Not Started | 8.5 | 0%
FIFI - OSO - Boutique Order - DTS not in M3 | DTS NOT IN M3 | 17 | ACS2I |  | 0 |  | 2019-01-15 |  | Not Started | 8.5 | 0%
FIFI - WSH - Items - DTS not in M3 | DTS NOT IN M3 | 18 | ACS2I |  | 0 |  | 2018-09-20 |  | Not Started | 8.5 | 0%
FIFI - WSH - Offer - DTS not in M3 | DTS NOT IN M3 | 19 | ACS2I |  | 0 |  | 2018-09-26 |  | Not Started | 8.5 | 0%
FIFI - WSH - Prices - DTS not in M3 | DTS NOT IN M3 | 20 | ACS2I |  | 0 |  | 2018-09-26 |  | Not Started | 8.5 | 0%
FIFI - WSH - Client - DTS not in M3 | DTS NOT IN M3 | 21 | ACS2I |  | 0 |  | 2018-09-27 |  | Not Started | 4 | 0%
FIFI - WSH - Stock ? - DTS not in M3 | DTS NOT IN M3 | 22 | ACS2I |  | 0 |  | 2018-09-20 |  | Not Started | 8.5 | 0%
FIFI - WSH - Exclusivity + Drops - DTS not in M3 | DTS NOT IN M3 | 23 | ACS2I |  | 0 |  | 2018-10-02 |  | Not Started | 8.5 | 0%
FIFI - WSH - Client Order - DTS not in M3 | DTS NOT IN M3 | 24 | ACS2I |  | 0 |  | 2018-09-26 |  | Not Started | 4 | 0%
FIFI - WSH - LINELIST - DTS not in M3 | DTS NOT IN M3 | 25 | ACS2I |  | 0 |  | 2018-11-27 |  | Not Started | 8.5 | 0%
FIFI - PIGALLE - Client Order/DO - DTS not in M3 | DTS NOT IN M3 | 26 | OHWEE |  | 0 |  | 2018-10-08 |  | Not Started | 11.5 | 0%
FIFI - PIGALLE - Stock - DTS not in M3 | DTS NOT IN M3 | 27 | OHWEE |  | 0 |  | 2018-09-26 |  | Not Started | 4 | 0%
FIFI - PIGALLE - Master Client - DTS not in M3 | DTS NOT IN M3 | 28 | OHWEE |  | 0 |  | 2018-09-28 |  | Not Started | 8.5 | 0%
FIFI - PIGALLE - Assortment - DTS not in M3 | DTS NOT IN M3 | 29 | OHWEE |  | 0 |  | 2018-10-02 |  | Not Started | 8.5 | 0%
FIFI - PIGALLE - Allocation/Unallocation - DTS not in M3 | DTS NOT IN M3 | 30 | OHWEE |  | 0 |  | 2018-10-11 |  | Not Started | 8.5 | 0%
FIFI - LOUIS - Purchase Order - DTS not in M3 | DTS NOT IN M3 | 31 | Sysdat |  | 0 |  | 2018-08-09 |  | Not Started | 11.5 | 0%
FIFI - LOUIS - PO Confirmation - DTS not in M3 | DTS NOT IN M3 | 32 | Sysdat |  | 0 |  | 2018-08-09 |  | Not Started | 11.5 | 0%
FIFI - EXPERIENCE - Product - DTS not in M3 | DTS NOT IN M3 | 33 | Sysdat |  | 0 |  | 2018-08-09 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Master Supplier - DTS not in M3 | DTS NOT IN M3 | 34 | Sysdat |  | 0 |  | 2018-08-16 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Master Customer - DTS not in M3 | DTS NOT IN M3 | 35 | Sysdat |  | 0 |  | 2018-08-21 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - PO Reception - DTS not in M3 | DTS NOT IN M3 | 36 | Sysdat |  | 0 |  | 2018-08-28 |  | Not Started | 11.5 | 0%
FIFI - EXPERIENCE - Supplier Return - DTS not in M3 | DTS NOT IN M3 | 37 | Sysdat |  | 0 |  |  |  | Not Started | 11.5 | 0%
FIFI - EXPERIENCE - DO - DTS not in M3 | DTS NOT IN M3 | 38 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - DO Reception - DTS not in M3 | DTS NOT IN M3 | 39 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Picking List - DTS not in M3 | DTS NOT IN M3 | 40 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Pick&packing - DTS not in M3 | DTS NOT IN M3 | 41 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Releasing the stock - DTS not in M3 | DTS NOT IN M3 | 42 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Expedition creation - DTS not in M3 | DTS NOT IN M3 | 43 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Customer Return - DTS not in M3 | DTS NOT IN M3 | 44 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Reception+QC of Customer Retunr - DTS not in M3 | DTS NOT IN M3 | 45 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Inventory+variance - DTS not in M3 | DTS NOT IN M3 | 46 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Inventory+variance - DTS not in M3 | DTS NOT IN M3 | 47 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Retail Price - DTS not in M3 | DTS NOT IN M3 | 48 | Sysdat |  | 0 |  | 2018-11-14 |  | Not Started | 8.5 | 0%
FIFI - EXPERIENCE - Stock Adjustment - DTS not in M3 | DTS NOT IN M3 | 49 | Sysdat |  | 0 |  | 2018-11-15 |  | Not Started | 11.5 | 0%
FIFI - EXPERIENCE - Stock Adjustment - DTS not in M3 | DTS NOT IN M3 | 50 | Sysdat |  | 0 |  | 2018-11-15 |  | Not Started | 11.5 | 0%
FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - DTS not in M3 | DTS NOT IN M3 | 51 | Sysdat |  | 0 |  | 2018-11-13 |  | Not Started | 4 | 0%
FIFI - EXPERIENCE - Other - DTS not in M3 | DTS NOT IN M3 | 52 | Sysdat |  | 0 |  | 2019-01-16 |  | Not Started | 11.5 | 0%
FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - DTS not in M3 | DTS NOT IN M3 | 53 | 0 |  | 0 |  |  |  | Not Started | 0 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - DTS not in M3 | DTS NOT IN M3 | 54 | 0 |  | 0 |  |  |  | Not Started | 0 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - DTS not in M3 | DTS NOT IN M3 | 55 | 0 |  | 0 |  |  |  | Not Started | 0 | 0%
FIFI - M3 PRINTOUT - PACKING LIST FORM - DTS not in M3 | DTS NOT IN M3 | 56 | 0 |  | 0 |  |  |  | Not Started | 0 | 0%
FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - DTS not in M3 | DTS NOT IN M3 | 57 | 0 |  | 0 |  | 2018-07-05 |  | Not Started | 0 | 0%
FIFI - PALOMA - TBC - DTS not in M3 | DTS NOT IN M3 | 58 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - DTS not in M3 | DTS NOT IN M3 | 59 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - DTS not in M3 | DTS NOT IN M3 | 60 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - DTS not in M3 | DTS NOT IN M3 | 61 | 0 |  | 0 |  |  |  | Not Started |  | 0%
FIFI - Y2 - TBC - DTS not in M3 | DTS NOT IN M3 | 62 | #N/A |  | #N/A |  |  |  | Not Started |  | 0%
test- DTS not in M3 | DTS NOT IN M3 | 63 | #N/A |  | #N/A |  |  |  | Not Started |  | 0%
FIFI - PRICING - Sales price - Unit Tests | UNIT TESTS | 1 | Maxime |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PRICING - Retail price - Unit Tests | UNIT TESTS | 2 | Maxime |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PRICING - Master Client - Unit Tests | UNIT TESTS | 3 | Maxime |  | CL TBD |  |  |  | Not Started | 1 | 0%
FIFI - PRICING - Client Order - Unit Tests | UNIT TESTS | 4 | Maxime |  | CL TBD |  |  |  | Not Started | 1 | 0%
FIFI - PLM - Item+attributes (weight, dimension, etc..) - Unit Tests | UNIT TESTS | 5 | 3Kles (TBD) |  | Centric/3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - Purchase Price - Unit Tests | UNIT TESTS | 6 | 3Kles (TBD) |  | Centric/3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - Madein - Unit Tests | UNIT TESTS | 7 | 3Kles (TBD) |  | 3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - HS Code - Unit Tests | UNIT TESTS | 8 | 3Kles (TBD) |  | 3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - Composition - Unit Tests | UNIT TESTS | 9 | 3Kles (TBD) |  | 3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - Offer - Unit Tests | UNIT TESTS | 10 | 3Kles (TBD) |  | 3Kles |  |  |  | Not Started | 4 | 0%
FIFI - PLM - Offer - Unit Tests | UNIT TESTS | 11 | 3Kles (TBD) |  | 3Kles |  |  |  | Not Started | 4 | 0%
FIFI - N/A - Items - Unit Tests | UNIT TESTS | 12 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - N/A - Retail price - Unit Tests | UNIT TESTS | 13 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - OSO - Items - Unit Tests | UNIT TESTS | 14 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - OSO - Prices - Unit Tests | UNIT TESTS | 15 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - OSO - Client List - Unit Tests | UNIT TESTS | 16 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - OSO - Boutique Order - Unit Tests | UNIT TESTS | 17 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Items - Unit Tests | UNIT TESTS | 18 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Offer - Unit Tests | UNIT TESTS | 19 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Prices - Unit Tests | UNIT TESTS | 20 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Client - Unit Tests | UNIT TESTS | 21 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Stock ? - Unit Tests | UNIT TESTS | 22 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Exclusivity + Drops - Unit Tests | UNIT TESTS | 23 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - Client Order - Unit Tests | UNIT TESTS | 24 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - WSH - LINELIST - Unit Tests | UNIT TESTS | 25 | TBConfirmed |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PIGALLE - Client Order/DO - Unit Tests | UNIT TESTS | 26 | JC 3Kles TBD |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - PIGALLE - Stock - Unit Tests | UNIT TESTS | 27 | JC 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PIGALLE - Master Client - Unit Tests | UNIT TESTS | 28 | JC 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PIGALLE - Assortment - Unit Tests | UNIT TESTS | 29 | JC 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - PIGALLE - Allocation/Unallocation - Unit Tests | UNIT TESTS | 30 | JC 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - LOUIS - Purchase Order - Unit Tests | UNIT TESTS | 31 | Arnaud |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - LOUIS - PO Confirmation - Unit Tests | UNIT TESTS | 32 | Arnaud |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Product - Unit Tests | UNIT TESTS | 33 | Arnaud |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Master Supplier - Unit Tests | UNIT TESTS | 34 | Arnaud |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Master Customer - Unit Tests | UNIT TESTS | 35 | Arnaud |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - PO Reception - Unit Tests | UNIT TESTS | 36 | Arnaud |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Supplier Return - Unit Tests | UNIT TESTS | 37 | Arnaud |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - DO - Unit Tests | UNIT TESTS | 38 | Arnaud |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - DO Reception - Unit Tests | UNIT TESTS | 39 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Picking List - Unit Tests | UNIT TESTS | 40 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Pick&packing - Unit Tests | UNIT TESTS | 41 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Releasing the stock - Unit Tests | UNIT TESTS | 42 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Expedition creation - Unit Tests | UNIT TESTS | 43 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Customer Return - Unit Tests | UNIT TESTS | 44 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Reception+QC of Customer Retunr - Unit Tests | UNIT TESTS | 45 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Inventory+variance - Unit Tests | UNIT TESTS | 46 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Inventory+variance - Unit Tests | UNIT TESTS | 47 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Retail Price - Unit Tests | UNIT TESTS | 48 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Unit Tests | UNIT TESTS | 49 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Stock Adjustment - Unit Tests | UNIT TESTS | 50 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - EXPERIENCE - Sending Printout (Invoice, proforma, etc..) - Unit Tests | UNIT TESTS | 51 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 1 | 0%
FIFI - EXPERIENCE - Other - Unit Tests | UNIT TESTS | 52 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 2 | 0%
FIFI - M3 PRINTOUT - PURCHASE ORDER FORM - Unit Tests | UNIT TESTS | 53 | Arnaud |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Unit Tests | UNIT TESTS | 54 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PROFORMA First Cost - Unit Tests | UNIT TESTS | 55 | Anne-Marie 3Kles TBD |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - PACKING LIST FORM - Unit Tests | UNIT TESTS | 56 | Rodolph (3Kles) |  | 3Kles |  |  |  | Not Started | 0.5 | 0%
FIFI - M3 PRINTOUT - INVOICE/CREDIT NOTE FORM - Unit Tests | UNIT TESTS | 57 | Atef |  | Atef |  |  |  | Not Started | 0.5 | 0%
FIFI - PALOMA - TBC - Unit Tests | UNIT TESTS | 58 | 0 |  | 3Kles |  |  |  | Not Started |  | 0%
FIFI - GETPAID - - Unit Tests | [8 empty] | Not Started |  | 0%
FIFI - GETPAID - - Unit Tests | [8 empty] | Not Started |  | 0%
FIFI - Y2 - TBC - Unit Tests | [8 empty] | Not Started |  | 0%
FIFI - Y2 - TBC - Unit Tests | [8 empty] | Not Started |  | 0%
test - Unit Tests | [8 empty] | Not Started |  | 0%

## REF
FUNCTIONAL SPECIFICATION | 18
TECHNICAL SPECIFICATION | 30
DETAILED TECH SPECIFICATION | 42
DTS NOT IN M3 | 50
UNIT TESTS | 70
Note on A3: Sophie Boisseau: 1/2 FLOW IN M3