## Feuil1
FIRST ISSUE DATE | HPC DAY REMAINING | PURPOSE | PAUL TRS Num. | PAUL TRANSMET A LA DATE | DATE DE RETOUR PREVU PAR MICHEL | MICHEL CRS Num. | MICHEL REPOND LE: | DOCUMENT STATUS | PAUL REPOND LE : | TRS NUMBER | MICHEL RE-REPOND LE: | CRS N° | MICHEL STATUS | FINAL STATUS | TODAY | PAUL DOIT REPONDRE LE | RETARD DE PAUL | RETARD DE MICHEL
2019-01-07 | 0 | FR | TRS-00002 | 2019-01-07 | 2019-01-14 | TRS_00002 | 2019-01-14 | A | [5 empty] | A | 2019-02-20 | 2019-01-21 | 0 | 0
2019-01-07 | 0 | FR | TRS-00002 | 2019-01-07 | 2019-01-14 | TRS_00002 | 2019-01-14 | C | 2019-01-18 | TRS-00006 |  |  |  |  | 2019-02-20 | 2019-01-21 | 23 | 0
2019-01-07 | 0 | FR | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0010 | 2019-01-28 | C | 2019-02-05 | TRS-00016 | 2019-02-11 | TRS-0018 | C |  | 2019-02-20 | 2019-02-04 | 8 | 0
2019-01-04 | 0 | FR | TRS-00001 | 2019-01-04 | 2019-01-11 | TRS_00001 | 2019-01-11 | C | 2019-01-15 | TRS-00004 | 2019-01-23 | TRS-00009 | A |  | 2019-02-20 | 2019-01-18 | 0 | 0
2019-01-04 | 0 | FR | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0010 | 2019-01-28 | C | 2019-01-31 | TRS-00015 | 2019-02-14 | TRS-0022 | A | A | 2019-02-20 | 2019-02-04 | 0 | 0
1 - quand Paul envoi : Q3=date donc R3= Q3+7 et AE=nbr de jours AB3;R3
2 - quand Michel répond :t3=date avec U3=A alors AC3 et AD3=0
3 - quand Michel répond :t3=date avec U3=B ou C alors AC3=T3+7 et AD3=nbre je jours AB3;AC3
4 - quand Paul répond car U3=B ou C ou D - V3=date alors AC3=0; AD3=0 et AE3=nbre de jours AB3;V3+7
5 - Michel répond si Z=A; AC3 et AD3 et AE3=0, si Z=B,C,D alors AC3 et AC3=X3+7 et AD3=nbre de jours AB3;AC3 et AE=0
AC3 change de date si T3; V3; X3 une date est inlus
Formulas:
HPC DAY REMAINING = IF(([PAUL TRANSMET A LA DATE]<>0),0,NETWORKDAYS([TODAY],[FIRST ISSUE DATE])-(1))
DATE DE RETOUR PREVU PAR MICHEL = [PAUL TRANSMET A LA DATE]+7
PAUL DOIT REPONDRE LE = IF([MICHEL REPOND LE:]="","",[MICHEL REPOND LE:]+7)
RETARD DE PAUL = IF([DOCUMENT STATUS]="A",0,IF(OR([DOCUMENT STATUS]="B",[DOCUMENT STATUS]="C",[DOCUMENT STATUS]="D"),IF([PAUL REPOND LE :]=[PAUL TRANSMET A LA DATE],0,IF([MICHEL STATUS]="A",0,IF(OR([MICHEL STATUS]="B",[MICHEL STATUS]="C",[MICHEL STATUS]="D"),NETWORKDAYS([MICHEL RE-REPOND LE:],[TODAY]),NETWORKDAYS([PAUL DOIT REPONDRE LE],[TODAY])))),0))
RETARD DE MICHEL = IF([DOCUMENT STATUS]="A",0,IF(AND(OR([DOCUMENT STATUS]="B",[DOCUMENT STATUS]="C",[DOCUMENT STATUS]="D"),[PAUL REPOND LE :]=[MICHEL RE-REPOND LE:]),NETWORKDAYS([PAUL REPOND LE :],[TODAY]),0))