## MDL
CLIENT PROJECT REF : |  |  | DEMF02600 (FIT4 nr: I-0201041) | [5 empty] | MASTER DOCUMENTS REGISTER - DD-201 Electric Vacuum Column Feed Heater | [8 empty] | HPS PROJECT REF. : |  | 09970H60
CLIENT : |  |  | SHELL Deutschland GmbH Germany | [14 empty] | HPS PROPOSAL REF. :
PROJECT NAME : |  |  | SHELL Rheinland R3 Base Oil Project | [14 empty] | DELIVERY DATE | [15 empty] | .
TECHNICAL REQUISITION Ref : | [17 empty] | HPS MDL Doc_Number | 09970H60-D201-FA-001
[18 empty] | Revision | Rev_09 | 2025-01-22
DOC CONTROL E-MAIL : |  |  | 09970H60_doccontrol@heurtey.net | [14 empty] | HPS DOC. CONTROL NAME : | Jean-Claude ROOSSENS
Project: 09970H60 | [21 empty] | 1 |  |  | 2 |  | 3
Company | Discipline | Document Type | Deliverable | Planned Date | SHELL Doc_Number | Shell Disc_Code | Shell Doc_Type | HPS Document Number | Supplier Doc_Ref. | Document Description | Revision | Status | Revision Date | HPS - SHELL TRS N° | HPS - SHELL TRS Date | SHELL Due Date | SHELL TRS N° | SHELL TRS Date | SHELL Status Code | SHELL Time limit or Delay | SHELL Time limit or Delay | Supplier TRS N° | Supplier TRS Date | HPS - Suppliers EXPECTED DATE | DCC to HPS TRS N° | DCC to HPS TRS Date | HPS - Suppliers TRS N° | HPS - Supplier TRS Date | HPS - Supplier Status | Today | Suppliers -HPS Time limit or Delay | HPS - SHELL EXPECTED DATE | HPS - SHELL Time limit or Delay | HPS - Suppliers EXPECTED DATE | HPS - Supplier Time limit or Delay
HPS | QC | PR | TRUE | 2024-06-28 | RHL-001293960 | QA | QA6180 | 09970H60-D201-FA-004 |  | QMP - Quality Management Plan | 00 | IFD | 2024-07-11 | HPS-SHE-TN-0048 | 2024-07-16 | 2024-07-29 |  |  |  | case doit etre rouge | -128 | VEP 0004 | 2024-11-05 | 2024-11-15 |  |  | HPS-SCH-TN-0017 | 2024-12-04 | A – Reviewed Without Comment | 2025-01-22
HPS | 3COLL | FM | FALSE |  | RHL-001293791 |  |  | 09970H60-D201-DR-002 |  | 3D For BETA | 00 | IFD | 2024-09-23 | [16 empty] | 2025-01-22
HPS | PRJ | MR | TRUE | 2024-06-28 | RHL-001293952 | AA | AA6944 | 09970H60-D201-FA-007 |  | Monthly Report | 01 | IFD | 2024-08-13 | HPS-SHE-TN-0057 | 2024-08-13 | 2024-08-26 |  |  |  |  | -108 | VEP 0003 | 2024-09-30 | 2024-10-10 | SCH-HPS-TN-0003 | 2024-09-30 | HPS-SCH-TN-0013 | 2024-11-27 | A – Reviewed Without Comment | 2025-01-22
HPS | AUT | DS | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FD-817 |  | PLC - Maintenance Contract | [19 empty] | 2025-01-22
HPS | AUT | DW | FALSE | 2025-07-22 | For Information End of Project |  |  | 09970H60-D201-FD-862 |  | Basic Logic Diagram | [16 empty] | SHE-HPS-TN-0062 | 2025-01-13 | C – Rejected | 2025-01-22 | 2 |  |  | 2025-01-23
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293897 | IN | IN2105 | 09970H60-D201-FS-802 |  | ON/OFF Valves - Specification | 03 | IFD | 2024-09-03 | HPS-SHE-TN-0063 | 2024-09-05 | 2024-09-18 |  |  |  |  | -91 | [8 empty] | 2025-01-22
HPS | AUT | LST | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FD-881 |  | PLC - I/O List | 02 | IFD | 2024-10-08 | HPS-SHE-TN-0078 | 2024-10-10 | 2024-10-23 |  |  |  |  | -66 | [5 empty] | SHE-HPS-TN-0049 | 2024-11-12 | C – Rejected | 2025-01-22 | -44 |  |  | 2024-11-22
HPS | AUT | LST | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FD-884 |  | PLC/BPCS - Communication List | [19 empty] | 2025-01-22
HPS | AUT | MTR | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FS-880 |  | PLC - Technical requisition | [19 empty] | 2025-01-22
HPS | AUT | OM | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FD-886 |  | PLC - Maintenance and Operation Manual | [19 empty] | 2025-01-22
HPS | AUT | PR | FALSE |  |  |  |  | 09970H60-D201-FD-818 |  | PLC - Handling,Preservation & Installation Procedure | 00 | IFD | 2024-12-05 | [16 empty] | 2025-01-22
HPS | AUT | SPEC | FALSE |  | For Information End of Project |  |  | 09970H60-D201-FD-808 |  | Functional Design spec.of PLC package and BPCS communication | [19 empty] | 2025-01-22
SE - SCHNEIDER | AUT | LST | FALSE | 2025-01-27 |  |  |  | 09970H60-D201-FD-834 |  | Network and Signals Cable List (E-House) | [19 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-09-02 | RHL-001293899 | IN | IN2105 | 09970H60-D201-FS-804 |  | Control Valve - Specification | 01 | IFD | 2024-09-04 | HPS-SHE-TN-0063 | 2024-09-05 | 2024-09-18 |  |  |  |  | -91 | [8 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  |  |  |  | 09970H60-D201-FE-801 |  | CANCELED - PLC - Instrument Loop Diagrams (E-Heater) |  | CAN | [17 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293902 | IN | IN2105 | 09970H60-D201-FS-807 |  | TW/TE/TT - Specification | 01 | IFD | 2024-08-30 | HPS-SHE-TN-0063 | 2024-09-05 | 2024-09-18 |  |  |  |  | -91 | [8 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293905 | IN | IN2105 | 09970H60-D201-FS-812 |  | Skin Thermocouples - Specification | 00 | IFD | 2024-08-30 | HPS-SHE-TN-0063 | 2024-09-05 | 2024-09-18 |  |  |  |  | -91 | [8 empty] | 2025-01-22
HPS | HSE | PR | TRUE | 2024-10-18 | RHL-001293885 | HX | HX5701 | 09970H60-D201-FS-907 |  | HSSE PLAN (Site works) | 00 | IFD | 2024-09-27 | HPS-SHE-TN-0069 | 2024-09-30 | 2024-10-13 |  |  |  |  | -73 | [8 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  | For Information |  |  | 09970H60-D201-FE-805 |  | PLC - Typical Loops | 00 | IFD | 2024-10-08 | HPS-SHE-TN-0077 | 2024-10-09 | 2024-10-22 | SHE-HPS-TN-0077 | 2024-10-29 | B - Proceed Change as Noted & Resubmit | daces doit etre en vert | [9 empty] | 2025-01-22 |  | 2024-11-08 | -54
AGEX | INS | DW | TRUE | 2024-10-11 | RHL-001293896 | IN | IN0901 | 09970H60-D201-FD-841 |  | Instrumentation Supports Drawing Typicals (E-Heater) | 00 | IFD | 2024-09-27 | HPS-SHE-TN-0069 | 2024-09-30 | 2024-10-13 |  |  |  |  | -73 | [8 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  |  |  |  | 09970H60-D201-FE-807 |  | CANCELED - PLC - Functional design specification of HMI |  | CAN | [14 empty] | HPS-AGEX-TN-0002 | 2024-10-09 | B – Reviewed With Comments | 2025-01-22
TECHMA | AUT | FE | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FE-809 |  | PLC - Equipment List | 00 | IFD | 2024-08-14 | [16 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  |  |  |  | 09970H60-D201-FE-810 |  | CANCELED - PLC - License List |  | CAN | [17 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FE-812 |  | PLC - Spare Parts (Com + 2 Y) (if option is selected by Customer) | [19 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FE-813 |  | Licence List | [19 empty] | 2025-01-22
TECHMA | AUT | FE | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FE-814 |  | PLC - Consumable list | [16 empty] | HPS-AGEX-TN-0003 | 2024-10-30 | B – Reviewed With Comments | 2025-01-22 | -53 |  |  | 2024-11-09
TECHMA | AUT | FE | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FE-815 |  | Warranty List | [19 empty] | 2025-01-22
TECHMA | AUT | FQ | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FQ-801 |  | PLC - Certificate of Conformity | 00 | IFR | 2024-08-14 | [16 empty] | 2025-01-22
TECHMA | AUT | FQ | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FQ-802 |  | PLC - Inspection & Test Plan (ITP), FAT procedure and FAT report at subcontractor factory | 00 | IFR | 2024-10-02 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0001 | 2024-12-04 | B – Reviewed With Comments | 2025-01-22 | -28 |  |  | 2024-12-14
TECHMA | AUT | FQ | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-FQ-803 |  | PLC - Power on power off Procedure | 00 | IFR | 2024-10-02 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | B – Reviewed With Comments | 2025-01-22 | -18 |  |  | 2024-12-29
BETA | CONS | PR | FALSE |  |  |  |  | 09970H60-D201-FQ-3080 |  | CANCELED - TRIAL ASSEMBLY PROCEDURE |  | CAN | [9 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
HPS | PCS | FJ | TRUE | 2024-09-16 | RHL-001293937 | PX | PX2105 | 09970H60-D201-FJ-721 |  | ID Fan - Datasheet | 00 | IFD | 2024-09-27 | HPS-SHE-TN-0069 | 2024-09-30 | 2024-10-13 |  |  |  |  | -73 | [8 empty] | 2025-01-22
HPS | CONS | MTR | FALSE | 2024-07-18 |  |  |  | 09970H60-D201-FS-301 |  | Technical Requisition E-Heater - Shop Fabrication | 05 | IFO | 2024-09-04 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
HPS | STR | DW | TRUE |  | RHL-001293932 | CS |  | 09970H60-D201-FD-910 |  | SFMOD 1 - PACKING AND LIFTING ARRANGEMENT | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
HPS | CONS | PR | FALSE |  |  |  |  | 09970H60-D201-FS-903 |  | CANCELED - Modularization Memorandum |  | CAN | [9 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0002 | 2024-12-18 | C – Rejected | 2025-01-22 |  |  |  |  | -23
HPS | STR | DW | TRUE |  | RHL-001293933 | CS |  | 09970H60-D201-FD-911 |  | SFMOD 2 - PACKING AND LIFTING ARRANGEMENT | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293934 | CS |  | 09970H60-D201-FD-912 |  | SFMOD 3 - PACKING AND LIFTING ARRANGEMENT | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293946 | CS |  | 09970H60-D201-FD-913 |  | SFMOD 4 - PACKING AND LIFTING ARRANGEMENT | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
BARTEC | DCC | SDL | FALSE |  |  |  |  | 09970H60-D201-FE-8000 |  | Terminal Boxes - Supplier Documents List | 01 | IFD | 2024-12-10 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
BETA | DCC | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3000 |  | Index - Master DataBook - Radiant Coil | 02 | IFD | 2024-12-02 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -23
BETA | DCC | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3001 |  | Index - Master DataBook - Steel Structure | 02 | IFD | 2024-12-02 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -23
BETA | DCC | SDL | FALSE |  |  |  |  | 09970H60-D201-FE-3003 | Rev_00 - Internal | Supplier Documents Register List | [11 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -23
BETA | DCC | VB | FALSE |  |  |  |  | 09970H60-D201-VB-3000 |  | Manufacturing DataBook | [11 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -23
DISTRISOL | DCC | SDL | FALSE | 2024-11-26 |  |  |  | 09970H60-D201-FE-500 |  | Refractory - Supplier Documents List | 00 | IFD | 2025-01-13 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -23
HPS | DCC | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-010 |  | Index - Early Engineering Databook | 01 | IEE | 2024-05-02 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293947 | CS |  | 09970H60-D201-FD-914 |  | SFMOD 5 - PACKING AND LIFTING ARRANGEMENT | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293948 | CS |  | 09970H60-D201-FD-920 |  | PACKING AND LIFTING ARRANGEMENT - COVERS DETAIL | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0072 | 2024-10-03 | 2024-10-16 | SHE-HPS-TN-0072 | 2024-10-29 | D - for Information Only | [10 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293898 | IN | IN2105 | 09970H60-D201-FS-803 |  | Relief Valve - Specification | 02 | IFD | 2024-10-04 | HPS-SHE-TN-0073 | 2024-10-07 | 2024-10-20 |  |  |  |  | -68 |  |  |  | SHE-HPS-TN-0028 | 2024-10-08 |  |  |  | 2025-01-22
HPS | DCC | VB | FALSE | 2024-06-03 |  |  |  | 09970H60-D201-FQ-020 |  | Early Engineering Databook | 00 | IEE | 2024-04-15 | [16 empty] | 2025-01-22
AGEX | INS | DW | TRUE | 2024-10-14 | RHL-001293892 | IN | IN2389 | 09970H60-D201-FD-814 |  | Instrument Junction Boxes Wiring Diagram (E-Heater) | 00 | IFD | 2024-10-14 | HPS-SHE-TN-0079 | 2024-10-16 | 2024-10-29 |  |  |  |  | -62 | [8 empty] | 2025-01-22
AGEX | INS | DW | TRUE | 2024-10-11 | RHL-001293893 | IN | IN4024 | 09970H60-D201-FD-815 |  | Instrument Cable Routing (A/G) - Instrum & JB Layout (E-Heater) | 00 | IFD | 2024-10-14 | HPS-SHE-TN-0079 | 2024-10-16 | 2024-10-29 |  |  |  |  | -62 | [8 empty] | 2025-01-22
HPS | DCC | VB | FALSE |  |  |  |  | 09970H60-D201-VB-720 |  | ID Fan - Manufacturing Databook | [19 empty] | 2025-01-22
KANTHAL | DCC | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-205 |  | Heating Elements - Manufacturing Data Book - Index | 01 | IFD | 2024-12-04 | [16 empty] | 2025-01-22
KANTHAL | DCC | SDL | FALSE |  |  |  |  | 09970H60-D201-FE-200 |  | Heating Elements - Documents List (SDRL) | 00 | IFD | 2024-09-09 | [16 empty] | 2025-01-22
KANTHAL | DCC | VB | FALSE |  |  |  |  | 09970H60-D201-VB-200 |  | Heating Elements - Manufacturing Data Book | [19 empty] | 2025-01-22
SE - SCHNEIDER | DCC | SDL | FALSE | 2024-08-23 |  |  |  | 09970H60-D201-FE-001 |  | SCHNEIDER - Supplier Documents List (E-House) | 3 | IFD | 2024-12-02 | [16 empty] | 2025-01-22
SE - SCHNEIDER | DCC | VB | FALSE | 2025-07-20 | RHL-001293814 |  |  | 09970H60-D201-VB-880 | End of Project - For Info | Manufacturing Data Book- (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | DCC | VB | FALSE | 2025-07-20 | RHL-001293815 |  |  | 09970H60-D201-VB-882 | End of Project - For Info | LV Switchboard - MDB (Manufacturer Data Book) (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | DCC | VB | FALSE | 2025-05-15 | RHL-001293816 |  |  | 09970H60-D201-VB-884 | End of Project - For Info | MV/LV Transformer - MDB (Manufacturer Data Book) (E-House) | [19 empty] | 2025-01-22
SISTEC | DCC | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8110 |  | Analysers - Index - Manufacturer's file (Wendor DataBook) | [19 empty] | 2025-01-22
SISTEC | DCC | SDL | FALSE |  |  |  |  | 09970H60-D201-FE-8100 |  | Analysers - Supplier Document list | 01 | IFD | 2025-01-13 | [16 empty] | 2025-01-22
SISTEC | DCC | VB | FALSE |  |  |  |  | 09970H60-D201-VB-8100 |  | Analysers - Manufacturer's file (Vendor DataBook) | [19 empty] | 2025-01-22
TECHMA | DCC | VB | FALSE |  | For Information - End of Project |  |  | 09970H60-D201-VB-800 |  | PLC - Manufacturing DataBook | 00 | IFR | 2024-10-02 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293988 | CS |  | 09970H60-D201-FK-002 |  | Radiant Coil & Refractories | 05 | IFD | 2024-10-16 | HPS-SHE-TN-0090 | 2024-10-21 | 2024-11-03 |  |  |  |  | -58 | [8 empty] | 2025-01-22
AGEX | INS | DS | TRUE | 2024-10-28 | RHL-001293908 | IN | IN4308 | 09970H60-D201-FS-816 |  | Instrument Cable - Specification | 00 | IFD | 2024-10-22 | HPS-SHE-TN-0095 | 2024-10-23 | 2024-11-05 |  |  |  |  | -57 | [8 empty] | 2025-01-22
HPS | INS | LST | TRUE | 2024-09-09 | RHL-001293890 | IN | IN4327 | 09970H60-D201-FD-811 |  | Instrument List & I/O List (Including Alarm and Trip Settings) | 02 | IFD | 2024-09-09 | HPS-SHE-TN-0097 | 2024-10-24 | 2024-11-06 |  |  |  |  | -56 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | TRUE | 2024-12-04 | RHL-001293826 | EA |  | 09970H60-D201-FD-825 |  | Main Single Line Diagrams (E-House) | 07 | IFD | 2024-10-29 | HPS-SHE-TN-0101 | 2024-10-29 | 2024-11-11 |  |  |  |  | -53 | TN-0001 | 2024-11-25 | 2024-12-05 | DIS-HPS-TN-0001 | 2024-11-28 | HPS-DIS-TN-0003 | 2024-12-09 | B – Reviewed With Comments | 2025-01-22 | -25 |  |  | 2024-12-19
HPS | INSP | FQ | TRUE |  | RHL-001293924 | BA | BA7880 | 09970H60-D201-FQ-006 |  | SOI – Heat éléments | 00 | IFD | 2024-11-04 | HPS-SHE-TN-0107 | 2024-11-05 | 2024-11-18 |  |  |  |  | -48 | [8 empty] | 2025-01-22
HPS | PCS | PD | TRUE | 2024-07-24 | RHL-001293940 | PX |  | 09970H60-D201-FJ-805 |  | Ctrl and Safeguarding Narrative | 01 | IFD | 2024-07-19 | HPS-SHE-TN-0109 | 2024-11-05 | 2024-11-18 |  |  |  |  | -48 | TN-0008 | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0015 | 2024-12-30 |  |  |  | 2025-01-22 |  |  |  |  | -18
HPS | MEC | CRE | TRUE | 2024-10-04 | RHL-001293929 | MS | MS1208 | 09970H60-D201-FC-410 |  | Process Coil Stress Analysis | 00 | IFD | 2024-11-04 | HPS-SHE-TN-0113 | 2024-11-07 | 2024-11-20 |  |  |  |  | -46 | [8 empty] | 2025-01-22
AGEX | ELE | DW | FALSE |  |  |  |  | 09970H60-D201-FD-871 |  | CANCELED - Electrical & Instrumentation Cable Routing U/G (trench) Layout ( SHELL SOW) | 02 | CAN | [9 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
HPS | MEC | CN | TRUE | 2024-09-09 | RHL-001293930 | MS | MS1208 | 09970H60-D201-FC-401 |  | Coils Pressure Part calculation note | 02 | IFD | 2024-09-06 | HPS-SHE-TN-0117 | 2024-11-14 | 2024-11-27 |  |  |  |  | -41 | [8 empty] | 2025-01-22
HPS | MEC | DW | TRUE | 2024-07-15 | RHL-001293928 | MX | MX2580 | 09970H60-D201-FD-401 |  | Radiant Coil Drawings - Electrical Radiant Tubular Heater | 02 | IFD | 2024-10-04 | HPS-SHE-TN-0117 | 2024-11-14 | 2024-11-27 |  |  |  |  | -41 | [8 empty] | 2025-01-22
AGEX | INS | DS | TRUE | 2024-11-12 | RHL-001293771 | IN | IN2105 | 09970H60-D201-FS-819 |  | E&I Bulk Specification (E-Heater) | 00 | IFD | 2024-11-16 | HPS-SHE-TN-0118 | 2024-11-18 | 2024-12-01 |  |  |  |  | -38 | [8 empty] | 2025-01-22
AGEX | ELE | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-814 |  | MR for Lighting Junction Boxes | 00 | IEE | 2023-12-18 | [8 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
AGEX | ELE | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-815 |  | MR for Lighting Fixture (E-Heater) | 01 | IFD | 2024-11-22 | [8 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
AGEX | INS | DS | TRUE | 2024-11-07 | RHL-001293907 | IN | IN2105 | 09970H60-D201-FS-815 |  | Instrument Junction Box & Hand Switch Specification | 01 | IFD | 2024-11-22 | HPS-SHE-TN-0119 | 2024-11-25 | 2024-12-08 |  |  |  |  | -33 | [8 empty] | 2025-01-22
HPS | INSP | FQ | TRUE | 2024-09-03 | RHL-001293915 | BA | BA7880 | 09970H60-D201-FQ-001 |  | SOI - Pressure Parts | 01 | IFD | 2024-11-22 | HPS-SHE-TN-0120 | 2024-11-25 | 2024-12-08 |  |  |  |  | -33 | [8 empty] | 2025-01-22
AGEX | ELE | SPE | FALSE |  |  |  |  | 09970H60-D201-FS-817 |  | Lighting Fixture Specification | 00 | IFD | 2024-12-09 | [8 empty] | VEP 0015 | 2024-12-19 | 2024-12-29 | BET-HPS-TN-0018 | 2024-12-23 |  |  |  | 2025-01-22 |  |  |  |  | -18
HPS | ELE | DS | TRUE | 2024-08-09 | RHL-001293868 | EA | EA2105 | 09970H60-D201-FS-860 |  | Electrical Design Basis for Tubular Electrical Heater | 03 | IFD | 2024-11-21 | HPS-SHE-TN-0125 | 2024-12-02 | 2024-12-15 |  |  |  |  | -28 | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0007 | 2024-10-24 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8001 |  | Terminal Boxes - ESI Junction Boxe Datasheet | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0014 | 2024-12-13 | 2024-12-23 | BET-HPS-TN-0016 | 2024-12-16 | HPS-BET-TN-0029 | 2025-01-02 | B – Reviewed With Comments | 2025-01-22 | -8 |  |  | 2025-01-12
BARTEC | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8002 |  | Terminal Boxes - Datasheet | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0014 | 2024-12-13 | 2024-12-23 | BET-HPS-TN-0016 | 2024-12-16 | HPS-BET-TN-0028 | 2024-12-30 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8003 |  | Terminal Boxes - Sealing fitting Datasheet (bushing & Riegler removable double threaded nipple) | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0004 | 2024-11-13 | 2024-11-23 | BET-HPS-TN-0007 | 2024-11-13 | HPS-BET-TN-0010 | 2024-11-14 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8004 |  | Terminal Boxes - Cable glands Datasheet | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0007 | 2024-10-24 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8007 |  | Terminal Boxes - Cable Datasheet | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0007 | 2024-10-24 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | DW | FALSE |  |  |  |  | 09970H60-D201-FE-8005 |  | Terminal Boxes - Junction box drawing | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0004 | 2024-11-13 | 2024-11-23 | BET-HPS-TN-0007 | 2024-11-13 | HPS-BET-TN-0010 | 2024-11-14 | A – Reviewed Without Comment | 2025-01-22
BARTEC | ELE | OM | FALSE |  |  |  |  | 09970H60-D201-FE-8006 |  | Terminal Boxes - Junction box Manual operating instruction | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0004 | 2024-11-13 | 2024-11-23 | BET-HPS-TN-0007 | 2024-11-13 | HPS-BET-TN-0010 | 2024-11-14 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FS-818 |  | CANCELED - Instrument Cable Specification |  | CAN | [9 empty] | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0009 | 2024-10-31 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | LST | TRUE | 2024-10-07 | RHL-001293825 | EA |  | 09970H60-D201-FD-824 |  | Electrical Consumers List | 02 | IFD | 2024-12-03 | HPS-SHE-TN-0128 | 2024-12-04 | 2024-12-17 |  |  |  |  | -27 | VEP 0004 | 2024-11-13 | 2024-11-23 | BET-HPS-TN-0007 | 2024-11-13 | HPS-BET-TN-0010 | 2024-11-14 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | DS | FALSE | 2024-07-26 |  |  |  | 09970H60-D201-FS-876 |  | CANCELED - Local Panel (Lighting) |  | CAN | [9 empty] | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0009 | 2024-10-31 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | DS | FALSE | 2024-09-27 |  |  |  | 09970H60-D201-FS-877 |  | CANCELED - Feed Through Electrode - Technical Specification |  | CAN | [9 empty] | VEP 0017 | 2025-01-15 | 2025-01-25 | BET-HPS-TN-0021 | 2025-01-15 | HPS-BET-TN-0031 | 2025-01-16 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | DW | FALSE |  |  |  |  | 09970H60-D201-FD-830 |  | CANCELED - Local Panel (Lighting) |  | CAN | [9 empty] | VEP 0002 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0009 | 2024-10-31 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | GAD | FALSE |  |  |  |  | 09970H60-D201-FD-876 |  | CANCELED - MV/LV Transformer Cubicles Layout and GAD: included in FD-874) |  | CAN | [9 empty] | VEP 0017 | 2025-01-15 | 2025-01-25 | BET-HPS-TN-0021 | 2025-01-15 | HPS-BET-TN-0032 | 2025-01-20 | A – Reviewed Without Comment | 2025-01-22
KANTHAL | INSP | FQ | TRUE |  | RHL-001293763 | QA | QA5733 | 09970H60-D201-FQ-204 |  | Heating Elements - Inspection Test Plan | 01 | IFD | 2024-10-02 | HPS-SHE-TN-0131 | 2024-12-09 | 2024-12-22 |  |  |  |  | -23 | [8 empty] | 2025-01-22
HPS | ELE | LST | FALSE |  |  |  |  | 09970H60-D201-FS-863 |  | Schneider Electric Delivery List | 00 | IEE | 2023-11-03 | [8 empty] | VEP 0016 | 2025-01-07 | 2025-01-17 | BET-HPS-TN-0019 | 2025-01-07 | HPS-BET-TN-0030 | 2025-01-08 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | MTR | FALSE |  |  |  |  | 09970H60-D201-FS-861 |  | Technical Requisition for Power and Control Panel for Electrical Heater | 00 | IFO | 2023-10-27 |  |  |  |  | 2024-04-12 | B - Proceed Change as Noted & Resubmit |  |  | VEP 0012 | 2024-12-11 | 2024-12-21 | BET-HPS-TN-0014 | 2024-12-11 |  |  |  | 2025-01-22 |  | 2024-04-22 |  |  | -23
HPS | ELE | MTR | FALSE |  |  |  |  | 09970H60-D201-FS-862 |  | Technical Requisition for Electrical Engineering Studies & Material Cost Estimate | 00 | IFO | 2023-10-27 | [8 empty] | VEP 0004 | 2024-11-13 | 2024-11-23 | BET-HPS-TN-0007 | 2024-11-13 | HPS-BET-TN-0013 | 2024-11-18 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | MTR | FALSE | 2024-06-28 | RHL-001293872 |  |  | 09970H60-D201-FS-868 |  | Technical Requisition for E-HOUSE (717) Package | 03 | IFO | 2024-08-14 | HPS-SHE-TN-0174 | 2025-01-13 | 2025-01-26 |  |  |  | case doit etre orange | 3 | VEP 0007 | 2024-11-18 | 2024-11-28 | BET-HPS-TN-0012 | 2024-11-28 | HPS-BET-TN-0026 | 2024-12-12 | A – Reviewed Without Comment | 2025-01-22
HPS | ELE | MTR | FALSE | 2024-10-04 | RHL-001293876 |  |  | 09970H60-D201-FS-874 |  | Technical Requisition for Electrical Terminal Boxes | 03 | IFD | 2024-11-13 | [8 empty] | VEP 0013 | 2024-12-12 | 2024-12-22 | BET-HPS-TN-0015 | 2024-12-12 |  |  |  | 2025-01-22 |  |  |  |  | -23
HPS | ELE | MTR | FALSE | 2024-06-14 |  |  |  | 09970H60-D201-FS-875 |  | Technical Requisition for Heating Elements | 01 | IFO | 2024-07-08 | [8 empty] | TN-0008 | 2024-11-07 | 2024-11-17 | BET-HPS-TN-0006 | 2024-11-07 |  |  |  | 2025-01-22 |  |  |  |  | -48
HPS | ELE | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-820 |  | MR - MV/LV Electrical Cables | [19 empty] | 2025-01-22
KANTHAL | ELE | OM | FALSE |  |  |  |  | 09970H60-D201-FE-201 | JN | Heating Elements - Engineering Summary | 00 | IFR | 2024-07-22 | [8 empty] | Mail | 2024-12-19 | 2024-12-29 | BET-HPS-TN-0020 | 2025-01-07 |  |  |  | 2025-01-22 |  |  |  |  | -18
TUBACEX - TTI | INSP | FQ | TRUE |  | RHL-001293996 | QA | QA5733 | 09970H60-D201-FQ-111 | ITP400564 | Tubes - Inspection & Test Plan | 01 | IFD | 2024-12-05 | HPS-SHE-TN-0130 | 2024-12-09 | 2024-12-22 |  |  |  |  | -23 |  |  |  | SHE-HPS-TN-0058 | 2024-11-25 |  |  |  | 2025-01-22
SE - SCHNEIDER | ELE | CN | FALSE | 2025-01-17 | RHL-001293817 |  |  | 09970H60-D201-FC-804 |  | Lighting calculation (E-House) | 00 | IFD | 2024-12-30 | [16 empty] | 2025-01-22
AGEX | INS | DW | TRUE | 2024-10-04 | RHL-001293895 | IN | IN2335 | 09970H60-D201-FD-840 |  | Instrument Hook Ups (E-Heater) | 01 | IFD | 2024-10-01 | HPS-SHE-TN-0135 | 2024-12-11 | 2024-12-24 |  |  |  |  | -22 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | CN | FALSE | 2025-01-17 |  |  |  | 09970H60-D201-FD-883 |  | Lighting Layout (E-House) |  | IFR | [9 empty] | TN-0001 | 2024-11-25 | 2024-12-05 | DIS-HPS-TN-0002 | 2024-11-28 | HPS-DIS-TN-0004 | 2024-12-19 | B – Reviewed With Comments | 2025-01-22 | -18 |  |  | 2024-12-29
SE - SCHNEIDER | ELE | DS | FALSE |  | RHL-001293819 |  |  | 09970H60-D201-FD-843 |  | (E-House) Bulk Equipment Datasheet | [19 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293992 | CX |  | 09970H60-D201-FK-006 |  | E-Heater GAD - Nozzles layout | 03 | IFD | 2024-12-06 | HPS-SHE-TN-0133 | 2024-12-11 | 2024-12-24 |  |  |  |  | -22 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PH | TRUE | 2025-01-20 | RHL-001293870 | EA |  | 09970H60-D201-FS-866 |  | Electrical Study (Load Flow and short circuit study) (E-House) | 02 | IFD | 2024-12-16 | HPS-SHE-TN-0139 | 2024-12-16 | 2024-12-29 |  |  |  |  | -18 | [8 empty] | 2025-01-22
HPS | QC | PR | TRUE | 2024-10-08 | RHL-001293961 | QA | QA6180 | 09970H60-D201-FJ-002 |  | CE - Certification Plan | 03 | IFD | 2024-12-13 | HPS-SHE-TN-0137 | 2024-12-16 | 2024-12-29 |  |  |  |  | -18 | VEP 0012 | 2024-12-11 | 2024-12-21 |  |  | HPS-SCH-TN-0025 | 2024-12-18 | A – Reviewed Without Comment | 2025-01-22
HPS | DCC | MDL | TRUE | 2024-06-28 | RHL-001293950 | JA | JA6611 | 09970H60-D201-FA-001 |  | Master Document List | 08 | IFD | 2024-12-11 | HPS-SHE-TN-0154 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DS | FALSE |  |  |  |  | 09970H60-D201-FS-872 |  | CANCELED - LV Cable 600- 1 KV - Datasheet |  | CAN | [9 empty] | TN-0002 | 2024-12-02 | 2024-12-12 | DIS-HPS-TN-0003 | 2024-12-02 | HPS-DIS-TN-0004 | 2024-12-19 | A – Reviewed Without Comment | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293772 |  |  | 09970H60-D201-FE-3010 | Rev_00 - Internal | PLATFORM EL.+1589 AND STAIRS | 02 | IFD | 2024-12-19 | HPS-SHE-TN-0142 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DS | FALSE | 2025-01-12 | RHL-001293877 |  |  | 09970H60-D201-FS-878 | to send for Information | HVAC Equipment (E-House) - Datasheets | 00 | IFD | 2024-12-18 | [16 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293773 |  |  | 09970H60-D201-FE-3015 | Rev_00 - Internal | HANDRAILS FOR PLATFORM EL.+1589 AND STAIRS | 01 | IFD | 2024-12-19 | HPS-SHE-TN-0143 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293774 |  |  | 09970H60-D201-FE-3020 | Rev_00 - Internal | PLATFORM EL.+6551 | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0144 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2024-09-11 |  |  |  | 09970H60-D201-FD-827 |  | CANCELED - Single Line diagram (E-Heater) |  | CAN | [12 empty] | SHE-HPS-TN-0056 | 2024-11-25 |  |  |  | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2025-02-21 | RHL-001293830 |  |  | 09970H60-D201-FD-835 |  | MCT Layout (E-House) | 0 | IFD | 2024-12-02 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2024-10-31 | RHL-001293831 |  |  | 09970H60-D201-FD-836 |  | LV Switchboard - GAD (General Arrangement Drawing) (E-House) | 01 | IFD | 2024-10-30 | HPS-SHE-TN-0098 | 2024-10-29 | 2024-11-11 | SHE-HPS-TN-0098 | 2024-11-15 | D - for Information Only | [5 empty] | SHE-HPS-TN-0055 | 2024-11-25 |  |  |  | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2024-11-27 | RHL-001293832 |  |  | 09970H60-D201-FD-837 |  | LV Switchboard - Wiring Diagram (E-House) | 0 | IFD | 2024-11-07 | HPS-SHE-TN-0114 | 2024-11-07 | 2024-11-20 |  |  |  |  | -46 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2024-10-30 | RHL-001293833 |  |  | 09970H60-D201-FD-838 |  | MV/LV Transformer - GAD (General Arrangement Drawing) (E-House) | 01 | IFD | 2024-10-29 | HPS-SHE-TN-0102 | 2024-10-29 | 2024-11-11 | SHE-HPS-TN-0102 | 2024-11-15 | D - for Information Only | [10 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2024-11-24 | RHL-001293834 |  |  | 09970H60-D201-FD-839 |  | MV/LV Transformer - Wiring Diagram (E-House) | 03 |  | 2025-01-20 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2025-04-02 | RHL-001293836 |  |  | 09970H60-D201-FD-844 |  | LV Busduct Layout and General Arrangement (E-House) | [19 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293775 |  |  | 09970H60-D201-FE-3025 | Rev_00 - Internal | HANDRAILS PLATFORM EL.+6551 | 01 | IFD | 2024-12-19 | HPS-SHE-TN-0145 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293776 |  |  | 09970H60-D201-FE-3030 | Rev_00 - Internal | PLATFORM EL.+11513 | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0146 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2025-01-18 | RHL-001293849 |  |  | 09970H60-D201-FD-868 |  | Cable Routing, Cable Tray, Layout and Details (E-House) | SAME o | [18 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2025-01-18 | RHL-001293850 |  |  | 09970H60-D201-FD-869 |  | HVAC Layouts (E-House) | SAME o | [18 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293770 |  |  | 09970H60-D201-FE-3035 | Rev_00 - Internal | HANDRAILS PLATFORM EL.+11513 | 02 | IFD | 2024-12-19 | HPS-SHE-TN-0147 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | FALSE | 2025-01-18 | RHL-001293861 |  |  | 09970H60-D201-FD-887 |  | Lighting and Small Power Layout (E-House) | SAME o | [18 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293778 |  |  | 09970H60-D201-FE-3040 | Rev_00 - Internal | PLATFORM EL.+14430 | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0148 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | LST | FALSE | 2024-12-04 | RHL-001293839 |  |  | 09970H60-D201-FD-847 |  | CANCELED - LV Switchboard - Item List (E-House) |  | CAN | [17 empty] | 2025-01-22
SE - SCHNEIDER | ELE | LST | FALSE | 2024-11-28 | RHL-001293840 |  |  | 09970H60-D201-FD-848 |  | CANCELED MV/LV Transformer - Item List (E-House) |  | CAN | [17 empty] | 2025-01-22
SE - SCHNEIDER | ELE | LST | FALSE | 2025-03-28 | RHL-001293841 |  |  | 09970H60-D201-FD-849 |  | Item List (E-House) | [19 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293779 |  |  | 09970H60-D201-FE-3045 | Rev_00 - Internal | HANDRAILS PLATFORM EL.+14430 | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0149 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293781 |  |  | 09970H60-D201-FE-3050 | Rev_00 - Internal | RADIANT LADDERS L1 ; L2 & L3 | 01 | IFD | 2024-12-19 | HPS-SHE-TN-0150 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | FALSE | 2024-11-29 | RHL-001293844 |  |  | 09970H60-D201-FD-857 |  | LV Switchboard - IOM (Instruction & Operating Manual) (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | FALSE | 2024-12-16 | RHL-001293846 |  |  | 09970H60-D201-FD-860 |  | MV/LV Transformer - IOM (Instruction & Operating Manual) (E-House) | 00 | IFD | 2024-09-30 | HPS-SHE-TN-0075 | 2024-10-08 | 2024-10-21 | SHE-HPS-TN-0075 | 2024-10-22 | A - Proceed | [10 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293782 |  |  | 09970H60-D201-FE-3060 | Rev_00 - Internal | Stair Case - Structure | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0151 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | FALSE |  |  |  |  | 09970H60-D201-FD-889 |  | E-House - IOM (Instruction & Operating Manual) | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | FALSE |  |  |  |  | DOCA0101EN-00 |  | CANCELED - Circuit Breaker - Masterpact MTZ2/MTZ3 - Circuit Breakers and Switch-Disconnectors - User Guide | 00 | CAN | [17 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | FALSE |  |  |  |  | DOCA0102EN-01 |  | CANCELED - Circuit Breaker - Masterpact MTZ Micrologic X - Control Unit - User Guide | 00 | CAN | [17 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293783 |  |  | 09970H60-D201-FE-3070 | Rev_00 - Internal | Stair Case - Stairs | 02 | IFD | 2024-12-19 | HPS-SHE-TN-0152 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293784 |  |  | 09970H60-D201-FE-3075 | Rev_00 - Internal | Stair Case - Handrails | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0153 | 2024-12-19 | 2025-01-01 |  |  |  |  | -16 | [8 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE |  | For Information - End of Project |  |  | 09970H60-D201-FE-806 |  | PLC - Power Consumption, Load and Heat Dissipation | 00 | IFR | 2024-10-02 | HPS-SHE-TN-0162 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PH | FALSE | 2025-01-17 | RHL-001293873 |  |  | 09970H60-D201-FS-869 |  | LV Switchboard and MV/LV Transformer (E-House) and LV Equipment Plant (E-House) | 0 | IFD | 2024-12-02 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PH | FALSE | 2025-01-17 | RHL-001293874 |  |  | 09970H60-D201-FS-870 | see FS-869 | CANCELED - MV/LV Transformer - Tagging Specification (E-House) |  | CAN | [17 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PR | FALSE | 2025-06-18 | RHL-001293864 |  |  | 09970H60-D201-FQ-863 |  | FAT Procedure and Report (E-House) | [19 empty] | 2025-01-22
HPS | CONS | PR | TRUE | 2025-04-02 | RHL-001293801 | BA | BA5736 | 09970H60-D201-FS-901 |  | Site Installation Plan - (Erection Sequence Procedure) | 01 | IEE | 2024-04-18 | HPS-SHE-TN-0164 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
SE - SCHNEIDER | ELE | SPIR | FALSE | 2024-12-20 | RHL-001293843 |  |  | 09970H60-D201-FD-854 |  | LV Switchboard - Spare Parts List (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | SPIR | FALSE | 2024-11-05 | RHL-001293845 |  |  | 09970H60-D201-FD-858 |  | MV/LV Transformer - Spare Parts List (E-House) | 0 | IFD | 2024-11-06 | HPS-SHE-TN-0112 | 2024-11-06 | 2024-11-19 |  |  |  |  | -47 | [8 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3000 |  | ELECTRICAL RADIANT TUBULAR HEATER - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3010 |  | PLATFORM EL.+1589 AND STAIRS - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3015 |  | HANDRAILS FOR PLATFORM EL.+1589 AND STAIRS - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3020 |  | PLATFORM EL.+6551 - ERECTION DRAWINGS & BOM | [14 empty] | SHE-HPS-TN-0042 | 2024-10-30 |  |  |  | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3025 |  | HANDRAILS PLATFORM EL.+6551 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3030 |  | PLATFORM EL.+11513 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3035 |  | HANDRAILS PLATFORM EL.+11513 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3040 |  | PLATFORM EL.+14430 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3045 |  | HANDRAILS PLATFORM EL.+14430 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3047 |  | SELF-CLOSING SAFETY GATE - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3050 |  | RADIANT LADDERS L1 ; L2 & L3 - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3060 |  | STAIR CASE STRUCTURE - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3070 |  | STAIR CASE - STAIRS - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
BETA | FAB | FE | FALSE |  |  |  |  | 09970H60-D201-ED-3075 |  | STAIR CASE - HANDRAILS - ERECTION DRAWINGS & BOM | [19 empty] | 2025-01-22
AGEX | ELE | DW | TRUE | 2024-10-07 | RHL-001293827 | EA |  | 09970H60-D201-FD-828 |  | Single Line Diagram (E-Heater) | 01 | IFD | 2024-12-20 | HPS-SHE-TN-0156 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
AGEX | ELE | SPE | TRUE | 2024-10-30 | RHL-001293866 | EA |  | 09970H60-D201-FS-814 |  | Lighting Junction Boxes Specification | 00 | IFD | 2024-12-20 | HPS-SHE-TN-0160 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | VEP 0008 | 2024-11-19 | 2024-11-29 | BET-HPS-TN-0011 | 2024-11-20 | HPS-BET-TN-0018 | 2024-11-25 | B – Reviewed With Comments | 2025-01-22 | -35 |  |  | 2024-12-05
BETA | FAB | FQ | TRUE |  | RHL-001293997 |  |  | 09970H60-D201-FQ-3003 |  | Structure - Welding Book (Weld Map,PQR’s and WPS’s) | 01 | IFD | 2024-11-20 | HPS-SHE-TN-0163 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
BETA | FAB | FQ | TRUE |  | RHL-001294000 |  |  | 09970H60-D201-FQ-3024 |  | Radian Coil - Inspection & Tests Plan | 02 | IFD | 2024-12-12 | HPS-SHE-TN-0155 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
HPS | PCS | CEC | TRUE | 2024-07-24 | RHL-001293941 | PX | PX2310 | 09970H60-D201-FJ-861 |  | Cause and effect chart ESD | 03 | IFD | 2024-12-19 | HPS-SHE-TN-0159 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | TN-0002 | 2025-01-08 | 2025-01-18 | ICA-HPS-TN-0002 | 2025-01-08 | HPS-ICA-TN-0002 | 2025-01-09 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | FJ | TRUE | 2024-06-11 | RHL-001293936 | PX | PX2105 | 09970H60-D201-FJ-001 |  | E-Heater - Electrical Heater - Datasheet | 04 | IFD | 2024-12-19 | HPS-SHE-TN-0158 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | MAIL | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0014 | 2024-12-30 | HPS-KAN-TN-0011 | 2025-01-02 | A – Reviewed Without Comment | 2025-01-22
HPS | PRJ | SCH | TRUE | 2024-07-17 | RHL-001293953 | FA | FA5722 | 09970H60-D201-FA-009 |  | GENERAL SCHEDULE - EPF | 04 | IFD | 2024-12-19 | HPS-SHE-TN-0157 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | VEP 0013 | 2024-12-13 | 2024-12-23 | SCH-HPS-TN-0008 | 2024-12-09 |  |  |  | 2025-01-22 |  |  |  |  | -23
BETA | FAB | FQ | TRUE |  | RHL-001294000 |  |  | 09970H60-D201-FQ-3024 |  | INSPECTION & TESTS PLAN - RADIANT COIL | 02 | IFD | 2024-12-12 | HPS-SHE-TN-0155 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | VEP 0013 | 2024-12-12 | 2024-12-22 | BET-HPS-TN-0015 | 2024-12-12 |  |  |  | 2025-01-22 |  |  |  |  | -23
AGEX | ELE | DW | TRUE | 2024-10-07 | RHL-001293827 |  |  | 09970H60-D201-FD-828 |  | Single Line Diagram (E-Heater) | 01 | IFD | 2024-12-20 | HPS-SHE-TN-0156 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
HPS | PRJ | SCH | TRUE | 2024-07-17 | RHL-001293953 |  |  | 09970H60-D201-FA-009 |  | GENERAL SCHEDULE - EPF | 04 | IFD | 2024-12-19 | HPS-SHE-TN-0157 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
HPS | PCS | FJ | TRUE | 2024-06-11 | RHL-001293936 |  |  | 09970H60-D201-FJ-001 |  | E-Heater - Electrical Heater - Datasheet | 04 | IFD | 2024-12-19 | HPS-SHE-TN-0158 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
HPS | PCS | CEC | TRUE | 2024-07-24 | RHL-001293941 |  |  | 09970H60-D201-FJ-861 |  | Cause and effect chart ESD | 03 | IFD | 2024-12-19 | HPS-SHE-TN-0159 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
AGEX | ELE | SPE | TRUE | 2024-10-30 | RHL-001293866 |  |  | 09970H60-D201-FS-814 |  | Lighting Junction Boxes Specification | 00 | IFD | 2024-12-20 | HPS-SHE-TN-0160 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE |  | For Information - End of Project |  |  | 09970H60-D201-FE-806 |  | PLC - Power Consumption, Load and Heat Dissipation | 00 | IFR | 2024-10-02 | HPS-SHE-TN-0162 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | TN-0001 | 2024-10-07 | 2024-10-17 | TEC-HPS-TN-0001 | 2024-10-08 | HPS-TEC-TN-0003 | 2024-12-30 | A – Reviewed Without Comment | 2025-01-22
BETA | FAB | FQ | TRUE |  | RHL-001293997 |  |  | 09970H60-D201-FQ-3003 |  | WELDING BOOK - STRUCTURE (Weld Map,PQR’s and WPS’s) | 01 | IFD | 2024-11-20 | HPS-SHE-TN-0163 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | VEP 0008 | 2024-11-19 | 2024-11-29 | BET-HPS-TN-0011 | 2024-11-20 | HPS-BET-TN-0018 | 2024-11-25 | B – Reviewed With Comments | 2025-01-22 | -35 |  |  | 2024-12-05
HPS | CONS | PR | TRUE | 2025-04-02 | RHL-001293801 |  |  | 09970H60-D201-FS-901 |  | Site Installation Plan - (Erection Sequence Procedure) | 01 | IEE | 2024-04-18 | HPS-SHE-TN-0164 | 2024-12-30 | 2025-01-12 |  |  |  |  | -8 | [8 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3005 |  | OFFICIAL CERTIFICATE (ISO 9001, ISO 14001, PED, CPR…) | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3006 |  | NDE PLAN - RADIANT COIL | 00 | IFD | 2024-12-16 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3007 |  | NDE PLAN - STEEL STRUCTURE | 01 | IFD | 2024-12-16 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3008 |  | PMI PROCEDURE (Positive Material Identification) | 01 | IFD | 2024-11-13 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3009 |  | VT PROCEDURE EN | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3010 |  | VT PROCEDURE ASME | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3011 |  | PT PROCEDURE EN | 01 | IFD | 2024-11-13 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3012 |  | PT PROCEDURE ASME | 01 | IFD | 2024-11-13 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3013 |  | MT PROCEDURE EN | 00 | IFD | 2024-10-14 | [11 empty] | SHE-HPS-TN-0045 | 2024-10-30 |  |  |  | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3014 |  | MT PROCEDURE ASME | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3015 |  | UT PROCEDURE EN | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3016 |  | UT PROCEDURE ASME | 01 | IFD | 2025-01-15 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3017 |  | RT PROCEDURE EN | 00 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3018 |  | RT PROCEDURE ASME | 01 | IFD | 2025-01-15 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3019 |  | HYDROTEST PROCEDURE | 01 | IFD | 2024-11-13 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3020 | For Information | SURFACE PREPARATION & PAINTING PROCEDURE | 02 | IFD | 2025-01-07 | [11 empty] | SHE-HPS-TN-0040 | 2024-10-30 |  |  |  | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3021 |  | TRIAL ASSEMBLY PROCEDURE | 02 | IFD | 2024-12-11 | [16 empty] | 2025-01-22
BETA | FAB | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-3022 |  | RECEIVED INSPECTION PROCEDURE | 01 | IFD | 2024-11-13 | [11 empty] | SHE-HPS-TN-0047 | 2024-11-04 |  |  |  | 2025-01-22
BETA | FAB | FQ | TRUE |  | RHL-001293998 |  |  | 09970H60-D201-FQ-3004 |  | Radian Coil - Welding Book (Weld Map,PQR’s and WPS’s) | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0165 | 2025-01-02 | 2025-01-15 |  |  |  |  | -6 | [8 empty] | 2025-01-22
BETA | FAB | FQ | TRUE |  | RHL-001293998 |  |  | 09970H60-D201-FQ-3004 |  | WELDING BOOK - RADIANT COIL (Weld Map,PQR’s and WPS’s) | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0165 | 2025-01-02 | 2025-01-15 |  |  |  |  | -6 | VEP 0015 | 2024-12-19 | 2024-12-29 | BET-HPS-TN-0018 | 2024-12-23 |  |  |  | 2025-01-22 |  |  |  |  | -18
BETA | HSE | PR | FALSE |  |  |  |  | 09970H60-D201-FQ-3030 |  | HSE PLAN & STATISTICS | 00 | IFD | 2024-11-08 | [16 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-09-02 | RHL-001293903 | IN | IN2105 | 09970H60-D201-FS-809 |  | Rupture Disc - Specification | 02 | IFD | 2024-09-05 | HPS-SHE-TN-0167 | 2025-01-07 | 2025-01-20 |  |  |  |  | -3 | [8 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-09-02 | RHL-001293903 |  |  | 09970H60-D201-FS-809 |  | Rupture Disc - Specification | 02 | IFD | 2024-09-05 | HPS-SHE-TN-0167 | 2025-01-07 | 2025-01-20 |  |  |  |  | -3 | [8 empty] | 2025-01-22
HPS | HSE | PR | FALSE |  |  |  |  | RUE HSE IN 0264 EN |  | Standard HSE Plan for Engineering, Procurement & Fabrication | 00 |  | 2024-08-06 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | TRUE | 2025-02-21 | RHL-001293854 | EA |  | 09970H60-D201-FD-873 |  | Earthing Layout - E-House | 01 | IFD | 2025-01-08 | HPS-SHE-TN-0169 | 2025-01-08 | 2025-01-21 |  |  |  |  | -2 | [8 empty] | 2025-01-22
AGEX | INS | LST | TRUE | 2024-09-10 | RHL-001293894 | IN | IN4308 | 09970H60-D201-FD-831 |  | Instrument Cables List | 01 | IFD | 2024-09-06 | HPS-SHE-TN-0168 | 2025-01-08 | 2025-01-21 |  |  |  |  | -2 | [8 empty] | 2025-01-22
AGEX | INS | LST | TRUE | 2024-09-10 | RHL-001293894 |  |  | 09970H60-D201-FD-831 |  | Instrument Cables List | 01 | IFD | 2024-09-06 | HPS-SHE-TN-0168 | 2025-01-08 | 2025-01-21 |  |  |  |  | -2 | [5 empty] | HPS-AGEX-TN-0003 | 2024-10-30 | B – Reviewed With Comments | 2025-01-22 | -53 |  |  | 2024-11-09
SE - SCHNEIDER | ELE | DW | TRUE | 2025-02-21 | RHL-001293854 |  |  | 09970H60-D201-FD-873 |  | Earthing Layout - E-House | 01 | IFD | 2025-01-08 | HPS-SHE-TN-0169 | 2025-01-08 | 2025-01-21 |  |  |  |  | -2 | [8 empty] | 2025-01-22
SE - SCHNEIDER | INSP | FQ | TRUE | 2025-04-29 | RHL-001293864 | QA | QA5733 | 09970H60-D201-FQ-862 |  | ITP (E-House) | 01 | IFD | 2024-12-05 | HPS-SHE-TN-0170 | 2025-01-09 | 2025-01-22 |  |  |  |  | 1 |  |  |  | SHE-HPS-TN-0057 | 2024-11-25 |  |  |  | 2025-01-22
SE - SCHNEIDER | INSP | FQ | TRUE | 2025-04-29 | RHL-001293864 |  |  | 09970H60-D201-FQ-862 |  | ITP (E-House) | 01 | IFD | 2024-12-05 | HPS-SHE-TN-0170 | 2025-01-09 | 2025-01-22 |  |  |  |  | 1 | VEP 0010 | 2024-12-05 | 2024-12-15 | SCH-HPS-TN-0005 | 2024-12-05 |  |  |  | 2025-01-22 |  |  |  |  | -28
BETA | FAB | FE | TRUE |  | RHL-001293785 |  |  | 09970H60-D201-FE-3000 | Rev_00 - Internal | ELECTRICAL RADIANT TUBULAR HEATER | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0176 | 2025-01-13 | 2025-01-26 |  |  |  |  | 3 | [8 empty] | 2025-01-22
BETA | PRJ | FE | TRUE |  | RHL-001293786 | AA |  | 09970H60-D201-FE-3002 | Rev_00 - Internal | Acces Door - Electrical Radiant Tubular Heater | 00 | IFD | 2024-12-19 | HPS-SHE-TN-0175 | 2025-01-13 | 2025-01-26 |  |  |  |  | 3 | [8 empty] | 2025-01-22
SE - SCHNEIDER | STR | DW | TRUE | 2025-01-06 | RHL-001293970 |  |  | 09970H60-D201-FD-002 | PO+20 | Foundation Layout Drawing & Base Plate Details Drawing ( E-House ) | 01 | IFD | 2024-12-20 | HPS-SHE-TN-0171 | 2025-01-13 | 2025-01-26 |  |  |  |  | 3 | [5 empty] | HPS-SCH-TN-0030 | 2025-01-13 | B – Reviewed With Comments | 2025-01-22 | 2 |  |  | 2025-01-23
AGEX | INS | LST | FALSE |  |  |  |  | 09970H60-D201-FD-856 |  | MTO - E&I Bulk (E-Heater) | 00 | IFD | 2024-12-16 | [16 empty] | 2025-01-22
AGEX | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-816 |  | MR for Instrument Junction Box & Hand Switch | 00 | IFD | 2024-10-24 | [16 empty] | 2025-01-22
SE - SCHNEIDER | STR | DW | TRUE | 2025-01-29 | RHL-001293985 |  |  | 09970H60-D201-FD-852 |  | Structural Steel Drawings (Detailed Eng.) (E-house) | 00 | IFD | 2025-01-06 | HPS-SHE-TN-0172 | 2025-01-13 | 2025-01-26 |  |  |  |  | 3 | VEP 0019 | 2025-01-06 | 2025-01-16 |  |  | HPS-SCH-TN-0030 | 2025-01-13 | B – Reviewed With Comments | 2025-01-22 | 2 |  |  | 2025-01-23
SE - SCHNEIDER | STR | FC | TRUE | 2025-01-29 | RHL-001293968 |  |  | 09970H60-D201-FC-302 |  | Structural steel, Lifting lugs and Foundation Load calculation note (E-House) | 00 | IFD | 2025-01-06 | HPS-SHE-TN-0173 | 2025-01-13 | 2025-01-26 |  |  |  |  | 3 | VEP 0019 | 2025-01-06 | 2025-01-16 |  |  | HPS-SCH-TN-0030 | 2025-01-13 | B – Reviewed With Comments | 2025-01-22 | 2 |  |  | 2025-01-23
AGEX | ELE | LST | TRUE | 2024-11-08 | RHL-001293859 | EA |  | 09970H60-D201-FD-880 |  | LV Electrical Cable List (E-Heater) (sockets, instrum, lighting, fan) | 01 | IFD | 2025-01-14 | HPS-SHE-TN-0180 | 2025-01-15 | 2025-01-28 |  |  |  |  | 5 | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
AGEX | ELE | PH | TRUE | 2024-10-30 | RHL-001293777 | EA |  | 09970H60-D201-FD-878 |  | Earthing Philosophy and Typicals (E-Heater) | 01 | IFD | 2025-01-15 | HPS-SHE-TN-0179 | 2025-01-15 | 2025-01-28 |  |  |  |  | 5 | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
SE - SCHNEIDER | ELE | LST | TRUE | 2024-11-22 | RHL-001293829 | EA |  | 09970H60-D201-FD-833 |  | MV/LV Electrical Cable list (E House) | 02 | IFD | 2024-10-29 | HPS-SHE-TN-0177 | 2025-01-15 | 2025-01-28 |  |  |  |  | 5 | [8 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293900 | IN | IN2105 | 09970H60-D201-FS-805 |  | O2 Analyzer - Specification | 02 | IFD | 2024-12-09 | HPS-SHE-TN-0181 | 2025-01-16 | 2025-01-29 |  |  |  |  | 6 | [8 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-08-30 | RHL-001293901 | IN | IN2105 | 09970H60-D201-FS-806 |  | HC Analyzer - Specification | 02 | IFD | 2024-12-09 | HPS-SHE-TN-0182 | 2025-01-16 | 2025-01-29 |  |  |  |  | 6 | [8 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-10-02 | RHL-001293904 | IN | IN2105 | 09970H60-D201-FS-810 |  | FLOWMETERS (Coriolis) - Specification | 01 | IFD | 2025-01-15 | HPS-SHE-TN-0183 | 2025-01-20 | 2025-02-02 |  |  |  |  | 8 | [8 empty] | 2025-01-22
HPS | 3COLL | FM | TRUE | 2024-07-25 | RHL-001293790 |  |  | 09970H60-D201-DR-001 |  | 3D review 30% | 03 | IFD | 2024-10-17 | HPS-SHE-TN-0080 | 2024-10-21 | 2024-11-03 | SHE-HPS-TN-0080 | 2024-11-20 | B - Proceed Change as Noted & Resubmit | [7 empty] | SHE-HPS-TN-0049 | 2024-11-12 | C – Rejected | 2025-01-22 | -44 | 2024-11-30 | -38 | 2024-11-22
HPS | 3COLL | FM | TRUE |  | RHL-001293792 |  |  | 09970H60-D201-DR-003 |  | 3D review 60% | 00 | IFD | 2024-10-29 | HPS-SHE-TN-0105 | 2024-10-30 | 2024-11-12 | SHE-HPS-TN-0105 | 2024-11-20 | B - Proceed Change as Noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-30 | -38
HPS | INS | DS | FALSE | 2024-08-02 |  |  |  | 09970H60-D201-FS-830 |  | CANCELED - Local Instruments All Types |  | CAN | [17 empty] | 2025-01-22
HPS | INS | DW | FALSE |  |  |  |  | 09970H60-D201-FD-832 |  | CANCELED - Instrument & Electrical Cable Routing (A/G and U/G) - JB Layout | 01 | CAN | [17 empty] | 2025-01-22
HPS | AUT | ITP | TRUE |  | For Information End of Project |  |  | 09970H60-D201-FQ-800 |  | PLC - Inspection & Test Plan (ITP), FAT procedure and FAT report | [16 empty] | SHE-HPS-TN-0060 | 2024-12-17 | B – Reviewed With Comments | 2025-01-22 | -19 |  |  | 2024-12-27
HPS | INS | LST | FALSE |  |  |  |  | 09970H60-D201-FD-812 |  | CANCELED - I/O List With Trip & Alarm List |  | CAN | [17 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-802 |  | MR - ON/OFF Valves | 02 | IFI | 2024-09-03 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-803 |  | MR - Relief Valves Requisition | 01 | IFI | 2024-09-06 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-804 |  | MR - Control Valve | 01 | IFI | 2024-08-30 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-805 |  | MR - O2 Analyzer | 02 | IFO | 2024-12-09 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-806 |  | MR - HC Analyzer | 02 | IFO | 2024-12-09 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-807 |  | MR - TW/TE/TT | 01 | IFI | 2024-08-30 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-809 |  | MR - Rupture Disc | 01 | IFI | 2024-09-05 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-810 |  | MR - Flowmeter (Coriolis) | 01 | IFO | 2025-01-15 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-812 |  | MR - Skin Thermocouples | 00 | IFI | 2024-08-30 | [16 empty] | 2025-01-22
HPS | INS | MTR | FALSE |  |  |  |  | 09970H60-D201-NT-813 |  | MR - Pressure & DP Flow Transmitters | 00 | IFI | 2024-09-27 | [16 empty] | 2025-01-22
SISTEC | INS | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8106 |  | Analysers - Heurtey Petrochem Solutions's datasheet completed by supplier | [19 empty] | 2025-01-22
SISTEC | INS | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8111 |  | Analysers - Product catalog and datasheets - 12400573 Annex 8 - Hummel M20x1.5 fitting - data sheet | [19 empty] | 2025-01-22
SISTEC | INS | DS | FALSE |  |  |  |  | 09970H60-D201-FE-8112 |  | Analysers - Product catalog and datasheets - LaserGas-III-SP-Gas-Analyzer_0224 | [19 empty] | 2025-01-22
SISTEC | INS | DW | FALSE |  |  |  |  | 09970H60-D201-FE-8101 |  | Analysers - Dimensional drawings GADs - 12400573 Annex 5 - GAD Analyser | [19 empty] | 2025-01-22
SISTEC | INS | DW | FALSE |  |  |  |  | 09970H60-D201-FE-8102 |  | Analysers - Electrical connection drawing- 12400573 – Example of electrical scheme - cables to BJ | [19 empty] | 2025-01-22
SISTEC | INS | DW | FALSE |  |  |  |  | 09970H60-D201-FE-8110 |  | Analysers - Pneumatic Diagram - 12400573-02 Annex 6 – Estimated dimensions and layout for control panels | [19 empty] | 2025-01-22
SISTEC | INS | LST | FALSE |  |  |  |  | 09970H60-D201-FE-8108 |  | Analysers - Packing list | [19 empty] | 2025-01-22
SISTEC | INS | OM | FALSE |  |  |  |  | 09970H60-D201-FE-8103 |  | Analysers - Erection and operating manual - 12400573 Annex 7 - LG_III_Modbus TCP-ENG | [19 empty] | 2025-01-22
SISTEC | INS | OM | FALSE |  |  |  |  | 09970H60-D201-FE-8104 |  | Analysers - Erection and operating manual - 12400573 Annex 9 - User Manual LG III SP ATEX for SIL SW Ver 1_0 -new-ENG | [19 empty] | 2025-01-22
SISTEC | INS | OM | FALSE |  |  |  |  | 09970H60-D201-FE-8105 |  | Analysers - Erection and operating manual German | [19 empty] | 2025-01-22
SISTEC | INS | PR | FALSE |  |  |  |  | 09970H60-D201-FE-8107 |  | Analysers - Instruction for transportation and storing | [19 empty] | 2025-01-22
SISTEC | INS | SPIR | FALSE |  |  |  |  | 09970H60-D201-FE-8113 |  | Analysers - Spare part list for start up and commissioning with prices | [19 empty] | 2025-01-22
SISTEC | INS | SPIR | FALSE |  |  |  |  | 09970H60-D201-FE-8114 |  | Analysers - Spare part list for two years operation without prices | [19 empty] | 2025-01-22
BARTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8004 |  | Terminal Boxes - FAT/ITP | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE |  | RHL-001293795 |  |  | 09970H60-D201-FE-800 |  | PLC - IS Loops Calculation Note (E-Heater) | [19 empty] | 2025-01-22
HPS | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-001B |  | CANCELED - Specification of Inspection - Annex B - Cast pressure parts (TBC) |  | CAN | [17 empty] | 2025-01-22
HPS | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-001F |  | CANCELED - Specification of Inspection - Annex F - Cast supports |  | CAN | [17 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE | 2024-08-21 | RHL-001293796 |  |  | 09970H60-D201-FE-802 |  | PLC - Wiring Diagram (incl. Single Line Diagrams & Earthing Arrangemt) | 02 | IFD | 2025-01-14 | [16 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE |  | RHL-001293798 |  |  | 09970H60-D201-FE-803 |  | PLC - GAD (incl. layout, dimension & Bill of Material) | 02 | IFD | 2025-01-14 | [16 empty] | 2025-01-22
TECHMA | AUT | FE | TRUE |  | RHL-001293797 |  |  | 09970H60-D201-FE-804 |  | PLC - System Architecture | 01 | IFD | 2025-01-14 | [16 empty] | 2025-01-22
HPS | CONS | FS | TRUE |  | RHL-001293768 | BA | BA5537 | 09970H60-D201-FS-902 |  | Accessibility Memorandum | 01 | IEE | 2023-11-20 | [8 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
HPS | CONS | PR | TRUE |  | RHL-001293803 | BC | BC5799 | 09970H60-D201-FS-904 |  | Precom / Com - General Procedure | [11 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
HPS | CONS | PR | TRUE |  | RHL-001293805 | BA | BA6070 | 09970H60-D201-FS-905 |  | Start -Up Procedure | [11 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0005 | 2024-12-19 | A – Reviewed Without Comment | 2025-01-22
HPS | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-009 |  | E-House - Axens Organization for Inspection | 00 | IFD | 2024-12-14 | [16 empty] | 2025-01-22
HPS | INSP | PR | FALSE | 2024-06-24 |  |  |  | 09970H60-D201-PR-101 |  | Particular Requirements for Heater Parts | 02 | IFD | 2024-09-30 | [11 empty] | SHE-HPS-TN-0051 | 2024-11-14 |  |  |  | 2025-01-22
KANTHAL | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-200 |  | Heating Elements - Welding procedure | 00 | IFR | 2024-10-02 | [16 empty] | 2025-01-22
KANTHAL | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-201 |  | Heating Elements - Material certificate 3.1 | 00 | IFD | 2024-12-30 | [11 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
KANTHAL | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-202 |  | Heating Elements - Visual and Dimensionnal control | 03 | IFD | 2024-12-20 | [16 empty] | 2025-01-22
KANTHAL | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-203 |  | Heating Elements - Order conformity certificate | 00 | IFD | 2024-12-20 | [16 empty] | 2025-01-22
HPS | CONS | PR | TRUE |  | RHL-001293804 | BA | BA6070 | 09970H60-D201-FS-908 |  | Mounting Sequence Fibrothal | [11 empty] | TN-0002 | 2024-12-11 | 2024-12-21 | BAR-HPS-TN-0001 | 2024-12-11 | HPS-BAR-TN-0003 | 2024-12-19 | D – For Information | 2025-01-22 |  |  |  |  | -23
SE - SCHNEIDER | INSP | FQ | FALSE | 2025-01-20 | RHL-001293862 |  |  | 09970H60-D201-FQ-860 |  | LV Switchboard - ITP (E-House) | 01 | IFD | 2024-12-11 | [16 empty] | 2025-01-22
SE - SCHNEIDER | INSP | FQ | FALSE | 2025-02-18 | RHL-001293863 |  |  | 09970H60-D201-FQ-861 |  | MV/LV Transformer - ITP (E-House) | 2 | IFD | 2024-12-05 | [16 empty] | 2025-01-22
HPS | DCC | FQ | TRUE | 2025-04-01 | RHL-001293810 | JA | JA4372 | 09970H60-D201-FQ-030 |  | Index - EPF Engineering Databook | [11 empty] | VEP 0010 | 2024-11-28 | 2024-12-08 | BET-HPS-TN-0013 | 2024-12-02 | HPS-BET-TN-0023 | 2024-12-05 | A – Reviewed Without Comment | 2025-01-22
SE - SCHNEIDER | INSP | FQ | FALSE | 2024-12-28 | RHL-001293920 |  |  | 09970H60-D201-FQ-865 | End of Project - For Info | Welding Procedure Specifications (WPS) and Qualification (WPQ) Records (E-House) | 00 | IFD | 2024-12-18 | [11 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
SE - SCHNEIDER | INSP | FQ | FALSE | 2025-02-20 | RHL-001293922 |  |  | 09970H60-D201-FQ-867 | End of Project - For Info | NDT Procedure, Liquid Penetrant Examination (E-House) | 0 | IFD | 2024-12-02 | [11 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
SE - SCHNEIDER | INSP | PR | FALSE | 2024-12-20 | RHL-001293923 |  |  | 09970H60-D201-FQ-868 | End of Project - For Info | Surface Preparations and Painting Procedure (E-House) | 0 | IFD | 2024-12-02 | [11 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8100 |  | Analysers - Calibration test certificate hysteresis Functional test | [14 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8101 |  | Analysers - Calibration / test certificate / hysteresis / Functional test reports | [14 empty] | SHE-HPS-TN-0038 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8102 |  | Analysers - Inspection and test plan | [19 empty] | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8103 |  | Analysers - CEM Directive (89/336/CE) | [14 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8104 |  | Analysers - Material certificates EN (3.1, 2.2, 2.1) | [14 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8105 |  | Analysers - Quality assurance certificate Conformity -certificate Orneo-mo-iqnet-ems | [14 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8106 |  | Analysers - Quality assurance certificate Conformity neo-mo-iqnet-qms | [14 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8107 |  | Analysers - Quality assurance certificate Conformity neo-mo-qms-cert-doc-eng | [14 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8108 |  | Analysers - Quality assurance certificate Conformity neo-mo-qms-eng | [19 empty] | 2025-01-22
SISTEC | INSP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-8109 |  | Analysers - Low Voltage Directive (73/23/CE) | [19 empty] | 2025-01-22
HPS | DCC | FQ | TRUE | 2025-06-02 | RHL-001293812 | JA | JA4372 | 09970H60-D201-FQ-050 |  | Index - Manufacturing DataBook - (All Suppliers) | [11 empty] | VEP 0010 | 2024-11-28 | 2024-12-08 | BET-HPS-TN-0013 | 2024-12-02 | HPS-BET-TN-0023 | 2024-12-05 | A – Reviewed Without Comment | 2025-01-22
HPS | DCC | VB | TRUE | 2025-05-01 | RHL-001293811 | AA | AA4880 | 09970H60-D201-FQ-040 | End of Project - For Info | EPF - Engineering Databook | [19 empty] | 2025-01-22
HPS | DCC | VB | TRUE | 2025-09-18 | RHL-001293813 | AA | AA4880 | 09970H60-D201-FQ-060 | End of Project - For Info | Manufacturing Databook (all suppliers) | [19 empty] | 2025-01-22
AGEX | ELE | CN | TRUE | 2024-10-04 | RHL-001293821 | EA | EA1380 | 09970H60-D201-FC-802 |  | Lighting Calculation note (E-Heater) | 00 | IFD | 2024-10-15 | HPS-SHE-TN-0088 | 2024-10-21 | 2024-11-03 | SHE-HPS-TN-0088 | 2024-11-08 | C - Do not Proceed change as noted & Resubmit |  |  | Mail | 2024-12-19 | 2024-12-29 | BET-HPS-TN-0017 | 2024-12-19 |  |  |  | 2025-01-22 |  | 2024-11-18 | -48 |  | -18
AGEX | ELE | CN | TRUE | 2024-10-18 | RHL-001293822 | EA | EA2901 | 09970H60-D201-FC-803 |  | LV Electrical Cables Sizing (E-Heater) (sockets, instrum, lighting, fan) | [11 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
HPS | MEC | DW | FALSE |  |  |  |  | 09970H60-D201-FD-402 |  | CANCELED - Radiant Coil Bottow Guides - Electrical Radiant Tubular Heater | 00 | CAN | [12 empty] | SHE-HPS-TN-0053 | 2024-11-14 |  |  |  | 2025-01-22
AGEX | ELE | DW | TRUE | 2024-10-18 | RHL-001293824 | EA |  | 09970H60-D201-FD-816 |  | Terminal Boxes Wiring Diagram (E-Heater) | [11 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
ICARUS | MEC | FE | FALSE |  |  |  |  | 09970H60-D201-FE-220 |  | ASME B16.5 - Flange - 4” 300 WN RF WT= 6.02 AWT | 01 | IFD | 2025-01-08 | [16 empty] | 2025-01-22
ICARUS | MEC | FE | FALSE |  |  |  |  | 09970H60-D201-FE-221 |  | ASME B16.5 - Flange - 10” 300 WN RF WT= 9.27 AWT | 01 | IFD | 2025-01-08 | [16 empty] | 2025-01-22
KANTHAL | MEC | FE | FALSE |  |  |  |  | 09970H60-D201-FE-203 | JN | Heating Elements - Drawings (Fibrothal Isolation & Kanthal Element) | 04 | IFD | 2024-11-14 | [16 empty] | 2025-01-22
KANTHAL | MEC | LST | FALSE |  |  |  |  | 09970H60-D201-FE-208 |  | Heating Elements - Material List | [14 empty] | SHE-HPS-TN-0035 | 2024-10-29 |  |  |  | 2025-01-22
SE - SCHNEIDER | MEC | CN | FALSE | 2025-01-24 | RHL-001293931 |  |  | 09970H60-D201-FC-303 | End of Project - For Info | Lifting lugs Calculation Notes (Structural) (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | MEC | DW | FALSE | 2025-03-14 | RHL-001293926 |  |  | 09970H60-D201-FD-850 |  | LV Switchboard - Lifting Plan (E-House) | 0 | IFD | 2024-11-06 | HPS-SHE-TN-0110 | 2024-11-06 | 2024-11-19 |  |  |  |  | -47 | [8 empty] | 2025-01-22
SE - SCHNEIDER | MEC | DW | FALSE | 2024-11-08 | RHL-001293925 |  |  | 09970H60-D201-FD-851 |  | MV/LV Transformer - Lifting Plan Technical Specification & Map (E-House) | 0 | IFD | 2024-11-06 | HPS-SHE-TN-0112 | 2024-11-06 | 2024-11-19 |  |  |  |  | -47 |  |  |  | SHE-HPS-TN-0026 | 2024-10-08 |  |  |  | 2025-01-22
AGEX | ELE | DW | TRUE | 2024-10-30 | RHL-001293828 | EA |  | 09970H60-D201-FD-829 |  | Lighting Junction Boxes Wiring Diagram (E-Heater) | 00 | IFD | 2024-11-18 | HPS-SHE-TN-0123 | 2024-11-26 | 2024-12-09 | SHE-HPS-TN-0123 | 2025-01-10 | C - Do not Proceed change as noted & Resubmit |  |  | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  | 2025-01-20 | -3 |  | -18
AGEX | ELE | DW | TRUE | 2024-09-19 | RHL-001293835 | EA |  | 09970H60-D201-FD-842 |  | Electrical Supports drawings Typicals (E-Heater) | 00 | IFD | 2024-11-26 | HPS-SHE-TN-0122 | 2024-11-26 | 2024-12-09 | SHE-HPS-TN-0122 | 2024-12-17 | B - Proceed Change as Noted & Resubmit |  |  | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  | 2024-12-27 | -19 |  | -18
AGEX | ELE | DW | TRUE | 2024-10-30 | RHL-001293851 | EA |  | 09970H60-D201-FD-870 |  | Lighting Layout (E-Heater) | 00 | IFD | 2024-10-17 | HPS-SHE-TN-0089 | 2024-10-21 | 2024-11-03 | SHE-HPS-TN-0089 | 2024-11-08 | C - Do not Proceed change as noted & Resubmit |  |  | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  | 2024-11-18 | -48 |  | -18
HPS | PCS | FJ | FALSE | 2024-09-16 |  |  |  | 09970H60-D201-FJ-003 |  | CANCELED - ID Fan - Datasheet |  | CAN | [9 empty] | MAIL | 2024-09-06 | 2024-09-16 |  |  | HPS-KAN-TN-0001 | 2024-09-11 | A – Reviewed Without Comment | 2025-01-22
AGEX | ELE | DW | TRUE | 2024-10-25 | RHL-001293857 | EA |  | 09970H60-D201-FD-877 |  | LV Electrical Cables Routing (A/G) - JB & Consumers Layout (E-Heater) |  | IFR | [9 empty] | Mail | 2024-12-19 | 2024-12-29 | [5 empty] | 2025-01-22 |  |  |  |  | -18
HPS | PCS | FJ | FALSE |  |  |  |  | 09970H60-D201-FJ-782 |  | Eductor - Datasheet | 01 | IFI | 2024-01-24 | [8 empty] | TN-0001 | 2024-09-13 | 2024-09-23 | KAN-HPS-TN-0003 | 2024-09-17 |  |  |  | 2025-01-22 |  |  |  |  | -88
HPS | PCS | FS | FALSE |  |  |  |  | 09970H60-D201-FJ-809 |  | Drain and Vent and Relief Requirements (if any) | [11 empty] | TN-0003 | 2024-10-02 | 2024-10-12 | KAN-HPS-TN-0005 | 2024-10-03 | HPS-KAN-TN-0005 | 2024-10-03 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | FS | FALSE |  |  |  |  | 09970H60-D201-FJ-893 |  | Boundary conditions for vent piping finning design | 00 | IFD | 2025-01-08 | [8 empty] | TN-0008 | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0015 | 2024-12-30 | HPS-KAN-TN-0012 | 2025-01-09 | B – Reviewed With Comments | 2025-01-22 | -3 |  |  | 2025-01-19
AGEX | ELE | DW | TRUE | 2024-10-30 | RHL-001293858 | EA |  | 09970H60-D201-FD-879 |  | Earthing Layout (E-Heater) | 00 | IEE | 2024-03-05 | [16 empty] | 2025-01-22
AGEX | ELE | SPE | TRUE | 2024-11-01 | RHL-001293867 | EA |  | 09970H60-D201-FS-820 |  | LV Electrical Cables Specification (sockets, instrum, lighting, fan) | [11 empty] | VEP 0003 | 2024-10-11 | 2024-10-21 | BET-HPS-TN-0002 | 2024-10-14 | HPS-BET-TN-0005 | 2024-10-16 | A – Reviewed Without Comment | 2025-01-22
SE - SCHNEIDER | ELE | CN | TRUE | 2024-10-30 | RHL-001293820 | EA | EA2901 | 09970H60-D201-FC-801 |  | MV/LV Cable Sizing Calculation (E-House) | 02 | IFD | 2024-10-28 | HPS-SHE-TN-0099 | 2024-10-29 | 2024-11-11 | SHE-HPS-TN-0099 | 2024-11-20 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-30 | -38
SE - SCHNEIDER | ELE | CN | TRUE | 2025-01-15 | RHL-001293823 | EA | EA1380 | 09970H60-D201-FC-805 |  | Airconditioning Load Calculation and Heat Load Calculation (E-House) | 00 | IFD | 2024-12-18 | [16 empty] | 2025-01-22
HPS | PCS | PD | FALSE | 2024-07-24 |  |  |  | 09970H60-D201-FJ-801 |  | CONFIDENTIAL - Ctrl and Safeguarding Narrative (Functional Analysis) (internal HPS) | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DS | TRUE | 2025-03-21 | RHL-001293856 | EA | EA2180 | 09970H60-D201-FD-875 |  | E-House - Technical Specification | 02 | IFD | 2024-12-16 | HPS-SHE-TN-0138 | 2024-12-16 | 2024-12-29 | SHE-HPS-TN-0138 | 2024-12-17 | C - Do not Proceed change as noted & Resubmit |  |  | TN-0005 | 2025-01-02 | 2025-01-12 | DIS-HPS-TN-0005 | 2025-01-02 | HPS-DIS-TN-0005 | 2025-01-09 | A – Reviewed Without Comment | 2025-01-22 |  | 2024-12-27 | -19
SE - SCHNEIDER | ELE | DS | TRUE |  | RHL-001293760 | EA | EA2105 | 09970H60-D201-FD-888 |  | Fire Detection | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DS | TRUE | 2024-11-20 | RHL-001293869 | EA | EA2105 | 09970H60-D201-FS-865 |  | MV/LV - Transformer Technical Specification (E-House) | 04 | IFD | 2024-10-29 | HPS-SHE-TN-0104 | 2024-10-29 | 2024-11-11 | SHE-HPS-TN-0104 | 2025-01-10 | A - Proceed | [10 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DS | TRUE |  | RHL-001293762 | EA | EA2105 | 09970H60-D201-FS-871 |  | MV-LV Cable 6-10 KV - Datasheet | 01 | IEE | 2024-04-07 | [8 empty] | TN-0004 | 2024-12-11 | 2024-12-21 | DIS-HPS-TN-0004 | 2024-12-12 |  |  |  | 2025-01-22 |  |  |  |  | -23
SE - SCHNEIDER | ELE | DS | TRUE | 2024-12-27 | RHL-001293875 | EA | EA2105 | 09970H60-D201-FS-873 |  | PCP (LV switchgear rated 690 V) - Technical Specification (E-House) | 01 | IEE | 2024-02-21 | [16 empty] | 2025-01-22
HPS | PCS | RE | FALSE |  |  |  |  | 09970H60-D201-FJ-891 |  | CANCELED -Emergency vent sizing philosophy (Relief Valve requirement) |  | CAN | [9 empty] | TN-0001 | 2024-11-19 | 2024-11-29 | MST-HPS-TN-0002 | 2024-11-19 | HPS-MST-TN-0002 | 2024-11-25 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | SPE | FALSE | 2024-07-19 |  |  |  | 09970H60-D201-FS-002 |  | CFD / Thermal Analysis Study | 01 |  | 2024-04-17 | [16 empty] | 2025-01-22
KANTHAL | PCS | FE | FALSE |  |  |  |  | 09970H60-D201-FE-204 | RD | Heating Elements - Fibrothal Datasheet | 00 | IFD | 2024-12-20 | [8 empty] | VEP 0007 | 2024-11-28 | 2024-12-08 | SCH-HPS-TN-0004 | 2024-12-02 | HPS-SCH-TN-0029 | 2025-01-09 | D – For Information | 2025-01-22 |  |  |  |  | -33
KANTHAL | PCS | FE | FALSE |  |  |  |  | 09970H60-D201-FE-205 | RAFIK | Heating Elements - Material Safety DataSheet | 00 | IFD | 2024-12-20 | [16 empty] | 2025-01-22
KANTHAL | PCS | OM | FALSE |  |  |  |  | 09970H60-D201-FE-206 | RAKIK - JN | Heating Elements - IOM for Fibrothal | 00 | IFD | 2024-11-26 | [16 empty] | 2025-01-22
VIO-VERRES | PCS | FE | FALSE |  |  |  |  | 09970H60-D201-FE-701 |  | MATERIAL DATASHEET - SAPPHIRE | 00 | IFD | 2024-12-04 | [16 empty] | 2025-01-22
VIO-VERRES | PCS | FE | FALSE |  |  |  |  | 09970H60-D201-FE-702 |  | TEST REPORT - SAPPHIRE | 04 | IFD | 2024-12-04 | [13 empty] | HPS-SCH-TN-0012 | 2024-11-25 | C – Rejected | 2025-01-22 | -35 |  |  | 2024-12-05
SE - SCHNEIDER | ELE | DW | TRUE | 2025-02-27 | RHL-001293761 | EA |  | 09970H60-D201-FD-826 |  | Single Line Diagram Auxiliaries (E-House) | 01 | IEE | 2024-03-03 | [16 empty] | 2025-01-22
HPS | PIP | DW | FALSE |  |  |  |  | 09970H60-D201-FD-4001 |  | Piping lay-out drawings | 01 | IEE | 2024-02-23 | [8 empty] | VEP 0017 | 2024-12-18 | 2024-12-28 | [5 empty] | 2025-01-22 |  |  |  |  | -18
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-101 |  | Seamless Steel Pipe NPS 4 - Austenitic Stainless Steel (114.3mm / 6.02mm) | 01 | IFR | 2024-09-30 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-102 |  | Seamless Steel Pipe NPS 6 - Austenitic Stainless Steel (168.3mm / 7.11mm) | 00 |  | 2024-07-15 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-103 |  | Seamless Steel Pipe NPS 8 - Austenitic Stainless Steel (219.1mm / 8.18mm) | 00 |  | 2024-07-15 | [8 empty] | VEP 0013 | 2024-12-13 | 2024-12-23 |  |  | HPS-SCH-TN-0023 | 2024-12-17 | C – Rejected | 2025-01-22 | -19 |  |  | 2024-12-27
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-104 |  | Seamless Steel Pipe NPS 10 - Austenitic Stainless Steel (273.11mm / 9.27mm) | 00 |  | 2024-07-15 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-08-01 |  |  |  | 09970H60-D201-FN-105 |  | Seamless Steel Pipe NPS 2 - Austenitic Stainless Steel (60_3mm _ 8_74mm) | 01 | IFR | 2024-09-26 | [13 empty] | HPS-SCH-TN-0032 | 2025-01-13 | A – Reviewed Without Comment | 2025-01-22
HPS | PIP | FN | FALSE | 2024-08-01 |  |  |  | 09970H60-D201-FN-106 |  | Seamless Steel Pipe NPS 4 - Austenitic Stainless Steel (114_3mm _ 8_56mm) | 00 |  | 2024-07-31 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-08-01 |  |  |  | 09970H60-D201-FN-107 |  | Seamless Steel Pipe NPS 4 - Austenitic Stainless Steel (60.3mm _8.74mm) | 00 |  | 2024-07-31 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-08-01 |  |  |  | 09970H60-D201-FN-108 |  | Seamless Steel Pipe NPS 4 - Austenitic Stainless Steel (114_3mm _ 13_49mm) | 00 |  | 2024-07-31 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2025-07-11 |  |  |  | 09970H60-D201-FN-130 |  | Butt Weld Pipe Fitting - Austenitic Stainless Steel (273.11mm / 9.27mm) | 00 |  | 2024-07-15 | [8 empty] | VEP 0017 | 2024-12-18 | 2024-12-28 | SCH-HPS-TN-0008 | 2024-12-18 | HPS-SCH-TN-0026 | 2024-12-18 | D – For Information | 2025-01-22 |  |  |  |  | -18
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-160 |  | Flange - ASME B16.5 (NPS 1/2 to NPS 24) - Austenitic Stainless Steel (Welding Neck) | 00 |  | 2024-07-15 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE | 2024-07-11 |  |  |  | 09970H60-D201-FN-161 |  | Flange - EN 1092.1 - Austenitic Stainless Steel (Weld-Neck type11) | 01 |  | 2024-09-26 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE |  |  |  |  | 09970H60-D201-FN-180 |  | Stud Bolts with 2 Heavy Nuts - Class 2A Coarse series Threads | 00 |  | 2024-09-27 | [16 empty] | 2025-01-22
HPS | PIP | FN | FALSE |  |  |  |  | 09970H60-D201-FN-181 |  | Spiral Wound Gaskets - ASME B16.20 | 00 |  | 2024-09-27 | [8 empty] | VEP 0006 | 2024-11-28 | 2024-12-08 | SCH-HPS-TN-0004 | 2024-12-02 | HPS-SCH-TN-0035 | 2025-01-16 | C – Rejected | 2025-01-22 | 3 |  |  | 2025-01-26
HPS | PIP | FN | FALSE |  |  |  |  | 09970H60-D201-FN-607 |  | Observation Windows Glasses | 00 | IFO | 2024-10-07 | [13 empty] | HPS-SCH-TN-0013 | 2024-11-27 | D – For Information | 2025-01-22
HPS | PIP | LST | FALSE |  |  |  |  | 09970H60-D201-FS-4001 |  | Line list | 01 | IEE | 2024-03-06 | [8 empty] | VEP 0005 | 2024-11-07 | 2024-11-17 |  |  | HPS-SCH-TN-0016 | 2024-12-04 | B – Reviewed With Comments | 2025-01-22 | -28 |  |  | 2024-12-14
HPS | PIP | LST | FALSE |  |  |  |  | 09970H60-D201-FS-4002 |  | Manual Valves List | 00 | IEE | 2023-12-21 | [13 empty] | HPS-SCH-TN-0013 | 2024-11-27 | D – For Information | 2025-01-22
MST | PIP | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-1000 |  | Tubes - Manufacturing, Inspection & Testing Plan | 01 | IFD | 2024-11-19 | [8 empty] | VEP 0014 | 2024-12-16 | 2024-12-26 | SCH-HPS-TN-0007 | 2024-12-16 |  |  |  | 2025-01-22 |  |  |  |  | -20
SISTEC | PL | PR | FALSE |  |  |  |  | 09970H60-D201-FE-8109 |  | Analysers - Planning (Project time schedule) | [19 empty] | 2025-01-22
BARTEC | PRJ | FE | FALSE |  |  |  |  | 09970H60-D201-FE-8008 |  | Terminal Boxes - Overall Project Schedule | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
BARTEC | PRJ | FE | FALSE |  |  |  |  | 09970H60-D201-FE-8009 |  | Terminal Boxes - Subcontractors - List | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
BETA | PRJ | FE | FALSE |  |  |  |  | 09970H60-D201-FE-3001 | Rev_00 - Internal | ELECTRICAL RADIANT TUBULAR HEATER - INSTRUMENTATION | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | TRUE | 2025-02-27 | RHL-001293837 | EA |  | 09970H60-D201-FD-845 |  | Fire Detection - Wiring Diagram and Datasheets (E-House) | [19 empty] | 2025-01-22
BETA | PRJ | FE | FALSE |  |  |  |  | 09970H60-D201-FE-3009 | Rev_00 - Internal | SHIPPING RELEASE NOTE | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | DW | TRUE | 2024-12-20 | RHL-001293838 | EA |  | 09970H60-D201-FD-846 |  | Metering and Protection Key Diagram (E-House) | [19 empty] | 2025-01-22
HPS | PRJ | FA | FALSE |  |  |  |  | 09970H60-D201-FA-012 |  | KOM int SHELL E-Heater | 01 | IFD | 2024-06-12 | [16 empty] | 2025-01-22
HPS | PRJ | FA | FALSE |  |  |  |  | 09970H60-D201-FA-101 |  | Master Document List - Internal HPS | 00 | IEE | 2024-07-12 | [16 empty] | 2025-01-22
HPS | PRJ | FS | FALSE | 2025-04-11 |  |  |  | 09970H60-D201-FS-910 |  | List of Spare Parts for Commissioning | [19 empty] | 2025-01-22
HPS | PRJ | FS | FALSE | 2025-04-11 |  |  |  | 09970H60-D201-FS-911 |  | List of Spare Parts for 2 Years Operation | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | LST | TRUE | 2024-12-16 | RHL-001293860 | EA |  | 09970H60-D201-FD-882 |  | I/O List for PCP and Transformer Operation, Monitoring and Alarm signals - E-House | 00 | IEE | 2023-12-22 | [16 empty] | 2025-01-22
HPS | PRJ | LST | FALSE |  |  |  |  | 09970H60-D201-FS-001 |  | Equipment List | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | TRUE | 2025-01-18 | RHL-001293842 | EA |  | 09970H60-D201-FD-853 |  | Fire Alarm - Sensors Layout (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | ELE | OM | TRUE |  | RHL-001294003 | EA |  | 09970H60-D201-FD-885 |  | Maintenance Contract (E-House) | [19 empty] | 2025-01-22
HPS | PRJ | MTR | FALSE | 2024-09-25 |  |  |  | 099H70-60-D201-FS-501 |  | Lining Specification (Engineering & Materails Supply) | 00 | IFI | 2024-09-25 | [16 empty] | 2025-01-22
HPS | PRJ | PR | FALSE |  |  |  |  | 09970H60-D201-FA-008 |  | 3D Procedure | 01 | IFD | 2024-10-14 | [16 empty] | 2025-01-22
HPS | PRJ | PR | FALSE |  |  |  |  | 09970H60-D201-FQ-106 |  | Documents Control Procedure for SCHNEIDER | 00 | IFD | 2024-12-20 | [16 empty] | 2025-01-22
HPS | PRJ | SCH | FALSE | 2024-06-28 |  |  |  | 09970H60-D201-FA-005 |  | Project Organization Chart | 06 | IFD | 2024-12-11 | [16 empty] | 2025-01-22
HPS | PRJ | SCH | FALSE |  |  |  |  | 09970H60-D201-FA-006 |  | Documents Control Procedure for Suppliers | 02 | IFD | 2024-09-19 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PH | TRUE | 2025-02-11 | RHL-001293853 | EA |  | 09970H60-D201-FD-872 |  | Earthing Philosophy and Typicals (E-House) | 00 | IEE | 2024-01-07 | [16 empty] | 2025-01-22
KANTHAL | PRJ | FE | FALSE |  |  |  |  | 09970H60-D201-FE-202 | MALGO | Heating Elements - Manufacturing planning | 01 | IFR | 2024-10-07 | [16 empty] | 2025-01-22
BARTEC | QC | CER | FALSE |  |  |  |  | 09970H60-D201-FQ-8000 |  | Terminal Boxes - ESI Junction box certificate | 00 | IFD | 2024-12-10 | [8 empty] | VEP 0007 | 2024-11-28 | 2024-12-08 | SCH-HPS-TN-0004 | 2024-12-02 | HPS-SCH-TN-0028 | 2025-01-09 | D – For Information | 2025-01-22 |  |  |  |  | -33
BARTEC | QC | CER | FALSE |  |  |  |  | 09970H60-D201-FQ-8001 |  | Terminal Boxes - Terminal Certificate | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
BARTEC | QC | CER | FALSE |  |  |  |  | 09970H60-D201-FQ-8002 |  | Terminal Boxes - Sealing fitting certificate ((bushing & Riegler removable double threaded nipple) | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
BARTEC | QC | CER | FALSE |  |  |  |  | 09970H60-D201-FQ-8003 |  | Terminal Boxes - Cable glands certificate | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
BARTEC | QC | CER | FALSE |  |  |  |  | 09970H60-D201-FQ-8005 |  | Terminal Boxes - VDE Certificate Cable | 00 | IFD | 2024-12-10 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | PH | TRUE | 2025-05-20 | RHL-001293871 | EA |  | 09970H60-D201-FS-867 | to send for Information | Electrical Operation Philosophy | 00 | IEE | 2024-01-12 | [16 empty] | 2025-01-22
SE - SCHNEIDER | ELE | SPE | TRUE |  | RHL-001293818 | EA |  | 09970H60-D201-FE-717 |  | E-House - Safety Signs Technical Specification & Map | [19 empty] | 2025-01-22
BETA | FAB | FE | TRUE |  | RHL-001293780 |  |  | 09970H60-D201-FE-3047 | Rev_00 - Internal | SELF-CLOSING SAFETY GATE | 01 | IFD | [17 empty] | 2025-01-22
HPS | QC | PR | FALSE |  |  |  |  | 09970H60-D201-FS-102 |  | Technical Requisition for ATEX Certification | 04 | IFO | 2024-08-09 | [8 empty] | VEP 0010 | 2024-12-05 | 2024-12-15 | SCH-HPS-TN-0005 | 2024-12-05 |  |  |  | 2025-01-22 |  |  |  |  | -28
SE - SCHNEIDER | QC | PR | FALSE | 2025-07-10 | RHL-001293963 |  |  | 09970H60-D201-FQ-864 |  | CE - Declaration of conformity (E-House) | [11 empty] | VEP 0016 | 2024-12-18 | 2024-12-28 | SCH-HPS-TN-0008 | 2024-12-18 | HPS-SCH-TN-0031 | 2025-01-13 | B – Reviewed With Comments | 2025-01-22 | 2 |  |  | 2025-01-23
DISTRISOL | REF | BOM | FALSE | 2024-11-25 |  |  |  | 09970H60-D201-FE-501 | SAMI + JN | Refractory - Bill of Material | 00 | IFD | 2024-11-28 | [8 empty] | VEP 0006 | 2024-11-28 | 2024-12-08 | SCH-HPS-TN-0004 | 2024-12-02 | HPS-SCH-TN-0020 | 2024-12-12 | D – For Information | 2025-01-22 |  |  |  |  | -33
DISTRISOL | REF | CER | FALSE | 2025-01-20 |  |  |  | 09970H60-D201-FQ-501 | CP | Refractory - Certificate 3.1 - UNIFRAX | [11 empty] | VEP 0006 | 2024-11-28 | 2024-12-08 | SCH-HPS-TN-0004 | 2024-12-02 | HPS-SCH-TN-0019 | 2024-12-12 | D – For Information | 2025-01-22 |  |  |  |  | -33
DISTRISOL | REF | CER | FALSE | 2025-01-20 |  |  |  | 09970H60-D201-FQ-502 |  | Refractory - Certificate 3.1 - ANCHORING | 00 | IFD | 2025-01-02 | [16 empty] | 2025-01-22
DISTRISOL | REF | CER | FALSE | 2025-01-20 |  |  |  | 09970H60-D201-FQ-503 |  | Refractory - Certificate 3.1 - BEAD | 00 | IFD | [9 empty] | VEP 0004 | 2024-11-05 | 2024-11-15 |  |  | HPS-SCH-TN-0017 | 2024-12-04 | D – For Information | 2025-01-22 |  |  |  |  | -49
DISTRISOL | REF | CER | FALSE | 2025-01-07 |  |  |  | 09970H60-D201-FQ-505 | MALGO + PC | Refractory - Certificate of Origin Issued by Camber of Commerce | 00 | IFD | [9 empty] | VEP 0004 | 2024-11-05 | 2024-11-15 |  |  | HPS-SCH-TN-0017 | 2024-12-04 | D – For Information | 2025-01-22 |  |  |  |  | -49
BETA | FAB | FQ | TRUE |  | RHL-001293999 |  |  | 09970H60-D201-FQ-3023 |  | Steel Structe - Inspection & Tests Plan | 02 | IFD | 2024-11-18 | HPS-SHE-TN-0132 | 2024-12-09 | 2024-12-22 | SHE-HPS-TN-0132 | 2024-12-12 | D - for Information Only | [10 empty] | 2025-01-22
DISTRISOL | REF | DW | FALSE | 2024-11-25 |  |  |  | 09970H60-D201-FE-503 | SAMI+JN | Refractory - Drawings | 00 | IFD | 2024-12-02 | [11 empty] | HPS-SCH-TN-0034 | 2025-01-16 | HPS-SCH-TN-0034 | 2025-01-16 | C – Rejected | 2025-01-22 | 3 |  |  | 2025-01-26
DISTRISOL | REF | FQ | FALSE |  |  |  |  | 09970H60-D201-FQ-506 |  | Refractory - Positive Material IDentification | [11 empty] | VEP 0019 | 2025-01-06 | 2025-01-16 | HPS-SCH-TN-0034 | 2025-01-16 | HPS-SCH-TN-0034 | 2025-01-16 | C – Rejected | 2025-01-22 | 3 |  |  | 2025-01-26
DISTRISOL | REF | IOM | FALSE | 2024-11-25 |  |  |  | 09970H60-D201-FE-504 | RAKIF | Refractory - Installation & Operation Manual | [19 empty] | 2025-01-22
HPS | HSE | PR | TRUE |  | RHL-001293767 | HX | HX5701 | 09970H60-D201-FS-906 |  | HSSE PLAN (EPF Engineering, Procurement, Fabrication in Workshop) | 00 | IFD | 2024-08-05 | [16 empty] | 2025-01-22
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-501 | confidential | Heater casing temp mapping | 00 | IEE | 2024-02-05 | [16 empty] | 2025-01-22
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-801 | confidential | Heating Element Layout Z1/Z2 | 00 | IFR | 2024-06-21 | [8 empty] | VEP 0019 | 2025-01-06 | 2025-01-16 | HPS-SCH-TN-0034 | 2025-01-16 | HPS-SCH-TN-0034 | 2025-01-16 | C – Rejected | 2025-01-22 | 3 |  |  | 2025-01-26
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-802 | confidential | Heating Elements Layout Z3-Z4 | 00 | IFR | 2024-06-21 | [8 empty] | VEP 0009 | 2024-12-05 | 2024-12-15 |  |  | HPS-SCH-TN-0021 | 2024-12-16 | C – Rejected | 2025-01-22 | -20 |  |  | 2024-12-26
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-850 | confidential | Electrical Terminal Box (Welder Connection) | 02 | IFD | 2024-12-18 | [8 empty] | VEP 0017 | 2024-12-17 | 2024-12-27 | SCH-HPS-TN-0010 | 2024-12-18 |  |  |  | 2025-01-22 |  |  |  |  | -19
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-851 | confidential | Electrical Terminal Box (Screwed Connection) | 00 | IFO | 2024-03-18 | [16 empty] | 2025-01-22
HPS | STR | CONF | FALSE |  |  |  |  | 09970H60-D201-FK-860 |  | Observation Door | 00 | IFD | 2024-12-14 | [16 empty] | 2025-01-22
AGEX | INS | DW | TRUE | 2024-09-06 | RHL-001293891 | IN | IN0901 | 09970H60-D201-FD-813 |  | Instrumentation Interconnection Diagram | 02 | IFD | 2024-09-06 | HPS-SHE-TN-0065 | 2024-09-10 | 2024-09-23 | SHE-HPS-TN-0065 | 2024-10-01 | B - Proceed Change as Noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-10-11 | -74
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FD-010 |  | CANCELED - General assembly - General data (E-Heater) |  | CAN | [17 empty] | 2025-01-22
HPS | INS | DS | TRUE | 2024-09-30 | RHL-001293906 | IN | IN2105 | 09970H60-D201-FS-813 |  | Pressure & DP Flow Transmitters - Specification | 00 | IFD | 2024-09-27 | [5 empty] | B - Proceed Change as Noted & Resubmit | [10 empty] | 2025-01-22
HPS | INSP | FQ | TRUE |  | RHL-001293916 | BA | BA7880 | 09970H60-D201-FQ-002 |  | SOI - Steel Structure | 01 | IFD | 2024-11-22 | HPS-SHE-TN-0121 | 2024-11-25 | 2024-12-08 | SHE-HPS-TN-0121 | 2024-12-05 | A - Proceed | [10 empty] | 2025-01-22
HPS | INSP | FQ | TRUE |  | RHL-001293917 | BA | BA7880 | 09970H60-D201-FQ-003 |  | SOI – Fan | 00 | IFD | 2024-10-09 | HPS-SHE-TN-0077 | 2024-10-09 | 2024-10-22 | SHE-HPS-TN-0077 | 2024-10-29 | A - Proceed | [10 empty] | 2025-01-22
HPS | INSP | FQ | TRUE |  | RHL-001293918 | BA | BA7880 | 09970H60-D201-FQ-004 |  | SOI – Instrumentation | [19 empty] | 2025-01-22
HPS | INSP | FQ | TRUE |  | RHL-001293919 | BA | BA7880 | 09970H60-D201-FQ-005 |  | SOI – E-House | [19 empty] | 2025-01-22
HPS | INSP | FQ | TRUE |  | RHL-001293925 | BA | BA7880 | 09970H60-D201-FQ-007 |  | SOI – Site coils welding and NDE (Non destructive examination) | [19 empty] | 2025-01-22
TUBACEX - TTA | INSP | FQ | TRUE |  | RHL-001293995 | QA | QA5733 | 09970H60-D201-FQ-101 | ITP10336 | Seamless Fittings - Inspection & Test Plan | 01 | IFD | 2024-10-21 | [11 empty] | SHE-HPS-TN-0034 | 2024-10-30 |  |  |  | 2025-01-22
HPS | MEC | DW | TRUE |  | RHL-001293949 | MS |  | 09970H60-D201-FD-901 | BETA + Florian IONITA + Florian TOUBLANC | Coil Packing ??????? | [19 empty] | 2025-01-22
HPS | PCS | CEC | TRUE | 2024-10-11 | RHL-001293766 | PX | PX2310 | 09970H60-D201-FJ-862 |  | PLC - Cause and effect chart | 00 | IEE | 2024-02-20 | [8 empty] | TN-0002 | 2025-01-08 | 2025-01-18 | ICA-HPS-TN-0002 | 2025-01-08 | HPS-ICA-TN-0002 | 2025-01-09 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | LST | TRUE | 2024-12-25 | RHL-001293938 | PX | PX4322 | 09970H60-D201-FJ-802 |  | Utility Consumption List (including instrument air) | 01 | IEE | 2024-02-08 | [8 empty] | TN-0008 | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0015 | 2024-12-30 | HPS-KAN-TN-0011 | 2025-01-02 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | LST | TRUE | 2024-12-13 | RHL-001293939 | PX | PX4322 | 09970H60-D201-FJ-804 |  | Effluent List | 01 | IEE | 2024-02-08 | [8 empty] | TN-0008 | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0015 | 2024-12-30 | HPS-KAN-TN-0011 | 2025-01-02 | A – Reviewed Without Comment | 2025-01-22
HPS | PCS | LST | TRUE |  | RHL-001293765 | PX |  | 09970H60-D201-FS-808 |  | Drain and Vent and Relief Requirements (if any) | 00 | IEE | 2023-12-22 | [8 empty] | TN-0003 | 2024-10-02 | 2024-10-12 | KAN-HPS-TN-0005 | 2024-10-03 | HPS-KAN-TN-0005 | 2024-10-03 | A – Reviewed Without Comment | 2025-01-22
HPS | STR | DW | FALSE | 2024-07-24 |  |  |  | 09970H60-D201-FD-3XX |  | CANCELED - Structural drawings |  | CAN | [17 empty] | 2025-01-22
HPS | PCS | OM | TRUE | 2024-02-17 | RHL-001293943 | PX | PX4814 | 09970H60-D201-FJ-901 |  | OMM (Operating & Maintenance Manual) (E-Heater) | [11 empty] | TN-0006 | 2024-11-14 | 2024-11-24 | KAN-HPS-TN-0011 | 2024-11-14 |  |  |  | 2025-01-22 |  |  |  |  | -43
HPS | PCS | PD | TRUE | 2025-01-21 | RHL-001293942 | PX | PX8248 | 09970H60-D201-FJ-863 |  | CFD Study & Thermal Analysis | [11 empty] | TN-0008 | 2024-12-20 | 2024-12-30 | KAN-HPS-TN-0015 | 2024-12-30 |  |  |  | 2025-01-22 |  |  |  |  | -18
HPS | PCS | PDS | TRUE | 2024-06-03 | RHL-001293945 | PX | PX2105 | 09970H60-D201-FS-801 |  | Heating Elements - Process Datasheet | 02 | IEE | 2023-12-15 | [8 empty] | TN-0008 | 2024-12-10 | 2024-12-20 | KAN-HPS-TN-0013 | 2024-12-11 |  |  |  | 2025-01-22 |  |  |  |  | -24
HPS | PCS | PID | TRUE | 2025-01-16 | RHL-001293935 | PX | PX2366 | 09970H60-D201-FD-801 |  | P&ID - Radiant Electrical Heater DD-201 | 07 | IFD | 2024-09-25 | HPS-SHE-TN-0068 | 2024-09-26 | 2024-10-09 | SHE-HPS-TN-0066 | 2024-10-08 | B - Proceed Change as Noted & Resubmit |  |  | TN-0004 | 2024-10-07 | 2024-10-17 | KAN-HPS-TN-0007 | 2024-10-08 |  |  |  | 2025-01-22 |  | 2024-10-18 | -69 |  | -70
HPS | PCS | PR | TRUE | 2025-03-04 | RHL-001293944 | PX | PX6180 | 09970H60-D201-FJ-902 |  | Performance test procedure | [19 empty] | 2025-01-22
HPS | PIP | CHL | TRUE |  | RHL-001293764 | MP | MP4363 | 09970H60-D201-FS-4003 |  | TIE-INS & Nozzle table with Allowable Nozzle Loads | 00 | IEE | 2024-01-25 | [8 empty] | VEP 0018 | 2024-12-19 | 2024-12-29 | SCH-HPS-TN-0011 | 2024-12-30 | HPS-SCH-TN-0033 | 2025-01-13 | C – Rejected | 2025-01-22 | 2 |  |  | 2025-01-23
HPS | PRJ | FA | TRUE |  | RHL-001293951 | AA | AA4322 | 09970H60-D201-FA-002 |  | Vendors list | [19 empty] | 2025-01-22
HPS | PRJ | LST | TRUE |  | RHL-001293954 | AA | AA4322 | 09970H60-D201-FR-001 |  | Packing List | [19 empty] | 2025-01-22
HPS | PRJ | MR | TRUE |  | RHL-001294002 | AA | AA0709 | 09970H60-D201-FA-003 |  | Risk Analysis | 01 | IEE | 2024-03-04 | [16 empty] | 2025-01-22
HPS | QC | PR | TRUE |  | RHL-001293962 | QA | QA6180 | 09970H60-D201-FQ-008 |  | CE - Declaration of Conformity & Instruction for Use (for Coil) | [11 empty] | VEP 0010 | 2024-12-05 | 2024-12-15 | SCH-HPS-TN-0005 | 2024-12-05 | HPS-SCH-TN-0027 | 2025-01-08 | A – Reviewed Without Comment | 2025-01-22
DISTRISOL | REF | DS | TRUE | 2024-11-25 | RHL-001294001 |  |  | 09970H60-D201-FE-502 | RD | Refractory - Material Safety DataSheet | 00 | IFD | 2024-12-11 | [16 empty] | 2025-01-22
DISTRISOL | REF | ITP | TRUE | 2024-11-25 | RHL-001293769 |  |  | 09970H60-D201-FQ-504 |  | Refractory - Inspection & Test Plan | 00 | IFD | 2024-11-28 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE | 2024-07-26 | RHL-001293969 | CX |  | 09970H60-D201-FD-001 |  | Foundation Layout Drawing & Base Plate Details Drawing ( E-Heater ) | 04 | IFD | 2024-10-17 | HPS-SHE-TN-0081 | 2024-10-21 | 2024-11-03 | SHE-HPS-TN-0081 | 2024-11-13 | B - Proceed Change as Noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-23 | -43
HPS | STR | DW | TRUE | 2024-08-09 | RHL-001293972 | CS |  | 09970H60-D201-FD-301 |  | General Notes - Steel Structure | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-29 | A - Proceed | [10 empty] | 2025-01-22
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-502 |  | Fibrothal Layout | 00 | IFD | 2024-06-21 | [16 empty] | 2025-01-22
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-503 |  | Ceramic Isolators | 02 | IFD | 2025-01-13 | [16 empty] | 2025-01-22
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-803 |  | Heating Elements Layout Observation doors | 00 | IFD | 2024-06-21 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE | 2024-10-11 | RHL-001293973 | CS |  | 09970H60-D201-FD-310 |  | Electrical Radiant Tubular Heater - SFMOD 1 Steel Structure | 03 | IFD | 2024-11-22 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293974 | CS |  | 09970H60-D201-FD-311 |  | Electrical Radiant Tubular Heater - SFMOD 2 Steel Structure | 02 | IFD | 2024-11-22 | [8 empty] | Mail | 2025-01-05 | 2025-01-15 |  |  | HPS-SIS-TN-0002 | 2025-01-14 | D – For Information | 2025-01-22 |  |  |  |  | -6
HPS | STR | RE | FALSE |  |  |  |  | 09970H60-D201-FS-300 |  | SWFU (Steel Weight Follow-Up) - Basic design | 05 | IEE | 2023-11-29 | [8 empty] | TN-0003 | 2025-01-15 | 2025-01-25 | TEC-HPS-TN-0003 | 2025-01-15 |  |  |  | 2025-01-22 |  |  |  |  | 3
HPS | STR | DW | TRUE |  | RHL-001293975 | CS |  | 09970H60-D201-FD-312 |  | Electrical Radiant Tubular Heater - SFMOD 3 Steel Structure | 02 | IFD | 2024-11-22 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293976 | CS |  | 09970H60-D201-FD-313 |  | Electrical Radiant Tubular Heater - SFMOD 4 Steel Structure | 02 | IFD | 2024-11-22 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293977 | CS |  | 09970H60-D201-FD-314 |  | Electrical Radiant Tubular Heater - SFMOD 5 Steel Structure | 03 | IFD | 2024-11-22 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE | 2024-08-09 | RHL-001293978 | CS |  | 09970H60-D201-FD-360 |  | Platforms Access & Handrail - Typical Details | 00 | IFD | 2024-08-14 | HPS-SHE-TN-0115 | 2024-11-12 | 2024-11-25 | SHE-HPS-TN-0115 | 2024-11-25 | A - Proceed | [10 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293979 | CS |  | 09970H60-D201-FD-361 |  | Electrical Radiant Tubular Heater - Platforms EL.+1589 | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-30 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-09 | -53
SE - SCHNEIDER | STR | FC | FALSE | 2025-01-06 | RHL-001293966 |  |  | 09970H60-D201-FC-002 | PO+20w | Foundation Load Calculation Note ( E-House ) | 00 | IEE | 2024-02-22 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293980 | CS |  | 09970H60-D201-FD-362 |  | Electrical Radiant Tubular Heater - Platforms EL.+6551 | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-29 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-08 | -54
HPS | STR | DW | TRUE |  | RHL-001293981 | CS |  | 09970H60-D201-FD-363 |  | Electrical Radiant Tubular Heater - Platforms EL.+11513 | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-29 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-08 | -54
HPS | STR | DW | TRUE |  | RHL-001293982 | CS |  | 09970H60-D201-FD-364 |  | Electrical Radiant Tubular Heater - Platforms EL.+14430 | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-29 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-08 | -54
BETA | SUP | LST | FALSE |  |  |  |  | 09970H60-D201-FE-3008 | Rev_00 - Internal | PACKINKS LIST | [11 empty] | TN-0003 | 2025-01-15 | 2025-01-25 | TEC-HPS-TN-0003 | 2025-01-15 |  |  |  | 2025-01-22 |  |  |  |  | 3
DISTRISOL | SUP | LST | FALSE | 2025-01-21 |  |  |  | 09970H60-D201-FE-505 | MALGP | Refractory - Packing List | [11 empty] | TN-0001 | 2024-10-07 | 2024-10-17 | TEC-HPS-TN-0001 | 2024-10-08 | HPS-TEC-TN-0002 | 2024-10-10 | A – Reviewed Without Comment | 2025-01-22
KANTHAL | SUP | LST | FALSE |  |  |  |  | 09970H60-D201-FE-207 | MALGO | Heating Elements - Shipping & Packing list | [11 empty] | TN-0001 | 2024-10-07 | 2024-10-17 | TEC-HPS-TN-0001 | 2024-10-08 | HPS-TEC-TN-0002 | 2024-10-10 | A – Reviewed Without Comment | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-03-25 |  |  |  | 09970H60-D201-FD-855 |  | LV Switchboard - Packing List (E-House) | [11 empty] | TN-0001 | 2024-10-07 | 2024-10-17 | TEC-HPS-TN-0001 | 2024-10-08 | HPS-TEC-TN-0002 | 2024-10-10 | A – Reviewed Without Comment | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-03-28 |  |  |  | 09970H60-D201-FD-859 |  | MV/LV Transformer - Packing List (E-House) | [11 empty] | TN-0001 | 2024-10-18 | 2024-10-28 | TUB_TTA-HPS-TN-0001 | 2024-10-21 | HPS-TUB_TTA-TN-0002 | 2024-11-04 | B – Reviewed With Comments | 2025-01-22 | -50 |  |  | 2024-11-14
SE - SCHNEIDER | SUP | LST | FALSE | 2025-07-16 |  |  |  | 09970H60-D201-FD-861 |  | Packing List (E-House) | [11 empty] | Mail | 2024-12-04 | 2024-12-14 | [5 empty] | 2025-01-22 |  |  |  |  | -28
SE - SCHNEIDER | SUP | LST | FALSE | 2025-05-16 | RHL-001293848 |  |  | 09970H60-D201-FD-866 | to send for Information | LV Busduct packing list (E-House) | [11 empty] | Mail | 2024-12-03 | 2024-12-13 | VIO-HPS-TN-0001 | 2024-12-04 | HPS-VIO-TN-0001 | 2025-01-02 | B – Reviewed With Comments | 2025-01-22 | -8 |  |  | 2025-01-12
SE - SCHNEIDER | SUP | LST | FALSE | 2025-07-01 | RHL-001293921 |  |  | 09970H60-D201-FQ-866 | to send for Information | MV/LV Transformer - Packing List (E-House) | [11 empty] | Mail | 2024-12-03 | 2024-12-13 | VIO-HPS-TN-0001 | 2024-12-04 | HPS-VIO-TN-0002 | 2025-01-02 | B – Reviewed With Comments | 2025-01-22 | -8 |  |  | 2025-01-12
HPS | STR | DW | TRUE | 2024-10-11 | RHL-001293983 | CS |  | 09970H60-D201-FD-365 |  | Electrical Radiant Tubular Heater - Stair Case | 00 | IFD | 2024-08-02 | HPS-SHE-TN-0054 | 2024-08-06 | 2024-08-19 | SHE-HPS-TN-0054 | 2024-10-29 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-11-08 | -54
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FD-3XX |  | CANCELED - Structural drawings |  | CAN | [17 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293955 | CS |  | 09970H60-D201-FD-915 | BETA + Florian IONITA + Florian TOUBLANC | COIL - Packing Arrangement | 01 | IFD | 2024-12-12 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293956 | CS |  | 09970H60-D201-FD-916 | send For Info - BETA + IONITA + TOUBLANC | COIL - Lifting Arrangement | [19 empty] | 2025-01-22
HPS | STR | DW | TRUE | 2024-07-19 | RHL-001293987 | CS |  | 09970H60-D201-FK-001 |  | E-Heater General Assembly Drawing | 04 | IFD | 2024-09-20 | HPS-SHE-TN-0116 | 2024-11-12 | 2024-11-25 | SHE-HPS-TN-0116 | 2024-11-25 | A - Proceed | [10 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293989 | CX |  | 09970H60-D201-FK-003 | non diffusé | Control Zones & Terminals Boxes Layout Electrical Radiant Tubular Heater | 00 | IEE | 2023-12-01 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293990 | CS |  | 09970H60-D201-FK-004 |  | Visibility Study Electrical Radiant Tubular Heater | 00 | IEE | 2023-12-01 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE | 2024-10-04 | RHL-001293991 | CX |  | 09970H60-D201-FK-005 |  | E-Heater GAD - Skin thermocouples layout | 01 | IFD | 2024-08-12 | HPS-SHE-TN-0077 | 2024-10-09 | 2024-10-22 | SHE-HPS-TN-0077 | 2024-11-29 | B - Proceed Change as Noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-12-09 | -33
HPS | STR | FC | TRUE | 2024-07-22 | RHL-001293965 | CS |  | 09970H60-D201-FC-001 |  | Foundation Load & Base Plate Calculation Note ( E-Heater ) | 04 | IFD | 2024-10-16 | HPS-SHE-TN-0092 | 2024-10-22 | 2024-11-04 | SHE-HPS-TN-0092 | 2024-11-13 | A - Proceed |  |  | TN-0003 | 2025-01-15 | 2025-01-25 | TEC-HPS-TN-0003 | 2025-01-15 |  |  |  | 2025-01-22 |  |  |  |  | 3
HPS | STR | FC | TRUE | 2024-07-31 | RHL-001293967 | CS |  | 09970H60-D201-FC-301 |  | STRUCTURAL STEEL ( + platforms, stairs and ladders) Design calculation note (E-Heater) | 04 | IFD | 2025-01-06 | HPS-SHE-TN-0166 | 2025-01-06 | 2025-01-19 | SHE-HPS-TN-0166 | 2025-01-09 | A - Proceed |  |  | TN-0003 | 2025-01-15 | 2025-01-25 | TEC-HPS-TN-0003 | 2025-01-15 |  |  |  | 2025-01-22 |  |  |  |  | 3
HPS | STR | SPE | TRUE | 2024-06-07 | RHL-001293993 | CS |  | 09970H60-D201-FS-003 |  | Structural Design brief | 00 | IFD | 2024-06-21 | HPS-SHE-TN-0044 | 2024-06-21 | 2024-07-04 | SHE-HPS-TN-0044 | 2024-10-07 | B - Proceed Change as Noted & Resubmit |  |  | TN-0001 | 2024-10-07 | 2024-10-17 | SHE-HPS-TN-0046 | 2024-10-30 |  |  |  | 2025-01-22 |  | 2024-10-17 | -70 |  | -70
SE - SCHNEIDER | STR | DW | TRUE | 2025-01-06 | RHL-001293970 | CX |  | 09970H60-D201-FD-002 | PO+20 | Foundation Layout Drawing & Base Plate Details Drawing ( E-House ) | 01 | IFD | 2024-12-20 | HPS-SHE-TN-0171 | 2025-01-13 | 2025-01-26 | SHE-HPS-TN-0171 | 2025-01-16 | C - Do not Proceed change as noted & Resubmit |  |  | TN-0001 | 2024-10-07 | 2024-10-17 | TEC-HPS-TN-0001 | 2024-10-08 | HPS-TEC-TN-0003 | 2024-12-30 | A – Reviewed Without Comment | 2025-01-22 |  | 2025-01-26 | 3
SE - SCHNEIDER | STR | DW | TRUE | 2025-01-29 | RHL-001293985 | CS |  | 09970H60-D201-FD-852 |  | Structural Steel Drawings (Detailed Eng.) (E-house) | 00 | IFD | 2025-01-06 | HPS-SHE-TN-0172 | 2025-01-13 | 2025-01-26 | SHE-HPS-TN-0172 | 2025-01-16 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2025-01-26 | 3
SE - SCHNEIDER | STR | DW | TRUE | 2025-02-17 | RHL-001293994 | CS |  | 09970H60-D201-FD-863 |  | Structural Steel Drawings (Fabrication) (E-house) | [11 empty] | TN-0003 | 2025-01-15 | 2025-01-25 | TEC-HPS-TN-0003 | 2025-01-15 |  |  |  | 2025-01-22 |  |  |  |  | 3
SE - SCHNEIDER | STR | DW | TRUE | 2025-02-24 | RHL-001293986 | CS |  | 09970H60-D201-FD-864 |  | Buildings & Platforms details (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | STR | FC | TRUE | 2025-01-29 | RHL-001293968 | CS |  | 09970H60-D201-FC-302 | Merged With FC-302 | Structural steel, Lifting lugs and Foundation Load calculation note (E-House) | 00 | IFD | 2025-01-06 | HPS-SHE-TN-0173 | 2025-01-13 | 2025-01-26 | SHE-HPS-TN-0173 | 2025-01-16 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2025-01-26 | 3
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-502 |  | Fibrothal Layout | 00 | IFD | 2024-06-21 | [16 empty] | 2025-01-22
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-503 |  | Ceramic Isolators | 02 | IFD | 2025-01-13 | [16 empty] | 2025-01-22
HPS | STR | DW | FALSE |  |  |  |  | 09970H60-D201-FK-803 |  | Heating Elements Layout Observation doors | 00 | IFD | 2024-06-21 | [16 empty] | 2025-01-22
SE - SCHNEIDER | STR | GAD | TRUE | 2024-12-27 | RHL-001293855 | CX | CX4018 | 09970H60-D201-FD-874 |  | E-House - Layout and General Arrangement | 03 | IFD | 2024-12-03 | HPS-SHE-TN-0129 | 2024-12-05 | 2024-12-18 | SHE-HPS-TN-0129 | 2024-12-12 | C - Do not Proceed change as noted & Resubmit | [10 empty] | 2025-01-22 |  | 2024-12-22 | -23
SE - SCHNEIDER | STR | OM | TRUE | 2025-06-15 | RHL-001293847 | CS |  | 09970H60-D201-FD-865 | to send for Information | Lifting and Transport Manual - Lifting Plan (E-House) | 01 | IFD | 2024-12-18 | [16 empty] | 2025-01-22
HPS | STR | RE | FALSE |  |  |  |  | 09970H60-D201-FS-300 |  | SWFU (Steel Weight Follow-Up) - Basic design | 05 | IEE | 2023-11-29 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293955 |  |  | 09970H60-D201-FD-915 | BETA + Florian IONITA + Florian TOUBLANC | COIL - Packing Arrangement | 01 | IFD | 2024-12-12 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293956 |  |  | 09970H60-D201-FD-916 | BETA + Florian IONITA + Florian TOUBLANC | COIL - Lifting Arrangement | [19 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293989 |  |  | 09970H60-D201-FK-003 | non diffusé | Control Zones & Terminals Boxes Layout Electrical Radiant Tubular Heater | 00 | IEE | 2023-12-01 | [16 empty] | 2025-01-22
HPS | STR | DW | TRUE |  | RHL-001293990 |  |  | 09970H60-D201-FK-004 |  | Visibility Study Electrical Radiant Tubular Heater | 00 | IEE | 2023-12-01 | [16 empty] | 2025-01-22
HPS | STR | FC | TRUE | 2024-07-31 | RHL-001293967 |  |  | 09970H60-D201-FC-301 |  | STRUCTURAL STEEL ( + platforms, stairs and ladders) Design calculation note (E-Heater) | 04 | IFD | 2025-01-06 | HPS-SHE-TN-0166 | 2025-01-06 | 2025-01-19 | SHE-HPS-TN-0166 | 2025-01-09 | A - Proceed | [10 empty] | 2025-01-22
SE - SCHNEIDER | STR | DW | TRUE | 2025-02-17 | RHL-001293994 |  |  | 09970H60-D201-FD-863 |  | Structural Steel Drawings (Fabrication) (E-house) | [19 empty] | 2025-01-22
SE - SCHNEIDER | STR | DW | TRUE | 2025-02-24 | RHL-001293986 |  |  | 09970H60-D201-FD-864 |  | Buildings & Platforms details (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | STR | FC | TRUE | 2025-01-06 | RHL-001293966 |  |  | 09970H60-D201-FC-002 | PO+20w | Foundation Load Calculation Note ( E-House ) | 00 | IEE | 2024-02-22 | [16 empty] | 2025-01-22
SE - SCHNEIDER | STR | OM | TRUE | 2025-06-15 | RHL-001293847 |  |  | 09970H60-D201-FD-865 | to send for Information | Lifting and Transport Manual - Lifting Plan (E-House) | 01 | IFD | 2024-12-18 | [8 empty] | VEP 0017 | 2024-12-17 | 2024-12-27 | SCH-HPS-TN-0010 | 2024-12-18 |  |  |  | 2025-01-22 |  |  |  |  | -19
SHELL | STR | DW | FALSE |  |  |  |  | 10-2000-SZ-0800002_BL01 |  | Nameplate | 00 |  | 2024-12-16 | [16 empty] | 2025-01-22
SHELL | STR | DW | FALSE |  |  |  |  | 240313 |  | Export_Staircase_incl_Heater | 00 |  | 2024-03-15 | [16 empty] | 2025-01-22
SHELL | STR | DW | FALSE |  |  |  |  | 240313 X |  | Export_Staircase_without_Heater | 00 |  | 2024-03-15 | [16 empty] | 2025-01-22
SHELL | STR | DW | FALSE |  |  |  |  | GR 16680 0153 |  | E-House General Arrangement Drawing (GAD) (for construction permit) (Contractual) | 00 |  | 2024-04-25 | [16 empty] | 2025-01-22
SHELL | STR | DW | FALSE |  |  |  |  | GR 16680 0154 |  | E-Heater General Arrangement Drawing (GAD) – Plan view (for construction permit) (Contractual) | 00 |  | 2024-04-25 | [16 empty] | 2025-01-22
SHELL | STR | DW | FALSE |  |  |  |  | GR 16680 0155 |  | E-Heater General Arrangement Drawing (GAD) – Elevation view (for construction permit) (Contractual) | 01 |  | 2024-04-25 | [16 empty] | 2025-01-22
SHELL | STR | PR | FALSE |  |  |  |  | 10-2000-RI-12002 |  | Structural standard (gratings, ladders, stairs, handrails, etc.) (Contractual) | 00 |  | 2024-03-04 | [16 empty] | 2025-01-22
SHELL | STR | PR | FALSE |  |  |  |  | ASR-A2-3 |  | Escape ways & Emergency exit | 00 |  | 2024-03-04 | [16 empty] | 2025-01-22
SHELL | STR | SPE | FALSE |  |  |  |  | DEP 30.00.60.20-Gen |  | DEP Human Factors design engineering – Workspace | 00 |  | 2023-02-08 | [16 empty] | 2025-01-22
SHELL | STR | SPE | FALSE |  |  |  |  | Site Data |  | Site data & Structural basis of design | 00 |  | 2023-10-09 | [16 empty] | 2025-01-22
BETA | SUP | LST | FALSE |  |  |  |  | 09970H60-D201-FE-3008 | Rev_00 - Internal | PACKINKS LIST | [19 empty] | 2025-01-22
DISTRISOL | SUP | LST | FALSE | 2025-01-21 |  |  |  | 09970H60-D201-FE-505 | MALGP | Refractory - Packing List | [19 empty] | 2025-01-22
KANTHAL | SUP | LST | FALSE |  |  |  |  | 09970H60-D201-FE-207 | MALGO | Heating Elements - Shipping & Packing list | [19 empty] | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-03-25 |  |  |  | 09970H60-D201-FD-855 |  | LV Switchboard - Packing List (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-03-28 |  |  |  | 09970H60-D201-FD-859 |  | MV/LV Transformer - Packing List (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-07-16 |  |  |  | 09970H60-D201-FD-861 |  | Packing List (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-05-16 | RHL-001293848 |  |  | 09970H60-D201-FD-866 | to send for Information | LV Busduct packing list (E-House) | [19 empty] | 2025-01-22
SE - SCHNEIDER | SUP | LST | FALSE | 2025-07-01 | RHL-001293921 |  |  | 09970H60-D201-FQ-866 | to send for Information | MV/LV Transformer - Packing List (E-House) | [19 empty] | 2025-01-22
Formulas:
SHELL Due Date = IF(ISBLANK([HPS - SHELL TRS Date]),"",[HPS - SHELL TRS Date]+13)
SHELL Time limit or Delay = IFERROR(IF(OR(ISBLANK([SHELL TRS N°]),AND(ISNUMBER([HPS - SHELL Time limit or Delay]),[HPS - SHELL Time limit or Delay]<>0)),"",IF(OR([Jean-Claude ROOSSENS]="A - Proceed",[Jean-Claude ROOSSENS]="C - Do not Proceed change as noted & Resubmit",[Jean-Claude ROOSSENS]="B - Proceed Change as Noted & Resubmit",[Jean-Claude ROOSSENS]="D - For Information Only"),"",NETWORKDAYS([Today],[SHELL Due Date]))),"")
HPS - Suppliers EXPECTED DATE = IF(ISBLANK([Supplier TRS Date]),"",[Supplier TRS Date]+10)
Suppliers -HPS Time limit or Delay = IF([HPS - Suppliers TRS N°]="","",IF(OR([HPS - Supplier Status]="A – Reviewed Without Comment",[HPS - Supplier Status]="D – For Information",[Status]="CAN"),"",IF(OR([HPS - Supplier Status]="B – Reviewed With Comments",[HPS - Supplier Status]="C – Rejected "),NETWORKDAYS([Today],[HPS - Supplier TRS Date]-(-10)),"")))
HPS - SHELL Time limit or Delay = IF(([Status]="CAN"),"",IF([SHELL TRS N°]="","",IF(OR([Jean-Claude ROOSSENS]="A - Proceed",[Jean-Claude ROOSSENS]="D - For Information Only"),"",IF(OR([Jean-Claude ROOSSENS]="B - Proceed Change as Noted & Resubmit",[Jean-Claude ROOSSENS]="C - Do not Proceed change as noted & Resubmit"),NETWORKDAYS([Today],[HPS PROPOSAL REF. :]-(-10))))))
HPS - Supplier Time limit or Delay = IFERROR(IF(OR(ISBLANK([HPS - Suppliers TRS N°]),AND(ISNUMBER([Suppliers -HPS Time limit or Delay]),[Suppliers -HPS Time limit or Delay]<>0)),"",IF(OR([HPS - Supplier Status]="A – Reviewed Without Comment",[HPS - Supplier Status]="B – Reviewed With Comments",[HPS - Supplier Status]="C - Rejected",[HPS - Supplier Status]="D - For information"),"",NETWORKDAYS([Today],[HPS - Suppliers EXPECTED DATE]))),"")

## Feuil2
JIAHUA II PROJECT - STATUS OF LATEST REVISION OF DOCUMENTS DISPATCHED TO CLIENT
2025-01-22
PROGRESS - ALL DOCUMENTS LATEST REVISION
WEEK | Total Documents MDL | Total Documents MDL - Due (livrable) | Total Dispatched Documents Latest Rev. | Total APPROVED Documents Latest Rev. | Total COMMENTED Documents Latest Rev. | Document to be Returned by Client | General Progress Docs. DUE APPROVED | General Progress Docs. LR APPROVED | General Progress Documents COMMENTED | General Progress Documents DUE - Client | GENERAL PROGRESS TOTAL
S46 | 369 | 179 | 84 | 10 | 21 | 53 | 5.587% | 11.9% | 25% | 63.1% | 100%
S47 | 376 | 166 | 71 | 13 | 25 | 33 | 7.831% | 18.31% | 35.21% | 46.48% | 100%
S48 | 403 | 170 | 72 | 12 | 23 | 37 | 7.059% | 16.67% | 31.94% | 51.39% | 100%
S49 | 403 | 147 | 71 | 12 | 22 | 37 | 8.163% | 16.9% | 30.99% | 52.11% | 100%
S01 | 414 | 168 | 99 | 14 | 23 | 62 | 8.333% | 14.14% | 23.23% | 62.63% | 100%
S02 | 492 | 169 | 103 | 15 | 21 | 67 | 8.876% | 14.56% | 20.39% | 65.05% | 100%
S03 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S04 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S05 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S06 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S07 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S08 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S09 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S10 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S11 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S12 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S13 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S14 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S15 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S16 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S17 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S18 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S19 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S20 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S21 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S22 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S23 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S24 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S25 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S26 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S27 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S28 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S29 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S30 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S31 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S32 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S33 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S34 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S35 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S36 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S37 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S38 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S39 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S40 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S41 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S42 | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Evolutions Documents Approuvés
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation =
|  |  |  | % ENGINEERING | (precedent ) - variation = |  |  | Calcul de Variation (%)
|  |  |  | Evolutions Documents Commentés |  |  |  | Valeur Initiale
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation = |  |  | Valeur Finale
|  |  |  | % ENGINEERING | (precedent ) - variation =
[8 empty] | Variation : |  | %
Documents chez le client / Mise à jour HPC
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation =

## PROGRESS (hidden)
JIAHUA II PROJECT - STATUS OF LATEST REVISION OF DOCUMENTS DISPATCHED TO CLIENT
2025-01-22
PROGRESS - ALL DOCUMENTS LATEST REVISION
WEEK | Total Documents MDL | Total Documents MDL - Due (livrable) | Total Dispatched Documents Latest Rev. | Total APPROVED Documents Latest Rev. | Total COMMENTED Documents Latest Rev. | Document to be Returned by Client | General Progress Docs. DUE APPROVED | General Progress Docs. LR APPROVED | General Progress Documents COMMENTED | General Progress Documents DUE - Client | GENERAL PROGRESS TOTAL
S37 | 184 | 96 | 28 | 0 | 0 | 28 | 0% | 0% | 0% | 100% | 100%
S42 | 209 | 98 | 54 | 11 | 12 | 31 | 11.22% | 20.37% | 22.22% | 57.41% | 100%
S43 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S44 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S45 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S46 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S47 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S48 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S49 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S50 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S51 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S52 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S53 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S54 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S55 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S56 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S57 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S58 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S59 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S60 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S61 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S62 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S63 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S64 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S65 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S66 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S67 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S68 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S69 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S70 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S71 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S72 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S73 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S74 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S75 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S76 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S77 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S78 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S79 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S80 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S81 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S82 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S83 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S84 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S85 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
S86 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Evolutions Documents Approuvés
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation =
|  |  |  | % ENGINEERING | (precedent ) - variation = |  |  | Calcul de Variation (%)
|  |  |  | Evolutions Documents Commentés |  |  |  | Valeur Initiale
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation = |  |  | Valeur Finale
|  |  |  | % ENGINEERING | (precedent ) - variation =
[8 empty] | Variation : |  | %
Documents chez le client / Mise à jour HPC
|  |  |  | % GENERAL | (precedent ) - variation =
|  |  |  | % SUPPLIERS | (precedent ) - variation =

## ValueList_Helper (hidden)
TPS | 3DCOLL
CALLIDUS | CONS
HPM | DCC
HPR | ELE
HPS | GEN
INTERNAL | HSE
CLIENT | INS
INSP
MEC
PCS
PIP
PL
PRJ
PVS
QC
STR
SUP
WSH