## Epics de la refonte (Jira)
Issue Type,Priority,Issue key,Issue id,Summary,Component/s,Component/s,Status,Assignee,Custom field (RÃ©alisÃ© par),Custom field (Story Points),Custom field (Story point rÃ©Ã©valuÃ©),Custom field (Epic Link),Reporter,Sprint,Sprint,Sprint,Sprint,Sprint,Created,Resolved,Custom field (Front/Back),Fix Version/s,Fix Version/s,Custom field (2eme dÃ©veloppeur),Updated,Custom field (Configuration ?)
New Feature,Medium,ETAM-9856,81862,Nettoyage CSS / Style Guide - Undiz ,*GlobalMarque,Demandware,To Do,baudicg,DoeJ,13.0,,ETAM-9632,tomasid,Sprint07.20-15/04-10,,,,,12/Mar/20 4:30 PM,12/Mar/20 7:19 PM,Front,,,DoeJ,12/Mar/20 7:21 PM,non
New Feature,Medium,ETAM-9854,81860,Front - Style Guide - Undiz,*GlobalMarque,Demandware,To Do,baudicg,DoeJ,3.0,,ETAM-9632,tomasid,Sprint07.20-15/04-10,,,,,12/Mar/20 4:20 PM,12/Mar/20 7:18 PM,Front,,,DoeJ,13/Mar/20 11:00 AM,non
Task,Medium,ETAM-9187,80430,Back - Audit backinstock,*GlobalMarque,,To Do,buffignl,DoeJ,2.0,,ETAM-9632,ribeils,Sprint07.20-15/04-10,,,,,06/Nov/19 2:49 PM,13/Mar/20 2:33 PM,Back,,,DoeJ,13/Mar/20 3:35 PM,non
New Feature,Medium,ETAM-9853,81859,Front - Style Guide - Etam ,*GlobalMarque,Demandware,To Do,baudicg,DoeJ,3.0,,ETAM-9632,tomasid,Sprint06.20-01/04-10,,,,,12/Mar/20 3:53 PM,12/Mar/20 7:20 PM,Front,,,DoeJ,13/Mar/20 3:51 PM,non
New Feature,Medium,ETAM-9855,81861,Nettoyage CSS / Style Guide - Etam ,*GlobalMarque,Demandware,To Do,baudicg,DoeJ,13.0,,ETAM-9632,tomasid,Sprint07.20-15/04-10,,,,,12/Mar/20 4:23 PM,12/Mar/20 7:19 PM,Front,,,DoeJ,13/Mar/20 3:52 PM,non
Bug,Medium,ETAM-9862,81869,Front - Identification - Retour Module Layer/panel,*GlobalMarque,,To Do,baudicg,DoeJ,5.0,,ETAM-9632,dorcetb,Sprint06.20-01/04-10,,,,,13/Mar/20 12:00 PM,13/Mar/20 12:25 PM,Front,,,DoeJ,13/Mar/20 5:39 PM,non
New Feature,Medium,ETAM-9824,81816,Back - Recommandations - Revue du module gÃ©nÃ©rique,*GlobalMarque,,To Do,ribeils,DoeJ,8.0,,ETAM-9632,ribeils,Sprint07.20-15/04-10,,,,,09/Mar/20 6:59 PM,11/Mar/20 11:45 AM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9323,80665,Front - Installer slider sur cross sell et Ab test du nombre de rÃ©sultats,*GlobalMarque,,To Do,robers01,robers01,3.0,,ETAM-9632,ribeils,Sprint04.20-04/03-10,Sprint07.20-15/04-10,,,,27/Nov/19 10:52 AM,05/Dec/19 3:54 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-7919,77696,Front - Analyse - DÃ©finir des valeurs z-index par dÃ©faut,*Etam,*GlobalMarque,To Do,ribeils,DoeJ,3.0,,ETAM-9632,perneyb,Sprint07.20-15/04-10,,,,,18/Feb/19 3:21 PM,13/Nov/19 2:46 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
Task,Medium,ETAM-8423,78742,Front - Analyser - Produit/Panier/CatÃ©gorie/Identification - Unifier JS,*GlobalMarque,,To Do,perneyb,perneyb,3.0,,ETAM-9632,ribeils,Sprint07.20-15/04-10,,,,,21/May/19 10:54 AM,07/Jun/19 3:42 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
Task,Medium,ETAM-9682,81459,Front - Analyse - AccessibilitÃ© web,*GlobalMarque,,To Do,buffignl,DoeJ,5.0,,ETAM-9632,ribeils,Sprint07.20-15/04-10,,,,,14/Feb/20 3:14 PM,14/Feb/20 4:24 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
Task,Medium,ETAM-9186,80429,Front - Audit backinstock,*GlobalMarque,,Backlog,buffignl,DoeJ,2.0,,ETAM-9632,ribeils,Sprint07.20-15/04-10,,,,,06/Nov/19 2:48 PM,,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9508,80977,Back - Service content asset,*GlobalMarque,,Additional information required,ribeils,DoeJ,,,ETAM-9632,ribeils,,,,,,07/Jan/20 2:39 PM,,Back,,,DoeJ,25/Feb/20 2:03 PM,non
New Feature,Medium,ETAM-9683,81460,Front - Module layer/panel,*GlobalMarque,Demandware,To Release,brunierg,baudicg,8.0,,ETAM-9632,pitancea,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,,,14/Feb/20 4:39 PM,13/Mar/20 12:52 PM,Front,ETAM_20_03_05 (RD 18/03),,perneyb,13/Mar/20 12:52 PM,non
Maintenance,Medium,ETAM-9724,81601,CrÃ©ation sandbox test,*GlobalMarque,,Closed,Eychenet,brunierg,,,ETAM-9632,antoia01,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,,,20/Feb/20 11:09 AM,,Back,,,DoeJ,10/Mar/20 11:32 AM,non
New Feature,High,ETAM-9492,80955,Back - Shipping - Suppression des surcharges relatives aux forms ,*GlobalMarque,Demandware,waiting for QAT sur dev,brunierg,LENOBP01,8.0,,ETAM-9241,pitancea,Sprint02.20-05/02-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,02/Jan/20 2:25 PM,02/Jan/20 2:25 PM,Back,,,DoeJ,06/Mar/20 6:02 PM,non
New Feature,Medium,ETAM-9491,80954,Back - Checkout/Global - DÃ©finition des forms dans app_core,*GlobalMarque,Demandware,waiting for QAT sur dev,brunierg,brunierg,8.0,,ETAM-9241,pitancea,Sprint02.20-05/02-10,Sprint01/3.20-22/01-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,02/Jan/20 2:18 PM,02/Jan/20 2:22 PM,Back,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,High,ETAM-9408,80778,Back - Shipping - Optimisation du code shipping,*GlobalMarque,,waiting for QAT sur dev,brunierg,brunierg,8.0,,ETAM-9241,ribeils,Sprint02.20-05/02-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,13/Dec/19 10:47 AM,16/Dec/19 11:18 AM,Back,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,High,ETAM-9403,80773,Back - Shipping - Suppression des surcharges store et migration en controller,*GlobalMarque,,waiting for QAT sur dev,brunierg,LENOBP01,8.0,,ETAM-9241,ribeils,Sprint02.20-05/02-10,Sprint01/3.20-22/01-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,12/Dec/19 5:44 PM,12/Dec/19 5:58 PM,Back,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,Medium,ETAM-9243,80566,Front - Shipping - Revue de la structure de la page,*GlobalMarque,,waiting for QAT sur dev,brunierg,perneyb,13.0,,ETAM-9241,ribeils,Sprint02.20-05/02-10,Sprint01/3.20-22/01-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,18/Nov/19 5:31 PM,06/Mar/20 4:23 PM,Front,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,Medium,ETAM-9654,81419,Front - Shipping - Template de rappel panier,*GlobalMarque,,QAT SB,dorcetb,perneyb,5.0,,ETAM-9241,ribeils,Sprint04.20-04/03-10,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,12/Feb/20 11:36 AM,17/Feb/20 11:04 AM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9652,81417,Front - Shipping - Restructuration de la page,*GlobalMarque,,QAT SB,Eychenet,perneyb,5.0,8.0,ETAM-9241,ribeils,Sprint04.20-04/03-10,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,12/Feb/20 11:00 AM,17/Feb/20 11:04 AM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9696,81479,Front - Shipping - Domicile - Cliente connectÃ©e avec carnet d'adresse,*GlobalMarque,,QAT SB,Eychenet,perneyb,0.5,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,18/Feb/20 2:48 PM,27/Feb/20 5:21 PM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9826,81819,Front - Shipping - Mag/relais - Module - GÃ©olocalisation et recherche proximitÃ©,*GlobalMarque,,To Do,ribeils,DoeJ,3.0,,ETAM-9241,ribeils,,,,,,10/Mar/20 12:35 PM,12/Mar/20 4:55 PM,Front,,,DoeJ,12/Mar/20 4:55 PM,non
New Feature,Medium,ETAM-9704,81495,Back - Shipping - Mag/relais - Enregistrement du dernier mag / relais colis / inpost,*GlobalMarque,,To Do,ribeils,DoeJ,3.0,,ETAM-9241,ribeils,Sprint07.20-15/04-10,,,,,19/Feb/20 12:45 PM,27/Feb/20 3:54 PM,Back,,,DoeJ,13/Mar/20 3:41 PM,non
New Feature,Medium,ETAM-9694,81477,Front - Shipping - Domicile - EntrÃ©e d'une adresse de livraison en mode connectÃ©,*GlobalMarque,,To Do,perneyb,perneyb,2.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,18/Feb/20 1:58 PM,28/Feb/20 3:18 PM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9705,81496,Front - Shipping - Mag/relais - Selection relais et mag et gestion liste dÃ©roulante,*GlobalMarque,,To Do,perneyb,DoeJ,3.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,19/Feb/20 12:47 PM,10/Mar/20 7:08 PM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9828,81822,"Front - Shipping - Mag/relais - Module - Vue plan, vu liste, dÃ©tails magasin",*GlobalMarque,,To Do,perneyb,DoeJ,3.0,,ETAM-9241,ribeils,Sprint07.20-15/04-10,,,,,10/Mar/20 3:55 PM,12/Mar/20 4:58 PM,Front,,,DoeJ,13/Mar/20 3:55 PM,non
New Feature,Medium,ETAM-9798,81781,Front - Shipping - Mise Ã jour du rappel panier,*GlobalMarque,,To Do,perneyb,DoeJ,2.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,04/Mar/20 2:01 PM,04/Mar/20 2:15 PM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9738,81704,Front - Shipping - Mag/relais - Module - CrÃ©ation du module et structure,*GlobalMarque,,To Do,perneyb,DoeJ,3.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,24/Feb/20 12:15 PM,13/Mar/20 11:33 AM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9701,81491,Front - Shipping - Domicile - Adresse de facturation,*GlobalMarque,,To Do,perneyb,perneyb,3.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,19/Feb/20 11:14 AM,28/Feb/20 4:12 PM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9861,81868,Front - Shipping - Gestion des properties FIL ROUGE,*GlobalMarque,,To Do,perneyb,DoeJ,3.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,13/Mar/20 11:25 AM,13/Mar/20 11:30 AM,Front,,,DoeJ,13/Mar/20 3:56 PM,non
New Feature,Medium,ETAM-9815,81802,Back - Woosmap - IntÃ©gration des mags,*GlobalMarque,,To Do,LENOBP01,DoeJ,5.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,06/Mar/20 2:51 PM,11/Mar/20 11:18 AM,Back,,,DoeJ,13/Mar/20 6:36 PM,non
New Feature,Medium,ETAM-9695,81478,Front - Shipping - Domicile - EntrÃ©e d'une adresse de livraison en mode guest,*GlobalMarque,,To Do,perneyb,perneyb,1.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,18/Feb/20 2:43 PM,28/Feb/20 4:11 PM,Front,,,DoeJ,17/Mar/20 9:56 AM,non
New Feature,Medium,ETAM-9493,80957,Back - Shipping - Utilisation de la dÃ©finition de formulaire profile pour le guest ,*GlobalMarque,Demandware,Pending,brunierg,brunierg,5.0,,ETAM-9241,pitancea,Sprint03.20-19/02-10,Sprint06.20-01/04-10,,,,02/Jan/20 2:30 PM,02/Jan/20 2:30 PM,Back,,,DoeJ,13/Mar/20 3:33 PM,non
New Feature,Medium,ETAM-9697,81484,Front - Shipping - Domicile - Bloc d'adresse / Modification d'adresse / Changement d'adresse,*GlobalMarque,,PR Under Review,brunierg,perneyb,3.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,18/Feb/20 3:59 PM,28/Feb/20 4:12 PM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9703,81494,Front - Shipping - Domicile - Choix de la mÃ©thode de livraison,*GlobalMarque,,PR Under Review,brunierg,perneyb,2.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,19/Feb/20 11:42 AM,27/Feb/20 5:28 PM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
Bug,Medium,ETAM-9212,80517,Back - Tous facteurs - Event aprÃ¨s bug,*GlobalMarque,,Additional information required,ribeils,LENOBP01,1.0,,ETAM-9241,ribeils,,,,,,14/Nov/19 10:46 AM,18/Nov/19 10:24 AM,Back,,,DoeJ,25/Feb/20 1:40 PM,non
New Feature,Medium,ETAM-9739,81706,Front - Shipping - Domicile - Sur crÃ©neaux,*GlobalMarque,,Additional information required,ribeils,DoeJ,,,ETAM-9241,ribeils,,,,,,24/Feb/20 3:00 PM,,Back,,,DoeJ,24/Feb/20 3:00 PM,non
New Feature,Medium,ETAM-9646,81411,Back - Shipping - Enregistrement potentiel multishipping,*GlobalMarque,,Additional information required,ribeils,DoeJ,,,ETAM-9241,ribeils,,,,,,11/Feb/20 7:48 PM,,Back,,,DoeJ,12/Feb/20 11:29 AM,non
New Feature,Medium,ETAM-9825,81818,Front - Shipping - Mag/relais - Module - La recherche,*GlobalMarque,,Additional information required,ribeils,DoeJ,5.0,,ETAM-9241,ribeils,,,,,,10/Mar/20 12:32 PM,,Front,,,DoeJ,13/Mar/20 11:16 AM,non
New Feature,Medium,ETAM-9404,80774,Back - Shipping - Domicile - Sur crÃ©neaux,*GlobalMarque,,Additional information required,ribeils,DoeJ,8.0,,ETAM-9241,ribeils,,,,,,12/Dec/19 5:47 PM,16/Dec/19 11:17 AM,Back,,,DoeJ,13/Mar/20 12:32 PM,non
Bug,Medium,ETAM-9373,80734,Back - TAH - guest certaines shippings ne remontent pas,*1.2.3,,Additional information required,ribeils,LENOBP01,3.0,,ETAM-9241,Eychenet,,,,,,05/Dec/19 6:17 PM,05/Dec/19 6:27 PM,Back,,,DoeJ,13/Mar/20 12:32 PM,non
New Feature,Medium,ETAM-9708,81503,Front - Shipping - Mag/relais - Adresse de facturation guest et connectÃ©,*GlobalMarque,,Additional information required,ribeils,DoeJ,2.0,,ETAM-9241,ribeils,Sprint07.20-15/04-10,,,,,19/Feb/20 5:23 PM,,Front,,,DoeJ,13/Mar/20 3:55 PM,non
Task,Medium,ETAM-9279,80616,Back - Analyse - Audit back passage du checkout sur le CORE,*GlobalMarque,,Closed,ribeils,brunierg,8.0,,ETAM-9241,ribeils,Sprint01/1.20-22/01-10,,,,,21/Nov/19 6:37 PM,13/Dec/19 10:48 AM,Back,,,DoeJ,13/Dec/19 10:48 AM,non
Task,Medium,ETAM-9277,80614,Front - Analyse - Shipping - Audit du code,*GlobalMarque,,Closed,ribeils,perneyb,5.0,,ETAM-9241,ribeils,Sprint01/1.20-22/01-10,,,,,21/Nov/19 5:09 PM,16/Dec/19 11:19 AM,Front,,,DoeJ,16/Dec/19 11:19 AM,non
Task,High,ETAM-9202,80449,Front - Analyse - ImplÃ©mentation Woosmap,*GlobalMarque,,Closed,buffignl,mariono,3.0,5.0,ETAM-9241,buffignl,Sprint03.20-19/02-10,Sprint04.20-04/03-10,,,,08/Nov/19 5:02 PM,28/Feb/20 2:36 PM,Front,,,DoeJ,06/Mar/20 3:49 PM,non
New Feature,Medium,ETAM-9829,81830,Back - Shipping - Controller modification d'adresse,*GlobalMarque,,In Progress,brunierg,brunierg,2.0,,ETAM-9241,ribeils,Sprint06.20-01/04-10,,,,,10/Mar/20 7:12 PM,13/Mar/20 11:31 AM,Back,,,DoeJ,16/Mar/20 10:35 AM,non
New Feature,Medium,ETAM-9702,81493,Back - Shipping - Domicile/Relais/Mag - Adresse de facturation et email,*GlobalMarque,,In Progress,brunierg,LENOBP01,5.0,,ETAM-9241,ribeils,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,19/Feb/20 11:36 AM,24/Feb/20 10:26 AM,Back,,,lefevrey,16/Mar/20 10:58 AM,non
New Feature,Medium,ETAM-8904,79697,Back - Gpay / shipping adress/ pays pour lesquels on accepte de livrer ou non,*Etam,,To Do,ribeils,DoeJ,1.0,,ETAM-9628,tomasid,,,,,,04/Sep/19 12:21 PM,11/Sep/19 11:49 AM,Back,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9676,81448,Back - Panier - Retour Burn,Demandware,,To Do,antoia01,DoeJ,,,ETAM-9628,tomasid,,,,,,13/Feb/20 11:14 AM,13/Feb/20 11:30 AM,Back,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9675,81446,Front - Panier - Bloc Identification ,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,13/Feb/20 10:47 AM,13/Feb/20 11:01 AM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9674,81444,Back - Panier - Mise en place stratÃ©gie cross sell,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,13/Feb/20 10:42 AM,13/Feb/20 10:44 AM,Back,,,DoeJ,06/Mar/20 3:23 PM,non
Task,Medium,ETAM-9672,81441,Back - Panier - Analyse stratÃ©gie cross sell panier,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 5:37 PM,13/Feb/20 10:40 AM,Back,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9667,81436,Front - Panier - A UTLISER2,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 4:48 PM,12/Feb/20 4:56 PM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9664,81431,Front - Panier - Partage panier,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 3:44 PM,12/Feb/20 3:57 PM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9653,81418,Front - Panier - Burn,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 11:04 AM,12/Feb/20 12:24 PM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9650,81415,Front - Panier - Recapitulatif Panier + Total ,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 9:19 AM,12/Feb/20 10:55 AM,Front,,,DoeJ,10/Mar/20 11:20 AM,non
New Feature,Medium,ETAM-9639,81401,Front - Panier - Bloc Free shipping,*GlobalMarque,Demandware,To Do,tomasid,DoeJ,3.0,,ETAM-9628,tomasid,,,,,,11/Feb/20 4:15 PM,11/Feb/20 4:46 PM,Front,,,DoeJ,11/Mar/20 2:28 PM,non
New Feature,Medium,ETAM-9662,81427,Front - Panier - Retrait article panier,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,3.0,,ETAM-9628,tomasid,,,,,,12/Feb/20 3:09 PM,12/Feb/20 3:42 PM,Front,,,DoeJ,12/Mar/20 2:27 PM,non
New Feature,Medium,ETAM-9659,81424,Front - Panier - Bloc Promodon,Demandware,,To Do,antoia01,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 12:24 PM,12/Feb/20 12:30 PM,Front,,,DoeJ,13/Mar/20 9:59 AM,non
New Feature,Medium,ETAM-9642,81407,Front - Panier - Bloc produit offert ,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,11/Feb/20 7:11 PM,11/Feb/20 7:12 PM,Front,,,DoeJ,13/Mar/20 4:55 PM,non
New Feature,Medium,ETAM-9670,81439,Front - Panier - RÃ©assurance - Template de rÃ©assurance paiement,*GlobalMarque,Demandware,To Do,pitancea,DoeJ,0.5,,ETAM-9628,tomasid,Sprint07.20-15/04-10,,,,,12/Feb/20 5:17 PM,12/Feb/20 5:25 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9668,81437,Front - Panier - RÃ©assurance - Template de rÃ©assurance site,*GlobalMarque,Demandware,To Do,tomasid,DoeJ,2.0,,ETAM-9628,tomasid,Sprint07.20-15/04-10,,,,,12/Feb/20 4:59 PM,12/Feb/20 5:12 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9647,81412,Front - Panier - Code Promotionnel ,*GlobalMarque,Demandware,To Do,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,11/Feb/20 7:49 PM,11/Feb/20 7:50 PM,Front,,,DoeJ,17/Mar/20 10:04 AM,non
New Feature,Medium,ETAM-9811,81797,Front - Panier - Bloc Free shipping - Local,*GlobalMarque,Demandware,Backlog,tomasid,DoeJ,,,ETAM-9628,tomasid,,,,,,06/Mar/20 12:08 PM,,Front,,,DoeJ,06/Mar/20 2:14 PM,non
New Feature,Medium,ETAM-9669,81438,Front - Panier - A UTILISER3,*GlobalMarque,Demandware,Backlog,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 5:05 PM,12/Feb/20 5:12 PM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9649,81414,Front - Panier - Panier vide ,*GlobalMarque,Demandware,Backlog,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 9:01 AM,,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9661,81426,Front - Panier - bloc produit ,*GlobalMarque,Demandware,Backlog,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 2:18 PM,,Front,,,DoeJ,12/Mar/20 12:35 PM,non
New Feature,Medium,ETAM-9820,81809,Front - Panier - BanniÃ¨re Temporaire ,*GlobalMarque,Demandware,Backlog,pitancea,DoeJ,,,ETAM-9628,tomasid,,,,,,09/Mar/20 10:26 AM,,Front,,,DoeJ,12/Mar/20 6:13 PM,non
New Feature,Medium,ETAM-9819,81808,Front - Panier - Message promotionnel,*GlobalMarque,Demandware,Backlog,pitancea,DoeJ,2.0,,ETAM-9628,tomasid,Sprint07.20-15/04-10,,,,,09/Mar/20 9:38 AM,,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9813,81799,Front - Panier - Mode livraison,*GlobalMarque,Demandware,Backlog,buffignl,DoeJ,0.5,,ETAM-9628,tomasid,Sprint07.20-15/04-10,,,,,06/Mar/20 12:35 PM,,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9859,81866,Front - Panier - Produits complÃ©mentaires (Emballage Cadeau/Micro Don),Demandware,,Backlog,antoia01,DoeJ,,,ETAM-9628,tomasid,,,,,,13/Mar/20 9:59 AM,,Front,,,DoeJ,16/Mar/20 2:50 PM,oui
Task,Medium,ETAM-9325,80667,Front - Lister les diffÃ©rents messages d'erreur liÃ©s aux coupons de promotion,*GlobalMarque,,Additional information required,pitancea,perneyb,2.0,,ETAM-9628,tomasid,,,,,,27/Nov/19 10:58 AM,27/Nov/19 11:00 AM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
Bug,Medium,ETAM-8938,79752,Back - DÃ©passement de la limite d'exemplaires d'un mÃªme article,*GlobalMarque,,Additional information required,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,09/Sep/19 3:25 PM,18/Nov/19 10:24 AM,Back,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9666,81433,Front - Panier - Structure Page Panier + AB mobile,*GlobalMarque,Demandware,Additional information required,buffignl,DoeJ,,,ETAM-9628,tomasid,,,,,,12/Feb/20 4:09 PM,12/Feb/20 4:56 PM,Front,,,DoeJ,06/Mar/20 3:23 PM,non
New Feature,Medium,ETAM-9671,81440,Front- Panier - Header checkout,*GlobalMarque,Demandware,To Release,brunierg,baudicg,5.0,,ETAM-9628,pitancea,Sprint04.20-04/03-10,,,,,12/Feb/20 5:27 PM,02/Mar/20 1:41 PM,Front,ETAM_20_03_05 (RD 18/03),,DoeJ,06/Mar/20 5:17 PM,non
New Feature,Medium,ETAM-9752,81726,Back - Paiement - Cartes bancaires sur une ligne unique et paiement en back,*GlobalMarque,,waiting for QAT sur dev,brunierg,brunierg,5.0,,ETAM-9643,ribeils,Sprint05.20-18/03-10,,,,,25/Feb/20 5:36 PM,27/Feb/20 4:03 PM,Back,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,High,ETAM-9427,80800,Front - Paiement - Passage page de paiement en CORE,*GlobalMarque,,QAT SB,Eychenet,meyronnf,8.0,13.0,ETAM-9643,ribeils,Sprint02.20-05/02-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint06.20-01/04-10,,17/Dec/19 12:55 PM,17/Dec/19 12:55 PM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9749,81723,Front - Paiement - Paiement par CCD,*GlobalMarque,,To Do,ribeils,DoeJ,2.0,,ETAM-9643,ribeils,,,,,,25/Feb/20 5:23 PM,12/Mar/20 3:54 PM,Front,,,DoeJ,12/Mar/20 3:54 PM,non
New Feature,Medium,ETAM-9795,81777,Front - Paiement - Passage de 4 moyens de paiement dans le CORE,*GlobalMarque,,To Do,meyronnf,DoeJ,2.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,03/Mar/20 7:27 PM,12/Mar/20 4:01 PM,Front,,,DoeJ,13/Mar/20 5:37 PM,non
New Feature,Medium,ETAM-9812,81798,Front - Paiement - Gestion des properties FIL ROUGE,*GlobalMarque,,To Do,meyronnf,DoeJ,3.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,06/Mar/20 12:09 PM,13/Mar/20 5:38 PM,Front,,,DoeJ,13/Mar/20 5:38 PM,non
New Feature,Medium,ETAM-9799,81782,Front - Paiement - Affichage des conditions gÃ©nÃ©rales de vente,*GlobalMarque,,To Do,ribeils,DoeJ,1.0,,ETAM-9643,ribeils,,,,,,04/Mar/20 2:22 PM,13/Mar/20 5:38 PM,Front,,,DoeJ,13/Mar/20 5:38 PM,non
New Feature,Medium,ETAM-9753,81727,Front - Paiement - Detection de la carte de crÃ©dit,*GlobalMarque,,To Do,meyronnf,DoeJ,2.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,25/Feb/20 5:52 PM,12/Mar/20 3:59 PM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9748,81722,Front - Paiement - Choix du mode de paiement et paiement,*GlobalMarque,,To Do,meyronnf,DoeJ,3.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,25/Feb/20 5:22 PM,28/Feb/20 5:23 PM,Front,,,DoeJ,13/Mar/20 8:19 PM,non
New Feature,Medium,ETAM-9640,81402,Front - Paiement - Template de rappel Livraison,*GlobalMarque,,PR Under Review,brunierg,meyronnf,3.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,11/Feb/20 4:26 PM,14/Feb/20 4:02 PM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9637,81399,Front - Paiement - Restructuration de la page,*GlobalMarque,,PR Under Review,brunierg,meyronnf,2.0,,ETAM-9643,ribeils,Sprint03.20-19/02-10,Sprint06.20-01/04-10,,,,11/Feb/20 4:08 PM,17/Feb/20 11:05 AM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9808,81794,Front - Paiement - DÃ©clinaison Undiz,*Undiz,,Additional information required,ribeils,DoeJ,2.0,,ETAM-9643,ribeils,,,,,,06/Mar/20 11:42 AM,,Front,,,DoeJ,12/Mar/20 4:20 PM,non
New Feature,Medium,ETAM-9807,81793,Front - Paiement - DÃ©clinaison Etam,*Etam,,Additional information required,ribeils,DoeJ,8.0,,ETAM-9643,ribeils,,,,,,06/Mar/20 11:15 AM,,Front,,,DoeJ,12/Mar/20 4:19 PM,non
New Feature,Medium,ETAM-9810,81796,Front - Paiement - DÃ©clinaison Livy,*Li-vy,,Additional information required,vastels,DoeJ,2.0,,ETAM-9643,ribeils,,,,,,06/Mar/20 11:47 AM,,Front,,,DoeJ,12/Mar/20 4:22 PM,non
New Feature,Medium,ETAM-9809,81795,Front - Paiement - DÃ©clinaison Maison123,*1.2.3,,Additional information required,ribeils,DoeJ,2.0,,ETAM-9643,ribeils,,,,,,06/Mar/20 11:45 AM,,Front,,,DoeJ,12/Mar/20 4:21 PM,non
New Feature,Medium,ETAM-9814,81800,Front - Paiement - Validation des formulaires,*GlobalMarque,,Additional information required,pitancea,DoeJ,3.0,,ETAM-9643,ribeils,,,,,,06/Mar/20 12:39 PM,12/Mar/20 4:17 PM,Front,,,DoeJ,13/Mar/20 5:40 PM,non
New Feature,Medium,ETAM-9750,81724,Front - Paiement - Sauvegarde et prÃ©sÃ©lection de la carte,*GlobalMarque,,In Progress,meyronnf,meyronnf,3.0,,ETAM-9643,ribeils,Sprint06.20-01/04-10,,,,,25/Feb/20 5:28 PM,27/Feb/20 5:10 PM,Front,,,DoeJ,16/Mar/20 5:14 PM,non
New Feature,Medium,ETAM-9660,81425,Front - Confirmation - Blocs produits,*GlobalMarque,,Backlog,buffignl,DoeJ,,,ETAM-9631,ribeils,,,,,,12/Feb/20 12:27 PM,,Front,,,DoeJ,12/Feb/20 12:38 PM,non
New Feature,Medium,ETAM-9648,81413,Front - Confirmation - Message de confirmation de commande,*GlobalMarque,,Backlog,buffignl,DoeJ,,,ETAM-9631,ribeils,,,,,,11/Feb/20 7:55 PM,,Front,,,DoeJ,11/Feb/20 7:56 PM,non
Task,Medium,ETAM-9644,81409,Back - Analyse - Rattachement commande aprÃ¨s prise de commande,*GlobalMarque,,Backlog,buffignl,DoeJ,,,ETAM-9631,ribeils,,,,,,11/Feb/20 7:24 PM,,Back,,,DoeJ,11/Feb/20 7:25 PM,non
New Feature,Medium,ETAM-9645,81410,Front - Confirmation - Structure ,*GlobalMarque,,Additional information required,buffignl,DoeJ,,,ETAM-9631,ribeils,,,,,,11/Feb/20 7:41 PM,,Front,,,DoeJ,12/Feb/20 2:22 PM,non
Task,Medium,ETAM-9754,81728,Back - Identification - FonctionnalitÃ© Indice mdp,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,2.0,,ETAM-9633,pitancea,,,,,,25/Feb/20 7:03 PM,11/Mar/20 11:10 AM,Back,,,DoeJ,11/Mar/20 4:08 PM,non
New Feature,Medium,ETAM-9756,81730,Front - Identification - Inscription,*GlobalMarque,Demandware,To Do,baudicg,baudicg,0.5,,ETAM-9633,pitancea,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,25/Feb/20 7:04 PM,27/Feb/20 10:46 AM,Front,,,DoeJ,13/Mar/20 3:52 PM,non
New Feature,Medium,ETAM-9823,81815,Front - Identification - Parcours Identification depuis encart Fid panier,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,8.0,,ETAM-9633,pitancea,Sprint07.20-15/04-10,,,,,09/Mar/20 4:53 PM,10/Mar/20 12:36 PM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9836,81837,Front - Identification - Condition affichage encart fid dans panier,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,2.0,,ETAM-9633,pitancea,Sprint07.20-15/04-10,,,,,11/Mar/20 12:41 PM,11/Mar/20 12:53 PM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9760,81734,Front - Identification - Nouvelle Ã©tape Identification,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,2.0,,ETAM-9633,pitancea,Sprint07.20-15/04-10,,,,,25/Feb/20 7:21 PM,11/Mar/20 12:37 PM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9822,81814,Front - Identification - Auto Sign-in,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,2.0,,ETAM-9633,pitancea,Sprint07.20-15/04-10,,,,,09/Mar/20 4:14 PM,09/Mar/20 4:29 PM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9434,80808,Front - Globalmarques - Chargement diffÃ©rÃ© Reach5,*GlobalMarque,Demandware,To Do,brunierg,DoeJ,3.0,,ETAM-9633,pitancea,Sprint03.20-19/02-10,Sprint07.20-15/04-10,,,,18/Dec/19 11:32 AM,18/Dec/19 11:49 AM,Front,,,DoeJ,13/Mar/20 5:52 PM,non
New Feature,Medium,ETAM-9839,81840,Back - Identification - Gestion module cartÃ© dans connexion,*GlobalMarque,Demandware,To Do,ribeils,DoeJ,2.0,,ETAM-9633,pitancea,Sprint07.20-15/04-10,,,,,11/Mar/20 12:56 PM,11/Mar/20 12:57 PM,Back,,,DoeJ,13/Mar/20 6:28 PM,non
New Feature,Medium,ETAM-9733,81629,Identification : changement wording mot de passe,*Etam,,Backlog,ribeils,DoeJ,,,ETAM-9633,demaye,,,,,,21/Feb/20 10:18 AM,,Front,,,DoeJ,25/Feb/20 2:39 PM,non
New Feature,Medium,ETAM-9759,81733,Front - Identification - Ouverture module Identification,*GlobalMarque,Demandware,PR Under Review,brunierg,baudicg,1.0,,ETAM-9633,pitancea,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,25/Feb/20 7:21 PM,27/Feb/20 10:46 AM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9755,81729,Front - Identification - Connexion,*GlobalMarque,Demandware,PR Under Review,brunierg,baudicg,0.5,,ETAM-9633,pitancea,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,25/Feb/20 7:04 PM,27/Feb/20 10:46 AM,Front,,,DoeJ,13/Mar/20 3:50 PM,non
New Feature,Medium,ETAM-9441,80816,Wording - Se connecter s'incrire,*Undiz,,Additional information required,pitancea,DoeJ,,,ETAM-9633,buffignl,,,,,,18/Dec/19 5:38 PM,,Front,,,DoeJ,06/Mar/20 2:18 PM,non
New Feature,Medium,ETAM-9214,80520,Front - Pop in identification - NumÃ©ro de tÃ©lÃ©phone RGPD non obligatoire,*Etam,,Additional information required,pitancea,DoeJ,2.0,,ETAM-9633,demaye,,,,,,14/Nov/19 3:07 PM,30/Jan/20 3:17 PM,Back,,,DoeJ,25/Feb/20 12:31 PM,non
New Feature,Medium,ETAM-9204,80451,"Identification / crÃ©ation de compte : rajout genre ""Non prÃ©cisÃ©""",*Etam,*GlobalMarque,Additional information required,pascalm,DoeJ,,,ETAM-9633,demaye,,,,,,12/Nov/19 12:06 PM,,Back,,,DoeJ,25/Feb/20 1:43 PM,non
New Feature,Medium,ETAM-9194,80438,UND - MPR - Modification du genre dans le formulaire de crÃ©ation de compte,*GlobalMarque,*Undiz,Additional information required,buffignl,DoeJ,,,ETAM-9633,priourm,,,,,,07/Nov/19 5:39 PM,,Front,,,DoeJ,06/Mar/20 2:18 PM,non
New Feature,Medium,ETAM-9031,80108,Back - Formulaires - Confirmation changement de mot de passe,*Etam,*GlobalMarque,Additional information required,pitancea,DoeJ,,,ETAM-9633,demaye,,,,,,01/Oct/19 4:50 PM,18/Oct/19 4:50 PM,Back,,,DoeJ,25/Feb/20 2:02 PM,non
New Feature,Medium,ETAM-9020,80023,Front - IdentificatÂ° - Gestion mot de passe ,*GlobalMarque,Demandware,Additional information required,pitancea,pitancea,2.0,,ETAM-9633,pitancea,,,,,,27/Sep/19 2:20 PM,27/Sep/19 2:21 PM,Front,,,DoeJ,06/Mar/20 2:17 PM,non
Bug,Minor,ETAM-8862,79594,Back - Reach5 - Connexion aprÃ¨s annulation connexion RS,*GlobalMarque,,Additional information required,pitancea,DoeJ,3.0,,ETAM-9633,ribeils,,,,,,22/Aug/19 5:32 PM,18/Nov/19 10:24 AM,Back,,,DoeJ,25/Feb/20 1:37 PM,non
New Feature,Medium,ETAM-9827,81820,Front - Identification - Mot de passe oubliÃ©,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,,,ETAM-9633,pitancea,,,,,,10/Mar/20 2:04 PM,,Front,,,DoeJ,10/Mar/20 3:18 PM,non
New Feature,Medium,ETAM-9843,81849,Front - Identification - DÃ©clinaison Undiz ,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,,,ETAM-9633,pitancea,,,,,,12/Mar/20 11:01 AM,,Front,,,DoeJ,12/Mar/20 11:20 AM,non
New Feature,Medium,ETAM-9844,81850,Front - Identification - DÃ©clinaison Livy ,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,,,ETAM-9633,pitancea,,,,,,12/Mar/20 11:02 AM,,Front,,,DoeJ,12/Mar/20 11:20 AM,non
New Feature,Medium,ETAM-9846,81852,Front - Identification - DÃ©clinaison Maison 123,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,,,ETAM-9633,pitancea,,,,,,12/Mar/20 11:07 AM,,Front,,,DoeJ,12/Mar/20 11:20 AM,non
New Feature,Medium,ETAM-9842,81848,Front - Identification - DÃ©clinaison ETAM ,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,,,ETAM-9633,pitancea,,,,,,12/Mar/20 10:57 AM,,Front,,,DoeJ,12/Mar/20 11:19 AM,non
New Feature,Medium,ETAM-9758,81732,Front - Identification - Bloc FidÃ©litÃ© - Depuis bloc Inscription classique ,*GlobalMarque,Demandware,In Progress,baudicg,baudicg,2.0,,ETAM-9633,pitancea,Sprint05.20-18/03-10,Sprint06.20-01/04-10,,,,25/Feb/20 7:19 PM,27/Feb/20 10:46 AM,Front,,,DoeJ,13/Mar/20 3:49 PM,non
New Feature,Medium,ETAM-8403,78704,Front - Suppression custom pref de dossier de content assets pour la HP,*Li-vy,*Undiz,To Do,sellahm,sellahm,1.0,,ETAM-9242,perneyb,,,,,,16/May/19 5:38 PM,17/May/19 2:45 PM,Front,,,DoeJ,12/Mar/20 12:39 PM,non
New Feature,Medium,ETAM-9837,81838,Front - Homepage - Cross sell slider,*GlobalMarque,,To Do,sellahm,DoeJ,5.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,11/Mar/20 12:46 PM,12/Mar/20 11:05 AM,Front,,,DoeJ,13/Mar/20 5:54 PM,non
New Feature,Medium,ETAM-9838,81839,Front - Homepage - Cross sell carroussel,*GlobalMarque,,To Do,sellahm,DoeJ,3.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,11/Mar/20 12:47 PM,12/Mar/20 4:37 PM,Front,,,DoeJ,13/Mar/20 5:54 PM,non
New Feature,Medium,ETAM-9847,81853,Front - Homepage - Full banner - Application du DIS,*GlobalMarque,,To Do,robers01,DoeJ,1.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,12/Mar/20 11:09 AM,12/Mar/20 11:09 AM,Front,,,DoeJ,13/Mar/20 5:55 PM,non
New Feature,Medium,ETAM-9818,81807,Front - Homepage - Slider vertical,*GlobalMarque,,To Do,ribeils,DoeJ,2.0,,ETAM-9242,ribeils,Sprint07.20-15/04-10,,,,,06/Mar/20 5:04 PM,12/Mar/20 4:29 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
New Feature,Medium,ETAM-9851,81857,Front - Homepage - Composant liens multiples,*GlobalMarque,,To Do,robers01,DoeJ,2.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,12/Mar/20 11:42 AM,12/Mar/20 4:40 PM,Front,,,DoeJ,13/Mar/20 5:55 PM,non
New Feature,Medium,ETAM-9830,81831,Back - Homepage - Ajout d'attibuts sur les composants de cross sell,*GlobalMarque,,To Do,lefevrey,DoeJ,3.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,10/Mar/20 7:37 PM,11/Mar/20 11:32 AM,Back,,,DoeJ,13/Mar/20 6:34 PM,non
New Feature,Medium,ETAM-9794,81776,Back - Homepage - Gestion homepage et customer groups,*GlobalMarque,,To Do,LENOBP01,DoeJ,3.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,03/Mar/20 6:27 PM,13/Mar/20 3:48 PM,Back,,,DoeJ,13/Mar/20 6:34 PM,non
New Feature,Medium,ETAM-9834,81835,Back - Homepage - Composant liens multiples,*GlobalMarque,,To Do,lefevrey,DoeJ,2.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,11/Mar/20 10:50 AM,13/Mar/20 2:33 PM,Back,,,DoeJ,13/Mar/20 6:35 PM,non
New Feature,Medium,ETAM-9831,81832,Back - Homepage - manual defined product recommender,*GlobalMarque,,To Do,lefevrey,DoeJ,2.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,10/Mar/20 7:56 PM,11/Mar/20 11:35 AM,Back,,,DoeJ,13/Mar/20 6:35 PM,non
New Feature,Medium,ETAM-9802,81786,Front - Homepage - Mode 100% hauteur pour les layout,*GlobalMarque,,To Do,robers01,DoeJ,3.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,05/Mar/20 11:56 AM,13/Mar/20 6:42 PM,Front,,,DoeJ,13/Mar/20 6:42 PM,non
Task,Medium,ETAM-9832,81833,Back - Analyse - Module Instagram,*GlobalMarque,,To Do,LENOBP01,DoeJ,3.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,10/Mar/20 8:05 PM,13/Mar/20 11:39 AM,Back,,,DoeJ,16/Mar/20 10:49 AM,non
Bug,Medium,ETAM-9772,81750,Front - Homepage - Le panel de connexion ne s'ouvre pas,*GlobalMarque,,Backlog,ribeils,DoeJ,2.0,,ETAM-9242,Eychenet,,,,,,27/Feb/20 3:05 PM,,Front,,,DoeJ,27/Feb/20 5:03 PM,non
New Feature,Medium,ETAM-9845,81851,Back - Homepage - Full banner - Envoie du DIS au front,*GlobalMarque,,PR Under Review,brunierg,LENOBP01,1.0,2.0,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,12/Mar/20 11:04 AM,12/Mar/20 11:08 AM,Back,,,DoeJ,16/Mar/20 4:53 PM,oui
New Feature,Medium,ETAM-9762,81736,Back - Homepage - Sous-composant banner content,*GlobalMarque,,To Release,brunierg,LENOBP01,5.0,,ETAM-9242,ribeils,Sprint04.20-04/03-10,,,,,26/Feb/20 1:04 PM,28/Feb/20 2:35 PM,Back,ETAM_20_03_05 (RD 18/03),,DoeJ,06/Mar/20 5:16 PM,non
New Feature,Medium,ETAM-9761,81735,Back - Homepage - Composant Full banner,*GlobalMarque,,To Release,brunierg,LENOBP01,2.0,,ETAM-9242,ribeils,Sprint04.20-04/03-10,,,,,26/Feb/20 11:37 AM,28/Feb/20 12:54 PM,Back,ETAM_20_03_05 (RD 18/03),,lefevrey,06/Mar/20 5:17 PM,non
New Feature,Medium,ETAM-9611,81363,Back - Homepage - Passage en controller et pluggage page designer,*GlobalMarque,,To Release,brunierg,LENOBP01,5.0,8.0,ETAM-9242,ribeils,Sprint04.20-04/03-10,,,,,07/Feb/20 2:16 PM,27/Feb/20 6:52 PM,Back,ETAM_20_03_05 (RD 18/03),,DoeJ,06/Mar/20 5:16 PM,non
New Feature,Medium,ETAM-9004,79931,Back - Page Designer: Installation de la cartridge,*GlobalMarque,,To Release,brunierg,LENOBP01,8.0,,ETAM-9242,ribeils,Sprint03.20-19/02-10,Sprint04.20-04/03-10,,,,20/Sep/19 6:28 PM,27/Feb/20 6:49 PM,Back,ETAM_20_02_03 (RD 19/02),ETAM_20_03_05 (RD 18/03),brunierg,11/Mar/20 6:00 PM,oui
New Feature,Medium,ETAM-9775,81757,Back - Homepage - CrÃ©ation de 4 composants Einstein,*GlobalMarque,,To Release,brunierg,lefevrey,5.0,,ETAM-9242,ribeils,Sprint05.20-18/03-10,,,,,28/Feb/20 4:02 PM,12/Mar/20 5:10 PM,Back,ETAM_20_03_05 (RD 18/03),,LENOBP01,12/Mar/20 5:10 PM,non
New Feature,Medium,ETAM-9767,81745,Front - Homepage - Composant Full banner,*GlobalMarque,,To Release,brunierg,meyronnf,2.0,,ETAM-9242,ribeils,Sprint05.20-18/03-10,,,,,27/Feb/20 1:20 PM,13/Mar/20 11:10 AM,Front,ETAM_20_03_05 (RD 18/03),,lefevrey,13/Mar/20 11:10 AM,non
New Feature,Medium,ETAM-9768,81746,Front - Homepage - Largeur/Hauteur des layouts,*GlobalMarque,,To Release,brunierg,meyronnf,2.0,,ETAM-9242,ribeils,Sprint05.20-18/03-10,,,,,27/Feb/20 1:33 PM,13/Mar/20 11:29 AM,Front,ETAM_20_03_05 (RD 18/03),,DoeJ,13/Mar/20 11:29 AM,oui
Task,Medium,ETAM-9764,81740,Back - Analyse - Homepage - Composants Einstein,*GlobalMarque,,Closed,ribeils,lefevrey,3.0,,ETAM-9242,ribeils,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,,,26/Feb/20 3:53 PM,06/Mar/20 5:22 PM,Back,,,DoeJ,06/Mar/20 5:22 PM,non
New Feature,Medium,ETAM-9769,81747,Front - Homepage - Sous-composant banner content,*GlobalMarque,,In Progress,sellahm,sellahm,5.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,27/Feb/20 1:52 PM,10/Mar/20 12:06 PM,Front,,,DoeJ,13/Mar/20 3:29 PM,non
New Feature,Medium,ETAM-9801,81785,Back - Homepage - Mode 100% hauteur pour les layout,*GlobalMarque,,In Progress,lefevrey,lefevrey,1.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,05/Mar/20 11:55 AM,11/Mar/20 11:25 AM,Back,,,DoeJ,16/Mar/20 8:27 AM,non
New Feature,Medium,ETAM-9817,81806,Back - Homepage - Slider vertical,*GlobalMarque,,In Progress,LENOBP01,LENOBP01,2.0,,ETAM-9242,ribeils,Sprint06.20-01/04-10,,,,,06/Mar/20 4:57 PM,11/Mar/20 11:56 AM,Back,,,DoeJ,16/Mar/20 5:54 PM,non
New Feature,Medium,ETAM-9327,80669,BACK - Valeur par dÃ©faut dans le country switcher aprÃ¨s changement de la locale,*GlobalMarque,,To Do,LENOBP01,LENOBP01,2.0,,ETAM-9745,LENOBP01,,,,,,27/Nov/19 11:09 AM,02/Dec/19 4:57 PM,Back,,,DoeJ,25/Feb/20 1:50 PM,non
Bug,Medium,ETAM-9609,81357,Front - Suppression rapide depuis panier KO - Maison 123,*1.2.3,Demandware,To Do,sellahm,sellahm,2.0,,ETAM-9745,bedoras,Sprint07.20-15/04-10,,,,,07/Feb/20 9:25 AM,14/Feb/20 4:38 PM,Front,,,DoeJ,13/Mar/20 5:59 PM,non
Bug,Medium,ETAM-9524,81008,"Front - iPad mode paysage, burger menu pas fixe ",*Etam,,Additional information required,ribeils,DoeJ,,,ETAM-9745,malanj,,,,,,10/Jan/20 4:54 PM,,Front,,,DoeJ,25/Feb/20 1:36 PM,non
New Feature,Medium,ETAM-9332,80677,"[FRONT] - Ajouter la police ""Satisfy"" sur ""edito"" dans le header - Maison 123",*1.2.3,Demandware,Additional information required,bedoras,DoeJ,1.0,,ETAM-9745,bedoras,,,,,,27/Nov/19 4:50 PM,,Front,,,DoeJ,25/Feb/20 2:23 PM,non
Bug,Medium,ETAM-9074,80179,Front - Header + selecteur de langue KO page 404,*Etam,,Additional information required,ribeils,meyronnf,,,ETAM-9745,demaye,,,,,,15/Oct/19 2:56 PM,13/Nov/19 3:04 PM,Front,,,DoeJ,25/Feb/20 2:10 PM,non
Task,Medium,ETAM-9638,81400,Back - Analyse - Search Einstein,*Etam,,Closed,pascalm,lefevrey,2.0,,ETAM-9745,pascalm,Sprint04.20-04/03-10,,,,,11/Feb/20 4:11 PM,28/Feb/20 2:57 PM,Back,,,DoeJ,28/Feb/20 2:57 PM,non
New Feature,Medium,ETAM-9516,80994,Front - Formulaires - Revoir les ISML des forms,*GlobalMarque,Demandware,waiting for QAT sur dev,brunierg,mariono,8.0,,ETAM-9629,pitancea,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,,09/Jan/20 4:35 PM,09/Jan/20 4:35 PM,Front,,,DoeJ,06/Mar/20 5:18 PM,non
New Feature,High,ETAM-9513,80990,Front - Formulaires - Structure des types de champs des formulaires ,*GlobalMarque,Demandware,waiting for QAT sur dev,brunierg,mariono,8.0,,ETAM-9629,pitancea,Sprint02.20-05/02-10,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint05.20-18/03-10,,09/Jan/20 2:35 PM,09/Jan/20 2:35 PM,Front,,,DoeJ,06/Mar/20 5:19 PM,non
New Feature,Medium,ETAM-9763,81739,Front - Formulaires - Gestion rÃ¨gle de validation formulaires,*GlobalMarque,Demandware,QAT SB,Eychenet,pitancea,5.0,,ETAM-9629,pitancea,Sprint06.20-01/04-10,,,,,26/Feb/20 3:12 PM,16/Mar/20 2:45 PM,Front,,,DoeJ,16/Mar/20 2:45 PM,non
New Feature,Medium,ETAM-9635,81396,Front - Formulaires - Validation des formulaires,*GlobalMarque,,QAT SB,Eychenet,pitancea,13.0,,ETAM-9629,ribeils,Sprint06.20-01/04-10,,,,,11/Feb/20 3:02 PM,16/Mar/20 2:42 PM,Front,,,DoeJ,16/Mar/20 2:42 PM,non
New Feature,Medium,ETAM-9864,81876,Front - Formulaires - Application sur page non refondue,*GlobalMarque,Demandware,To Do,derrouml,DoeJ,5.0,,ETAM-9629,pitancea,Sprint06.20-01/04-10,,,,,16/Mar/20 4:36 PM,16/Mar/20 5:07 PM,Front,,,DoeJ,17/Mar/20 9:52 AM,non
New Feature,Medium,ETAM-9515,80992,Front - Formulaires - Ajout de masques de saisies,*GlobalMarque,Demandware,To Do,derrouml,DoeJ,5.0,,ETAM-9629,pitancea,Sprint06.20-01/04-10,,,,,09/Jan/20 2:42 PM,09/Jan/20 2:42 PM,Front,,,DoeJ,17/Mar/20 9:51 AM,non
New Feature,Medium,ETAM-9863,81875,Front - Formulaires - Gestion Formulaire Identification,*GlobalMarque,Demandware,To Do,derrouml,DoeJ,3.0,,ETAM-9629,pitancea,Sprint06.20-01/04-10,,,,,16/Mar/20 4:29 PM,16/Mar/20 4:33 PM,Front,,,DoeJ,17/Mar/20 9:52 AM,non
New Feature,Medium,ETAM-9736,81646,Back - Formulaires - ClÃ©s des champs,*GlobalMarque,Demandware,Pending,ribeils,pitancea,,,ETAM-9629,pitancea,,,,,,21/Feb/20 7:28 PM,21/Feb/20 7:28 PM,Back,,,DoeJ,25/Feb/20 5:27 PM,non
New Feature,Medium,ETAM-9514,80991,Front - Formulaires - Validation des champs,*GlobalMarque,Demandware,PR Under Review,brunierg,derrouml,13.0,,ETAM-9629,pitancea,Sprint03.20-19/02-10,Sprint04.20-04/03-10,Sprint06.20-01/04-10,,,09/Jan/20 2:38 PM,09/Jan/20 2:38 PM,Front,,,DoeJ,13/Mar/20 7:19 PM,oui
New Feature,Medium,ETAM-9211,80516,RU/commande mode invitÃ© : message erreur tÃ©lÃ©phone invalide,*Etam,,Additional information required,pitancea,DoeJ,,,ETAM-9629,demaye,,,,,,13/Nov/19 3:58 PM,,Back,,,DoeJ,25/Feb/20 1:27 PM,non
New Feature,Medium,ETAM-9071,80173,FRONT - Changement libellÃ© DE,*1.2.3,Demandware,Additional information required,pitancea,DoeJ,,,ETAM-9629,bedoras,,,,,,14/Oct/19 6:04 PM,16/Dec/19 1:18 PM,Front,,,DoeJ,27/Feb/20 6:39 PM,non
Bug,Medium,ETAM-8922,79730,CrÃ©ation compte via rÃ©seau social sans adresse mail ko,*GlobalMarque,,Additional information required,pitancea,DoeJ,,,ETAM-9629,Eychenet,,,,,,06/Sep/19 5:18 PM,,Front,,,DoeJ,25/Feb/20 1:30 PM,non
Task,Medium,ETAM-8824,79523,Front - Analyse - Etendre l'utilisation gÃ©nÃ©rique de la tooltip CSS,*GlobalMarque,,Additional information required,pitancea,DoeJ,2.0,,ETAM-9629,perneyb,,,,,,14/Aug/19 3:15 PM,13/Nov/19 3:37 PM,Front,,,DoeJ,25/Feb/20 1:30 PM,non
New Feature,Medium,ETAM-8406,78708,NumÃ©ro de tel Suisse,*Etam,*GlobalMarque,Additional information required,pitancea,DoeJ,,,ETAM-9629,pascalm,,,,,,17/May/19 10:01 AM,,Front,,,DoeJ,25/Feb/20 1:31 PM,non
Bug,High,ETAM-9527,81100,Formulaires - Blocage de caractÃ¨res spÃ©ciaux,*GlobalMarque,,Additional information required,pitancea,brunierg,,,ETAM-9629,buffignl,Sprint02.20-05/02-10,Sprint01/3.20-22/01-10,Sprint03.20-19/02-10,,,11/Jan/20 11:39 AM,11/Jan/20 11:39 AM,Front,,,DoeJ,13/Mar/20 5:53 PM,non
Task,Medium,ETAM-9268,80602,Front - Formulaires - Audit Formulaires ,*GlobalMarque,Demandware,Closed,pitancea,perneyb,8.0,,ETAM-9629,pitancea,Sprint01/1.20-22/01-10,,,,,21/Nov/19 9:47 AM,04/Feb/20 6:11 PM,Front,,,DoeJ,11/Feb/20 2:45 PM,non
Task,Medium,ETAM-9267,80601,Back - Formulaires - Audit Formulaires ,*GlobalMarque,Demandware,Closed,pitancea,brunierg,5.0,,ETAM-9629,pitancea,Sprint01/1.20-22/01-10,,,,,21/Nov/19 9:24 AM,04/Feb/20 6:11 PM,Back,,,DoeJ,11/Feb/20 2:45 PM,non
New Feature,Medium,ETAM-9865,81877,Front - Formulaires - Gestion des diffÃ©rents types d'erreurs,*GlobalMarque,Demandware,In Progress,perneyb,perneyb,3.0,,ETAM-9629,pitancea,Sprint06.20-01/04-10,,,,,16/Mar/20 5:11 PM,16/Mar/20 5:13 PM,Front,,,DoeJ,17/Mar/20 9:57 AM,non
New Feature,Medium,ETAM-9406,80776,[FRONT] RÃ©gler l'affichage du Product Timer - Maison 123,*1.2.3,Demandware,Additional information required,pitancea,DoeJ,,,ETAM-9744,bedoras,,,,,,13/Dec/19 10:21 AM,,Front,,,DoeJ,25/Feb/20 2:25 PM,non
New Feature,Medium,ETAM-9213,80518,Back - Categ - Redirection vers une fiche produit,*GlobalMarque,,Additional information required,ribeils,DoeJ,,,ETAM-9744,ribeils,,,,,,14/Nov/19 10:59 AM,,Back,,,DoeJ,25/Feb/20 1:47 PM,non
New Feature,Medium,ETAM-8461,78789,Front - Nouvelle fiche produit - Auto select my size,*GlobalMarque,,Additional information required,perneyb,mariono,3.0,,ETAM-9744,autiea,Sprint11.19-10/07-10,,,,,24/May/19 2:52 PM,06/Jun/19 4:03 PM,Front,,,DoeJ,25/Feb/20 1:29 PM,non
Bug,Medium,ETAM-8335,78568,Front - Produit - Bug affichage paysage/portrait,*GlobalMarque,,Additional information required,ribeils,ribeils,5.0,,ETAM-9744,sauratf,,,,,,29/Apr/19 6:37 PM,02/May/19 3:57 PM,Front,,,DoeJ,25/Feb/20 1:47 PM,
New Feature,Medium,ETAM-8673,79101,Font - Produit - Animation sur les pictos,*GlobalMarque,,Additional information required,priourm,DoeJ,2.0,,ETAM-9744,priourm,,,,,,12/Jul/19 4:32 PM,19/Jul/19 10:17 AM,Front,,,DoeJ,25/Feb/20 2:03 PM,non
New Feature,High,ETAM-9692,81471,Conversion des tailles pour les pays,*GlobalMarque,,Additional information required,ribeils,DoeJ,,,ETAM-9744,demaye,,,,,,17/Feb/20 5:48 PM,,Front,,,DoeJ,25/Feb/20 2:38 PM,non
Bug,Medium,ETAM-9555,81157,UND - JCO - Analyse gestion titre / H1 catÃ©gorie,*Undiz,,Backlog,pitancea,DoeJ,,,ETAM-9746,couchyj,,,,,,20/Jan/20 3:50 PM,,Back,,,DoeJ,25/Feb/20 2:33 PM,non
Task,Medium,ETAM-9437,80811,Front - Globalmarques - Chargement CSS diffÃ©rÃ© page produit/ page categ,*GlobalMarque,Demandware,Additional information required,ribeils,DoeJ,3.0,,ETAM-9746,pitancea,,,,,,18/Dec/19 11:42 AM,18/Dec/19 11:49 AM,Front,,,DoeJ,25/Feb/20 2:03 PM,non
New Feature,Medium,ETAM-9011,80008,Front - Categ - Page de recherche - Cross sell Zero result cross sell,*GlobalMarque,,Additional information required,ribeils,ribeils,2.0,,ETAM-9746,sauratf,,,,,,25/Sep/19 11:26 AM,25/Sep/19 11:27 AM,Front,,,DoeJ,25/Feb/20 2:07 PM,non
Bug,High,ETAM-8826,79525,Back - Page Categ - Tailles indispo remontent,*GlobalMarque,,Additional information required,brunierg,DoeJ,2.0,,ETAM-9746,autiea,,,,,,16/Aug/19 10:42 AM,19/Aug/19 11:01 AM,Back,,,DoeJ,25/Feb/20 1:38 PM,non
New Feature,Medium,ETAM-9600,81329, Dev d'un carroussel cross-sell sur page les pages NO RESULTS + page 404,*Etam,,Additional information required,ribeils,DoeJ,,,ETAM-9746,pascalm,,,,,,03/Feb/20 2:34 PM,,Front,,,DoeJ,25/Feb/20 1:58 PM,non
New Feature,Medium,ETAM-9806,81791,Front - Categ - Revu du quick add to cart desktop,*GlobalMarque,,To Release,brunierg,perneyb,3.0,,ETAM-9746,ribeils,Sprint05.20-18/03-10,,,,,05/Mar/20 6:38 PM,12/Mar/20 7:10 PM,Front,ETAM_20_03_05 (RD 18/03),,DoeJ,12/Mar/20 7:10 PM,oui
Go !