## Chantier
Liste Chantiers | Prix | % sur chantier | Phase | % Avancement |  | Heures étude restantes | Plannification chantier
[7 empty] | OS | Fin de chantier | Livraison
Pont | 403527.9 | 100 |  | 77.5713 | -22.43% | 150.8432 | XX | 20 | 25
Mission 1 | 67460 | 16.7176 | FAB | 16.7176 | 0% | 0
Mission 2 | 1926.8 | 0.47749 | PR+ | 0.14325 | -70% | 2.2479
Mission 3 | 2987 | 0.74022 | PR+ | 0.22207 | -70% | 3.4848
Mission 4 | 10905 | 2.7024 | PR | 0.27024 | -90% | 16.3575
Mission 5 | 26792.1 | 6.6395 | PR+ | 1.9918 | -70% | 31.2575
Mission 6 | 5383 | 1.334 | PR | 0.1334 | -90% | 8.0745
Mission 7 | 228460 | 56.6157 | FAB | 56.6157 | 0% | 0
Mission 8 | 45680 | 11.3202 | PR | 1.132 | -90% | 68.52
Mission 9 | 13934 | 3.453 | PR | 0.3453 | -90% | 20.901
Parking | 526239 | 100 |  | 92.6764 | -7.324% | 64.2329 | XX | 14 | 19
Mission 1 | 163438.5 | 31.0578 | FAB | 31.0578 | 0% | 0
Mission 2 | 20064.5 | 3.8128 | EXE | 1.9064 | -50% | 16.7204
Mission 3 | 6144 | 1.1675 | FAB | 1.1675 | 0% | 0
Mission 4 | 72340 | 13.7466 | FAB | 13.7466 | 0% | 0
Mission 5 | 8243 | 1.5664 | FAB | 1.5664 | 0% | 0
Mission 6 | 83504 | 15.8681 | FAB | 15.8681 | 0% | 0
Mission 7 | 37765 | 7.1764 | FAB | 7.1764 | 0% | 0
Mission 8 | 31675 | 6.0191 | PR | 0.60191 | -90% | 47.5125
Mission 9 | 51440 | 9.775 | FAB | 9.775 | 0% | 0
Mission 10 | 4440 | 0.84372 | FAB | 0.84372 | 0% | 0
Mission 11 | 3240 | 0.61569 | FAB | 0.61569 | 0% | 0
Mission 12 | 23040 | 4.3782 | FAB | 4.3782 | 0% | 0
Mission 13 | 10360 | 1.9687 | FAB | 1.9687 | 0% | 0
Mission annexe | 10545 | 2.0038 | FAB | 2.0038 | 0% | 0
Batiment Publique | 908202.4 | 100 |  | 44.4165 | -55.58% | 841.3517 | XX | 12 | 17
Mission 1 | 32297.4 | 3.5562 | FAB | 3.5562 | 0% | 0
Mission 2 | 56000 | 6.166 | FAB | 6.166 | 0% | 0
Mission 3 | 154315 | 16.9913 | FAB | 16.9913 | 0% | 0
Mission 4 | 41624 | 4.5831 | 0 | 0 | -100% | 69.3733
Mission 5 | 79186 | 8.719 | 0 | 0 | -100% | 131.9767
Mission 6 | 17500 | 1.9269 | PR | 0.19269 | -90% | 26.25
Mission 7 | 36549 | 4.0243 | FAB | 4.0243 | 0% | 0
Mission 8 | 9600 | 1.057 | PR | 0.1057 | -90% | 14.4
Mission 9 | 2160 | 0.23783 | FAB | 0.23783 | 0% | 0
Mission 10 | 10071 | 1.1089 | FAB | 1.1089 | 0% | 0
Mission 11 | 13570 | 1.4942 | PR | 0.14942 | -90% | 20.355
Mission 12 | 22100 | 2.4334 | PR+ | 0.73001 | -70% | 25.7833
Mission 13 | 114720 | 12.6315 | PR | 1.2632 | -90% | 172.08
Mission 14 | 52200 | 5.7476 | FAB | 5.7476 | 0% | 0
Mission 15 | 203050 | 22.3574 | 0 | 0 | -100% | 338.4167
Mission 16 | 12000 | 1.3213 | FAB | 1.3213 | 0% | 0
Mission 17 | 51260 | 5.6441 | EXE | 2.8221 | -50% | 42.7167
Tunnel | 550313 | 100 |  | 5.1326 | -94.87% | 870.1125 | XX | 29 | 34
Mission 1 | 56000 | 10.176 | 0 | 0 | -100% | 93.3333
Mission 2 | 116258 | 21.1258 | 0 | 0 | -100% | 193.7633
Mission 3 | 95600 | 17.3719 | 0 | 0 | -100% | 159.3333
Mission 4 | 169900 | 30.8733 | PR | 3.0873 | -90% | 254.85
Mission 5 | 112555 | 20.4529 | PR | 2.0453 | -90% | 168.8325
Tunnel 2 | [6 empty] | XX | XX | XX
Revetement sol | 573783.2 | 100 |  | 18.5624 | -81.44% | 778.7924 | XX | 40 | 45
Mission 1 | 45830 | 7.9873 | PR | 0.79873 | -90% | 68.745
Mission 2 | 95200 | 16.5916 | PR+ | 4.9775 | -70% | 111.0667
Mission 3 | 77214 | 13.457 | PR+ | 4.0371 | -70% | 90.083
Mission 4 | 111634 | 19.4558 | PR+ | 5.8367 | -70% | 130.2397
Mission 5 | 30311.2 | 5.2827 | PR+ | 1.5848 | -70% | 35.3631
Mission 6 | 9226 | 1.6079 | PR+ | 0.48238 | -70% | 10.7637
Mission 7 | 16164 | 2.8171 | PR+ | 0.84513 | -70% | 18.858
Mission 8 | 9988 | 1.7407 | 0 | 0 | -100% | 16.6467
Mission 9 | 96016 | 16.7338 | 0 | 0 | -100% | 160.0267
Mission 10 | 77000 | 13.4197 | 0 | 0 | -100% | 128.3333
Mission 11 | 1500 | 0.26142 | 0 | 0 | -100% | 2.5
Mission 12 | 3700 | 0.64484 | 0 | 0 | -100% | 6.1667

## Calendrier
CHANTIER | Avancement chantier | Semaine 38 |  |  |  |  | SEPTEMBRE 2017 | [20 empty] | OCTOBRE 2017 | [21 empty] | NOVEMBRE 2017 | [21 empty] | DECEMBRE 2017 | [20 empty] | JANVIER 2018 | [22 empty] | FEVRIER 2018 | [19 empty] | MARS 2018 | [21 empty] | AVRIL 2018 | [20 empty] | MAI 2018 | [22 empty] | JUIN 2018 | [20 empty] | JUILLET 2018 | [21 empty] | AOUT 2018 | [22 empty] | SEPTEMBRE 2018 | [19 empty] | OCTOBRE 2018 | [22 empty] | NOVEMBRE 2018
[8 empty] | Semaine n° |  |  |  | 36 | Semaine n° |  |  |  | 37 | Semaine n° |  |  |  | 38 | Semaine n° |  |  |  | 39 | Semaine n° |  |  |  | 40 | Semaine n° |  |  |  | 41 | Semaine n° |  |  |  | 42 | Semaine n° |  |  |  | 43 | Semaine n° |  |  |  | 44 | Semaine n° |  |  |  | 45 | Semaine n° |  |  |  | 46 | Semaine n° |  |  |  | 47 | Semaine n° |  |  |  | 48 | Semaine n° |  |  |  | 49 | Semaine n° |  |  |  | 50 | Semaine n° |  |  |  | 51 | Semaine n° |  |  |  | 52 | Semaine n° |  |  |  | 1 | Semaine n° |  |  |  | 2 | Semaine n° |  |  |  | 3 | Semaine n° |  |  |  | 4 | Semaine n° |  |  |  | 5 | Semaine n° |  |  |  | 6 | Semaine n° |  |  |  | 7 | Semaine n° |  |  |  | 8 | Semaine n° |  |  |  | 9 | Semaine n° |  |  |  | 10 | Semaine n° |  |  |  | 11 | Semaine n° |  |  |  | 12 | Semaine n° |  |  |  | 13 | Semaine n° |  |  |  | 14 | Semaine n° |  |  |  | 15 | Semaine n° |  |  |  | 16 | Semaine n° |  |  |  | 17 | Semaine n° |  |  |  | 18 | Semaine n° |  |  |  | 19 | Semaine n° |  |  |  | 20 | Semaine n° |  |  |  | 21 | Semaine n° |  |  |  | 22 | Semaine n° |  |  |  | 23 | Semaine n° |  |  |  | 24 | Semaine n° |  |  |  | 25 | Semaine n° |  |  |  | 26 | Semaine n° |  |  |  | 27 | Semaine n° |  |  |  | 28 | Semaine n° |  |  |  | 29 | Semaine n° |  |  |  | 30 | Semaine n° |  |  |  | 31 | Semaine n° |  |  |  | 32 | Semaine n° |  |  |  | 33 | Semaine n° |  |  |  | 34 | Semaine n° |  |  |  | 35 | Semaine n° |  |  |  | 36 | Semaine n° |  |  |  | 37 | Semaine n° |  |  |  | 38 | Semaine n° |  |  |  | 39 | Semaine n° |  |  |  | 40 | Semaine n° |  |  |  | 41 | Semaine n° |  |  |  | 42 | Semaine n° |  |  |  | 43 | Semaine n° |  |  |  | 44 | Semaine n° |  |  |  | 45 | Semaine n° |  |  |  | 46 | Semaine n° |  |  |  | 47 | Semaine n° |  |  |  | 48
 | time axis 2017-09-01 to 2018-11-30
[7 empty] | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj | jjjj
[7 empty] | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj | Jj
|  | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22
Pont | 78%
Parking | 93%
Revetement sol | 19%
Batiment Publique | 44%
Tunnel | 5%
Tunnel 2 | ?

## Données (hidden)
0
PR
PR+
EXE
FAB