## Feuil1
Last Update : |  |  | 2018-03-26 |  |  | Version Beta |  |  |  |  | Thompson Programs
Program Characteristics | [10 empty] | Program monitoring | [13 empty] | ECU Caracteristics |  |  |  |  | Done
Customer Program number | Program number (PGA) | Customer Interlocutor | In charge PM | name of the Airline | Airline Code | Plane type | Seat | Shipset | PAX per ship | TOTAL PAX | Status | Main Programm Markers | [9 empty] | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | Parameters Version | In charge Develloper
[12 empty] | ITCM | ITCM Validation | PDR | PDR Validation | CDR | CDR Validation | FAI | FAI Validation | ODD | ODD Validation
VT xxx | PJ 10xx | M.XXXXXX | XXY | XWY Air Travel | XWY | B787 | VNTR | 17 | 70 | 1190 | GOING | 2018-04-05 |  | 2018-04-12 |  | 2018-05-29 |  | 2018-06-15 |  | 2018-07-02 | Done | OVER | GOING | GOING | GEN 7 | P78xxx | V32.xxx | VT01xx | XWX
VT xyz | PJ 10yz | M.XXXXXX | WXW | TWA Airlines | TWA | A321 | VNTR | 19 | 20 | 380 | GOING | 2018-03-25 | Done | 2018-06-25 |  | 2018-07-21 |  | 2018-08-16 |  | 2018-09-11 |  | GOING | GOING | GOING | 3600 | P78xyx | V32.xyz | VT01xy | XYZ
VT yyx | PJ 10yx | M.XXXXXX | XVZ | WTZ Airlines | WTZ | B747 | VNTR | 5 | 75 | 375 | CLOSED | 2018-04-07 |  | 2018-04-25 |  | 2018-05-21 |  | 2018-06-03 |  | 2018-06-16 |  | OVER | OVER | OVER | GEN 7 | P78xzx | V32.zyz | VT01xz | WZX | GOING
VT zxz | PJ 10xz | M.XXXXXX | ZYW | WWZ Air | WWZ | A330 | VNTR | 15 | 50 | 750 | GOING | 2018-04-08 |  | 2018-03-21 |  | 2018-03-21 |  | 2018-03-21 |  | 2018-03-21 |  | OVER | LATE | LATE | 3600 | P78xyz | V32.yyy | VT01yy | XXX | CLOSED
Bouton 3