## Thompson
Last Update : | 2018-04-24 | By CAI | [8 empty] | Thompson Programs
Program Characteristics | [12 empty] | Program monitoring | [11 empty] | NRC | [5 empty] | ECU Caracteristics
Program Name | PJ | Customer Interlocutor email | Creation year | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | SS qty | PAX per SS | TOTAL PAX | Status | SS1 Delivery year | Main Programm Markers | [9 empty] | BL PDR |  | BL CDR |  | End of Project Billing |  | ECU Generation | ECU PN | Soft | Dev
[15 empty] | ITCM |  | PDR |  | CDR |  | FAI |  | ODD
VT26 | PJ0793 | lorraine.mckay@thompsonaero.com | 2016 | GHT | FCH | China Eastern Airline | CES | A330-300 | VTXL | 18 | 28 | 504 | STANDBY | 2016 | N/A | Done | 2016-04-20 | Done | 2016-11-08 | Done | 2016-12-13 | Done | N/A | Done | 2016-04-20 | Done | 2016-11-08 | Done | N/A | Done | ECU 3100 | P78624A460 | V32.148x | N/A
VT27 | PJ0794 | Katie.McGovern@thompsonaero.com | 2016 | RPT | SDN | Delta | DAL | B777 | VTXL | 15 | 32 | 480 | CLOSED | 2016 | N/A | Done | 2016-06-29 | Done | 2016-08-03 | Done | 2016-08-01 | Done | N/A | Done | 2016-06-29 | Done | 2016-08-03 | Done | N/A | Done | ECU Gen7 | P78700M140 | V40.162 | N/A
VT28 | PJ0795 | Leeanne.Managh@thompsonaero.com | 2016 | GHT | FCH | Phillipines Airlines | PAL | A330-300 | VTXL | 7 | 18 | 126 | CLOSED | 2017 | N/A | Done | 2016-07-04 | Done | 2016-09-27 | Done | 2017-02-09 | Done | N/A | Done | 2016-07-04 | Done | 2016-09-27 | Done | N/A | Done | ECU 3100 | P78624A450 | V32.1492 | N/A
VT29 | PJ0864 | Marc.Montgomery@thompsonaero.com | 2016 | RPT | SDN | Eva Air | EVA | B787 | VTXL | 24 | 32 | 784 | GOING | 2018 | N/A | Done | 2016-10-11 |  | 2017-05-02 | Done | 2018-05-01 |  | 2017-10-04 |  | 2016-10-11 |  | 2017-05-02 | Done | 2017-10-04 |  | ECU Gen7 | P78700M210 | V40.232
VT30 | PJ0810 | Dianne.Taylor@thompsonaero.com | 2016 | FFS | SDN | FlyDubai | FDB | B737 | VTXL | 8 | 10 | 80 | CLOSED |  | N/A | Done | 2016-10-19 | Done | 2018-03-30 | Done | 2017-09-28 | Done | 2017-07-30 | Done | 2018-04-28 | Done | 2018-04-28 | Done | 2018-04-28 | Done | ECU 3600 | P78635B170 | V35.312 | N/A
VT30-2 | PJ0810 | Orla.Odonnell@thompsonaero.com | 2016 | FFS | SDN | FlyDubai | FDB | B738 | VTXL |  |  |  | CLOSED |  | N/A | Done | 2018-04-29 | Done | 2018-04-29 | Done | 2018-04-29 | Done | 2018-04-29 | Done | 2018-04-29 | Done | 2018-04-29 | Done | 2018-04-29 | Done |  |  |  | N/A
VT31 | PJ0867 | Ryan.Teggart@thompsonaero.com | 2016 | GHT | FCH | Latam | CES | A350-900 | VTXL | 5 | 15 | 80 | GOING |  | N/A | Done | 2016-11-29 | Done | 2017-07-25 | Done | 2018-03-21 |  | N/A |  | 2016-11-29 | Done | 2017-07-25 | Done |  |  | ECU Gen7 | P78700M230 | V40.26x
VT32 | PJ0868 | lorraine.mckay@thompsonaero.com | 2016 | GHT | FCH | China Eastern Airline | CES | A350-900 | VTXL | 20 | 36 | 720 | GOING |  | N/A | Done | 2016-11-30 | Done | 2017-07-26 | Done | 2018-02-22 |  | N/A |  | 2016-11-30 | Done | 2017-07-26 | Done |  |  | ECU Gen7 | P78700M240 | V40.27x
VT33 | PJ0869 | Ryan.Teggart@thompsonaero.com | 2016 | GHT | FCH | China Eastern Airline | CES | B787 | VTXL | 4 | 15 | 60 | GOING |  | N/A | Done | 2016-11-15 | Done | 2017-06-20 | Done | 2018-01-09 |  | N/A |  | 2016-11-15 | Done | 2017-06-20 | Done |  |  | ECU Gen7 | P78700M250 | V40.28x
VT34 | PJ0870 | lorraine.mckay@thompsonaero.com | 2016 | GHT | FCH | China Eastern Airline | CES | B787 | VTXL | 6 | 30 | 180 | GOING |  | N/A | Done | N/A | Done | N/A | Done | N/A |  | N/A |  | N/A | Done | N/A | Done |  |  | ECU Gen7 | P78700M260 | V40.29x
VT35 | PJ0871 | Leeanne.Managh@thompsonaero.com | 2016 | GHT | FCH | Phillipines Airlines | PAL | A350-900 | VTXL | 6 | 30 | 180 | STANDBY |  | N/A | Done | 2018-05-04 | Done | 2018-05-04 | Done | 2018-05-04 | Done | 2018-05-04 | Done | 2018-05-04 | Done | 2018-05-04 | Done | 2018-05-04 | Done | ECU Gen7 | P78700M220 | V40.242 | N/A
VT36 | PJ0865 | Orla.Odonnell@thompsonaero.com | 2016 | RPN | SDN | Swiss Air | SWR | A340-300 | VTLB | 5 | 8 | 40 | GOING |  | 2018-05-18 | Done | 2017-01-18 |  | 2017-08-02 |  | 2018-08-23 |  | 2018-02-16 |  | 2017-01-18 |  | 2017-08-02 |  | 2018-02-16 |  | ECU Gen7 (x2) | P78700M290 P78700M300 | v40.32x v40.37x
VT37 | PJ0866 | Suz.Graham@thompsonaero.com | 2016 | RPN | GDN | Swiss Air | SWR | A340-300 | VNT2 | 5 | 47 | 235 | GOING |  | 2017-03-18 | Done | 2017-01-18 |  | 2017-07-31 |  | 2018-02-07 |  | 2018-02-16 |  | 2017-01-18 |  | 2017-07-31 |  | 2018-04-01 |  | ECU 3100 | P78624A470 | v32.152x
VT38 | PJ0903 | Jessica.Kingsnorth@thompsonaero.com | 2016 | RPT | TGX | China Southern Airlines | CSN | B787 | VTXL | 20 | 28 | 560 | CLOSED |  | N/A | Done | 2016-12-13 | Done | 2017-03-07 | Done | 2107-11-30 | Done | 071801/2018 | Done | 2018-05-07 | Done | 2018-05-07 | Done | 2018-05-07 | Done | ECU Gen7 | P78700M270 | V40.31x | N/A
VT39 | PJ0937 | Shaun.Cawood@thompsonaero.com | 2017 | GSR | JBG | Iran Airlines | IRA | B777 | VTXL | N/A | N/A |  | STANDBY |  | N/A | Done | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  |  | ECU 3600 | P78635B180 | v35.32x
VT40 | PJ0945 | Shaun.Cawood@thompsonaero.com | 2017 | GSR | JBG | Iran Airlines | IRA | A330 | VTXL | N/A | N/A |  | STANDBY |  | N/A | Done | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  |  | ECU 3100 | P78624A480 | v32.153x
VT41 | PJ0996 | l | 2017 | RPN | GDN | Thai Airways | THA | A330 | VNT2 | 3 | 31 | 93 | CLOSED |  | N/A | Done | 2017-03-28 | Done | 2017-07-25 | Done | 2017-12-11 | Done | 2017-10-31 | Done | 2017-03-28 | Done | 2017-07-25 | Done | 2017-10-31 | Done | ECU 3100 | P78624A490 | v32.154x | N/A
VT42 | PJ0989 | Dianne.Taylor@thompsonaero.com | 2017 | RPN | GDN | Air Portugal | TAP | A321 | VNT2 | 12 | 44 | 528 | GOING |  | N/A | Done | - |  | 2017-11-28 |  | 2018-05-04 |  | 2018-07-30 |  | - |  | 2017-11-28 |  | 2018-07-30 |  | ECU Gen7 | P78700M350 | v40.43x
VT43 | PJ1030 | Wanda.Chan@thompsonaero.com | 2017 | HD1 | MMR | Latam | TAM | A350 | VTXL | 44 | 16 | 704 | GOING |  | N/A | Done | 2018-03-01 | Done | 2018-10-04 |  | 2019-06-19 |  | 2019-09-02 |  | 2018-03-01 |  | 2018-10-04 |  | 2019-09-02 |  | ECU Gen7 | P78700M380 | v40.46x
VT44 | PJ1003 | Niall.Nolan@thompsonaero.com | 2017 | RPT | SDN | Delta | DAL | A330 | VTXL | 25 | 29 | 725 | GOING |  | N/A | Done | 2017-08-01 | Done | 2018-02-27 | Done | 2018-09-11 |  | 2018-10-14 |  | 2017-08-01 | Done | 2018-02-27 | Done | 2018-10-14 |  | ECU Gen7 | P78700M370
VT45 | PJ1000 | Niall.Nolan@thompsonaero.com | 2017 | RPT | SDN | Delta | DAL | B767 | VTXL | 21 | 34 | 714 | GOING |  | N/A | Done | 2017-06-13 | Done | 2017-02-13 | Done | 2018-06-26 |  | 2018-09-12 |  | 2017-06-13 | Done | 2017-02-13 | Done | 2018-09-12 |  | ECU Gen7 | P78700M330 | V40.39x
VT46 | PJ1018 | Wanda.Chan@thompsonaero.com | 2017 | RPT | MMR | Azerbaijan Airlines | AHY | B737 | VNT2 | 4 | 16 | 64 | GOING |  | N/A | Done | 2017-09-07 | Done | 2018-06-11 |  | 2018-11-02 |  | 2017-07-10 |  | 2017-09-07 | Done | 2017-05-18 | Done | 2017-07-10 |  | ECU Gen7 | P78700M360 | V40.44x
VT47 | PJ1027 | Shaun.Cawood@thompsonaero.com | 2017 | RPN | GDN | Juneyao Airlines | DKH | B787 | VTXL | 10 | 29 | 290 | GOING |  | N/A | Done | 2017-11-15 |  | 2018-04-03 |  | 2018-08-08 |  | 2018-09-15 |  | 2017-08-16 |  | 2017-01-09 |  | 2018-05-26 |  | ECU Gen7 | P78700M340 | v40.40x
VT48 | PJ1028 | Jessica.Kingsnorth@thompsonaero.com | 2017 | GSR | JBG | Scandinavian Airlines | SAS | A350 | VTXL |  | 40 |  | GOING |  | N/A | Done |  |  | 30/2018 | Done | 2018-01-29 | Done | 2018-05-17 | Done | 2018-05-17 | Done | 2018-05-17 | Done | 2018-05-17 | Done | ECU Gen7 | P78700M410 | v40.49x | N/A
VT49 | PJ1045 | Erinn.McMahon@thompsonaero.com | 2017 | HD1 | MMR | Latam | TAM | B777 | VTXL | 5 | 38 | 190 | GOING |  | N/A | Done | 2017-11-15 |  | 2017-04-03 |  | 2017-08-08 |  | 2018-09-15 |  | 2017-11-15 |  | 2017-04-03 |  | 2018-09-15 |  | ECU Gen7 | P78700M390 | v40.47x
VT50 | PJ1046 | Wanda.Chan@thompsonaero.com | 2017 | HD1 | MMR | Latam | TAM | B767 | VTXL | 8 | 30 | 240 | GOING |  | N/A | Done | 2017-10-25 |  | 2018-03-06 |  | 2018-08-13 |  | 2018-09-21 |  | 2017-10-25 |  | 2018-03-06 |  | 2018-09-21 |  | ECU Gen7 | P78700M400 | v40.48x
VT53 | PJ1052 | Dianne.Taylor@thompsonaero.com | 2017 | RPN | GDN | Air Astana | KZR | A321 | VNT2 | N/A | N/A |  | GOING |  | N/A | Done | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2018-05-02 |  | ECU Gen7 | P78700Mxxx | V40.xxx
VT54 | PJ1071 | Wanda.Chan@thompsonaero.com | 2017 | GSR | JBG | Brussels Airlines | BEL | A330 | VNT2 | 7 | 30 | 210 | GOING | 2018 | N/A | Done | 2017-10-25 |  | 2017-03-06 |  | 2018-08-13 |  | 2018-09-21 |  | 2017-10-25 |  | 2017-03-06 |  | 2018-09-21 |  | ECU3100 | P78624Axxx | v32.xxx
VT55 | PJ1092 | Dianne.Taylor@thompsonaero.com | 2017 | RPT | TGX | Qantas | QFA | A380 | VTXL | 12 | 70 | 840 | GOING | 2019 | N/A | Done | 2018-01-09 |  | 2018-05-29 |  | 2019-01-08 |  | - |  | 2018-01-09 |  | 2018-05-29 |  | -
VT56 | PJ1111 | Dianne.Taylor@thompsonaero.com | 2017 | RPT | TGX | Air Lingus | EIN | A321 | VNT2 | 7 | 16 | 112 | GOING | 2018 | N/A | Done | 2017-01-16 |  | 2018-06-26 |  | 2018-12-18 |  | 2019-02-01 |  | 2017-01-16 |  | 2018-06-26 |  | 2019-02-01 |  | ECU Gen7 | P78700M430 | v40.50x
VS01 | PJ1135 | Aaron.McLaughlin@thompsonaero.com | 2018 | RPN | GDN | JetBlue | JBU | A321 | Solo | 15 | 16 | 240 | GOING | 2019 | N/A | Done | 2018-03-05 | Done | 2018-08-06 | Done | 2019-04-29 | Done | 2019-06-18 | Done | 2018-03-05 | Done | 2018-08-06 | Done | 2019-06-18 | Done | ECU Gen7 | P78700M460 | v40.53x | N/A

## Rockwell Aerospace
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Rockwell Aerospace Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
|  |  | MQR | GDN |  | BAW | A350 | SFC | 20 | 8 | 160 | GOING | N/A | 42991 | 42822 | 43129 | 43181 | 2017-09-13 | 2017-03-28 |  | N/A | P78700M000 | V40
CLOSED
|  |  | MQR | GDN |  | CSC | A330-A300 | HVH | 3 | 24 | 72 | CLOSED | N/A | N/A | 42705 | N/A | N/A | N/A | 2016-12-01 |  | N/A | N/A | N/A |  | ECU 3100
|  |  | MQR | GDN |  | CSZ | A330-A300 | HVH | 6 | 18 | 108 | GOING | N/A | N/A | 42675 | N/A | 42917 | N/A | 2016-11-01 |  | N/A | N/A | N/A |  | ECU 3600
ECU Gen 7
|  |  | MNI | GDN |  |  | B787 | SERENITY |  |  |  |  | N/A | 42670 | 42807 | 43019 | N/A | [7 empty] | ECU Gen VII
|  |  | GHT | FCH |  |  | B737-8 Max | [5 empty] | N/A | 42621 | 42723 | 42984 | 43101 | [7 empty] | ECU Gen V
|  |  | RPN | GDN |  | JAL | A350 | FC | 11 | 12 | 132 |  | N/A | xx/05/2017 | xx/12/2017 | xx/06/2018 | N/A
|  |  | DCE | SDN |  | CHH | B787-9 | SDIAM | 9 | 26 | 234 |  | N/A | 42956 | 43037 | 43355 | N/A | 2017-08-09 | 2017-10-29 |  | N/A | N/A | N/A
|  |  | DCE | JBG |  | BAW | B777 | SDIAM | 27 | N/A |  | GOING | N/A | 43146 | 43263 | 43580 | N/A | 2018-02-15 | 2018-06-12 |  | N/A | N/A | N/A
[7 empty] | B787 | SDIAM |  |  |  |  | N/A | 43146 | 43263 | 43299 | 43580
|  |  | DCE | SDN |  | AFL | A350 | BC | 28 | 28 | 784 | GOING | N/A | 43217 | 43312 | 43626 | 43647 | 2018-04-27 | 2018-07-31 |  | N/A | N/A | N/A
N/A
|  |  | DCE | SDN |  |  | B787-9 |  | 4 | 30 | 120 | GOING | N/A | 43145 | 43237 | 43537 | N/A
|  |  | DCE | SDN | [8 empty] | N/A
|  |  | DCE | SDN |  |  | b787-9 | SDIAM | 6 | 30 | 180 |  | N/A | 43165 | 43243 | 43400
l

## Stelia Aerospace
Last Update : | 2018-04-24 | By CAI |  |  |  |  | 0 |  |  | Stelia Aerospace Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ1097 | Nicolas.Martinak@stelia-aerospace.com | CVU | VRX | Air Senegal | SNG | A330-900 | OPAL | 2 | 52 | 104 | GOING |  | N/A | 2017-03-20 | N/A | 2018-10-01 | N/A | 2017-03-20 |  | N/A | N/A | N/A |  | GOING
| PJ1007 | jean-francois.soulard@stelia-aerospace.com | CVU | VRX | Air Mauritius | MAU | A330-A340 | SOLSTYS | 4 (2x A330 + 2x A340) | 18 par A330 et 28 par A340 |  | GOING |  | TBD | TBD | TBD | TBD | TBD | TBD |  | N/A | P78624M71 | V32.534x |  | CLOSED
| PJ1113 | mathilde.frenais@stelia-aerospace.com | CVU | VRX | Géneric | N/A | AIRBUS/BOEING | CELESTE | TBD | TBD |  | GOING |  | TBD | TBD | TBD | TBD | TBD | TBD |  | N/A | N/A | N/A |  | ECU 3100
| PJ1031 | cyril.barrier@stelia-aerospace.com | CVU | VRX | Air Mauritius | MAU | A330-900 Neo | SOLSTYS | 2 | 28 | 56 | GOING |  | NC | NC | NC | NC | NC | NC |  | N/A | P78624M171 | V32.534x |  | ECU 3600
| PJ0968 | Benoit.cymbor@stelia-aerospace.com | CVU | VRX | Air Berlin | BER | A330-900 | SOLSTYS | 2 | 29 | 58 | GOING |  | TBD | TBD | TBD | 2017-08-23 | TBD | TBD |  | N/A | P78624M171 | V32.534x |  | ECU 3601
| PJ0814 | N/A | NMI | GDN | Iberia Lineas Aereas de Espana | IBE | A350 | SOLSTYS | N/A | N/A |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | P78700M010 | N/A |  | ECU 3602
| PJ0744 | pascal.carretero@stelia-aerospace.com | NMI | GDN | Singapore Ailines | SIA | B787 | SYMP | N/A | N/A |  | GOING |  | 2015-04-25 | 2016-10-10 | 2017-03-22 | TBC | 2015-04-25 | 2016-10-10 |  | GENVII | P78700M110 | V40.13x |  | ECU 3603
ECU 3604

## Jamco
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Jamco Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ0882 | andrew_cheung@jamco-america.com | RPN | GDN | Royal Dutch Airlines | KLM | B787 | VNTR | 7 | 38 | 266 | GOING |  | 2017-10-31 | 2018-03-01 | 2018-09-01 | 2018-11-27 | 2017-10-31 | 2018-03-10 |  | Gen 7 | P78700M320 | V40.xx |  | GOING
| PJ0962 | kenji_nojiri@jamco‐america.com | RPN | GDN | Japan Airlines | JAL | A350 | FC | 11 | 12 | 132 | GOING |  | 2017-05-01 | 2017-12-01 | 2017-06-01 | N/A | 2017-05-01 | 2017-12-01 |  | N/A | N/A | N/A
| PJ1106 | Jianqi_Yang@jamco‐america.com | RPN | GDN | Japan Airlines | JAL | B787 | N/A | N/A | N/A |  | GOING |  | 2018-01-01 | 2018-07-01 | 2019-05-01 | N/A | 2018-07-01 | 2018-07-01 |  | N/A | N/A | N/A
| PJ1165 | Helio_Nakassa@jamco-america.co | RPN | GDN | Air Europa | AEA | B787-9 | VNTR | 12 | 32 | 384 | GOING |  | 2018-06-12 | 2018-09-27 | 2019-05-05 | 2019-07-11 | 2018-06-12 | 2018-09-27 |  | GEN VII | P78700M480 | v40.55x
ECU Gen VII
ECU Gen V

## Zodiac Seats France
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Zodiac Seats France Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJxxxxx | Frederic.Parage@zodiacaerospace.com | CVU | VRX | Air Mauritius | MAU | A350 | MAJISTY | TBD | TBD |  | GOING |  | 2017-03-31 | TBD | TBD | TBD | 2017-03-31 | TBD |  | N/A | N/A | N/A |  | GOING
| PJ01126_04 | N/A | CVU | VRX | Cathay Pacific | CPA | A350 | CIRRUS | N/A | N/A |  | GOING |  | N/A | N/A | N/A | Decembre 2015 | N/A | N/A |  | N/A | N/A | N/A |  | CLOSED
| PJ0876 | TBD | CVU | VRX | Standard | N/A | Comac C919 | PILOTE | TBD | 2 |  | GOING |  | TBD | TBD | TBD | TBD | TBD | TBD |  | N/A | N/A | N/A |  | CLOSED
| PJ0787 | Emilie.Brun@zodiacaerospace.com / Frederic.Parage@zodiacaerospace.com | MQR | GDN | British Airways | BAW | A350 & B787 | FC | 20 | 8 | 160 | GOING |  | 2016-09-13 | 2017-03-29 | 2016-01-29 | 2018-03-22 | 2016-09-13 | 2017-03-29 |  | N/A | P78700M000 | V40 |  | CLOSED
| PJ0790 | Laurent.Genevay@zodiacaerospace.com | CVU | VRX | Air Nippons Airways | ANA | B777 | FUSIO | 12 | 64 | 768 | GOING |  | 2017-04-19 | 2017-11-14 | 2018-05-22 | 2018-05-03 | 2017-04-19 | 2017-11-14 |  | ECU GEN VII | P78700M180 | V40.06x |  | ECU Gen 7
| PJ1186 | N/A | DCE | SDN | Air Nippons Airways | ANA | B777-9 | FUSIO | 20 | 56 pour les 3 premiers69 pour les 17 autres |  | GOING |  | 2018-03-26 | 2018-09-24 | 08/07/2019 4 pax TBC | 2019-10-22 | 2018-03-26 | 2018-09-24 |  | N/A | N/A | N/A |  | ECU Gen VII
| PJ0845 | Emilie.Brun@zodiacaerospace.com / Frederic.Parage@zodiacaerospace.com | MQR | TDN | N/A | N/A | B767/B777/B787 & A330/A350/A380 | N/A | TBD | TBD |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | ECU Gen V

## Zodiac Seats UK
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Thompson Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ1103 | kim.dufty@zodiacaerospace.com | CVU | VRX | Air France | AFR | A350-B777-A380 | ASTERICS | 10 x A350 + 14 x B777 + 7 x A380 | N/A |  | GOING |  | 2017-08-29 | 2018-04-03 | 2019-02-11 | 2019-04-10 | 2017-08-29 | 2018-04-03 |  | N/A | N/A | N/A |  | GOING
| PJ1041 | kim.dufty@zodiacaerospace.com | CVU | VRX | TBD | N/A | A350 - B777 - A380 | OPTIMA | 29 | N/A |  | GOING |  | TBD | TBD | TBD | 2019-01-01 | TBD | TBD |  | N/A | N/A | N/A |  | CLOSED
| PJ0987 | kim.dufty@zodiacaerospace.com | CVU | VRX | TBD | N/A | B777-9x | NEPTUNE | 34 | 47 | 1598 | GOING |  | 2017-09-01 | 2018-07-01 | 2019-04-01 | 2019-09-01 | 2017-09-01 | 2018-07-01 |  | N/A | N/A | N/A |  | ECU 3100
| PJ0906 | TBD | CVU | VRX | Cathay Pacific | CPA | B777-9X | PEACOCK | 21 | 4 | 84 | GOING |  | TBC | Juin-2018 (TBC) | TBC | 2021-01-01 | TBC | 2018-07-01 |  | N/A | N/A | N/A
| PJ0442 | N/A | FES | SDN | British Airways | BAW | B777 | SKYL | N/A | 64 |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | ECU GEN VII | Pxxxxxxx | V40.06x
| PJ0444 | N/A | FES | SDN | British Airways | BAW | B777 | SKYL | N/A | 64 |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | ECU GEN VII | Pxxxxxxx | V40.06x
| PJ0443 | N/A | FES | SDN | British Airways | BAW | B777 | SKYL | N/A | 64 |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | ECU GEN VII | Pxxxxxxx | V40.06x

## PAC Seating System
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Pac Seating Systems Programs
Program Characteristics | [11 empty] | Program monitoring | [9 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers | [8 empty] | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR |  | CDR |  | FAI |  | ODD
| PJ0872 | dhillon@pac-fl.com | RPN | N/A | Blue Sky | N/A | B777 | LIEF | 1 | 9 | 9 | GOING | N/A | N/A |  | N/A |  | 2017-01-19 |  | N/A |  | N/A | N/A |  | Gen 7 | P78700M170 | V40.19x |  | GOING
| PJ0809 | tufano@pac-fl.com | CVU | VRX | VIP (Ceiba) | CEI | B777 | POD | 1 | 10 | 10 | GOING | N/A | Fait |  | 2016-06-01 |  | 2016-11-01 |  | N/A |  | FAIT | 2016-06-01 |  | ECU 3600 | P78634M080 | V35.39X |  | CLOSED
| PJ0601 | marini@pac-fl.com | CVU | VRX | VIP (Firts Look) | N/A | B787 | GUST POD | 1 | 28 | 28 | GOING | N/A | TBD |  | TBD |  | TBD |  | TBD |  | TBC | TBD |  | ECU 3600 | P78634M050 | V32.23x |  | ECU 3100
| PJ0895 | dhillon@pac-fl.com | RPN | GDN | Blue Sky | N/A | B777 | BC | 1 | 12 | 12 | GOING | N/A | N/A |  | N/A |  | 2017-03-17 |  | N/A |  | N/A | N/A |  | GEN VII | P78700M120 | V40.20x |  | ECU 3600
| PJ0669 | N/A | CVU | VRX | VIP (Royal Jet) | ROJ | B737 | POD | 2 | 8 | 16 | CLOSED | N/A | 2015-11-02 | Done | 08/12/2015 22/01/2016 (CDR2) | Done | 2016-05-23 | Done | 2016-07-20 | Done | 2015-11-02 | 2015-12-08 |  | N/A | P78700M090 | V40.08x |  | ECU Gen 7
| PJ0668 | N/A | CVU | VRX | VIP (Royal Jet) | ROJ | B737 | SVIP | 2 | 8 | 16 | CLOSED | N/A | 2015-11-02 | Done | 08/12/2015 22/01/2016 (CDR2) | Done | 2016-05-23 | Done | 2016-07-21 | Done | 2015-11-02 | 2015-12-08 |  | N/A | P78700M100 | V40.09x |  | ECU Gen VII
ECU Gen V

## Optimares
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Optimares Programs
Program Characteristics | [11 empty] | Program monitoring | [9 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers | [8 empty] | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM |  | PDR |  | CDR |  | FAI |  | ODD
| PJ0967 | giampaolo.pandolfi@optimares.com | CVU | VRX | QATAR | QTR | A321 | VIVA | 50 | 16 | 800 | GOING |  |  | N/A |  | Besoin pièces mi-décembre 2017 |  | besoin pièces mai 2018 |  | AO | N/A | 2017-12-01 |  | N/A | P78700Mxxx | N/A |  | GOING
| PJxxxxx | giampaolo.pandolfi@optimares.com | CVU | VRX | TBD | N/A | B787-8 et -9 | VIVA | 20 | 16 | 320 | GOING |  |  | TBD |  | April 2018 |  | TBD |  | TBD ( AO) | TBD | 2018-04-01 |  | N/A | N/A | N/A |  | CLOSED
| PJ1142 | giampaolo.pandolfi@optimares.com | CVU | VRX | N/A | N/A | Hamburg | N/A | 0 | 4 |  | GOING |  |  | N/A |  | N/A |  | N/A |  | N/A | N/A | N/A |  | N/A | P78700Mxxx | N/A |  | ECU 3100
| PJ0955 | giampaolo.pandolfi@optimares.com | CVU | VRX | AVOLON | N/A | A330 | BC | N/A | N/A |  | CLOSED | N/A | Done | N/A | Done | April 2017 | Done | July 2017 | Done | (Términé) | N/A | 2017-04-01 |  | N/A | P78623A | V32.134x |  | ECU 3600
ECU Gen 7
ECU Gen VII

## Iaobucci
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Iacobucci Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ1155 | embabi.hesham@iacobucci.aero | CVU | VRX | VIP (Jet Aviation) | JAS | B737-800 | SPOD | 1 | 8 | 8 | GOING |  | 2018-02-27 | TBD | TBD | TBD | 2018-02-27 | TBD |  | ECU 3100 | P78625M030 | V32.127x |  | GOING
| PJ1067 | embabi.hesham@iacobucci.aero | CVU | VRX | VIP (FOKKER) |  | B737 | SPOD | 1 | 12 | 12 | GOING |  | N/A | TBD | TBD | 2018-11-10 | N/A | TBD |  | ECU 3100 | P78625M030 | V32.127x |  | CLOSED
ECU 3100
ECU 3600
ECU Gen 7
ECU Gen VII
ECU Gen V

## Avionteriors
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Avionteriors Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ1022 | N/A | CVU | VRX | QATAR | QTR | TBD | BC | 10 | 12 | 120 | GOING |  | TBD | TBD | TBD | AO | TBD | TBD |  | N/A | N/A | N/A |  | GOING
| PJ0908 | e.papetti@aviointeriors.it | CVU | VRX | TBC | TBC | A340-600 | KYMERA | 7 | 47 | 329 | GOING |  | TBD | début janvier 2017 | livraison PGA : Juillet 2017 (puis 1/mois) | TBD | TBD | 2017-01-01 |  | N/A | P78700 | N/A |  | CLOSED
| PJ1016 | e.papetti@aviointeriors.it | CVU | VRX | (VIP) |  | A340-601 | BC | 4 | TBD |  | GOING |  | TBD | TBD | livraison PGA : Octobre 2017 Novembre 2017 Janvier 2018 Février 2018 | TBD | TBD | 2017-01-02 |  | N/A | P78700M130 | V40.382x |  | ECU 3100
ECU 3600
ECU Gen 7
ECU Gen VII
ECU Gen V

## Recaro
Last Update : | 2018-04-24 | By CAI |  |  |  |  | Version Beta |  |  | Recaro Programs
Program Characteristics | [11 empty] | Program monitoring | [5 empty] | NRC |  |  | ECU Caracteristics |  |  |  | Done
Customer Program Name | PJ | Customer Interlocutor email | PGA PM | PGA TC | Airline | Airline OACI Code | Aircraft | Seat | Shipset qty | PAX per shipset | TOTAL PAX | Status | Main Programm Markers |  |  |  |  | BL PDR | BL CDR | End of Project Billing | ECU Generation | PN of the ECU | Software Caracteristics | In charge Develloper
[13 empty] | ITCM | PDR | CDR | FAI | ODD
| PJ1128 | motoki.hirai@jal.com / masaya.shimizu@jal.com | CVU | VRX | Japon Airlines | JAL | B787 | BC | N/A | N/A |  | GOING |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | GOING
| PJ0984 | motoki.hirai@jal.com | CVU | VRX | Japon Airlines | JAL | A350 | BC | 11 | 94 | 1034 | GOING |  | 2017-06-01 | 2017-09-01 | N/A | 2018-08-01 | 2017-06-01 | 2017-09-01 |  | N/A | N/A | N/A |  | CLOSED
ECU 3100
ECU 3600
ECU Gen 7
ECU Gen VII
ECU Gen V

## Notice
xx/xx/xxxx | En retard de plus de 2 semaines
xx/xx/xxxx | En retard d'une semaine
xx/xx/xxxx | En avance d'un mois
xx/xx/xxxx | En avance moins de 2 semaines
mois-année | En retard de plus de 2 semaines
mois-année | En avance moins de 2 semaines
mois-année | En avance d'un mois