## PROJECT DOC MATRIX
PROJECT :
JOB N°
WRITTENT BY :
CHECHEKD BY:
[52 empty] | REV : | [5 empty] | 0
DATE
LEGEND |  | INTERNAL DISPATCH | [55 empty] | EXTERNAL DISPATCH
W=Writter, A= Approbation, R =Review, i =Information, C =Check |  | HEURTEY PETROCHEM | [55 empty] | Contrat Org.
|  |  |  | PMT HPF |  |  | Proposals & Process HPF | [7 empty] | Finance & Costs HPF |  |  | Engineering | [22 empty] | Procurement | [11 empty] | Contracts & Construction HPF
[18 empty] | HPF | [14 empty] | HPRus | [5 empty] | HPR |  | HPF | [5 empty] | HPRus
|  | CEO HPF + Deputy | Quality Assurance & Safety director HPF | Project management dept Director | Project Manager & project engineer | Planning Manager | Proposal & process dept Director | Proposal service manager | Proposal Engineer | Process service manager | Process Engineer | Spare Parts service manager | PFS service manager | Start up Engineer | Accounts and finance dept Director | Accounts | Cost Control | Engineering dept Director | Heater service manager | Heater Designer | Structural Engineer | Cast & Pressure part Calculation | Static equipemnt engineer | Piping service manager | Piping coordinator engineer | Stress engineer | Instrumentation service manager | E & I Engineer | E & I Subcontractor | Document control service manager | Document Controller | Data book compiler | Heater service manager | Heater Designer HPRussie | Structural Engineer | Document control service manager | Document Controller | Data book compiler | Heater service manager | Piping Engineer | Procurement department Director | Purchaser | Logistic & Expediting service manager | Logistic & Expediting engineer | Inspection service manager | Inspection | Procurement department Director | Purchaser | Logistic & Expediting service manager | Logistic & Expediting engineer | Inspection service manager | Inspection | Construction department Director | Construction purchaser | Construction coordinateur | Workshop HPM | Site manager | Owner /EPC(M) & PMC = Master Document List | Notified body or thrird party | Licencor | Include in DATA BOOK | Master doc list - CODE Number.
PROJECT
0000-FA | Project | [56 empty] | x
0000-FA-001 | Project organization chart |  | i | A | W | i | i | i | C | i | i | i | i | i | i | i | i | i | i | i | i | i |  | i | i | i | i | i |  | i | i | i | i | i | i | i | i | i |  | i | i | i | i | i | i | i | i | i | i | i |  |  | i | i | i | i |  | X |  |  |  |  | 4 | PO
0000-FA-002 | Project risk rating | i | [55 empty] | X | bar: A to i
0000-FA-003 | Project steel weight follow-up |  | W: A; i: i; C: W; i: i; i: C | [11 empty] | i | C | [17 empty] | i | i | i | i | i | X
0000-FA-004 | Project document matrix | [21 empty] | i | i | i | i | i | i | i | A | W | i | i | i | i | A | W | i |  | i | [5 empty] | i | [6 empty] | i |  | i |  |  | X | bar: W to i; C; i to i; i to i
0000-FA-005 | Project coordination procedure |  | i | A | W | i | i | i | C | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i |  | i | i | i | i | i | i | i | i | i | i | i |  |  | i | i | i | i |  | X
0000-FA-006 | Project general schedule |  | i |  | A | W |  | i | i | i | i | i | i | [5 empty] | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i | i |  | i |  | i | i | i | i | i |  | i | i | i |  |  |  | i | i | i |  | X |  |  |  |  | 3
0000-FA-007 | Project procurement request (DA) |  | A: A; W: W; i: i; i: i |  |  | i | i | i | [9 empty] | i | i |  |  |  | X
0000-FA-008 | Sub Order Status | [40 empty] | i | A | W |  |  |  | i | A | W | [7 empty] | X | bar: W to i
0000-FA-009 | Internal monthly progress report |  | i: i; A: A; W: W; i: i; i: i; i: i; i: i; i: i; i: i |  |  | i | [5 empty] | i | [5 empty] | i |  |  |  |  | X
0000-FA-010 | Project monthly progress report |  | i: i; A: A; W: W; i: i; i: i; i: i; i: i; i: i; i: i |  |  | i | [5 empty] | i | [5 empty] | i |  |  |  |  | X |  |  |  |  | each month
0000-FA-011 | Purchasing follow-up (Suivi HA) | [39 empty] | C | W | i | i |  |  |  |  | i | i |  |  | i | i |  |  |  | X | bar: A to W
0000-FA-012 | Change order request |  | A: A; W: W; i: i; i: i; i: i; i: i; i: i |  |  | i | [5 empty] | i | [5 empty] | i |  |  |  |  | X
0000-FA-013 | Concession / Deviation Request |  |  |  | A | W | i |  |  | A | W | W | W |  | A | W | W | i | A | W | W | W | W | A | W | W | A | W |  |  |  |  | A | W | W |  |  |  |  | W | i | w | A | W | A | W | i | w | A | W |  |  | A |  | W | W | i | X |  | x
0000-FA-014 | Master document list | [56 empty] | X |  |  |  |  | 3
0000-FA-015 | Project vendor list | [39 empty] | i | [5 empty] | i | [10 empty] | X | bar: W
X
0000-FC | CALCULATION | [56 empty] | X
X
001 | Foundation & Base Plates | [56 empty] | X
X
0000-FC-001 | HEATER - Foundation loads |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x |  | 9
X
300 | Main structures | [56 empty] | X
X
0000-FC-300 |  |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x
0000-FC-301 | HEATER - Mechanical calculation of steel structure |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x |  | 15
0000-FC-351 | HEATER - Mechanical calculation of stack |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x |  | 9
0000-FC-361 |  |  | W: A; i: i; i: C; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x
0000-FC-371 | HEATER - Mechanical calculation of ducting system |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x |  | 13
0000-FC-372 | HEATER - Mechanical calculation of Piping supports |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x
- | Secondary structures |  | W: A; i: i; i: C; i: i; i: A; i: W; i: i; i: i | [19 empty] | X
X
400 | Coil & manifolds | [56 empty] | X
X
0000-FC-410 | Coil pressure parts calculation |  | W: A; i: A; i: i; i: i; i: i; i: W+C; i: i; i: i; i: i; i: i |  | i | [17 empty] | X | x |  | x |  | 9
0000-FC-411 | Coil analysis calculation |  | W: A; i: A; i: i; i: i; i: i; i: W+C; i: i; i: i; i: i; i: i |  | i | [17 empty] | X | x |  | x |  | 14
X
450 | Piping Stress Analysis | [56 empty] | X
X
0000-FC-4001 | Piping stress analysis |  | W: A; i: i; i: i; i: A; i: i; i: W+C; i: i; i: i; i: i; i: i |  | i | [17 empty] | X | x |  | x |  | 28
X
500 | calcul process | [56 empty] | X
X
0000-FC-501 | Outside casing temperature calculation note |  | W: A; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 17
X
600 | Cast support | [56 empty] | X
X
0000-FC-601 | cast supports |  | W: A; i: A; i: i; i: i; i: W; i: i; i: i; i: i; i: i; i: i; i: i; i: i |  | i | [17 empty] | X |  |  | x
X
800 | intrumentation | [56 empty] | X
X
0000-FC-801 | FFB, TW stress, SIL, Valves & Orifice Plate |  | W: A; i: i; i: A; i: W; i: i; i: i | [19 empty] | X
- | IS, Instrument sizing |  | W: A; i: i; i: A; i: C; i: W; i: i; i: i | [19 empty] | X
X
900 | Lifting | [56 empty] | X
X
0000-FC-901 | HEATER - Mechanical calculation of lifting devices |  | W: A; i: i; i: A; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  |  | x |  | 16
X
0000-FD | DRAWINGS | [56 empty] | X
X
000 | General | [56 empty] | X
X
0000-FG-001 | HEATER SCHEMATIC VIEWS - ELEVATIONS | [56 empty] | X |  |  |  |  | 7
0000-FG-002 | HEATER SCHEMATIC VIEWS - PLAN VIEWS | [56 empty] | X |  |  |  |  | 7
0000-FG-005 | FLUE GAS DUCT & AIR DUCT SCHEMATIC VIEWS (if APH System) | [56 empty] | X |  |  |  |  | 9
0000-FD-001 | FOUNDATION LAYOUT |  | W: A; i: i; i: C; i: A; i: W; i: C; i: i; i: i | [7 empty] | i | [7 empty] | i | i | i | i | X |  |  | x |  | 10
0000-FD-002 | BASE PLATE DETAILS | [56 empty] | X |  |  |  |  | 10
0000-FD-005 | PLOT PLAN (if not provided by client) | [56 empty] | X |  |  |  |  | 9
0000-FD-010 | GENERAL ASSEMBLY – GENERAL DATA |  | W: A; i: i; i: i; i: C; i: i; i: C; i: C; i: A; i: W; i: i; i: i; i: i |  | C |  |  |  | i |  | i |  |  |  | i |  |  | i | i | i | i | i | X |  | x | x |  | 8 | 11
0000-FD-020 | GENERAL ASSEMBLY – ELEVATIONS |  | W: A; i: i; i: i; i: C; i: i; i: C; i: C; i: A; i: W; i: i; i: i; i: i |  | C |  |  |  | i |  | i |  |  |  | i |  |  | i | i | i | i | i | X |  | x | x |  | 8 | 11
0000-FD-021 | GENERAL ASSEMBLY – ELEVATIONS |  | W: A; i: i; i: i; i: C; i: i; i: C; i: C; i: A; i: W; i: i; i: i; i: i |  | C |  |  |  | i |  | i |  |  |  | i |  |  | i | i | i | i | i | X |  | x | x
0000-FD-030 | GENERAL ASSEMBLY – PLAN VIEWS |  | W: A; i: i; i: i; i: C; i: i; i: C; i: C; i: A; i: W; i: i; i: i; i: i |  | C |  |  |  | i |  | i |  |  |  | i |  |  | i | i | i | i | i | X |  | x | x |  | 8 | 11
0000-FD-040 | FLUE GAS DUCT - GENERAL ASSEMBLY (if APH System) |  | W: A; i: i; i: i; i: C; i: i; i: C; i: C; i: A; i: W; i: i; i: i; i: i |  | C |  |  |  | i |  | i |  |  |  | i |  |  | i | i | i | i | i | X |  | x | x |  | 25
0000-FD-050 | AIR DUCT - GENERAL ASSEMBLY (if APH System) | [56 empty] | X |  |  |  |  | 25
X
300 | Structure detail | [56 empty] | X
X
0000-FD-301 | GENERAL NOTES – STEEL STRUCTURE |  | W: A; i: i; i: C; i: i; i: A; i: W; i: C; i: i; i: i | [15 empty] | i | i | i | i | X |  |  | x |  | 11
0000-FD-360 | PLATFORM ACCESS AND HANDRAIL – TYPICAL DETAILS |  | W: A; i: i; i: C; i: i; i: i; i: A; i: W; i: C; i: i; i: i | [15 empty] | i | i | i | i | X |  |  | x |  | 11
0000-FD-361 | GRATING PLATFORMS |  | W: A; i: i; i: C; i: i; i: A; i: W; i: C; i: i; i: i | [15 empty] | i | i | i | i | X |  |  | x
0000-FD-362 | GRATING PLATFORMS |  | W: A; i: i; i: C; i: i; i: A; i: W; i: C; i: i; i: i | [15 empty] | i | i | i | i | X |  |  | x
X
400 | Coil & manifold | [56 empty] | X
X
0000-FD-401 | RADIANT COIL |  | W: A; i: C; i: i; i: C; i: C; i: i; i: C; i: A; i: W; i: i; i: i |  | i | [5 empty] | i | [7 empty] | i | i | i | i | X | x | x | x |  | 12
0000-FD-402 | CONVECTION COIL |  | W: A; i: C; i: i; i: C; i: C; i: i; i: C; i: A; i: W; i: i; i: i |  | i | [5 empty] | i | [7 empty] | i | i | i | i | X | x | x | x |  | 12
0000-FD-403 | CROSS OVER |  | W: A; i: C; i: i; i: C; i: C; i: i; i: C; i: A; i: W; i: i; i: i |  | i | [5 empty] | i | [7 empty] | i | i | i | i | X | x | x | x |  | 12
0000-FD-404 |  |  | W: A; i: C; i: i; i: C; i: C; i: i; i: C; i: A; i: W; i: i; i: i |  | i | [5 empty] | i | [7 empty] | i | i | i | i | X | x | x | x
0000-FD-405 |  |  | W: A; i: C; i: i; i: C; i: C; i: i; i: C; i: A; i: W; i: i; i: i |  | i | [5 empty] | i | [7 empty] | i | i | i | i | X | x | x | x
X
500 | Insulation | [56 empty] | X
X
0000-FD-501 | INSULATION - General assembly & detail and BOM |  | W: A; i: i; i: C; i: i; i: A; i: W; i: C; i: i; i: i | [15 empty] | i | i | i | i | X |  |  | x
X
700 | Equipment | [56 empty] | X
X
0000-FD-781 | STEAM DISENGAGING DRUM |  | W: i; i: i; i: i; i: C; i: W; i: A; i: C; i: C; i: C; i: i; i: i |  |  |  | i | [11 empty] | i | i | i | i | X |  |  | x
0000-FD-782 | STEAM DISENGAGING DRUM + PLATFORM |  | W: i; i: i; i: C; i: W; i: A; i: C; i: C; i: C; i: i; i: i |  |  |  | i | [11 empty] | i | i | i | i | X |  |  | x
X
800 | PFD & PID | [56 empty] | X
X
0000-FD-800 | PID - Legends and symbols |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-801 | PID - Heater |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-802 | PID - Air preheating system |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-803 | PID - Fuel system |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-804 | PID - Utility (instrument air, snuffing steam) |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-805 | PID - Steam drum and appurtenances |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x |  | 12 | PO
0000-FD-806 |  |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x
0000-FD-807 |  |  | W: A; i: A; i: A; i: i; i: C; i: i; i: C; i: W; i: i; i: i; i: i; i: i |  | C | [5 empty] | i | [7 empty] | i | i | i | i | X |  | x | x
0000-FD-820 | Instrument list |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [17 empty] | i | i | X |  | x | x |  | 16
0000-FD-821 | I/O list |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [17 empty] | i | i | X |  | x | x |  | 16
0000-FD-822 | Instrument & Electrical cable list |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [17 empty] | i | i | X |  | x | x
0000-FD-823 | Electrical & air consumer list |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [17 empty] | i |  | X |  | x | x |  | 16
0000-FD-824 | Instrument and Electrical layout (with JB and cable trays) |  | W: i; i: i; i: i; i: i; i: i; i: A; i: W; i: i; i: i; i: i |  | i | [15 empty] | i | i | X |  | x | x
0000-FD-825 | Interconnection diagrams |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  | x | x |  | 18
0000-FD-826 | Instruments Hook up drawings |  | W: i; i: i; i: i; i: i; i: A; i: W; i: i; i: i |  | i | [16 empty] | i | X |  | x | x |  | 28
0000-FD-827 | Junction boxes wiring |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  | x | x |  | 24
0000-FD-828 | Local panel layout |  | W: i; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  | x | x |  | 22
0000-FD-829 | Instruments, junction boxes and local panel supports |  | W: i; i: i; i: i; i: i; i: A; i: W; i: i; i: i |  | i | [17 empty] | X |  | x | x
0000-FD-830 | Cause & effect chart |  | W: i; i: A; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  | x | x |  | 22
0000-FD-831 | Basic logic diagram and start-up sequence diagram |  | W: i; i: A; i: i; i: i; i: A; i: W; i: i; i: i | [19 empty] | X |  | x | x |  | 22
0000-FD-890 | SKIN THERMOCOUPLES |  | W: i; i: i; i: A; i: C; i: C; i: c; i: A; i: W; i: i; i: i |  |  |  | i | [5 empty] | i | [6 empty] | i | i | i | X |  | x | x |  | 12
X
900 | Transport | [56 empty] | X | bar: i
X
0000-FD-901 | LIFTING LUGS AND REINFORCEMENT FOR TRANSPORTATION |  | i: i; i: C; i: A; i: W; i: C | [7 empty] | i | [7 empty] | i | i | i | i | X | X |  |  |  | 30 | HPM or HPF
0000-FD-902 | LIFTING LUGS AND REINFORCEMENT FOR TRANSPORTATION |  | i: i; i: C; i: A; i: W; i: C | [7 empty] | i | [7 empty] | i | i | i | i | X | X
X
4000 | Piping layout, Tie-ins, Drum & Boiler, Line list | [56 empty] | X
X
0000‐FD‐4001 | SKID PIPING ‐ LAYOUT | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 26 | bar: W; i; i; i to i
0000‐FD‐4002 | [39 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4003 | SKID PIPING ‐ ISOMETRIC BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 25 | bar: W; i; i; i to i
0000‐FD‐4004 | SKID PIPING ‐ SUPPORT BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 27 | bar: W; i; i; i to i
0000‐FD‐4006 | HEATER PIPING ‐ ISOMETRIC BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 27 | bar: W; i; i; i to i
0000‐FD‐4011 | HEATER PIPING ‐ LAYOUT | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 28 | bar: W; i; i; i to i
0000‐FD‐4012 | HEATER PIPING ‐ LAYOUT | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4013 | HEATER PIPING ‐ LAYOUT | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4021 | HEATER PIPING ‐ LAYOUT | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4007 | HEATER PIPING ‐ SUPPORT BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x |  | 29 | bar: W; i; i; i to i
0000‐FD‐4023 | STEAM GENERATION PIPING ‐ PRIMARY SUPPORT BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4024 | SKID FRAME | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4025 | HEATER PIPING ‐ SECONDARY SUPPORT BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
0000‐FD‐4026 | STEAM GENERATION PIPING ‐ SECONDARY SUPPORT BOOK | [38 empty] | W | [13 empty] | i | i | i | i | X |  |  | x | bar: W; i; i; i to i
X
H000-FE | SUB CONTRACTORS DOCUMENTS | [56 empty] | X
X
100 | TUBES & FITTINGS | [56 empty] | X
X
0000-FE-100 | TUBES & FITTINGS - Sub-vendor monthly progress report |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-101 | TUBES & FITTINGS - Fabrication schedule | [56 empty] | X
0000-FE-102 | TUBES & FITTINGS - Document List | [56 empty] | X
0000-FE-103 | TUBES & FITTINGS -Calculation note |  | i: R/A; i: i; i: i | [19 empty] | X
0000-FE-104 | TUBES & FITTINGS -General assembly & detail and BOM |  | W: i; i: i; i: A; i: R; i: R; i: i; i: R; i: i | [7 empty] | i | [10 empty] | i | X |  |  | x
0000-FE-105 | TUBES & FITTINGS -Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: W; i; i
0000-FE-106 | TUBES & FITTINGS -Quality - Chemical analysis | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-107 | TUBES & FITTINGS -Quality - Air pressure test procedure | [43 empty] | A | R | [10 empty] | x | X | x |  | x | bar: i; i
0000-FE-108 | TUBES & FITTINGS -Quality - Radiographic examination procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-109 | TUBES & FITTINGS -Quality - Eddy current test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-110 | TUBES & FITTINGS -Quality - Hydrostatic pressure test procedure | [43 empty] | A | R | [11 empty] | X | x |  | x | bar: i; i
0000-FE-111 | TUBES & FITTINGS -Quality - Positive material identification procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-112 | TUBES & FITTINGS -Quality - GO Gauge test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-113 | TUBES & FITTINGS -Quality - Liquid penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-114 | TUBES & FITTINGS -Quality - Welding wires storage management procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-115 | TUBES & FITTINGS -Quality - Visual examination procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-116 | TUBES & FITTINGS -Quality - Roughness test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-117 | TUBES & FITTINGS -Quality - Marking procedure for tube and assembly | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-118 | TUBES & FITTINGS -Quality - Visual examination on static casting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-119 | TUBES & FITTINGS -Quality - Cleaning procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-120 | TUBES & FITTINGS -Quality - Fluorescent liquid penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-121 | TUBES & FITTINGS -Quality - Dimensional inspection procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-122 | TUBES & FITTINGS -Quality - Procedure for chemical analysis by spectrometer | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-123 | TUBES & FITTINGS -Quality - Macroetching test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-124 | TUBES & FITTINGS -Quality - Welding specification | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-125 | TUBES & FITTINGS -Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-126 | TUBES & FITTINGS -Shipping and packing instructions | [41 empty] | A | R | [12 empty] | i | X | bar: W; i
0000-FE-127 | TUBES & FITTINGS -Index data book | [44 empty] | R | [10 empty] | i | X |  |  | x | bar: W; i to i; i; i
0000-FE-128 | TUBES & FITTINGS -Spare part list |  | W: A; i: R; i: i; i: i; i: i | [5 empty] | i | [12 empty] | i | X |  |  | x
0000-FE-129 | TUBES & FITTINGS - Data book | [44 empty] | R | [10 empty] | i | X |  |  | x | bar: W; i to i; i; i
X
200 | BURNER | [56 empty] | X
X
0000-FE-200 | BURNER - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-201 | BURNER - Fabrication schedule |  | W: A; i: R; i: i; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-202 | BURNER - Document List |  | W: A; i: R; i: R; i: i | [19 empty] | X
0000-FE-203 | BURNER - General assembly & detail and BOM |  | W: A; i: R; i: i; i: i; i: R; i: R; i: C; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 16
0000-FE-204 | BURNER - Flame rod detection general assembly and detail |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: C; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 16
0000-FE-205 | BURNER - Pilot general assembly and detail |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: C; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 16
0000-FE-206 | BURNER - Ignition equipement detail |  | W: A; i: i; i: i; i: i; i: i; i: A; i: R; i: C; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 16
0000-FE-207 | BURNER - Curve, data sheet, |  | W: A; i: A; i: R; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 16
0000-FE-208 | BURNER - BURNERs box |  | i: R; i: C; i: i; i: i | [18 empty] | i | X |  |  | x |  | 16
0000-FE-209 | BURNER - Internal box wiring |  | i: R; i: C; i: i; i: i | [18 empty] | i | X |  |  | x |  | 16
0000-FE-210 | BURNER - Special cable /certificates |  | i: R; i: R; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 16
0000-FE-211 | BURNER - Quality - Test procedure |  | W: i; i: A; i: R; i: i; i: i; i: i | [7 empty] | i | [11 empty] | X |  |  | x
0000-FE-212 | BURNER - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 15 | bar: W; i to i; i; i
0000-FE-213 | BURNER - Quality - Dye penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-214 | BURNER - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-215 | BURNER - Quality - Air flow test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 15 | bar: i; i
0000-FE-216 | BURNER - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 15 | bar: W; i; i
0000-FE-217 | BURNER - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 15 | bar: i; i
0000-FE-218 | BURNER - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-219 | BURNER - Installation, operating and maintenance manuals | [48 empty] | R | [6 empty] | i | X |  |  | x | bar: W; i; i; i; i; i; i
0000-FE-220 | BURNER - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  | x | bar: i; i; i
0000-FE-221 | BURNER - Shipping and packing instructions | [47 empty] | A | R | [6 empty] | i | X |  |  | x | bar: i; i
0000-FE-222 | BURNER - Index data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 15
0000-FE-223 | BURNER - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [6 empty] | i | X |  |  | x
0000-FE-224 | BURNER - Noise data sheet | [56 empty] | X | bar: i
0000-FE-225 | BURNER - Data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x
X
300 | PREFABRICATION Structure / coil & manifold | [56 empty] | X
X
0000-FE-300 | PREFABRICATION - Sub-vendor monthly progress report |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-301 | PREFABRICATION - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-302 | PREFABRICATION - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-303 | PREFABRICATION - General assembly & detail and BOM | [53 empty] | i | W | i | X |  |  | x |  | 23 | bar: W; i; i; i; i
0000-FE-304 | PREFABRICATION - Quality - Inspection and test plan | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-305 | PREFABRICATION - Procedure for refractory and lining application | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-306 | PREFABRICATION - Quality - Radiography Procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-307 | PREFABRICATION - Quality - Hydrostatic pressure test procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-308 | PREFABRICATION - Quality - PMI procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-309 | PREFABRICATION - Quality - Dry Penetrant Test Procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-310 | PREFABRICATION - Quality - PWHT & Hardness Test Procedure (if applicable) | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-311 | PREFABRICATION - Quality - Visual examination Procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-312 | PREFABRICATION - Quality - Dimensional Procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-313 | [44 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-314 | PREFABRICATION - Quality - Trial assembly Procedure |  | i: A; i: R; i: R; i: i; i: R; i: R; i: i | [16 empty] | i | W | i | X |  |  | x |  | 23
0000-FE-315 | PREFABRICATION - Painting procedure | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-316 | PREFABRICATION - Quality - Welding book | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-317 | PREFABRICATION - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [8 empty] | i | W |  | X |  |  | x |  | 23 | bar: i; i
0000-FE-318 | PREFABRICATION - Lifting spreader beams procedures or drawing |  | i: A; i: R; i: R; i: i; i: R; i: R; i: i | [11 empty] | R |  |  |  |  | i | i | i | X |  |  | x |  | 23
0000-FE-319 | PREFABRICATION - Site storage procedure | [47 empty] | A | R |  |  |  |  | i | W | i | X |  |  | x |  | 23 | bar: i; i; i
0000-FE-320 | PREFABRICATION - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X |  |  | x |  | 23 | bar: i; i
0000-FE-321 | PREFABRICATION - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [9 empty] | W | i | X |  |  | x |  | 23
0000-FE-322 | PREFABRICATION - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  | x |  | 23
0000-FE-323 | PREFABRICATION - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [9 empty] | W | i | X |  |  | x |  | 23
X
400 | FINNING OR STUD | [56 empty] | X
X
0000-FE-400 | FINNING - Sub-vendor monthly progress report | [41 empty] | A | R |  | i | [11 empty] | X | bar: W to i; i
0000-FE-401 | FINNING - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-402 | FINNING - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-403 | FINNING - General assembly & detail and BOM |  | W: i; i: i; i: i; i: A; i: R; i: R; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i | [7 empty] | X |  |  | x
0000-FE-404 | FINNING - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 13 | 10w PO | 3w after PO | bar: W; i; i
0000-FE-405 | FINNING - Hydrostatic pressure test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-406 | FINNING - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-407 | STUDDING - Quality - PWHT & Hardness Test Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 13 | bar: i; i
0000-FE-408 | FINNING - Quality - Radiography Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-409 | FINNING - Quality - Dye Penetrant Test Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-410 | FINNING - Quality - Visual examination Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-411 | FINNING - Quality - Dimensional Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-412 | [44 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-413 | FINNING - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 13 | bar: i; i
0000-FE-414 | FINNING - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [9 empty] | i |  | X |  |  | x | bar: i; i
0000-FE-415 | FINNING - Site storage procedure | [41 empty] | A | R | [13 empty] | X |  |  | x | bar: i; i; i
0000-FE-416 | FINNING - Shipping and packing instructions | [41 empty] | A | R | [13 empty] | X |  |  | x | bar: i; i
0000-FE-417 | FINNING - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x |  | 13
0000-FE-418 | FINNING - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [7 empty] | X |  |  | x
0000-FE-419 | FINNING - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x
X
500 | INSULATION | [56 empty] | X
X
0000-FE-500 | INSULATION - Sub-vendor monthly progress report |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-501 | INSULATION - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-502 | INSULATION - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-503 | INSULATION - General assembly & detail and BOM |  | W: A; i: R; i: i; i: i; i: i; i: R; i: i | [5 empty] | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 19 | 3 w after PO of refractory
0000-FE-504 | INSULATION - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 19 | bar: W; i; i
0000-FE-505 | INSULATION - Material data sheet for refactory materials |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 19
0000-FE-506 | INSULATION - Material safety data sheet for refactory materials |  | i: R; i: A; i: R; i: i; i: i | [5 empty] | i |  | i |  |  |  | i | [7 empty] | X |  |  | x |  | 19
0000-FE-507 | INSULATION - Product compliance data sheet for refactory materials |  | i: A; i: R; i: i; i: i | [7 empty] | i | [11 empty] | X |  |  | x |  | 19
0000-FE-508 | INSULATION - Heat transfer calculations |  | i: A; i: R; i: i; i: i | [7 empty] | i | [11 empty] | X |  |  | x |  | 19
0000-FE-509 | INSULATION - Application procédure | [43 empty] | A | R | [10 empty] | i | X |  |  | x |  | 19 | bar: i; i
0000-FE-510 | INSULATION - Quality - Density test certificate | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 19 | bar: i; i
0000-FE-511 | INSULATION - Quality - Crunching test certificate | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 19 | bar: i; i
0000-FE-512 | INSULATION - Quality - Shrinkage test certificate | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 19 | bar: i; i
0000-FE-513 | INSULATION - Quality - B252Hammer test certificate | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 19 | bar: i; i
0000-FE-514 | INSULATION - Quality - Dry out procedure (if applicable) |  | i: A; i: R; i: i; i: i; i: i | [7 empty] | R | [11 empty] | X |  |  | x |  | 19 | after PO of refractory
0000-FE-515 | INSULATION - Erection procedure | [43 empty] | A | R | [9 empty] | i | i | X |  |  | x |  | 19 | bar: i; i; i; i
0000-FE-516 | INSULATION - Site storage procedure | [41 empty] | A | R |  |  |  |  | A | R | [6 empty] | i | X |  |  | x |  | 19 | bar: i; i; i
0000-FE-517 | INSULATION - Shipping and packing instructions | [41 empty] | A | R |  |  |  |  | A | R | [5 empty] | W | i | X |  |  | x |  | 19 | bar: i; i
0000-FE-518 | INSULATION - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 19
0000-FE-519 | INSULATION - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  | x |  | 19
0000-FE-520 | INSULATION - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 19
X
600 | CAST PIECES | [56 empty] | X
X
0000-FE-600 | CAST PIECES - Sub-vendor monthly progress report |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-601 | CAST PIECES - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-602 | CAST PIECES - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-603 | CAST PIECES - General assembly & detail and BOM | [44 empty] | i | [10 empty] | i | X |  |  | x |  | 17 | bar: W; i; i; i; i; i; i
0000-FE-604 | CAST PIECES - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: W; i; i
0000-FE-605 | CAST PIECES - Quality - Material datasheets | [43 empty] | A | R | [10 empty] | i | X |  |  | x |  | 17 | bar: i; i
0000-FE-606 | CAST PIECES - Quality - Destructive & Non-Destructive testing | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-607 | CAST PIECES - Quality - Pilot Cast | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-608 | CAST PIECES - Quality - Repair / Acceptance | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-609 | CAST PIECES - Quality - Hot Testing | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-610 | CAST PIECES - Quality - Casting Repair Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-611 | CAST PIECES - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-612 | CAST PIECES - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-613 | CAST PIECES - Quality - Dye Penetrant Test Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-614 | CAST PIECES - Quality - Visual examination Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-615 | CAST PIECES - Quality - Radiography Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-616 | CAST PIECES - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-617 | CAST PIECES - Quality - Dimensional Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-618 | CAST PIECES - Site storage procedure | [41 empty] | A | R | [12 empty] | i | X |  |  | x |  | 17 | bar: i; i; i
0000-FE-619 | CAST PIECES - Shipping and packing instructions | [41 empty] | A | R | [12 empty] | i | X |  |  | x |  | 17 | bar: i; i
0000-FE-620 | CAST PIECES - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 17
0000-FE-621 | CAST PIECES - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [6 empty] | i | X |  |  | x
0000-FE-622 | CAST PIECES - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
X
7100 | FANS (ID or FD) | [56 empty] | X
X
0000-FE-7100 | FANS - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7101 | FANS - Fabrication schedule |  | W: A; i: R; i: i; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7102 | FANS - Document List |  | W: A; i: R; i: R; i: i | [19 empty] | X
0000-FE-7103 | FANS - General assembly & detail and BOM |  | W: A; i: R; i: i; i: i; i: R; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 23
0000-FE-7104 | FANS - Motor general assembly and detail |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: R; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 23
0000-FE-7105 | FANS - Control local control système |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: R; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 23
0000-FE-7106 | FANS - Silencer drawing |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: R; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 23
0000-FE-7107 | FANS - Terminal box | [55 empty] | i | X |  |  | x |  | 23 | bar: i to i; i; i
0000-FE-7108 | FANS - Pneumatic actuator drawing | [55 empty] | i | X |  |  | x |  | 23 | bar: i to i; i; i
0000-FE-7109 | FANS - Motor Data sheet |  | W: A; i: i; i: i; i: i; i: i; i: A; i: R; i: R; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 23
0000-FE-7110 | FANS - Data sheet, |  | W: A; i: A; i: R; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 23
0000-FE-7111 | FANS - Performance Curve |  | W: A; i: A; i: R; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 23
0000-FE-7112 | FANS -Noise data sheet | [56 empty] | X |  |  | x | bar: i to i; i; i
0000-FE-7113 | FANS -Temperature probe | [56 empty] | X |  |  | x | bar: i to i; i; i
0000-FE-7114 | FANS - Motor - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: W; i to i; i; i
0000-FE-7115 | FANS - Quality- Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: W; i to i; i; i
0000-FE-7116 | FANS - Quality - Dye penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7117 | FANS - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7118 | FANS - Test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7119 | FANS - Motor test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7120 | FANS - Mecanical running test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7121 | FANS - Performance test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7122 | FANS - Balancing procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7123 | FANS - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: W; i; i
0000-FE-7124 | FANS - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7125 | FANS - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 22 | bar: i; i
0000-FE-7126 | FANS - Installation, operating and maintenance manuals | [48 empty] | R | [6 empty] | i | X |  |  | x |  | 22 | bar: W; i; i; i; i; i; i
0000-FE-7127 | FANS - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 22 | bar: i; i; i
0000-FE-7128 | FANS - Shipping and packing instructions | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 22 | bar: i; i
0000-FE-7129 | FANS - Index data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 22
0000-FE-7130 | FANS - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [6 empty] | i | X |  |  | x
0000-FE-7131 | FANS - Data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x
X
7300 | Process Gaz Boiler | [56 empty] | X
X
0000-FE-7300 | PGB - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | R | R |  | i | [11 empty] | X
0000-FE-7301 | PGB - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7302 | PGB - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-7303 | PGB - General assembly & detail and BOM | [38 empty] | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x | bar: W; i; i; i to i; i; i; i; i; i; i
0000-FE-7304 | PGB - Calculation note |  | W: i; i: R; i: i; i: A; i: i; i: i | [6 empty] | A | R | [11 empty] | X |  |  | x
0000-FE-7305 | PGB - Spare part list |  | W: i; i: R/A; i: i; i: A; i: i; i: i | [5 empty] | i | [5 empty] | i | [7 empty] | X |  |  | x
0000-FE-7306 | PGB - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7307 | PGB - Quality - Hydrostatic pressure test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7308 | PGB - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7309 | PGB - Quality - PWHT Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7310 | PGB - Quality - Dye Penetrant Test Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7311 | PGB - Quality - Radiography Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7312 | PGB - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7313 | PGB - Quality - Visual examination Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7314 | PGB - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7315 | PGB - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7316 | PGB - Quality - Dimensional Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-7317 | PGB - Site storage procedure | [47 empty] | A | R | [7 empty] | X |  |  | x | bar: i; i; i; i
0000-FE-7318 | PGB - Shipping and packing instructions | [47 empty] | A | R | [7 empty] | X |  |  | x | bar: W; i; i; i
0000-FE-7319 | PGB - Index data book |  | W: i; i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x
0000-FE-7320 | PGB - Data book |  | W: i; i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x
X
X
7400 | Steam Air PreHeater | [56 empty] | X
X
0000-FE-7400 | SAPH - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7401 | SAPH - Fabrication schedule |  | W: A; i: R; i: i; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7402 | SAPH - Document List |  | W: A; i: R; i: R; i: i | [19 empty] | X
0000-FE-7403 | SAPH - General assembly & detail and BOM |  | W: A; i: R; i: i; i: i; i: R; i: R; i: C; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 18
0000-FE-7404 |  |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: C; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 18
0000-FE-7405 | SAPH - Data sheet, |  | W: A; i: A; i: R; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 18
0000-FE-7406 | SAPH - Quality- Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: W; i to i; i; i
0000-FE-7407 | SAPH - Quality - Dye penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7408 | SAPH - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7409 | SAPH - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: W; i; i
0000-FE-7410 | SAPH - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7411 | SAPH - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7412 | SAPH - Installation, operating and maintenance manuals | [48 empty] | R | [6 empty] | i | X |  |  | x |  | 17 | bar: W; i; i; i; i; i; i
0000-FE-7413 | SAPH - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 17 | bar: i; i; i
0000-FE-7414 | SAPH - Shipping and packing instructions | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 17 | bar: i; i
0000-FE-7415 | SAPH - Index data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 17
0000-FE-7416 | SAPH - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [6 empty] | i | X |  |  | x |  | 17
0000-FE-7417 | SAPH - Data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 17
| SAPH - Hydrostatic Test Procedure | [56 empty] | X |  |  |  |  | 17
| SAPH - Leak test procedure | [56 empty] | X |  |  |  |  | 17
X
7500 | Air PreHeater | [56 empty] | X
X
0000-FE-7500 | APH - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7501 | APH - Fabrication schedule |  | W: A; i: R; i: i; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7502 | APH - Document List |  | W: A; i: R; i: R; i: i | [19 empty] | X
0000-FE-7503 | APH - General assembly & detail and BOM |  | W: A; i: R; i: i; i: i; i: R; i: R; i: C; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 18
0000-FE-7504 | APH - Thermocouple datasheet |  | W: A; i: i; i: i; i: i; i: i; i: R; i: R; i: C; i: i; i: i; i: i |  | i | [16 empty] | i | X |  |  | x |  | 18
0000-FE-7505 | APH - Data sheet, |  | W: A; i: A; i: R; i: i; i: i; i: i | [19 empty] | X |  |  | x |  | 18
0000-FE-7506 | APH - Quality- Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: W; i to i; i; i
0000-FE-7507 | APH - Quality - Dye penetrant test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7508 | APH - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7509 | APH - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: W; i; i
0000-FE-7510 | APH - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7511 | APH - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 17 | bar: i; i
0000-FE-7512 | APH - Installation, operating and maintenance manuals | [48 empty] | R | [6 empty] | i | X |  |  | x |  | 17 | bar: W; i; i; i; i; i; i
0000-FE-7513 | APH - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 17 | bar: i; i; i
0000-FE-7514 | APH - Shipping and packing instructions | [47 empty] | A | R | [6 empty] | i | X |  |  | x |  | 17 | bar: i; i
0000-FE-7515 | APH - Index data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 17
0000-FE-7516 | APH - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [6 empty] | i | X |  |  | x
0000-FE-7517 | APH - Data book |  | W: i; i: A; i: i; i: C; i: A; i: C | [7 empty] | R | [10 empty] | i | X |  |  | x
| APH - Leak test procedure | [56 empty] | X |  |  |  |  | 21
X
7600 | PUMPS | [56 empty] | X
X
0000-FE-7600 | PUMPS - Sub-vendor monthly progress report | [41 empty] | A | R |  | i | [11 empty] | X | bar: W to i; i; i
0000-FE-7601 | PUMPS - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7602 | PUMPS - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-7603 | PUMPS - Data sheet | [56 empty] | X |  |  | x |  | 26 | bar: i; i; i; i
0000-FE-7604 | PUMPS - Data sheet of auxiliaries equipment | [56 empty] | X |  |  | x |  | 26 | bar: i; i; i; i
0000-FE-7605 | PUMPS - General arrangement drawings (GAD) |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 26
0000-FE-7606 | PUMPS - Outline drawings for off base equipment (oil console etc.) (if applicable) |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 26
0000-FE-7607 | PUMPS - Foundation layout & loading plan |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 26
0000-FE-7608 | PUMPS - Plot plan & elevation |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 26
0000-FE-7609 | PUMPS - Drawings of auxiliaries and itemized equipment supplied loose (if any) |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 26
0000-FE-7610 | PUMPS - Equipment list & line list |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7611 | PUMPS - Detailed drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7612 | PUMPS - Cross sectional and assembly drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7613 | PUMPS - Mechanical seal drawings with material list |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7614 | PUMPS - Piping - Insulation, ladder and platform support drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7615 | PUMPS - Piping - Layout & drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7616 | PUMPS - Piping - Interconnecting drawing at Battery limit |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7617 | PUMPS - Piping - Flushing auxiliaries drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7618 | PUMPS - Piping - Isometric drawings & interconnecting |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7619 | PUMPS - Critical speed analysis | [56 empty] | X |  |  | x | bar: i; i; i; i
0000-FE-7620 | PUMPS - Utility balance | [56 empty] | X |  |  | x | bar: i; i; i; i
0000-FE-7621 | PUMPS - Lubricant charts | [56 empty] | X |  |  | x | bar: i; i; i; i
0000-FE-7622 | PUMPS - Noise data sheet | [56 empty] | X |  |  | x | bar: i; i; i; i
0000-FE-7623 | PUMPS - Painting specification | [56 empty] | X |  |  | x |  | 26 | bar: i to i; i; i; i
0000-FE-7624 | PUMPS - Nameplate drawings |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7625 | PUMPS - List of spare parts |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7626 | PUMPS - List of special tools for erection and assembly |  | i: A; i: i; i: i; i: R; i: R; i: i; i: R; i: i |  | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x
0000-FE-7627 | PUMPS - Instrumentation - List of instruments (set points, ranges, alarms…) |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7628 | PUMPS - Instrumentation - List of junction boxes, control boxes, cabinets & panels |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7629 | PUMPS - Instrumentation - Instrument data sheets |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7630 | PUMPS - Instrumentation - Instrument documentation |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7631 | PUMPS - Instrumentation - Control boxes, cab.ts & panels dwgs |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7632 | PUMPS - Instrumentation - JB, terminal block, plug, connector wiring dwgs |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7633 | PUMPS - Instrumentation - Instruments, JB, control boxes, cab.ts & panel location dwgs |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7634 | PUMPS - Instrumentation - Instruments hook-up dwgs |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7635 | PUMPS - Instrumentation - Loop diagram or typical + I/O database |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7636 | PUMPS - Electrical - Consumer list & data |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7637 | PUMPS - Electrical - Motor data sheets |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 26
0000-FE-7638 | PUMPS - Electrical - Motor drawings (general arrangement detail, cross sectional…) |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7639 | PUMPS - Electrical - Motor nameplate |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7640 | PUMPS - Electrical - Torque versus speed/current/power factor curves, efficiency |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7641 | PUMPS - Electrical - Terminal box detail dwg with termination details |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-7642 | PUMPS - Quality - Inspection & Test Plan (Fabrication & quality control plan) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7643 | PUMPS - Quality - Quality assurance & HSE (Quality assurance, quality plan, ) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7644 | PUMPS - Quality - Running test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i to i; i; i; i
0000-FE-7645 | PUMPS - Quality - PWHT Procedures (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7646 | PUMPS - Quality - NDT Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7647 | PUMPS - Quality - Material certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i to i; i; i; i
0000-FE-7648 | [44 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7649 | PUMPS - Quality - Welding book (WKF, WPS, PQR) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7650 | [44 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i; i; i
0000-FE-7651 | PUMPS - Quality - Final Disposition Records (Inspection Book) (5) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 25 | bar: i to i; i; i; i
0000-FE-7652 | PUMPS - Transport - Recommendations for protection during transportation | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7653 | PUMPS - Transport - Heavy and/or large equipment drawings with weight, transportation drawings | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7654 | PUMPS - Transport - Packing list | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7655 | PUMPS - Special precautions for handling prior erection | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7656 | PUMPS - Recommendations for storage prior and during erection | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7657 | PUMPS - Procedure for erection and installation of the equipment | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7658 | PUMPS - Procedure for site assembly, leveling and welding | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7659 | PUMPS - Procedure for Installation, start-up and commissioning manuals | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7660 | PUMPS - Site performance testing procedure | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7661 | PUMPS - Operating and maintenance manuals | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7662 | PUMPS - Maintenance data sheet | [53 empty] | i |  | i | X |  |  | x |  | 25 | bar: i; i; i; i
0000-FE-7663 | PUMPS - Data Book |  | i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x |  | 25
0000-FE-7664 | PUMPS - Index data book |  | i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x |  | 25
X
7800 | STEAM DRUM | [56 empty] | X
X
0000-FE-7800 | STEAM DRUM - Sub-vendor monthly progress report |  | W: A; i: R; i: R; i: i |  |  |  |  | R | R |  | i | [11 empty] | X
0000-FE-7801 | STEAM DRUM - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-7802 | STEAM DRUM - Progress report documents list | [56 empty] | X | bar: W to i; i
| STEAM DRUM - Data sheet | [56 empty] | X |  |  |  |  | 25
0000-FE-7803 | STEAM DRUM - General assembly & detail and BOM | [38 empty] | R |  |  |  | i | [5 empty] | i |  |  |  |  | i | i | i | X |  |  | x |  | 25 | bar: W; i; i; i to i; i; i; i; i; i; i
0000-FE-7804 | STEAM DRUM - Calculation note |  | W: i; i: R; i: i; i: A; i: i; i: i | [6 empty] | A | R | [11 empty] | X |  |  | x |  | 25
0000-FE-7805 | STEAM DRUM - Spare part list |  | W: i; i: R/A; i: i; i: A; i: i; i: i | [5 empty] | i | [5 empty] | i | [7 empty] | X |  |  | x |  | 25
0000-FE-7806 | STEAM DRUM - Quality - Inspection and test plan | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7807 | STEAM DRUM - Quality - Hydrostatic pressure test procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7808 | STEAM DRUM - Quality - PMI procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7809 | STEAM DRUM - Quality - PWHT Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7810 | STEAM DRUM - Quality - Dye Penetrant Test Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7811 | STEAM DRUM - Quality - Radiography Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7812 | STEAM DRUM - Quality - Welders,NDT Operator, Consumables, Material / Certificates | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7813 | STEAM DRUM - Quality - Visual examination Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7814 | STEAM DRUM - Quality - Painting procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7815 | STEAM DRUM - Quality - Welding book | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7816 | STEAM DRUM - Quality - Dimensional Procedure | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 24 | bar: i; i; i
0000-FE-7817 | STEAM DRUM - Site storage procedure | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 24 | bar: i; i; i; i
0000-FE-7818 | STEAM DRUM - Shipping and packing instructions | [47 empty] | A | R | [7 empty] | X |  |  | x |  | 24 | bar: W; i; i; i
0000-FE-7819 | STEAM DRUM - Index data book |  | W: i; i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x |  | 24
0000-FE-7820 | STEAM DRUM - Data book |  | W: i; i: A; i: A; i: i; i: A; i: R | [7 empty] | R | [11 empty] | X |  |  | x
X
8000 | INSTRUMENTATION | [56 empty] | X
X
8000 | CONTROL VALVES | [56 empty] | X
X
0000-FE-8000 | CONTROL VALVES - Sub-vendor monthly progress report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8001 | CONTROL VALVES - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8002 | CONTROL VALVES - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8003 | CONTROL VALVES - Calculation sheet |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 31
0000-FE-8004 | CONTROL VALVES - Dimensional drawing |  | i: i; i: A; i: R; i: i; i: i |  | i | [17 empty] | X |  |  | x |  | 35
0000-FE-8005 | CONTROL VALVES - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8006 | CONTROL VALVES - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [6 empty] | A | R | [11 empty] | X |  |  | x
0000-FE-8007 | CONTROL VALVES - Quality - Painting procedure & examination with reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-8008 | CONTROL VALVES - Quality - NDT procedure and reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-8009 | CONTROL VALVES - Quality - PMI procedure and reports (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-8010 | CONTROL VALVES - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i; i
0000-FE-8011 | CONTROL VALVES - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 28 | bar: i; i; i
0000-FE-8012 | CONTROL VALVES - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 33 | bar: W; i to i; i; i
| CONTROL VALVES - Quality - Hydrostatic pressure test procedure | [56 empty] | X |  |  |  |  | 28
0000-FE-8013 | CONTROL VALVES - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8014 | CONTROL VALVES - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8015 | CONTROL VALVES - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8016 | CONTROL VALVES - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8017 | CONTROL VALVES - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 28
0000-FE-8018 | CONTROL VALVES - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8050 | ON/OFF VALVES | [56 empty] | X
X
0000-FE-8050 | ON/OFF VALVES - Sub-vendor monthly progress report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8051 | ON/OFF VALVES - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8052 | ON/OFF VALVES - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8053 | ON/OFF VALVES - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 33 | bar: W; i to i; i; i
0000-FE-8054 | ON/OFF VALVES - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8055 | ON/OFF VALVES - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8056 | ON/OFF VALVES - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8057 | ON/OFF VALVES - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8058 | ON/OFF VALVES - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 28
0000-FE-8059 | ON/OFF VALVES - Calculation sheet |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 31
0000-FE-8060 | ON/OFF VALVES - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 33
0000-FE-8061 | ON/OFF VALVES - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8062 | ON/OFF VALVES - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8063 | ON/OFF VALVES - Quality - SIL certificate |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8064 | ON/OFF VALVES - Quality - Painting procedure & examination with reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8065 | ON/OFF VALVES - Quality - NDT procedure and reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8066 | ON/OFF VALVES - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8067 | ON/OFF VALVES - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 28 | bar: i; i
0000-FE-8068 | ON/OFF VALVES - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8100 | SAFETY RELIEF VALVES | [56 empty] | X
X
0000-FE-8100 | SAFETY RELIEF VALVES - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8101 | SAFETY RELIEF VALVES - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8102 | SAFETY RELIEF VALVES - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8103 | SAFETY RELIEF VALVES - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 33 | bar: W; i to i; i; i
0000-FE-8104 | SAFETY RELIEF VALVES - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8105 | SAFETY RELIEF VALVES - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8106 | SAFETY RELIEF VALVES - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8107 | SAFETY RELIEF VALVES - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8108 | SAFETY RELIEF VALVES - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 28
0000-FE-8109 | SAFETY RELIEF VALVES - Calculation sheet |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 31
0000-FE-8110 | SAFETY RELIEF VALVES - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 33
0000-FE-8111 | SAFETY RELIEF VALVES - Quality - Painting procedure & examination with reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8112 | SAFETY RELIEF VALVES - Quality - NDT procedure and reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8113 | SAFETY RELIEF VALVES - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8114 | SAFETY RELIEF VALVES - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 28 | bar: i; i
0000-FE-8115 | SAFETY RELIEF VALVES - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8150 | PNEUMATIC ACTUATOR | [56 empty] | X
X
0000-FE-8150 | PNEUMATIC ACTUATOR - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8151 | PNEUMATIC ACTUATOR - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8152 | PNEUMATIC ACTUATOR - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8153 | PNEUMATIC ACTUATOR - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8154 | PNEUMATIC ACTUATOR - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8155 | PNEUMATIC ACTUATOR - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8156 | PNEUMATIC ACTUATOR - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8157 | PNEUMATIC ACTUATOR - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8158 | PNEUMATIC ACTUATOR - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 36
0000-FE-8159 | PNEUMATIC ACTUATOR - General arrangement drawing & operating diagram |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 39
0000-FE-8160 | PNEUMATIC ACTUATOR - Quality - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8161 | PNEUMATIC ACTUATOR - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8162 | PNEUMATIC ACTUATOR - Quality - NDT procedure and reports | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8163 | PNEUMATIC ACTUATOR - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8164 | PNEUMATIC ACTUATOR - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 36 | bar: i; i
0000-FE-8165 | PNEUMATIC ACTUATOR - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8200 | O2 & CO ANALYSER | [56 empty] | X
X
0000-FE-8200 | O2 & CO ANALYSER - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8201 | O2 & CO ANALYSER - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8202 | O2 & CO ANALYSER - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8203 | O2 & CO ANALYSER - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 46 | bar: W; i to i; i; i
0000-FE-8204 | O2 & CO ANALYSER - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8205 | O2 & CO ANALYSER - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8206 | O2 & CO ANALYSER - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8207 | O2 & CO ANALYSER - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8208 | O2 & CO ANALYSER - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 36
0000-FE-8209 | O2 & CO ANALYSER - General arrangement drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 39
0000-FE-8210 | O2 & CO ANALYSER - Pneumatic connection drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8211 | O2 & CO ANALYSER - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8212 | O2 & CO ANALYSER - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8213 | O2 & CO ANALYSER - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8250 | DENSITY METER | [56 empty] | X
X
0000-FE-8250 | DENSITY METER - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8251 | DENSITY METER - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8252 | DENSITY METER - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8253 | DENSITY METER - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 46 | bar: W; i to i; i; i
0000-FE-8254 | DENSITY METER - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8255 | DENSITY METER - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8256 | DENSITY METER - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8257 | DENSITY METER - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8258 | DENSITY METER - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x |  | 36
0000-FE-8259 | DENSITY METER - General arrangement drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 39
0000-FE-8260 | DENSITY METER - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8261 | DENSITY METER - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8262 | DENSITY METER - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8300 | ORIFICE PLATE | [56 empty] | X
X
0000-FE-8300 | ORIFICE PLATE - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8301 | ORIFICE PLATE - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8302 | ORIFICE PLATE - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8303 | ORIFICE PLATE - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8304 | ORIFICE PLATE - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8305 | ORIFICE PLATE - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8306 | ORIFICE PLATE - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8307 | ORIFICE PLATE - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8308 | ORIFICE PLATE - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8309 | ORIFICE PLATE - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8310 | ORIFICE PLATE - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8350 | LEVEL GAUGE | [56 empty] | X
X
0000-FE-8350 | LEVEL GAUGE - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8351 | LEVEL GAUGE - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8352 | LEVEL GAUGE - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8353 | LEVEL GAUGE - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8354 | LEVEL GAUGE - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X
0000-FE-8355 | LEVEL GAUGE - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8356 | LEVEL GAUGE - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X | bar: i; i; i
0000-FE-8357 | LEVEL GAUGE - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8358 | LEVEL GAUGE - Index data book |  | W: i; i: A; i: i; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8359 | LEVEL GAUGE - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8360 | LEVEL GAUGE - Electrical connection wiring (lighting) |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8361 | LEVEL GAUGE - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8362 | LEVEL GAUGE - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8363 | LEVEL GAUGE - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 36 | bar: i; i
0000-FE-8364 | LEVEL GAUGE - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8400 | RADAR LEVEL | [56 empty] | X
X
0000-FE-8400 | RADAR LEVEL - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8401 | RADAR LEVEL - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8402 | RADAR LEVEL - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8403 | RADAR LEVEL - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8404 | RADAR LEVEL - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8405 | RADAR LEVEL - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8406 | RADAR LEVEL - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8407 | RADAR LEVEL - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8408 | RADAR LEVEL - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8409 | RADAR LEVEL - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8410 | RADAR LEVEL - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8411 | RADAR LEVEL - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8412 | RADAR LEVEL - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8413 | RADAR LEVEL - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 36 | bar: i; i
0000-FE-8414 | RADAR LEVEL - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8450 | PRESSURE & DP FLOW TRANSMITTER | [56 empty] | X
X
0000-FE-8450 | PRESSURE & DP FLOW TRANSMITTER - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8451 | PRESSURE & DP FLOW TRANSMITTER - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8452 | PRESSURE & DP FLOW TRANSMITTER - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8453 | PRESSURE & DP FLOW TRANSMITTER - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8454 | PRESSURE & DP FLOW TRANSMITTER - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8455 | PRESSURE & DP FLOW TRANSMITTER - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8456 | PRESSURE & DP FLOW TRANSMITTER - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8457 | PRESSURE & DP FLOW TRANSMITTER - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8458 | PRESSURE & DP FLOW TRANSMITTER - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8459 | PRESSURE & DP FLOW TRANSMITTER - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8460 | PRESSURE & DP FLOW TRANSMITTER - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8461 | PRESSURE & DP FLOW TRANSMITTER - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8462 | PRESSURE & DP FLOW TRANSMITTER - Quality - SIL certificate |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8463 | PRESSURE & DP FLOW TRANSMITTER - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8500 | PRESSURE GAUGE | [56 empty] | X
X
0000-FE-8500 | PRESSURE GAUGE - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8501 | PRESSURE GAUGE - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8502 | PRESSURE GAUGE - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8503 | PRESSURE GAUGE - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8504 | PRESSURE GAUGE - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8505 | PRESSURE GAUGE - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8506 | PRESSURE GAUGE - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8507 | PRESSURE GAUGE - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8508 | PRESSURE GAUGE - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8509 | PRESSURE GAUGE - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8510 | PRESSURE GAUGE - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8550 | DRAFT GAUGE | [56 empty] | X
X
0000-FE-8550 | DRAFT GAUGE - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8551 | DRAFT GAUGE - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8552 | DRAFT GAUGE - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8553 | DRAFT GAUGE - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8554 | DRAFT GAUGE - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8555 | DRAFT GAUGE - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8556 | DRAFT GAUGE - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8557 | DRAFT GAUGE - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8558 | DRAFT GAUGE - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8559 | DRAFT GAUGE - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8560 | DRAFT GAUGE - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8600 | TEMPERATURE ELEMENT & THERMOWELL | [56 empty] | X
X
0000-FE-8600 | TEMPERATURE ELEMENT & THERMOWELL - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8601 | TEMPERATURE ELEMENT & THERMOWELL - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8602 | TEMPERATURE ELEMENT & THERMOWELL - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8603 | TEMPERATURE ELEMENT & THERMOWELL - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8604 | TEMPERATURE ELEMENT & THERMOWELL - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8605 | TEMPERATURE ELEMENT & THERMOWELL - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8606 | TEMPERATURE ELEMENT & THERMOWELL - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8607 | TEMPERATURE ELEMENT & THERMOWELL - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8608 | TEMPERATURE ELEMENT & THERMOWELL - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8609 | TEMPERATURE ELEMENT & THERMOWELL - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8610 | TEMPERATURE ELEMENT & THERMOWELL - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8611 | TEMPERATURE ELEMENT & THERMOWELL - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8612 | TEMPERATURE ELEMENT & THERMOWELL - Quality - PWHT Procedure (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x | bar: i; i
0000-FE-8613 | TEMPERATURE ELEMENT & THERMOWELL - Quality - Welding book (if applicable) | [43 empty] | A | R | [11 empty] | X |  |  | x |  | 36 | bar: i; i
0000-FE-8614 | TEMPERATURE ELEMENT & THERMOWELL - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8650 | SKIN THERMOCOUPLE | [56 empty] | X
X
0000-FE-8650 | SKIN THERMOCOUPLE - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8651 | SKIN THERMOCOUPLE - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8652 | SKIN THERMOCOUPLE - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8653 | SKIN THERMOCOUPLE - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8654 | SKIN THERMOCOUPLE - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8655 | SKIN THERMOCOUPLE - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8656 | SKIN THERMOCOUPLE - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8657 | SKIN THERMOCOUPLE - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8658 | SKIN THERMOCOUPLE - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8659 | SKIN THERMOCOUPLE - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8660 | SKIN THERMOCOUPLE - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8661 | SKIN THERMOCOUPLE - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8700 | TEMPERATURE TRANSMITTER | [56 empty] | X
X
0000-FE-8700 | TEMPERATURE TRANSMITTER - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8701 | TEMPERATURE TRANSMITTER - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8702 | TEMPERATURE TRANSMITTER - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8703 | TEMPERATURE TRANSMITTER - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8704 | TEMPERATURE TRANSMITTER - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8705 | TEMPERATURE TRANSMITTER - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8706 | TEMPERATURE TRANSMITTER - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8707 | TEMPERATURE TRANSMITTER - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8708 | TEMPERATURE TRANSMITTER - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8709 | TEMPERATURE TRANSMITTER - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8710 | TEMPERATURE TRANSMITTER - Electrical connection wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8711 | TEMPERATURE TRANSMITTER - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8712 | TEMPERATURE TRANSMITTER - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 0
X
8750 | JUNCTION BOX | [56 empty] | X
X
0000-FE-8750 | JUNCTION BOX - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8751 | JUNCTION BOX - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8752 | JUNCTION BOX - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8753 | JUNCTION BOX - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8754 | JUNCTION BOX - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8755 | JUNCTION BOX - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8756 | JUNCTION BOX - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8757 | JUNCTION BOX - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8758 | JUNCTION BOX - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8759 | JUNCTION BOX - General arrangement drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8760 | JUNCTION BOX - Internal electrical wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8761 | JUNCTION BOX - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8762 | JUNCTION BOX - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8800 | LOCAL PANEL | [56 empty] | X
X
0000-FE-8800 | LOCAL PANEL - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8801 | LOCAL PANEL - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8802 | LOCAL PANEL - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8803 | LOCAL PANEL - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8804 | LOCAL PANEL - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8805 | LOCAL PANEL - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8806 | LOCAL PANEL - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8807 | LOCAL PANEL - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8808 | LOCAL PANEL - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8809 | LOCAL PANEL - General arrangement drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8810 | LOCAL PANEL - Internal electrical wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8811 | LOCAL PANEL - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8812 | LOCAL PANEL - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8850 | ELECTRICAL BULK (cable, cable trays, cable glands, hook-up accessories, supports) | [56 empty] | X
X
0000-FE-8850 | ELECTRICAL BULK - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8851 | ELECTRICAL BULK - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8852 | ELECTRICAL BULK - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8853 | ELECTRICAL BULK - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8854 | ELECTRICAL BULK - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8855 | ELECTRICAL BULK - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8856 | ELECTRICAL BULK - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8857 | ELECTRICAL BULK - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8858 | ELECTRICAL BULK - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8859 | ELECTRICAL BULK - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8860 | ELECTRICAL BULK - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8861 | ELECTRICAL BULK - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8900 | INSTRUMENT PROTECTION BOX | [56 empty] | X
X
0000-FE-8900 | INSTRUMENT PROTECTION BOX - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8901 | INSTRUMENT PROTECTION BOX - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8902 | INSTRUMENT PROTECTION BOX - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8903 | INSTRUMENT PROTECTION BOX - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8904 | INSTRUMENT PROTECTION BOX - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8905 | INSTRUMENT PROTECTION BOX - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8906 | INSTRUMENT PROTECTION BOX - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8907 | INSTRUMENT PROTECTION BOX - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8908 | INSTRUMENT PROTECTION BOX - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8909 | INSTRUMENT PROTECTION BOX - Dimensional drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8910 | INSTRUMENT PROTECTION BOX - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
8950 | AIRCRAFT WARNING LIGHT | [56 empty] | X
X
0000-FE-8950 | AIRCRAFT WARNING LIGHT - Sub-vendor monthly report | [41 empty] | A | R | [13 empty] | X | bar: W to i; i
0000-FE-8951 | AIRCRAFT WARNING LIGHT - Fabrication schedule |  | W: A; i: R; i: i |  |  |  |  | A | R |  | i | [11 empty] | X
0000-FE-8952 | AIRCRAFT WARNING LIGHT - Progress report documents list | [56 empty] | X | bar: W to i; i
0000-FE-8953 | AIRCRAFT WARNING LIGHT - Quality - Inspection and test plan | [44 empty] | R | [11 empty] | X |  |  |  |  | 41 | bar: W; i to i; i; i
0000-FE-8954 | AIRCRAFT WARNING LIGHT - Spare part list |  | W: i; i: R/A; i: i; i: i; i: i | [5 empty] | i | [5 empty] | i | [5 empty] | W | i | X |  |  |  |  | 0
0000-FE-8955 | AIRCRAFT WARNING LIGHT - Shipping and packing instructions | [47 empty] | A | R | [5 empty] | W | i | X | bar: i; i
0000-FE-8956 | AIRCRAFT WARNING LIGHT - Site storage procedure | [47 empty] | A | R | [6 empty] | i | X |  |  |  |  | 0 | bar: i; i; i
0000-FE-8957 | AIRCRAFT WARNING LIGHT - Instruction, operating and maintenance manual |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  | x
0000-FE-8958 | AIRCRAFT WARNING LIGHT - Index data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X |  |  |  |  | 36
0000-FE-8959 | AIRCRAFT WARNING LIGHT - General arrangement drawing |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x |  | 43
0000-FE-8960 | AIRCRAFT WARNING LIGHT - Internal electrical wiring |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8961 | AIRCRAFT WARNING LIGHT - Quality - ATEX / GOST certificates |  | i: A; i: R; i: i; i: i | [19 empty] | X |  |  | x
0000-FE-8962 | AIRCRAFT WARNING LIGHT - Data book |  | W: i; i: A; i: i; i: A; i: R | [7 empty] | R | [10 empty] | i | X
X
0000-FG | SKETCHES & STUDIES | [56 empty] | X
X
0000-FG-001 | Key design sketches | [56 empty] | X | bar: i; i to i; i to i
X
0000-FJ | PROCESS | [56 empty] | X
X
0000-FJ-001 | DATA SHEET - Heater |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i; i: i; i: i; i: i; i: i; i: i |  | i | [5 empty] | i | [11 empty] | X |  | x | x |  | 4 | PO
0000-FJ-201 | DATA SHEET - Burner |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X |  |  | x |  | 5
X
700 | Equipments | [56 empty] | X
X
0000-FJ-720 | DATA SHEET - Fans |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X | x |  | x |  | 8 | PO
0000-FJ-740 | DATA SHEET - APH/Saph |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X | x |  | x |  | 6 | PO
0000-FJ-760 | DATA SHEET - Pump |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X | x |  | x |  | 10 | PO
0000-FJ-780 | DATA SHEET - Steam drum |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: C; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X | x |  | x |  | 10 | PO
0000-FJ-700 | DATA SHEET - Sootblower | [56 empty] | X |  |  |  |  | 8 | PO
X
800 | Process Instrument DS |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i | [19 empty] | X
X
0000-FJ-801 | Functional Analysis |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i | [19 empty] | X |  |  |  |  | 16 | PO
0000-FJ-802 | Control loop description | [56 empty] | X |  |  |  |  | 22 | PO
| DATA PROCESS - Control valve |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 15 | PO
| DATA PROCESS - Pressure safety valve |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 15 | PO
| DATA PROCESS - Flow element |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 25 | PO
| DATA PROCESS - Pressure instrument |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 25 | PO
| DATA PROCESS - Level instrument |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 25 | PO
| DATA PROCESS - Temperature instrument |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 25 | PO
| DATA PROCESS - Analyser |  | W: i; i: A; i: W; i: i; i: i; i: C; i: i; i: i | [19 empty] | X |  |  | x |  | 25 | PO
0000-FJ-810 | DATA SHEET - Silencers |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X |  |  | x |  | 25 | PO
| DATA SHEET - Desuperheater |  | W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i |  | i |  |  |  | i |  | i | [9 empty] | X |  |  | x |  | 25 | PO
X
900 | Operating & Maintenance Manual | [56 empty] | X
X
0000-FJ-901 | Operating & Maintenance Manual |  | i: i; W: i; i: A; i: W; i: i; i: i; i: i; i: i; i: i; i: i |  | i | [5 empty] | i | [11 empty] | X |  |  | x |  | 30 | PO
X
0000-FK | PROCESS WORK SHEETS | [56 empty] | X
X
0000-FK-001 | SCHEMATIC VIEW-ELEVATION |  | W: i; i: i; i: C; i: W; i: i; i: i; i: i | [19 empty] | X
0000-FK-002 | SCHEMATIC VIEW-PLAN VIEW |  | W: i; i: i; i: C; i: W; i: i; i: i; i: i | [19 empty] | X
x | Tube wall calculation, FG T° across convection coils | [56 empty] | X | bar: i; i; i; i; i; i
- | Outside casing T° | [56 empty] | X | bar: i; i to i; i to i; i
- | Others | [56 empty] | X | bar: i; i; i; i
X
H000-FL | LICENCOR and / or CLIENT DOCUMENTATION | [56 empty] | X
X
0000 | General | [38 empty] | i | [5 empty] | i | [7 empty] | i | i | i | i | X |  | W | bar: W; i; i to i; i to i; i to i; i; i to i; i
1000 | Tube & fittings | [38 empty] | i | [5 empty] | i | [7 empty] | i | i | i | i | X |  | W | bar: i; i; i; i; i to i; i; i
2000 | BURNERs | [38 empty] | i | [5 empty] | i | [11 empty] | X |  | W | bar: W; i; i; i; i; i
3000 | Casing & structure | [44 empty] | i | [7 empty] | i | i | i | i | X |  | W | bar: i; i to i; i to i; i
4000 | Coil & Manifolds | [44 empty] | i | [7 empty] | i | i | i | i | X |  | W | bar: i; i; i; i; i; i
5000 | Insulation | [44 empty] | i | [7 empty] | i | i | i | i | X |  | W | bar: i; i; i; i; i
6000 | Cast pieces | [44 empty] | i | [11 empty] | X |  | W | bar: i; i; i; i; i
7000 | Equipments (Steam Drum, Fan, APH, Soot blower…) | [38 empty] | i | [5 empty] | i | [11 empty] | X |  | W | bar: W; i; i to i; i; i; i; i; i
8000 | Instrumentation | [52 empty] | i | i |  |  | X |  | W | bar: i; i to i; i; i
9000 | Transport, packing, Commissioning & start up | [42 empty] | i | [5 empty] | i | [7 empty] | X |  | W | bar: W; i; i to i; i to i; i to i; i
4500 | Piping | [38 empty] | i | [13 empty] | i | i | i | i | X |  | W | bar: i; i; i to i; i
X
0000-FM | 3D MODEL | [56 empty] | X
X
0000-FM-001 | Heater 3D Model (30%) |  | W: i; i: i; i: i; i: i; i: i; i: i; i: A; i: W; i: i; i: i; i: i |  | i | [13 empty] | i | i | i | i | X |  | x |  |  | 9 | 5w DS heater
0000-FM-002 | Heater 3D Model (60%) | [56 empty] | X |  |  |  |  | 14
0000-FM-003 | Heater 3D Model (90%) | [56 empty] | X |  |  |  |  | 19
4000 | Piping 3D Model | [38 empty] | W | [13 empty] | i | i | i | i | X |  | x | bar: W; i; i; i; i; i; i to i
0000‐FM‐4001 | PIPING ‐ SKID | [38 empty] | W | [15 empty] | i |  | X |  |  | x |  | 24 | bar: W; i; i; i; i to i
0000‐FM‐4002 | PIPING ‐ HEATER | [38 empty] | W | [15 empty] | i |  | X |  |  | x |  | 26 | bar: W; i; i; i; i to i
0000‐FM‐4003 | PIPING ‐ STEAM GENERATION | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4004 | PIPING ‐ UTILITIES HPRUS | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4021 | PIPING ‐ PRIMARY SUPPORTS‐SKID | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4022 | PIPING - PRIMARY SUPPORTS‐HEATER | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4023 | PIPING - PRIMARY SUPPORTS‐STEAM GENERATION | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4024 | PIPING - PRIMARY SUPPORTS‐UTILITIES | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4025 | PIPING - SECONDARY SUPPORTS‐SKID (FRAME) | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4026 | PIPING - SECONDARY SUPPORTS‐HEATER | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4027 | PIPING - SECONDARY SUPPORTS‐STEAM GENERATION | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
0000‐FM‐4028 | PIPING - SECONDARY SUPPORTS‐UTILITIES HPRUS | [38 empty] | W | [15 empty] | i |  | X |  |  | x | bar: W; i; i; i; i to i
X
0000-FN | Material Requisition with Particular Requirement | [56 empty] | X
X
0000 | General |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
100 | Tube & fittings: CS & Alloy steel |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
0000-FN-101 | SEAMLESS STEEL PIPE (AS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-102 | SEAMLESS STEEL PIPE (AS) |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-103 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-104 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-105 | SEAMLESS STEEL PIPE (AS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-106 | SEAMLESS STEEL PIPE (AS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-107 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-108 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-109 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-110 | SEAMLESS STEEL PIPE (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-111 | EXTRUDED PIPE (AS) |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-130 | ELBOWS (CS ) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-131 | ELBOWS (AS ) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-132 | REDUCING TEES (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-133 | CAPS (CS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-134 | FORGED STUB |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-160 | FLANGES (CS ) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-161 | FLANGES (AS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-162 | FLANGES (AS) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-180 | STUD BOLTS WITH 2 HEAVY NUTS |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-181 | SPIRAL WOUND GASKET |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
- | Tube & fittings: SS and higher |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
300 | Steel plate, beams, accessories | [56 empty] | X
X
0000-FN-301 | Drop warp tape |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-302 | Sealing sleeves |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-303 | Ceramic fiber materials (rope, cloth , packing) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-304 | Name plate |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-305 | Mastic |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-306 | Winch control |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-306 to 330 | 25/20 materials (pipes for istrument., plates,..) |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
400 | Extended surface, spring supports | [56 empty] | X
X
0000-FN-401 | BENDING PIPE |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-402 | FINNED PIPE |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-403 | FINNED PIPE |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-404 | FINNED PIPE |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-410 | SPRING SUPPORT |  | W: A; i: i; i: i; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
500 | Insulation | [56 empty] | X
X
600 | Cast pieces | [56 empty] | X
X
0000-FN-601 | MATERIAL REQUISITION - TUBE SHEET STEAM SUPERHEATER |  | W: A; i: i; i: A; i: i; i: W; i: i; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-602 | MATERIAL REQUISITION - TUBE SHEET UPPER STEAM GENERATION (1/2) |  | W: A; i: i; i: A; i: i; i: W; i: i; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-603 | MATERIAL REQUISITION - TUBE SHEET UPPER STEAM GENERATION (2/2) |  | W: A; i: i; i: A; i: i; i: W; i: i; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-604 | MATERIAL REQUISITION - TUBE SHEET LOWER BFW |  | W: A; i: i; i: A; i: i; i: W; i: i; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-605 | MATERIAL REQUISITION - TUBE SHEET UPPER BFW |  | W: A; i: i; i: A; i: i; i: W; i: i; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FN-606 | MATERIAL REQUISITION - OBSERVATION WINDOW |  | W: A; i: i; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
890 | Instrumentations | [56 empty] | X
X
0000-NT-801 | MATERIAL REQUISITION ‐ CONTROL VALVE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-802 | MATERIAL REQUISITION ‐ ON/OFF VALVE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-803 | MATERIAL REQUISITION ‐ SAFETY RELIEF VALVE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-805 | MATERIAL REQUISITION ‐ PNEUMATIC ACTUATOR |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-810 | MATERIAL REQUISITION ‐ O2 & COe ANALYSER |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-811 | MATERIAL REQUISITION ‐ DENSITY METER |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-820 | MATERIAL REQUISITION ‐ ORIFICE PLATE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-830 | MATERIAL REQUISITION ‐ LEVEL GAUGE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-831 | MATERIAL REQUISITION ‐ RADAR LEVEL TRANSMITTER |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-840 | MATERIAL REQUISITION ‐ PRESSURE & DP FLOW TRANSMITTER |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-841 | MATERIAL REQUISITION ‐ PRESSURE GAUGE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-842 | MATERIAL REQUISITION ‐ DRAFT GAUGE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-850 | MATERIAL REQUISITION ‐ THERMOWELL & TEMPERATURE ELEMENT |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-851 | MATERIAL REQUISITION ‐ SKIN THERMOCOUPLE |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-852 | MATERIAL REQUISITION ‐ TEMPERATURE TRANSMITTER |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-860 | MATERIAL REQUISITION ‐ INTRUMENT PROTECTION BOX |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-870 | MATERIAL REQUISITION ‐ LOCAL PANEL |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-871 | MATERIAL REQUISITION ‐ JUNCTION BOX |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-880 | MATERIAL REQUISITION ‐ BULK |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-NT-890 | MATERIAL REQUISITION ‐ AIRCRAFT WARNING LIGHT |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X
0000-FN-891 | MATERIAL REQUISITION ‐ Skin thermocouples |  | W: A; i: i; i: i; i: C; i: C; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
4400 | Valves,bulk piping , | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
X
0000‐FN‐4400 | MATERIAL REQUISITION ‐ PIPES (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4401 | MATERIAL REQUISITION ‐ FLANGES (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4402 | MATERIAL REQUISITION ‐ ELBOWS (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4403 | MATERIAL REQUISITION ‐ REDUCERS (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4404 | MATERIAL REQUISITION ‐ TEES (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4405 | MATERIAL REQUISITION ‐ CAPS (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4406 | MATERIAL REQUISITION ‐ MISCELLANEOUS ITEMS (CS & LTCS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4407 | MATERIAL REQUISITION ‐ GASKETS5 | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4408 | MATERIAL REQUISITION ‐ HARDWARE5 | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4410 | MATERIAL REQUISITION ‐ PIPES (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4411 | MATERIAL REQUISITION ‐ FLANGES (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4412 | MATERIAL REQUISITION ‐ ELBOWS (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4413 | MATERIAL REQUISITION ‐ REDUCERS (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4414 | MATERIAL REQUISITION ‐ TEES (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4415 | MATERIAL REQUISITION ‐ CAPS (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000‐FN‐4416 | MATERIAL REQUISITION ‐ MISCELLANEOUS ITEMS (SS) | [38 empty] | W |  | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i to i
0000-FN-4440 | MATERIAL REQUISITION - Spring supports | [56 empty] | X
X
0000-FQ | QUALITY CONTROL | [56 empty] | X
X
0000-FQ-001 | Scope of inspection Heater and Equipment & Appendix |  | W: A; i: i; i: C; i: C; i: C; i: i; i: i |  | C | [5 empty] | W | [7 empty] | i | i | C | i | X |  |  | x |  | 9
0000-FQ-002 | Quality assurance plan |  | i: W; W: A; i: i; i: i; i: i | [19 empty] | X |  |  | x
0000-FQ-003 | Manufacturing Data Book Index | [44 empty] | W | [11 empty] | X |  |  | x |  | 2 months after last delivery | bar: W; i; i to i
0000-FQ-004 | Manufacturing Data Book | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-005 | Mechanical Data Book Index | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-006 | Mechanical Data Book | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-007 | Erection Data Book Index | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-008 | Erection Data Book | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-009 | Installation Operating Maintenance Manuel | [56 empty] | X |  |  |  |  | 2 months after last delivery
0000-FQ-010 | Inspection schedule | [42 empty] | i |  | W |  |  |  | i | [7 empty] | X | bar: W to i; i; i to i
| Inspection Report | [40 empty] | i |  | i |  | W |  | i |  | i |  |  |  | i | i | i | i | X | bar: W to i; i; i to i
| non conformity |  | i: W; W: i; i: i; i: i; i: C; i: C; i: C; i: C; i: i; i: i |  |  |  |  | C |  |  | W |  |  | C |  |  |  | C |  |  |  |  | X
- | Inspection release note | [42 empty] | i |  | W |  |  |  | i | [7 empty] | X | bar: W to i; i; i to i
X
0000-FR | TRANSPORT | [56 empty] | X
X
0000-FR-001 | Packing List | [42 empty] | W | [5 empty] | W | [7 empty] | X | bar: W
X
0000-FS | TECHNICAL SPECIFICATION | [56 empty] | X
X
200 | BURNERs specification |  | W: A; i: A; i: W; i: i; i: i; i: C; i: C; i: i; i: i; i: i |  | C |  | i |  |  |  | i |  | i | [9 empty] | X |  |  |  |  | 12 |  | Process document
X
300 | General prefabrication heater | [38 empty] | i | [5 empty] | i | [6 empty] | i | i | i | C | i | X | bar: W; i; i; i; i; i
X
400 | Prefab Coils & Manifolds | [44 empty] | i | [7 empty] | i | i | i | i | X | bar: W; i; i; i; i to i
X
450 | Piping prefabrication | [56 empty] | X
X
500 | Lining application | [44 empty] | i | [7 empty] | i | i | i | i | X |  |  |  |  | 8 | DS heater, GA | Project document | bar: W; i; i; i; i to i
X
600 | Cast pieces | [40 empty] | i |  |  |  | i |  | i | [9 empty] | X | bar: W; i; i; i; i to i
X
700 | Equipment (Steam Drum, Fan, APH) | [56 empty] | X |  |  |  |  | 12 |  | Process document for APH, Fan, Saph | Steam drum by BE | Sootblower by ? | bar: i to i
X
0000-FS-761 | CENTRIFUGAL PUMPS AND MOTORS - TECHNICAL SPECIFICATION |  | W: A; i: A; i: W; i: i; i: C; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FS-781 | STEAN DISENGAGING DRUM - TECHNICAL SPECIFICATION |  | W: A; i: i; i: C; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
0000-FS-782 | STEAN SEPARATOR - TECHNICAL SPECIFICATION |  | W: A; i: i; i: C; i: i; i: i |  |  |  | i |  |  |  | i |  | i | [9 empty] | X
X
800 | E & I FOR SHOP ERECTION |  | W: i; i: i; i: A; i: W | [15 empty] | i | i |  | i | X
X
0000-FS-801 | CONTROL VALVE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 18
0000-FS-802 | ON/OFF VALVE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 19
0000-FS-803 | SAFETY RELIEF VALVE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 18
0000-FS-804 | FLAME DETECTOR SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 14
0000-FS-805 | PNEUMATIC ACTUATOR SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-810 | O2 & COe ANALYSER SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 28
0000-FS-811 | DENSITY METER SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-820 | ORIFICE PLATE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x |  | 28
0000-FS-830 | LEVEL GAUGE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-831 | RADAR LEVEL TRANSMITTER SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-840 | PRESSURE & DP FLOW TRANSMITTER SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-841 | PRESSURE GAUGE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-842 | DRAFT GAUGE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-850 | THERMOWELL & TEMPERATURE ELEMENT SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-851 | SKIN THERMOCOUPLE SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-852 | TEMPERATURE TRANSMITTER SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-860 | INTRUMENT PROTECTION BOX SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-870 | LOCAL PANEL SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-871 | JUNCTION BOX SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-880 | BULK SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
0000-FS-890 | AIRCRAFT WARNING LIGHT SPECIFICATION |  | W: A; i: i; i: A; i: W; i: i; i: i |  |  |  | i |  |  |  | i | [11 empty] | X |  |  | x
X
900 | spare parts | [44 empty] | i |  |  | A | W |  |  |  | i | i | C | i | X | bar: W; i; i; i; i to i
X
0000-FS-901 | COMMISSIONNING AND START UP - SPARE PART LIST |  | W: A; i: C; i: W; i: W; i: i; i: i |  | W |  | W | [15 empty] | X |  |  |  |  | 24
0000-FS-902 | SPARE PARTS LIST FOR YEARS OPERATION |  | W: A; i: C; i: W; i: W; i: i; i: i |  | W |  | W | [15 empty] | X |  |  |  |  | 24
X
9XX | Erection | [56 empty] | X
0000-FS-9XX | ERECTION PROCEDURE | [56 empty] | X |  |  |  |  | 2 months before the first delivery
0000-FS-9XX | ERECTION DRAWING | [56 empty] | X |  |  |  |  | 2 months before the first delivery
X
950 | Transport specification (packing) | [56 empty] | X
X
4000 | piping | [56 empty] | X
X
0000‐FS‐4000 | PIPING CLASS |  | W: i; i: i; i: i; i: A; i: W; i: C; i: i; i: i; i: i |  | i | [13 empty] | i | i | i | i | X |  |  | x |  | 18
0000‐FS‐4001 | LINE DESIGNATION LIST | [56 empty] | X |  |  |  |  | 16 | bar: i to i
0000‐FS‐4002 | TIES-IN LIST | [38 empty] | W | [13 empty] | i | i | i | C | X |  |  |  |  | 14 | bar: i to i
PROJECT DOCUMENT MATRIX

## Inputs
MASTER DOCUMENT LIST GENERATION TOOL - FOR PROPOSAL
GENERAL DATA |  |  |  |  | HEATER(S) TAG(S)
HPC Proposal Number: |  | EP18020 |  |  | H-510-09A |  | Done by | D.LUSTOSA
Stard Date (expected): |  | 2018-09-15 |  |  | H-510-09B |  | Revision | 2
Duration expected (months): |  | 2 |  |  |  |  | Date | 2019-02-18
Finish Date (expected): |  | 2018-11-14
Client Project Reference: |  | N°3000864
Client: |  | NYNAS |  |  |  | NOT GENERATED WITH THE TOOL! NOT THE USUAL HPC SCOPE
Project Name: |  | BED HEATER - New Heater Gothenburg Refinery
Technical Requisition Ref.:
SCOPE SELECTION |  |  |  | ATTENTION
ENGINEERING |  | OTHERS |  | Keep list as a minimum during proposal stage!
HEATER | TRUE | INCLUDE SUB-VENDOR DOCUMENTS (FE) | FALSE | Start with HEATER, add items as needed - HEATER is based on DOC CONTROL recommendations for MDL
E&I SIMPLE | TRUE |  |  | Please check the list after it has ben generated!
E&I COMPLEX | FALSE | ERECTION DOCUMENTS | TRUE | Include new documents if necessary. HPF Doc Matrix is on this tool to be consulted!
PIPING | TRUE | CONVECTION SERVICES
SUPPLY |  | BFW / SSH / SGEN | TRUE
APH | FALSE |  |  | NOTES
sAPH | FALSE |  |  | Heater comprises heater + burner documentation issued by HPC - minimum scope
FANS & MOTORS | TRUE |  |  | E&I Simple comprises heater instruments only (Pressure, Temperature, Analyzers, Damper actuator)
SOOTBLOWERS | FALSE
SPRING SUPPORTS | FALSE
PUMP | FALSE |  |  | Piping comprises all piping skids documentation
STEAM DRUM | FALSE
AWL | FALSE
TURBINE | FALSE
Generate List

## PDL
WEEKLY | ITEM | ITEMS | HP DOCUMENT N° | X TRS Num. | TRANSMITTAL DATE | Y SCHEDULE RETURN DATE | Y CRS Num. | RETURN DATE | DOCUMENT STATUS | X REPLY CRS DATE | TRS NUMBER | Y STATUS | CRS N° | FINAL STATUS | TODAY | X EXPECTED DATE | X DELAY | Y DELAY
S02 | 1 | AD/VD | EF18012-09AV-FA-001 | TRS-00002 | 2019-01-07 | 2019-01-14 | TRS_00002 | 2019-01-14 | A |  |  |  |  | A | 2019-02-18 | 2019-01-21 | 0 | 0
S13 | 2 | AD/VD | EF18012-09AV-FA-002 | [11 empty] | 2019-02-18
S02 | 3 | AD/VD | EF18012-09AV-FA-003 | TRS-00002 | 2019-01-07 | 2019-01-14 | TRS_00002 | 2019-01-14 | C | 2019-01-18 | TRS-00006 |  |  |  | 2019-02-18 | 2019-01-21 | 0 | 0
S02 | 3 | AD/VD | EF18012-09AV-FA-003 | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0010 | 2019-01-28 | C | 2019-02-05 | TRS-00016 | C | TRS-0018 |  | 2019-02-18 | 2019-02-04 | 0 | 0
S18 | 4 | AD/VD | EF18012-09AV-FA-004 | [11 empty] | 2019-02-18
S18 | 5 | AD/VD | EF18012-09AV-FA-005 | [11 empty] | 2019-02-18
S01 | 6 | AD/VD | EF18012-09AV-FA-006 | TRS-00001 | 2019-01-04 | 2019-01-11 | TRS_00001 | 2019-01-11 | C | 2019-01-15 | TRS-00004 | A | TRS-00009 |  | 2019-02-18 | 2019-01-18 | 0 | 0
S01 | 6 | AD/VD | EF18012-09AV-FA-006 | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0010 | 2019-01-28 | C | 2019-01-31 | TRS-00015 | A | TRS-0022 | A | 2019-02-18 | 2019-02-04 | 0 | 0
S02 | 6 | AD/VD | EF18012-09AV-FA-006 | TRS-00023 | 2019-02-18 | 2019-02-25 | [8 empty] | 2019-02-18 |  |  | 8
S08 | 7 | AD/VD | EF18012-09AV-FA-007 | [11 empty] | 2019-02-18
S19 | 8 | AD/VD | EF18012-09AV-FA-008 | [11 empty] | 2019-02-18
S19 | 9 | AD/VD | EF18012-09AV-FA-009 | [11 empty] | 2019-02-18
S01 | 10 | AD/VD | EF18012-09AV-FA-010 | TRS-00014 | 2019-02-01 | 2019-02-08 | TRS_0017 | 2019-02-07 | C | 2019-02-12 | TRS-00020 |  |  |  | 2019-02-18 | 2019-02-14 | 0 | 0
S02 | 10 | AD/VD | EF18012-09AV-FA-010 | TRS-00023 | 2019-02-18 | 2019-02-25 | [8 empty] | 2019-02-18 |  |  | 8
S01 | 10 | AD/VD | EF18012-09AV-FA-010 | TRS-00002 | 2019-01-07 | 2019-01-14 | TRS_00002 | 2019-01-14 | B | 2019-01-16 | TRS-00005 | A | TRS-00009 |  | 2019-02-18 | 2019-01-21 | 0 | 0
S01 | 10 | AD/VD | EF18012-09AV-FA-010 | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0010 | 2019-01-28 | B | 2019-01-31 | TRS-00013 |  |  |  | 2019-02-18 | 2019-02-04 | 0 | 0
S04 | 11 | AD/VD | EF18012-09AV-FA-011 | TRS-00008 | 2019-01-21 | 2019-01-28 | TRS_0011 | 2019-01-29 | C | 2019-02-05 | TRS-00016 | A | TRS-0022 | A | 2019-02-18 | 2019-02-05 | 0 | 0
S04 | 12 | AD/VD | EF18012-09AV-FA-012 | TRS-00011 | 2019-01-29 | 2019-02-05 | TRS-0015 | 2019-02-05 | C | 2019-02-12 | TRS-00021 |  |  |  | 2019-02-18 | 2019-02-12 | 0 | 0
S04 | 13 | AD/VD | EF18012-09AV-FA-020 | [11 empty] | 2019-02-18
Formulas:
Y SCHEDULE RETURN DATE = [TRANSMITTAL DATE]+7
Y SCHEDULE RETURN DATE = IF([TRANSMITTAL DATE]="","",[TRANSMITTAL DATE]+7)
X EXPECTED DATE = IF([RETURN DATE]="","",[RETURN DATE]+7)
X DELAY = IFERROR(IF(OR([DOCUMENT STATUS]="A",[TRS NUMBER]<>0),0,NETWORKDAYS([TODAY],[X EXPECTED DATE])),"")
Y DELAY = IFERROR(IF(SUMPRODUCT(([DOCUMENT STATUS]={"a";"b";"c";"d"})*1)>=1,0,IF([CRS N°]="",NETWORKDAYS([TODAY],[Y SCHEDULE RETURN DATE]+2),0)),"")

## DATA (hidden)
132
|  |  | DOC UTIL DATABASE - DO NOT ALTER |  |  | Standard Documents | [35 empty] | 853
[8 empty] | SELECTION |  |  | X |  |  | X | X |  | X |  |  | X |  |  |  |  | X
Type | Class | Chrono | Description | Doc Number | Purpose | AREA | GROUP1 | GROUP 2 | Vendor Document | Internal Document | STD | APH | SAPH | FAN | E&I_SIMPLE | E&I_COMPL | PIP | PUMP | DRUM | STEAM | SOOT | AWL | SPRING | TURB | EREC | INCL APH | INCL sAPH | INCL FAN | INCL E&I_SIMPLE | INCL E&I_COMPL | INCL PIP | INCL PUMP | INCL STEAM | INCL STEAM | INCL SOOT | INCL AWL | INCL SPRING | INCL TURB | INCL EREC | INCL VENDOR | INCLUDE HPC | INCLUDE? | Weeks after PO | Estimate date Rev0 | PO+
FA | 0 | 1 | PROJECT ORGANIZATION CHART | 0000-FA-001 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 4 | 2018-10-15 | PO+4W
FA | 0 | 2 | PROJECT RISK RATING | 0000-FA-002 | FI | GEN | PROJ | PROJECT | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 4 | 2018-10-15 | PO+4W
FA | 0 | 3 | PROJECT STEEL WEIGHT FOLLOW-UP | 0000-FA-003 | FI | GEN | PROJ | PROJECT | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 4 | 2018-10-15 | PO+4W
FA | 0 | 4 | PROJECT DOCUMENT MATRIX | 0000-FA-004 | FI | GEN | PROJ | PROJECT | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 4 | 2018-10-15 | PO+4W
FA | 0 | 5 | PROJECT COORDINATION PROCEDURE | 0000-FA-005 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 4 | 2018-10-15 | PO+4W
FA | 0 | 6 | PROJECT GENERAL SCHEDULE | 0000-FA-006 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 6 | 2018-10-29 | PO+6W
FA | 0 | 7 | PROJECT PROCUREMENT REPORT | 0000-FA-007 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 4 | 2018-10-15 | PO+4W
FA | 0 | 8 | SUB ORDER STATUS | 0000-FA-008 | FI | GEN | PROJ | PROJECT | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 4 | 2018-10-15 | PO+4W
FA | 0 | 9 | INTERNAL MONTHLY PROGRESS REPORT | 0000-FA-009 | FI | GEN | PROJ | PROJECT | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FA | 0 | 10 | PROJECT MONTHLY PROGRESS REPORT | 0000-FA-010 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 3 | 2018-10-08 | PO+3W
FA | 0 | 11 | PURCHASING FOLLOW-UP (SUIVI HA) | 0000-FA-011 | FI | GEN | PROJ | PROJECT | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FA | 0 | 12 | CHANGE ORDER REQUEST | 0000-FA-012 | FI | GEN | PROJ | PROJECT | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FA | 0 | 14 | MASTER DOCUMENT LIST | 0000-FA-014 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 3 | 2018-10-08 | PO+3W
FA | 0 | 15 | PROJECT VENDOR LIST | 0000-FA-015 | FI | GEN | PROJ | PROJECT | NO | NO | YES | YES | YES | YES | YES | YES | NO | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 3 | 2018-10-08 | PO+3W
FC | 0 | 1 | HEATER - FOUNDATION LOADS | 0000-FC-001 | FR | STR | CALC | CALCULATION | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 10 | 2018-11-26 | PO+10W
FC | 300 | 301 | HEATER - MECHANICAL CALCULATION OF STEEL STRUCTURE | 0000-FC-301 | FI | STR | STRU | MAIN STRUCTURES | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 300 | 302 | HEATER - MECHANICAL CALCULATION OF STACK | 0000-FC-302 | FI | STR | STRU | MAIN STRUCTURES | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 300 | 371 | HEATER - MECHANICAL CALCULATION OF DUCTING SYSTEM | 0000-FC-371 | FI | STR | STRU | MAIN STRUCTURES | NO | NO | NO | YES | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 300 | 372 | HEATER - MECHANICAL CALCULATION OF PIPING SUPPORTS | 0000-FC-372 | FI | STR | STRU | MAIN STRUCTURES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 301 | 373 | SECONDARY STRUCTURES | 0000-FC-373 | FI | STR | STRU | MAIN STRUCTURES | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 400 | 410 | COIL PRESSURE PARTS CALCULATION | 0000-FC-410 | FI | MEC | COIL | COIL & MANIFOLDS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FC | 400 | 411 | COIL STRESS ANALYSIS CALCULATION | 0000-FC-411 | FI | MEC | COIL | COIL & MANIFOLDS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FC | 500 | 501 | OUTSIDE CASING TEMPERATURE CALCULATION NOTE | 0000-FC-501 | FI | PRO | CALC | CALCUL PROCESS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 17 | 2019-01-14 | PO+17W
FC | 600 | 601 | CAST SUPPORTS | 0000-FC-601 | FI | MEC | CAST | CAST SUPPORT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FC | 800 | 801 | FFB, TW STRESS, SIL, VALVES & ORIFICE PLATE, IS, INSTRUMENT SIZING | 0000-FC-801 | FI | E&I | INST | INSTRUMENTATION | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FC | 900 | 901 | HEATER - MECHANICAL CALCULATION OF LIFTING DEVICES | 0000-FC-901 | FI | TRA | TRAN | TRANSPORT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FC | 4000 | 4001 | PIPING STRESS ANALYSIS | 0000-FC-4001 | FI | PIP | PIPI | PIPING STRESS ANALYSIS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FC | 4000 | 4002 | PIPING STRESS ANALYSIS – BFW / STEAM GENERATION / SUPERHEATING LINES | 0000-FC-4002 | FI | PIP | DRUM | PIPING STRESS ANALYSIS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 0 | 1 | FOUNDATION LAYOUT | 0000-FD-001 | FR | STR | GENE | GENERAL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 10 | 2018-11-26 | PO+10W
FD | 0 | 2 | BASE PLATE DETAILS | 0000-FD-002 | FR | STR | GENE | GENERAL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 10 | 2018-11-26 | PO+10W
FD | 0 | 5 | PLOT PLAN | 0000-FD-005 | FR | CLI | GENE | GENERAL DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 10 | 2018-11-26 | PO+10W
FD | 0 | 10 | GENERAL ASSEMBLY – GENERAL DATA | 0000-FD-010 | FR | MEC | GENE | GENERAL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FD | 0 | 20 | GENERAL ASSEMBLY – ELEVATIONS | 0000-FD-020 | FR | MEC | GENE | GENERAL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FD | 0 | 30 | GENERAL ASSEMBLY – PLAN VIEWS | 0000-FD-030 | FR | MEC | GENE | GENERAL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FD | 0 | 40 | FLUE GAS DUCT - GENERAL ASSEMBLY | 0000-FD-040 | FR | STR | APH | GENERAL DRAWINGS | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FD | 0 | 50 | AIR DUCT - GENERAL ASSEMBLY | 0000-FD-050 | FR | STR | APH | GENERAL DRAWINGS | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FD | 300 | 301 | GENERAL NOTES – STEEL STRUCTURE | 0000-FD-301 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 310 | RADIANT STEEL STRUCTURE | 0000-FD-310 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 311 | RADIANT STEEL STRUCTURE - DETAILS | 0000-FD-311 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 312 | RADIANT SHIELD STEEL STRUCTURE | 0000-FD-312 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 320 | CONVECTION STEEL STRUCTURE | 0000-FD-320 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 321 | CONVECTION STEEL STRUCTURE - DETAILS | 0000-FD-321 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 322 | HEADER BOXES FOR CONVECTION MODULE | 0000-FD-322 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 323 | STACK SUPPORT STRUCTURE | 0000-FD-323 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 324 | EXTERNAL STEEL STRUCTURE | 0000-FD-324 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 340 | FLUE GAS DUCT STEEL STRUCTURE | 0000-FD-340 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 341 | DAMPERS AND BLADE SHUTTER | 0000-FD-341 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 350 | STACK STEEL STRUCTURE | 0000-FD-350 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 300 | 360 | HANDRAILS, STAIRWAY AND LADDERS - TYPICAL DETAILS | 0000-FD-360 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 300 | 361 | GRATING PLATFORMS | 0000-FD-361 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 400 | 401 | RADIANT COIL | 0000-FD-401 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 400 | 402 | CONVECTION COIL - PROCESS | 0000-FD-402 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 400 | 403 | CROSS OVER | 0000-FD-403 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 400 | 404 | CONVECTION STEAM GENERATION COIL ( SG ) | 0000-FD-404 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 400 | 405 | CONVECTION STEAM SUPERHEATING COIL (SSH) | 0000-FD-405 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 400 | 406 | CONVECTION BOILER FEEWATER COIL (BFW) | 0000-FD-406 | FR | MEC | COIL | COIL & MANIFOLD DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 500 | 501 | INSULATION - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FD-501 | FR | PIP | INSU | INSULATION DRAWINGS | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 800 | 800 | PID - LEGENDS AND SYMBOLS | 0000-FD-800 | FR | PRO | PID0 | PFD & PID | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 801 | PID - HEATER | 0000-FD-801 | FR | PRO | PID0 | PFD & PID | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 802 | PID - AIR PREHEATING SYSTEM | 0000-FD-802 | FR | PRO | APH | PFD & PID | NO | NO | NO | YES | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 803 | PID - FUEL SYSTEM | 0000-FD-803 | FR | PRO | PID0 | PFD & PID | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 804 | PID - UTILITY (INSTRUMENT AIR, SNUFFING STEAM) | 0000-FD-804 | FR | PRO | PID0 | PFD & PID | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 805 | PID - STEAM DRUM AND APPURTENANCES | 0000-FD-805 | FR | PRO | DRUM | PFD & PID | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 820 | INSTRUMENT LIST | 0000-FD-820 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 10 | 2018-11-26 | PO+10W
FD | 800 | 821 | I/O LIST | 0000-FD-821 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | YES | YES | YES | NO | YES | NO | NO | YES | NO | NO | YES | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 10 | 2018-11-26 | PO+10W
FD | 800 | 822 | INSTRUMENT & ELECTRICAL CABLE LIST | 0000-FD-822 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | YES | YES | YES | NO | NO | NO | NO | YES | NO | NO | YES | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 800 | 823 | CONSUMER LIST | 0000-FD-823 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | YES | YES | YES | NO | NO | NO | NO | YES | NO | NO | YES | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FD | 800 | 824 | INSTRUMENT AND ELECTRICAL LAYOUT (WITH JB AND CABLE TRAYS) | 0000-FD-824 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | YES | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FD | 800 | 825 | INTERCONNECTION DIAGRAMS | 0000-FD-825 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FD | 800 | 826 | INSTRUMENTS HOOK UP DRAWINGS | 0000-FD-826 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 18 | 2019-01-21 | PO+18W
FD | 800 | 827 | JUNCTION BOXES WIRING | 0000-FD-827 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 18 | 2019-01-21 | PO+18W
FD | 800 | 828 | LOCAL PANEL LAYOUT | 0000-FD-828 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 800 | 829 | INSTRUMENTS, JUNCTION BOXES AND LOCAL PANEL SUPPORTS | 0000-FD-829 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
FD | 800 | 830 | CAUSE & EFFECT CHART | 0000-FD-830 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 800 | 831 | BASIC LOGIC DIAGRAM AND START-UP SEQUENCE DIAGRAM | 0000-FD-831 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 800 | 832 | SOOTBLOWER PANEL LAYOUT | 0000-FD-832 | FR | E&I | PID0 | PFD & PID | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 800 | 890 | SKIN THERMOCOUPLES | 0000-FD-890 | FR | PRO | PID0 | PFD & PID | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 18 | 2019-01-21 | PO+18W
FD | 900 | 901 | LIFTING LUGS AND REINFORCEMENT FOR TRANSPORTATION | 0000-FD-901 | FI | TRA | TRAN | TRANSPORT | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4001 | SKID PIPING ‐ LAYOUT | 0000-FD-4001 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 4000 | 4003 | SKID PIPING ‐ ISOMETRIC BOOK | 0000-FD-4003 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4004 | SKID PIPING ‐ SUPPORT BOOK | 0000-FD-4004 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4006 | HEATER PIPING ‐ ISOMETRIC BOOK | 0000-FD-4006 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4007 | HEATER PIPING ‐ SUPPORT BOOK | 0000-FD-4007 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4011 | HEATER PIPING ‐ LAYOUT | 0000-FD-4011 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FD | 4000 | 4023 | STEAM GENERATION PIPING ‐ PRIMARY SUPPORT BOOK | 0000-FD-4023 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4024 | SOOTBLOWER PIPING LAYOUT | 0000-FD-4024 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4025 | SKID FRAME | 0000-FD-4025 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4026 | HEATER PIPING ‐ SECONDARY SUPPORT BOOK | 0000-FD-4026 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4027 | STEAM GENERATION PIPING ‐ SECONDARY SUPPORT BOOK | 0000-FD-4027 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FD | 4000 | 4028 | STEAM TURBINE PIPING LAYOUT | 0000-FD-4028 | FR | PIP | PIPI | PIPING DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 100 | TUBES & FITTINGS - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-100 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 101 | TUBES & FITTINGS - FABRICATION SCHEDULE | 0000-FE-101 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 102 | TUBES & FITTINGS - DOCUMENT LIST | 0000-FE-102 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 103 | TUBES & FITTINGS -CALCULATION NOTE | 0000-FE-103 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 104 | TUBES & FITTINGS -GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-104 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 105 | TUBES & FITTINGS -QUALITY - INSPECTION AND TEST PLAN | 0000-FE-105 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 106 | TUBES & FITTINGS -QUALITY - CHEMICAL ANALYSIS | 0000-FE-106 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 107 | TUBES & FITTINGS -QUALITY - AIR PRESSURE TEST PROCEDURE | 0000-FE-107 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 108 | TUBES & FITTINGS -QUALITY - RADIOGRAPHIC EXAMINATION PROCEDURE | 0000-FE-108 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 109 | TUBES & FITTINGS -QUALITY - EDDY CURRENT TEST PROCEDURE | 0000-FE-109 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 110 | TUBES & FITTINGS -QUALITY - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-110 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 111 | TUBES & FITTINGS -QUALITY - POSITIVE MATERIAL IDENTIFICATION PROCEDURE | 0000-FE-111 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 112 | TUBES & FITTINGS -QUALITY - GO GAUGE TEST PROCEDURE | 0000-FE-112 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 113 | TUBES & FITTINGS -QUALITY - LIQUID PENETRANT TEST PROCEDURE | 0000-FE-113 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 114 | TUBES & FITTINGS -QUALITY - WELDING WIRES STORAGE MANAGEMENT PROCEDURE | 0000-FE-114 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 115 | TUBES & FITTINGS -QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-115 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 116 | TUBES & FITTINGS -QUALITY - ROUGHNESS TEST PROCEDURE | 0000-FE-116 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 117 | TUBES & FITTINGS -QUALITY - MARKING PROCEDURE FOR TUBE AND ASSEMBLY | 0000-FE-117 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 118 | TUBES & FITTINGS -QUALITY - VISUAL EXAMINATION ON STATIC CASTING PROCEDURE | 0000-FE-118 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 119 | TUBES & FITTINGS -QUALITY - CLEANING PROCEDURE | 0000-FE-119 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 120 | TUBES & FITTINGS -QUALITY - FLUORESCENT LIQUID PENETRANT TEST PROCEDURE | 0000-FE-120 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 121 | TUBES & FITTINGS -QUALITY - DIMENSIONAL INSPECTION PROCEDURE | 0000-FE-121 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 122 | TUBES & FITTINGS -QUALITY - PROCEDURE FOR CHEMICAL ANALYSIS BY SPECTROMETER | 0000-FE-122 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 123 | TUBES & FITTINGS -QUALITY - MACROETCHING TEST PROCEDURE | 0000-FE-123 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 124 | TUBES & FITTINGS -QUALITY - WELDING SPECIFICATION | 0000-FE-124 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 125 | TUBES & FITTINGS -QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-125 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 126 | TUBES & FITTINGS -SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-126 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 127 | TUBES & FITTINGS -INDEX DATA BOOK | 0000-FE-127 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 100 | 128 | TUBES & FITTINGS -SPARE PART LIST | 0000-FE-128 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 100 | 129 | TUBES & FITTINGS - DATA BOOK | 0000-FE-129 | FI | MEC | TUBE | TUBES & FITTINGS | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 200 | 200 | BURNER - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-200 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 201 | BURNER - FABRICATION SCHEDULE | 0000-FE-201 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 202 | BURNER - DOCUMENT LIST | 0000-FE-202 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 203 | BURNER - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-203 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 204 | BURNER - FLAME ROD DETECTION GENERAL ASSEMBLY AND DETAIL | 0000-FE-204 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 205 | BURNER - PILOT GENERAL ASSEMBLY AND DETAIL | 0000-FE-205 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 206 | BURNER - IGNITION EQUIPEMENT DETAIL | 0000-FE-206 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 207 | BURNER - CURVE, DATA SHEET, | 0000-FE-207 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 208 | BURNER - BURNERS BOX | 0000-FE-208 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 209 | BURNER - INTERNAL BOX WIRING | 0000-FE-209 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 210 | BURNER - SPECIAL CABLE /CERTIFICATES | 0000-FE-210 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 211 | BURNER - QUALITY - TEST PROCEDURE | 0000-FE-211 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 212 | BURNER - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-212 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 213 | BURNER - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-213 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 214 | BURNER - QUALITY - PMI PROCEDURE | 0000-FE-214 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 215 | BURNER - QUALITY - AIR FLOW TEST PROCEDURE | 0000-FE-215 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 216 | BURNER - QUALITY - PAINTING PROCEDURE | 0000-FE-216 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 217 | BURNER - QUALITY - WELDING BOOK | 0000-FE-217 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 200 | 218 | BURNER - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-218 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 219 | BURNER - INSTALLATION, OPERATING AND MAINTENANCE MANUALS | 0000-FE-219 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 220 | BURNER - SITE STORAGE PROCEDURE | 0000-FE-220 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 221 | BURNER - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-221 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 222 | BURNER - INDEX DATA BOOK | 0000-FE-222 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 200 | 223 | BURNER - SPARE PART LIST | 0000-FE-223 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 224 | BURNER - NOISE DATA SHEET | 0000-FE-224 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 200 | 225 | BURNER - DATA BOOK | 0000-FE-225 | FI | PRO | BURN | BURNER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 300 | 300 | PREFABRICATION - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-300 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 301 | PREFABRICATION - FABRICATION SCHEDULE | 0000-FE-301 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 302 | PREFABRICATION - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-302 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 303 | PREFABRICATION - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-303 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 304 | PREFABRICATION - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-304 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 305 | PREFABRICATION - PROCEDURE FOR REFRACTORY AND LINING APPLICATION | 0000-FE-305 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 306 | PREFABRICATION - QUALITY - RADIOGRAPHY PROCEDURE | 0000-FE-306 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 307 | PREFABRICATION - QUALITY - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-307 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 308 | PREFABRICATION - QUALITY - PMI PROCEDURE | 0000-FE-308 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 309 | PREFABRICATION - QUALITY - DRY PENETRANT TEST PROCEDURE | 0000-FE-309 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 310 | PREFABRICATION - QUALITY - PWHT & HARDNESS TEST PROCEDURE (IF APPLICABLE) | 0000-FE-310 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 311 | PREFABRICATION - QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-311 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 312 | PREFABRICATION - QUALITY - DIMENSIONAL PROCEDURE | 0000-FE-312 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 314 | PREFABRICATION - QUALITY - TRIAL ASSEMBLY PROCEDURE | 0000-FE-314 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 315 | PREFABRICATION - PAINTING PROCEDURE | 0000-FE-315 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 316 | PREFABRICATION - QUALITY - WELDING BOOK | 0000-FE-316 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 300 | 317 | PREFABRICATION - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-317 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 318 | PREFABRICATION - LIFTING SPREADER BEAMS PROCEDURES OR DRAWING | 0000-FE-318 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 319 | PREFABRICATION - SITE STORAGE PROCEDURE | 0000-FE-319 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 320 | PREFABRICATION - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-320 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 321 | PREFABRICATION - INDEX DATA BOOK | 0000-FE-321 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 300 | 322 | PREFABRICATION - SPARE PART LIST | 0000-FE-322 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 300 | 323 | PREFABRICATION - DATA BOOK | 0000-FE-323 | FI | FAB | PREF | PREFABRICATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 400 | 400 | FINNING - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-400 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 401 | FINNING - FABRICATION SCHEDULE | 0000-FE-401 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 402 | FINNING - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-402 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 403 | FINNING - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-403 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 404 | FINNING - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-404 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 405 | FINNING - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-405 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 406 | FINNING - QUALITY - PMI PROCEDURE | 0000-FE-406 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 407 | STUDDING - QUALITY - PWHT & HARDNESS TEST PROCEDURE | 0000-FE-407 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 408 | FINNING - QUALITY - RADIOGRAPHY PROCEDURE | 0000-FE-408 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 409 | FINNING - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-409 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 410 | FINNING - QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-410 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 411 | FINNING - QUALITY - DIMENSIONAL PROCEDURE | 0000-FE-411 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 413 | FINNING - QUALITY - WELDING BOOK | 0000-FE-413 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 400 | 414 | FINNING - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-414 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 415 | FINNING - SITE STORAGE PROCEDURE | 0000-FE-415 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 416 | FINNING - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-416 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 417 | FINNING - INDEX DATA BOOK | 0000-FE-417 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 400 | 418 | FINNING - SPARE PART LIST | 0000-FE-418 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 400 | 419 | FINNING - DATA BOOK | 0000-FE-419 | FI | MEC | FINN | FINNING STUDDING | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 500 | 500 | INSULATION - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-500 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 501 | INSULATION - FABRICATION SCHEDULE | 0000-FE-501 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 502 | INSULATION - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-502 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 503 | INSULATION - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-503 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 504 | INSULATION - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-504 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 505 | INSULATION - MATERIAL DATA SHEET FOR REFACTORY MATERIALS | 0000-FE-505 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 506 | INSULATION - MATERIAL SAFETY DATA SHEET FOR REFACTORY MATERIALS | 0000-FE-506 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 507 | INSULATION - PRODUCT COMPLIANCE DATA SHEET FOR REFACTORY MATERIALS | 0000-FE-507 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 508 | INSULATION - HEAT TRANSFER CALCULATIONS | 0000-FE-508 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 509 | INSULATION - APPLICATION PROCÉDURE | 0000-FE-509 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 510 | INSULATION - QUALITY - DENSITY TEST CERTIFICATE | 0000-FE-510 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 511 | INSULATION - QUALITY - CRUNCHING TEST CERTIFICATE | 0000-FE-511 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 512 | INSULATION - QUALITY - SHRINKAGE TEST CERTIFICATE | 0000-FE-512 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 513 | INSULATION - QUALITY - B252HAMMER TEST CERTIFICATE | 0000-FE-513 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 514 | INSULATION - QUALITY - DRY OUT PROCEDURE (IF APPLICABLE) | 0000-FE-514 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 515 | INSULATION - ERECTION PROCEDURE | 0000-FE-515 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 516 | INSULATION - SITE STORAGE PROCEDURE | 0000-FE-516 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 517 | INSULATION - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-517 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 518 | INSULATION - INDEX DATA BOOK | 0000-FE-518 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 500 | 519 | INSULATION - SPARE PART LIST | 0000-FE-519 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 500 | 520 | INSULATION - DATA BOOK | 0000-FE-520 | FI | MEC | INSU | INSULATION | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 600 | 600 | CAST PIECES - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-600 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 601 | CAST PIECES - FABRICATION SCHEDULE | 0000-FE-601 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 602 | CAST PIECES - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-602 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 603 | CAST PIECES - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-603 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 604 | CAST PIECES - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-604 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 605 | CAST PIECES - QUALITY - MATERIAL DATASHEETS | 0000-FE-605 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 606 | CAST PIECES - QUALITY - DESTRUCTIVE & NON-DESTRUCTIVE TESTING | 0000-FE-606 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 607 | CAST PIECES - QUALITY - PILOT CAST | 0000-FE-607 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 608 | CAST PIECES - QUALITY - REPAIR / ACCEPTANCE | 0000-FE-608 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 609 | CAST PIECES - QUALITY - HOT TESTING | 0000-FE-609 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 610 | CAST PIECES - QUALITY - CASTING REPAIR PROCEDURE | 0000-FE-610 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 611 | CAST PIECES - QUALITY - PMI PROCEDURE | 0000-FE-611 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 612 | CAST PIECES - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-612 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 613 | CAST PIECES - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-613 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 614 | CAST PIECES - QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-614 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 615 | CAST PIECES - QUALITY - RADIOGRAPHY PROCEDURE | 0000-FE-615 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 616 | CAST PIECES - QUALITY - WELDING BOOK | 0000-FE-616 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 600 | 617 | CAST PIECES - QUALITY - DIMENSIONAL PROCEDURE | 0000-FE-617 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 618 | CAST PIECES - SITE STORAGE PROCEDURE | 0000-FE-618 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 619 | CAST PIECES - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-619 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 620 | CAST PIECES - INDEX DATA BOOK | 0000-FE-620 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 600 | 621 | CAST PIECES - SPARE PART LIST | 0000-FE-621 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 600 | 622 | CAST PIECES - DATA BOOK | 0000-FE-622 | FI | MEC | CAST | CAST PIECES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7100 | 7100 | FANS - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7100 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7101 | FANS - FABRICATION SCHEDULE | 0000-FE-7101 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7102 | FANS - DOCUMENT LIST | 0000-FE-7102 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7103 | FANS - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-7103 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7104 | FANS - MOTOR GENERAL ASSEMBLY AND DETAIL | 0000-FE-7104 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7105 | FANS - CONTROL LOCAL CONTROL SYSTÈME | 0000-FE-7105 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7106 | FANS - SILENCER DRAWING | 0000-FE-7106 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7107 | FANS - TERMINAL BOX | 0000-FE-7107 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7108 | FANS - PNEUMATIC ACTUATOR DRAWING | 0000-FE-7108 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7109 | FANS - MOTOR DATA SHEET | 0000-FE-7109 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7110 | FANS - DATA SHEET, | 0000-FE-7110 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7111 | FANS - PERFORMANCE CURVE | 0000-FE-7111 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7112 | FANS -NOISE DATA SHEET | 0000-FE-7112 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7113 | FANS -TEMPERATURE PROBE | 0000-FE-7113 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7114 | FANS - MOTOR - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-7114 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7115 | FANS - QUALITY- INSPECTION AND TEST PLAN | 0000-FE-7115 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7116 | FANS - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-7116 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7117 | FANS - QUALITY - PMI PROCEDURE | 0000-FE-7117 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7118 | FANS - TEST PROCEDURE | 0000-FE-7118 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7119 | FANS - MOTOR TEST PROCEDURE | 0000-FE-7119 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7120 | FANS - MECANICAL RUNNING TEST PROCEDURE | 0000-FE-7120 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7121 | FANS - PERFORMANCE TEST PROCEDURE | 0000-FE-7121 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7122 | FANS - BALANCING PROCEDURE | 0000-FE-7122 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7123 | FANS - QUALITY - PAINTING PROCEDURE | 0000-FE-7123 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7124 | FANS - QUALITY - WELDING BOOK | 0000-FE-7124 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 7100 | 7125 | FANS - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-7125 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7126 | FANS - INSTALLATION, OPERATING AND MAINTENANCE MANUALS | 0000-FE-7126 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7127 | FANS - SITE STORAGE PROCEDURE | 0000-FE-7127 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7128 | FANS - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-7128 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7129 | FANS - INDEX DATA BOOK | 0000-FE-7129 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 7100 | 7130 | FANS - SPARE PART LIST | 0000-FE-7130 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 7100 | 7131 | FANS - DATA BOOK | 0000-FE-7131 | FI | MEC | FANS | FANS | YES | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 7300 | 7300 | PGB - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7300 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7301 | PGB - FABRICATION SCHEDULE | 0000-FE-7301 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7302 | PGB - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-7302 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7303 | PGB - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-7303 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7304 | PGB - CALCULATION NOTE | 0000-FE-7304 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7305 | PGB - SPARE PART LIST | 0000-FE-7305 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7306 | PGB - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-7306 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7307 | PGB - QUALITY - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-7307 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7308 | PGB - QUALITY - PMI PROCEDURE | 0000-FE-7308 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7309 | PGB - QUALITY - PWHT PROCEDURE | 0000-FE-7309 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7310 | PGB - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-7310 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7311 | PGB - QUALITY - RADIOGRAPHY PROCEDURE | 0000-FE-7311 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7312 | PGB - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-7312 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7313 | PGB - QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-7313 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7314 | PGB - QUALITY - PAINTING PROCEDURE | 0000-FE-7314 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7315 | PGB - QUALITY - WELDING BOOK | 0000-FE-7315 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7300 | 7316 | PGB - QUALITY - DIMENSIONAL PROCEDURE | 0000-FE-7316 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7317 | PGB - SITE STORAGE PROCEDURE | 0000-FE-7317 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7318 | PGB - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-7318 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7300 | 7319 | PGB - INDEX DATA BOOK | 0000-FE-7319 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7300 | 7320 | PGB - DATA BOOK | 0000-FE-7320 | FI | MEC | BOIL | GAS BOILER | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7400 | 7400 | SAPH - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7400 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7401 | SAPH - FABRICATION SCHEDULE | 0000-FE-7401 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7402 | SAPH - DOCUMENT LIST | 0000-FE-7402 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7403 | SAPH - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-7403 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7405 | SAPH - DATA SHEET, | 0000-FE-7405 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7406 | SAPH - QUALITY- INSPECTION AND TEST PLAN | 0000-FE-7406 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7407 | SAPH - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-7407 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7408 | SAPH - QUALITY - PMI PROCEDURE | 0000-FE-7408 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7409 | SAPH - QUALITY - PAINTING PROCEDURE | 0000-FE-7409 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7410 | SAPH - QUALITY - WELDING BOOK | 0000-FE-7410 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7400 | 7411 | SAPH - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-7411 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7412 | SAPH - INSTALLATION, OPERATING AND MAINTENANCE MANUALS | 0000-FE-7412 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7413 | SAPH - SITE STORAGE PROCEDURE | 0000-FE-7413 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7414 | SAPH - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-7414 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7415 | SAPH - INDEX DATA BOOK | 0000-FE-7415 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7400 | 7416 | SAPH - SPARE PART LIST | 0000-FE-7416 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7417 | SAPH - DATA BOOK | 0000-FE-7417 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7400 | 7418 | SAPH - HYDROSTATIC TEST PROCEDURE | 0000-FE-7418 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7400 | 7419 | SAPH - LEAK TEST PROCEDURE | 0000-FE-7419 | FI | MEC | SAPH | SAPH | YES | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7500 | APH - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7500 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7501 | APH - FABRICATION SCHEDULE | 0000-FE-7501 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7502 | APH - DOCUMENT LIST | 0000-FE-7502 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7503 | APH - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-7503 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7504 | APH - THERMOCOUPLE DATASHEET | 0000-FE-7504 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7505 | APH - DATA SHEET, | 0000-FE-7505 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7506 | APH - QUALITY- INSPECTION AND TEST PLAN | 0000-FE-7506 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7507 | APH - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-7507 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7508 | APH - QUALITY - PMI PROCEDURE | 0000-FE-7508 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7509 | APH - QUALITY - PAINTING PROCEDURE | 0000-FE-7509 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7510 | APH - QUALITY - WELDING BOOK | 0000-FE-7510 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7500 | 7511 | APH - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-7511 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7512 | APH - INSTALLATION, OPERATING AND MAINTENANCE MANUALS | 0000-FE-7512 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7513 | APH - SITE STORAGE PROCEDURE | 0000-FE-7513 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7514 | APH - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-7514 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7515 | APH - INDEX DATA BOOK | 0000-FE-7515 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7500 | 7516 | APH - SPARE PART LIST | 0000-FE-7516 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7500 | 7517 | APH - DATA BOOK | 0000-FE-7517 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7500 | 7518 | APH - LEAK TEST PROCEDURE | 0000-FE-7518 | FI | MEC | APH0 | APH | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7600 | PUMPS - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7600 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7601 | PUMPS - FABRICATION SCHEDULE | 0000-FE-7601 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7602 | PUMPS - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-7602 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7603 | PUMPS - DATA SHEET | 0000-FE-7603 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7604 | PUMPS - DATA SHEET OF AUXILIARIES EQUIPMENT | 0000-FE-7604 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7605 | PUMPS - GENERAL ARRANGEMENT DRAWINGS (GAD) | 0000-FE-7605 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7606 | PUMPS - OUTLINE DRAWINGS FOR OFF BASE EQUIPMENT (OIL CONSOLE ETC.) (IF APPLICABLE) | 0000-FE-7606 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7607 | PUMPS - FOUNDATION LAYOUT & LOADING PLAN | 0000-FE-7607 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7608 | PUMPS - PLOT PLAN & ELEVATION | 0000-FE-7608 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7609 | PUMPS - DRAWINGS OF AUXILIARIES AND ITEMIZED EQUIPMENT SUPPLIED LOOSE (IF ANY) | 0000-FE-7609 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7610 | PUMPS - EQUIPMENT LIST & LINE LIST | 0000-FE-7610 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7611 | PUMPS - DETAILED DRAWINGS | 0000-FE-7611 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7612 | PUMPS - CROSS SECTIONAL AND ASSEMBLY DRAWINGS | 0000-FE-7612 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7613 | PUMPS - MECHANICAL SEAL DRAWINGS WITH MATERIAL LIST | 0000-FE-7613 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7614 | PUMPS - PIPING - INSULATION, LADDER AND PLATFORM SUPPORT DRAWINGS | 0000-FE-7614 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7615 | PUMPS - PIPING - LAYOUT & DRAWINGS | 0000-FE-7615 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7616 | PUMPS - PIPING - INTERCONNECTING DRAWING AT BATTERY LIMIT | 0000-FE-7616 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7617 | PUMPS - PIPING - FLUSHING AUXILIARIES DRAWINGS | 0000-FE-7617 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7618 | PUMPS - PIPING - ISOMETRIC DRAWINGS & INTERCONNECTING | 0000-FE-7618 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7619 | PUMPS - CRITICAL SPEED ANALYSIS | 0000-FE-7619 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7620 | PUMPS - UTILITY BALANCE | 0000-FE-7620 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7621 | PUMPS - LUBRICANT CHARTS | 0000-FE-7621 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7622 | PUMPS - NOISE DATA SHEET | 0000-FE-7622 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7623 | PUMPS - PAINTING SPECIFICATION | 0000-FE-7623 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7624 | PUMPS - NAMEPLATE DRAWINGS | 0000-FE-7624 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7625 | PUMPS - LIST OF SPARE PARTS | 0000-FE-7625 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7626 | PUMPS - LIST OF SPECIAL TOOLS FOR ERECTION AND ASSEMBLY | 0000-FE-7626 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7627 | PUMPS - INSTRUMENTATION - LIST OF INSTRUMENTS (SET POINTS, RANGES, ALARMS…) | 0000-FE-7627 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7628 | PUMPS - INSTRUMENTATION - LIST OF JUNCTION BOXES, CONTROL BOXES, CABINETS & PANELS | 0000-FE-7628 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7629 | PUMPS - INSTRUMENTATION - INSTRUMENT DATA SHEETS | 0000-FE-7629 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7630 | PUMPS - INSTRUMENTATION - INSTRUMENT DOCUMENTATION | 0000-FE-7630 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7631 | PUMPS - INSTRUMENTATION - CONTROL BOXES, CAB.TS & PANELS DWGS | 0000-FE-7631 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7632 | PUMPS - INSTRUMENTATION - JB, TERMINAL BLOCK, PLUG, CONNECTOR WIRING DWGS | 0000-FE-7632 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7633 | PUMPS - INSTRUMENTATION - INSTRUMENTS, JB, CONTROL BOXES, CAB.TS & PANEL LOCATION DWGS | 0000-FE-7633 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7634 | PUMPS - INSTRUMENTATION - INSTRUMENTS HOOK-UP DWGS | 0000-FE-7634 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7635 | PUMPS - INSTRUMENTATION - LOOP DIAGRAM OR TYPICAL + I/O DATABASE | 0000-FE-7635 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7636 | PUMPS - ELECTRICAL - CONSUMER LIST & DATA | 0000-FE-7636 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7637 | PUMPS - ELECTRICAL - MOTOR DATA SHEETS | 0000-FE-7637 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7638 | PUMPS - ELECTRICAL - MOTOR DRAWINGS (GENERAL ARRANGEMENT DETAIL, CROSS SECTIONAL…) | 0000-FE-7638 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7639 | PUMPS - ELECTRICAL - MOTOR NAMEPLATE | 0000-FE-7639 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7640 | PUMPS - ELECTRICAL - TORQUE VERSUS SPEED/CURRENT/POWER FACTOR CURVES, EFFICIENCY | 0000-FE-7640 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7641 | PUMPS - ELECTRICAL - TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS | 0000-FE-7641 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7642 | PUMPS - QUALITY - INSPECTION & TEST PLAN (FABRICATION & QUALITY CONTROL PLAN) | 0000-FE-7642 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7643 | PUMPS - QUALITY - QUALITY ASSURANCE & HSE (QUALITY ASSURANCE, QUALITY PLAN, ) | 0000-FE-7643 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7644 | PUMPS - QUALITY - RUNNING TEST PROCEDURE | 0000-FE-7644 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7645 | PUMPS - QUALITY - PWHT PROCEDURES (IF APPLICABLE) | 0000-FE-7645 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7646 | PUMPS - QUALITY - NDT PROCEDURE | 0000-FE-7646 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7647 | PUMPS - QUALITY - MATERIAL CERTIFICATES | 0000-FE-7647 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7649 | PUMPS - QUALITY - WELDING BOOK (WKF, WPS, PQR) | 0000-FE-7649 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7600 | 7651 | PUMPS - QUALITY - FINAL DISPOSITION RECORDS (INSPECTION BOOK) (5) | 0000-FE-7651 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7600 | 7652 | PUMPS - TRANSPORT - RECOMMENDATIONS FOR PROTECTION DURING TRANSPORTATION | 0000-FE-7652 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7653 | PUMPS - TRANSPORT - HEAVY AND/OR LARGE EQUIPMENT DRAWINGS WITH WEIGHT, TRANSPORTATION DRAWINGS | 0000-FE-7653 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7654 | PUMPS - TRANSPORT - PACKING LIST | 0000-FE-7654 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7655 | PUMPS - SPECIAL PRECAUTIONS FOR HANDLING PRIOR ERECTION | 0000-FE-7655 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7656 | PUMPS - RECOMMENDATIONS FOR STORAGE PRIOR AND DURING ERECTION | 0000-FE-7656 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7657 | PUMPS - PROCEDURE FOR ERECTION AND INSTALLATION OF THE EQUIPMENT | 0000-FE-7657 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7658 | PUMPS - PROCEDURE FOR SITE ASSEMBLY, LEVELING AND WELDING | 0000-FE-7658 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7659 | PUMPS - PROCEDURE FOR INSTALLATION, START-UP AND COMMISSIONING MANUALS | 0000-FE-7659 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7660 | PUMPS - SITE PERFORMANCE TESTING PROCEDURE | 0000-FE-7660 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7661 | PUMPS - OPERATING AND MAINTENANCE MANUALS | 0000-FE-7661 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7662 | PUMPS - MAINTENANCE DATA SHEET | 0000-FE-7662 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7600 | 7663 | PUMPS - DATA BOOK | 0000-FE-7663 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7600 | 7664 | PUMPS - INDEX DATA BOOK | 0000-FE-7664 | FI | MEC | PUMP | PUMP | YES | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7800 | 7800 | STEAM DRUM - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-7800 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7801 | STEAM DRUM - FABRICATION SCHEDULE | 0000-FE-7801 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7802 | STEAM DRUM - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-7802 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7803 | STEAM DRUM - DATA SHEET | 0000-FE-7803 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7804 | STEAM DRUM - GENERAL ASSEMBLY & DETAIL AND BOM | 0000-FE-7804 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7805 | STEAM DRUM - CALCULATION NOTE | 0000-FE-7805 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7806 | STEAM DRUM - SPARE PART LIST | 0000-FE-7806 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7807 | STEAM DRUM - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-7807 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7808 | STEAM DRUM - QUALITY - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-7808 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7809 | STEAM DRUM - QUALITY - PMI PROCEDURE | 0000-FE-7809 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7810 | STEAM DRUM - QUALITY - PWHT PROCEDURE | 0000-FE-7810 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7811 | STEAM DRUM - QUALITY - DYE PENETRANT TEST PROCEDURE | 0000-FE-7811 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7812 | STEAM DRUM - QUALITY - RADIOGRAPHY PROCEDURE | 0000-FE-7812 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7813 | STEAM DRUM - QUALITY - WELDERS,NDT OPERATOR, CONSUMABLES, MATERIAL / CERTIFICATES | 0000-FE-7813 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7814 | STEAM DRUM - QUALITY - VISUAL EXAMINATION PROCEDURE | 0000-FE-7814 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7815 | STEAM DRUM - QUALITY - PAINTING PROCEDURE | 0000-FE-7815 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7816 | STEAM DRUM - QUALITY - WELDING BOOK | 0000-FE-7816 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7800 | 7817 | STEAM DRUM - QUALITY - DIMENSIONAL PROCEDURE | 0000-FE-7817 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7818 | STEAM DRUM - SITE STORAGE PROCEDURE | 0000-FE-7818 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7819 | STEAM DRUM - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-7819 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 7800 | 7820 | STEAM DRUM - INDEX DATA BOOK | 0000-FE-7820 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 7800 | 7821 | STEAM DRUM - DATA BOOK | 0000-FE-7821 | FI | MEC | DRUM | STEAM DRUM | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8000 | CONTROL VALVES - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-8000 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8001 | CONTROL VALVES - FABRICATION SCHEDULE | 0000-FE-8001 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8002 | CONTROL VALVES - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8002 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8003 | CONTROL VALVES - CALCULATION SHEET | 0000-FE-8003 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8004 | CONTROL VALVES - DIMENSIONAL DRAWING | 0000-FE-8004 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8005 | CONTROL VALVES - ELECTRICAL CONNECTION WIRING | 0000-FE-8005 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8006 | CONTROL VALVES - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8006 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8007 | CONTROL VALVES - QUALITY - PAINTING PROCEDURE & EXAMINATION WITH REPORTS | 0000-FE-8007 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8008 | CONTROL VALVES - QUALITY - NDT PROCEDURE AND REPORTS | 0000-FE-8008 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8009 | CONTROL VALVES - QUALITY - PMI PROCEDURE AND REPORTS (IF APPLICABLE) | 0000-FE-8009 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8010 | CONTROL VALVES - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8010 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8011 | CONTROL VALVES - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8011 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8012 | CONTROL VALVES - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8012 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8013 | CONTROL VALVES - QUALITY - HYDROSTATIC PRESSURE TEST PROCEDURE | 0000-FE-8013 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8014 | CONTROL VALVES - SPARE PART LIST | 0000-FE-8014 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8015 | CONTROL VALVES - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8015 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8016 | CONTROL VALVES - SITE STORAGE PROCEDURE | 0000-FE-8016 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8017 | CONTROL VALVES - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8017 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8018 | CONTROL VALVES - INDEX DATA BOOK | 0000-FE-8018 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8019 | CONTROL VALVES - DATA BOOK | 0000-FE-8019 | FI | E&I | CV00 | CV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8050 | ON/OFF VALVES - SUB-VENDOR MONTHLY PROGRESS REPORT | 0000-FE-8050 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8051 | ON/OFF VALVES - FABRICATION SCHEDULE | 0000-FE-8051 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8052 | ON/OFF VALVES - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8052 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8053 | ON/OFF VALVES - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8053 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8054 | ON/OFF VALVES - SPARE PART LIST | 0000-FE-8054 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8055 | ON/OFF VALVES - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8055 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8056 | ON/OFF VALVES - SITE STORAGE PROCEDURE | 0000-FE-8056 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8057 | ON/OFF VALVES - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8057 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8058 | ON/OFF VALVES - INDEX DATA BOOK | 0000-FE-8058 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8059 | ON/OFF VALVES - CALCULATION SHEET | 0000-FE-8059 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8060 | ON/OFF VALVES - DIMENSIONAL DRAWING | 0000-FE-8060 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8061 | ON/OFF VALVES - ELECTRICAL CONNECTION WIRING | 0000-FE-8061 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8062 | ON/OFF VALVES - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8062 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8063 | ON/OFF VALVES - QUALITY - SIL CERTIFICATE | 0000-FE-8063 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8064 | ON/OFF VALVES - QUALITY - PAINTING PROCEDURE & EXAMINATION WITH REPORTS | 0000-FE-8064 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8065 | ON/OFF VALVES - QUALITY - NDT PROCEDURE AND REPORTS | 0000-FE-8065 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8066 | ON/OFF VALVES - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8066 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8000 | 8067 | ON/OFF VALVES - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8067 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8000 | 8068 | ON/OFF VALVES - DATA BOOK | 0000-FE-8068 | FI | E&I | ONOF | ONOFF | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8100 | SAFETY RELIEF VALVES - SUB-VENDOR MONTHLY REPORT | 0000-FE-8100 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8101 | SAFETY RELIEF VALVES - FABRICATION SCHEDULE | 0000-FE-8101 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8102 | SAFETY RELIEF VALVES - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8102 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8103 | SAFETY RELIEF VALVES - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8103 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8104 | SAFETY RELIEF VALVES - SPARE PART LIST | 0000-FE-8104 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8105 | SAFETY RELIEF VALVES - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8105 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8106 | SAFETY RELIEF VALVES - SITE STORAGE PROCEDURE | 0000-FE-8106 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8107 | SAFETY RELIEF VALVES - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8107 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8108 | SAFETY RELIEF VALVES - INDEX DATA BOOK | 0000-FE-8108 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8109 | SAFETY RELIEF VALVES - CALCULATION SHEET | 0000-FE-8109 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8110 | SAFETY RELIEF VALVES - DIMENSIONAL DRAWING | 0000-FE-8110 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8111 | SAFETY RELIEF VALVES - QUALITY - PAINTING PROCEDURE & EXAMINATION WITH REPORTS | 0000-FE-8111 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8112 | SAFETY RELIEF VALVES - QUALITY - NDT PROCEDURE AND REPORTS | 0000-FE-8112 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8113 | SAFETY RELIEF VALVES - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8113 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8114 | SAFETY RELIEF VALVES - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8114 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8115 | SAFETY RELIEF VALVES - DATA BOOK | 0000-FE-8115 | FI | E&I | PSV0 | PSV | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8150 | PNEUMATIC ACTUATOR - SUB-VENDOR MONTHLY REPORT | 0000-FE-8150 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8151 | PNEUMATIC ACTUATOR - FABRICATION SCHEDULE | 0000-FE-8151 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8152 | PNEUMATIC ACTUATOR - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8152 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8153 | PNEUMATIC ACTUATOR - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8153 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8154 | PNEUMATIC ACTUATOR - SPARE PART LIST | 0000-FE-8154 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8155 | PNEUMATIC ACTUATOR - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8155 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8156 | PNEUMATIC ACTUATOR - SITE STORAGE PROCEDURE | 0000-FE-8156 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8157 | PNEUMATIC ACTUATOR - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8157 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8158 | PNEUMATIC ACTUATOR - INDEX DATA BOOK | 0000-FE-8158 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8159 | PNEUMATIC ACTUATOR - GENERAL ARRANGEMENT DRAWING & OPERATING DIAGRAM | 0000-FE-8159 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8160 | PNEUMATIC ACTUATOR - QUALITY - ELECTRICAL CONNECTION WIRING | 0000-FE-8160 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8161 | PNEUMATIC ACTUATOR - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8161 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8162 | PNEUMATIC ACTUATOR - QUALITY - NDT PROCEDURE AND REPORTS | 0000-FE-8162 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8163 | PNEUMATIC ACTUATOR - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8163 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8100 | 8164 | PNEUMATIC ACTUATOR - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8164 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8100 | 8165 | PNEUMATIC ACTUATOR - DATA BOOK | 0000-FE-8165 | FI | E&I | ACTU | ACTUATOR | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8200 | 8200 | O2 & CO ANALYSER - SUB-VENDOR MONTHLY REPORT | 0000-FE-8200 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8201 | O2 & CO ANALYSER - FABRICATION SCHEDULE | 0000-FE-8201 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8202 | O2 & CO ANALYSER - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8202 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8203 | O2 & CO ANALYSER - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8203 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8204 | O2 & CO ANALYSER - SPARE PART LIST | 0000-FE-8204 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8205 | O2 & CO ANALYSER - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8205 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8206 | O2 & CO ANALYSER - SITE STORAGE PROCEDURE | 0000-FE-8206 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8207 | O2 & CO ANALYSER - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8207 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8208 | O2 & CO ANALYSER - INDEX DATA BOOK | 0000-FE-8208 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8200 | 8209 | O2 & CO ANALYSER - GENERAL ARRANGEMENT DRAWING | 0000-FE-8209 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8210 | O2 & CO ANALYSER - PNEUMATIC CONNECTION DRAWING | 0000-FE-8210 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8211 | O2 & CO ANALYSER - ELECTRICAL CONNECTION WIRING | 0000-FE-8211 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8212 | O2 & CO ANALYSER - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8212 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8213 | O2 & CO ANALYSER - DATA BOOK | 0000-FE-8213 | FI | E&I | ANAL | ANALYSER | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8200 | 8250 | DENSITY METER - SUB-VENDOR MONTHLY REPORT | 0000-FE-8250 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8251 | DENSITY METER - FABRICATION SCHEDULE | 0000-FE-8251 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8252 | DENSITY METER - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8252 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8253 | DENSITY METER - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8253 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8254 | DENSITY METER - SPARE PART LIST | 0000-FE-8254 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8255 | DENSITY METER - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8255 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8256 | DENSITY METER - SITE STORAGE PROCEDURE | 0000-FE-8256 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8257 | DENSITY METER - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8257 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8258 | DENSITY METER - INDEX DATA BOOK | 0000-FE-8258 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8200 | 8259 | DENSITY METER - GENERAL ARRANGEMENT DRAWING | 0000-FE-8259 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8260 | DENSITY METER - ELECTRICAL CONNECTION WIRING | 0000-FE-8260 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8261 | DENSITY METER - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8261 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8200 | 8262 | DENSITY METER - DATA BOOK | 0000-FE-8262 | FI | E&I | DENS | DENSITY | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8300 | 8300 | ORIFICE PLATE - SUB-VENDOR MONTHLY REPORT | 0000-FE-8300 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8301 | ORIFICE PLATE - FABRICATION SCHEDULE | 0000-FE-8301 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8302 | ORIFICE PLATE - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8302 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8303 | ORIFICE PLATE - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8303 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8304 | ORIFICE PLATE - SPARE PART LIST | 0000-FE-8304 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8305 | ORIFICE PLATE - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8305 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8306 | ORIFICE PLATE - SITE STORAGE PROCEDURE | 0000-FE-8306 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8307 | ORIFICE PLATE - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8307 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8308 | ORIFICE PLATE - INDEX DATA BOOK | 0000-FE-8308 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8300 | 8309 | ORIFICE PLATE - DIMENSIONAL DRAWING | 0000-FE-8309 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8310 | ORIFICE PLATE - DATA BOOK | 0000-FE-8310 | FI | E&I | ORIF | ORIFICE | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8300 | 8350 | LEVEL GAUGE - SUB-VENDOR MONTHLY REPORT | 0000-FE-8350 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8351 | LEVEL GAUGE - FABRICATION SCHEDULE | 0000-FE-8351 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8352 | LEVEL GAUGE - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8352 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8353 | LEVEL GAUGE - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8353 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8354 | LEVEL GAUGE - SPARE PART LIST | 0000-FE-8354 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8355 | LEVEL GAUGE - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8355 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8356 | LEVEL GAUGE - SITE STORAGE PROCEDURE | 0000-FE-8356 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8357 | LEVEL GAUGE - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8357 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8358 | LEVEL GAUGE - INDEX DATA BOOK | 0000-FE-8358 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8300 | 8359 | LEVEL GAUGE - DIMENSIONAL DRAWING | 0000-FE-8359 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8360 | LEVEL GAUGE - ELECTRICAL CONNECTION WIRING (LIGHTING) | 0000-FE-8360 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8361 | LEVEL GAUGE - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8361 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8362 | LEVEL GAUGE - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8362 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8300 | 8363 | LEVEL GAUGE - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8363 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8300 | 8364 | LEVEL GAUGE - DATA BOOK | 0000-FE-8364 | FI | E&I | LEVE | LEVEL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8400 | 8400 | RADAR LEVEL - SUB-VENDOR MONTHLY REPORT | 0000-FE-8400 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8401 | RADAR LEVEL - FABRICATION SCHEDULE | 0000-FE-8401 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8402 | RADAR LEVEL - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8402 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8403 | RADAR LEVEL - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8403 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8404 | RADAR LEVEL - SPARE PART LIST | 0000-FE-8404 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8405 | RADAR LEVEL - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8405 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8406 | RADAR LEVEL - SITE STORAGE PROCEDURE | 0000-FE-8406 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8407 | RADAR LEVEL - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8407 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8408 | RADAR LEVEL - INDEX DATA BOOK | 0000-FE-8408 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8400 | 8409 | RADAR LEVEL - DIMENSIONAL DRAWING | 0000-FE-8409 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8410 | RADAR LEVEL - ELECTRICAL CONNECTION WIRING | 0000-FE-8410 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8411 | RADAR LEVEL - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8411 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8412 | RADAR LEVEL - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8412 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8413 | RADAR LEVEL - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8413 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8400 | 8414 | RADAR LEVEL - DATA BOOK | 0000-FE-8414 | FI | E&I | LEVE | RADAR | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8400 | 8450 | PRESSURE & DP FLOW TRANSMITTER - SUB-VENDOR MONTHLY REPORT | 0000-FE-8450 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8451 | PRESSURE & DP FLOW TRANSMITTER - FABRICATION SCHEDULE | 0000-FE-8451 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8452 | PRESSURE & DP FLOW TRANSMITTER - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8452 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8453 | PRESSURE & DP FLOW TRANSMITTER - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8453 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8454 | PRESSURE & DP FLOW TRANSMITTER - SPARE PART LIST | 0000-FE-8454 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8455 | PRESSURE & DP FLOW TRANSMITTER - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8455 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8456 | PRESSURE & DP FLOW TRANSMITTER - SITE STORAGE PROCEDURE | 0000-FE-8456 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8457 | PRESSURE & DP FLOW TRANSMITTER - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8457 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8458 | PRESSURE & DP FLOW TRANSMITTER - INDEX DATA BOOK | 0000-FE-8458 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8400 | 8459 | PRESSURE & DP FLOW TRANSMITTER - DIMENSIONAL DRAWING | 0000-FE-8459 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8460 | PRESSURE & DP FLOW TRANSMITTER - ELECTRICAL CONNECTION WIRING | 0000-FE-8460 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8461 | PRESSURE & DP FLOW TRANSMITTER - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8461 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8462 | PRESSURE & DP FLOW TRANSMITTER - QUALITY - SIL CERTIFICATE | 0000-FE-8462 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8400 | 8463 | PRESSURE & DP FLOW TRANSMITTER - DATA BOOK | 0000-FE-8463 | FI | E&I | FLOW | FLOW | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8500 | 8500 | PRESSURE GAUGE - SUB-VENDOR MONTHLY REPORT | 0000-FE-8500 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8501 | PRESSURE GAUGE - FABRICATION SCHEDULE | 0000-FE-8501 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8502 | PRESSURE GAUGE - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8502 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8503 | PRESSURE GAUGE - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8503 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8504 | PRESSURE GAUGE - SPARE PART LIST | 0000-FE-8504 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8505 | PRESSURE GAUGE - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8505 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8506 | PRESSURE GAUGE - SITE STORAGE PROCEDURE | 0000-FE-8506 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8507 | PRESSURE GAUGE - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8507 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8508 | PRESSURE GAUGE - INDEX DATA BOOK | 0000-FE-8508 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8500 | 8509 | PRESSURE GAUGE - DIMENSIONAL DRAWING | 0000-FE-8509 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8510 | PRESSURE GAUGE - DATA BOOK | 0000-FE-8510 | FI | E&I | PRES | PRESSURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8500 | 8550 | DRAFT GAUGE - SUB-VENDOR MONTHLY REPORT | 0000-FE-8550 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8551 | DRAFT GAUGE - FABRICATION SCHEDULE | 0000-FE-8551 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8552 | DRAFT GAUGE - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8552 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8553 | DRAFT GAUGE - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8553 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8554 | DRAFT GAUGE - SPARE PART LIST | 0000-FE-8554 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8555 | DRAFT GAUGE - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8555 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8556 | DRAFT GAUGE - SITE STORAGE PROCEDURE | 0000-FE-8556 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8557 | DRAFT GAUGE - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8557 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8558 | DRAFT GAUGE - INDEX DATA BOOK | 0000-FE-8558 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8500 | 8559 | DRAFT GAUGE - DIMENSIONAL DRAWING | 0000-FE-8559 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8500 | 8560 | DRAFT GAUGE - DATA BOOK | 0000-FE-8560 | FI | E&I | DRAF | DRAFT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8600 | 8600 | TEMPERATURE ELEMENT & THERMOWELL - SUB-VENDOR MONTHLY REPORT | 0000-FE-8600 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8601 | TEMPERATURE ELEMENT & THERMOWELL - FABRICATION SCHEDULE | 0000-FE-8601 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8602 | TEMPERATURE ELEMENT & THERMOWELL - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8602 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8603 | TEMPERATURE ELEMENT & THERMOWELL - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8603 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8604 | TEMPERATURE ELEMENT & THERMOWELL - SPARE PART LIST | 0000-FE-8604 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8605 | TEMPERATURE ELEMENT & THERMOWELL - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8605 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8606 | TEMPERATURE ELEMENT & THERMOWELL - SITE STORAGE PROCEDURE | 0000-FE-8606 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8607 | TEMPERATURE ELEMENT & THERMOWELL - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8607 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8608 | TEMPERATURE ELEMENT & THERMOWELL - INDEX DATA BOOK | 0000-FE-8608 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8600 | 8609 | TEMPERATURE ELEMENT & THERMOWELL - DIMENSIONAL DRAWING | 0000-FE-8609 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8610 | TEMPERATURE ELEMENT & THERMOWELL - ELECTRICAL CONNECTION WIRING | 0000-FE-8610 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8611 | TEMPERATURE ELEMENT & THERMOWELL - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8611 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8612 | TEMPERATURE ELEMENT & THERMOWELL - QUALITY - PWHT PROCEDURE (IF APPLICABLE) | 0000-FE-8612 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8613 | TEMPERATURE ELEMENT & THERMOWELL - QUALITY - WELDING BOOK (IF APPLICABLE) | 0000-FE-8613 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8600 | 8614 | TEMPERATURE ELEMENT & THERMOWELL - DATA BOOK | 0000-FE-8614 | FI | E&I | TEMP | TEMPERATURE | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8600 | 8650 | SKIN THERMOCOUPLE - SUB-VENDOR MONTHLY REPORT | 0000-FE-8650 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8651 | SKIN THERMOCOUPLE - FABRICATION SCHEDULE | 0000-FE-8651 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8652 | SKIN THERMOCOUPLE - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8652 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8653 | SKIN THERMOCOUPLE - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8653 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8654 | SKIN THERMOCOUPLE - SPARE PART LIST | 0000-FE-8654 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8655 | SKIN THERMOCOUPLE - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8655 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8656 | SKIN THERMOCOUPLE - SITE STORAGE PROCEDURE | 0000-FE-8656 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8657 | SKIN THERMOCOUPLE - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8657 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8658 | SKIN THERMOCOUPLE - INDEX DATA BOOK | 0000-FE-8658 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8600 | 8659 | SKIN THERMOCOUPLE - DIMENSIONAL DRAWING | 0000-FE-8659 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8660 | SKIN THERMOCOUPLE - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8660 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8600 | 8661 | SKIN THERMOCOUPLE - DATA BOOK | 0000-FE-8661 | FI | E&I | SKIN | SKIN | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8700 | 8700 | TEMPERATURE TRANSMITTER - SUB-VENDOR MONTHLY REPORT | 0000-FE-8700 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8701 | TEMPERATURE TRANSMITTER - FABRICATION SCHEDULE | 0000-FE-8701 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8702 | TEMPERATURE TRANSMITTER - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8702 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8703 | TEMPERATURE TRANSMITTER - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8703 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8704 | TEMPERATURE TRANSMITTER - SPARE PART LIST | 0000-FE-8704 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8705 | TEMPERATURE TRANSMITTER - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8705 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8706 | TEMPERATURE TRANSMITTER - SITE STORAGE PROCEDURE | 0000-FE-8706 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8707 | TEMPERATURE TRANSMITTER - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8707 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8708 | TEMPERATURE TRANSMITTER - INDEX DATA BOOK | 0000-FE-8708 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8700 | 8709 | TEMPERATURE TRANSMITTER - DIMENSIONAL DRAWING | 0000-FE-8709 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8710 | TEMPERATURE TRANSMITTER - ELECTRICAL CONNECTION WIRING | 0000-FE-8710 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8711 | TEMPERATURE TRANSMITTER - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8711 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8712 | TEMPERATURE TRANSMITTER - DATA BOOK | 0000-FE-8712 | FI | E&I | TT00 | TT | YES | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | 40 | 2019-06-24 | PO+40W
FE | 8700 | 8750 | JUNCTION BOX - SUB-VENDOR MONTHLY REPORT | 0000-FE-8750 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8751 | JUNCTION BOX - FABRICATION SCHEDULE | 0000-FE-8751 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8752 | JUNCTION BOX - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8752 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8753 | JUNCTION BOX - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8753 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8754 | JUNCTION BOX - SPARE PART LIST | 0000-FE-8754 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8755 | JUNCTION BOX - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8755 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8756 | JUNCTION BOX - SITE STORAGE PROCEDURE | 0000-FE-8756 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8757 | JUNCTION BOX - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8757 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8758 | JUNCTION BOX - INDEX DATA BOOK | 0000-FE-8758 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8700 | 8759 | JUNCTION BOX - GENERAL ARRANGEMENT DRAWING | 0000-FE-8759 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8760 | JUNCTION BOX - INTERNAL ELECTRICAL WIRING | 0000-FE-8760 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8761 | JUNCTION BOX - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8761 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8700 | 8762 | JUNCTION BOX - DATA BOOK | 0000-FE-8762 | FI | E&I | JB00 | JB | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8800 | 8800 | LOCAL PANEL - SUB-VENDOR MONTHLY REPORT | 0000-FE-8800 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8801 | LOCAL PANEL - FABRICATION SCHEDULE | 0000-FE-8801 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8802 | LOCAL PANEL - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8802 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8803 | LOCAL PANEL - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8803 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8804 | LOCAL PANEL - SPARE PART LIST | 0000-FE-8804 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8805 | LOCAL PANEL - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8805 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8806 | LOCAL PANEL - SITE STORAGE PROCEDURE | 0000-FE-8806 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8807 | LOCAL PANEL - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8807 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8808 | LOCAL PANEL - INDEX DATA BOOK | 0000-FE-8808 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8800 | 8809 | LOCAL PANEL - GENERAL ARRANGEMENT DRAWING | 0000-FE-8809 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8810 | LOCAL PANEL - INTERNAL ELECTRICAL WIRING | 0000-FE-8810 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8811 | LOCAL PANEL - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8811 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8812 | LOCAL PANEL - DATA BOOK | 0000-FE-8812 | FI | E&I | LP00 | LP | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8800 | 8850 | ELECTRICAL BULK - SUB-VENDOR MONTHLY REPORT | 0000-FE-8850 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8851 | ELECTRICAL BULK - FABRICATION SCHEDULE | 0000-FE-8851 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8852 | ELECTRICAL BULK - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8852 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8853 | ELECTRICAL BULK - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8853 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8854 | ELECTRICAL BULK - SPARE PART LIST | 0000-FE-8854 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8855 | ELECTRICAL BULK - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8855 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8856 | ELECTRICAL BULK - SITE STORAGE PROCEDURE | 0000-FE-8856 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8857 | ELECTRICAL BULK - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8857 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8858 | ELECTRICAL BULK - INDEX DATA BOOK | 0000-FE-8858 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8800 | 8859 | ELECTRICAL BULK - DIMENSIONAL DRAWING | 0000-FE-8859 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8860 | ELECTRICAL BULK - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8860 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8800 | 8861 | ELECTRICAL BULK - DATA BOOK | 0000-FE-8861 | FI | E&I | BULK | BULK ELECTRICAL | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8900 | 8900 | INSTRUMENT PROTECTION BOX - SUB-VENDOR MONTHLY REPORT | 0000-FE-8900 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8901 | INSTRUMENT PROTECTION BOX - FABRICATION SCHEDULE | 0000-FE-8901 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8902 | INSTRUMENT PROTECTION BOX - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8902 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8903 | INSTRUMENT PROTECTION BOX - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8903 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8904 | INSTRUMENT PROTECTION BOX - SPARE PART LIST | 0000-FE-8904 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8905 | INSTRUMENT PROTECTION BOX - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8905 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8906 | INSTRUMENT PROTECTION BOX - SITE STORAGE PROCEDURE | 0000-FE-8906 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8907 | INSTRUMENT PROTECTION BOX - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8907 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8908 | INSTRUMENT PROTECTION BOX - INDEX DATA BOOK | 0000-FE-8908 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8900 | 8909 | INSTRUMENT PROTECTION BOX - DIMENSIONAL DRAWING | 0000-FE-8909 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8910 | INSTRUMENT PROTECTION BOX - DATA BOOK | 0000-FE-8910 | FI | E&I | PB00 | PROTECTION BOX | YES | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8900 | 8950 | AIRCRAFT WARNING LIGHT - SUB-VENDOR MONTHLY REPORT | 0000-FE-8950 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8951 | AIRCRAFT WARNING LIGHT - FABRICATION SCHEDULE | 0000-FE-8951 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8952 | AIRCRAFT WARNING LIGHT - PROGRESS REPORT DOCUMENTS LIST | 0000-FE-8952 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8953 | AIRCRAFT WARNING LIGHT - QUALITY - INSPECTION AND TEST PLAN | 0000-FE-8953 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8954 | AIRCRAFT WARNING LIGHT - SPARE PART LIST | 0000-FE-8954 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8955 | AIRCRAFT WARNING LIGHT - SHIPPING AND PACKING INSTRUCTIONS | 0000-FE-8955 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8956 | AIRCRAFT WARNING LIGHT - SITE STORAGE PROCEDURE | 0000-FE-8956 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8957 | AIRCRAFT WARNING LIGHT - INSTRUCTION, OPERATING AND MAINTENANCE MANUAL | 0000-FE-8957 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8958 | AIRCRAFT WARNING LIGHT - INDEX DATA BOOK | 0000-FE-8958 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FE | 8900 | 8959 | AIRCRAFT WARNING LIGHT - GENERAL ARRANGEMENT DRAWING | 0000-FE-8959 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8960 | AIRCRAFT WARNING LIGHT - INTERNAL ELECTRICAL WIRING | 0000-FE-8960 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8961 | AIRCRAFT WARNING LIGHT - QUALITY - ATEX / GOST CERTIFICATES | 0000-FE-8961 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FE | 8900 | 8962 | AIRCRAFT WARNING LIGHT - DATA BOOK | 0000-FE-8962 | FI | E&I | AWL0 | AWL | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 40 | 2019-06-24 | PO+40W
FG | 0 | 1 | HEATER SCHEMATIC VIEWS - ELEVATIONS | 0000-FG-001 | FI | MEC | GENE | GENERAL DRAWINGS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FG | 0 | 1 | KEY DESIGN SKETCHES | 0000-FG-001 | FI | PRO | APH0 | ??? | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FG | 0 | 2 | HEATER SCHEMATIC VIEWS - PLAN VIEWS | 0000-FG-002 | FI | MEC | GENE | GENERAL DRAWINGS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FG | 0 | 5 | FLUE GAS DUCT & AIR DUCT SCHEMATIC VIEWS (IF APH SYSTEM) | 0000-FG-005 | FI | STR | APH | GENERAL DRAWINGS | NO | YES | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 3 | 2018-10-08 | PO+3W
FJ | 0 | 1 | DATA SHEET - HEATER | 0000-FJ-001 | FR | PRO | GENE | GENERAL | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 6 | 2018-10-29 | PO+6W
FJ | 200 | 201 | DATA SHEET - BURNER | 0000-FJ-201 | FR | PRO | BURN | BURNER | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 6 | 2018-10-29 | PO+6W
FJ | 700 | 700 | DATA SHEET - SOOTBLOWER | 0000-FJ-700 | FR | PRO | SOOT | SOOTBLOWER | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FJ | 700 | 720 | DATA SHEET - FANS | 0000-FJ-720 | FR | PRO | FANS | FAN | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FJ | 700 | 720 | DATA SHEET - STEAM TURBINE | 0000-FJ-720 | FR | PRO | FANS | FAN | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FJ | 700 | 740 | DATA SHEET - APH/SAPH | 0000-FJ-740 | FR | PRO | APH0 | APH | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FJ | 700 | 760 | DATA SHEET - PUMP | 0000-FJ-760 | FR | PRO | PUMP | PUMP | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 10 | 2018-11-26 | PO+10W
FJ | 700 | 780 | DATA SHEET - STEAM DRUM | 0000-FJ-780 | FR | PRO | DRUM | STEAM DRUM | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 10 | 2018-11-26 | PO+10W
FJ | 800 | 801 | FUNCTIONAL ANALYSIS | 0000-FJ-801 | FR | E&I | INST | INSTRUMENTATION | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 802 | CONTROL LOOP DESCRIPTION | 0000-FJ-802 | FR | E&I | INST | INSTRUMENTATION | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 24 | 2019-03-04 | PO+24W
FJ | 800 | 803 | DATA PROCESS - CONTROL VALVE | 0000-FJ-803 | FR | E&I | CV00 | CV | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 804 | DATA PROCESS - PRESSURE SAFETY VALVE | 0000-FJ-804 | FR | E&I | PSV0 | PSV | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 16 | 2019-01-07 | PO+16W
FJ | 800 | 805 | DATA PROCESS - FLOW ELEMENT | 0000-FJ-805 | FR | E&I | FLOW | FLOW | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 806 | DATA PROCESS - PRESSURE INSTRUMENT | 0000-FJ-806 | FR | E&I | PRES | PRESSURE | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 807 | DATA PROCESS - LEVEL INSTRUMENT | 0000-FJ-807 | FR | E&I | LEVE | LEVEL | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 16 | 2019-01-07 | PO+16W
FJ | 800 | 808 | DATA PROCESS - TEMPERATURE INSTRUMENT | 0000-FJ-808 | FR | E&I | TEMP | TEMPERATURE | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 809 | DATA PROCESS - ANALYSER | 0000-FJ-809 | FR | E&I | ANAL | ANALYSER | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FJ | 800 | 810 | DATA SHEET - SILENCERS | 0000-FJ-810 | FR | E&I | SILE | SILENCER | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 16 | 2019-01-07 | PO+16W
FJ | 800 | 811 | DATA SHEET - DESUPERHEATER | 0000-FJ-811 | FR | E&I | DESU | DESUP | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 16 | 2019-01-07 | PO+16W
FJ | 900 | 901 | OPERATING & MAINTENANCE MANUAL | 0000-FJ-901 | FR | PRO | OPMA | OPERATING MANUAL | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 30 | 2019-04-15 | PO+30W
FK | 0 | 1 | SCHEMATIC VIEW-ELEVATION | 0000-FK-001 | FI | PRO | PROC | PROCESS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FK | 0 | 2 | SCHEMATIC VIEW-PLAN VIEW | 0000-FK-002 | FI | PRO | PROC | PROCESS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FK | 0 | 3 | TUBE WALL CALCULATION, FG T° ACROSS CONVECTION COILS | 0000-FK-003 | FI | PRO | PROC | PROCESS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FK | 0 | 4 | OUTSIDE CASING T° | 0000-FK-004 | FI | PRO | PROC | PROCESS | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FK | 0 | 5 | OTHERS | 0000-FK-005 | FI | PRO | PROC | PROCESS | NO | YEs | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FM | 0 | 1 | HEATER 3D MODEL | 0000-FM-001 | FR | MEC | 3D00 | 3D | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 10 | 2018-11-26 | PO+10W
FM | 0 | 2 | HEATER 3D MODEL (60%) | 0000-FM-002 | FR | MEC | 3D00 | 3D | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 15 | 2018-12-31 | PO+15W
FM | 0 | 3 | HEATER 3D MODEL (90%) | 0000-FM-003 | FR | MEC | 3D00 | 3D | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
FN | 100 | 101 | SEAMLESS STEEL PIPE (AS) | 0000-FN-101 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 102 | SEAMLESS STEEL PIPE (AS) | 0000-FN-102 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 103 | SEAMLESS STEEL PIPE (CS) | 0000-FN-103 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 104 | SEAMLESS STEEL PIPE (CS) | 0000-FN-104 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 105 | SEAMLESS STEEL PIPE (AS) | 0000-FN-105 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 106 | SEAMLESS STEEL PIPE (AS) | 0000-FN-106 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 107 | SEAMLESS STEEL PIPE (CS) | 0000-FN-107 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 108 | SEAMLESS STEEL PIPE (CS) | 0000-FN-108 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 109 | SEAMLESS STEEL PIPE (CS) | 0000-FN-109 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 110 | SEAMLESS STEEL PIPE (CS) | 0000-FN-110 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 111 | EXTRUDED PIPE (AS) | 0000-FN-111 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 130 | ELBOWS (CS ) | 0000-FN-130 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 131 | ELBOWS (AS ) | 0000-FN-131 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 132 | REDUCING TEES (CS) | 0000-FN-132 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 133 | CAPS (CS) | 0000-FN-133 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 134 | FORGED STUB | 0000-FN-134 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 160 | FLANGES (CS ) | 0000-FN-160 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 161 | FLANGES (AS) | 0000-FN-161 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 162 | FLANGES (AS) | 0000-FN-162 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 180 | STUD BOLTS WITH 2 HEAVY NUTS | 0000-FN-180 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 181 | SPIRAL WOUND GASKET | 0000-FN-181 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 100 | 182 | TUBE & FITTINGS: SS AND HIGHER | 0000-FN-182 | FI | MEC | FITI | FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 300 | STEEL PLATE, BEAMS, ACCESSORIES | 0000-FN-300 | FI | STR | STRU | STRUCTURE DETAIL DRAWINGS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 301 | DROP WARP TAPE | 0000-FN-301 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 302 | SEALING SLEEVES | 0000-FN-302 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 303 | CERAMIC FIBER MATERIALS (ROPE, CLOTH , PACKING) | 0000-FN-303 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 304 | NAME PLATE | 0000-FN-304 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 305 | MASTIC | 0000-FN-305 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 300 | 306 | WINCH CONTROL | 0000-FN-306 | FI | STR | STRU | STEEL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 400 | 401 | BENDING PIPE | 0000-FN-401 | FI | MEC | TUBE | TUBE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 400 | 402 | FINNED PIPE | 0000-FN-402 | FI | MEC | FINN | FINNING | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 400 | 403 | FINNED PIPE | 0000-FN-403 | FI | MEC | FINN | FINNING | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 400 | 404 | FINNED PIPE | 0000-FN-404 | FI | MEC | FINN | FINNING | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 400 | 410 | SPRING SUPPORT | 0000-FN-410 | FI | MEC | SSUP | SPRING SUPPORT | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 600 | 601 | MATERIAL REQUISITION - TUBE SHEET STEAM SUPERHEATER | 0000-FN-601 | FI | MEC | TSHE | TUBESHEET | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 600 | 602 | MATERIAL REQUISITION - TUBE SHEET STEAM GENERATION | 0000-FN-602 | FI | MEC | TSHE | TUBESHEET | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 600 | 603 | MATERIAL REQUISITION - TUBE SHEET CONVECTION | 0000-FN-603 | FI | MEC | TSHE | TUBESHEET | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 600 | 605 | MATERIAL REQUISITION - TUBE SHEET BFW | 0000-FN-605 | FI | MEC | TSHE | TUBESHEET | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 600 | 606 | MATERIAL REQUISITION - OBSERVATION WINDOW | 0000-FN-606 | FI | MEC | STRU | STRUCTURE | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FN | 800 | 891 | MATERIAL REQUISITION ‐ SKIN THERMOCOUPLES | 0000-FN-891 | FI | E&I | SKIN | SKIN | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4400 | MATERIAL REQUISITION ‐ PIPES (CS & LTCS) | 0000-FN-4400 | FI | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4401 | MATERIAL REQUISITION ‐ FLANGES (CS & LTCS) | 0000-FN-4401 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4402 | MATERIAL REQUISITION ‐ ELBOWS (CS & LTCS) | 0000-FN-4402 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4403 | MATERIAL REQUISITION ‐ REDUCERS (CS & LTCS) | 0000-FN-4403 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4404 | MATERIAL REQUISITION ‐ TEES (CS & LTCS) | 0000-FN-4404 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4405 | MATERIAL REQUISITION ‐ CAPS (CS & LTCS) | 0000-FN-4405 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4406 | MATERIAL REQUISITION ‐ MISCELLANEOUS ITEMS (CS & LTCS) | 0000-FN-4406 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4407 | MATERIAL REQUISITION ‐ GASKETS5 | 0000-FN-4407 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4408 | MATERIAL REQUISITION ‐ HARDWARE5 | 0000-FN-4408 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4410 | MATERIAL REQUISITION ‐ PIPES (SS) | 0000-FN-4410 | FI | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4411 | MATERIAL REQUISITION ‐ FLANGES (SS) | 0000-FN-4411 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4412 | MATERIAL REQUISITION ‐ ELBOWS (SS) | 0000-FN-4412 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4413 | MATERIAL REQUISITION ‐ REDUCERS (SS) | 0000-FN-4413 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4414 | MATERIAL REQUISITION ‐ TEES (SS) | 0000-FN-4414 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4415 | MATERIAL REQUISITION ‐ CAPS (SS) | 0000-FN-4415 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4416 | MATERIAL REQUISITION ‐ MISCELLANEOUS ITEMS (SS) | 0000-FN-4416 | FI | PIP | PIPI | PIPING FITTINGS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FN | 4400 | 4440 | MATERIAL REQUISITION - SPRING SUPPORTS | 0000-FN-4440 | FI | PIP | PIPI | PIPING SPRING SUPPPORTS | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 8 | 2018-11-12 | PO+8W
FQ | 0 | 1 | SCOPE OF INSPECTION HEATER AND EQUIPMENT & APPENDIX | 0000-FQ-001 | FR | INS | INSP | INSPECTION | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FQ | 0 | 2 | QUALITY ASSURANCE PLAN | 0000-FQ-002 | FR | QUA | QUAL | QUALITY | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 24 | 2019-03-04 | PO+24W
FQ | 0 | 3 | MANUFACTURING DATA BOOK INDEX | 0000-FQ-003 | FR | DOC | MADB | MAN DB | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 4 | MANUFACTURING DATA BOOK | 0000-FQ-004 | FR | DOC | MADB | MAN DB | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 5 | MECHANICAL DATA BOOK INDEX | 0000-FQ-005 | FR | DOC | MEDB | MECH DB | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 6 | MECHANICAL DATA BOOK | 0000-FQ-006 | FR | DOC | MEDB | MECH DB | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 7 | ERECTION DATA BOOK INDEX | 0000-FQ-007 | FR | DOC | ERDB | ERECTION DB | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 8 | ERECTION DATA BOOK | 0000-FQ-008 | FR | DOC | ERDB | ERECTION DB | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 9 | OPERATING AND MAINTENANCE MANUAL ( INSTALLATION, START-UP AND COMMISSIONING MANUAL ) | 0000-FQ-009 | FR | PRO | IMAN | INSTALLATION MANUAL | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FQ | 0 | 10 | INSPECTION SCHEDULE | 0000-FQ-010 | FR | INS | INSP | INSPECTION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
FR | 0 | 1 | PACKING LIST | 0000-FR-001 | FR | TRA | TRAN | TRANSPORT | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 30 | 2019-04-15 | PO+30W
FS | 200 | 200 | BURNERS SPECIFICATION | 0000-FS-200 | FI | PRO | BURN | BURNER | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FS | 300 | 300 | GENERAL PREFABRICATION HEATER | 0000-FS-300 | FI | MEC | PREF | PREFABRICATION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FS | 400 | 400 | PREFABRICATION COILS & MANIFOLDS | 0000-FS-400 | FI | MEC | PREF | PREFABRICATION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FS | 400 | 450 | PIPING PREFABRICATION | 0000-FS-450 | FI | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 6 | 2018-10-29 | PO+6W
FS | 500 | 500 | LINING APPLICATION | 0000-FS-500 | FI | MEC | PREF | PREFABRICATION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FS | 600 | 600 | CAST PIECES | 0000-FS-600 | FI | MEC | CAST | CAST PIECES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 6 | 2018-10-29 | PO+6W
FS | 700 | 700 | EQUIPMENT (STEAM DRUM, FAN, APH, sAPH) | 0000-FS-700 | FI | MEC | GENE | GENERAL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FS | 700 | 761 | CENTRIFUGAL PUMPS AND MOTORS - TECHNICAL SPECIFICATION | 0000-FS-761 | FI | MEC | PUMP | PUMP | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
FS | 700 | 781 | STEAM TURBINE - TECHNICAL SPECIFICATION | 0000-FS-781 | FI | PRO | DRUM | DRUM | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 700 | 782 | STEAM SEPARATOR - TECHNICAL SPECIFICATION | 0000-FS-782 | FI | MEC | DRUM | DRUM | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 801 | CONTROL VALVE SPECIFICATION | 0000-FS-801 | FI | E&I | CV00 | CV | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 802 | ON/OFF VALVE SPECIFICATION | 0000-FS-802 | FI | E&I | ONOF | ONOFF | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 803 | SAFETY RELIEF VALVE SPECIFICATION | 0000-FS-803 | FI | E&I | PSV0 | PSV | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 804 | FLAME DETECTOR SPECIFICATION | 0000-FS-804 | FI | E&I | BURN | BURNER | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 805 | PNEUMATIC ACTUATOR SPECIFICATION | 0000-FS-805 | FI | E&I | ACTU | ACTUATOR | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 810 | O2 & COE ANALYSER SPECIFICATION | 0000-FS-810 | FI | E&I | ANAL | ANALYSER | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 811 | DENSITY METER SPECIFICATION | 0000-FS-811 | FI | E&I | DENS | DENSITY | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 820 | ORIFICE PLATE SPECIFICATION | 0000-FS-820 | FI | E&I | ORIF | ORIFICE | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 830 | LEVEL GAUGE SPECIFICATION | 0000-FS-830 | FI | E&I | LEVE | LEVEL | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 831 | RADAR LEVEL TRANSMITTER SPECIFICATION | 0000-FS-831 | FI | E&I | LEVE | RADAR | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 840 | PRESSURE & DP FLOW TRANSMITTER SPECIFICATION | 0000-FS-840 | FI | E&I | FLOW | FLOW | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 841 | PRESSURE GAUGE SPECIFICATION | 0000-FS-841 | FI | E&I | PRES | PRESSURE | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 842 | DRAFT GAUGE SPECIFICATION | 0000-FS-842 | FI | E&I | DRAF | DRAFT | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 850 | THERMOWELL & TEMPERATURE ELEMENT SPECIFICATION | 0000-FS-850 | FI | E&I | TEMP | TEMPERATURE | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 851 | SKIN THERMOCOUPLE SPECIFICATION | 0000-FS-851 | FI | E&I | SKIN | SKIN | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 852 | TEMPERATURE TRANSMITTER SPECIFICATION | 0000-FS-852 | FI | E&I | TT00 | TT | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 860 | INTRUMENT PROTECTION BOX SPECIFICATION | 0000-FS-860 | FI | E&I | PB00 | PROTECTION BOX | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 12 | 2018-12-10 | PO+12W
FS | 800 | 870 | LOCAL PANEL SPECIFICATION | 0000-FS-870 | FI | E&I | LP00 | LP | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 871 | JUNCTION BOX SPECIFICATION | 0000-FS-871 | FI | E&I | JB00 | JB | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 880 | BULK SPECIFICATION | 0000-FS-880 | FI | E&I | BULK | BULK | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 12 | 2018-12-10 | PO+12W
FS | 800 | 890 | AIRCRAFT WARNING LIGHT SPECIFICATION | 0000-FS-890 | FI | E&I | AWL0 | AWL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
FS | 900 | 901 | SPARE PART LISTS | 0000-FS-901 | FR | MEC | SPAR | SPARE | NO | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES | YES | NO | YES | NO | NO | YES | NO | NO | NO | NO | YES | NO | YES | YES | 30 | 2019-04-15 | PO+30W
FS | 900 | 930 | ERECTION PROCEDURE | 0000-FS-930 | FI | TRA | EREC | ERECTION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | YES | YES | 0 |  | PO+0W
FS | 900 | 930 | ERECTION DRAWING | 0000-FS-930 | FI | TRA | EREC | ERECTION | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | YES | YES | 0 |  | PO+0W
FS | 900 | 950 | TRANSPORT SPECIFICATION (PACKING) | 0000-FS-950 | FR | TRA | PACK | PACKING | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
FS | 4000 | 4000 | PIPING CLASS | 0000-FS-4000 | FR | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FS | 4000 | 4001 | LINE DESIGNATION LIST | 0000-FS-4001 | FR | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 16 | 2019-01-07 | PO+16W
FS | 4000 | 4002 | TIES-IN LIST | 0000-FS-4002 | FR | PIP | PIPI | PIPING | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 14 | 2018-12-24 | PO+14W
NT | 800 | 801 | MATERIAL REQUISITION ‐ CONTROL VALVE | 0000-NT-801 | FI | E&I | CV00 | CV | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 802 | MATERIAL REQUISITION ‐ ON/OFF VALVE | 0000-NT-802 | FI | E&I | ONOF | ONOFF | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 803 | MATERIAL REQUISITION ‐ SAFETY RELIEF VALVE | 0000-NT-803 | FI | E&I | PSV0 | PSV | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 805 | MATERIAL REQUISITION ‐ PNEUMATIC ACTUATOR | 0000-NT-805 | FI | E&I | ACTU | ACTUATOR | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 810 | MATERIAL REQUISITION ‐ O2 & COE ANALYSER | 0000-NT-810 | FI | E&I | ANAL | ANALYSER | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 811 | MATERIAL REQUISITION ‐ DENSITY METER | 0000-NT-811 | FI | E&I | DENS | DENSITY | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 820 | MATERIAL REQUISITION ‐ ORIFICE PLATE | 0000-NT-820 | FI | E&I | ORIF | ORIFICE | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 830 | MATERIAL REQUISITION ‐ LEVEL GAUGE | 0000-NT-830 | FI | E&I | LEVE | LEVEL | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 831 | MATERIAL REQUISITION ‐ RADAR LEVEL TRANSMITTER | 0000-NT-831 | FI | E&I | LEVE | RADAR | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 840 | MATERIAL REQUISITION ‐ PRESSURE & DP FLOW TRANSMITTER | 0000-NT-840 | FI | E&I | FLOW | FLOW | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 841 | MATERIAL REQUISITION ‐ PRESSURE GAUGE | 0000-NT-841 | FI | E&I | PRES | PRESSURE | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 842 | MATERIAL REQUISITION ‐ DRAFT GAUGE | 0000-NT-842 | FI | E&I | DRAF | DRAFT | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 850 | MATERIAL REQUISITION ‐ THERMOWELL & TEMPERATURE ELEMENT | 0000-NT-850 | FI | E&I | TEMP | TEMPERATURE | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 851 | MATERIAL REQUISITION ‐ SKIN THERMOCOUPLE | 0000-NT-851 | FI | E&I | SKIN | SKIN | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 852 | MATERIAL REQUISITION ‐ TEMPERATURE TRANSMITTER | 0000-NT-852 | FI | E&I | TT00 | TT | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | 20 | 2019-02-04 | PO+20W
NT | 800 | 860 | MATERIAL REQUISITION ‐ INTRUMENT PROTECTION BOX | 0000-NT-860 | FI | E&I | PB00 | PROTECTION BOX | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 870 | MATERIAL REQUISITION ‐ LOCAL PANEL | 0000-NT-870 | FI | E&I | LP00 | LP | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 871 | MATERIAL REQUISITION ‐ JUNCTION BOX | 0000-NT-871 | FI | E&I | JB00 | JB | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 880 | MATERIAL REQUISITION ‐ BULK | 0000-NT-880 | FI | E&I | BULK | BULK | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
NT | 800 | 890 | MATERIAL REQUISITION ‐ AIRCRAFT WARNING LIGHT | 0000-NT-890 | FI | E&I | AWL0 | AWL | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 20 | 2019-02-04 | PO+20W
FS | 400 | 410 | SPRING SUPPORTS SPECIFICATION | 0000-FS-410 | FI | MEC |  |  | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | 8 | 2018-11-12 | PO+8W
| 800 | 800 | E & I FOR SHOP ERECTION | 0000--800 |  | E&I |  |  | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO |  | #VALUE! | PO+W
Formulas:
Estimate date Rev0 = IF([Weeks after PO]=0,"",IF(WEEKDAY(IF([Weeks after PO]=0,"",SDATE+[Weeks after PO]*7),1)=1,IF([Weeks after PO]=0,"",SDATE+[Weeks after PO]*7)+1,IF(WEEKDAY(IF([Weeks after PO]=0,"",SDATE+[Weeks after PO]*7),1)=7,IF([Weeks after PO]=0,"",SDATE+[Weeks after PO]*7)+2,IF([Weeks after PO]=0,"",SDATE+[Weeks after PO]*7))))

## Auxiliary (hidden)
GROUP1 | GROUP2 | TO USE | TYPE | TYPE_DESCR | AREA | AREA_DESCR | REVISION | DATE | BY
3D00 | 3D | 3D00 | FA | PROJECT | GEN | GENERAL
ACTU | ACTUATOR | ACTU | FC | CALCULATION | STR | STRUCTURE
ANAL | ANALYSER | ANAL | FD | DRAWINGS | MEC | MECHANICAL
APH0 | APH | APH0 | FE | SUB CONTRACTORS DOCUMENTS | PIP | PIPING
AWL0 | AWL | AWL0 | FG | SKETCHES & STUDIES | PRO | PROCESS
BOIL | GAS BOILER | BOIL | FJ | PROCESS | E&I | ELECTRICAL & INSTRUMENTATION
BULK | BULK ELECTRICAL | BULK | FK | PROCESS WORK SHEETS | TRA | TRANSPORT
BULK | BULK | BULK | FL | LICENCOR AND / OR CLIENT DOCUMENTATION | CLI | CLIENT DOCUMENTATION
BURN | BURNER | BURN | FM | 3D MODEL | FAB | FABRICATION
CALC | CALCULATION | CALC | FN | MATERIAL REQUISITIONWITH PARTICULAR REQUIREMENT | INS | INPECTION
CALC | CALCUL PROCESS | CALC | FQ | QUALITY CONTROL | QUA | QUALITY
CAST | CAST SUPPORT | CAST | FR | TRANSPORT | DOC | DOC CONTROL
CAST | CAST PIECES | CAST | FS | TECHNICAL SPECIFICATION
COIL | COIL & MANIFOLDS | COIL
COIL | COIL & MANIFOLD DRAWINGS | COIL
CV00 | CV | CV00
DENS | DENSITY | DENS
DESU | DESUP | DESU
DRAF | DRAFT | DRAF
DRUM | STEAM DRUM | DRUM
DRUM | DRUM | DRUM
EQUI | EQUIPMENT DRAWINGS | EQUI
ERDB | ERECTION DB | ERDB
EREC | ERECTION | EREC
FANS | FANS | FANS
FANS | FAN | FANS
FINN | FINNING STUDDING | FINN
FINN | FINNING | FINN
FITI | FITTINGS | FITI
FLOW | FLOW | FLOW
GENE | GENERAL DRAWINGS | GENE
GENE | GENERAL | GENE
IMAN | INSTALLATION MANUAL | IMAN
INSP | INSPECTION | INSP
INST | INSTRUMENTATION | INST
INSU | INSULATION DRAWINGS | INSU
INSU | INSULATION | INSU
JB00 | JB | JB00
LEVE | LEVEL | LEVE
LEVE | RADAR | LEVE
LIFT | LIFTING | LIFT
LP00 | LP | LP00
MADB | MAN DB | MADB
MEDB | MECH DB | MEDB
ONOF | ONOFF | ONOF
OPMA | OPERATING MANUAL | OPMA
ORIF | ORIFICE | ORIF
PB00 | PROTECTION BOX | PB00
PID0 | PFD & PID | PID0
PIPI | PIPING STRESS ANALYSIS | PIPI
PIPI | PIPING DRAWINGS | PIPI
PIPI | PIPING | PIPI
PIPI | PIPING FITTINGS | PIPI
PIPI | PIPING SPRING SUPPPORTS | PIPI
PREF | PREFABRICATION | PREF
PRES | PRESSURE | PRES
PROC | PROCESS | PROC
PROJ | PROJECT | PROJ
PSV0 | PSV | PSV0
PUMP | PUMPS | PUMP
PUMP | PUMP | PUMP
QUAL | QUALITY | QUAL
REFE | REFERENCE | REFE
SAPH | SAPH | SAPH
SILE | SILENCER | SILE
SKIN | SKIN | SKIN
SOOT | SOOTBLOWER | SOOT
SPAR | SPARE | SPAR
SSUP | SPRING SUPPORT | SSUP
STRU | MAIN STRUCTURES | STRU
STRU | STRUCTURE DETAIL DRAWINGS | STRU
STRU | STEEL | STRU
STRU | STRUCTURE | STRU
TEMP | TEMPERATURE | TEMP
TRAN | TRANSPORT DRAWINGS | TRAN
TRAN | TRANSPORT | TRAN
TSHE | TUBESHEET | TSHE
TT00 | TT | TT00
TUBE | TUBES & FITTINGS | TUBE
TUBE | TUBE | TUBE
PACK | PACKING | PACK

## PDL0 (MODEL) (hidden)
MASTER DOCUMENT LIST
CLIENT PROJECT REF. : |  | N°3000864 |  |  |  |  | HEURTEY PROJECT REF. : |  | TBD
CLIENT : |  | NYNAS |  |  |  |  | HEURTEY PROPOSAL REF.: |  | EP18020
PROJECT NAME : |  | BED HEATER - New Heater Gothenburg Refinery |  |  |  |  | DELIVERY DATE (PRELIMINARY) : |  | 2018-11-14
TECHNICAL REQUISITION REF. : | [6 empty] | HP MDL : |  | 0000-FA-014
DOC CONTROL E-MAIL : |  | TBD |  |  |  |  | DOC CONTROL HP : |  | TBD
LEGEND : PO : Purchase order / W : Week / M : Month / BD : Before delivery / AD : After delivery - PURPOSE: FI : For information / FR : For review and comments | [6 empty] | PRELIMINARY ISSUED FOR PROPOSAL TO SHOW SCOPE. ANY INCLUSIONS/DIVISIONS OF DOCUMENTS WILL BE DONE AFTER P.O
CLIENT DOCUMENT N° | ITEMS | HP DOCUMENT N° | DOCUMENT TITLE | FIRST ISSUE DATE | DUE DATE | PURPOSE | HP TN Num. | REV. | TRANSMITTAL DATE | SCHEDULE RETURN DATE | TN Num. | RETURN DATE | DOCUMENT STATUS
| H-1001 | 0000-FA-001 | PROJECT ORGANIZATION CHART | PO+4W | 2018-10-29 | FI |  | 0
| H-1001 | 0000-FA-005 | PROJECT COORDINATION PROCEDURE | PO+4W | 2018-10-29 | FI |  | 0
| H-1001 | 0000-FA-006 | PROJECT GENERAL SCHEDULE | PO+6W | 2018-11-12 | FI |  | 0
| H-1001 | 0000-FA-007 | PROJECT PROCUREMENT REPORT | PO+4W | 2018-10-29 | FI |  | 0
| H-1001 | 0000-FA-010 | PROJECT MONTHLY PROGRESS REPORT | PO+3W | 2018-10-22 | FI |  | 0
| H-1001 | 0000-FA-014 | MASTER DOCUMENT LIST | PO+3W | 2018-10-22 | FI |  | 0
| H-1001 | 0000-FA-015 | PROJECT VENDOR LIST | PO+3W | 2018-10-22 | FI |  | 0
| H-1001 | 0000-FC-001 | HEATER - FOUNDATION LOADS | PO+10W | 2018-12-10 | FR |  | 0
| H-1001 | 0000-FC-301 | HEATER - MECHANICAL CALCULATION OF STEEL STRUCTURE | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-FC-302 | HEATER - MECHANICAL CALCULATION OF STACK | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-FC-373 | SECONDARY STRUCTURES | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-FC-410 | COIL PRESSURE PARTS CALCULATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FC-411 | COIL STRESS ANALYSIS CALCULATION | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FC-501 | OUTSIDE CASING TEMPERATURE CALCULATION NOTE | PO+17W | 2019-01-28 | FI |  | 0
| H-1001 | 0000-FC-601 | CAST SUPPORTS | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FC-901 | HEATER - MECHANICAL CALCULATION OF LIFTING DEVICES | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-FD-001 | FOUNDATION LAYOUT | PO+10W | 2018-12-10 | FR |  | 0
| H-1001 | 0000-FD-002 | BASE PLATE DETAILS | PO+10W | 2018-12-10 | FR |  | 0
| H-1001 | 0000-FD-010 | GENERAL ASSEMBLY – GENERAL DATA | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FD-020 | GENERAL ASSEMBLY – ELEVATIONS | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FD-030 | GENERAL ASSEMBLY – PLAN VIEWS | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FD-301 | GENERAL NOTES – STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-310 | RADIANT STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-311 | RADIANT STEEL STRUCTURE - DETAILS | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-312 | RADIANT SHIELD STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-320 | CONVECTION STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-321 | CONVECTION STEEL STRUCTURE - DETAILS | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-322 | HEADER BOXES FOR CONVECTION MODULE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-323 | STACK SUPPORT STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-324 | EXTERNAL STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-340 | FLUE GAS DUCT STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-341 | DAMPERS AND BLADE SHUTTER | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-350 | STACK STEEL STRUCTURE | PO+16W | 2019-01-21 | FI |  | 0
| H-1001 | 0000-FD-360 | HANDRAILS, STAIRWAY AND LADDERS - TYPICAL DETAILS | PO+24W | 2019-03-18 | FI |  | 0
| H-1001 | 0000-FD-361 | GRATING PLATFORMS | PO+24W | 2019-03-18 | FI |  | 0
| H-1001 | 0000-FD-401 | RADIANT COIL | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-402 | CONVECTION COIL - PROCESS | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-403 | CROSS OVER | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-501 | INSULATION - GENERAL ASSEMBLY & DETAIL AND BOM | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-800 | PID - LEGENDS AND SYMBOLS | PO+8W | 2018-11-26 | FR |  | 0
| H-1001 | 0000-FD-801 | PID - HEATER | PO+8W | 2018-11-26 | FR |  | 0
| H-1001 | 0000-FD-803 | PID - FUEL SYSTEM | PO+8W | 2018-11-26 | FR |  | 0
| H-1001 | 0000-FD-804 | PID - UTILITY (INSTRUMENT AIR, SNUFFING STEAM) | PO+8W | 2018-11-26 | FR |  | 0
| H-1001 | 0000-FD-820 | INSTRUMENT LIST | PO+10W | 2018-12-10 | FR |  | 0
| H-1001 | 0000-FD-821 | I/O LIST | PO+10W | 2018-12-10 | FR |  | 0
| H-1001 | 0000-FD-822 | INSTRUMENT & ELECTRICAL CABLE LIST | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FD-823 | CONSUMER LIST | PO+8W | 2018-11-26 | FR |  | 0
| H-1001 | 0000-FD-824 | INSTRUMENT AND ELECTRICAL LAYOUT (WITH JB AND CABLE TRAYS) | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FD-825 | INTERCONNECTION DIAGRAMS | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FD-826 | INSTRUMENTS HOOK UP DRAWINGS | PO+18W | 2019-02-04 | FR |  | 0
| H-1001 | 0000-FD-827 | JUNCTION BOXES WIRING | PO+18W | 2019-02-04 | FR |  | 0
| H-1001 | 0000-FD-828 | LOCAL PANEL LAYOUT | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-829 | INSTRUMENTS, JUNCTION BOXES AND LOCAL PANEL SUPPORTS | PO+20W | 2019-02-18 | FR |  | 0
| H-1001 | 0000-FD-830 | CAUSE & EFFECT CHART | PO+24W | 2019-03-18 | FR |  | 0
| H-1001 | 0000-FD-831 | BASIC LOGIC DIAGRAM AND START-UP SEQUENCE DIAGRAM | PO+24W | 2019-03-18 | FR |  | 0
| H-1001 | 0000-FD-890 | SKIN THERMOCOUPLES | PO+18W | 2019-02-04 | FR |  | 0
| H-1001 | 0000-FJ-001 | DATA SHEET - HEATER | PO+6W | 2018-11-12 | FR |  | 0
| H-1001 | 0000-FJ-201 | DATA SHEET - BURNER | PO+6W | 2018-11-12 | FR |  | 0
| H-1001 | 0000-FJ-801 | FUNCTIONAL ANALYSIS | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-803 | DATA PROCESS - CONTROL VALVE | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-805 | DATA PROCESS - FLOW ELEMENT | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-806 | DATA PROCESS - PRESSURE INSTRUMENT | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-808 | DATA PROCESS - TEMPERATURE INSTRUMENT | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-809 | DATA PROCESS - ANALYSER | PO+16W | 2019-01-21 | FR |  | 0
| H-1001 | 0000-FJ-901 | OPERATING & MAINTENANCE MANUAL | PO+30W | 2019-04-29 | FR |  | 0
| H-1001 | 0000-FN-891 | MATERIAL REQUISITION ‐ SKIN THERMOCOUPLES | PO+8W | 2018-11-26 | FI |  | 0
| H-1001 | 0000-FQ-001 | SCOPE OF INSPECTION HEATER AND EQUIPMENT & APPENDIX | PO+12W | 2018-12-24 | FR |  | 0
| H-1001 | 0000-FQ-002 | QUALITY ASSURANCE PLAN | PO+24W | 2019-03-18 | FR |  | 0
| H-1001 | 0000-FQ-003 | MANUFACTURING DATA BOOK INDEX | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-004 | MANUFACTURING DATA BOOK | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-005 | MECHANICAL DATA BOOK INDEX | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-006 | MECHANICAL DATA BOOK | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-007 | ERECTION DATA BOOK INDEX | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-008 | ERECTION DATA BOOK | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FQ-009 | OPERATING AND MAINTENANCE MANUAL ( INSTALLATION, START-UP AND COMMISSIONING MANUAL ) | PO+72W | 2020-02-17 | FR |  | 0
| H-1001 | 0000-FR-001 | PACKING LIST | PO+30W | 2019-04-29 | FR |  | 0
| H-1001 | 0000-FS-804 | FLAME DETECTOR SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-805 | PNEUMATIC ACTUATOR SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-810 | O2 & COE ANALYSER SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-841 | PRESSURE GAUGE SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-842 | DRAFT GAUGE SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-850 | THERMOWELL & TEMPERATURE ELEMENT SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-851 | SKIN THERMOCOUPLE SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-852 | TEMPERATURE TRANSMITTER SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-860 | INTRUMENT PROTECTION BOX SPECIFICATION | PO+12W | 2018-12-24 | FI |  | 0
| H-1001 | 0000-FS-901 | SPARE PART LISTS | PO+30W | 2019-04-29 | FR |  | 0
| H-1001 | 0000-FS-930 | ERECTION PROCEDURE | PO+56W | 2019-10-28 | FI |  | 0
| H-1001 | 0000-FS-930 | ERECTION DRAWING | PO+56W | 2019-10-28 | FI |  | 0
| H-1001 | 0000-NT-805 | MATERIAL REQUISITION ‐ PNEUMATIC ACTUATOR | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-NT-810 | MATERIAL REQUISITION ‐ O2 & COE ANALYSER | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-NT-842 | MATERIAL REQUISITION ‐ DRAFT GAUGE | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-NT-850 | MATERIAL REQUISITION ‐ THERMOWELL & TEMPERATURE ELEMENT | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-NT-851 | MATERIAL REQUISITION ‐ SKIN THERMOCOUPLE | PO+20W | 2019-02-18 | FI |  | 0
| H-1001 | 0000-NT-852 | MATERIAL REQUISITION ‐ TEMPERATURE TRANSMITTER | PO+20W | 2019-02-18 | FI |  | 0