## Planning avec dates
Coefficient
| Projet Frencky |  | Low
[5 empty] | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
Id | Tâches | Statut | Nombre | NA? | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | X | NA
1 | A1 |  | 1 | NA | bar: 2018-11-01 to 2019-02-01
2 | A2 |  | 2 | bar: 2018-12-01 to 2019-01-01
3 | A3 |  | 3 | bar: 2018-12-01 to 2019-02-01
4 | A4 |  | 1 | NA | bar: 2019-01-01
5 | A5 |  | 4 | bar: 2019-01-01
6 | A6 |  | 5 | bar: 2019-01-01
7 | A7 |  | 1 | bar: 2019-01-01
8 | A8 |  | 2 | bar: 2019-01-01 to 2019-02-01
9 | A9 |  | 3 | bar: 2019-01-01 to 2019-02-01
10 | A10 |  | 1 | bar: 2018-12-01 to 2019-03-01
11 | A11 |  | 4 | bar: 2019-01-01 to 2019-03-01
12 | A12 |  | 5 | bar: 2019-01-01 to 2019-05-01
13 | A13 |  | 1 | bar: 2019-02-01 to 2019-04-01
14 | A14 |  | 2 | bar: 2019-01-01 to 2019-03-01
15 | A15 |  | 3 | bar: 2019-02-01 to 2019-03-01
16 | A16 |  | 1 | bar: 2019-03-01 to 2019-04-01
17 | A17 |  | 4 | bar: 2019-03-01 to 2019-04-01
18 | A18 |  | 5 | bar: 2019-04-01 to 2019-05-01
19 | A19 |  | 1 | bar: 2019-02-01 to 2019-03-01
20 | A20 |  | 2 | bar: 2019-01-01 to 2019-02-01
21 | A21 |  | 3 | bar: 2019-02-01
22 | A22 |  | 1 | bar: 2019-02-01
23 | A23 |  | 4 | bar: 2019-02-01
24 | A24 |  | 5 | bar: 2019-02-01
25 | A25 |  | 1 | bar: 2019-02-01 to 2019-05-01
26 | A26 |  | 2 | bar: 2019-02-01 to 2019-03-01
27 | A27 |  | 3 | bar: 2019-01-01 to 2019-03-01
28 | A28 |  | 1 | bar: 2019-01-01 to 2019-04-01
29 | A29 |  | 4 | bar: 2019-01-01 to 2019-04-01
30 | A30 |  | 5 | bar: 2018-12-01 to 2019-01-01
31 | A31 |  | 1 | bar: 2019-01-01 to 2019-02-01
32 | A32 |  | 2 | bar: 2019-01-01 to 2019-02-01
33 | A33 |  | 3 | bar: 2018-12-01 to 2019-01-01
34 | A34 |  | 1 | bar: 2018-12-01 to 2019-04-01
35 | A35 |  | 4 | bar: 2019-02-01 to 2019-03-01
36 | A36 |  | 5 | bar: 2019-01-01 to 2019-02-01
37 | A37 |  | 1 | bar: 2019-02-01
38 | A38 |  | 2 | NA | bar: 2019-02-01 to 2019-03-01
39 | A39 |  | 1 | bar: 2019-03-01 to 2019-04-01
40 | A40 |  | 2 | bar: 2019-04-01 to 2019-05-01
41 | A41 |  | 4 | NA | bar: 2019-05-01 to 2019-06-01
42 | A42 |  | 5 | bar: 2019-05-01 to 2019-08-01
43 | A43 |  | 3 | bar: 2018-11-01 to 2019-02-01
44 | A44 |  | 1 | bar: 2018-12-01 to 2019-01-01
45 | A45 |  | 4 | bar: 2018-12-01 to 2019-02-01
46 | A46 |  | 5 | bar: 2019-01-01
47 | A47 |  | 1 | bar: 2019-01-01
48 | A48 |  | 2 | bar: 2019-01-01
49 | A49 |  | 3 | bar: 2019-01-01
50 | A50 |  | 1 | bar: 2019-01-01 to 2019-02-01
51 | A51 |  | 4 | bar: 2019-01-01 to 2019-02-01
52 | A52 |  | 5 | bar: 2018-12-01 to 2019-03-01
53 | A53 |  | 1 | bar: 2019-01-01 to 2019-03-01
54 | A54 |  | 2 | bar: 2019-01-01 to 2019-05-01
55 | A55 |  | 3 | bar: 2019-02-01 to 2019-04-01
56 | A56 |  | 1 | bar: 2019-01-01 to 2019-03-01
57 | A57 |  | 4 | NA | bar: 2019-02-01 to 2019-03-01
58 | A58 |  | 5 | bar: 2019-03-01 to 2019-04-01
59 | A59 |  | 1 | bar: 2019-03-01 to 2019-04-01
60 | A60 |  | 2 | NA | bar: 2019-04-01 to 2019-05-01
61 | A61 |  | 3 | bar: 2019-02-01 to 2019-03-01
62 | A62 |  | 1 | NA | bar: 2019-01-01 to 2019-02-01
63 | A63 |  | 4 | bar: 2019-02-01
64 | A64 |  | 5 | bar: 2019-02-01
65 | A65 |  | 1 | bar: 2019-02-01
66 | A66 |  | 2 | bar: 2019-02-01
67 | A67 |  | 1 | bar: 2019-02-01 to 2019-05-01
68 | A68 |  | 2 | bar: 2019-02-01 to 2019-03-01
69 | A69 |  | 4 | bar: 2019-01-01 to 2019-03-01
70 | A70 |  | 5 | NA | bar: 2019-01-01 to 2019-04-01
71 | A71 |  | 3 | bar: 2019-01-01 to 2019-04-01
72 | A72 |  | 1 | bar: 2018-12-01 to 2019-01-01
73 | A73 |  | 4 | bar: 2019-01-01 to 2019-02-01
74 | A74 |  | 5 | bar: 2019-01-01 to 2019-02-01
75 | A75 |  | 1 | NA | bar: 2018-12-01 to 2019-01-01
76 | A76 |  | 2 | bar: 2018-12-01 to 2019-04-01
77 | A77 |  | 3 | bar: 2019-02-01 to 2019-03-01
78 | A78 |  | 1 | NA | bar: 2019-01-01 to 2019-02-01
79 | A79 |  | 4 | NA | bar: 2019-02-01
80 | A80 |  | 5 | bar: 2019-02-01 to 2019-03-01
81 | A81 |  | 1 | bar: 2019-03-01 to 2019-04-01
82 | A82 |  | 2 | bar: 2019-04-01 to 2019-05-01
83 | A83 |  | 3 | bar: 2019-05-01 to 2019-06-01
84 | A84 |  | 1 | bar: 2019-05-01 to 2019-08-01
85 | A85 |  | 4 | bar: 2018-11-01 to 2019-02-01
86 | A86 |  | 5 | bar: 2018-12-01 to 2019-01-01
87 | A87 |  | 1 | NA | bar: 2018-12-01 to 2019-02-01
88 | A88 |  | 2 | NA | bar: 2019-01-01
89 | A89 |  | 3 | NA | bar: 2019-01-01
90 | A90 |  | 1 | bar: 2019-01-01
91 | A91 |  | 4 | bar: 2019-01-01
92 | A92 |  | 5 | bar: 2019-01-01 to 2019-02-01
93 | A93 |  | 1 | bar: 2019-01-01 to 2019-02-01
94 | A94 |  | 2 | bar: 2018-12-01 to 2019-03-01
95 | A95 |  | 1 | bar: 2019-01-01 to 2019-03-01
96 | A96 |  | 2 | bar: 2019-01-01 to 2019-05-01
97 | A97 |  | 4 | bar: 2019-02-01 to 2019-04-01
98 | A98 |  | 5 | bar: 2019-01-01 to 2019-03-01
99 | A99 |  | 2 | NA | bar: 2019-02-01 to 2019-03-01
100 | A100 |  | 1 | bar: 2019-03-01 to 2019-04-01
101 | A101 |  | 2 | bar: 2019-03-01 to 2019-04-01
102 | A102 |  | 4 | bar: 2019-04-01 to 2019-05-01
103 | A103 |  | 5 | bar: 2019-02-01 to 2019-03-01
104 | A104 |  | 3 | bar: 2019-01-01 to 2019-02-01
105 | A105 |  | 1 | NA | bar: 2019-02-01
106 | A106 |  | 4 | bar: 2019-02-01
107 | A107 |  | 5 | bar: 2019-02-01
108 | A108 |  | 1 | bar: 2019-02-01
Masquer
Afficher

## Temps moyens
Tâches concernées | Temps moyen | Coefficients
A1 | 50 | Low | Medium | High
A3 | 25 | 0.75 | 1 | 1.25
A5 | 10
A6 | 15
A12 | 20
A14 | 25
A18 | 33
A19 | 15
A28 | 12
A25 | 20
A23 | 14
A11 | 12
A31 | 13
A30 | 18
A35 | 14
A36 | 15
A38 | 22
A42 | 52
A44 | 41
A46 | 25
A47 | 50
A45 | 24
A51 | 15
A53 | 22
A59 | 31
A52 | 39
A60 | 45
A61 | 18
A89 | 54

## Task_Table1
ID | Name | Outline_Level | Competences | Baseline10_Work | Task | Start_Date | Flag1 | Flag2 | Flag3 | Flag4 | Flag5 | Flag8 | Flag19 | Flag20 | Task_Mode | Predecessors | Milestone | N°_Clarity | Constraint_Type | Type | Flag9 | Duration | Finish_Date
| Projet Frencky | 0 |  | 0h | No | [9 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | bar: Flag1 to Flag20
| A1 | 1 |  | 0h | No | 2018-11-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 120 | 2019-03-01 | bar: Flag1 to Flag20
| A2 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A3 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 90 | 2019-03-01 | bar: Flag1 to Flag20
| A4 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A5 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A6 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A7 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A8 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A9 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A10 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-03-29 | bar: Flag1 to Flag20
| A11 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A12 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | 148 | 2019-05-29 | bar: Flag1 to Flag20
| A13 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-04-29 | bar: Flag1 to Flag20
| A14 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A15 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A16 | 1 |  | 0h | No | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A17 | 1 |  | 0h | Yes | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A18 | 1 |  | 0h | No | 2019-04-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 58 | 2019-05-29 | bar: Flag1 to Flag20
| A19 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A20 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A21 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A22 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A23 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A24 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A25 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 117 | 2019-05-29 | bar: Flag1 to Flag20
| A26 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A27 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A28 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-04-29 | bar: Flag1 to Flag20
| A29 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-04-29 | bar: Flag1 to Flag20
| A30 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A31 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A32 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A33 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A34 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 149 | 2019-04-29 | bar: Flag1 to Flag20
| A35 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A36 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A37 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A38 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A39 | 1 |  | 0h | Yes | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A40 | 1 |  | 0h | Yes | 2019-04-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 58 | 2019-05-29 | bar: Flag1 to Flag20
| A41 | 1 |  | 0h | Yes | 2019-05-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-06-29 | bar: Flag1 to Flag20
| A42 | 1 |  | 0h | Yes | 2019-05-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 120 | 2019-08-29 | bar: Flag1 to Flag20
| A43 | 1 |  | 0h | Yes | 2018-11-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 120 | 2019-03-01 | bar: Flag1 to Flag20
| A44 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | Start No Earlier Than | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A45 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 90 | 2019-03-01 | bar: Flag1 to Flag20
| A46 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A47 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A48 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A49 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A50 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A51 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A52 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-03-29 | bar: Flag1 to Flag20
| A53 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A54 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 148 | 2019-05-29 | bar: Flag1 to Flag20
| A55 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-04-29 | bar: Flag1 to Flag20
| A56 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A57 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A58 | 1 |  | 0h | No | 2019-03-01 | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A59 | 1 |  | 0h | No | 2019-03-01 | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A60 | 1 |  | 0h | No | 2019-04-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 58 | 2019-05-29 | bar: Flag1 to Flag20
| A61 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A62 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A63 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A64 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A65 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A66 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A67 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 117 | 2019-05-29 | bar: Flag1 to Flag20
| A68 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A69 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A70 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-04-29 | bar: Flag1 to Flag20
| A71 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-04-29 | bar: Flag1 to Flag20
| A72 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A73 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A74 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A75 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A76 | 1 |  | 0h | Yes | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 149 | 2019-04-29 | bar: Flag1 to Flag20
| A77 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A78 | 1 |  | 0h | Yes | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A79 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A80 | 1 |  | 0h | Yes | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A81 | 1 |  | 0h | Yes | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A82 | 1 |  | 0h | Yes | 2019-04-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 58 | 2019-05-29 | bar: Flag1 to Flag20
| A83 | 1 |  | 0h | Yes | 2019-05-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-06-29 | bar: Flag1 to Flag20
| A84 | 1 |  | 0h | Yes | 2019-05-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 120 | 2019-08-29 | bar: Flag1 to Flag20
| A85 | 1 |  | 0h | Yes | 2018-11-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 120 | 2019-03-01 | bar: Flag1 to Flag20
| A86 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-01-29 | bar: Flag1 to Flag20
| A87 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 90 | 2019-03-01 | bar: Flag1 to Flag20
| A88 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A89 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A90 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A91 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-01-29 | bar: Flag1 to Flag20
| A92 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A93 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A94 | 1 |  | 0h | No | 2018-12-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 118 | 2019-03-29 | bar: Flag1 to Flag20
| A95 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A96 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 148 | 2019-05-29 | bar: Flag1 to Flag20
| A97 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-04-29 | bar: Flag1 to Flag20
| A98 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 87 | 2019-03-29 | bar: Flag1 to Flag20
| A99 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A100 | 1 |  | 0h | No | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A101 | 1 |  | 0h | No | 2019-03-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-04-29 | bar: Flag1 to Flag20
| A102 | 1 |  | 0h | No | 2019-04-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 58 | 2019-05-29 | bar: Flag1 to Flag20
| A103 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 56 | 2019-03-29 | bar: Flag1 to Flag20
| A104 | 1 |  | 0h | No | 2019-01-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 59 | 2019-03-01 | bar: Flag1 to Flag20
| A105 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A106 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A107 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| A108 | 1 |  | 0h | No | 2019-02-01 | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | 28 | 2019-03-01 | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | Yes |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | No | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20
| 0 | 1 |  | 0h | Yes | #N/A | [8 empty] | Auto Scheduled |  | No |  | As Soon As Possible | Fixed Work | No | #N/A | #N/A | bar: Flag1 to Flag20