## RECHANGES
[21 empty] | 90% |  | 10% | [16 empty] | Q:AOAP1U:AO
| PROGRAMME | [8 empty] | INDUS | [10 empty] | PURCHASE ANALYSIS | [5 empty] | MANUFACTURING PROGRESS |  |  |  | PROGRAMME
| PRODUCT | [8 empty] | PRODUCT | [7 empty] | LDF creation | INDUS | GO/NOGO PURCHASING |  |  |  | GO/NOGO PROD | COMPONENTS SERVITUDE |  |  |  | PROGRESS | Team Leader comments. | SHUTTLE COL |  |  |  | BL | CUSTOMER DELIVERY |  |  |  |  | Commentaires Product Manager | State |  | OTD | [5 empty] | Volume |  | CHARGE
CONCAT | ENTRY DATE | PO TYPE | CUSTOMER | PRODUCT NAME | CUSTOMER ORDER | SAP ORDER | ITEM | QTY | Criticité | CUSTOMER PN | ARTICLE SAP | Indus | N° DP/DA | SN | OF | Launched O/N | Printed O/N | 50% | 50%2 | INDUS PROGRESS | Coverage | Coverage date | FIP (confié) | Coverage progress | Go prod | Task progress | FAI | EASA | State of progress | Team Leader comments. | Fin planifiée prod | Requested shipment | Reforecasted shipment | Real shipment | N° | Requested delivery | Delivery Reforecasted | Real delivery | Collaborated Oui = "OK" | DELIVERY | Comments PM | Shipped="O" Cancelled="C" | Colonne1 | Délai expédition | On Time (Forecasted) | On Time (Contractual) | On time (Production) | Shipping month | Shipping year | Month entry date | Year entry date | Semaine | Mois | Année | LUV | MANUF | CONTRÔLE/TEST | TOTAL | TEMPS PASSÉ MANUF | RAF MANUF | CONSO MATIERE | CA
510891750 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5108917 | NON-SPARES | 50 | 1 | RTN | A9252597000800 | 1STR*01148 | NA | 0 |  | NA | NA | NA | NA | NA | 100% | 100% | 2015-06-16 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-06-16 | 2015-06-16 | Sous-poste | Sous-poste | 2015-06-19 | 2015-06-19 | 2015-06-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2015 | 1 | 2014 | 25 | 6 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
513139920 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 5131399 | NON-SPARES | 20 | 3 | RTN | D9251490100000 | IS0032740S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-06-24 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-06-24 | 2015-06-24 | Sous-poste | Sous-poste | 2015-06-29 | 2015-06-29 | 2015-06-29 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2015 | 1 | 2014 | 26 | 6 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
510891710 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 5108917 | NON-SPARES | 10 | 2 | RTN | A9252236000000 | 1STR*01447 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% |  | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-06-26 | 2015-06-26 | Sous-poste | Sous-poste | 2015-07-01 | 2015-07-01 | 2015-07-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2015 | 1 | 2014 | 26 | 6 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
524408810 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 5244088 | NON-SPARES | 10 | 12 | RTN | S9251594420000 | 1STR*10668 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-07 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-07 | 2015-07-07 | Sous-poste | Sous-poste | 2015-07-10 | 2015-07-10 | 2015-07-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 28 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
524483010 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 5244830 | NON-SPARES | 10 | 11 | RTN | S9251598400000 | 1STR*01599 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-07 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-07 | 2015-07-07 | Sous-poste | Sous-poste | 2015-07-10 | 2015-07-10 | 2015-07-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 28 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
524486610 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 5244866 | NON-SPARES | 10 | 11 | RTN | S9251598400100 | 1STR*01600 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-07 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-07 | 2015-07-07 | Sous-poste | Sous-poste | 2015-07-10 | 2015-07-10 | 2015-07-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 28 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
540869720 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 5408697 | NON-SPARES | 20 | 10 | RTN | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-10 | 2015-07-10 | Sous-poste | Sous-poste | 2015-07-15 | 2015-07-15 | 2015-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 28 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
540869710 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 5408697 | NON-SPARES | 10 | 10 | RTN | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-10 | 2015-07-10 | Sous-poste | Sous-poste | 2015-07-15 | 2015-07-15 | 2015-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 28 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
549931610 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE HAUT-PARLEUR | 5499316 | NON-SPARES | 10 | 3 | RTN | S2521656820000 | 4STR*00771 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-13 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-13 | 2015-07-13 | Sous-poste | Sous-poste | 2015-07-16 | 2015-07-16 | 2015-07-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 29 | 7 | 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0
524387510 | 2014-01-01 | HA/REVENTE | STELIA | PRISE SUP 82 VU | 5243875 | NON-SPARES | 10 | 13 | RTN | S9251596820000 | 1STR*10666 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-15 | 2015-07-15 | Sous-poste | Sous-poste | 2015-07-20 | 2015-07-20 | 2015-07-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 29 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
544228910 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 5442289 | NON-SPARES | 10 | 1 | RTN | D9251490100000 | IS0032740S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-07-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-07-21 | 2015-07-21 | Sous-poste | Sous-poste | 2015-07-24 | 2015-07-24 | 2015-07-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2015 | 1 | 2014 | 30 | 7 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
513873310 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE ASSY 426VU | 5138733 | NON-SPARES | 10 | 5 | RTN | A92524705001D00 | 1STR*11168 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-08-20 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-08-20 | 2015-08-20 | Sous-poste | Sous-poste | 2015-08-25 | 2015-08-25 | 2015-08-25 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2015 | 1 | 2014 | 34 | 8 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
540392910 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5403929 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-08-27 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-08-27 | 2015-08-27 | Sous-poste | Sous-poste | 2015-09-01 | 2015-09-01 | 2015-09-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2015 | 1 | 2014 | 35 | 8 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
522203510 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5222035 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-09-02 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-09-02 | 2015-09-02 | Sous-poste | Sous-poste | 2015-09-07 | 2015-09-07 | 2015-09-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 36 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
548753110 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPORT ASSY | 5487531 | NON-SPARES | 10 | 2 | RTN | F9241259500000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-09-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-09-15 | 2015-09-15 | Sous-poste | Sous-poste | 2015-09-18 | 2015-09-18 | 2015-09-18 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 38 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
510891740 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5108917 | NON-SPARES | 40 | 2 | RTN | A9252597000900 | 1STR*01482 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-09-16 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-09-16 | 2015-09-16 | Sous-poste | Sous-poste | 2015-09-21 | 2015-09-21 | 2015-09-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 38 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
565336110 | 2014-01-01 |  | TBD |  | 5653361 | NON-SPARES | 10 | 1 | RTN | A9253010627300 | 39VU CONTROL PANEL ASSY | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-09-21 | 2015-09-21 | Sous-poste | Sous-poste | 2015-09-24 | 2015-09-24 | 2015-09-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 39 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
565336110 | 2014-01-01 |  | TBD |  | 5653361 | NON-SPARES | 10 | 1 | RTN | A9253010627300 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-09-23 | 2015-09-23 | Sous-poste | Sous-poste | 2015-09-28 | 2015-09-28 | 2015-09-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 39 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
548691610 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 5486916 | NON-SPARES | 10 | 1 | RTN | S9251363300100 | IS0054056S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-09-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-09-25 | 2015-09-25 | Sous-poste | Sous-poste | 2015-09-30 | 2015-09-30 | 2015-09-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 39 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
543820610 | 2014-01-01 |  | TBD |  | 5438206 | NON-SPARES | 10 | 3 | RTN | A9253229400100 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-09-30 | 2015-09-30 | Sous-poste | Sous-poste | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 40 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
543820620 | 2014-01-01 |  | TBD |  | 5438206 | NON-SPARES | 20 | 3 | RTN | A9253229400000 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-09-30 | 2015-09-30 | Sous-poste | Sous-poste | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2015 | 1 | 2014 | 40 | 9 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
550481710 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE HAUT-PARLEUR | 5504817 | NON-SPARES | 10 | 2 | RTN | S2521656820000 | 4STR*00771 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-10-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-10-01 | 2015-10-01 | Sous-poste | Sous-poste | 2015-10-06 | 2015-10-06 | 2015-10-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 40 | 10 | 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490002725510 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE HAUT-PARLEUR | 4900027255 | NON-SPARES | 10 | 14 | RTN | S2521656820000 | 4STR*00771 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-10-14 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-10-14 | 2015-10-14 | Sous-poste | Sous-poste | 2015-10-19 | 2015-10-19 | 2015-10-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 42 | 10 | 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490002725520 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 4900027255 | NON-SPARES | 20 | 1 | RTN | S9251363300100 | IS0054056S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-10-16 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-10-16 | 2015-10-16 | Sous-poste | Sous-poste | 2015-10-21 | 2015-10-21 | 2015-10-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 42 | 10 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
568955310 | 2014-01-01 |  | TBD |  | 5689553 | NON-SPARES | 10 | 2 | RTN | A9253010627300 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-10-16 | 2015-10-16 | Sous-poste | Sous-poste | 2015-10-21 | 2015-10-21 | 2015-10-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 42 | 10 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
566367710 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 5663677 | NON-SPARES | 10 | 2 | RTN | D9251490100000 | IS0032740S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-10-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-10-19 | 2015-10-19 | Sous-poste | Sous-poste | 2015-10-22 | 2015-10-22 | 2015-10-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 43 | 10 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
532548210 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5325482 | NON-SPARES | 10 | 3 | RTN | A9252597000900 | 1STR*01482 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-10-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-10-21 | 2015-10-21 | Sous-poste | Sous-poste | 2015-10-26 | 2015-10-26 | 2015-10-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2015 | 1 | 2014 | 43 | 10 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002725530 | 2014-01-01 | HA/REVENTE | STELIA | PLAQUE | 4900027255 | NON-SPARES | 30 | 4 | RTN | S9251450300000 | 1QME*00169 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-04 | 2015-11-04 | Sous-poste | Sous-poste | 2015-11-09 | 2015-11-09 | 2015-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 45 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002748910 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU DE FERMETURE ÉQUIPÉ | 4900027489 | NON-SPARES | 10 | 1 | RTN | S9251451700100 | 1STR*01133 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-11 | 2015-11-11 | Sous-poste | Sous-poste | 2015-11-16 | 2015-11-16 | 2015-11-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 46 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002731410 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 4900027314 | NON-SPARES | 10 | 3 | RTN | S9251363300100 | IS0054056S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-18 | 2015-11-18 | Sous-poste | Sous-poste | 2015-11-23 | 2015-11-23 | 2015-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 47 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
591525810 | 2014-01-01 |  | TBD |  | 5915258 | NON-SPARES | 10 | 1 | RTN | A9252250401500 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2015-11-24 | 2015-11-24 | Sous-poste | Sous-poste | 2015-11-27 | 2015-11-27 | 2015-11-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 48 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002747020 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900027470 | NON-SPARES | 20 | 10 | RTN | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-25 | 2015-11-25 | Sous-poste | Sous-poste | 2015-11-30 | 2015-11-30 | 2015-11-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 48 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002747010 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900027470 | NON-SPARES | 10 | 10 | RTN | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-25 | 2015-11-25 | Sous-poste | Sous-poste | 2015-11-30 | 2015-11-30 | 2015-11-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 48 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
588733510 | 2014-01-01 | HA/REVENTE | SATAIR | PIECE COUDÉE | 5887335 | NON-SPARES | 10 | 1 | RTN | F9251423500000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-26 | 2015-11-26 | Sous-poste | Sous-poste | 2015-12-01 | 2015-12-01 | 2015-12-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 48 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
588734410 | 2014-01-01 | HA/REVENTE | SATAIR | 0 | 5887344 | NON-SPARES | 10 | 1 | RTN | F9251423320000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-11-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-11-26 | 2015-11-26 | Sous-poste | Sous-poste | 2015-12-01 | 2015-12-01 | 2015-12-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2015 | 1 | 2014 | 48 | 11 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
590509210 | 2014-01-01 | HA/REVENTE | SATAIR | ENS TOLE LATERALE INF G | 5905092 | NON-SPARES | 10 | 5 | RTN | A9252882500400 | 3STR*01342 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-12-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-12-18 | 2015-12-18 | Sous-poste | Sous-poste | 2015-12-23 | 2015-12-23 | 2015-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2015 | 1 | 2014 | 51 | 12 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
591097610 | 2014-01-01 | HA/REVENTE | SATAIR | ENS TOLE LATERALE INF G | 5910976 | NON-SPARES | 10 | 10 | RTN | A9252882500400 | 3STR*01342 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-12-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-12-18 | 2015-12-18 | Sous-poste | Sous-poste | 2015-12-23 | 2015-12-23 | 2015-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2015 | 1 | 2014 | 51 | 12 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
590566210 | 2014-01-01 | HA/REVENTE | SATAIR | ENS TOLE LATERALE INF G | 5905662 | NON-SPARES | 10 | 1 | RTN | A9252882500400 | 3STR*01342 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-12-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-12-18 | 2015-12-18 | Sous-poste | Sous-poste | 2015-12-23 | 2015-12-23 | 2015-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2015 | 1 | 2014 | 51 | 12 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002771610 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900027716 | NON-SPARES | 10 | 1 | RTN | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-12-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-12-18 | 2015-12-18 | Sous-poste | Sous-poste | 2015-12-23 | 2015-12-23 | 2015-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2015 | 1 | 2014 | 51 | 12 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002771620 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900027716 | NON-SPARES | 20 | 1 | RTN | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2015-12-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2015-12-18 | 2015-12-18 | Sous-poste | Sous-poste | 2015-12-23 | 2015-12-23 | 2015-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2015 | 1 | 2014 | 51 | 12 | 2015 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002740710 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE HAUT-PARLEUR | 4900027407 | NON-SPARES | 10 | 6 |  | S2521656820000 | 4STR*00771 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-04 | 2016-01-04 | Sous-poste | Sous-poste | 2016-01-07 | 2016-01-07 | 2016-01-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 2 | 1 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490002756510 | 2014-01-01 | HA/REVENTE | STELIA | VIS 114VU | 4900027565 | NON-SPARES | 10 | 18 |  | S9251112620000 | 3STR*00810 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-04 | 2016-01-04 | Sous-poste | Sous-poste | 2016-01-07 | 2016-01-07 | 2016-01-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 2 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
60666812B |  | FABRICATION | SATAIR | PLATE | 6066681 | NON-SPARES | 2B | 1 | EXP | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #DIV/0! | #N/A | #N/A | NA | NA | NA |  |  | 2016-01-15 | 2016-01-15 | Sous-poste | Sous-poste | 2016-01-20 | 2016-01-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 1900 | 3 | 1 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
490002758610 | 2014-01-01 | HA/REVENTE | STELIA | Colonette | 4900027586 | NON-SPARES | 10 | 6 |  | S9251130520900 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-18 | 2016-01-18 | Sous-poste | Sous-poste | 2016-01-21 | 2016-01-21 | 2016-01-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 4 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002758620 | 2014-01-01 | HA/REVENTE | STELIA | Colonette | 4900027586 | NON-SPARES | 20 | 6 |  | S9251130521300 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-18 | 2016-01-18 | Sous-poste | Sous-poste | 2016-01-21 | 2016-01-21 | 2016-01-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 4 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002758630 | 2014-01-01 | HA/REVENTE | STELIA | Colonette | 4900027586 | NON-SPARES | 30 | 6 |  | S9251130521400 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-18 | 2016-01-18 | Sous-poste | Sous-poste | 2016-01-21 | 2016-01-21 | 2016-01-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 4 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
543615710 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5436157 | NON-SPARES | 10 | 1 |  | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-18 | 2016-01-18 | Sous-poste | Sous-poste | 2016-01-21 | 2016-01-21 | 2016-01-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 4 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002766310 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU DE FERMETURE 120VU | 4900027663 | NON-SPARES | 10 | 1 |  | S9251324700400 | 1STR*01147 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-22 | 2016-01-22 | Sous-poste | Sous-poste | 2016-01-27 | 2016-01-27 | 2016-01-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 4 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
609535710 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 6095357 | NON-SPARES | 10 | 1 | AOG | F9251110720000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-25 | 2016-01-25 | Sous-poste | Sous-poste | 2016-01-27 | 2016-01-27 | 2016-01-27 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 5 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002764310 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900027643 | NON-SPARES | 10 | 12 |  | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-29 | 2016-01-29 | Sous-poste | Sous-poste | 2016-02-03 | 2016-02-03 | 2016-02-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 5 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490002764320 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900027643 | NON-SPARES | 20 | 12 |  | S9252333600000 | 1STR*10937 | NA | K. FORFERT | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-01-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-01-29 | 2016-01-29 | Sous-poste | Sous-poste | 2016-02-03 | 2016-02-03 | 2016-02-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2016 | 1 | 2014 | 5 | 1 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
590582110 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 5905821 | NON-SPARES | 10 | 2 |  | D9251490100000 | IS0032740S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-02-05 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-02-05 | 2016-02-05 | Sous-poste | Sous-poste | 2016-02-10 | 2016-02-10 | 2016-02-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 2014 | 6 | 2 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
557609710 |  | FABRICATION | SATAIR | PLATE | 5576097 | NON-SPARES | 10 | 6 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-02-08 | 2016-02-08 | Sous-poste | Sous-poste | 2016-02-11 | 2016-02-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 1900 | 7 | 2 | 2016 | 0 | 18.8232 | 0.72 | 19.5432 | NA | 0 | 0
611981410 | 0 | FABRICATION | SATAIR | 412 | 6119814 | NON-SPARES | 10 | 1 | RTN | A9550041272695 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #DIV/0! | #N/A | #N/A | NA | NA | NA |  |  | 2016-02-24 | 2016-02-18 | Sous-poste | Sous-poste | 2016-02-29 | 2016-02-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2016 | 0 | 0 | 0 | 0 | LAB | 0 | 0
612066210 | 0 | FABRICATION | SATAIR | 412 | 6120662 | NON-SPARES | 10 | 1 | RTN | A9550041272695 | 0 | NON PRESENT INDUS | 52544 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-02-23 | 100% | NA | NA | 5.556% |  |  | 2016-02-24 | 2016-02-18 | Sous-poste | Sous-poste | 2016-02-29 | 2016-02-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2016 | 0 | 0 | 0 | 0 | LAB | 0 | 0
650014791810 | 2014-01-01 | HA/REVENTE | SATAIR | TÔLE EQUIPÉE APM | 6500147918 | NON-SPARES | 10 | 1 |  | F9252018800000 | 1STR*10493 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-02-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-02-19 | 2016-02-19 | Sous-poste | Sous-poste | 2016-02-24 | 2016-02-24 | 2016-02-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 2014 | 8 | 2 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
569920210 |  | FABRICATION | SATAIR | PLATE | 5699202 | NON-SPARES | 10 | 35 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-02-24 | 2016-02-24 | Sous-poste | Sous-poste | 2016-02-29 | 2016-02-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 1900 | 9 | 2 | 2016 | 0 | 109.802 | 0.72 | 110.522 | NA | 0 | 0
566386610 |  | FABRICATION | SATAIR | PLATE | 5663866 | NON-SPARES | 10 | 106 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-02-24 | 2016-02-24 | Sous-poste | Sous-poste | 2016-02-29 | 2016-02-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 1900 | 9 | 2 | 2016 | 0 | 332.5432 | 0.72 | 333.2632 | NA | 0 | 0
530947310 | 2014-01-01 | HA/REVENTE | SATAIR | PIECE COUDÉE | 5309473 | NON-SPARES | 10 | 1 |  | F9251423500000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-02-24 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-02-24 | 2016-02-24 | Sous-poste | Sous-poste | 2016-02-29 | 2016-02-29 | 2016-02-29 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 2014 | 9 | 2 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
575653810 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5756538 | NON-SPARES | 10 | 1 |  | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-02-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-02-25 | 2016-02-25 | Sous-poste | Sous-poste | 2016-03-01 | 2016-03-01 | 2016-03-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 2014 | 9 | 2 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
611229610 | 2014-01-01 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 6112296 | NON-SPARES | 10 | 2 |  | F9251367800000 | 1STR*10672 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-02-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-02-26 | 2016-02-26 | Sous-poste | Sous-poste | 2016-03-02 | 2016-03-02 | 2016-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2016 | 1 | 2014 | 9 | 2 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
618091410 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 6180914 | NON-SPARES | 10 | 1 |  | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-02 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-02 | 2016-03-02 | Sous-poste | Sous-poste | 2016-03-07 | 2016-03-07 | 2016-03-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 10 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
581545810 | 2014-01-01 | HA/REVENTE | SATAIR | PLATINE 807VU | 5815458 | NON-SPARES | 10 | 1 | AOG | F0041428900000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-03 | 2016-03-03 | Sous-poste | Sous-poste | 2016-03-07 | 2016-03-07 | 2016-03-07 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 10 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
55749382B | 0 | FABRICATION | SATAIR | 510 | 5574938 | NON-SPARES | 2B | 3 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #DIV/0! | #N/A | #N/A | NA | NA | NA |  |  | 2016-03-09 | 2016-03-03 | Sous-poste | Sous-poste | 2016-03-13 | 2016-03-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2016 | 0 | 10.6551 | 0.88793 | 11.543 | COL | 0 | 0
5546416 620289510 | 0 | FABRICATION | SATAIR | 510 | 5546416 6202895 | NON-SPARES | 10 | 2 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 50772 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-03-08 | 100% | NA | NA | 5.556% |  |  | 2016-03-09 | 2016-03-03 | Sous-poste | Sous-poste | 2016-03-14 | 2016-03-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2016 | 0 | 7.1034 | 0.88793 | 7.9913 | COL | 0 | 0
5700157 620292310 | 0 | FABRICATION | SATAIR | 510 | 5700157 6202923 | NON-SPARES | 10 | 2 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 50772 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-03-08 | 100% | NA | NA | 5.556% |  |  | 2016-03-09 | 2016-03-03 | Sous-poste | Sous-poste | 2016-03-14 | 2016-03-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2016 | 0 | 7.1034 | 0.88793 | 7.9913 | COL | 0 | 0
490002831610 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900028316 | NON-SPARES | 10 | 5 |  | S9251303120000 | 1QEL*00029 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-04 | 2016-03-04 | Sous-poste | Sous-poste | 2016-03-09 | 2016-03-09 | 2016-03-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 10 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
569435510 | 0 | FABRICATION | SATAIR | 510 | 5694355 | NON-SPARES | 10 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 50772 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-03-15 | 100% | NA | NA | 5.556% |  |  | 2016-03-16 | 2016-03-10 | Sous-poste | Sous-poste | 2016-03-19 | 2016-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 11 | 3 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
540393110 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 5403931 | NON-SPARES | 10 | 0 | RTN | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-16 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-16 | 2016-03-16 | Sous-poste | Sous-poste | 2016-03-21 | 2016-03-21 | 2016-03-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 12 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
611832710 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 6118327 | NON-SPARES | 10 | 2 |  | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-16 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-16 | 2016-03-16 | Sous-poste | Sous-poste | 2016-03-21 | 2016-03-21 | 2016-03-21 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 12 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
590936310 |  | FABRICATION | SATAIR | PLATE | 5909363 | NON-SPARES | 10 | 68 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #DIV/0! | #N/A | #N/A | NA | NA | NA |  |  | 2016-03-22 | 2016-03-22 | Sous-poste | Sous-poste | 2016-03-25 | 2016-03-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 1900 | 13 | 3 | 2016 | 0 | 213.3296 | 0.72 | 214.0496 | NA | 0 | 0
4902138 620292910 | 0 | FABRICATION | SATAIR | 510 | 4902138 6202929 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-03-29 | 2016-03-23 | Sous-poste | Sous-poste | 2016-04-01 | 2016-03-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 13 | 3 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
570551410 |  | FABRICATION | SATAIR | PLATE | 5705514 | NON-SPARES | 10 | 136 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-03-24 | 2016-03-24 | Sous-poste | Sous-poste | 2016-03-29 | 2016-03-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 1900 | 13 | 3 | 2016 | 0 | 426.6592 | 0.72 | 427.3792 | NA | 0 | 0
604447610 |  | FABRICATION | SATAIR | PLATE | 6044476 | NON-SPARES | 10 | 12 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-03-24 | 2016-03-24 | Sous-poste | Sous-poste | 2016-03-29 | 2016-03-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 1900 | 13 | 3 | 2016 | 0 | 37.6464 | 0.72 | 38.3664 | NA | 0 | 0
5546441 620290410 | 0 | FABRICATION | SATAIR | 510 | 5546441 6202904 | NON-SPARES | 10 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 50772 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-04-05 | 100% | NA | NA | 5.556% |  |  | 2016-04-06 | 2016-03-31 | Sous-poste | Sous-poste | 2016-04-11 | 2016-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 14 | 3 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
563253510 | 0 | FABRICATION | SATAIR | 510 | 5632535 | NON-SPARES | 10 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 50772 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2016-04-05 | 100% | NA | NA | 5.556% |  |  | 2016-04-06 | 2016-03-31 | Sous-poste | Sous-poste | 2016-04-11 | 2016-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 14 | 3 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
490002872110 | 2014-01-01 | HA/REVENTE | STELIA | GOUJON | 4900028721 | NON-SPARES | 10 | 15 |  | S9251304020200 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-03-31 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-03-31 | 2016-03-31 | Sous-poste | Sous-poste | 2016-04-05 | 2016-04-05 | 2016-04-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2016 | 1 | 2014 | 14 | 3 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
6138363180 | 0 | FABRICATION | SATAIR | 510 | 6138363 | NON-SPARES | 180 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-04-15 | 2016-04-11 | Sous-poste | Sous-poste | 2016-04-20 | 2016-04-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
571339310 |  | FABRICATION | SATAIR | PLATE | 5713393 | NON-SPARES | 10 | 22 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-12 | 2016-04-12 | Sous-poste | Sous-poste | 2016-04-15 | 2016-04-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 69.0184 | 0.72 | 69.7384 | NA | 0 | 0
6076347ABS0951B3LP029 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | ABS0951B3LP029 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 4 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 12.5488 | 0.72 | 13.2688 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 2 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 2 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
607634770 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 70 | 3 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 9.4116 | 0.72 | 10.1316 | NA | 0 | 0
607634780 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 80 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
607634790 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 90 | 7 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 21.9604 | 0.72 | 22.6804 | NA | 0 | 0
6076347110 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 110 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
6076347120 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 120 | 7 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 21.9604 | 0.72 | 22.6804 | NA | 0 | 0
6076347140 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 140 | 9 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% |  | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 28.2348 | 0.72 | 28.9548 | NA | 0 | 0
6076347150 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 150 | 6 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 18.8232 | 0.72 | 19.5432 | NA | 0 | 0
6076347160 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 160 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% |  | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
6076347170 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 170 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-04-13 | 2016-04-13 | Sous-poste | Sous-poste | 2016-04-18 | 2016-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 1900 | 16 | 4 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
5940361190 | 0 | FABRICATION | SATAIR | 510 | 5940361 | NON-SPARES | 190 | 7 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-04-21 | 2016-04-15 | Sous-poste | Sous-poste | 2016-04-26 | 2016-04-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2016 | 0 | 24.8619 | 0.88793 | 25.7498 | COL | 0 | 0
2704958710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27049587 | NON-SPARES | 10 | 4 |  | D9251101900000 | 1STR*11007 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-04-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-04-25 | 2016-04-25 | Sous-poste | Sous-poste | 2016-04-28 | 2016-04-28 | 2016-04-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2016 | 1 | 2014 | 18 | 4 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
601008960 | 0 | FABRICATION | SATAIR | 510 | 6010089 | NON-SPARES | 60 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-05-13 | 2016-05-09 | Sous-poste | Sous-poste | 2016-05-18 | 2016-05-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 20 | 5 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
6010113100 | 0 | FABRICATION | SATAIR | 510 | 6010113 | NON-SPARES | 100 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-05-13 | 2016-05-09 | Sous-poste | Sous-poste | 2016-05-18 | 2016-05-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 20 | 5 | 2016 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
6076347210 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 210 | 12 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 37.6464 | 0.72 | 38.3664 | NA | 0 | 0
6076347220 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 220 | 10 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 31.372 | 0.72 | 32.092 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 9 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 28.2348 | 0.72 | 28.9548 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 5 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 15.686 | 0.72 | 16.406 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 10 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 31.372 | 0.72 | 32.092 | NA | 0 | 0
607634750 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 50 | 10 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-05-11 | 2016-05-11 | Sous-poste | Sous-poste | 2016-05-16 | 2016-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 1900 | 20 | 5 | 2016 | 0 | 31.372 | 0.72 | 32.092 | NA | 0 | 0
490002855610 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900028556 | NON-SPARES | 10 | 2 |  | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-05-12 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-05-12 | 2016-05-12 | Sous-poste | Sous-poste | 2016-05-17 | 2016-05-17 | 2016-05-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2016 | 1 | 2014 | 20 | 5 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
27094261230 | 0 | FABRICATION | SATAIR | 108 | 27094261 | NON-SPARES | 230 | 1 | CRIT | D9550010801295 | IS0032586M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-05-23 | 2016-05-19 | Sous-poste | Sous-poste | 2016-05-25 | 2016-05-23 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 21 | 5 | 2016 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
490002869710 | 2014-01-01 |  | TBD |  | 4900028697 | NON-SPARES | 10 | 2 |  | S9251363300100 |  | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 100% | 2016-06-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-01 | 2016-06-01 | Sous-poste | Sous-poste | 2016-06-06 | 2016-06-06 | 2016-06-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 23 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2710536210 | 2014-01-01 | HA/REVENTE | SATAIR | ENS TOLE LATERALE INF G | 27105362 | NON-SPARES | 10 | 10 |  | A9252882500400 | 3STR*01342 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-07 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-07 | 2016-06-07 | Sous-poste | Sous-poste | 2016-06-10 | 2016-06-10 | 2016-06-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 24 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
6076347240 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 240 | 3 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% |  | 100% | NA | NA | 5.556% |  |  | 2016-06-08 | 2016-06-08 | Sous-poste | Sous-poste | 2016-06-13 | 2016-06-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 24 | 6 | 2016 | 0 | 9.4116 | 0.72 | 10.1316 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 12 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-06-08 | 2016-06-08 | Sous-poste | Sous-poste | 2016-06-13 | 2016-06-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 24 | 6 | 2016 | 0 | 37.6464 | 0.72 | 38.3664 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-06-08 | 2016-06-08 | Sous-poste | Sous-poste | 2016-06-13 | 2016-06-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 24 | 6 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
607634710 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 10 | 6 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-06-08 | 2016-06-08 | Sous-poste | Sous-poste | 2016-06-13 | 2016-06-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 24 | 6 | 2016 | 0 | 18.8232 | 0.72 | 19.5432 | NA | 0 | 0
607634720 |  | FABRICATION | SATAIR | PLATE | 6076347 | NON-SPARES | 20 | 1 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2016-06-08 | 2016-06-08 | Sous-poste | Sous-poste | 2016-06-13 | 2016-06-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 24 | 6 | 2016 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
490003011410 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AVANT 110VU | 4900030114 | NON-SPARES | 10 | 1 |  | S9251038100100 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-10 | 2016-06-10 | Sous-poste | Sous-poste | 2016-06-15 | 2016-06-15 | 2016-06-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 24 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003001610 | 2014-01-01 | HA/REVENTE | STELIA | DIAPHRAGME | 4900030016 | NON-SPARES | 10 | 1 |  | S9251019520700 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-21 | 2016-06-21 | Sous-poste | Sous-poste | 2016-06-24 | 2016-06-24 | 2016-06-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 26 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003018510 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU DE FERMETURE 120VU | 4900030185 | NON-SPARES | 10 | 1 | CRIT | S9251324700400 | 1STR*01147 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-27 | 2016-06-27 | Sous-poste | Sous-poste | 2016-06-29 | 2016-06-29 | 2016-06-29 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2704091910 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27040919 | NON-SPARES | 10 | 1 |  | A9252236000000 | 1STR*01447 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-29 | 2016-06-29 | Sous-poste | Sous-poste | 2016-07-03 | 2016-07-03 | 2016-07-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2704092010 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27040920 | NON-SPARES | 10 | 1 |  | A9253115800000 | IS0031675S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-29 | 2016-06-29 | Sous-poste | Sous-poste | 2016-07-03 | 2016-07-03 | 2016-07-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003032610 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900030326 | NON-SPARES | 10 | 2 |  | S0003027000000 | 1STR*01261 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-29 | 2016-06-29 | Sous-poste | Sous-poste | 2016-07-04 | 2016-07-04 | 2016-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2709934910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27099349 | NON-SPARES | 10 | 1 |  | F9251110800500 | 1STR*00297 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-29 | 2016-06-29 | Sous-poste | Sous-poste | 2016-07-04 | 2016-07-04 | 2016-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2709935110 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27099351 | NON-SPARES | 10 | 2 |  | F9251445920000 | 1STR*01520 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-06-29 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-06-29 | 2016-06-29 | Sous-poste | Sous-poste | 2016-07-04 | 2016-07-04 | 2016-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 2014 | 27 | 6 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
605283630 |  | FABRICATION | SATAIR | PLATE | 6052836 | NON-SPARES | 30 | 3 |  | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-06-30 | 2016-06-30 | Sous-poste | Sous-poste | 2016-07-05 | 2016-07-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2016 | 1 | 1900 | 27 | 6 | 2016 | 0 | 9.4116 | 0.72 | 10.1316 | NA | 0 | 0
490003028810 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900030288 | NON-SPARES | 10 | 11 |  | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-06 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-06 | 2016-07-06 | Sous-poste | Sous-poste | 2016-07-11 | 2016-07-11 | 2016-07-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 28 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003034310 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900030343 | NON-SPARES | 10 | 2 |  | S0003027000000 | 1STR*01261 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-13 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-13 | 2016-07-13 | Sous-poste | Sous-poste | 2016-07-18 | 2016-07-18 | 2016-07-18 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 29 | 7 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2712179210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE-BLANKING | 27121792 | NON-SPARES | 10 | 9 |  | A9252842100000 | 1QME*00162 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-20 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-20 | 2016-07-20 | Sous-poste | Sous-poste | 2016-07-25 | 2016-07-25 | 2016-07-25 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 30 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2709935710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27099357 | NON-SPARES | 10 | 1 |  | F9251485300000 | 1STR*01521 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-22 | 2016-07-22 | Sous-poste | Sous-poste | 2016-07-27 | 2016-07-27 | 2016-07-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 30 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003047810 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AV 23VU | 4900030478 | NON-SPARES | 10 | 1 |  | S9251165200000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-25 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-25 | 2016-07-25 | Sous-poste | Sous-poste | 2016-07-28 | 2016-07-28 | 2016-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 31 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2711973710 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27119737 | NON-SPARES | 10 | 0 |  | F9251110800300 | 1STR*10653 | NA | 805 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-27 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-27 | 2016-07-27 | Sous-poste | Sous-poste | 2016-07-30 | 2016-07-30 | 2016-07-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 31 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003018410 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 4900030184 | NON-SPARES | 10 | 3 |  | S9251363300100 | IS0054056S | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-27 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-27 | 2016-07-27 | Sous-poste | Sous-poste | 2016-08-01 | 2016-08-01 | 2016-08-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 31 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003050110 | 2014-01-01 | HA/REVENTE | STELIA | STRUCTURE 27VU | 4900030501 | NON-SPARES | 10 | 1 |  | S9252347900000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-07-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-07-28 | 2016-07-28 | Sous-poste | Sous-poste | 2016-08-02 | 2016-08-02 | 2016-08-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2016 | 1 | 2014 | 31 | 7 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003045810 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900030458 | NON-SPARES | 10 | 4 |  | S0003027000000 | 1STR*01261 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-09 | 2016-08-09 | Sous-poste | Sous-poste | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 33 | 8 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2712098310 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27120983 | NON-SPARES | 10 | 1 |  | F9251110800500 | 1STR*00297 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-09 | 2016-08-09 | Sous-poste | Sous-poste | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 33 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2712098410 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27120984 | NON-SPARES | 10 | 2 |  | F9251445920000 | 1STR*01520 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-09 | 2016-08-09 | Sous-poste | Sous-poste | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 33 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2712098510 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27120985 | NON-SPARES | 10 | 1 |  | F9251485300000 | 1STR*01521 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-09 | 2016-08-09 | Sous-poste | Sous-poste | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 33 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003050510 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900030505 | NON-SPARES | 10 | 2 |  | S0003027000000 | 1STR*01261 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-19 | 2016-08-19 | Sous-poste | Sous-poste | 2016-08-24 | 2016-08-24 | 2016-08-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 34 | 8 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003026910 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900030269 | NON-SPARES | 10 | 11 |  | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-24 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-24 | 2016-08-24 | Sous-poste | Sous-poste | 2016-08-29 | 2016-08-29 | 2016-08-29 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 35 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003019410 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900030194 | NON-SPARES | 10 | 1 | CRIT | S9251107820000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-25 | 2016-08-25 | Sous-poste | Sous-poste | 2016-08-29 | 2016-08-29 | 2016-08-29 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 35 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003035210 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900030352 | NON-SPARES | 10 | 11 |  | S9252333700000 | 1STR*10936 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-08-31 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-08-31 | 2016-08-31 | Sous-poste | Sous-poste | 2016-09-05 | 2016-09-05 | 2016-09-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2016 | 1 | 2014 | 36 | 8 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
695630410 | 2014-01-01 | HA/REVENTE | SATAIR | PLATEAU ASPIRANT | 6956304 | NON-SPARES | 10 | 1 |  | D9251041101400 | 1STR*00135 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-06 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-06 | 2016-09-06 | Sous-poste | Sous-poste | 2016-09-09 | 2016-09-09 | 2016-09-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 37 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003044310 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900030443 | NON-SPARES | 10 | 6 |  | S9252333600000 | 1STR*10937 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-07 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-07 | 2016-09-07 | Sous-poste | Sous-poste | 2016-09-12 | 2016-09-12 | 2016-09-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 37 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2716525010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27165250 | NON-SPARES | 10 | 2 |  | F9251110800600 | 1STR*10659 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-14 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-14 | 2016-09-14 | Sous-poste | Sous-poste | 2016-09-19 | 2016-09-19 | 2016-09-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 38 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003048110 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900030481 | NON-SPARES | 10 | 16 |  | S9252333600000 | 1STR*10937 | NA | 1000 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-14 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-14 | 2016-09-14 | Sous-poste | Sous-poste | 2016-09-19 | 2016-09-19 | 2016-09-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 38 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003048240 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 91VU | 4900030482 | NON-SPARES | 40 | 11 |  | S9252333700000 | 1STR*10936 | NA | 1000 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-14 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-14 | 2016-09-14 | Sous-poste | Sous-poste | 2016-09-19 | 2016-09-19 | 2016-09-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 38 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718541910 | 2014-01-01 | HA/REVENTE | SATAIR | PANEL-ASSY | 27185419 | NON-SPARES | 10 | 2 | RTN | D9251626900100 | 0 | NA | 841 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-09-30 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-09-30 | 2016-09-30 | Sous-poste | Sous-poste | 2016-10-05 | 2016-10-05 | 2016-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2016 | 1 | 2014 | 40 | 9 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003023810 | 2014-01-01 | HA/REVENTE | STELIA | ENS.MECANIQUE ECLAIRAGE | 4900030238 | NON-SPARES | 10 | 1 |  | S9241304100000 | 0 | NA | 714 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-05 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-05 | 2016-10-05 | Sous-poste | Sous-poste | 2016-10-10 | 2016-10-10 | 2016-10-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 41 | 10 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2717619110 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27176191 | NON-SPARES | 10 | 50 | EXP | D9251101900000 | 1STR*11007 | NA | 1457 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-17 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-17 | 2016-10-17 | Sous-poste | Sous-poste | 2016-10-20 | 2016-10-20 | 2016-10-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718189310 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27181893 | NON-SPARES | 10 | 3 |  | V9251111522400 | 1STR*10662 | NA | 1841 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-19 | 2016-10-19 | Sous-poste | Sous-poste | 2016-10-23 | 2016-10-23 | 2016-10-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2718190210 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27181902 | NON-SPARES | 10 | 6 |  | V9251111521200 | 1STR*10663 | NA | 1841 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-19 | 2016-10-19 | Sous-poste | Sous-poste | 2016-10-23 | 2016-10-23 | 2016-10-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003062310 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE LISEUSE | 4900030623 | NON-SPARES | 10 | 10 |  | S9251306420100 | 1STR*00283 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-19 | 2016-10-19 | Sous-poste | Sous-poste | 2016-10-23 | 2016-10-23 | 2016-10-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718013110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27180131 | NON-SPARES | 10 | 1 |  | F9251110800500 | 1STR*00297 | NA | 1680 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-21 | 2016-10-21 | Sous-poste | Sous-poste | 2016-10-26 | 2016-10-26 | 2016-10-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718013210 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27180132 | NON-SPARES | 10 | 2 |  | F9251445920000 | 1STR*01520 | NA | 1680 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-21 | 2016-10-21 | Sous-poste | Sous-poste | 2016-10-26 | 2016-10-26 | 2016-10-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718013310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27180133 | NON-SPARES | 10 | 1 |  | F9251485300000 | 1STR*01521 | NA | 1680 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-21 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-21 | 2016-10-21 | Sous-poste | Sous-poste | 2016-10-26 | 2016-10-26 | 2016-10-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 43 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2721999010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27219990 | NON-SPARES | 10 | 1 |  | F9251110800300 | 1STR*10653 | NA | 2326 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-10-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-28 | 2016-10-28 | Sous-poste | Sous-poste | 2016-11-02 | 2016-11-02 | 2016-11-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2016 | 1 | 2014 | 44 | 10 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718975010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27189750 | NON-SPARES | 10 | 1 |  | F9251110800300 | 1STR*10653 | NA | 2326 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-08 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-11-08 | 2016-11-08 | Sous-poste | Sous-poste | 2016-11-11 | 2016-11-11 | 2016-11-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 46 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003115510 | 2014-01-01 | HA/REVENTE | STELIA | SUPPLATE FRONT 27VU | 4900031155 | NON-SPARES | 10 | 1 | CRIT | S9251428800100 | 3STR*01418 | NA | 2491 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-11-14 | 2016-11-14 | Sous-poste | Sous-poste | 2016-11-16 | 2016-11-16 | 2016-11-16 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 47 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003108110 | 2014-01-01 | HA/REVENTE | STELIA | SUPPLATE FRONT 27VU | 4900031081 | NON-SPARES | 10 | 1 | CRIT | S9251428800100 | 3STR*01418 | NA | 2265 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-17 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-11-16 | 2016-11-16 | Sous-poste | Sous-poste | 2016-11-18 | 2016-11-18 | 2016-11-18 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 47 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003116410 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ARRIERE 112VU | 4900031164 | NON-SPARES | 10 | 2 | EXP | S9251380900000 | 3STR*01340 | NA | 2496 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-21 | NA | 100% | 2016-11-17 | 100% | NA | NA | 100% |  |  | 2016-11-21 | 2016-11-21 | Sous-poste | Sous-poste | 2016-11-24 | 2016-11-24 | 2016-11-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 48 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003100910 | 2014-01-01 | HA/REVENTE | STELIA | CARTER EQUIPE | 4900031009 | NON-SPARES | 10 | 1 | AOG | S9251020300100 | 0 | NA | 1942 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-23 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-11-22 | 2016-11-22 | Sous-poste | Sous-poste | 2016-11-24 | 2016-11-24 | 2016-11-24 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 48 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2715106410 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27151064 | NON-SPARES | 10 | 1 |  | A9252597000800 | 1STR*01148 | NA | 1327 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-22 | NA | 100% | 2016-11-22 | 100% | NA | NA | 100% |  |  | 2016-11-22 | 2016-11-22 | Sous-poste | Sous-poste | 2016-11-25 | 2016-11-25 | 2016-11-25 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 48 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003092210 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 4900030922 | NON-SPARES | 10 | 2 |  | S9251363300100 | IS0054056S | NA | 1894 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-11-23 | NA | 100% | 2016-11-21 | 100% | NA | NA | 100% |  |  | 2016-11-23 | 2016-11-23 | Sous-poste | Sous-poste | 2016-11-28 | 2016-11-28 | 2016-11-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2016 | 1 | 2014 | 48 | 11 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2716351110 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27163511 | NON-SPARES | 10 | 10 |  | D9251101900000 | 1STR*11007 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-01 | 2016-12-01 | Sous-poste | Sous-poste | 2016-12-06 | 2016-12-06 | 2016-12-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 49 | 12 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003125610 | 2014-01-01 | HA/REVENTE | STELIA | ENSEMBLE COMPAS | 4900031256 | NON-SPARES | 10 | 1 | CRIT | S9251340100100 | 1STR*11056 | NA | 2822 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-06 | NA | 100% | 2016-11-30 | 100% | NA | NA | 100% |  |  | 2016-12-05 | 2016-12-05 | Sous-poste | Sous-poste | 2016-12-07 | 2016-12-07 | 2016-12-07 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 50 | 12 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2715995810 | 2014-01-01 | HA/REVENTE | SATAIR | FLANGE ASSY | 27159958 | NON-SPARES | 10 | 2 |  | D9251127600000 | IS0008826S | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-12 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-12 | 2016-12-12 | Sous-poste | Sous-poste | 2016-12-15 | 2016-12-15 | 2016-12-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 51 | 12 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003112410 | 2014-01-01 | HA/REVENTE | STELIA | RONDELLE | 4900031124 | NON-SPARES | 10 | 4 |  | S0003012600000 | IS0013828S | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-14 | NA | 100% | 2016-11-07 | 100% | NA | NA | 100% |  |  | 2016-12-14 | 2016-12-14 | Sous-poste | Sous-poste | 2016-12-19 | 2016-12-19 | 2016-12-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 51 | 12 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
530948510 | 2014-01-01 | HA/REVENTE | SATAIR | 0 | 5309485 | NON-SPARES | 10 | 1 |  | F9251423320000 | 0 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-19 | 2016-12-19 | Sous-poste | Sous-poste | 2016-12-22 | 2016-12-22 | 2016-12-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 52 | 12 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
2724715310 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27247153 | NON-SPARES | 10 | 6 |  | V9251111520000 | 1STR*10661 | NA | 2968 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-22 | 2016-12-22 | Sous-poste | Sous-poste | 2016-12-27 | 2016-12-27 | 2016-12-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 52 | 12 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003147010 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900031470 | NON-SPARES | 10 | 2 | CRIT | S9252318000000 | 1STR*02063 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-23 | 2016-12-23 | Sous-poste | Sous-poste | 2016-12-27 | 2016-12-27 | 2016-12-27 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 52 | 12 | 2016 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003145510 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900031455 | NON-SPARES | 10 | 1 | EXP | S0003027000000 | 1STR*01261 | NA | 3491 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2016-12-30 | NA | 100% | 2016-12-21 | 100% | NA | NA | 100% |  |  | 2016-12-30 | 2016-12-30 | Sous-poste | Sous-poste | 2017-01-04 | 2017-01-04 | 2017-01-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2016 | 1 | 2014 | 53 | 12 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2723639510 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPORT | 27236395 | NON-SPARES | 10 | 6 |  | D9251551000100 | 1STR*00201 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-01-06 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-01-06 | 2017-01-06 | Sous-poste | Sous-poste | 2017-01-11 | 2017-01-11 | 2017-01-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2017 | 1 | 2014 | 1 | 1 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2724312210 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27243122 | NON-SPARES | 10 | 4 |  | F9251110800300 | 1STR*10653 | NA | 2326 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-01-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-12-20 | 2017-01-10 | Sous-poste | Sous-poste | 2016-12-23 | 2017-01-13 | 2017-01-13 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2017 | 1 | 2014 | 2 | 1 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2718673910 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPORT ASSY | 27186739 | NON-SPARES | 10 | 2 |  | F9241259500000 | 0 | NA | 1893 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-02-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2016-10-11 | 2017-02-09 | Sous-poste | Sous-poste | 2016-10-14 | 2017-02-14 | 2017-02-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2017 | 1 | 2014 | 6 | 2 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2723539010 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27235390 | NON-SPARES | 10 | 20 |  | D9251101900000 | 1STR*11007 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-02-13 | NA | 100% | 2017-01-30 | 100% | NA | NA | 100% |  |  | 2017-02-13 | 2017-02-13 | Sous-poste | Sous-poste | 2017-02-16 | 2017-02-16 | 2017-02-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2017 | 1 | 2014 | 7 | 2 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2719210910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27192109 | NON-SPARES | 10 | 2 |  | F9251110800600 | 1STR*10659 | NA | 3459 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-02-14 | NA | 100% | 2017-02-07 | 100% | NA | NA | 100% |  |  | 2017-01-10 | 2017-02-14 | Sous-poste | Sous-poste | 2017-01-13 | 2017-02-17 | 2017-02-17 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2017 | 1 | 2014 | 7 | 2 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003185810 | 2014-01-01 | HA/REVENTE | STELIA | ENSEMBLE COMPAS | 4900031858 | NON-SPARES | 10 | 1 |  | S9251340100100 | 1STR*11056 | NA | 4474 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-02-14 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-02-14 | 2017-02-14 | Sous-poste | Sous-poste | 2017-02-17 | 2017-02-17 | 2017-02-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2017 | 1 | 2014 | 7 | 2 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2727321110 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27273211 | NON-SPARES | 10 | 1 |  | A9253115800000 | IS0031675S | NA | 3871 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-02-15 | NA | 100% | 2017-02-10 | 100% | NA | NA | 100% |  |  | 2017-01-26 | 2017-02-15 | Sous-poste | Sous-poste | 2017-01-31 | 2017-02-20 | 2017-02-20 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2017 | 1 | 2014 | 7 | 2 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2725294110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27252941 | NON-SPARES | 10 | 1 |  | F9251110800300 | 1STR*10653 | NA | 3166 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-01 | NA | 100% | 2017-01-20 | 100% | NA | NA | 100% |  |  | 2017-03-01 | 2017-03-01 | Sous-poste | Sous-poste | 2017-03-04 | 2017-03-04 | 2017-03-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 9 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2730085710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27300857 | NON-SPARES | 10 | 50 |  | D9251101900000 | 1STR*11007 | NA | 4334 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-01 | NA | 100% | 2017-02-20 | 100% | NA | NA | 100% |  |  | 2017-03-01 | 2017-03-01 | Sous-poste | Sous-poste | 2017-03-05 | 2017-03-05 | 2017-03-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 9 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003155210 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900031552 | NON-SPARES | 10 | 2 |  | S0003027000000 | 1STR*01261 | NA | 4472 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-08 | NA | 100% | 2017-02-28 | 100% | NA | NA | 100% |  |  | 2017-03-08 | 2017-03-08 | Sous-poste | Sous-poste | 2017-03-13 | 2017-03-13 | 2017-03-13 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 10 | 3 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2733880110 | 2014-01-01 | HA/REVENTE | SATAIR | FOAM SILICONE | 27338801 | NON-SPARES | 10 | 2 | AOG | A9253172120000 | 0 | NA | 4959 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-03-09 | 2017-03-09 | Sous-poste | Sous-poste | 2017-03-13 | 2017-03-13 | 2017-03-13 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 10 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2726633010 | 2014-01-01 | HA/REVENTE | SATAIR | ENS PLATINE AR INF | 27266330 | NON-SPARES | 10 | 1 |  | F9251216800200 | 1STR*10655 | NA | 3367 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-09 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-03-09 | 2017-03-09 | Sous-poste | Sous-poste | 2017-03-14 | 2017-03-14 | 2017-03-14 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 10 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2724763910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY-CLOSING | 27247639 | NON-SPARES | 10 | 2 | AOG | F9251339200000 | IS0054706S | NA | 3009 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-15 | NA | 100% | 2017-03-10 | 100% | NA | NA | 100% |  |  | 2017-01-06 | 2017-03-14 | Sous-poste | Sous-poste | 2017-01-10 | 2017-03-16 | 2017-03-16 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 3 | 2017 | 1 | 2014 | 11 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2732220110 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27322201 | NON-SPARES | 10 | 8 |  | D9251101900000 | 1STR*11007 | NA | 4676 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-14 | NA | 100% | 2017-03-07 | 100% | NA | NA | 100% |  |  | 2017-03-14 | 2017-03-14 | Sous-poste | Sous-poste | 2017-03-17 | 2017-03-17 | 2017-03-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2017 | 1 | 2014 | 11 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2710580610 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27105806 | NON-SPARES | 10 | 1 |  | A9252882500700 | 1STR*10638 | NA | 598 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-03-27 | NA | 100% | 2017-03-23 | 100% | NA | NA | 100% |  |  | 2016-08-31 | 2017-03-27 | Sous-poste | Sous-poste | 2016-09-04 | 2017-03-30 | 2017-03-30 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 3 | 2017 | 1 | 2014 | 13 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2739789410 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27397894 | NON-SPARES | 10 | 1 | CRIT | F9251110801200 | 1STR*00294 | NA | 5389 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-04-03 | NA | 100% | 2017-04-14 | 100% | NA | NA | 100% |  |  | 2017-03-31 | 2017-03-31 | Sous-poste | Sous-poste | 2017-04-04 | 2017-04-04 | 2017-04-04 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 4 | 2017 | 1 | 2014 | 13 | 3 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2738420310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27384203 | NON-SPARES | 10 | 50 |  | D9251101900000 | 1STR*11007 | NA | 5132 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-04-05 | NA | 100% | 2017-03-29 | 100% | NA | NA | 100% |  |  | 2017-04-05 | 2017-04-05 | Sous-poste | Sous-poste | 2017-04-09 | 2017-04-09 | 2017-04-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2017 | 1 | 2014 | 14 | 4 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003181710 | 2014-01-01 | HA/REVENTE | STELIA | CAPOT | 4900031817 | NON-SPARES | 10 | 3 |  | S9251363300100 | IS0054056S | NA | 4589 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-04-05 | NA | 100% | 2017-03-29 | 100% | NA | NA | 100% |  |  | 2017-04-05 | 2017-04-05 | Sous-poste | Sous-poste | 2017-04-10 | 2017-04-10 | 2017-04-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2017 | 1 | 2014 | 14 | 4 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2729148410 | 2014-01-01 |  | TBD |  | 27291484 | NON-SPARES | 10 | 4 |  | A9242100020000 |  | NON PRESENT INDUS | 4028 | 0 |  |  |  | 100% | 0% | 50% | 100% | 2017-04-19 | NA | 100% | 2017-04-07 | 100% | NA | NA | 100% |  |  | 2017-02-08 | 2017-04-19 | Sous-poste | Sous-poste | 2017-02-12 | 2017-04-24 | 2017-04-24 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2017 | 1 | 2014 | 16 | 4 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27397188 | 0 | FABRICATION | SATAIR | 117 | 27397188 | NON-SPARES |  | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990257 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-04-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2017-04-20 | Sous-poste | Sous-poste | 2017-05-01 | 2017-04-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2739718910 | 0 | FABRICATION | SATAIR | 117 | 27397189 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990258 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-04-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2017-04-20 | Sous-poste | Sous-poste | 2017-05-01 | 2017-04-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2739719010 | 0 | FABRICATION | SATAIR | 117 | 27397190 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990259 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-04-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2017-04-20 | Sous-poste | Sous-poste | 2017-05-01 | 2017-04-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
490003235210 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900032352 | NON-SPARES | 10 | 3 |  | S0003027000000 | 1STR*01261 | NA | 4948 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-04-27 | NA | 100% | 2017-04-18 | 100% | NA | NA | 100% |  |  | 2017-04-27 | 2017-04-27 | Sous-poste | Sous-poste | 2017-05-02 | 2017-05-02 | 2017-05-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2017 | 1 | 2014 | 17 | 4 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2731544110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27315441 | NON-SPARES | 10 | 2 |  | F9251110800300 | 1STR*10653 | NA | 4524 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-03 | NA | 100% | 2017-04-26 | 100% | NA | NA | 100% |  |  | 2017-05-03 | 2017-05-03 | Sous-poste | Sous-poste | 2017-05-06 | 2017-05-06 | 2017-05-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 18 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2730803010 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27308030 | NON-SPARES | 10 | 1 |  | A9252236000000 | 1STR*01447 | NA | 4333 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-03 | NA | 100% | 2017-04-24 | 100% | NA | NA | 100% |  |  | 2017-05-03 | 2017-05-03 | Sous-poste | Sous-poste | 2017-05-07 | 2017-05-07 | 2017-05-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 18 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2730907410 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27309074 | NON-SPARES | 10 | 50 |  | D9251101900000 | 1STR*11007 | NA | 4334 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-03 | NA | 100% | 2017-04-21 | 100% | NA | NA | 100% |  |  | 2017-05-03 | 2017-05-03 | Sous-poste | Sous-poste | 2017-05-08 | 2017-05-08 | 2017-05-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 18 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2742397410 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPORT | 27423974 | NON-SPARES | 10 | 8 |  | D9251551000100 | 1STR*00201 | NA | 5875 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-05 | NA | 100% | 2017-05-04 | 100% | NA | NA | 100% |  |  | 2017-05-05 | 2017-05-05 | Sous-poste | Sous-poste | 2017-05-10 | 2017-05-10 | 2017-05-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 18 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003248410 | 2014-01-01 | HA/REVENTE | STELIA | ADAPTATEUR DME | 4900032484 | NON-SPARES | 10 | 2 |  | S9251179200000 | 3STR*01293 | NA | 5730 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-05-10 | 2017-05-10 | Sous-poste | Sous-poste | 2017-05-15 | 2017-05-15 | 2017-05-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 19 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003242810 | 2014-01-01 | HA/REVENTE | STELIA | JOINT | 4900032428 | NON-SPARES | 10 | 5 | CRIT | S9251054820000 | 1QME*16550 | NA | 5773 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-18 | NA | 100% | 2017-05-15 | 100% | NA | NA | 100% |  |  | 2017-05-17 | 2017-05-17 | Sous-poste | Sous-poste | 2017-05-19 | 2017-05-19 | 2017-05-19 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 20 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003209610 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT FIXE SUPERPOSE | 4900032096 | NON-SPARES | 10 | 1 |  | S0003027000000 | 1STR*01261 | NA | 4948 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-17 | NA | 100% | 2017-04-18 | 100% | NA | NA | 100% |  |  | 2017-05-17 | 2017-05-17 | Sous-poste | Sous-poste | 2017-05-22 | 2017-05-22 | 2017-05-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 20 | 5 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003245910 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 4900032459 | NON-SPARES | 10 | 2 |  | S9251083800000 | 1CMP*16129 | NA | 5876 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-17 | NA | 100% | 2017-05-15 | 100% | NA | NA | 100% |  |  | 2017-05-17 | 2017-05-17 | Sous-poste | Sous-poste | 2017-05-22 | 2017-05-22 | 2017-05-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 20 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003244910 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900032449 | NON-SPARES | 10 | 2 |  | S9251059700100 | 3STR*00061 | NA | 5825 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-19 | NA | 100% | 2017-05-16 | 100% | NA | NA | 100% |  |  | 2017-05-19 | 2017-05-19 | Sous-poste | Sous-poste | 2017-05-24 | 2017-05-24 | 2017-05-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 20 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003247610 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900032476 | NON-SPARES | 10 | 2 |  | S9251446520000 | 1STR*11044 | NA | 5917 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-24 | NA | 100% | 2017-05-17 | 100% | NA | NA | 100% |  |  | 2017-05-18 | 2017-05-24 | Sous-poste | Sous-poste | 2017-05-23 | 2017-05-29 | 2017-05-29 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2017 | 1 | 2014 | 21 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003249410 | 2014-01-01 | HA/REVENTE | STELIA | ENSEMBLE COMPAS | 4900032494 | NON-SPARES | 10 | 2 |  | S9251340100100 | 1STR*11056 | NA | 6102 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-24 | NA | 100% | 2017-05-19 | 100% | NA | NA | 100% |  |  | 2017-05-24 | 2017-05-24 | Sous-poste | Sous-poste | 2017-05-29 | 2017-05-29 | 2017-05-29 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 21 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2739924110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27399241 | NON-SPARES | 10 | 1 |  | F9251110800900 | 1STR*10658 | NA | 5481 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-25 | NA | 100% | 2017-05-22 | 100% | NA | NA | 100% |  |  | 2017-04-28 | 2017-05-25 | Sous-poste | Sous-poste | 2017-05-03 | 2017-05-30 | 2017-05-30 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2017 | 1 | 2014 | 21 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2740755410 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27407554 | NON-SPARES | 10 | 4 |  | F9251110800600 | 1STR*10659 | NA | 5612 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-25 | NA | 100% | 2017-05-22 | 100% | NA | NA | 100% |  |  | 2017-05-05 | 2017-05-25 | Sous-poste | Sous-poste | 2017-05-10 | 2017-05-30 | 2017-05-30 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2017 | 1 | 2014 | 21 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2733300610 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27333006 | NON-SPARES | 10 | 2 |  | A9252236000000 | 1STR*01447 | NA | 4947 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-05-31 | NA | 100% | 2017-05-18 | 100% | NA | NA | 100% |  |  | 2017-05-31 | 2017-05-31 | Sous-poste | Sous-poste | 2017-06-05 | 2017-06-05 | 2017-06-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2017 | 1 | 2014 | 22 | 5 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2742367110 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27423671 | NON-SPARES | 10 | 2 |  | V9251111520000 | 1STR*10661 | NA | 5879 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-09 | NA | 100% | 2017-06-07 | 100% | NA | NA | 100% |  |  | 2017-05-24 | 2017-06-09 | Sous-poste | Sous-poste | 2017-05-27 | 2017-06-14 | 2017-06-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2017 | 1 | 2014 | 23 | 6 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2742367210 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27423672 | NON-SPARES | 10 | 1 |  | V9251111522400 | 1STR*10662 | NA | 5879 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-09 | NA | 100% | 2017-06-07 | 100% | NA | NA | 100% |  |  | 2017-05-24 | 2017-06-09 | Sous-poste | Sous-poste | 2017-05-27 | 2017-06-14 | 2017-06-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2017 | 1 | 2014 | 23 | 6 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2744276610 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27442766 | NON-SPARES | 10 | 2 |  | V9251111521200 | 1STR*10663 | NA | 6107 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-09 | NA | 100% | 2017-06-09 | 100% | NA | NA | 100% |  |  | 2017-05-24 | 2017-06-09 | Sous-poste | Sous-poste | 2017-05-27 | 2017-06-14 | 2017-06-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2017 | 1 | 2014 | 23 | 6 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2738724310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27387243 | NON-SPARES | 10 | 5 |  | D9251335500000 | 1STR*00012 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-14 | NA | 100% | 2017-05-30 | 100% | NA | NA | 100% |  |  | 2017-06-14 | 2017-06-14 | Sous-poste | Sous-poste | 2017-06-19 | 2017-06-19 | 2017-06-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2017 | 1 | 2014 | 24 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003270910 | 2014-01-01 | HA/REVENTE | STELIA | SUPPLATE FRONT 27VU | 4900032709 | NON-SPARES | 10 | 2 |  | S9251428800100 | 3STR*01418 | NA | 6654 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-26 | NA | 100% | 2017-06-23 | 100% | NA | NA | 100% |  |  | 2017-06-23 | 2017-06-26 | Sous-poste | Sous-poste | 2017-06-28 | 2017-06-29 | 2017-06-29 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2017 | 1 | 2014 | 26 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003244010 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE | 4900032440 | NON-SPARES | 10 | 5 |  | A9252250526300 | 1STR*10660 | NA | 3875 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-29 | NA | 100% | 2017-06-26 | 100% | NA | NA | 100% |  |  | 2017-06-29 | 2017-06-29 | Sous-poste | Sous-poste | 2017-07-04 | 2017-07-04 | 2017-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2017 | 1 | 2014 | 26 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003263310 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900032633 | NON-SPARES | 10 | 1 |  | S9251022100000 | 4ACC*00710 | NA | 5347 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-29 | NA | 100% | 2017-06-26 | 100% | NA | NA | 100% |  |  | 2017-06-29 | 2017-06-29 | Sous-poste | Sous-poste | 2017-07-04 | 2017-07-04 | 2017-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2017 | 1 | 2014 | 26 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003263320 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900032633 | NON-SPARES | 20 | 1 |  | S9251022200000 | 4ACC*00711 | NA | 5347 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-29 | NA | 100% | 2017-06-26 | 100% | NA | NA | 100% |  |  | 2017-06-29 | 2017-06-29 | Sous-poste | Sous-poste | 2017-07-04 | 2017-07-04 | 2017-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2017 | 1 | 2014 | 26 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003235710 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 122VU | 4900032357 | NON-SPARES | 10 | 8 |  | S9251090300000 | 1STR*10677 | NA | 4586 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-06-30 | NA | 100% | 2017-06-26 | 100% | NA | NA | 100% |  |  | 2017-04-20 | 2017-06-30 | Sous-poste | Sous-poste | 2017-04-25 | 2017-07-05 | 2017-07-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2017 | 1 | 2014 | 26 | 6 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003284610 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900032846 | NON-SPARES | 10 | 1 |  | S9251059700000 | 3STR*00945 | NA | 6855 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-07 | NA | 100% | 2017-07-04 | 100% | NA | NA | 100% |  |  | 2017-07-07 | 2017-07-07 | Sous-poste | Sous-poste | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 27 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003284620 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900032846 | NON-SPARES | 20 | 1 |  | S9251059600000 | 3STR*00944 | NA | 6855 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-07 | NA | 100% | 2017-07-04 | 100% | NA | NA | 100% |  |  | 2017-07-07 | 2017-07-07 | Sous-poste | Sous-poste | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 27 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2742366210 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423662 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990033 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2017-07-11 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2017-07-12 | Sous-poste | Sous-poste | 2017-07-15 | 2017-07-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 28 | 7 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366310 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423663 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990034 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2017-07-11 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2017-07-12 | Sous-poste | Sous-poste | 2017-07-15 | 2017-07-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 28 | 7 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366410 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423664 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990035 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2017-07-11 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2017-07-12 | Sous-poste | Sous-poste | 2017-07-15 | 2017-07-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 28 | 7 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366510 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423665 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990038 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2017-07-11 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2017-07-12 | Sous-poste | Sous-poste | 2017-07-15 | 2017-07-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 28 | 7 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2748253710 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27482537 | NON-SPARES | 10 | 4 | AOG | V9251111520000 | 1STR*10661 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-14 | NA | 100% | 2017-07-12 | 100% | NA | NA | 100% |  |  | 2017-06-27 | 2017-07-13 | Sous-poste | Sous-poste | 2017-06-29 | 2017-07-17 | 2017-07-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2748253610 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27482536 | NON-SPARES | 10 | 2 | AOG | V9251111522400 | 1STR*10662 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-14 | NA | 100% | 2017-07-12 | 100% | NA | NA | 100% |  |  | 2017-06-27 | 2017-07-13 | Sous-poste | Sous-poste | 2017-06-29 | 2017-07-17 | 2017-07-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2748341310 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27483413 | NON-SPARES | 10 | 4 | AOG | V9251111521200 | 1STR*10663 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-14 | NA | 100% | 2017-07-12 | 100% | NA | NA | 100% |  |  | 2017-06-28 | 2017-07-13 | Sous-poste | Sous-poste | 2017-06-30 | 2017-07-17 | 2017-07-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2748882710 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27488827 | NON-SPARES | 10 | 1 | AOG | V9251111522400 | 1STR*10662 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-14 | NA | 100% | 2017-07-13 | 100% | NA | NA | 100% |  |  | 2017-07-04 | 2017-07-13 | Sous-poste | Sous-poste | 2017-07-06 | 2017-07-17 | 2017-07-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2739923710 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27399237 | NON-SPARES | 10 | 2 |  | F9251110800100 | 1STR*10656 | NA | 5481 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-13 | NA | 100% | 2017-07-07 | 100% | NA | NA | 100% |  |  | 2017-04-28 | 2017-07-13 | Sous-poste | Sous-poste | 2017-05-03 | 2017-07-18 | 2017-07-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003283710 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AVANT 23VU | 4900032837 | NON-SPARES | 10 | 1 |  | S9251165200200 | 1STR*10664 | NA | 6889 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-14 | NA | 100% | 2017-07-12 | 100% | NA | NA | 100% |  |  | 2017-07-14 | 2017-07-14 | Sous-poste | Sous-poste | 2017-07-19 | 2017-07-19 | 2017-07-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 28 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2739923910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27399239 | NON-SPARES | 10 | 1 |  | F9251110800400 | 1STR*10657 | NA | 5481 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-18 | NA | 100% | 2017-07-20 | 100% | NA | NA | 100% |  |  | 2017-04-28 | 2017-07-18 | Sous-poste | Sous-poste | 2017-05-03 | 2017-07-21 | 2017-07-21 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 29 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2748882810 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27488828 | NON-SPARES | 10 | 2 | AOG | V9251111520000 | 1STR*10661 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-24 | NA | 100% | 2017-07-24 | 100% | NA | NA | 100% |  |  | 2017-07-04 | 2017-07-21 | Sous-poste | Sous-poste | 2017-07-06 | 2017-07-25 | 2017-07-25 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 29 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2748980310 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27489803 | NON-SPARES | 10 | 2 | AOG | V9251111521200 | 1STR*10663 | NA | 7017 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-24 | NA | 100% | 2017-07-24 | 100% | NA | NA | 100% |  |  | 2017-07-05 | 2017-07-21 | Sous-poste | Sous-poste | 2017-07-07 | 2017-07-25 | 2017-07-25 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2017 | 1 | 2014 | 29 | 7 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003290210 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ARRIERE 5VU | 4900032902 | NON-SPARES | 10 | 2 | EXP | S9251593120000 | 3STR*00145 | NA | 7105 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-25 | NA | 100% | 2017-07-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-07-25 | Sous-poste | Sous-poste | 2017-07-28 | 2017-07-28 | 2017-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003290220 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 4900032902 | NON-SPARES | 20 | 2 | EXP | S9251597520000 | 1STR*10667 | NA | 7107 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-25 | NA | 100% | 2017-07-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-07-25 | Sous-poste | Sous-poste | 2017-07-28 | 2017-07-28 | 2017-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003290240 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 4900032902 | NON-SPARES | 40 | 2 | EXP | S9251594420000 | 1STR*10668 | NA | 7109 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-25 | NA | 100% | 2017-07-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-07-25 | Sous-poste | Sous-poste | 2017-07-28 | 2017-07-28 | 2017-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003290250 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AVANT 112VU | 4900032902 | NON-SPARES | 50 | 2 | EXP | S9251372600000 | 3STR*00947 | NA | 7110 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-25 | NA | 100% | 2017-07-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-07-25 | Sous-poste | Sous-poste | 2017-07-28 | 2017-07-28 | 2017-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003290260 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE | 4900032902 | NON-SPARES | 60 | 4 | EXP | F0003057822800 | 1QME*16553 | NA | 7112 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-25 | NA | 100% | 2017-07-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-07-25 | Sous-poste | Sous-poste | 2017-07-28 | 2017-07-28 | 2017-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2750292810 | 2014-01-01 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 27502928 | NON-SPARES | 10 | 2 |  | F9251367800000 | 1STR*10672 | NA | 7455 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-07-26 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-07-26 | 2017-07-26 | Sous-poste | Sous-poste | 2017-07-31 | 2017-07-31 | 2017-07-31 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2017 | 1 | 2014 | 30 | 7 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749087810 | 0 | FABRICATION | SATAIR | 517 | 27490878 | NON-SPARES | 10 | 1 | EXP | WF417AFACAAE | 0 | NON PRESENT INDUS | 7217 | EFD990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-08-03 | 100% | NA | NA | 5.556% |  |  | 2017-08-04 | 2017-07-31 | Sous-poste | Sous-poste | 2017-08-09 | 2017-08-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 31 | 7 | 2017 | 0.205 | 1.7325 | 0.43312 | 2.1656 | LAB | 0 | 0
2744198710 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27441987 | NON-SPARES | 10 | 2 |  | V9251111522400 | 1STR*10662 | NA | 6107 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-02 | NA | 100% | 2017-07-26 | 100% | NA | NA | 100% |  |  | 2017-08-02 | 2017-08-02 | Sous-poste | Sous-poste | 2017-08-05 | 2017-08-05 | 2017-08-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2017 | 1 | 2014 | 31 | 8 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003295610 | 2014-01-01 | HA/REVENTE | STELIA | STRUCTURE 755 VU | 4900032956 | NON-SPARES | 10 | 1 |  | S2523044600000 | 1STR*10632 | NA | 7390 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-03 | NA | 100% | 2017-07-28 | 100% | NA | NA | 100% |  |  | 2017-08-03 | 2017-08-03 | Sous-poste | Sous-poste | 2017-08-08 | 2017-08-08 | 2017-08-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2017 | 1 | 2014 | 31 | 8 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2740811710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27408117 | NON-SPARES | 10 | 20 |  | D9251101900000 | 1STR*11007 | NA | 5568 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-07 | NA | 100% | 2017-05-15 | 100% | NA | NA | 100% |  |  | 2017-08-07 | 2017-08-07 | Sous-poste | Sous-poste | 2017-08-10 | 2017-08-10 | 2017-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2017 | 1 | 2014 | 32 | 8 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749811610 | 0 | FABRICATION | SATAIR | 119 | 27498116 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 7327 | EFD990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-08-21 | 100% | NA | NA | 5.556% |  |  | 2017-08-22 | 2017-08-16 | Sous-poste | Sous-poste | 2017-08-25 | 2017-08-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 33 | 8 | 2017 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
490003290230 | 2014-01-01 | HA/REVENTE | STELIA | PRISE SUP 82 VU | 4900032902 | NON-SPARES | 30 | 2 | EXP | S9251596820000 | 1STR*10666 | NA | 7108 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-16 | NA | 100% | 2017-08-18 | 100% | NA | NA | 100% |  |  | 2017-07-25 | 2017-08-16 | Sous-poste | Sous-poste | 2017-07-28 | 2017-08-21 | 2017-08-21 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2017 | 1 | 2014 | 33 | 8 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003315810 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900033158 | NON-SPARES | 10 | 1 | AOG | S9251303020000 | 1QEL*00025 | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-23 | NA | 100% | 2017-08-18 | 100% | NA | NA | 100% |  |  | 2017-08-22 | 2017-08-22 | Sous-poste | Sous-poste | 2017-08-24 | 2017-08-24 | 2017-08-24 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 8 | 2017 | 1 | 2014 | 34 | 8 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003285110 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU DE FERMETURE ÉQUIPÉ | 4900032851 | NON-SPARES | 10 | 1 |  | S9251451700100 | 1STR*01133 | NA | 5172 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-08-28 | NA | 100% | 2017-10-11 | 100% | NA | NA | 100% |  |  | 2017-07-19 | 2017-08-28 | Sous-poste | Sous-poste | 2017-07-24 | 2017-08-31 | 2017-08-31 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2017 | 1 | 2014 | 35 | 8 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2751094710 | 2014-01-01 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 27510947 | NON-SPARES | 10 | 6 | AOG | D9251863200000 | 1STR*10676 | NA | 7591 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-06 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-07-27 | 2017-09-05 | Sous-poste | Sous-poste | 2017-07-31 | 2017-09-07 | 2017-09-07 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 9 | 2017 | 1 | 2014 | 36 | 9 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2746677610 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27466776 | NON-SPARES | 10 | 2 |  | F9251110800600 | 1STR*10659 | NA | 6655 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-06 | NA | 100% | 2017-08-31 | 100% | NA | NA | 100% |  |  | 2017-09-06 | 2017-09-06 | Sous-poste | Sous-poste | 2017-09-09 | 2017-09-09 | 2017-09-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 36 | 9 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003320510 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ARRIERE 5VU | 4900033205 | NON-SPARES | 10 | 1 | CRIT | S9251593120000 | 3STR*00145 | NA | 7860 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-08 | NA | 100% | 2017-09-06 | 100% | NA | NA | 100% |  |  | 2017-09-07 | 2017-09-07 | Sous-poste | Sous-poste | 2017-09-11 | 2017-09-11 | 2017-09-11 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 36 | 9 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003333210 | 2014-01-01 | HA/REVENTE | STELIA | RONDELLE | 4900033332 | NON-SPARES | 10 | 22 | CRIT | S0003012600000 | IS0013828S | NA | DS | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-14 | NA | 100% | 2017-09-12 | 100% | NA | NA | 100% |  |  | 2017-09-13 | 2017-09-13 | Sous-poste | Sous-poste | 2017-09-15 | 2017-09-15 | 2017-09-15 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630014575910 | 2014-01-01 | HA/REVENTE | SATAIR | RAMP ASSY | 6300145759 | NON-SPARES | 10 | 4 | AOG | V9251014003600 | 1STR*10688 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-19 | 2017-09-19 | 2017-09-19 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630014881310 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. BRACKET | 6300148813 | NON-SPARES | 10 | 3 | AOG | V9251140400001 | 1STR*10689 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-19 | 2017-09-19 | 2017-09-19 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630014881320 | 2014-01-01 | HA/REVENTE | SATAIR | BRACKET ASSY | 6300148813 | NON-SPARES | 20 | 1 | AOG | V9251140000001 | 1STR*10690 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-19 | 2017-09-19 | 2017-09-19 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630015297510 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300152975 | NON-SPARES | 10 | 1 |  | V9251115700000 | N/A | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-20 | 2017-09-20 | 2017-09-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630015297520 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300152975 | NON-SPARES | 20 | 1 |  | V9251115500000 | N/A | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-20 | 2017-09-20 | 2017-09-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630015297530 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300152975 | NON-SPARES | 30 | 1 |  | V9251115600000 | N/A | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-20 | 2017-09-20 | 2017-09-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630015297540 | 2014-01-01 | HA/REVENTE | SATAIR | FITTING | 6300152975 | NON-SPARES | 40 | 5 |  | V9251040720000 | N/A | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-15 | 2017-09-15 | Sous-poste | Sous-poste | 2017-09-20 | 2017-09-20 | 2017-09-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 37 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630008946510 | 2017-08-24 | FABRICATION | STELIA | FAISCEAU | 6300089465 | NON-SPARES | 10 | 3 | EXP | S9110157200196 | 0 | NON PRESENT INDUS | N/A | W18729-1 => W18729-3 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2017-09-22 | 100% | NA | NA | 5.556% |  |  | 2017-09-25 | 2017-09-19 | Sous-poste | Sous-poste | 2017-09-28 | 2017-09-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 38 | 9 | 2017 | 0.615 | 2.1 | 0.07 | 2.17 | NA | 0 | 0
630016178810 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300161788 | NON-SPARES | 10 | 1 | AOG | V9251115700001 | 1STR*10691 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-21 | 2017-09-21 | Sous-poste | Sous-poste | 2017-09-25 | 2017-09-25 | 2017-09-25 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 38 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630016178820 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300161788 | NON-SPARES | 20 | 1 | AOG | V9251115600001 | 1STR*10692 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-21 | 2017-09-21 | Sous-poste | Sous-poste | 2017-09-25 | 2017-09-25 | 2017-09-25 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 38 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630016178830 | 2014-01-01 | HA/REVENTE | SATAIR | EQUIPED BRACKET | 6300161788 | NON-SPARES | 30 | 1 | AOG | V9251115500001 | 1STR*10693 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-21 | 2017-09-21 | Sous-poste | Sous-poste | 2017-09-25 | 2017-09-25 | 2017-09-25 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 38 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630016178840 | 2014-01-01 | HA/REVENTE | SATAIR | FITTING | 6300161788 | NON-SPARES | 40 | 5 | AOG | V9251040720201 | 1STR*10694 | NA | 8220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-22 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-09-21 | 2017-09-21 | Sous-poste | Sous-poste | 2017-09-25 | 2017-09-25 | 2017-09-25 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 38 | 9 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003329710 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE POST | 4900033297 | NON-SPARES | 10 | 1 | CRIT | F0003057820900 | 1STR*10679 | NA | 7908 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-27 | NA | 100% | 2017-09-20 | 100% | NA | NA | 100% |  |  | 2017-09-26 | 2017-09-26 | Sous-poste | Sous-poste | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 39 | 9 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003329720 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE POST | 4900033297 | NON-SPARES | 20 | 1 | CRIT | F0003057822100 | 1STR*10680 | NA | 7908 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-09-27 | NA | 100% | 2017-09-20 | 100% | NA | NA | 100% |  |  | 2017-09-26 | 2017-09-26 | Sous-poste | Sous-poste | 2017-09-28 | 2017-09-28 | 2017-09-28 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 9 | 2017 | 1 | 2014 | 39 | 9 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749646510 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27496465 | NON-SPARES | 10 | 1 |  | F9251110800600 | 1STR*10659 | NA | 7310 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-04 | NA | 100% | 2017-09-27 | 100% | NA | NA | 100% |  |  | 2017-10-04 | 2017-10-04 | Sous-poste | Sous-poste | 2017-10-07 | 2017-10-07 | 2017-10-07 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2017 | 1 | 2014 | 40 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2755267810 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27552678 | NON-SPARES | 10 | 2 | AOG | V9251111521200 | 1STR*10663 | NA | 8377 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-09 | NA | 100% | 2017-10-04 | 100% | NA | NA | 100% |  |  | 2017-09-19 | 2017-10-06 | Sous-poste | Sous-poste | 2017-09-21 | 2017-10-10 | 2017-10-10 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 40 | 10 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003304710 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 122VU | 4900033047 | NON-SPARES | 10 | 3 |  | S9251090300000 | 1STR*10677 | NA | 7596 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-10 | NA | 100% | 2017-10-17 | 100% | NA | NA | 100% |  |  | 2017-08-01 | 2017-10-10 | Sous-poste | Sous-poste | 2017-08-04 | 2017-10-13 | 2017-10-13 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 41 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749486210 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27494862 | NON-SPARES | 10 | 4 |  | D9251794600000 | 1STR*10671 | NA | 7277 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-11 | NA | 100% | 2017-10-12 | 100% | NA | NA | 100% |  |  | 2017-08-14 | 2017-10-11 | Sous-poste | Sous-poste | 2017-08-17 | 2017-10-16 | 2017-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 41 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749486310 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27494863 | NON-SPARES | 10 | 4 |  | D9251794200000 | 1STR*10670 | NA | 7277 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-11 | NA | 100% | 2017-10-12 | 100% | NA | NA | 100% |  |  | 2017-08-14 | 2017-10-11 | Sous-poste | Sous-poste | 2017-08-17 | 2017-10-16 | 2017-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 41 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2749533910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27495339 | NON-SPARES | 10 | 20 |  | D9251101900000 | 1STR*11007 | NA | 7294 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-13 | NA | 100% | 2017-10-09 | 100% | NA | NA | 100% |  |  | 2017-10-06 | 2017-10-13 | Sous-poste | Sous-poste | 2017-10-11 | 2017-10-18 | 2017-10-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 41 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2753580510 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27535805 | NON-SPARES | 10 | 15 | EXP | V9251111520000 | 1STR*10661 | NA | 7930 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-19 | NA | 100% | 2017-10-16 | 100% | NA | NA | 100% |  |  | 2017-09-27 | 2017-10-19 | Sous-poste | Sous-poste | 2017-10-01 | 2017-10-24 | 2017-10-24 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2017 | 1 | 2014 | 42 | 10 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2751171510 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27511715 | NON-SPARES | 10 | 6 |  | V9251111521200 | 1STR*10663 | NA | 7606 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-19 | NA | 100% | 2017-10-16 | 100% | NA | NA | 100% |  |  | 2017-10-19 | 2017-10-19 | Sous-poste | Sous-poste | 2017-10-24 | 2017-10-24 | 2017-10-24 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2017 | 1 | 2014 | 42 | 10 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003355510 | 2014-01-01 | HA/REVENTE | STELIA | CALE | 4900033555 | NON-SPARES | 10 | 1 | RTN | S9252335520000 | 4STR*00688 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-10-31 | NA | 100% | 2017-10-27 | 100% | NA | NA | 100% |  |  | 2017-10-31 | 2017-10-31 | Sous-poste | Sous-poste | 2017-11-03 | 2017-11-03 | 2017-11-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2017 | 1 | 2014 | 44 | 10 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003217610 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU DE FERMETURE ÉQUIPÉ | 4900032176 | NON-SPARES | 10 | 3 |  | S9251451700100 | 1STR*01133 | NA | 5172 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-03 | NA | 100% | 2017-11-02 | 100% | NA | NA | 100% |  |  | 2017-04-05 | 2017-11-03 | Sous-poste | Sous-poste | 2017-04-10 | 2017-11-08 | 2017-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2017 | 1 | 2014 | 44 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752038810 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27520388 | NON-SPARES | 10 | 30 |  | D9251101900000 | 1STR*11007 | NA | 7681 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-03 | NA | 100% | 2017-10-30 | 100% | NA | NA | 100% |  |  | 2017-11-03 | 2017-11-03 | Sous-poste | Sous-poste | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2017 | 1 | 2014 | 44 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752665110 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27526651 | NON-SPARES | 10 | 8 | AOG | A9252483620000 | 1QME*16563 | NA | 7709 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-14 | NA | 100% | 2017-11-06 | 100% | NA | NA | 100% |  |  | 2017-08-17 | 2017-11-13 | Sous-poste | Sous-poste | 2017-08-21 | 2017-11-15 | 2017-11-15 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 11 | 2017 | 1 | 2014 | 46 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2760473610 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27604736 | NON-SPARES | 10 | 3 | AOG | V9251111522400 | 1STR*10662 | NA | 7930 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-11-14 | 2017-11-14 | Sous-poste | Sous-poste | 2017-11-16 | 2017-11-16 | 2017-11-16 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 11 | 2017 | 1 | 2014 | 46 | 11 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2742366010 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423660 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990031 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2017-11-15 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2017-11-16 | Sous-poste | Sous-poste | 2017-11-21 | 2017-11-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 46 | 11 | 2017 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761097810 | 2017-11-22 | FABRICATION | SATAIR | 108 | 27610978 | NON-SPARES | 10 | 1 | AOG | D9550010802795 | 0 | NON PRESENT INDUS | 9827 | EFD990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2017-11-22 | 100% | NA | NA | 5.556% |  |  | 2017-11-22 | 2017-11-20 | Sous-poste | Sous-poste | 2017-11-24 | 2017-11-22 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2017 | 47 | 11 | 2017 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2753580410 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27535804 | NON-SPARES | 10 | 10 |  | V9251111521200 | 1STR*10663 | NA | 7930 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-27 | NA | 100% | 2017-11-27 | 100% | NA | NA | 100% |  |  | 2017-11-27 | 2017-11-27 | Sous-poste | Sous-poste | 2017-11-30 | 2017-11-30 | 2017-11-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2017 | 1 | 2014 | 48 | 11 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003362910 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900033629 | NON-SPARES | 10 | 2 | EXP | S9251059600000 | 3STR*00944 | NA | 9337 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-29 | NA | 100% | 2017-11-30 | 100% | NA | NA | 100% |  |  | 2017-11-14 | 2017-11-29 | Sous-poste | Sous-poste | 2017-11-17 | 2017-12-04 | 2017-12-04 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2017 | 1 | 2014 | 48 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003362920 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AVANT 23VU | 4900033629 | NON-SPARES | 20 | 2 | EXP | S9251165200200 | 1STR*10664 | NA | 9337 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-29 | NA | 100% | 2017-11-30 | 100% | NA | NA | 100% |  |  | 2017-11-14 | 2017-11-29 | Sous-poste | Sous-poste | 2017-11-17 | 2017-12-04 | 2017-12-04 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2017 | 1 | 2014 | 48 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003369210 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900033692 | NON-SPARES | 10 | 2 | EXP | S9251059700000 | 3STR*00945 | NA | 9337 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-11-29 | NA | 100% | 2017-11-30 | 100% | NA | NA | 100% |  |  | 2017-11-15 | 2017-11-29 | Sous-poste | Sous-poste | 2017-11-18 | 2017-12-04 | 2017-12-04 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2017 | 1 | 2014 | 48 | 11 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2750716010 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27507160 | NON-SPARES | 10 | 1 | EXP | L9251394100000 | 1STR*10675 | NA | 7507 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-05 | NA | 100% | 2017-11-30 | 100% | NA | NA | 100% |  |  | 2017-08-21 | 2017-12-05 | Sous-poste | Sous-poste | 2017-08-24 | 2017-12-08 | 2017-12-08 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2017 | 1 | 2014 | 49 | 12 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2727129010 | 2014-01-01 | HA/REVENTE | SATAIR | ENS TOLE LATERALE INF G | 27271290 | NON-SPARES | 10 | 13 |  | A9252882500400 | 3STR*01342 | NA | 3847 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-12 | NA | 100% | 2017-07-10 | 100% | NA | NA | 100% |  |  | 2017-01-17 | 2017-12-12 | Sous-poste | Sous-poste | 2017-01-20 | 2017-12-15 | 2017-12-15 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2017 | 1 | 2014 | 50 | 12 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2760603610 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27606036 | NON-SPARES | 10 | 2 | AOG | L9251321500000 | 1STR*01089 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-12-14 | 2017-12-14 | Sous-poste | Sous-poste | 2017-12-16 | 2017-12-16 | 2017-12-16 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2017 | 1 | 2014 | 50 | 12 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763499010 | 2014-01-01 | HA/REVENTE | SATAIR | POTENTIOMETRE | 27634990 | NON-SPARES | 10 | 1 | AOG | ABS2208AP08S | 4CMP*00026 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-15 | NA | 100% | 2017-12-15 | 100% | NA | NA | 100% |  |  | 2017-12-13 | 2017-12-14 | Sous-poste | Sous-poste | 2017-12-15 | 2017-12-18 | 2017-12-18 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2017 | 1 | 2014 | 50 | 12 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2756637610 | 2014-01-01 | HA/REVENTE | SATAIR | MOUNT | 27566376 | NON-SPARES | 10 | 1 | AOG | F9251259220000 | 1STR*10706 | NA | 8812 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-15 | NA | 100% | 2017-12-08 | 100% | NA | NA | 100% |  |  | 2017-10-09 | 2017-12-14 | Sous-poste | Sous-poste | 2017-10-11 | 2017-12-18 | 2017-12-18 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 12 | 2017 | 1 | 2014 | 50 | 12 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763331210 | 2017-12-14 | HA/REVENTE | SATAIR | SUPPORT ASSY | 27633312 | NON-SPARES | 10 | 3 | AOG | F9251259500100 | 1STR*01489 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2017-12-11 | 2017-12-14 | Sous-poste | Sous-poste | 2017-12-13 | 2017-12-18 | 2017-12-18 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 12 | 2017 | 12 | 2017 | 50 | 12 | 2017 | 0 | 0 | 0 | 0 | NA | 0 | 0
2757163010 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27571630 | NON-SPARES | 10 | 2 | CRIT | V9251111520000 | 1STR*10661 | NA | 8954 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2017-12-19 | NA | 100% | 2017-12-12 | 100% | NA | NA | 100% |  |  | 2017-10-16 | 2017-12-18 | Sous-poste | Sous-poste | 2017-10-18 | 2017-12-20 | 2017-12-20 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 12 | 2017 | 1 | 2014 | 51 | 12 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2755347710 | 0 | FABRICATION | SATAIR | 22 | 27553477 | NON-SPARES | 10 | 1 | RTN | D9551002201495 | 0 | NON PRESENT INDUS | 8449 | EFD990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-01-02 | 100% | NA | NA | 5.556% |  |  | 2017-10-11 | 2018-01-03 | Sous-poste | Sous-poste | 2017-10-16 | 2018-01-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 1 | 1 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2763373510 | 2017-12-13 | FABRICATION | SATAIR | 423 | 27633735 | NON-SPARES | 10 | 1 | EXP | A95500423000AA | 0 | NON PRESENT INDUS | 0 | EFD990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-01-08 | 100% | NA | NA | 5.556% |  |  | 2018-01-09 | 2018-01-03 | Sous-poste | Sous-poste | 2018-01-12 | 2018-01-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 12 | 2017 | 1 | 1 | 2018 | 0.205 | 13.33 | 3.3325 | 16.6625 | COL | 0 | 0
2752567810 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27525678 | NON-SPARES | 10 | 14 | RTN | A9251080821000 | 1QME*16558 | NA | 7700 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-03 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-03 | Sous-poste | Sous-poste | 2017-12-10 | 2018-01-08 | 2018-01-08 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 1 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752566210 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27525662 | NON-SPARES | 10 | 49 | RTN | A9251080820000 | 1QME*16559 | NA | 7700 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-03 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-03 | Sous-poste | Sous-poste | 2017-12-10 | 2018-01-08 | 2018-01-08 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 1 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765451410 | 2018-01-11 | HA/REVENTE | SATAIR | DIAPHRAGME | 27654514 | NON-SPARES | 10 | 1 | AOG | V9251111520600 | 1STR*10733 | NA | 10771 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-01-09 | 2018-01-09 | Sous-poste | Sous-poste | 2018-01-11 | 2018-01-11 | 2018-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 1 | 2018 | 1 | 2018 | 2 | 1 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2765451510 | 2018-01-11 | HA/REVENTE | SATAIR | DIAPHRAGME | 27654515 | NON-SPARES | 10 | 1 | AOG | V9251111522200 | 1STR*10734 | NA | 10771 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-10 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-01-09 | 2018-01-09 | Sous-poste | Sous-poste | 2018-01-11 | 2018-01-11 | 2018-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 1 | 2018 | 1 | 2018 | 2 | 1 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003375610 | 2014-01-01 | HA/REVENTE | STELIA | RONDELLE | 4900033756 | NON-SPARES | 10 | 3 | RTN | S0003012600000 | IS0013828S | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-09 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2018-01-09 | 2018-01-09 | Sous-poste | Sous-poste | 2018-01-12 | 2018-01-12 | 2018-01-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2018 | 1 | 2014 | 2 | 1 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2762594310 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27625943 | NON-SPARES | 10 | 4 | EXP | A9252236000000 | 1STR*01447 | NA | 10157 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-10 | NA | 100% | 2018-01-05 | 100% | NA | NA | 100% |  |  | 2018-01-02 | 2018-01-10 | Sous-poste | Sous-poste | 2018-01-05 | 2018-01-15 | 2018-01-15 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 2 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003409710 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900034097 | NON-SPARES | 10 | 2 | EXP | S9252318000000 | 1STR*02063 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-10 | NA | 100% | 2018-01-04 | 100% | NA | NA | 100% |  |  | 2018-01-10 | 2018-01-10 | Sous-poste | Sous-poste | 2018-01-15 | 2018-01-15 | 2018-01-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2018 | 1 | 2014 | 2 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2766120910 | 2018-01-18 | FABRICATION | SATAIR | 430 | 27661209 | NON-SPARES | 10 | 1 | AOG | A9550043077195 | 0 | NON PRESENT INDUS | 10952 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-01-17 | 100% | NA | NA | 5.556% |  |  | 2018-01-17 | 2018-01-15 | Sous-poste | Sous-poste | 2018-01-19 | 2018-01-17 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 2018 | 3 | 1 | 2018 | 0 | 41.2615 | 10.3154 | 51.5769 | COL | 0 | 0
2752566310 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27525663 | NON-SPARES | 10 | 35 | RTN | A9251080820200 | 1QME*16560 | NA | 7700 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-15 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-15 | Sous-poste | Sous-poste | 2017-12-10 | 2018-01-18 | 2018-01-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 3 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752567610 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27525676 | NON-SPARES | 10 | 7 | RTN | A9251080820800 | 1QME*16561 | NA | 7700 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-15 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-15 | Sous-poste | Sous-poste | 2017-12-10 | 2018-01-18 | 2018-01-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 3 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752567910 | 2014-01-01 | HA/REVENTE | SATAIR | SEAL | 27525679 | NON-SPARES | 10 | 7 | RTN | A9251080821200 | 1QME*16562 | NA | 7700 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-15 | NA | 100% | 2018-01-02 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-15 | Sous-poste | Sous-poste | 2017-12-10 | 2018-01-18 | 2018-01-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 3 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2762013310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY 52VU | 27620133 | NON-SPARES | 10 | 1 | EXP | D9251655400000 | 1STR*10725 | NA | 9974 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-16 | NA | 100% | 2018-01-11 | 100% | NA | NA | 100% |  |  | 2017-12-06 | 2018-01-16 | Sous-poste | Sous-poste | 2017-12-11 | 2018-01-19 | 2018-01-19 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 3 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763869310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27638693 | NON-SPARES | 10 | 80 | EXP | D9251101900000 | 1STR*11007 | NA | 10466 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-16 | NA | 100% | 2018-01-09 | 100% | NA | NA | 100% |  |  | 2018-01-16 | 2018-01-16 | Sous-poste | Sous-poste | 2018-01-19 | 2018-01-19 | 2018-01-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2018 | 1 | 2014 | 3 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003357910 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900033579 | NON-SPARES | 10 | 27 |  | S9251303120000 | 1QEL*00029 | NA | 9294 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-22 | NA | 100% | 2018-01-26 | 100% | NA | NA | 100% |  |  | 2018-01-03 | 2018-01-22 | Sous-poste | Sous-poste | 2018-01-08 | 2018-01-25 | 2018-01-25 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2762727810 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE ASSY 429VU | 27627278 | NON-SPARES | 10 | 1 | AOG | A9251050600000 | 1STR*10727 | NA | 10150 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-24 | NA | 100% | 2018-01-16 | 100% | NA | NA | 100% |  |  | 2017-12-05 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-07 | 2018-01-25 | 2018-01-25 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752650010 | 0 | FABRICATION | SATAIR | 116 | 27526500 | NON-SPARES | 10 | 3 | RTN | D9551011600195 | 0 | NON PRESENT INDUS | 7987 | LTE990001 => LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-01-22 | 100% | NA | NA | 5.556% |  |  | 2017-09-07 | 2018-01-23 | Sous-poste | Sous-poste | 2017-09-12 | 2018-01-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 4 | 1 | 2018 | 0.615 | 4.2 | 0.35 | 4.55 | COL | 0 | 0
2765332610 | 2018-01-10 | HA/REVENTE | SATAIR | PLACARD SET | 27653326 | NON-SPARES | 10 | 2 | EXP | D9100095010195 | 1STR*10715 | NA | 10991 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-01-23 | 2018-01-23 | Sous-poste | Sous-poste | 2018-01-26 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 1 | 2018 | 1 | 2018 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2756474910 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27564749 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-20 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-25 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2756475010 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27564750 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-20 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-25 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2759483810 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET | 27594838 | NON-SPARES | 10 | 1 | EXP | D9100095010195 | 1STR*10715 | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-20 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-25 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2761617210 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27616172 | NON-SPARES | 10 | 10 | EXP | D9251095400000 | IS0053354S | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-25 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-28 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2761617310 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27616173 | NON-SPARES | 10 | 10 | EXP | D9251095600000 | IS0053509S | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-25 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-28 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2761720010 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET | 27617200 | NON-SPARES | 10 | 10 | EXP | D9100095010195 | 1STR*10715 | NA | 8813 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-23 | NA | 100% | 2018-01-23 | 100% | NA | NA | 100% |  |  | 2017-12-25 | 2018-01-23 | Sous-poste | Sous-poste | 2017-12-28 | 2018-01-26 | 2018-01-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 4 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2709509610 | 0 | FABRICATION | SATAIR | 117 | 27095096 | NON-SPARES | 10 | 8 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 437 | LTE990001 => LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-01-25 | 100% | NA | NA | 5.556% |  |  | 2016-08-15 | 2018-01-26 | Sous-poste | Sous-poste | 2016-08-18 | 2018-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 4 | 1 | 2018 | 1.64 | 30.52 | 0.95375 | 31.4737 | COL | 0 | 0
2740515910 | 0 | FABRICATION | SATAIR | 117 | 27405159 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-01-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-01-26 | Sous-poste | Sous-poste | 2017-05-01 | 2018-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 4 | 1 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740525210 | 0 | FABRICATION | SATAIR | 117 | 27405252 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-01-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-01-26 | Sous-poste | Sous-poste | 2017-05-01 | 2018-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 4 | 1 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740527810 | 0 | FABRICATION | SATAIR | 117 | 27405278 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-01-25 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-01-26 | Sous-poste | Sous-poste | 2017-05-01 | 2018-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 4 | 1 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
630035585610 | 2017-12-07 | FABRICATION | STELIA | CABLE COAXIAL | 6300355856 | NON-SPARES | 10 | 6 | EXP | S9110104500295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-03 | 2018-01-26 | Sous-poste | Sous-poste | 2018-01-08 | 2018-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 12 | 2017 | 4 | 1 | 2018 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
2763331220 | 2017-12-14 | HA/REVENTE | SATAIR | SUPPORT ASSY | 27633312 | NON-SPARES | 20 | 3 | AOG | F9251259500100 | 1STR*01489 | NA | 10282 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-30 | NA | 100% | 2018-01-26 | 100% | NA | NA | 100% |  |  | 2017-12-11 | 2018-01-29 | Sous-poste | Sous-poste | 2017-12-13 | 2018-01-31 | 2018-01-31 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 1 | 2018 | 12 | 2017 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765796810 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPORT ASSY | 27657968 | NON-SPARES | 10 | 4 | AOG | F9251259500100 | 1STR*01489 | NA | 10282 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-30 | NA | 100% | 2018-01-26 | 100% | NA | NA | 100% |  |  | 2018-01-12 | 2018-01-29 | Sous-poste | Sous-poste | 2018-01-16 | 2018-01-31 | 2018-01-31 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763528110 | 2014-01-01 | HA/REVENTE | SATAIR | WASHER | 27635281 | NON-SPARES | 10 | 6 | AOG | L9251298020000 | 1QME*00812 | NA | 10363 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-30 | NA | 100% | 2018-01-19 | 100% | NA | NA | 100% |  |  | 2017-12-14 | 2018-01-29 | Sous-poste | Sous-poste | 2017-12-16 | 2018-01-31 | 2018-01-31 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2767370610 | 2018-02-01 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 27673706 | NON-SPARES | 10 | 1 | AOG | D9251863200000 | 1STR*10676 | NA | 11245 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-01-31 | 2018-01-31 | Sous-poste | Sous-poste | 2018-02-02 | 2018-02-02 | 2018-02-02 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 2 | 2018 | 2 | 2018 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2754716110 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27547161 | NON-SPARES | 10 | 1 | RTN | D9251794600000 | 1STR*10671 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-31 | NA | 100% | 2017-12-20 | 100% | NA | NA | 100% |  |  | 2017-12-01 | 2018-01-31 | Sous-poste | Sous-poste | 2017-12-06 | 2018-02-05 | 2018-02-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2754715710 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27547157 | NON-SPARES | 10 | 1 | RTN | D9251794200000 | 1STR*10670 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-01-31 | NA | 100% | 2018-01-29 | 100% | NA | NA | 100% |  |  | 2017-12-01 | 2018-01-31 | Sous-poste | Sous-poste | 2017-12-06 | 2018-02-05 | 2018-02-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 1 | 2018 | 1 | 2014 | 5 | 1 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765293510 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27652935 | NON-SPARES | 10 | 2 | CRIT | D9251095400000 | IS0053354S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-02 | NA | 100% | 2018-01-29 | 100% | NA | NA | 100% |  |  | 2018-01-09 | 2018-02-01 | Sous-poste | Sous-poste | 2018-01-11 | 2018-02-05 | 2018-02-05 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 5 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765293710 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27652937 | NON-SPARES | 10 | 2 | CRIT | D9251095600000 | IS0053509S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-02 | NA | 100% | 2018-01-29 | 100% | NA | NA | 100% |  |  | 2018-01-09 | 2018-02-01 | Sous-poste | Sous-poste | 2018-01-11 | 2018-02-05 | 2018-02-05 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 5 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765295110 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27652951 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-06 | NA | 100% | 2018-01-30 | 100% | NA | NA | 100% |  |  | 2018-02-06 | 2018-02-06 | Sous-poste | Sous-poste | 2018-02-09 | 2018-02-09 | 2018-02-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765295410 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27652954 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-06 | NA | 100% | 2018-01-30 | 100% | NA | NA | 100% |  |  | 2018-02-06 | 2018-02-06 | Sous-poste | Sous-poste | 2018-02-09 | 2018-02-09 | 2018-02-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2766568110 | 0 | FABRICATION | SATAIR | 313 | 27665681 | NON-SPARES | 10 | 1 | CRIT | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 11086 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-02-07 | 100% | NA | NA | 5.556% |  |  | 2018-01-24 | 2018-02-07 | Sous-poste | Sous-poste | 2018-01-26 | 2018-02-09 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 6 | 2 | 2018 | 0.51 | 3.85 | 0.9625 | 4.8125 | LAB | 0 | 0
2765719410 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27657194 | NON-SPARES | 10 | 2 | EXP | L9251321500000 | 1STR*01089 | NA | 10800 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-07 | NA | 100% | 2018-01-30 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-02-07 | Sous-poste | Sous-poste | 2018-02-11 | 2018-02-11 | 2018-02-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765625910 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27656259 | NON-SPARES | 10 | 6 | EXP | D9251095600000 | IS0053509S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-07 | NA | 100% | 2018-01-31 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-02-07 | Sous-poste | Sous-poste | 2018-02-11 | 2018-02-11 | 2018-02-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
E8789829L10 | 2018-01-10 | FABRICATION | AD&S | 12 | E8789829L | NON-SPARES | 10 | 1 | CRIT | MB170ACAAAAA | IS0032211M | NON PRESENT INDUS | 11494 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-02-12 | 100% | NA | NA | 5.556% |  |  | 2018-02-12 | 2018-02-08 | Sous-poste | Sous-poste | 2018-02-14 | 2018-02-12 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 2018 | 6 | 2 | 2018 | 0.205 | 8.3333 | 2.0833 | 10.4166 | LAB | 0 | 0
2765295310 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27652953 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-09 | NA | 100% | 2018-01-30 | 100% | NA | NA | 100% |  |  | 2018-02-06 | 2018-02-09 | Sous-poste | Sous-poste | 2018-02-09 | 2018-02-14 | 2018-02-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765295210 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27652952 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-09 | NA | 100% | 2018-01-30 | 100% | NA | NA | 100% |  |  | 2018-02-06 | 2018-02-09 | Sous-poste | Sous-poste | 2018-02-09 | 2018-02-14 | 2018-02-14 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765742910 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27657429 | NON-SPARES | 10 | 6 | EXP | D9251095400000 | IS0053354S | NA | 10902 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-09 | NA | 100% | 2018-02-02 | 100% | NA | NA | 100% |  |  | 2018-02-09 | 2018-02-09 | Sous-poste | Sous-poste | 2018-02-14 | 2018-02-14 | 2018-02-14 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 6 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2753545310 | 0 | FABRICATION | SATAIR | JACK ASSY | 27535453 | NON-SPARES | 10 | 6 | CRIT | F7161001100001 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-12-13 | 2018-02-12 | Sous-poste | Sous-poste | 2017-12-15 | 2018-02-14 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 7 | 2 | 2018 | 1.1196 | 9.2256 | 0.15376 | 9.3794 | COL | 0 | 0
2756919110 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27569191 | NON-SPARES | 10 | 1 | RTN | D9251794200000 | 1STR*10670 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-12 | NA | 100% | 2018-02-05 | 100% | NA | NA | 100% |  |  | 2018-02-12 | 2018-02-12 | Sous-poste | Sous-poste | 2018-02-15 | 2018-02-15 | 2018-02-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 7 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2756919410 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27569194 | NON-SPARES | 10 | 1 | RTN | D9251794600000 | 1STR*10671 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-12 | NA | 100% | 2018-02-05 | 100% | NA | NA | 100% |  |  | 2018-02-12 | 2018-02-12 | Sous-poste | Sous-poste | 2018-02-15 | 2018-02-15 | 2018-02-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 7 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27687280 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27687280 | NON-SPARES |  | 5 | AOG | F0003003000000 | IS0032144M | NON PRESENT INDUS | 11581 | Z55870-1 => Z55870-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-02-16 | 100% | NA | NA | 5.556% |  |  | 2018-02-20 | 2018-02-16 | Sous-poste | Sous-poste | 2018-02-22 | 2018-02-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 7 | 2 | 2018 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
2768048910 | 0 | FABRICATION | SATAIR | 27 | 27680489 | NON-SPARES | 10 | 5 | CRIT | D9551002700595 | IS0032094M | NON PRESENT INDUS | 10453 | LTE990001 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-02-19 | 100% | NA | NA | 5.556% |  |  | 2018-02-15 | 2018-02-19 | Sous-poste | Sous-poste | 2018-02-19 | 2018-02-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 1.8 | 24.5865 | 1.2293 | 25.8158 | COL | 0 | 0
2761382110 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27613821 | NON-SPARES | 10 | 10 | RTN | D9251794600000 | 1STR*10671 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-19 | NA | 100% | 2018-02-12 | 100% | NA | NA | 100% |  |  | 2018-02-19 | 2018-02-19 | Sous-poste | Sous-poste | 2018-02-22 | 2018-02-22 | 2018-02-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2766427810 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27664278 | NON-SPARES | 10 | 19 | EXP | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-19 | NA | 100% | 2018-02-12 | 100% | NA | NA | 100% |  |  | 2018-02-19 | 2018-02-19 | Sous-poste | Sous-poste | 2018-02-22 | 2018-02-22 | 2018-02-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27684576 | 0 | FABRICATION | SATAIR | JACK | 27684576 | NON-SPARES |  | 1 | AOG | A0041114100095 | IS0032651M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-08 | 2018-02-21 | Sous-poste | Sous-poste | 2018-02-12 | 2018-02-23 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2753604710 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27536047 | NON-SPARES | 10 | 3 | RTN | V9251111522400 | 1STR*10662 | NA | 9589 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-21 | NA | 100% | 2018-02-09 | 100% | NA | NA | 100% |  |  | 2017-11-27 | 2018-02-21 | Sous-poste | Sous-poste | 2017-11-30 | 2018-02-26 | 2018-02-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2765743610 | 2018-01-15 | FABRICATION | SATAIR | 301 | 27657436 | NON-SPARES | 10 | 1 | RTN | D9551030100295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-28 | 2018-02-22 | Sous-poste | Sous-poste | 2018-03-05 | 2018-02-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 8 | 2 | 2018 | 0.36 | 5.0118 | 1.253 | 6.2648 | COL | 0 | 0
2765743710 | 2018-01-15 | FABRICATION | SATAIR | 500 | 27657437 | NON-SPARES | 10 | 1 | RTN | D9551050000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-28 | 2018-02-22 | Sous-poste | Sous-poste | 2018-03-05 | 2018-02-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 8 | 2 | 2018 | 0.66 | 5.0503 | 1.2626 | 6.3129 | COL | 0 | 0
2753545110 | 0 | FABRICATION | SATAIR | JACK ASSY | 27535451 | NON-SPARES | 10 | 6 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-11-10 | 2018-02-22 | Sous-poste | Sous-poste | 2017-11-15 | 2018-02-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 1.1196 | 9.2256 | 0.15376 | 9.3794 | COL | 0 | 0
490003435510 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900034355 | NON-SPARES | 10 | 3 | EXP | S9251059600000 | 3STR*00944 | NA | 11160 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-22 | NA | 100% | 2018-02-20 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-02-22 | Sous-poste | Sous-poste | 2018-02-12 | 2018-02-27 | 2018-02-27 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003435520 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE AVANT 23VU | 4900034355 | NON-SPARES | 20 | 3 | EXP | S9251165200200 | 1STR*10664 | NA | 11160 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-22 | NA | 100% | 2018-02-20 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-02-22 | Sous-poste | Sous-poste | 2018-02-12 | 2018-02-27 | 2018-02-27 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003435530 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900034355 | NON-SPARES | 30 | 3 | EXP | S9251059700000 | 3STR*00945 | NA | 11160 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-22 | NA | 100% | 2018-02-20 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-02-22 | Sous-poste | Sous-poste | 2018-02-12 | 2018-02-27 | 2018-02-27 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27571271 | 0 | FABRICATION | SATAIR | JACK | 27571271 | NON-SPARES |  | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-11-10 | 2018-02-23 | Sous-poste | Sous-poste | 2017-11-15 | 2018-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2757129610 | 0 | FABRICATION | SATAIR | JACK | 27571296 | NON-SPARES | 10 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 9296 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-02-22 | 100% | NA | NA | 5.556% |  |  | 2017-11-10 | 2018-02-23 | Sous-poste | Sous-poste | 2017-11-15 | 2018-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2759524110 | 0 | FABRICATION | SATAIR | JACK | 27595241 | NON-SPARES | 10 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 9296 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-02-22 | 100% | NA | NA | 5.556% |  |  | 2017-12-01 | 2018-02-23 | Sous-poste | Sous-poste | 2017-12-06 | 2018-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
27503253 | 2017-11-06 | FABRICATION | SATAIR | JACK | 27503253 | NON-SPARES |  | 2 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-31 | 2018-02-23 | Sous-poste | Sous-poste | 2018-02-05 | 2018-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 8 | 2 | 2018 | 0 | 4.3372 | 0.54215 | 4.8793 | COL | 0 | 0
2766227710 | 0 | FABRICATION | SATAIR | JACK | 27662277 | NON-SPARES | 10 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 11000 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-02-22 | 100% | NA | NA | 5.556% |  |  | 2018-02-14 | 2018-02-23 | Sous-poste | Sous-poste | 2018-02-18 | 2018-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 8 | 2 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2763987410 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27639874 | NON-SPARES | 10 | 3 | EXP | V9251111522400 | 1STR*10662 | NA | 10490 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-23 | NA | 100% | 2018-02-16 | 100% | NA | NA | 100% |  |  | 2018-01-16 | 2018-02-23 | Sous-poste | Sous-poste | 2018-01-19 | 2018-02-28 | 2018-02-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2761346210 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27613462 | NON-SPARES | 10 | 10 | RTN | D9251794200000 | 1STR*10670 | NA | 8188 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-23 | NA | 100% | 2018-02-05 | 100% | NA | NA | 100% |  |  | 2018-02-12 | 2018-02-23 | Sous-poste | Sous-poste | 2018-02-15 | 2018-02-28 | 2018-02-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 8 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2767243910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27672439 | NON-SPARES | 10 | 1 | EXP | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-26 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-02-26 | 2018-02-26 | Sous-poste | Sous-poste | 2018-03-01 | 2018-03-01 | 2018-03-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2767244010 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27672440 | NON-SPARES | 10 | 1 | EXP | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-26 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-02-26 | 2018-02-26 | Sous-poste | Sous-poste | 2018-03-01 | 2018-03-01 | 2018-03-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763722210 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27637222 | NON-SPARES | 10 | 2 | RTN | D9251794600000 | 1STR*10671 | NA | 10413 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-27 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-02-27 | Sous-poste | Sous-poste | 2018-03-19 | 2018-03-02 | 2018-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763722410 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27637224 | NON-SPARES | 10 | 2 | RTN | D9251794200000 | 1STR*10670 | NA | 10413 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-27 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-02-27 | Sous-poste | Sous-poste | 2018-03-19 | 2018-03-02 | 2018-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763850810 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27638508 | NON-SPARES | 10 | 2 | RTN | D9251794200000 | 1STR*10670 | NA | 10413 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-27 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-02-27 | Sous-poste | Sous-poste | 2018-03-19 | 2018-03-02 | 2018-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2763548510 | 2014-01-01 |  | TBD |  | 27635485 | NON-SPARES | 10 | 123 | RTN | EN2997SE61212BN |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-17 | 2018-02-27 | Sous-poste | Sous-poste | 2018-01-22 | 2018-03-02 | 2018-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2762685310 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27626853 | NON-SPARES | 10 | 2 | RTN | A9252236000000 | 1STR*01447 | NA | 10157 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-28 | NA | 100% | 2018-01-19 | 100% | NA | NA | 100% |  |  | 2018-02-28 | 2018-02-28 | Sous-poste | Sous-poste | 2018-03-04 | 2018-03-04 | 2018-03-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003410910 | 2014-01-01 | HA/REVENTE | STELIA | RONDELLE | 4900034109 | NON-SPARES | 10 | 15 | RTN | S0003012600000 | IS0013828S | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-02-28 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-02-28 | 2018-02-28 | Sous-poste | Sous-poste | 2018-03-05 | 2018-03-05 | 2018-03-05 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 2 | 2018 | 1 | 2014 | 9 | 2 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2763437310 | 2017-12-15 | FABRICATION | SATAIR | 108 | 27634373 | NON-SPARES | 10 | 1 | AOG | D9550010802895 | 0 | NON PRESENT INDUS | N/A | EFD990001 |  |  |  | 0% | 0% | 0% | 100% | 0 | 100% | 100% | 2018-03-01 | 100% | NA | NA | 5.556% |  |  | 2018-01-04 | 2018-03-01 | Sous-poste | Sous-poste | 2018-01-08 | 2018-03-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2017 | 9 | 3 | 2018 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
E8791708L10 | 2018-02-05 | FABRICATION | AD&S | 34 | E8791708L | NON-SPARES | 10 | 1 | AOG | MB136ABAAAAC | IS0032208M | NON PRESENT INDUS | N/A | LTE990001 |  |  |  | 0% | 0% | 0% | 100% | 0 | 100% | 100% | 2018-03-01 | 100% | NA | NA | 5.556% |  |  | 2018-02-08 | 2018-03-01 | Sous-poste | Sous-poste | 2018-02-10 | 2018-03-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 2 | 2018 | 9 | 3 | 2018 | 0.205 | 3.2522 | 0.81305 | 4.0653 | LAB | 0 | 0
E9375445L10 | 0 | FABRICATION | AD&S | 51 | E9375445L | NON-SPARES | 10 | 1 | AOG | MB043ABAAAAB | IS0032575M | NON PRESENT INDUS | 10740 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-01 | 100% | NA | NA | 5.556% |  |  | 2018-02-13 | 2018-03-01 | Sous-poste | Sous-poste | 2018-02-15 | 2018-03-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 9 | 3 | 2018 | 0.205 | 3.3066 | 0.82665 | 4.1333 | LAB | 0 | 0
490003341910 | 0 | FABRICATION | STELIA | ENS. EQUIPEMENT 61VU | 4900033419 | NON-SPARES | 10 | 6 | AOG | S9251585900000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-12-15 | 2018-03-05 | Sous-poste | Sous-poste | 2017-12-19 | 2018-03-07 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2018 | 1.8 | 100.065 | 4.1694 | 104.2344 | NA | 0 | 0
2769452510 | 0 | FABRICATION | SATAIR | 27 | 27694525 | NON-SPARES | 10 | 5 | AOG | D9551002700495 | 0 | NON PRESENT INDUS | 11859 | LTE990001 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-07 | 100% | NA | NA | 5.556% |  |  | 2018-02-22 | 2018-03-07 | Sous-poste | Sous-poste | 2018-02-26 | 2018-03-09 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2018 | 1.025 | 24.5865 | 1.2293 | 25.8158 | COL | 0 | 0
630051692510 | 2018-02-28 | FABRICATION | STELIA | FAISCEAU GENERATION (ATR42) | 6300516925 | NON-SPARES | 10 | 1 | AOG | S9110125900195 | 0 | NON PRESENT INDUS | 11939 | Z70052-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-07 | 100% | NA | NA | 5.556% |  |  | 2018-02-28 | 2018-03-07 | Sous-poste | Sous-poste | 2018-03-02 | 2018-03-09 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 2 | 2018 | 10 | 3 | 2018 | 0.205 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
2763851010 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27638510 | NON-SPARES | 10 | 2 | RTN | D9251794600000 | 1STR*10671 | NA | 10413 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-08 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-03-08 | Sous-poste | Sous-poste | 2018-03-19 | 2018-03-13 | 2018-03-13 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2018 | 1 | 2014 | 10 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
PRE_APPRO_FFK | 0 | FABRICATION | STELIA | CÂBLE | PRE_APPRO_FFK | NON-SPARES |  | 1 | AOG | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-13 | 2018-03-09 | Sous-poste | Sous-poste | 2018-03-15 | 2018-03-13 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 10 | 3 | 2018 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490003471420 | 2017-12-12 | HA/REVENTE | STELIA | SUPPORT | 4900034714 | NON-SPARES | 20 | 5 | CRIT | S9251594420000 | 1STR*10668 | NA | 12035 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-03-09 | Sous-poste | Sous-poste | 2018-03-13 | 2018-03-13 | 2018-03-13 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2017 | 10 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003471450 | 2017-12-12 | HA/REVENTE | STELIA | SUPPORT | 4900034714 | NON-SPARES | 50 | 4 | CRIT | S9251597520000 | 1STR*10667 | NA | 12035 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-03-09 | Sous-poste | Sous-poste | 2018-03-13 | 2018-03-13 | 2018-03-13 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2017 | 10 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2769105510 | 2018-02-19 | FABRICATION | SATAIR | HARNESS ASSY CABLE | 27691055 | NON-SPARES | 10 | 1 | AOG | L9297725700000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-14 | 2018-03-12 | Sous-poste | Sous-poste | 2018-03-16 | 2018-03-14 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 2 | 2018 | 11 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770605310 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27706053 | NON-SPARES | 10 | 25 | AOG | F0003003000000 | IS0032144M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-08 | 2018-03-13 | Sous-poste | Sous-poste | 2018-03-12 | 2018-03-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 11 | 3 | 2018 | 0.0625 | 2.795 | 0.01118 | 2.8062 | NA | 0 | 0
2762579610 | 0 | FABRICATION | SATAIR | 463 | 27625796 | NON-SPARES | 10 | 1 | AOG | A9551046300196 | 0 | NON PRESENT INDUS | 10145 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-14 | 100% | NA | NA | 5.556% |  |  | 2017-12-05 | 2018-03-14 | Sous-poste | Sous-poste | 2017-12-07 | 2018-03-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 11 | 3 | 2018 | 0.205 | 3.2916 | 0.8229 | 4.1145 | COL | 0 | 0
2766222410 | 0 | FABRICATION | SATAIR | 56 | 27662224 | NON-SPARES | 10 | 1 | RTN | D9550005600295 | 0 | NON PRESENT INDUS | 10985 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-13 | 100% | NA | NA | 5.556% |  |  | 2018-02-07 | 2018-03-14 | Sous-poste | Sous-poste | 2018-02-11 | 2018-03-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 11 | 3 | 2018 | 0.205 | 1.8637 | 0.46593 | 2.3296 | COL | 0 | 0
4900033419 | 0 | FABRICATION | STELIA | ENS. EQUIPEMENT 61VU | 4900033419 | NON-SPARES |  | 2 | AOG | S9251585900000 | 0 | NON PRESENT INDUS | 7662 | EFD990004 = > EFD990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-15 | 100% | NA | NA | 5.556% |  |  | 2017-12-15 | 2018-03-15 | Sous-poste | Sous-poste | 2017-12-19 | 2018-03-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 11 | 3 | 2018 | 0.6 | 33.355 | 4.1694 | 37.5244 | NA | 0 | 0
630046499810 | 2018-02-05 | FABRICATION | STELIA | CABLE COAXIAL | 6300464998 | NON-SPARES | 10 | 6 | EXP | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-28 | 2018-03-15 | Sous-poste | Sous-poste | 2018-03-05 | 2018-03-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 2 | 2018 | 11 | 3 | 2018 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
2764035310 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27640353 | NON-SPARES | 10 | 1 | RTN | A9252597000900 | 1STR*01482 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-15 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-15 | 2018-03-15 | Sous-poste | Sous-poste | 2018-03-20 | 2018-03-20 | 2018-03-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2018 | 1 | 2014 | 11 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2754157410 | 0 | FABRICATION | SATAIR | 403 | 27541574 | NON-SPARES | 10 | 1 | RTN | D9550040300395 | 0 | NON PRESENT INDUS | 8066 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-19 | 100% | NA | NA | 5.556% |  |  | 2017-11-14 | 2018-03-20 | Sous-poste | Sous-poste | 2017-11-17 | 2018-03-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 12 | 3 | 2018 | 0.205 | 1.5857 | 0.39643 | 1.9821 | COL | 0 | 0
2757401710 | 0 | FABRICATION | SATAIR | 403 | 27574017 | NON-SPARES | 10 | 1 | RTN | D9550040300395 | 0 | NON PRESENT INDUS | 8066 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-19 | 100% | NA | NA | 5.556% |  |  | 2017-11-28 | 2018-03-20 | Sous-poste | Sous-poste | 2017-12-01 | 2018-03-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 12 | 3 | 2018 | 0.205 | 1.5857 | 0.39643 | 1.9821 | COL | 0 | 0
27621833 | 0 | FABRICATION | SATAIR | 41 | 27621833 | NON-SPARES |  | 1 | AOG | D9551004100195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-12-07 | 2018-03-21 | Sous-poste | Sous-poste | 2017-12-11 | 2018-03-23 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 12 | 3 | 2018 | 0.51 | 7.7869 | 1.9467 | 9.7336 | COL | 0 | 0
PRE_APPRO_FFK10 | 0 | FABRICATION | STELIA | CÂBLE | PRE_APPRO_FFK | NON-SPARES | 10 | 5 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | N/A |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-03-26 | 100% | NA | NA | 5.556% |  |  | 2018-03-27 | 2018-03-21 | Sous-poste | Sous-poste | 2018-03-30 | 2018-03-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 12 | 3 | 2018 | 1.025 | 5 | 0.1 | 5.1 | NA | 0 | 0
490003483310 | 2017-12-12 | HA/REVENTE | STELIA | SUPPLATE FRONT 27VU | 4900034833 | NON-SPARES | 10 | 4 | CRIT | S9251428800100 | 3STR*01418 | NA | 12300 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-22 | 2018-03-22 | Sous-poste | Sous-poste | 2018-03-26 | 2018-03-26 | 2018-03-26 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2017 | 12 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27715466 | 0 | FABRICATION | SATAIR | 613 | 27715466 | NON-SPARES |  | 1 | AOG | WF435ADAAAAC | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-15 | 2018-03-26 | Sous-poste | Sous-poste | 2018-03-19 | 2018-03-28 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 13 | 3 | 2018 | 0.205 | 1.75 | 0.4375 | 2.1875 | LAB | 0 | 0
2772157710 | 2014-01-01 | HA/REVENTE | SATAIR | POTENTIOMETRE | 27721577 | NON-SPARES | 10 | 1 | AOG | ABS2208AP08S | 4CMP*00026 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-28 | NA | 100% | 2018-03-27 | 100% | NA | NA | 100% |  |  | 2018-03-27 | 2018-03-27 | Sous-poste | Sous-poste | 2018-03-29 | 2018-03-29 | 2018-03-29 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 3 | 2018 | 1 | 2014 | 13 | 3 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2761893910 | 0 | FABRICATION | SATAIR | 41 | 27618939 | NON-SPARES | 10 | 1 | RTN | D9551004100195 | 0 | NON PRESENT INDUS | 10052 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-03-26 | 100% | NA | NA | 5.556% |  |  | 2017-12-06 | 2018-03-27 | Sous-poste | Sous-poste | 2017-12-11 | 2018-03-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 13 | 3 | 2018 | 0.51 | 7.7869 | 1.9467 | 9.7336 | COL | 0 | 0
2759972310 | 0 | FABRICATION | SATAIR | 423 | 27599723 | NON-SPARES | 10 | 1 | RTN | A95500423000AA | 0 | NON PRESENT INDUS | 5215 11483 | LTE990001 |  |  |  | 0% | 0% | 0% | 100% | 0 | 100% | 100% | 2018-03-26 | 100% | NA | NA | 5.556% |  |  | 2018-02-02 | 2018-03-27 | Sous-poste | Sous-poste | 2018-02-07 | 2018-03-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 13 | 3 | 2018 | 0.205 | 13.33 | 3.3325 | 16.6625 | COL | 0 | 0
2766824210 | 2014-01-01 | HA/REVENTE | SATAIR | BRACKET | 27668242 | NON-SPARES | 10 | 1 | EXP | A9253116020000 | IS0031653S | NA | 11123 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-27 | NA | 100% | 2018-03-20 | 100% | NA | NA | 100% |  |  | 2018-02-20 | 2018-03-27 | Sous-poste | Sous-poste | 2018-02-23 | 2018-03-30 | 2018-03-30 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 3 | 2018 | 1 | 2014 | 13 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770997710 | 0 | FABRICATION | SATAIR | 27 | 27709977 | NON-SPARES | 10 | 11 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | 11859 | LTE990001 => LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-28 | 100% | NA | NA | 5.556% |  |  | 2018-03-14 | 2018-03-28 | Sous-poste | Sous-poste | 2018-03-16 | 2018-03-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 13 | 3 | 2018 | 2.255 | 54.0903 | 1.2293 | 55.3196 | COL | 0 | 0
490003478310 | 2018-03-15 | FABRICATION | STELIA | 27 | 4900034783 | NON-SPARES | 10 | 1 | EXP | S9251279900057 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | 100% | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-04 | 2018-03-29 | Sous-poste | Sous-poste | 2018-04-09 | 2018-04-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 3 | 2018 | 13 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003476110 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900034761 | NON-SPARES | 10 | 3 | EXP | S9252318000000 | 1STR*02063 | NA | 12111 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-29 | NA | 100% | 2018-03-22 | 100% | NA | NA | 100% |  |  | 2018-03-29 | 2018-03-29 | Sous-poste | Sous-poste | 2018-04-03 | 2018-04-03 | 2018-04-03 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2018 | 1 | 2014 | 13 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
630040890910 | 2018-01-10 | FABRICATION | STELIA | CABLE COAXIAL | 6300408909 | NON-SPARES | 10 | 5 | EXP | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-05 | 2018-03-30 | Sous-poste | Sous-poste | 2018-04-10 | 2018-04-04 |  | 162086_10 | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 13 | 3 | 2018 | 0.963 | 3.7565 | 0.07513 | 3.8316 | NA | 0 | 0
2770223610 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27702236 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-03-30 | NA | 100% | 2018-03-06 | 100% | NA | NA | 100% |  |  | 2018-03-30 | 2018-03-30 | Sous-poste | Sous-poste | 2018-04-04 | 2018-04-04 | 2018-04-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 3 | 2018 | 1 | 2014 | 13 | 3 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2752903910 | 0 | FABRICATION | SATAIR | 22 | 27529039 | NON-SPARES | 10 | 1 | RTN | D9551002200895 | 0 | NON PRESENT INDUS | 7940 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-03-30 | 100% | NA | NA | 5.556% |  |  | 2017-09-19 | 2018-04-02 | Sous-poste | Sous-poste | 2017-09-22 | 2018-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 14 | 4 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2763535910 | 2017-12-15 |  | TBD |  | 27635359 | NON-SPARES | 10 | 119 | RTN | EN2997SE01212AN |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-17 | 2018-04-03 | Sous-poste | Sous-poste | 2018-01-22 | 2018-04-06 | 2018-04-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 12 | 2017 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765668810 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27656688 | NON-SPARES | 10 | 2 | EXP | F9251110800100 | 1STR*10656 | NA | 10800 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-03 | NA | 100% | 2018-03-10 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-04-03 | Sous-poste | Sous-poste | 2018-02-11 | 2018-04-06 | 2018-04-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765669110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27656691 | NON-SPARES | 10 | 1 | EXP | F9251110801200 | 1STR*00294 | NA | 10800 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-03 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-04-03 | Sous-poste | Sous-poste | 2018-02-11 | 2018-04-06 | 2018-04-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765669010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27656690 | NON-SPARES | 10 | 1 | EXP | F9251110800900 | 1STR*10658 | NA | 10800 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-03 | NA | 100% | 2018-02-19 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-04-03 | Sous-poste | Sous-poste | 2018-02-11 | 2018-04-06 | 2018-04-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765386210 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27653862 | NON-SPARES | 10 | 6 | RTN | D9251794200000 | 1STR*10670 | NA | 10413 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-04 | NA | 100% | 2018-03-28 | 100% | NA | NA | 100% |  |  | 2018-04-04 | 2018-04-04 | Sous-poste | Sous-poste | 2018-04-09 | 2018-04-09 | 2018-04-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2018 | 1 | 2014 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770261810 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27702618 | NON-SPARES | 10 | 2 | AOG | F9251110800500 | 1STR*00297 | NA | 11840 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-09 | NA | 100% | 2018-04-05 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-06 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-10 | 2018-04-10 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 14 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003341910 | 0 | FABRICATION | STELIA | ENS. EQUIPEMENT 61VU | 4900033419 | NON-SPARES | 10 | 4 | AOG | S9251585900000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-12-15 | 2018-04-09 | Sous-poste | Sous-poste | 2017-12-19 | 2018-04-11 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 15 | 4 | 2018 | 1.2 | 66.71 | 4.1694 | 70.8794 | NA | 0 | 0
27647806 | 2018-01-03 | FABRICATION | SATAIR | 22 | 27647806 | NON-SPARES |  | 1 | RTN | D9551002200895 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-23 | 2018-04-10 | Sous-poste | Sous-poste | 2018-01-26 | 2018-04-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 15 | 4 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
630035720130 | 2017-12-08 | FABRICATION | STELIA | CABLE COAXIAL | 6300357201 | NON-SPARES | 30 | 6 | EXP | S9110104500295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-01-03 | 2018-04-10 | Sous-poste | Sous-poste | 2018-01-08 | 2018-04-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 12 | 2017 | 15 | 4 | 2018 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
6300406059 | 2018-01-09 | FABRICATION | STELIA | CABLE COAXIAL | 6300406059 | NON-SPARES |  | 7 | EXP | S9110104500295 | 0 | NON PRESENT INDUS | 10711 | Z35551-1 => Z35551-7 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-04-09 | 100% | NA | NA | 5.556% |  |  | 2018-04-04 | 2018-04-10 | Sous-poste | Sous-poste | 2018-04-09 | 2018-04-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 15 | 4 | 2018 | 1.3482 | 5.2591 | 0.07513 | 5.3342 | NA | 0 | 0
630056116110 | 2018-03-21 | FABRICATION | STELIA | 61 | 6300561161 | NON-SPARES | 10 | 2 | CRIT | S9550061144495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-26 | 2018-04-11 | Sous-poste | Sous-poste | 2018-03-28 | 2018-04-13 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 3 | 2018 | 15 | 4 | 2018 | 0.41 | 2.685 | 0.33563 | 3.0206 | LAB | 0 | 0
27709977 | 0 | FABRICATION | SATAIR | 27 | 27709977 | NON-SPARES |  | 11 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-14 | 2018-04-13 | Sous-poste | Sous-poste | 2018-03-16 | 2018-04-17 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 15 | 4 | 2018 | 2.255 | 54.0903 | 1.2293 | 55.3196 | COL | 0 | 0
2770262110 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27702621 | NON-SPARES | 10 | 4 | AOG | F9251445920000 | 1STR*01520 | NA | 11840 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-16 | NA | 100% | 2018-04-12 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-13 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-17 | 2018-04-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 15 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003472110 | 2014-01-01 | HA/REVENTE | STELIA | PRISE SUP 82 VU | 4900034721 | NON-SPARES | 10 | 5 | AOG | S9251596820000 | 1STR*10666 | NA | 12107 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-16 | NA | 100% | 2018-04-13 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-13 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-17 | 2018-04-17 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 15 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27693188006 | 0 | FABRICATION | SATAIR | 301 | 27693188 | NON-SPARES | 006 | 3 | RTN | D9551030100296 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-14 | 2018-04-13 | Sous-poste | Sous-poste | 2018-03-19 | 2018-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 15 | 4 | 2018 | 1.08 | 15.0354 | 1.253 | 16.2883 | COL | 0 | 0
27693195 | 0 | FABRICATION | SATAIR | 500 | 27693195 | NON-SPARES |  | 3 | RTN | D9551050000296 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-14 | 2018-04-13 | Sous-poste | Sous-poste | 2018-03-19 | 2018-04-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 15 | 4 | 2018 | 1.98 | 15.1509 | 1.2626 | 16.4135 | COL | 0 | 0
2768732320 | 0 | FABRICATION | SATAIR | JACK | 27687323 | NON-SPARES | 20 | 3 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-07 | 2018-04-17 | Sous-poste | Sous-poste | 2018-03-12 | 2018-04-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2018 | 0 | 6.5058 | 0.54215 | 7.0479 | COL | 0 | 0
2765944510 | 2014-01-01 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 27659445 | NON-SPARES | 10 | 1 | EXP | D9251863200000 | 1STR*10676 | NA | 10880 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-17 | NA | 100% | 2018-03-26 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-04-17 | Sous-poste | Sous-poste | 2018-02-11 | 2018-04-20 | 2018-04-20 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 16 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2766824410 | 2014-01-01 | HA/REVENTE | SATAIR | HINGE | 27668244 | NON-SPARES | 10 | 1 | EXP | A9253116220000 | IS0031676S | NA | 11123 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-17 | NA | 100% | 2018-04-12 | 100% | NA | NA | 100% |  |  | 2018-02-20 | 2018-04-17 | Sous-poste | Sous-poste | 2018-02-23 | 2018-04-20 | 2018-04-20 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 16 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770997710 | 0 | FABRICATION | SATAIR | 27 | 27709977 | NON-SPARES | 10 | 11 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | 11859 | LTE990001 => LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-03-28 | 100% | NA | NA | 5.556% |  |  | 2018-03-14 | 2018-04-18 | Sous-poste | Sous-poste | 2018-03-16 | 2018-04-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2018 | 2.255 | 54.0903 | 1.2293 | 55.3196 | COL | 0 | 0
630056116120 | 2018-04-05 | FABRICATION | STELIA | 61 | 6300561161 | NON-SPARES | 20 | 2 | CRIT | S9550061144495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-26 | 2018-04-18 | Sous-poste | Sous-poste | 2018-03-28 | 2018-04-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 4 | 2018 | 16 | 4 | 2018 | 0.41 | 2.685 | 0.33563 | 3.0206 | LAB | 0 | 0
2770262210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27702622 | NON-SPARES | 10 | 2 | AOG | F9251485300000 | 1STR*01521 | NA | 11840 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-19 | NA | 100% | 2018-04-17 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-18 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-20 | 2018-04-20 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 4 | 2018 | 1 | 2014 | 16 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2772073510 | 0 | FABRICATION | SATAIR | 313 | 27720735 | NON-SPARES | 10 | 1 | AOG | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 12473 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-04-20 | 100% | NA | NA | 5.556% |  |  | 2018-03-22 | 2018-04-20 | Sous-poste | Sous-poste | 2018-03-26 | 2018-04-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 16 | 4 | 2018 | 0.51 | 3.85 | 0.9625 | 4.8125 | LAB | 0 | 0
630058633810 | 2018-04-03 | FABRICATION | STELIA | 61 | 6300586338 | NON-SPARES | 10 | 7 | EXP | S9550061144495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-27 | 2018-04-23 | Sous-poste | Sous-poste | 2018-05-02 | 2018-04-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 17 | 4 | 2018 | 1.435 | 9.3975 | 0.33563 | 9.7331 | LAB | 0 | 0
27686986008 | 0 | FABRICATION | SATAIR | HARNAIS 1 P2T2 | 27686986 | NON-SPARES | 008 | 8 | RTN | F7161001200001 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-17 | 2018-04-23 | Sous-poste | Sous-poste | 2018-04-20 | 2018-04-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 17 | 4 | 2018 | 1.5432 | 16.6552 | 0.52048 | 17.1757 | COL | 0 | 0
2772355010 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27723550 | NON-SPARES | 10 | 3 | EXP | A9252236000000 | 1STR*01447 | NA | 12532 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-04-23 | NA | 100% | 2018-04-16 | 100% | NA | NA | 100% |  |  | 2018-04-23 | 2018-04-23 | Sous-poste | Sous-poste | 2018-04-26 | 2018-04-26 | 2018-04-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 4 | 2018 | 1 | 2014 | 17 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27695127 | 0 | FABRICATION | SATAIR | 56 | 27695127 | NON-SPARES |  | 1 | RTN | D9550005600295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-20 | 2018-04-24 | Sous-poste | Sous-poste | 2018-03-23 | 2018-04-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 17 | 4 | 2018 | 0.205 | 1.8637 | 0.46593 | 2.3296 | COL | 0 | 0
630048873310 | 2018-02-15 | FABRICATION | STELIA | FAISCEAU | 6300488733 | NON-SPARES | 10 | 1 | EXP | S9110169500395 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-12 | 2018-04-24 | Sous-poste | Sous-poste | 2018-03-15 | 2018-04-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 2 | 2018 | 17 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
630056116120 | 2018-04-05 | FABRICATION | STELIA | 61 | 6300561161 | NON-SPARES | 20 | 2 | CRIT | S9550061144495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-26 | 2018-04-25 | Sous-poste | Sous-poste | 2018-03-28 | 2018-04-27 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 4 | 2018 | 17 | 4 | 2018 | 0.41 | 2.685 | 0.33563 | 3.0206 | LAB | 0 | 0
490003471410 | 2017-11-11 | HA/REVENTE | STELIA | PLAQUE 5VU(MARRON) | 4900034714 | NON-SPARES | 10 | 5 | CRIT | S9251353500100 | 3STR*00931 | NA | 12035 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-25 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-27 | 2018-04-27 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2017 | 17 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003471430 | 2017-11-11 | HA/REVENTE | STELIA | SUPPORT | 4900034714 | NON-SPARES | 30 | 5 | CRIT | S9251598400100 | 1STR*01600 | NA | 12035 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-25 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-27 | 2018-04-27 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2017 | 17 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003471440 | 2017-11-11 | HA/REVENTE | STELIA | SUPPORT | 4900034714 | NON-SPARES | 40 | 5 | CRIT | S9251598400000 | 1STR*01599 | NA | 12035 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-03-09 | 2018-04-25 | Sous-poste | Sous-poste | 2018-03-13 | 2018-04-27 | 2018-04-27 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2017 | 17 | 4 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771722310 | 2018-03-21 | HA/REVENTE | SATAIR | TUBE | 27717223 | NON-SPARES | 10 | 1 | AOG | F9251110800800 | 1STR*00292 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-03 | NA | 100% | 2018-04-24 | 100% | NA | NA | 100% |  |  | 2018-04-02 | 2018-05-02 | Sous-poste | Sous-poste | 2018-04-04 | 2018-05-04 | 2018-05-04 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 5 | 2018 | 3 | 2018 | 18 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771872010 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27718720 | NON-SPARES | 10 | 17 | EXP | D9251095400000 | IS0053354S | NA | 12405 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-02 | NA | 100% | 2018-04-23 | 100% | NA | NA | 100% |  |  | 2018-04-18 | 2018-05-02 | Sous-poste | Sous-poste | 2018-04-21 | 2018-05-07 | 2018-05-07 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 18 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771872110 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27718721 | NON-SPARES | 10 | 17 | EXP | D9251095600000 | IS0053509S | NA | 12405 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-02 | NA | 100% | 2018-04-23 | 100% | NA | NA | 100% |  |  | 2018-04-18 | 2018-05-02 | Sous-poste | Sous-poste | 2018-04-21 | 2018-05-07 | 2018-05-07 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 18 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27728167 | 0 | FABRICATION | SATAIR | HARNAIS 2 P2T2 | 27728167 | NON-SPARES |  | 2 | CRIT | F7161001300001 | 0 | NON PRESENT INDUS | 12277 | 004486 -1 => 004486-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-05-03 | 100% | NA | NA | 5.556% |  |  | 2018-07-04 | 2018-05-03 | Sous-poste | Sous-poste | 2018-07-06 | 2018-05-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 18 | 5 | 2018 | 0.3816 | 6.1338 | 0.76672 | 6.9005 | COL | 0 | 0
4900034946 | 2018-04-06 | FABRICATION | STELIA | 101 | 4900034946 | NON-SPARES |  | 1 | CRIT | S9251282200056 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-06 | 2018-05-03 | Sous-poste | Sous-poste | 2018-04-10 | 2018-05-07 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 4 | 2018 | 18 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 27 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279900051 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-03 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 18 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777423110 | 2014-01-01 | HA/REVENTE | SATAIR | POTENTIOMETRE | 27774231 | NON-SPARES | 10 | 3 | AOG | ABS2208AP08S | 4CMP*00026 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-10 | NA | 100% | 2018-05-07 | 100% | NA | NA | 100% |  |  | 2018-05-03 | 2018-05-09 | Sous-poste | Sous-poste | 2018-05-07 | 2018-05-11 | 2018-05-11 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003492210 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 122VU | 4900034922 | NON-SPARES | 10 | 4 | CRIT | S9251090300100 | 1STR*10179 | NA | 12628 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-10 | NA | 100% | 2018-05-18 | 100% | NA | NA | 100% |  |  | 2018-05-09 | 2018-05-09 | Sous-poste | Sous-poste | 2018-05-11 | 2018-05-11 | 2018-05-11 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771731510 | 2018-03-21 | HA/REVENTE | SATAIR | TUBE | 27717315 | NON-SPARES | 10 | 1 | AOG | F9251110801200 | 1STR*00294 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-14 | NA | 100% | 2018-04-24 | 100% | NA | NA | 100% |  |  | 2018-04-02 | 2018-05-11 | Sous-poste | Sous-poste | 2018-04-04 | 2018-05-15 | 2018-05-15 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 5 | 2018 | 3 | 2018 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27666566 | 0 | FABRICATION | SATAIR | 613 | 27666566 | NON-SPARES |  | 1 | EXP | WF435ADAAAAC | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-18 | 2018-05-11 | Sous-poste | Sous-poste | 2018-04-23 | 2018-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 19 | 5 | 2018 | 0.205 | 1.75 | 0.4375 | 2.1875 | LAB | 0 | 0
2769006810 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27690068 | NON-SPARES | 10 | 0 | EXP | V9251111522200 | 1STR*10734 | NA | 11610 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-11 | NA | 100% | 2018-04-09 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-05-11 | Sous-poste | Sous-poste | 2018-03-18 | 2018-05-16 | 2018-05-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2769007010 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27690070 | NON-SPARES | 10 | 0 | EXP | V9251111522600 | 1STR*10751 | NA | 11610 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-11 | NA | 100% | 2018-04-09 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-05-11 | Sous-poste | Sous-poste | 2018-03-18 | 2018-05-16 | 2018-05-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2769006910 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27690069 | NON-SPARES | 10 | 0 | EXP | V9251111520600 | 1STR*10733 | NA | 11610 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-11 | NA | 100% | 2018-04-09 | 100% | NA | NA | 100% |  |  | 2018-03-14 | 2018-05-11 | Sous-poste | Sous-poste | 2018-03-18 | 2018-05-16 | 2018-05-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 19 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2777990010 | 2018-05-11 | FABRICATION | SATAIR | 27 | 27779900 | NON-SPARES | 10 | 9 | AOG | D9551002700695 | IS0032097M | NON PRESENT INDUS | 13543 | LTE990034 => LTE990042 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-05-16 | 100% | NA | NA | 5.556% |  |  | 2018-05-16 | 2018-05-14 | Sous-poste | Sous-poste | 2018-05-18 | 2018-05-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 5 | 2018 | 20 | 5 | 2018 | 1.845 | 44.2557 | 1.2293 | 45.485 | COL | 0 | 0
2770605810 | 0 | FABRICATION | SATAIR | PLATE ASSY | 27706058 | NON-SPARES | 10 | 2 | RTN | F9252020200000 | IS0032657M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-03-14 | 2018-05-15 | Sous-poste | Sous-poste | 2018-03-19 | 2018-05-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 20 | 5 | 2018 | 0 | 0.3578 | 0.01789 | 0.37569 | NA | 0 | 0
2768878010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27688780 | NON-SPARES | 10 | 1 | RTN | F9251110801200 | 1STR*00294 | NA | 11578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-15 | NA | 100% | 2018-04-27 | 100% | NA | NA | 100% |  |  | 2018-05-02 | 2018-05-15 | Sous-poste | Sous-poste | 2018-05-07 | 2018-05-18 | 2018-05-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2768877810 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27688778 | NON-SPARES | 10 | 1 | RTN | F9251110800900 | 1STR*10658 | NA | 11578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-15 | NA | 100% | 2018-05-09 | 100% | NA | NA | 100% |  |  | 2018-05-02 | 2018-05-15 | Sous-poste | Sous-poste | 2018-05-05 | 2018-05-18 | 2018-05-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2768877610 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27688776 | NON-SPARES | 10 | 2 | RTN | F9251110800100 | 1STR*10656 | NA | 11578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-15 | NA | 100% | 2018-05-09 | 100% | NA | NA | 100% |  |  | 2018-05-02 | 2018-05-15 | Sous-poste | Sous-poste | 2018-05-05 | 2018-05-18 | 2018-05-18 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771722510 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717225 | NON-SPARES | 10 | 1 | RTN | F9251110800800 | 1STR*00292 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-16 | NA | 100% | 2018-05-14 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-05-16 | Sous-poste | Sous-poste | 2018-05-20 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2769111710 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27691117 | NON-SPARES | 10 | 6 | RTN | D9251095600000 | IS0053509S | NA | 11653 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-16 | NA | 100% | 2018-05-04 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-05-16 | Sous-poste | Sous-poste | 2018-05-20 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2769111810 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27691118 | NON-SPARES | 10 | 6 | RTN | D9251095400000 | IS0053354S | NA | 11653 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-16 | NA | 100% | 2018-05-04 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-05-16 | Sous-poste | Sous-poste | 2018-05-20 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771725010 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 27717250 | NON-SPARES | 10 | 1 | RTN | F9251485400000 | 1STR*10825 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-16 | NA | 100% | 2018-05-14 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-05-16 | Sous-poste | Sous-poste | 2018-05-20 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771731310 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717313 | NON-SPARES | 10 | 1 | RTN | F9251110801200 | 1STR*00294 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-16 | NA | 100% | 2018-05-14 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-05-16 | Sous-poste | Sous-poste | 2018-05-20 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771724910 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 27717249 | NON-SPARES | 10 | 1 | AOG | F9251485400000 | 1STR*10825 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-18 | NA | 100% | 2018-05-14 | 100% | NA | NA | 100% |  |  | 2018-04-02 | 2018-05-17 | Sous-poste | Sous-poste | 2018-04-04 | 2018-05-20 | 2018-05-20 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 5 | 2018 | 1 | 2014 | 20 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2778606610 | 2014-01-01 | HA/REVENTE | SATAIR | CONNECTEUR ARINC 600 | 27786066 | NON-SPARES | 10 | 1 | AOG | E0165D13A27X | 1CON*00242 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-22 | NA | 100% | 2018-05-17 | 100% | NA | NA | 100% |  |  | 2018-05-21 | 2018-05-21 | Sous-poste | Sous-poste | 2018-05-23 | 2018-05-23 | 2018-05-23 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E8799209L3 | 2018-05-09 | FABRICATION | AD&S | 12 | E8799209L | NON-SPARES | 3 | 1 | AOG | MB170ACAAAAB | IS0032212M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-05-18 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-22 | 2018-05-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 5 | 2018 | 21 | 5 | 2018 | 0.205 | 8.3333 | 2.0833 | 10.4166 | LAB | 0 | 0
2777361710 | 2018-05-07 | FABRICATION | SATAIR | 116 | 27773617 | NON-SPARES | 10 | 2 | CRIT | D9551011600195 | 0 | NON PRESENT INDUS | 13472 | LTE990001 => LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-05-29 | 100% | NA | NA | 5.556% |  |  | 2018-05-29 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-31 | 2018-05-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 5 | 2018 | 21 | 5 | 2018 | 0.41 | 2.8 | 0.35 | 3.15 | COL | 0 | 0
4900035095 | 2018-04-19 | FABRICATION | STELIA | 29 | 4900035095 | NON-SPARES |  | 1 | EXP | S9251280100054 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 26 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279800054 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 25 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279700054 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 24 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279600054 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 22 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279400054 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 23 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279500055 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509510 | 2018-04-19 | FABRICATION | STELIA | 27 | 4900035095 | NON-SPARES | 10 | 1 | EXP | S9251279900057 | 0 | NON PRESENT INDUS | 13195 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-05-08 | 100% | NA | NA | 5.556% |  |  | 2018-05-09 | 2018-05-25 | Sous-poste | Sous-poste | 2018-05-14 | 2018-05-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2018 | 21 | 5 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
DEPANNAGEN/A | 2014-01-01 | HA/REVENTE | SATAIR | CONNECTEUR | DEPANNAGE | NON-SPARES | N/A | 2 |  | EN2997RS61415BN | 1CON*06435 | NA | 13839 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-29 | NA | 100% | 2018-05-24 | 100% | NA | NA | 100% |  |  | 2018-05-29 | 2018-05-29 | Sous-poste | Sous-poste | 2018-06-01 | 2018-06-01 | 2018-06-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 5 | 2018 | 1 | 2014 | 22 | 5 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2778043810 | 0 | FABRICATION | SATAIR | WIRE-BONDING | 27780438 | NON-SPARES | 10 | 1 | EXP | F0003008100000 | IS0032145M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-06-06 | 2018-05-31 | Sous-poste | Sous-poste | 2018-06-10 | 2018-06-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 22 | 5 | 2018 | 0.2059 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2771721910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717219 | NON-SPARES | 10 | 2 | RTN | F9251110800500 | 1STR*00297 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-01 | NA | 100% | 2018-05-28 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-06-01 | Sous-poste | Sous-poste | 2018-05-20 | 2018-06-06 | 2018-06-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 22 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
E8799546L10 | 2018-05-14 | FABRICATION | AD&S | 39 | E8799546L | NON-SPARES | 10 | 1 | AOG | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 13693 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-06-06 | 100% | NA | NA | 5.556% |  |  | 2018-06-06 | 2018-06-04 | Sous-poste | Sous-poste | 2018-06-08 | 2018-06-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 5 | 2018 | 23 | 6 | 2018 | 0.205 | 4.38 | 1.095 | 5.475 | LAB | 0 | 0
DEPANNAGEN/A | 2014-01-01 | HA/REVENTE | SATAIR | CONNECTEUR | DEPANNAGE | NON-SPARES | N/A | 3 |  | EN2997RS61415AN | 1CON*01377 | NA | 13839 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-05-29 | NA | 100% | 2018-05-24 | 100% | NA | NA | 100% |  |  | 2018-05-29 | 2018-06-06 | Sous-poste | Sous-poste | 2018-06-01 | 2018-06-11 | 2018-06-11 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 23 | 6 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630058237810 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 6300582378 | NON-SPARES | 10 | 6 |  | F9251110800500 | 1STR*00297 | NA | 13332 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-07 | NA | 100% | 2018-06-11 | 100% | NA | NA | 100% |  |  | 2018-04-25 | 2018-06-07 | Sous-poste | Sous-poste | 2018-04-29 | 2018-06-12 | 2018-06-12 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 23 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2765668910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27656689 | NON-SPARES | 10 | 1 | EXP | F9251110800400 | 1STR*10657 | NA | 10800 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-07 | NA | 100% | 2018-06-05 | 100% | NA | NA | 100% |  |  | 2018-02-07 | 2018-06-07 | Sous-poste | Sous-poste | 2018-02-11 | 2018-06-12 | 2018-06-12 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 23 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2768877710 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27688777 | NON-SPARES | 10 | 1 | RTN | F9251110800400 | 1STR*10657 | NA | 11578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-07 | NA | 100% | 2018-06-05 | 100% | NA | NA | 100% |  |  | 2018-05-02 | 2018-06-07 | Sous-poste | Sous-poste | 2018-05-05 | 2018-06-12 | 2018-06-12 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 23 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003535310 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900035353 | NON-SPARES | 10 | 2 | EXP | S9252318000000 | 1STR*02063 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-11 | NA | 100% | 2018-06-04 | 100% | NA | NA | 100% |  |  | 2018-06-11 | 2018-06-11 | Sous-poste | Sous-poste | 2018-06-14 | 2018-06-14 | 2018-06-14 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2018 | 1 | 2014 | 24 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770605910 | 0 | FABRICATION | SATAIR | PLATE ASSY | 27706059 | NON-SPARES | 10 | 1 | RTN | F9252020200000 | IS0032657M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-17 | 2018-06-12 | Sous-poste | Sous-poste | 2018-04-20 | 2018-06-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 24 | 6 | 2018 | 0 | 0.1789 | 0.01789 | 0.19679 | NA | 0 | 0
2771723810 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27717238 | NON-SPARES | 10 | 4 | RTN | F9251445920000 | 1STR*01520 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-12 | NA | 100% | 2018-05-28 | 100% | NA | NA | 100% |  |  | 2018-06-12 | 2018-06-12 | Sous-poste | Sous-poste | 2018-06-15 | 2018-06-15 | 2018-06-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2018 | 1 | 2014 | 24 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2769104610 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27691046 | NON-SPARES | 10 | 6 | RTN | D9251095400000 | IS0053354S | NA | 11653 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-12 | NA | 100% | 2018-06-20 | 100% | NA | NA | 100% |  |  | 2018-06-27 | 2018-06-12 | Sous-poste | Sous-poste | 2018-07-01 | 2018-06-15 | 2018-06-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2018 | 1 | 2014 | 24 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775348310 | 0 | FABRICATION | SATAIR | HARNESS ASSY CABLE | 27753483 | NON-SPARES | 10 | 1 | AOG | L9297725700000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-16 | 2018-06-13 | Sous-poste | Sous-poste | 2018-04-18 | 2018-06-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 24 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771722110 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717221 | NON-SPARES | 10 | 4 | RTN | F9251110800500 | 1STR*00297 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-14 | NA | 100% | 2018-06-07 | 100% | NA | NA | 100% |  |  | 2018-06-14 | 2018-06-14 | Sous-poste | Sous-poste | 2018-06-19 | 2018-06-19 | 2018-06-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2018 | 1 | 2014 | 24 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2778554710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27785547 | NON-SPARES | 10 | 1 | AOG | D9251805800000 | IS0032777S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-21 | NA | 100% | 2018-06-18 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-06-20 | Sous-poste | Sous-poste | 2018-05-18 | 2018-06-22 | 2018-06-22 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 25 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2778554910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27785549 | NON-SPARES | 10 | 1 | AOG | D9251805700000 | IS0032776S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-21 | NA | 100% | 2018-06-18 | 100% | NA | NA | 100% |  |  | 2018-05-16 | 2018-06-20 | Sous-poste | Sous-poste | 2018-05-18 | 2018-06-22 | 2018-06-22 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 6 | 2018 | 1 | 2014 | 25 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003544310 | 2018-06-05 | FABRICATION | STELIA | CÂBLE | 4900035443 | NON-SPARES | 10 | 4 | EXP | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 053399-1 => 053399-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-06-25 | 100% | NA | NA | 5.556% |  |  | 2018-06-26 | 2018-06-26 | Sous-poste | Sous-poste | 2018-06-29 | 2018-06-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 26 | 6 | 2018 | 0.82 | 4 | 0.1 | 4.1 | NA | 0 | 0
2772519410 | 2018-03-28 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27725194 | NON-SPARES | 10 | 17 | RTN | D9251794600000 | 1STR*10671 | NA | 12561 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-26 | NA | 100% | 2018-06-19 | 100% | NA | NA | 100% |  |  | 2018-05-23 | 2018-06-26 | Sous-poste | Sous-poste | 2018-05-27 | 2018-06-29 | 2018-06-29 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 6 | 2018 | 3 | 2018 | 26 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27245656 | 2016-11-28 | FABRICATION | SATAIR | PLATE | 27245656 | NON-SPARES |  | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-06-27 | 2018-06-27 | Sous-poste | Sous-poste | 2018-06-30 | 2018-06-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2016 | 26 | 6 | 2018 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
27245656 | 2016-11-28 | FABRICATION | SATAIR | PLATE | 27245656 | NON-SPARES |  | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-06-27 | 2018-06-27 | Sous-poste | Sous-poste | 2018-06-30 | 2018-06-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2016 | 26 | 6 | 2018 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
490003521410 | 2018-05-09 | FABRICATION | STELIA | FAISCEAU | 4900035214 | NON-SPARES | 10 | 4 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 053182-1 => 053182-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-06-27 | 100% | NA | NA | 5.556% |  |  | 2018-06-28 | 2018-06-28 | Sous-poste | Sous-poste | 2018-07-03 | 2018-07-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 26 | 6 | 2018 | 0.82 | 2.8 | 0.07 | 2.87 | NA | 0 | 0
2773815010 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 500VU | 27738150 | NON-SPARES | 10 | 50 | RTN | D9251794600000 | 1STR*10671 | NA | 12561 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-06-29 | NA | 100% | 2018-06-22 | 100% | NA | NA | 100% |  |  | 2018-06-29 | 2018-06-29 | Sous-poste | Sous-poste | 2018-07-04 | 2018-07-04 | 2018-07-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 6 | 2018 | 1 | 2014 | 26 | 6 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575590 | 2018-06-21 | FABRICATION | STELIA | 27 | 4900035575 | NON-SPARES | 590 | 1 | EXP | S9251279900052 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-07-06 | 2018-07-02 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 27 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003509210 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE H1 | 4900035092 | NON-SPARES | 10 | 10 | EXP | S9251418100000 | 1STR*10890 | NA | 13143 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-03 | NA | 100% | 2018-05-30 | 100% | NA | NA | 100% |  |  | 2018-06-22 | 2018-07-03 | Sous-poste | Sous-poste | 2018-06-27 | 2018-07-06 | 2018-07-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 27 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2774562510 | 2014-01-01 | HA/REVENTE | SATAIR | DIAPHRAGME | 27745625 | NON-SPARES | 10 | 12 | RTN | V9251111520000 | 1STR*10661 | NA | 12961 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-10 | NA | 100% | 2018-07-05 | 100% | NA | NA | 100% |  |  | 2018-06-27 | 2018-07-10 | Sous-poste | Sous-poste | 2018-07-01 | 2018-07-13 | 2018-07-13 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2773815610 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27738156 | NON-SPARES | 10 | 50 | RTN | D9251794200000 | 1STR*10670 | NA | 12561 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-10 | NA | 100% | 2018-06-22 | 100% | NA | NA | 100% |  |  | 2018-06-29 | 2018-07-10 | Sous-poste | Sous-poste | 2018-07-04 | 2018-07-13 | 2018-07-13 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2772518910 | 2014-01-01 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 27725189 | NON-SPARES | 10 | 17 | RTN | D9251794200000 | 1STR*10670 | NA | 12561 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-10 | NA | 100% | 2018-06-20 | 100% | NA | NA | 100% |  |  | 2018-05-23 | 2018-07-10 | Sous-poste | Sous-poste | 2018-05-27 | 2018-07-13 | 2018-07-13 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362710 | 2018-05-18 | HA/REVENTE | SATAIR | CROSSBEAM ASSY | 27753627 | NON-SPARES | 10 | 5 | RTN | L9251266800001 | 1STR*10883 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362810 | 2018-05-18 | HA/REVENTE | SATAIR | CROSSBEAM | 27753628 | NON-SPARES | 10 | 5 | RTN | L9251266920001 | 1STR*10884 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362910 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753629 | NON-SPARES | 10 | 5 | RTN | L9251267020001 | 1STR*10885 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363110 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753631 | NON-SPARES | 10 | 5 | RTN | L9251267120001 | 1STR*10886 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363210 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753632 | NON-SPARES | 10 | 5 | RTN | L9251267220001 | 1STR*10887 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363410 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753634 | NON-SPARES | 10 | 10 | RTN | L9251267320001 | 1STR*10888 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363510 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753635 | NON-SPARES | 10 | 5 | RTN | L9251267420001 | 1STR*10889 | NA | 0 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-11 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-07-11 | Sous-poste | Sous-poste | 2018-07-15 | 2018-07-15 | 2018-07-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 5 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035558 | 2018-06-19 | FABRICATION | STELIA | 22 | 4900035558 | NON-SPARES |  | 1 | EXP | S9251279400054 | 0 | NON PRESENT INDUS | 14580 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-12 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2018-07-13 | Sous-poste | Sous-poste | 2018-07-02 | 2018-07-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003555810 | 2018-06-21 | FABRICATION | STELIA | 23 | 4900035558 | NON-SPARES | 10 | 1 | EXP | S9251279500055 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-06-27 | 2018-07-13 | Sous-poste | Sous-poste | 2018-07-02 | 2018-07-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035558 | 2018-06-21 | FABRICATION | STELIA | 24 | 4900035558 | NON-SPARES |  | 1 | EXP | S9251279600054 | 0 | NON PRESENT INDUS | 14580 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-12 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2018-07-13 | Sous-poste | Sous-poste | 2018-07-02 | 2018-07-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 28 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035321 | 2018-05-22 | FABRICATION | STELIA | FAISCEAU | 4900035321 | NON-SPARES |  | 3 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 055538-1 => 055538-3 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-07-12 | 100% | NA | NA | 5.556% |  |  | 2018-07-13 | 2018-07-13 | Sous-poste | Sous-poste | 2018-07-18 | 2018-07-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 28 | 7 | 2018 | 0.615 | 2.1 | 0.07 | 2.17 | NA | 0 | 0
490003564010 | 2017-11-11 | HA/REVENTE | STELIA | RAMPE 91VU | 4900035640 | NON-SPARES | 10 | 11 | EXP | S9252333700000 | 1STR*10936 | NA | 15952 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-16 | 2018-07-16 | Sous-poste | Sous-poste | 2018-07-19 | 2018-07-19 | 2018-07-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 29 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003564020 | 2017-11-11 | HA/REVENTE | STELIA | SUPPORT EQUIPE 91VU | 4900035640 | NON-SPARES | 20 | 11 | EXP | S9252333600000 | 1STR*10937 | NA | 15952 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-16 | 2018-07-16 | Sous-poste | Sous-poste | 2018-07-19 | 2018-07-19 | 2018-07-19 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 29 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2781882310 | 2014-01-01 | HA/REVENTE | SATAIR | FLANGE ASSY | 27818823 | NON-SPARES | 10 | 2 | CRIT | D9251127600000 | IS0008826S | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-19 | NA | 100% | 2018-07-12 | 100% | NA | NA | 100% |  |  | 2018-07-18 | 2018-07-18 | Sous-poste | Sous-poste | 2018-07-20 | 2018-07-20 | 2018-07-20 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 7 | 2018 | 1 | 2014 | 29 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27803321 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27803321 | NON-SPARES |  | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 14019 | 055528-1 => 055528-15 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-24 | 100% | NA | NA | 5.556% |  |  | 2018-07-25 | 2018-07-19 | Sous-poste | Sous-poste | 2018-07-30 | 2018-07-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 29 | 7 | 2018 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
2783338310 | 2018-06-26 |  | TBD |  | 27833383 | NON-SPARES | 10 | 2 | EXP | L9251230020100 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-07-23 | 2018-07-23 | Sous-poste | Sous-poste | 2018-07-26 | 2018-07-26 | 2018-07-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27699479 | 0 | FABRICATION | SATAIR | HARNAIS 2 P2T2 | 27699479 | NON-SPARES |  | 2 | RTN | F7161001300001 | 0 | NON PRESENT INDUS | 11974 | Z72243-1 => Z72243-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-23 | 100% | NA | NA | 5.556% |  |  | 2018-07-02 | 2018-07-24 | Sous-poste | Sous-poste | 2018-07-05 | 2018-07-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 30 | 7 | 2018 | 0.3816 | 6.1338 | 0.76672 | 6.9005 | COL | 0 | 0
2771724010 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | ANGLE | 27717240 | NON-SPARES | 10 | 2 | RTN | F9251445920000 | 1STR*01520 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-24 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-07-24 | 2018-07-24 | Sous-poste | Sous-poste | 2018-07-27 | 2018-07-27 | 2018-07-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771725110 | 2014-01-01 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 27717251 | NON-SPARES | 10 | 1 | RTN | F9251485400000 | 1STR*10825 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-24 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-07-24 | 2018-07-24 | Sous-poste | Sous-poste | 2018-07-27 | 2018-07-27 | 2018-07-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771731410 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717314 | NON-SPARES | 10 | 1 | RTN | F9251110801200 | 1STR*00294 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-24 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-07-24 | 2018-07-24 | Sous-poste | Sous-poste | 2018-07-27 | 2018-07-27 | 2018-07-27 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775605510 | 2014-01-01 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27756055 | NON-SPARES | 10 | 2 | AOG | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-26 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-05-04 | 2018-07-25 | Sous-poste | Sous-poste | 2018-05-08 | 2018-07-27 | 2018-07-27 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27851540 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27851540 | NON-SPARES |  | 5 | CRIT | F0003003000000 | IS0032144M | NON PRESENT INDUS | 14019 | 040471-1 => 040471-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-30 | 100% | NA | NA | 5.556% |  |  | 2018-07-30 | 2018-07-26 | Sous-poste | Sous-poste | 2018-08-01 | 2018-07-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 30 | 7 | 2018 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
490003559110 | 2018-06-22 | FABRICATION | STELIA | 101 | 4900035591 | NON-SPARES | 10 | 1 | RTN | S9251282200054 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-07-04 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-09 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035591 | 2018-06-22 | FABRICATION | STELIA | 34 | 4900035591 | NON-SPARES |  | 1 | RTN | S9251280200054 | 0 | NON PRESENT INDUS | 14685 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-04 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-09 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575 | 2018-06-21 | FABRICATION | STELIA | 26 | 4900035575 | NON-SPARES |  | 1 | EXP | S9251279800054 | 0 | NON PRESENT INDUS | 14685 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-06 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575 | 2018-06-21 | FABRICATION | STELIA | 28 | 4900035575 | NON-SPARES |  | 1 | EXP | S9251280000054 | 0 | NON PRESENT INDUS | 14685 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-06 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575 | 2018-06-21 | FABRICATION | STELIA | 29 | 4900035575 | NON-SPARES |  | 1 | EXP | S9251280100054 | 0 | NON PRESENT INDUS | 14685 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-06 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575 | 2018-06-21 | FABRICATION | STELIA | 25 | 4900035575 | NON-SPARES |  | 1 | EXP | S9251279700054 | 0 | NON PRESENT INDUS | 14685 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-06 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035575 | 2018-06-21 | FABRICATION | STELIA | 702 | 4900035575 | NON-SPARES |  | 1 | EXP | S9252309900053 | 0 | NON PRESENT INDUS | 14685 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-25 | 100% | NA | NA | 5.556% |  |  | 2018-07-06 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-11 | 2018-07-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2774933510 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27749335 | NON-SPARES | 10 | 1 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-26 | NA | 100% | 2018-07-19 | 100% | NA | NA | 100% |  |  | 2018-07-26 | 2018-07-26 | Sous-poste | Sous-poste | 2018-07-31 | 2018-07-31 | 2018-07-31 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
6804360 | 2018-07-04 | FABRICATION | AD&S | 49 | 6804360 | NON-SPARES |  | 1 | AOG | MB042ACABAAA | IS0032206M | NON PRESENT INDUS | 15410 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-27 | 100% | NA | NA | 5.556% |  |  | 2018-07-27 | 2018-07-27 | Sous-poste | Sous-poste | 2018-07-31 | 2018-07-31 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 7 | 2018 | 30 | 7 | 2018 | 0.205 | 2.39 | 0.5975 | 2.9875 | LAB | 0 | 0
27768839 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27768839 | NON-SPARES |  | 5 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 13428 | 033841-1 => 033841-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-26 | 100% | NA | NA | 5.556% |  |  | 2018-06-20 | 2018-07-27 | Sous-poste | Sous-poste | 2018-06-25 | 2018-08-01 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 30 | 7 | 2018 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
2771724210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27717242 | NON-SPARES | 10 | 2 | RTN | F9251485300000 | 1STR*01521 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-27 | NA | 100% | 2018-07-25 | 100% | NA | NA | 100% |  |  | 2018-06-12 | 2018-07-27 | Sous-poste | Sous-poste | 2018-06-15 | 2018-08-01 | 2018-08-01 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 30 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27715611 | 0 | FABRICATION | SATAIR | HARNAIS 2 P2T2 | 27715611 | NON-SPARES |  | 2 | CRIT | F7161001300001 | 0 | NON PRESENT INDUS | 12277 | Z93524-1 => Z93524-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-07-30 | 100% | NA | NA | 5.556% |  |  | 2018-07-11 | 2018-07-30 | Sous-poste | Sous-poste | 2018-07-13 | 2018-08-01 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 31 | 7 | 2018 | 0.3816 | 6.1338 | 0.76672 | 6.9005 | COL | 0 | 0
2771724410 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27717244 | NON-SPARES | 10 | 1 | RTN | F9251485300000 | 1STR*01521 | NA | 12417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-30 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-07-24 | 2018-07-30 | Sous-poste | Sous-poste | 2018-07-27 | 2018-08-02 | 2018-08-02 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 31 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770223710 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27702237 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 13084 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-31 | NA | 100% | 2018-07-27 | 100% | NA | NA | 100% |  |  | 2018-04-25 | 2018-07-31 | Sous-poste | Sous-poste | 2018-04-30 | 2018-08-03 | 2018-08-03 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 31 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775208410 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27752084 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 13084 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-07-31 | NA | 100% | 2018-07-27 | 100% | NA | NA | 100% |  |  | 2018-05-15 | 2018-07-31 | Sous-poste | Sous-poste | 2018-05-18 | 2018-08-03 | 2018-08-03 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 7 | 2018 | 1 | 2014 | 31 | 7 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2778043910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27780439 | NON-SPARES | 10 | 3 | EXP | F9251110800300 | 1STR*10653 | NA | 13557 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-01 | NA | 100% | 2018-06-26 | 100% | NA | NA | 100% |  |  | 2018-06-06 | 2018-08-01 | Sous-poste | Sous-poste | 2018-06-10 | 2018-08-04 | 2018-08-04 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 31 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777617910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27776179 | NON-SPARES | 10 | 3 | RTN | F9251110800300 | 1STR*10653 | NA | 13557 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-01 | NA | 100% | 2018-06-26 | 100% | NA | NA | 100% |  |  | 2018-08-01 | 2018-08-01 | Sous-poste | Sous-poste | 2018-08-04 | 2018-08-04 | 2018-08-04 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2018 | 1 | 2014 | 31 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003545610 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900035456 | NON-SPARES | 10 | 5 | RTN | S9252318000000 | 1STR*02063 | NA | 14165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-01 | NA | 100% | 2018-07-30 | 100% | NA | NA | 100% |  |  | 2018-08-01 | 2018-08-01 | Sous-poste | Sous-poste | 2018-08-06 | 2018-08-06 | 2018-08-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2018 | 1 | 2014 | 31 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2779489910 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27794899 | NON-SPARES | 10 | 3 | EXP | A9252236000000 | 1STR*01447 | NA | 13498 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-08-07 | 100% | NA | NA | 100% |  |  | 2018-06-19 | 2018-08-06 | Sous-poste | Sous-poste | 2018-06-22 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2767244110 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27672441 | NON-SPARES | 10 | 1 | EXP | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-06-08 | 100% | NA | NA | 100% |  |  | 2018-02-26 | 2018-08-06 | Sous-poste | Sous-poste | 2018-03-01 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2767244210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27672442 | NON-SPARES | 10 | 1 | EXP | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-06-08 | 100% | NA | NA | 100% |  |  | 2018-02-26 | 2018-08-06 | Sous-poste | Sous-poste | 2018-03-01 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2768318810 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27683188 | NON-SPARES | 10 | 2 | EXP | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-06-08 | 100% | NA | NA | 100% |  |  | 2018-05-10 | 2018-08-06 | Sous-poste | Sous-poste | 2018-05-15 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2769431910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27694319 | NON-SPARES | 10 | 2 | RTN | L9251321500000 | 1STR*01089 | NA | 11217 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-06-08 | 100% | NA | NA | 100% |  |  | 2018-05-17 | 2018-08-06 | Sous-poste | Sous-poste | 2018-05-22 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777730310 | 2014-01-01 | HA/REVENTE | SATAIR | HOOK | 27777303 | NON-SPARES | 10 | 5 | RTN | A9252236000000 | 1STR*01447 | NA | 13498 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-06 | NA | 100% | 2018-08-07 | 100% | NA | NA | 100% |  |  | 2018-08-01 | 2018-08-06 | Sous-poste | Sous-poste | 2018-08-06 | 2018-08-09 | 2018-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2779677710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27796777 | NON-SPARES | 10 | 8 | EXP | D9251805800000 | IS0032777S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-28 | 100% | NA | NA | 100% |  |  | 2018-06-20 | 2018-08-07 | Sous-poste | Sous-poste | 2018-06-24 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2779858810 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27798588 | NON-SPARES | 10 | 8 | EXP | D9251805700000 | IS0032776S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-28 | 100% | NA | NA | 100% |  |  | 2018-06-20 | 2018-08-07 | Sous-poste | Sous-poste | 2018-06-24 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2780315710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27803157 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-28 | 100% | NA | NA | 100% |  |  | 2018-06-26 | 2018-08-07 | Sous-poste | Sous-poste | 2018-06-29 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2779677720 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27796777 | NON-SPARES | 20 | 1 | EXP | D9251805800000 | IS0032777S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-28 | 100% | NA | NA | 100% |  |  | 2018-06-27 | 2018-08-07 | Sous-poste | Sous-poste | 2018-06-30 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2782262210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27822622 | NON-SPARES | 10 | 20 | EXP | D9251805700000 | IS0032776S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-31 | 100% | NA | NA | 100% |  |  | 2018-07-10 | 2018-08-07 | Sous-poste | Sous-poste | 2018-07-13 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2782262310 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27822623 | NON-SPARES | 10 | 20 | EXP | D9251805800000 | IS0032777S | NA | 13661 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-07 | NA | 100% | 2018-07-31 | 100% | NA | NA | 100% |  |  | 2018-07-10 | 2018-08-07 | Sous-poste | Sous-poste | 2018-07-13 | 2018-08-10 | 2018-08-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2785214510 | 2018-07-13 |  | TBD |  | 27852145 | NON-SPARES | 10 | 1 | EXP | L9251230020100 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-08-08 | 2018-08-08 | Sous-poste | Sous-poste | 2018-08-12 | 2018-08-12 | 2018-08-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2018 | 7 | 2018 | 32 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
277578997 | 0 | FABRICATION | SATAIR | HARNAIS 2 P2T2 | 27757899 | NON-SPARES | 7 | 3 | EXP | F7161001300001 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-07-27 | 2018-08-09 | Sous-poste | Sous-poste | 2018-08-01 | 2018-08-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 32 | 8 | 2018 | 0.5724 | 9.2007 | 0.76672 | 9.9674 | COL | 0 | 0
490003537910 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900035379 | NON-SPARES | 10 | 8 | RTN | S9251303120000 | 1QEL*00029 | NA | 13909 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-15 | NA | 100% | 2018-06-12 | 100% | NA | NA | 100% |  |  | 2018-08-15 | 2018-08-15 | Sous-poste | Sous-poste | 2018-08-20 | 2018-08-20 | 2018-08-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2018 | 1 | 2014 | 33 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2783858610 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27838586 | NON-SPARES | 10 | 1 | EXP | D9251805700000 | IS0032776S | NA | 14942 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-16 | NA | 100% | 2018-08-07 | 100% | NA | NA | 100% |  |  | 2018-07-27 | 2018-08-16 | Sous-poste | Sous-poste | 2018-08-01 | 2018-08-21 | 2018-08-21 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 33 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2783858710 | 2018-07-02 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27838587 | NON-SPARES | 10 | 1 | EXP | D9251805800000 | IS0032777S | NA | 14942 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-16 | NA | 100% | 2018-08-07 | 100% | NA | NA | 100% |  |  | 2018-07-27 | 2018-08-16 | Sous-poste | Sous-poste | 2018-08-01 | 2018-08-21 | 2018-08-21 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 7 | 2018 | 33 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2780577810 | 0 | FABRICATION | SATAIR | HARNESS ASSY CABLE | 27805778 | NON-SPARES | 10 | 2 | RTN | L9297725700000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-08-27 | 2018-08-21 | Sous-poste | Sous-poste | 2018-08-30 | 2018-08-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 34 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777730410 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27777304 | NON-SPARES | 10 | 6 | RTN | F9251110800600 | 1STR*10659 | NA | 13498 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-21 | NA | 100% | 2018-08-08 | 100% | NA | NA | 100% |  |  | 2018-08-01 | 2018-08-21 | Sous-poste | Sous-poste | 2018-08-06 | 2018-08-24 | 2018-08-24 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 34 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777886710 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27778867 | NON-SPARES | 10 | 1 | RTN | F9251110800600 | 1STR*10659 | NA | 13498 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-21 | NA | 100% | 2018-08-08 | 100% | NA | NA | 100% |  |  | 2018-08-08 | 2018-08-21 | Sous-poste | Sous-poste | 2018-08-13 | 2018-08-24 | 2018-08-24 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 34 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003561930 | 2018-06-29 | FABRICATION | STELIA | CÂBLE | 4900035619 | NON-SPARES | 30 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-08-22 | 2018-08-22 | Sous-poste | Sous-poste | 2018-08-27 | 2018-08-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 34 | 8 | 2018 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
27808864 | 0 | FABRICATION | SATAIR | WIRE-BONDING | 27808864 | NON-SPARES |  | 4 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | 14143 | 053722-1 => 053722-4 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-08-28 | 100% | NA | NA | 5.556% |  |  | 2018-08-29 | 2018-08-23 | Sous-poste | Sous-poste | 2018-09-01 | 2018-08-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 34 | 8 | 2018 | 0.8236 | 0.9532 | 0.02383 | 0.97703 | NA | 0 | 0
27860234 | 0 | FABRICATION | SATAIR | PROTECTION CAP | 27860234 | NON-SPARES |  | 5 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 15566 | 108049-1 => 108049-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-08-23 | 100% | NA | NA | 5.556% |  |  | 2018-08-24 | 2018-08-24 | Sous-poste | Sous-poste | 2018-08-29 | 2018-08-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 34 | 8 | 2018 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
2782205110 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27822051 | NON-SPARES | 10 | 2 | EXP | A9253115800000 | IS0031675S | NA | 14539 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-08-28 | Sous-poste | Sous-poste | 2018-07-14 | 2018-08-31 | 2018-08-31 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 35 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784568510 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27845685 | NON-SPARES | 10 | 1 | EXP | A9253115800000 | IS0031675S | NA | 14539 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-08-06 | 2018-08-28 | Sous-poste | Sous-poste | 2018-08-09 | 2018-08-31 | 2018-08-31 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 35 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2782367210 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27823672 | NON-SPARES | 10 | 1 | EXP | A9253115800000 | IS0031675S | NA | 14539 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-28 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-08-28 | Sous-poste | Sous-poste | 2018-07-15 | 2018-08-31 | 2018-08-31 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 35 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2774933610 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27749336 | NON-SPARES | 10 | 2 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-28 | NA | 100% | 2018-08-21 | 100% | NA | NA | 100% |  |  | 2018-08-28 | 2018-08-28 | Sous-poste | Sous-poste | 2018-08-31 | 2018-08-31 | 2018-08-31 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 8 | 2018 | 1 | 2014 | 35 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2771722610 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27717226 | NON-SPARES | 10 | 1 | RTN | F9251110800800 | 1STR*00292 | NA | 12360 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-08-29 | NA | 100% | 2018-07-17 | 100% | NA | NA | 100% |  |  | 2018-07-24 | 2018-08-29 | Sous-poste | Sous-poste | 2018-07-27 | 2018-09-03 | 2018-09-03 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 8 | 2018 | 1 | 2014 | 35 | 8 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
4900035685 | 2018-07-10 | FABRICATION | STELIA | CABLE COAXIAL | 4900035685 | NON-SPARES |  | 5 | CRIT | S9110104500195 | IS0032220M | NON PRESENT INDUS | 15251 | 077075-1 => 077075-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-08-30 | 100% | NA | NA | 5.556% |  |  | 2018-08-30 | 2018-08-30 | Sous-poste | Sous-poste | 2018-09-03 | 2018-09-03 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 7 | 2018 | 35 | 8 | 2018 | 0.963 | 3.7565 | 0.07513 | 3.8316 | NA | 0 | 0
490003566910 | 2018-07-09 | FABRICATION | STELIA | CÂBLE | 4900035669 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-08-31 | 2018-08-31 | Sous-poste | Sous-poste | 2018-09-05 | 2018-09-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 7 | 2018 | 35 | 8 | 2018 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2781288210 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27812882 | NON-SPARES | 10 | 1 | RTN | L9251321500000 | 1STR*01089 | NA | 14239 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-05 | NA | 100% | 2018-08-29 | 100% | NA | NA | 100% |  |  | 2018-09-05 | 2018-09-05 | Sous-poste | Sous-poste | 2018-09-08 | 2018-09-08 | 2018-09-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 1 | 2014 | 36 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2781703510 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27817035 | NON-SPARES | 10 | 6 | RTN | F9251110800300 | 1STR*10653 | NA | 13557 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-05 | NA | 100% | 2018-08-29 | 100% | NA | NA | 100% |  |  | 2018-09-05 | 2018-09-05 | Sous-poste | Sous-poste | 2018-09-09 | 2018-09-09 | 2018-09-09 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 1 | 2014 | 36 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775639910 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY | 27756399 | NON-SPARES | 10 | 2 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-05 | NA | 100% | 2018-08-01 | 100% | NA | NA | 100% |  |  | 2018-08-08 | 2018-09-05 | Sous-poste | Sous-poste | 2018-08-12 | 2018-09-10 | 2018-09-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 9 | 2018 | 1 | 2014 | 36 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27901127 | 2018-09-03 | FABRICATION | SATAIR | 60 | 27901127 | NON-SPARES |  | 5 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990001 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-09-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-06 | 2018-09-06 | Sous-poste | Sous-poste | 2018-09-10 | 2018-09-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 36 | 9 | 2018 | 1.025 | 6.7125 | 0.33563 | 7.0481 | COL | 0 | 0
27901130 | 2018-09-03 | FABRICATION | SATAIR | 61 | 27901130 | NON-SPARES |  | 5 | AOG | D9551006100295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-06 | 2018-09-06 | Sous-poste | Sous-poste | 2018-09-10 | 2018-09-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 36 | 9 | 2018 | 1.025 | 6.7125 | 0.33563 | 7.0481 | COL | 0 | 0
27901134 | 2018-09-03 | FABRICATION | SATAIR | 62 | 27901134 | NON-SPARES |  | 5 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990001 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-09-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-06 | 2018-09-06 | Sous-poste | Sous-poste | 2018-09-10 | 2018-09-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 36 | 9 | 2018 | 1.025 | 9.3235 | 0.46618 | 9.7897 | COL | 0 | 0
HNC200023956318 | 2014-01-01 | HA/REVENTE | SATAIR | ARINC | HNC2000239563 | NON-SPARES | 18 | 1 |  | E0163D21-45X | 1CON*01139 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-11 | NA | 100% | 2018-09-07 | 100% | NA | NA | 100% |  |  | 2018-09-11 | 2018-09-11 | Sous-poste | Sous-poste | 2018-09-14 | 2018-09-14 | 2018-09-14 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 1 | 2014 | 37 | 9 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27826931 | 2018-06-20 | FABRICATION | SATAIR | HARNAIS 2 P2T2 | 27826931 | NON-SPARES |  | 5 | RTN | F7161001300001 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-11 | 2018-09-11 | Sous-poste | Sous-poste | 2018-09-14 | 2018-09-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 37 | 9 | 2018 | 0.954 | 15.3345 | 0.76672 | 16.1012 | COL | 0 | 0
2788705710 | 2018-08-17 | HA/REVENTE | SATAIR | PLATE ASSY | 27887057 | NON-SPARES | 10 | 40 | EXP | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-12 | NA | 100% | 2018-09-06 | 100% | NA | NA | 100% |  |  | 2018-09-12 | 2018-09-12 | Sous-poste | Sous-poste | 2018-09-16 | 2018-09-16 | 2018-09-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 8 | 2018 | 37 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003573510 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900035735 | NON-SPARES | 10 | 5 | RTN | S9252318000000 | 1STR*02063 | NA | 15464 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-12 | NA | 100% | 2018-09-05 | 100% | NA | NA | 100% |  |  | 2018-09-12 | 2018-09-12 | Sous-poste | Sous-poste | 2018-09-17 | 2018-09-17 | 2018-09-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 1 | 2014 | 37 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784263710 | 0 | FABRICATION | SATAIR | PLATE ASSY | 27842637 | NON-SPARES | 10 | 2 | AOG | F9252020200000 | IS0032657M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-07-10 | 2018-09-13 | Sous-poste | Sous-poste | 2018-07-12 | 2018-09-17 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 1 | 1900 | 37 | 9 | 2018 | 0 | 0.3578 | 0.01789 | 0.37569 | NA | 0 | 0
279019558 | 2018-09-04 | FABRICATION | SATAIR | 22 | 27901955 | NON-SPARES | 8 | 2 | RTN | D9551002201695 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-20 | 2018-09-14 | Sous-poste | Sous-poste | 2018-09-25 | 2018-09-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 9 | 2018 | 37 | 9 | 2018 | 0.41 | 21.0738 | 2.6342 | 23.708 | COL | 0 | 0
27909752 | 2018-09-11 | FABRICATION | SATAIR | 22 | 27909752 | NON-SPARES |  | 1 | AOG | D9551002201695 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-21 | 2018-09-19 | Sous-poste | Sous-poste | 2018-09-25 | 2018-09-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 38 | 9 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
490003587810 | 2018-08-06 | FABRICATION | STELIA | CABLE COAXIAL | 4900035878 | NON-SPARES | 10 | 7 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-25 | 2018-09-19 | Sous-poste | Sous-poste | 2018-09-28 | 2018-09-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 38 | 9 | 2018 | 1.3482 | 5.2591 | 0.07513 | 5.3342 | NA | 0 | 0
2787301210 | 2018-08-07 | FABRICATION | SATAIR | 130 | 27873012 | NON-SPARES | 10 | 1 | AOG | D9550013000195 | 0 | NON PRESENT INDUS | 15966 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-09-20 | 100% | NA | NA | 5.556% |  |  | 2018-09-20 | 2018-09-20 | Sous-poste | Sous-poste | 2018-09-24 | 2018-09-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 8 | 2018 | 38 | 9 | 2018 | 0.36 | 5.157 | 1.2893 | 6.4463 | COL | 0 | 0
2771795410 | 2018-03-22 | HA/REVENTE | SATAIR | SEAL | 27717954 | NON-SPARES | 10 | 1 | EXP | A9252427220000 | 1QME*16762 | NA | 12421 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-20 | NA | 100% | 2018-09-19 | 100% | NA | NA | 100% |  |  | 2018-04-18 | 2018-09-20 | Sous-poste | Sous-poste | 2018-04-21 | 2018-09-25 | 2018-09-25 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 9 | 2018 | 3 | 2018 | 38 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2790681910 | 2018-09-07 | FABRICATION | SATAIR | PLATE ASSY | 27906819 | NON-SPARES | 10 | 1 | AOG | F9252020200000 | IS0032657M | NON PRESENT INDUS | 16666 | 124657-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-09-21 | 100% | NA | NA | 5.556% |  |  | 2018-09-12 | 2018-09-21 | Sous-poste | Sous-poste | 2018-09-14 | 2018-09-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 38 | 9 | 2018 | 0 | 0.1789 | 0.01789 | 0.19679 | NA | 0 | 0
2780527310 | 2018-06-01 | FABRICATION | SATAIR | PROTECTION CAP | 27805273 | NON-SPARES | 10 | 5 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 15914 | 108050-1 => 108050-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-09-24 | 100% | NA | NA | 5.556% |  |  | 2018-08-02 | 2018-09-25 | Sous-poste | Sous-poste | 2018-08-07 | 2018-09-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 39 | 9 | 2018 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
2784012210 | 2018-07-03 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27840122 | NON-SPARES | 10 | 5 | RTN | D9251095600000 | IS0053509S | NA | 15158 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-26 | NA | 100% | 2018-09-19 | 100% | NA | NA | 100% |  |  | 2018-09-26 | 2018-09-26 | Sous-poste | Sous-poste | 2018-10-01 | 2018-10-01 | 2018-10-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 7 | 2018 | 39 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784012110 | 2018-07-03 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27840121 | NON-SPARES | 10 | 8 | RTN | D9251095400000 | IS0053354S | NA | 15158 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-09-26 | NA | 100% | 2018-09-19 | 100% | NA | NA | 100% |  |  | 2018-09-26 | 2018-09-26 | Sous-poste | Sous-poste | 2018-10-01 | 2018-10-01 | 2018-10-01 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 9 | 2018 | 7 | 2018 | 39 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003624110 | 2017-11-11 | HA/REVENTE | STELIA | PLATINE AVANT 24VU | 4900036241 | NON-SPARES | 10 | 1 | CRIT | S9251425000000 | 1STR*10985 | NA | 17279 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-09-27 | 2018-09-27 | Sous-poste | Sous-poste | 2018-10-01 | 2018-10-01 | 2018-10-01 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2017 | 39 | 9 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362720 | 2018-05-18 | HA/REVENTE | SATAIR | CROSSBEAM ASSY | 27753627 | NON-SPARES | 20 | 5 | RTN | L9251266800001 | 1STR*10883 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362820 | 2018-05-18 | HA/REVENTE | SATAIR | CROSSBEAM | 27753628 | NON-SPARES | 20 | 5 | RTN | L9251266920001 | 1STR*10884 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775362920 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753629 | NON-SPARES | 20 | 5 | RTN | L9251267020001 | 1STR*10885 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363120 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753631 | NON-SPARES | 20 | 5 | RTN | L9251267120001 | 1STR*10886 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363220 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753632 | NON-SPARES | 20 | 5 | RTN | L9251267220001 | 1STR*10887 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363420 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753634 | NON-SPARES | 20 | 10 | RTN | L9251267320001 | 1STR*10888 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775363520 | 2018-05-18 | HA/REVENTE | SATAIR | ANGLE | 27753635 | NON-SPARES | 20 | 5 | RTN | L9251267420001 | 1STR*10889 | NA | 13118 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-02 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-07-11 | 2018-10-02 | Sous-poste | Sous-poste | 2018-07-15 | 2018-10-05 | 2018-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 5 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2772277910 | 2018-03-27 | FABRICATION | SATAIR | 22 | 27722779 | NON-SPARES | 10 | 1 | RTN | D9551002201595 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | 100% | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-04-12 | 2018-10-03 | Sous-poste | Sous-poste | 2018-04-17 | 2018-10-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 3 | 2018 | 40 | 10 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2789025410 | 2018-08-20 | HA/REVENTE | SATAIR | HOOK | 27890254 | NON-SPARES | 10 | 1 | EXP | A9252236000000 | 1STR*01447 | NA | 16579 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-05 | NA | 100% | 2018-10-02 | 100% | NA | NA | 100% |  |  | 2018-09-14 | 2018-10-05 | Sous-poste | Sous-poste | 2018-09-19 | 2018-10-10 | 2018-10-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 8 | 2018 | 40 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791127510 | 2018-09-12 | HA/REVENTE | SATAIR | PLATE ASSY | 27911275 | NON-SPARES | 10 | 2 | EXP | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-09 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-09 | 2018-10-09 | Sous-poste | Sous-poste | 2018-10-12 | 2018-10-12 | 2018-10-12 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 9 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791672810 | 2018-09-19 | FABRICATION | SATAIR | PROTECTION CAP | 27916728 | NON-SPARES | 10 | 20 | AOG | F0003003000000 | IS0032144M | NON PRESENT INDUS | 17054 | 138963-1 => 138963-20 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2018-09-17 | 2018-10-10 | Sous-poste | Sous-poste | 2018-09-19 | 2018-10-12 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 41 | 10 | 2018 | 0.05 | 2.236 | 0.01118 | 2.2472 | NA | 0 | 0
2784319110 | 2018-07-05 | HA/REVENTE | SATAIR | PLATE ASSY | 27843191 | NON-SPARES | 10 | 1 | RTN | F9251485300000 | 1STR*01521 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-09-19 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784318810 | 2018-07-05 | HA/REVENTE | SATAIR | TUBE | 27843188 | NON-SPARES | 10 | 2 | RTN | F9251110800500 | 1STR*00297 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319710 | 2018-07-05 | HA/REVENTE | SATAIR | TUBE | 27843197 | NON-SPARES | 10 | 1 | RTN | F9251110800800 | 1STR*00292 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319910 | 2018-07-05 | HA/REVENTE | SATAIR | TUBE | 27843199 | NON-SPARES | 10 | 1 | RTN | F9251110801200 | 1STR*00294 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319510 | 2018-07-05 | HA/REVENTE | SATAIR/AIS | ANGLE | 27843195 | NON-SPARES | 10 | 2 | RTN | F9251445920000 | 1STR*01520 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784320310 | 2018-07-05 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 27843203 | NON-SPARES | 10 | 1 | RTN | F9251485400000 | 1STR*10825 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-10 | NA | 100% | 2018-10-03 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-10-10 | Sous-poste | Sous-poste | 2018-10-15 | 2018-10-15 | 2018-10-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 7 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2753012810 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530128 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990016 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-10-11 | Sous-poste | Sous-poste | 2017-05-01 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753000810 | 0 | FABRICATION | SATAIR | 117 | 27530008 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990046 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-10-11 | Sous-poste | Sous-poste | 2017-05-01 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753012610 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530126 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990041 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-10-11 | Sous-poste | Sous-poste | 2017-05-01 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753000910 | 0 | FABRICATION | SATAIR | 117 | 27530009 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | LTE990057 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-10-11 | Sous-poste | Sous-poste | 2017-05-01 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753011010 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530110 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990053 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753012110 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530121 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990016 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753011310 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530113 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990058 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753011610 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530116 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366710 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423667 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | EFD990279 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753013810 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530138 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753011210 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530112 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048510 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610485 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990065 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753011910 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530119 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990024 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753000710 | 0 | FABRICATION | SATAIR | 117 | 27530007 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990038 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753001610 | 0 | FABRICATION | SATAIR | 117 | 27530016 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990047 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753009810 | 0 | FABRICATION | SATAIR | 117 | 27530098 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990027 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753013010 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530130 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990050 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048310 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610483 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990029 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753012510 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530125 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990030 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753013610 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530136 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990040 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753010310 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530103 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990043 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753013410 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530134 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990037 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-10-11 | Sous-poste | Sous-poste | 2017-07-15 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753000610 | 0 | FABRICATION | SATAIR | 117 | 27530006 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990039 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-10 | 100% | NA | NA | 5.556% |  |  | 2017-11-02 | 2018-10-11 | Sous-poste | Sous-poste | 2017-11-07 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 41 | 10 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2787896910 | 2018-08-10 | FABRICATION | SATAIR | PROTECTION CAP | 27878969 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 17018 | 138967-1 => 138967-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-10-16 | 100% | NA | NA | 5.556% |  |  | 2018-10-17 | 2018-10-11 | Sous-poste | Sous-poste | 2018-10-20 | 2018-10-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 41 | 10 | 2018 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2775607010 | 2018-04-20 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27756070 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-11 | NA | 100% | 2018-10-02 | 100% | NA | NA | 100% |  |  | 2018-05-31 | 2018-10-11 | Sous-poste | Sous-poste | 2018-06-05 | 2018-10-16 | 2018-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 4 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775608510 | 2018-04-20 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27756085 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-11 | NA | 100% | 2018-10-02 | 100% | NA | NA | 100% |  |  | 2018-08-17 | 2018-10-11 | Sous-poste | Sous-poste | 2018-08-22 | 2018-10-16 | 2018-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 4 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775640610 | 2018-04-20 | HA/REVENTE | SATAIR | PLATE ASSY | 27756406 | NON-SPARES | 10 | 2 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-11 | NA | 100% | 2018-10-04 | 100% | NA | NA | 100% |  |  | 2018-10-11 | 2018-10-11 | Sous-poste | Sous-poste | 2018-10-16 | 2018-10-16 | 2018-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 4 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2788852410 | 2018-08-17 | HA/REVENTE | SATAIR | COVER ASSY | 27888524 | NON-SPARES | 10 | 1 | EXP | A9253115800000 | IS0031675S | NA | 16578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-12 | NA | 100% | 2018-10-11 | 100% | NA | NA | 100% |  |  | 2018-09-12 | 2018-10-12 | Sous-poste | Sous-poste | 2018-09-16 | 2018-10-17 | 2018-10-17 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 8 | 2018 | 41 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791598810 | 2018-09-18 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 27915988 | NON-SPARES | 10 | 25 | EXP | D9251095400000 | IS0053354S | NA | 17174 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-15 | NA | 100% | 2018-10-12 | 100% | NA | NA | 100% |  |  | 2018-10-15 | 2018-10-15 | Sous-poste | Sous-poste | 2018-10-18 | 2018-10-18 | 2018-10-18 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 9 | 2018 | 42 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791598910 | 2018-09-18 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27915989 | NON-SPARES | 10 | 25 | EXP | D9251095600000 | IS0053509S | NA | 17174 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-15 | NA | 100% | 2018-10-12 | 100% | NA | NA | 100% |  |  | 2018-10-15 | 2018-10-15 | Sous-poste | Sous-poste | 2018-10-18 | 2018-10-18 | 2018-10-18 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 10 | 2018 | 9 | 2018 | 42 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2777079910 | 2018-05-16 | FABRICATION | SATAIR | JACK | 27770799 | NON-SPARES | 10 | 1 | RTN | B2352101700200 | 0 | NON PRESENT INDUS | 13430 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-17 | 100% | NA | NA | 5.556% |  |  | 2018-07-27 | 2018-10-18 | Sous-poste | Sous-poste | 2018-08-01 | 2018-10-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 42 | 10 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2777079910 | 2018-05-16 | FABRICATION | SATAIR | JACK | 27770799 | NON-SPARES | 10 | 1 | RTN | B2352101700200 | 0 | NON PRESENT INDUS | 13430 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-17 | 100% | NA | NA | 5.556% |  |  | 2018-07-27 | 2018-10-18 | Sous-poste | Sous-poste | 2018-08-01 | 2018-10-23 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 42 | 10 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2786281010 | 2018-07-25 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 27862810 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 15928 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-18 | NA | 100% | 2018-10-16 | 100% | NA | NA | 100% |  |  | 2018-08-21 | 2018-10-18 | Sous-poste | Sous-poste | 2018-08-24 | 2018-10-23 | 2018-10-23 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 7 | 2018 | 42 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2785261910 | 2018-07-16 | FABRICATION | SATAIR | 301 | 27852619 | NON-SPARES | 10 | 2 | AOG | D9551030100195 | 0 | NON PRESENT INDUS | 16356 | LTE990004 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-10-19 | 100% | NA | NA | 5.556% |  |  | 2018-09-11 | 2018-10-19 | Sous-poste | Sous-poste | 2018-09-13 | 2018-10-23 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 7 | 2018 | 42 | 10 | 2018 | 0.72 | 10.0236 | 1.253 | 11.2766 | COL | 0 | 0
2766302210 | 2018-01-22 | FABRICATION | SATAIR | 510 | 27663022 | NON-SPARES | 10 | 6 | EXP | A9550051000196 | IS0032621M | NON PRESENT INDUS | 11003 | LTE990001 => LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-10-18 | 100% | NA | NA | 5.556% |  |  | 2018-02-16 | 2018-10-19 | Sous-poste | Sous-poste | 2018-02-21 | 2018-10-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 42 | 10 | 2018 | 0 | 21.3102 | 0.88793 | 22.1981 | COL | 0 | 0
2793008110 | 2018-10-08 | FABRICATION | SATAIR | 116 | 27930081 | NON-SPARES | 10 | 2 | CRIT | D9551011600195 | 0 | NON PRESENT INDUS | 17696 | LTE990022 => LTE990023 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-10-23 | 100% | NA | NA | 5.556% |  |  | 2018-10-17 | 2018-10-23 | Sous-poste | Sous-poste | 2018-10-19 | 2018-10-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 10 | 2018 | 43 | 10 | 2018 | 0.41 | 2.8 | 0.35 | 3.15 | COL | 0 | 0
630041196920 | 2018-01-11 | FABRICATION | STELIA | 962 | 6300411969 | NON-SPARES | 20 | 1 | EXP | S9550096235395 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-07 | 2018-10-23 | Sous-poste | Sous-poste | 2018-02-12 | 2018-10-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 43 | 10 | 2018 | 0 | 0 | 0 | 0 | LAB | 0 | 0
2787305710 | 2018-08-07 | HA/REVENTE | SATAIR | PLATE ASSY | 27873057 | NON-SPARES | 10 | 97 | EXP | D9251101900000 | 1STR*11007 | NA | 15953 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-23 | NA | 100% | 2018-10-15 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-10-23 | Sous-poste | Sous-poste | 2018-09-06 | 2018-10-26 | 2018-10-26 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 10 | 2018 | 8 | 2018 | 43 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003629310 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE SOUDÉE | 4900036293 | NON-SPARES | 10 | 3 | CRIT | S9251080800100 | 1STR*10178 | NA | 17282 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-25 | NA | 100% | 2018-10-18 | 100% | NA | NA | 100% |  |  | 2018-10-24 | 2018-10-24 | Sous-poste | Sous-poste | 2018-10-26 | 2018-10-26 | 2018-10-26 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 10 | 2018 | 1 | 2014 | 43 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003629320 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE SOUDÉE | 4900036293 | NON-SPARES | 20 | 10 | CRIT | S9251317700100 | 1STR*10988 | NA | 17282 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-10-25 | NA | 100% | 2018-10-18 | 100% | NA | NA | 100% |  |  | 2018-10-24 | 2018-10-24 | Sous-poste | Sous-poste | 2018-10-26 | 2018-10-26 | 2018-10-26 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 10 | 2018 | 1 | 2014 | 43 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794113010 | 2018-10-19 | FABRICATION | SATAIR | PLACARD SET | 27941130 | NON-SPARES | 10 | 34 | CRIT | D9100095600395 | IS0032064M | NON PRESENT INDUS | NA | 168321-1 => 168321-34 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-10-31 | 100% | NA | NA | 5.556% |  |  | 2018-10-31 | 2018-10-31 | Sous-poste | Sous-poste | 2018-11-02 | 2018-11-02 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 10 | 2018 | 44 | 10 | 2018 | 0 | 6.97 | 0.0205 | 6.9905 | NA | 0 | 0
2785500210 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27855002 | NON-SPARES | 10 | 1 | AOG | L9251391200000 | 1STR*01134 | NA | 15440 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-13 | 2018-10-31 | Sous-poste | Sous-poste | 2018-07-17 | 2018-11-02 | 2018-11-02 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 44 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2785500310 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27855003 | NON-SPARES | 10 | 1 | AOG | L9251391300000 | 1STR*01135 | NA | 15440 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-07-13 | 2018-10-31 | Sous-poste | Sous-poste | 2018-07-17 | 2018-11-02 | 2018-11-02 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 44 | 10 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003613830 | 2017-11-11 | HA/REVENTE | STELIA | PLATINE ARRIERE 5VU | 4900036138 | NON-SPARES | 30 | 2 | EXP | S9251593120000 | 3STR*00145 | NA | 16821 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 0 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-09-18 | 2018-11-01 | Sous-poste | Sous-poste | 2018-09-21 | 2018-11-06 | 2018-11-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 44 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2783965710 | 2018-07-03 | HA/REVENTE | SATAIR | PLATE ASSY | 27839657 | NON-SPARES | 10 | 2 | RTN | F9251176900000 | 4STR*01313 | NA | 15161 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-01 | NA | 100% | 2018-10-25 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-11-01 | Sous-poste | Sous-poste | 2018-10-15 | 2018-11-06 | 2018-11-06 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 7 | 2018 | 44 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2787587510 | 2018-08-09 |  | TBD |  | 27875875 | NON-SPARES | 10 | 1 | RTN | L9251230020100 |  | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-11-01 | 2018-11-01 | Sous-poste | Sous-poste | 2018-11-06 | 2018-11-06 | 2018-11-06 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 8 | 2018 | 44 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003638910 | 2018-10-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900036389 | NON-SPARES | 10 | 7 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 18014 | 168256-1 168256-7 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-02 | 100% | NA | NA | 5.556% |  |  | 2018-11-05 | 2018-11-05 | Sous-poste | Sous-poste | 2018-11-08 | 2018-11-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 45 | 11 | 2018 | 1.3482 | 5.2591 | 0.07513 | 5.3342 | NA | 0 | 0
2793053810 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 27930538 | NON-SPARES | 10 | 2 | EXP | A9253115800000 | IS0031675S | NA | 17858 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-05 | NA | 100% | 2018-11-05 | 100% | NA | NA | 100% |  |  | 2018-11-05 | 2018-11-05 | Sous-poste | Sous-poste | 2018-11-08 | 2018-11-08 | 2018-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2785937610 | 2018-07-20 | HA/REVENTE | SATAIR | COVER ASSY | 27859376 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 15565 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-05 | NA | 100% | 2018-11-05 | 100% | NA | NA | 100% |  |  | 2018-08-15 | 2018-11-05 | Sous-poste | Sous-poste | 2018-08-19 | 2018-11-08 | 2018-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 7 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791430210 | 2018-09-17 | HA/REVENTE | SATAIR | COVER ASSY | 27914302 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 16578 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-05 | NA | 100% | 2018-11-07 | 100% | NA | NA | 100% |  |  | 2018-12-12 | 2018-11-05 | Sous-poste | Sous-poste | 2018-12-16 | 2018-11-08 | 2018-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 9 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2793053910 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 27930539 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 17858 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-05 | NA | 100% | 2018-11-05 | 100% | NA | NA | 100% |  |  | 2018-11-05 | 2018-11-05 | Sous-poste | Sous-poste | 2018-11-08 | 2018-11-08 | 2018-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2785262010 | 2018-07-16 | FABRICATION | SATAIR | 500 | 27852620 | NON-SPARES | 10 | 2 | AOG | D9551050000195 | 0 | NON PRESENT INDUS | 16699 | LTE990004 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-11 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-13 | 2018-11-08 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 7 | 2018 | 45 | 11 | 2018 | 1.32 | 10.1006 | 1.2626 | 11.3632 | COL | 0 | 0
2789500310 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27895003 | NON-SPARES | 10 | 2 | EXP | V9251155600000 | 1STR*10746 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789500410 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27895004 | NON-SPARES | 10 | 2 | EXP | V9251157800000 | 1STR*10749 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789500610 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27895006 | NON-SPARES | 10 | 2 | EXP | V9251156000000 | 1STR*10748 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501210 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27895012 | NON-SPARES | 10 | 2 | EXP | V9251157500000 | 1STR*10750 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 8 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501310 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27895013 | NON-SPARES | 10 | 2 | EXP | V9251156900000 | 1STR*10973 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 8 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789502210 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27895022 | NON-SPARES | 10 | 2 | EXP | V9251157300000 | 1STR*10979 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-06 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 8 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2791341710 | 2018-09-14 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 27913417 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 15928 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-10-16 | 100% | NA | NA | 100% |  |  | 2018-10-10 | 2018-11-06 | Sous-poste | Sous-poste | 2018-10-14 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 9 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792194010 | 2018-09-26 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 27921940 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 15928 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-06 | NA | 100% | 2018-10-16 | 100% | NA | NA | 100% |  |  | 2018-10-23 | 2018-11-06 | Sous-poste | Sous-poste | 2018-10-26 | 2018-11-09 | 2018-11-09 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 9 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2788228910 | 2018-08-14 | FABRICATION | SATAIR | 27 | 27882289 | NON-SPARES | 10 | 3 | RTN | D9551002700495 | 0 | NON PRESENT INDUS | 17014 | LTE990052 à LTE990054 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-26 | 2018-11-07 | Sous-poste | Sous-poste | 2018-10-01 | 2018-11-10 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 45 | 11 | 2018 | 0.615 | 14.7519 | 1.2293 | 15.9812 | COL | 0 | 0
2788294510 | 2018-08-14 | FABRICATION | SATAIR | JACK | 27882945 | NON-SPARES | 10 | 6 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 17010 | LTE990013 => LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-10 | 2018-11-07 | Sous-poste | Sous-poste | 2018-09-13 | 2018-11-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 45 | 11 | 2018 | 0 | 13.0116 | 0.54215 | 13.5537 | COL | 0 | 0
2793387510 | 2018-10-12 | FABRICATION | SATAIR | PLATE ASSY | 27933875 | NON-SPARES | 10 | 1 | EXP | F9252020200000 | IS0032657M | NON PRESENT INDUS | 17885 | 164073-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-06 | 100% | NA | NA | 5.556% |  |  | 2018-11-07 | 2018-11-07 | Sous-poste | Sous-poste | 2018-11-11 | 2018-11-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 45 | 11 | 2018 | 0 | 0.1789 | 0.01789 | 0.19679 | NA | 0 | 0
2788187810 | 2018-08-14 | HA/REVENTE | SATAIR | PLATE ASSY | 27881878 | NON-SPARES | 10 | 78 | RTN | D9251101900000 | 1STR*11007 | NA | 16581 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-07 | NA | 100% | 2018-10-24 | 100% | NA | NA | 100% |  |  | 2018-11-07 | 2018-11-07 | Sous-poste | Sous-poste | 2018-11-11 | 2018-11-11 | 2018-11-11 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 8 | 2018 | 45 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2782692910 | 2018-06-20 | FABRICATION | SATAIR | JACK ASSY | 27826929 | NON-SPARES | 10 | 8 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | 14642 | 075872-1 => 075872-8 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-07 | 100% | NA | NA | 5.556% |  |  | 2018-09-11 | 2018-11-08 | Sous-poste | Sous-poste | 2018-09-14 | 2018-11-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 6 | 2018 | 45 | 11 | 2018 | 1.4928 | 12.3008 | 0.15376 | 12.4546 | COL | 0 | 0
2775641110 | 2018-04-20 | HA/REVENTE | SATAIR | PLATE ASSY | 27756411 | NON-SPARES | 10 | 2 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-12 | NA | 100% | 2018-11-05 | 100% | NA | NA | 100% |  |  | 2018-11-12 | 2018-11-12 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-15 | 2018-11-15 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 4 | 2018 | 46 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
681137810 | 2018-09-27 | FABRICATION | AD&S | 48 | 6811378 | NON-SPARES | 10 | 1 | AOG | MB041ACAAAAE | IS0032204M | NON PRESENT INDUS | 17486 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-13 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-13 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 46 | 11 | 2018 | 0.205 | 2.96 | 0.74 | 3.7 | LAB | 0 | 0
2788631510 | 2018-08-16 | FABRICATION | SATAIR | JACK | 27886315 | NON-SPARES | 10 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 17010 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-12 | 100% | NA | NA | 5.556% |  |  | 2018-09-12 | 2018-11-13 | Sous-poste | Sous-poste | 2018-09-15 | 2018-11-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 46 | 11 | 2018 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2793904610 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 27939046 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 17858 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-13 | NA | 100% | 2018-11-07 | 100% | NA | NA | 100% |  |  | 2018-11-13 | 2018-11-13 | Sous-poste | Sous-poste | 2018-11-16 | 2018-11-16 | 2018-11-16 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 46 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791426810 | 2018-09-17 | FABRICATION | SATAIR | 22 | 27914268 | NON-SPARES | 10 | 1 | AOG | D9551002201695 | 0 | NON PRESENT INDUS | 17013 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-14 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 46 | 11 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2791427010 | 2018-09-17 | FABRICATION | SATAIR | 22 | 27914270 | NON-SPARES | 10 | 1 | AOG | D9551002201695 | 0 | NON PRESENT INDUS | 17013 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-14 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 46 | 11 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2769947210 | 2018-03-01 | FABRICATION | SATAIR | JACK ASSY | 27699472 | NON-SPARES | 10 | 2 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | 11974 | Z72227-1 => Z72227-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-13 | 100% | NA | NA | 5.556% |  |  | 2018-07-02 | 2018-11-14 | Sous-poste | Sous-poste | 2018-07-05 | 2018-11-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 3 | 2018 | 46 | 11 | 2018 | 0.3732 | 3.0752 | 0.15376 | 3.229 | COL | 0 | 0
2769947510 | 2018-03-01 | FABRICATION | SATAIR | JACK ASSY | 27699475 | NON-SPARES | 10 | 2 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | 11974 | Z73695-1 => Z73695-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-13 | 100% | NA | NA | 5.556% |  |  | 2018-08-09 | 2018-11-14 | Sous-poste | Sous-poste | 2018-08-14 | 2018-11-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 3 | 2018 | 46 | 11 | 2018 | 0.3732 | 3.0752 | 0.15376 | 3.229 | COL | 0 | 0
2769947710 | 2018-03-01 | FABRICATION | SATAIR | JACK ASSY | 27699477 | NON-SPARES | 10 | 2 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | 11974 | Z73698-1 => Z73698-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-13 | 100% | NA | NA | 5.556% |  |  | 2018-08-31 | 2018-11-14 | Sous-poste | Sous-poste | 2018-09-05 | 2018-11-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 3 | 2018 | 46 | 11 | 2018 | 0.3732 | 3.0752 | 0.15376 | 3.229 | COL | 0 | 0
2778240610 | 2018-05-15 | FABRICATION | SATAIR | HARNAIS 1 P2T2 | 27782406 | NON-SPARES | 10 | 2 | EXP | F7161001200001 | 0 | NON PRESENT INDUS | 13597 | 034708-1 => 034708-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-13 | 100% | NA | NA | 5.556% |  |  | 2018-11-05 | 2018-11-14 | Sous-poste | Sous-poste | 2018-11-08 | 2018-11-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 46 | 11 | 2018 | 0.3858 | 4.1638 | 0.52048 | 4.6843 | COL | 0 | 0
2709509810 | 0 | FABRICATION | SATAIR | 117 | 27095098 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 437 | EFD990243 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2016-08-15 | 2018-11-15 | Sous-poste | Sous-poste | 2016-08-18 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2708435310 | 0 | FABRICATION | SATAIR | 117 | 27084353 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 317 | EFD990205 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2016-09-14 | 2018-11-15 | Sous-poste | Sous-poste | 2016-09-18 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740510210 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405102 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990244 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-11-15 | Sous-poste | Sous-poste | 2017-05-01 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364210 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423642 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990044 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-15 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364810 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423648 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990049 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-15 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365910 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423659 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990048 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-14 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-15 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 46 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2796774310 | 2018-11-15 | FABRICATION | SATAIR | HARNESS 5R-6R 1000VU | 27967743 | NON-SPARES | 10 | 1 | AOG | V9251207600295 | 0 | NON PRESENT INDUS | NA | 186209-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-11-19 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-19 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2018 | 47 | 11 | 2018 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
2796778010 | 2018-11-15 | FABRICATION | SATAIR | HARNESS 5R-6R 1000VU | 27967780 | NON-SPARES | 10 | 1 | AOG | V9251207600295 | 0 | NON PRESENT INDUS | NA | 186211-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-11-19 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-19 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2018 | 47 | 11 | 2018 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
490003618740 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900036187 | NON-SPARES | 40 | 3 | RTN | S9252318000000 | 1STR*02063 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-19 | NA | 100% | 2018-11-15 | 100% | NA | NA | 100% |  |  | 2018-11-19 | 2018-11-19 | Sous-poste | Sous-poste | 2018-11-22 | 2018-11-22 | 2018-11-22 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003671410 | 2014-01-01 | HA/REVENTE | STELIA | ENSEMBLE COMPAS | 4900036714 | NON-SPARES | 10 | 1 | CRIT | S9251340100100 | 1STR*11056 | NA | 18974 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-21 | NA | 100% | 2018-11-15 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-19 | 2018-11-22 | 2018-11-22 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2793828610 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27938286 | NON-SPARES | 10 | 2 | RTN | V9251155800000 | 1STR*10747 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-18 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793829610 | 2014-01-01 | HA/REVENTE | SATAIR | ANGLE ASSY | 27938296 | NON-SPARES | 10 | 2 | RTN | V9251156200000 | 1STR*10970 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-18 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832710 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE | 27938327 | NON-SPARES | 10 | 4 | RTN | V9251147720000 | 1STR*10976 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-18 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789500010 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27895000 | NON-SPARES | 10 | 2 | EXP | V9251155800000 | 1STR*10747 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-26 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-20 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789440710 | 2018-08-24 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27894407 | NON-SPARES | 10 | 10 | RTN | D9251805800000 | IS0032777S | NA | 16585 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-21 | 100% | NA | NA | 100% |  |  | 2018-11-20 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-23 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 8 | 2018 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2789440810 | 2018-08-24 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27894408 | NON-SPARES | 10 | 10 | RTN | D9251805800000 | IS0032777S | NA | 16585 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-21 | 100% | NA | NA | 100% |  |  | 2018-11-20 | 2018-11-20 | Sous-poste | Sous-poste | 2018-11-23 | 2018-11-23 | 2018-11-23 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 8 | 2018 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791439010 | 2018-09-17 | FABRICATION | SATAIR | 22 | 27914390 | NON-SPARES | 10 | 1 | AOG | D9551002200595 | 0 | NON PRESENT INDUS | 17021 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2018-11-08 | 2018-11-21 | Sous-poste | Sous-poste | 2018-11-12 | 2018-11-23 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 47 | 11 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
490003656710 | 2014-01-01 | HA/REVENTE | STELIA | PLAQUE | 4900036567 | NON-SPARES | 10 | 1 |  | S9251450300000 | 1QME*00169 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-21 | NA | 100% | 2018-11-09 | 100% | NA | NA | 100% |  |  | 2018-11-22 | 2018-11-21 | Sous-poste | Sous-poste | 2018-11-27 | 2018-11-26 | 2018-11-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003662510 | 2014-01-01 | HA/REVENTE | STELIA | EMBASE ÉQUIPÉE | 4900036625 | NON-SPARES | 10 | 2 | EXP | S9251450200000 | 1QME*00170 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-21 | NA | 100% | 2018-11-09 | 100% | NA | NA | 100% |  |  | 2018-11-21 | 2018-11-21 | Sous-poste | Sous-poste | 2018-11-26 | 2018-11-26 | 2018-11-26 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2742364410 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423644 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990051 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-22 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364710 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423647 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990054 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-22 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365610 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423656 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990059 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-22 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366610 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423666 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990056 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-11-22 | Sous-poste | Sous-poste | 2017-11-21 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048910 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610489 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990062 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2018-02-07 | 2018-11-22 | Sous-poste | Sous-poste | 2018-02-10 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761049010 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610490 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990061 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2018-02-07 | 2018-11-22 | Sous-poste | Sous-poste | 2018-02-10 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 47 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2778413910 | 2018-05-16 | FABRICATION | SATAIR | 510 | 27784139 | NON-SPARES | 10 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 13629 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2018-08-01 | 2018-11-22 | Sous-poste | Sous-poste | 2018-08-05 | 2018-11-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 47 | 11 | 2018 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2784880110 | 2018-10-19 | FABRICATION | SATAIR | 119 | 27848801 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 15619 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-22 | 100% | NA | NA | 5.556% |  |  | 2018-09-24 | 2018-11-23 | Sous-poste | Sous-poste | 2018-09-27 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2784880110 | 2018-10-19 | FABRICATION | SATAIR | 119 | 27848801 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 15619 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-22 | 100% | NA | NA | 5.556% |  |  | 2018-09-24 | 2018-11-23 | Sous-poste | Sous-poste | 2018-09-27 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
27859375 2793994310 | 2018-07-20 | FABRICATION | SATAIR | 119 | 27859375 27939943 | NON-SPARES | 10 | 1 | EXP | D9550011900195 | 0 | NON PRESENT INDUS | 15619 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-22 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 7 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
27879924 2794012010 | 2018-08-10 | FABRICATION | SATAIR | 119 | 27879924 27940120 | NON-SPARES | 10 | 1 | EXP | D9550011900195 | 0 | NON PRESENT INDUS | 16378 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-22 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
27896375 2794012910 | 2018-08-28 | FABRICATION | SATAIR | 119 | 27896375 27940129 | NON-SPARES | 10 | 1 | EXP | D9550011900195 | 0 | NON PRESENT INDUS | 16378 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-22 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
27905624 2794013020 | 2018-09-06 | FABRICATION | SATAIR | 119 | 27905624 27940130 | NON-SPARES | 20 | 1 | EXP | D9550011900195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-11-12 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 9 | 2018 | 47 | 11 | 2018 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2793832310 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27938323 | NON-SPARES | 10 | 2 | RTN | V9251156900000 | 1STR*10973 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-23 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-18 | 2018-11-28 | 2018-11-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793833010 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27938330 | NON-SPARES | 10 | 2 | RTN | V9251157300000 | 1STR*10979 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-23 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-11-23 | Sous-poste | Sous-poste | 2018-11-18 | 2018-11-28 | 2018-11-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789500110 | 2014-01-01 | HA/REVENTE | SATAIR | ANGLE ASSY | 27895001 | NON-SPARES | 10 | 2 | EXP | V9251156200000 | 1STR*10970 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-23 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-23 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-28 | 2018-11-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 1 | 2014 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501910 | 2018-08-27 | HA/REVENTE | SATAIR | PLATE | 27895019 | NON-SPARES | 10 | 4 | EXP | V9251147720000 | 1STR*10976 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-23 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2018-11-23 | Sous-poste | Sous-poste | 2018-09-06 | 2018-11-28 | 2018-11-28 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 11 | 2018 | 8 | 2018 | 47 | 11 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2778413910 | 2018-05-16 | FABRICATION | SATAIR | 510 | 27784139 | NON-SPARES | 10 | 1 | RTN | A9550051000196 | IS0032621M | NON PRESENT INDUS | 13629 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-11-21 | 100% | NA | NA | 5.556% |  |  | 2018-08-01 | 2018-11-26 | Sous-poste | Sous-poste | 2018-08-05 | 2018-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 5 | 2018 | 48 | 11 | 2018 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
490003645110 | 2018-10-18 | FABRICATION | STELIA | 811 | 4900036451 | NON-SPARES | 10 | 2 | EXP | S9550081192795 | 0 | NON PRESENT INDUS | 18240 | LTE990001 => LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-23 | 100% | NA | NA | 5.556% |  |  | 2018-11-06 | 2018-11-26 | Sous-poste | Sous-poste | 2018-11-09 | 2018-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 48 | 11 | 2018 | 0.72 | 7.6084 | 0.95105 | 8.5595 | LAB | 0 | 0
2782278410 | 2018-06-15 | FABRICATION | SATAIR | 22 | 27822784 | NON-SPARES | 10 | 1 | AOG | D9551002200595 | 0 | NON PRESENT INDUS | 14516 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-27 | 100% | NA | NA | 5.556% |  |  | 2018-10-19 | 2018-11-27 | Sous-poste | Sous-poste | 2018-10-23 | 2018-11-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 6 | 2018 | 48 | 11 | 2018 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2791299720 | 2018-09-14 | FABRICATION | SATAIR | 510 | 27912997 | NON-SPARES | 20 | 1 | EXP | A9550051000296 | IS0031992M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-10-10 | 2018-11-27 | Sous-poste | Sous-poste | 2018-10-14 | 2018-11-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 9 | 2018 | 48 | 11 | 2018 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2789440010 | 2014-01-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27894400 | NON-SPARES | 10 | 10 | RTN | D9251805700000 | IS0032776S | NA | 16585 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-27 | NA | 100% | 2018-11-21 | 100% | NA | NA | 100% |  |  | 2018-11-27 | 2018-11-27 | Sous-poste | Sous-poste | 2018-11-30 | 2018-11-30 | 2018-11-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 1 | 2014 | 48 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2789440110 | 2018-08-24 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27894401 | NON-SPARES | 10 | 10 | RTN | D9251805700000 | IS0032776S | NA | 16585 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-27 | NA | 100% | 2018-11-21 | 100% | NA | NA | 100% |  |  | 2018-11-27 | 2018-11-27 | Sous-poste | Sous-poste | 2018-11-30 | 2018-11-30 | 2018-11-30 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 11 | 2018 | 8 | 2018 | 48 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791555220 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915552 | NON-SPARES | 20 | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-10-11 | 2018-11-28 | Sous-poste | Sous-poste | 2018-10-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 48 | 11 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791555510 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915555 | NON-SPARES | 10 | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-10-11 | 2018-11-28 | Sous-poste | Sous-poste | 2018-10-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 48 | 11 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791557510 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915575 | NON-SPARES | 10 | 1 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-10-11 | 2018-11-28 | Sous-poste | Sous-poste | 2018-10-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 48 | 11 | 2018 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2791557810 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915578 | NON-SPARES | 10 | 1 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-10-11 | 2018-11-28 | Sous-poste | Sous-poste | 2018-10-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 48 | 11 | 2018 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2792607710 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926077 | NON-SPARES | 10 | 1 | AOG | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-28 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 10 | 2018 | 48 | 11 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792607910 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926079 | NON-SPARES | 10 | 1 | AOG | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-11-13 | 2018-11-28 | Sous-poste | Sous-poste | 2018-11-15 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 10 | 2018 | 48 | 11 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2796239010 | 2018-11-12 | FABRICATION | SATAIR | OPTICAL FIBER | 27962390 | NON-SPARES | 10 | 1 | AOG | D9000095029495 | IS0032047M | NON PRESENT INDUS | NA | 185893-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-11-09 | 2018-11-28 | Sous-poste | Sous-poste | 2018-11-13 | 2018-11-30 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 11 | 2018 | 48 | 11 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2740519810 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405198 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990246 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-11-29 | Sous-poste | Sous-poste | 2017-05-01 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740530310 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405303 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990249 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-11-29 | Sous-poste | Sous-poste | 2017-05-01 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740532210 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405322 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990250 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-11-29 | Sous-poste | Sous-poste | 2017-05-01 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740537610 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405376 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 5394 | EFD990251 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2017-04-26 | 2018-11-29 | Sous-poste | Sous-poste | 2017-05-01 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742366810 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423668 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | EFD990280 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-11-29 | Sous-poste | Sous-poste | 2017-07-15 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048610 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610486 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990063 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-11-28 | 100% | NA | NA | 5.556% |  |  | 2018-02-07 | 2018-11-29 | Sous-poste | Sous-poste | 2018-02-10 | 2018-12-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2017 | 48 | 11 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
27737148 2774173710 | 2018-04-09 | FABRICATION | SATAIR | 313 | 27737148 27741737 | NON-SPARES | 10 | 1 | AOG | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | 100% | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-11 | 2018-12-03 | Sous-poste | Sous-poste | 2019-01-15 | 2018-12-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 4 | 2018 | 49 | 12 | 2018 | 0.51 | 3.85 | 0.9625 | 4.8125 | LAB | 0 | 0
2795530610 | 2018-11-06 | FABRICATION | SATAIR | WIRE-BONDING | 27955306 | NON-SPARES | 10 | 6 | EXP | F0003008100000 | IS0032145M | NON PRESENT INDUS | NA | 182820-1 => 182820-6 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-11-30 | 100% | NA | NA | 5.556% |  |  | 2018-12-03 | 2018-12-03 | Sous-poste | Sous-poste | 2018-12-06 | 2018-12-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 11 | 2018 | 49 | 12 | 2018 | 1.2354 | 1.4298 | 0.02383 | 1.4536 | NA | 0 | 0
2793998710 | 2018-10-18 | HA/REVENTE | SATAIR | SEAL | 27939987 | NON-SPARES | 10 | 8 | CRIT | A9252483620000 | 1QME*16563 | NA | 18031 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-05 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-10-26 | 2018-12-04 | Sous-poste | Sous-poste | 2018-10-30 | 2018-12-06 | 2018-12-06 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 12 | 2018 | 10 | 2018 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2793829810 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27938298 | NON-SPARES | 10 | 2 | RTN | V9251155600000 | 1STR*10746 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-05 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-12-05 | Sous-poste | Sous-poste | 2018-11-18 | 2018-12-10 | 2018-12-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2018 | 1 | 2014 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793829910 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27938299 | NON-SPARES | 10 | 2 | RTN | V9251157800000 | 1STR*10749 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-05 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-12-05 | Sous-poste | Sous-poste | 2018-11-18 | 2018-12-10 | 2018-12-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2018 | 1 | 2014 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793831510 | 2014-01-01 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27938315 | NON-SPARES | 10 | 2 | RTN | V9251156000000 | 1STR*10748 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-05 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-12-05 | Sous-poste | Sous-poste | 2018-11-18 | 2018-12-10 | 2018-12-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2018 | 1 | 2014 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832010 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 27938320 | NON-SPARES | 10 | 2 | RTN | V9251157500000 | 1STR*10750 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-05 | NA | 100% | 2018-11-22 | 100% | NA | NA | 100% |  |  | 2018-11-14 | 2018-12-05 | Sous-poste | Sous-poste | 2018-11-18 | 2018-12-10 | 2018-12-10 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2018 | 1 | 2014 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003628110 | 2018-10-04 | FABRICATION | STELIA | CÂBLE | 4900036281 | NON-SPARES | 10 | 4 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 144544-1 => 144544-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2018-12-04 | 100% | NA | NA | 5.556% |  |  | 2018-12-05 | 2018-12-05 | Sous-poste | Sous-poste | 2018-12-10 | 2018-12-10 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 49 | 12 | 2018 | 0.82 | 4 | 0.1 | 4.1 | NA | 0 | 0
2709509520 | 0 | FABRICATION | SATAIR | 117 | 27095095 | NON-SPARES | 20 | 16 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2016-08-15 | 2018-12-06 | Sous-poste | Sous-poste | 2016-08-18 | 2018-12-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 1900 | 49 | 12 | 2018 | 3.28 | 61.04 | 0.95375 | 61.9937 | COL | 0 | 0
2740539720 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405397 | NON-SPARES | 20 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-04-26 | 2018-12-06 | Sous-poste | Sous-poste | 2017-05-01 | 2018-12-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 49 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364610 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423646 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 6169 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-05 | 100% | NA | NA | 5.556% |  |  | 2017-07-12 | 2018-12-06 | Sous-poste | Sous-poste | 2017-07-15 | 2018-12-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 49 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365310 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423653 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990025 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-05 | 100% | NA | NA | 5.556% |  |  | 2017-11-02 | 2018-12-06 | Sous-poste | Sous-poste | 2017-11-07 | 2018-12-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 49 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
27405431150 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405431 | NON-SPARES | 150 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2017-11-16 | 2018-12-06 | Sous-poste | Sous-poste | 2017-11-21 | 2018-12-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 49 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2788294410 | 2018-08-14 | HA/REVENTE | SATAIR | COVER ASSY | 27882944 | NON-SPARES | 10 | 1 | RTN | A9252597000800 | 1STR*01148 | NA | 16582 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-07 | NA | 100% | 2018-11-30 | 100% | NA | NA | 100% |  |  | 2018-11-07 | 2018-12-07 | Sous-poste | Sous-poste | 2018-11-12 | 2018-12-12 | 2018-12-12 |  | Allemagne |  | O |  | 1 | #VALUE! | N | N | 12 | 2018 | 8 | 2018 | 49 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2798763910 | 2018-12-03 | FABRICATION | SATAIR | OPTICAL FIBER | 27987639 | NON-SPARES | 10 | 1 | CRIT | D9550303100195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-06 | 2018-12-12 | Sous-poste | Sous-poste | 2018-12-10 | 2018-12-14 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2018 | 50 | 12 | 2018 | 0 | 0 | 0 | 0 | COL | 0 | 0
2775641610 | 2018-04-20 | HA/REVENTE | SATAIR | PLATE ASSY | 27756416 | NON-SPARES | 10 | 2 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-12 | NA | 100% | 2018-12-05 | 100% | NA | NA | 100% |  |  | 2018-12-12 | 2018-12-12 | Sous-poste | Sous-poste | 2018-12-17 | 2018-12-17 | 2018-12-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2018 | 4 | 2018 | 50 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791824010 | 2018-09-21 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27918240 | NON-SPARES | 10 | 27 | RTN | D9251805700000 | IS0032776S | NA | 16585 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-12 | NA | 100% | 2018-11-21 | 100% | NA | NA | 100% |  |  | 2018-12-12 | 2018-12-12 | Sous-poste | Sous-poste | 2018-12-17 | 2018-12-17 | 2018-12-17 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2018 | 9 | 2018 | 50 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791346710 | 2018-09-14 | FABRICATION | SATAIR | 517 | 27913467 | NON-SPARES | 10 | 1 | AOG | WF417AFACAAE | 0 | NON PRESENT INDUS | 16992 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-13 | 100% | NA | NA | 5.556% |  |  | 2018-09-12 | 2018-12-13 | Sous-poste | Sous-poste | 2018-09-14 | 2018-12-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 50 | 12 | 2018 | 0.205 | 1.7325 | 0.43312 | 2.1656 | LAB | 0 | 0
2791376210 | 2018-09-16 | FABRICATION | SATAIR | 517 | 27913762 | NON-SPARES | 10 | 1 | AOG | WF417AFACAAE | 0 | NON PRESENT INDUS | 16992 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-13 | 100% | NA | NA | 5.556% |  |  | 2018-09-13 | 2018-12-13 | Sous-poste | Sous-poste | 2018-09-16 | 2018-12-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 9 | 2018 | 50 | 12 | 2018 | 0.205 | 1.7325 | 0.43312 | 2.1656 | LAB | 0 | 0
27988635 279990399 | 2018-12-04 | FABRICATION | SATAIR | 518 | 27988635 27999039 | NON-SPARES | 9 | 1 | AOG | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-14 | 2018-12-14 | Sous-poste | Sous-poste | 2018-12-18 | 2018-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 12 | 2018 | 50 | 12 | 2018 | 0.205 | 1.7325 | 0.43312 | 2.1656 | LAB | 0 | 0
490003686430 | 2014-01-01 | HA/REVENTE | STELIA | EMBASE ÉQUIPÉE | 4900036864 | NON-SPARES | 30 | 2 | EXP | S9251450200000 | 1QME*00170 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-17 | NA | 100% | 2018-12-04 | 100% | NA | NA | 100% |  |  | 2018-12-17 | 2018-12-17 | Sous-poste | Sous-poste | 2018-12-20 | 2018-12-20 | 2018-12-20 |  | Allemagne |  | O |  | 1 | #VALUE! | O | N | 12 | 2018 | 1 | 2014 | 51 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2801284810 | 2018-12-20 | HA/REVENTE | SATAIR | DUCT ASSY | 28012848 | NON-SPARES | 10 | 1 | AOG | A9252487900700 | 1STR*11045 | NA | 20245 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-19 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2018-12-18 | 2018-12-18 | Sous-poste | Sous-poste | 2018-12-20 | 2018-12-20 | 2018-12-20 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2018 | 12 | 2018 | 51 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794465410 | 2018-10-24 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 27944654 | NON-SPARES | 10 | 1 | CRIT | D9251863200000 | 1STR*10676 | NA | 18234 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-19 | NA | 100% | 2018-12-18 | 100% | NA | NA | 100% |  |  | 2018-11-20 | 2018-12-18 | Sous-poste | Sous-poste | 2018-11-22 | 2018-12-20 | 2018-12-20 |  | Allemagne |  | O |  | 0 | #VALUE! | N | N | 12 | 2018 | 10 | 2018 | 51 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
27947803010 | 2018-10-26 | FABRICATION | SATAIR | 56 | 27947803 | NON-SPARES | 010 | 5 | RTN | D9551005600695 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | 0% | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-18 | 2018-12-18 | Sous-poste | Sous-poste | 2018-12-22 | 2018-12-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 51 | 12 | 2018 | 1.025 | 9.3185 | 0.46593 | 9.7844 | COL | 0 | 0
2788228810 | 2018-08-14 | FABRICATION | SATAIR | 27 | 27882288 | NON-SPARES | 10 | 2 | AOG | D9551002700595 | IS0032094M | NON PRESENT INDUS | 16875 | LTE990013 => LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2018-12-19 | 100% | NA | NA | 5.556% |  |  | 2018-09-27 | 2018-12-19 | Sous-poste | Sous-poste | 2018-10-01 | 2018-12-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | O | N |  |  | 8 | 2018 | 51 | 12 | 2018 | 0.72 | 9.8346 | 1.2293 | 11.0639 | COL | 0 | 0
2798032510 | 2018-11-26 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27980325 | NON-SPARES | 10 | 27 | AOG | D9251805800000 | IS0032777S | NA | 19343 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-12-21 | NA | 100% | 2018-12-19 | 100% | NA | NA | 100% |  |  | 2018-12-25 | 2018-12-20 | Sous-poste | Sous-poste | 2018-12-27 | 2018-12-24 | 2018-12-24 |  | Allemagne |  | O |  | 0 | #VALUE! | O | N | 12 | 2018 | 11 | 2018 | 51 | 12 | 2018 | 0 | 0 | 0 | 0 | NA | 0 | 0
2742366110 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423661 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990075 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-12-21 | Sous-poste | Sous-poste | 2017-11-21 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2753012310 | 2017-08-24 | FABRICATION | SATAIR | 117 | 27530123 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990076 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-12-21 | Sous-poste | Sous-poste | 2017-11-21 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 8 | 2017 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364310 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423643 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990090 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2018-12-21 | Sous-poste | Sous-poste | 2017-11-21 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 4 | 2017 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764897110 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648971 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990046 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2018-12-21 | Sous-poste | Sous-poste | 2018-03-01 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764899210 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648992 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990047 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2018-12-21 | Sous-poste | Sous-poste | 2018-03-01 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764899310 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648993 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990050 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2018-12-21 | Sous-poste | Sous-poste | 2018-03-01 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 1 | 2018 | 51 | 12 | 2018 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2791555810 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915558 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2018-12-21 | Sous-poste | Sous-poste | 2018-10-15 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 9 | 2018 | 51 | 12 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791558110 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915581 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2018-12-21 | Sous-poste | Sous-poste | 2018-10-15 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 9 | 2018 | 51 | 12 | 2018 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2792608810 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926088 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-20 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2018-12-21 | Sous-poste | Sous-poste | 2018-11-15 | 2018-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | O | N |  |  | 10 | 2018 | 51 | 12 | 2018 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791555910 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915559 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-31 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2019-01-01 | Sous-poste | Sous-poste | 2018-10-15 | 2019-01-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 1 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791558320 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915583 | NON-SPARES | 20 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-10-10 | 2019-01-01 | Sous-poste | Sous-poste | 2018-10-15 | 2019-01-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 1 | 1 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2792609610 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926096 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2018-12-31 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2019-01-01 | Sous-poste | Sous-poste | 2018-11-15 | 2019-01-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 1 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2783975910 | 2018-07-03 | FABRICATION | SATAIR | 40 | 27839759 | NON-SPARES | 10 | 3 | RTN | D9551004000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-08 | 2019-01-02 | Sous-poste | Sous-poste | 2019-01-11 | 2019-01-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 1 | 1 | 2019 | 0.615 | 35.6458 | 2.9705 | 38.6163 | COL | 0 | 0
2789500710 | 2018-08-27 | FABRICATION | SATAIR | BUNDLE | 27895007 | NON-SPARES | 10 | 2 | EXP | V9251241700095 | 0 | NON PRESENT INDUS | 18957 | 185575-1 185575-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-01 | 100% | NA | NA | 5.556% |  |  | 2018-09-03 | 2019-01-02 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 1 | 1 | 2019 | 0.41 | 2 | 0.1 | 2.1 | COL | 0 | 0
2789500810 | 2018-08-27 | FABRICATION | SATAIR | BUNDLE | 27895008 | NON-SPARES | 10 | 2 | EXP | V9251243600095 | 0 | NON PRESENT INDUS | 18957 | 185577-1 185577-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-01 | 100% | NA | NA | 5.556% |  |  | 2018-09-03 | 2019-01-02 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 1 | 1 | 2019 | 0.41 | 2 | 0.1 | 2.1 | COL | 0 | 0
2793831610 | 2018-10-17 | FABRICATION | SATAIR | BUNDLE | 27938316 | NON-SPARES | 10 | 2 | RTN | V9251241700095 | 0 | NON PRESENT INDUS | 18957 | 185628-1 185628-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-01 | 100% | NA | NA | 5.556% |  |  | 2018-11-14 | 2019-01-02 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 1 | 1 | 2019 | 0.41 | 2 | 0.1 | 2.1 | COL | 0 | 0
2793831710 | 2018-10-17 | FABRICATION | SATAIR | BUNDLE | 27938317 | NON-SPARES | 10 | 2 | RTN | V9251243600095 | 0 | NON PRESENT INDUS | NA | 201514-1 => 201514-2 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-01-01 | 100% | NA | NA | 5.556% |  |  | 2018-12-04 | 2019-01-02 | Sous-poste | Sous-poste | 2018-12-07 | 2019-01-07 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 1 | 1 | 2019 | 0.41 | 2 | 0.1 | 2.1 | COL | 0 | 0
2801254810 | 2018-12-20 | FABRICATION | SATAIR | 27 | 28012548 | NON-SPARES | 10 | 4 | AOG | D9551002700495 | 0 | NON PRESENT INDUS | 20243 | LTE990055 à LTE990058 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-03 | 100% | NA | NA | 5.556% |  |  | 2018-12-18 | 2019-01-03 | Sous-poste | Sous-poste | 2018-12-20 | 2019-01-07 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 1 | 1 | 2019 | 0.82 | 19.6692 | 1.2293 | 20.8985 | COL | 0 | 0
2764899410 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648994 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990077 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-02 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2019-01-03 | Sous-poste | Sous-poste | 2018-03-01 | 2019-01-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2018 | 1 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764899510 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648995 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990074 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-02 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2019-01-03 | Sous-poste | Sous-poste | 2018-03-01 | 2019-01-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2018 | 1 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2791556010 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915560 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-07 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2019-01-08 | Sous-poste | Sous-poste | 2018-10-15 | 2019-01-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 2 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791558510 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915585 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE99005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-07 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2019-01-08 | Sous-poste | Sous-poste | 2018-10-15 | 2019-01-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 2 | 1 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
27926118 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926118 | NON-SPARES |  | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-11-12 | 2019-01-08 | Sous-poste | Sous-poste | 2018-11-15 | 2019-01-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 2 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2787158710 | 2018-08-06 | FABRICATION | SATAIR | JACK ASSY | 27871587 | NON-SPARES | 10 | 2 | EXP | F7161001100001 | 0 | NON PRESENT INDUS | 17020 | 133717-1 => 133717-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-07 | 100% | NA | NA | 5.556% |  |  | 2018-10-30 | 2019-01-08 | Sous-poste | Sous-poste | 2018-11-02 | 2019-01-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0.3732 | 3.0752 | 0.15376 | 3.229 | COL | 0 | 0
2788065510 | 2018-08-13 | FABRICATION | SATAIR | PROTECTION CAP | 27880655 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 17018 | 133608-1 => 133608-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-07 | 100% | NA | NA | 5.556% |  |  | 2019-01-01 | 2019-01-08 | Sous-poste | Sous-poste | 2019-01-04 | 2019-01-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2777991210 | 2018-05-11 | HA/REVENTE | SATAIR | PLATE ASSY | 27779912 | NON-SPARES | 10 | 3 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-08 | NA | 100% | 2019-01-04 | 100% | NA | NA | 100% |  |  | 2019-01-08 | 2019-01-08 | Sous-poste | Sous-poste | 2019-01-11 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2781148010 | 2018-06-07 | HA/REVENTE | SATAIR | FLANGE ASSY | 27811480 | NON-SPARES | 10 | 12 | RTN | D9251127600000 | IS0008826S | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-08 | NA | 100% | 2019-01-04 | 100% | NA | NA | 100% |  |  | 2019-01-08 | 2019-01-08 | Sous-poste | Sous-poste | 2019-01-11 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794135110 | 2018-10-19 | FABRICATION | SATAIR | 45 | 27941351 | NON-SPARES | 10 | 2 | CRIT | D9551004500495 | 0 | NON PRESENT INDUS | 18286 | LTE990001 LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-09 | 100% | NA | NA | 5.556% |  |  | 2018-10-24 | 2019-01-09 | Sous-poste | Sous-poste | 2018-10-26 | 2019-01-11 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 2 | 1 | 2019 | 0.41 | 26.2164 | 3.2771 | 29.4934 | COL | 0 | 0
682079711 | 2019-01-03 | FABRICATION | AD&S | 48 | 6820797 | NON-SPARES | 11 | 1 | AOG | MB041ACAAAAB | IS0032203M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-11 | 2019-01-09 | Sous-poste | Sous-poste | 2019-01-15 | 2019-01-11 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 2 | 1 | 2019 | 0.205 | 2.96 | 0.74 | 3.7 | COL | 0 | 0
2789499910 | 2018-08-27 | HA/REVENTE | SATAIR | BRACKET | 27894999 | NON-SPARES | 10 | 2 | AOG | V9251137920000 | 1STR*10969 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-09-04 | 2019-01-09 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501010 | 2018-08-27 | HA/REVENTE | SATAIR | BRACKET | 27895010 | NON-SPARES | 10 | 4 | AOG | V9251128220000 | 1STR*10971 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-09-04 | 2019-01-09 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789502110 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. ANGLE | 27895021 | NON-SPARES | 10 | 2 | AOG | V9251155500000 | 1STR*10978 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-09-04 | 2019-01-09 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793827510 | 2014-01-01 | HA/REVENTE | SATAIR | BRACKET | 27938275 | NON-SPARES | 10 | 2 | AOG | V9251137920000 | 1STR*10969 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793831810 | 2014-01-01 | HA/REVENTE | SATAIR | BRACKET | 27938318 | NON-SPARES | 10 | 4 | AOG | V9251128220000 | 1STR*10971 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832910 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. ANGLE | 27938329 | NON-SPARES | 10 | 2 | AOG | V9251155500000 | 1STR*10978 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793831910 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. ANGLE | 27938319 | NON-SPARES | 10 | 2 | AOG | V9251156800000 | 1STR*10972 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-08 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832510 | 2014-01-01 | HA/REVENTE | SATAIR | BRACKET | 27938325 | NON-SPARES | 10 | 2 | AOG | V9251157220000 | 1STR*10974 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-08 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832810 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. BRACKET | 27938328 | NON-SPARES | 10 | 6 | AOG | V9251120300000 | 1STR*10977 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-08 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793832610 | 2014-01-01 | HA/REVENTE | SATAIR | EQ. ANGLE | 27938326 | NON-SPARES | 10 | 2 | AOG | V9251157100000 | 1STR*10975 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-10 | NA | 100% | 2019-01-16 | 100% | NA | NA | 100% |  |  | 2018-11-15 | 2019-01-09 | Sous-poste | Sous-poste | 2018-11-18 | 2019-01-11 | 2019-01-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802589410 | 2019-01-09 | FABRICATION | SATAIR | PLACARD | 28025894 | NON-SPARES | 10 | 1 | AOG | D5211034722800 | 0 | NON PRESENT INDUS | NA | 239241-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-01-14 | 100% | NA | NA | 5.556% |  |  | 2019-01-14 | 2019-01-10 | Sous-poste | Sous-poste | 2019-01-16 | 2019-01-14 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 2 | 1 | 2019 | 0.205 | 0 | 0 | 0 | NA | 0 | 0
2796875510 | 2018-11-16 | FABRICATION | SATAIR | 27 | 27968755 | NON-SPARES | 10 | 1 | EXP | D9551002700595 | IS0032094M | NON PRESENT INDUS | 19079 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-09 | 100% | NA | NA | 5.556% |  |  | 2018-12-07 | 2019-01-10 | Sous-poste | Sous-poste | 2018-12-12 | 2019-01-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 2 | 1 | 2019 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2802082710 | 2019-01-03 | FABRICATION | SATAIR | PROTECTION CAP | 28020827 | NON-SPARES | 10 | 5 | EXP | F0003003000000 | IS0032144M | NON PRESENT INDUS | 20478 | 227005-1 => 227005-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-15 | 100% | NA | NA | 5.556% |  |  | 2019-01-16 | 2019-01-10 | Sous-poste | Sous-poste | 2019-01-20 | 2019-01-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 2 | 1 | 2019 | 0.0125 | 0.559 | 0.01118 | 0.57018 | NA | 0 | 0
280290651 | 2019-01-10 | FABRICATION | SATAIR | PLACARD | 28029065 | NON-SPARES | 1 | 1 | AOG | D5211034722900 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-15 | 2019-01-11 | Sous-poste | Sous-poste | 2019-01-17 | 2019-01-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 2 | 1 | 2019 | 0.205 | 0 | 0 | 0 | NA | 0 | 0
2789501110 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. ANGLE | 27895011 | NON-SPARES | 10 | 2 | EXP | V9251156800000 | 1STR*10972 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-09 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2019-01-11 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501410 | 2018-08-27 | HA/REVENTE | SATAIR | BRACKET | 27895014 | NON-SPARES | 10 | 2 | EXP | V9251157220000 | 1STR*10974 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-09 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2019-01-11 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789501810 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. ANGLE | 27895018 | NON-SPARES | 10 | 2 | EXP | V9251157100000 | 1STR*10975 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-09 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2019-01-11 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789502010 | 2018-08-27 | HA/REVENTE | SATAIR | EQ. BRACKET | 27895020 | NON-SPARES | 10 | 6 | EXP | V9251120300000 | 1STR*10977 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-09 | 100% | NA | NA | 100% |  |  | 2018-09-03 | 2019-01-11 | Sous-poste | Sous-poste | 2018-09-06 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003711610 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900037116 | NON-SPARES | 10 | 1 | EXP | S9251446520000 | 1STR*11044 | NA | 20222 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2019-01-11 | 2019-01-11 | Sous-poste | Sous-poste | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003711620 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 4900037116 | NON-SPARES | 20 | 1 | EXP | S9251083800000 | 1CMP*16129 | NA | 20222 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-11 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2019-01-11 | 2019-01-11 | Sous-poste | Sous-poste | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 2 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
278936491 | 2018-08-23 | FABRICATION | SATAIR | JACK | 27893649 | NON-SPARES | 1 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-09-19 | 2019-01-15 | Sous-poste | Sous-poste | 2018-09-22 | 2019-01-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 3 | 1 | 2019 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2792803510 | 2018-10-04 | FABRICATION | SATAIR | JACK | 27928035 | NON-SPARES | 10 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 17695 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-14 | 100% | NA | NA | 5.556% |  |  | 2018-10-31 | 2019-01-15 | Sous-poste | Sous-poste | 2018-11-03 | 2019-01-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 3 | 1 | 2019 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2781800510 | 2018-06-12 | FABRICATION | SATAIR | HARNAIS 1 P2T2 | 27818005 | NON-SPARES | 10 | 10 | RTN | F7161001200001 | 0 | NON PRESENT INDUS | 14415 | 060510-1 => 060510-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-14 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-01-15 | Sous-poste | Sous-poste | 2018-06-30 | 2019-01-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 1.929 | 20.819 | 0.52048 | 21.3395 | COL | 0 | 0
490003700310 | 2018-12-14 | FABRICATION | STELIA | CÂBLE | 4900037003 | NON-SPARES | 10 | 6 | EXP | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 222367-1 => 222367-6 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-01-14 | 100% | NA | NA | 5.556% |  |  | 2019-01-03 | 2019-01-15 | Sous-poste | Sous-poste | 2019-01-08 | 2019-01-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 3 | 1 | 2019 | 1.23 | 6 | 0.1 | 6.1 | NA | 0 | 0
490003705910 | 2018-12-19 | FABRICATION | STELIA | CÂBLE | 4900037059 | NON-SPARES | 10 | 4 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-09 | 2019-01-15 | Sous-poste | Sous-poste | 2019-01-14 | 2019-01-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 3 | 1 | 2019 | 0.82 | 4 | 0.1 | 4.1 | NA | 0 | 0
2782332810 | 2018-06-15 | FABRICATION | SATAIR | 117 | 27823328 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990070 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-16 | 100% | NA | NA | 5.556% |  |  | 2018-10-10 | 2019-01-17 | Sous-poste | Sous-poste | 2018-10-14 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049110 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830491 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990082 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-16 | 100% | NA | NA | 5.556% |  |  | 2018-10-16 | 2019-01-17 | Sous-poste | Sous-poste | 2018-10-19 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049340 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830493 | NON-SPARES | 40 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-10-16 | 2019-01-17 | Sous-poste | Sous-poste | 2018-10-19 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049510 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830495 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990084 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-16 | 100% | NA | NA | 5.556% |  |  | 2018-10-16 | 2019-01-17 | Sous-poste | Sous-poste | 2018-10-19 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049410 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830494 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990085 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-16 | 100% | NA | NA | 5.556% |  |  | 2018-11-14 | 2019-01-17 | Sous-poste | Sous-poste | 2018-11-19 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2782332910 | 2018-06-15 | FABRICATION | SATAIR | 117 | 27823329 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990071 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-16 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-01-17 | Sous-poste | Sous-poste | 2018-12-31 | 2019-01-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 3 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2792613110 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926131 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-21 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-01-22 | Sous-poste | Sous-poste | 2018-12-31 | 2019-01-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 4 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
HNC200024312027 | 2014-01-01 | HA/REVENTE | SATAIR | ARINC | HNC2000243120 | NON-SPARES | 27 | 1 | RTN | E0165D18A01X | 1CON*23500 | NA | 19867 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-22 | NA | 100% | 2019-01-15 | 100% | NA | NA | 100% |  |  | 2019-01-22 | 2019-01-22 | Sous-poste | Sous-poste | 2019-01-25 | 2019-01-25 | 2019-01-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27915589 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915589 | NON-SPARES |  | 1 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-11-13 | 2019-01-23 | Sous-poste | Sous-poste | 2018-11-15 | 2019-01-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 4 | 1 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
27915565 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915565 | NON-SPARES |  | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-13 | 2019-01-23 | Sous-poste | Sous-poste | 2018-12-15 | 2019-01-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 4 | 1 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2803363210 | 2019-01-15 | FABRICATION | SATAIR | 517 | 28033632 | NON-SPARES | 10 | 1 | AOG | WF417AFACAAE | 0 | NON PRESENT INDUS | 20792 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2019-01-11 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-15 | 2019-01-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2802066510 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. BRACKET | 28020665 | NON-SPARES | 10 | 1 | AOG | V9251120300000 | 1STR*10977 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-24 | NA | 100% | 2019-01-18 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-25 | 2019-01-25 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802066910 | 2019-01-03 | HA/REVENTE | SATAIR | BRACKET | 28020669 | NON-SPARES | 10 | 1 | AOG | V9251157220000 | 1STR*10974 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-24 | NA | 100% | 2019-01-18 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-25 | 2019-01-25 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802067210 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. ANGLE | 28020672 | NON-SPARES | 10 | 1 | AOG | V9251156800000 | 1STR*10972 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-24 | NA | 100% | 2019-01-18 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-25 | 2019-01-25 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802067510 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. ANGLE | 28020675 | NON-SPARES | 10 | 1 | AOG | V9251157100000 | 1STR*10975 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-24 | NA | 100% | 2019-01-18 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-25 | 2019-01-25 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2797275410 | 2018-11-19 | FABRICATION | SATAIR | PLATE ASSY | 27972754 | NON-SPARES | 10 | 8 | AOG | F9252008100000 | 0 | NON PRESENT INDUS | 19120 | 196920-1 => 196920-8 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2019-01-21 | 2019-01-23 | Sous-poste | Sous-poste | 2019-01-23 | 2019-01-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 4 | 1 | 2019 | 0 | 3.8336 | 0.04792 | 3.8815 | NA | 0 | 0
2709509710 | 2016-08-02 | FABRICATION | SATAIR | 117 | 27095097 | NON-SPARES | 10 | 13 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 437 | EFD990230 => EFD990242 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2016-08-15 | 2019-01-24 | Sous-poste | Sous-poste | 2016-08-18 | 2019-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2016 | 4 | 1 | 2019 | 2.665 | 49.595 | 0.95375 | 50.5487 | COL | 0 | 0
2764899610 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648996 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990079 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2019-01-24 | Sous-poste | Sous-poste | 2018-03-01 | 2019-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2018 | 4 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049610 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830496 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990086 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2018-12-05 | 2019-01-24 | Sous-poste | Sous-poste | 2018-12-09 | 2019-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 4 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2783049710 | 2018-06-22 | FABRICATION | SATAIR | 117 | 27830497 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990087 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2018-12-05 | 2019-01-24 | Sous-poste | Sous-poste | 2018-12-09 | 2019-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 4 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2784044610 | 2018-07-03 | FABRICATION | SATAIR | 117 | 27840446 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990073 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-23 | 100% | NA | NA | 5.556% |  |  | 2018-12-12 | 2019-01-24 | Sous-poste | Sous-poste | 2018-12-16 | 2019-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 4 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2802066810 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 28020668 | NON-SPARES | 10 | 1 | AOG | V9251156900000 | 1STR*10973 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-28 | NA | 100% | 2019-01-24 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-25 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-29 | 2019-01-29 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802067410 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 28020674 | NON-SPARES | 10 | 1 | AOG | V9251157300000 | 1STR*10979 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-28 | NA | 100% | 2019-01-24 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-25 | Sous-poste | Sous-poste | 2019-01-12 | 2019-01-29 | 2019-01-29 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2784402210 | 2018-07-06 | FABRICATION | SATAIR | 40 | 27844022 | NON-SPARES | 10 | 3 | RTN | D9551004000295 | 0 | NON PRESENT INDUS | 15132 | LTE990001 LTE990002 LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-24 | 100% | NA | NA | 5.556% |  |  | 2019-01-04 | 2019-01-25 | Sous-poste | Sous-poste | 2019-01-09 | 2019-01-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 4 | 1 | 2019 | 0.615 | 35.6458 | 2.9705 | 38.6163 | COL | 0 | 0
2724565610 | 2016-11-28 | FABRICATION | SATAIR | PLATE | 27245656 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-06-27 | 2019-01-28 | Sous-poste | Sous-poste | 2018-06-30 | 2019-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2016 | 5 | 1 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2753000010 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530000 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3625 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-25 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-01-28 | Sous-poste | Sous-poste | 2018-06-30 | 2019-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 5 | 1 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
490003703510 | 2018-12-18 | FABRICATION | STELIA | CABLE COAXIAL | 4900037035 | NON-SPARES | 10 | 5 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 20194 | 222700-1 => 222700-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-01-25 | 100% | NA | NA | 5.556% |  |  | 2019-01-28 | 2019-01-28 | Sous-poste | Sous-poste | 2019-01-31 | 2019-01-31 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 5 | 1 | 2019 | 0.963 | 3.7565 | 0.07513 | 3.8316 | NA | 0 | 0
490003686410 | 2018-12-03 | FABRICATION | STELIA | FAISCEAU | 4900036864 | NON-SPARES | 10 | 4 | EXP | S9110157200196 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-29 | 2019-01-29 | Sous-poste | Sous-poste | 2019-02-01 | 2019-02-01 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 5 | 1 | 2019 | 0.82 | 2.8 | 0.07 | 2.87 | NA | 0 | 0
2796050510 | 2018-11-09 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 27960505 | NON-SPARES | 10 | 6 | RTN | D9251805800000 | IS0032777S | NA | 18748 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-29 | NA | 100% | 2019-01-21 | 100% | NA | NA | 100% |  |  | 2019-01-29 | 2019-01-29 | Sous-poste | Sous-poste | 2019-02-01 | 2019-02-01 | 2019-02-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 5 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2796050310 | 2018-11-09 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 27960503 | NON-SPARES | 10 | 6 | RTN | D9251805700000 | IS0032776S | NA | 18748 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-29 | NA | 100% | 2019-01-21 | 100% | NA | NA | 100% |  |  | 2019-01-29 | 2019-01-29 | Sous-poste | Sous-poste | 2019-02-01 | 2019-02-01 | 2019-02-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 5 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003711630 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900037116 | NON-SPARES | 30 | 1 | EXP | S9251059700100 | 3STR*00061 | NA | 20222 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-29 | NA | 100% | 2019-01-24 | 100% | NA | NA | 100% |  |  | 2019-01-11 | 2019-01-29 | Sous-poste | Sous-poste | 2019-01-16 | 2019-02-01 | 2019-02-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 5 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2796076410 | 2018-11-09 | HA/REVENTE | SATAIR | TUBE | 27960764 | NON-SPARES | 10 | 1 | RTN | F9251110800300 | 1STR*10653 | NA | 18748 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-01-30 | NA | 100% | 2019-01-21 | 100% | NA | NA | 100% |  |  | 2019-01-30 | 2019-01-30 | Sous-poste | Sous-poste | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 5 | 1 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2802067610 | 2019-01-03 | HA/REVENTE | SATAIR | EQ. TORSION BAR | 28020676 | NON-SPARES | 10 | 1 | AOG | V9251157500000 | 1STR*10750 | NA | 20417 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-01 | NA | 100% | 2019-01-24 | 100% | NA | NA | 100% |  |  | 2019-01-10 | 2019-01-31 | Sous-poste | Sous-poste | 2019-01-12 | 2019-02-04 | 2019-02-04 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 5 | 1 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28043491600 | 2019-01-24 | FABRICATION | SATAIR | WIRE-BONDING | 28043491 | NON-SPARES | 600 | 2 | AOG | F0003008100000 | IS0032145M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-01-24 | 2019-01-31 | Sous-poste | Sous-poste | 2019-01-27 | 2019-02-04 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 5 | 1 | 2019 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2804349810 | 2019-01-24 | FABRICATION | SATAIR | WIRE-BONDING | 28043498 | NON-SPARES | 10 | 1 | AOG | F0003008100200 | IS0032147M | NON PRESENT INDUS | NA | 252284-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-01-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-24 | 2019-01-31 | Sous-poste | Sous-poste | 2019-01-27 | 2019-02-04 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 5 | 1 | 2019 | 0.2085 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2804349910 | 2019-01-24 | FABRICATION | SATAIR | LEAD-BONDING | 28043499 | NON-SPARES | 10 | 1 | AOG | F0003008100300 | IS0032149M | NON PRESENT INDUS | NA | 252286-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-01-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-24 | 2019-01-31 | Sous-poste | Sous-poste | 2019-01-27 | 2019-02-04 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 5 | 1 | 2019 | 0.2075 | 0.2383 | 0.059575 | 0.29788 | NA | 0 | 0
27423658040 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423658 | NON-SPARES | 040 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-02-07 | 2019-01-31 | Sous-poste | Sous-poste | 2018-02-10 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048810 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610488 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990064 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-30 | 100% | NA | NA | 5.556% |  |  | 2018-02-07 | 2019-01-31 | Sous-poste | Sous-poste | 2018-02-10 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2017 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764899710 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648997 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990080 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-30 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2019-01-31 | Sous-poste | Sous-poste | 2018-03-01 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2018 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2764899810 | 2018-01-04 | FABRICATION | SATAIR | 117 | 27648998 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990081 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-30 | 100% | NA | NA | 5.556% |  |  | 2018-02-26 | 2019-01-31 | Sous-poste | Sous-poste | 2018-03-01 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2018 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365010 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423650 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990023 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-30 | 100% | NA | NA | 5.556% |  |  | 2018-03-13 | 2019-01-31 | Sous-poste | Sous-poste | 2018-03-16 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2782333010 | 2018-06-15 | FABRICATION | SATAIR | 117 | 27823330 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990072 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-30 | 100% | NA | NA | 5.556% |  |  | 2018-10-08 | 2019-01-31 | Sous-poste | Sous-poste | 2018-10-11 | 2019-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 5 | 1 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2791558710 | 2018-09-18 | FABRICATION | SATAIR | 62 | 27915587 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE99006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-31 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2019-02-01 | Sous-poste | Sous-poste | 2018-11-15 | 2019-02-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 5 | 2 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2792612810 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926128 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-31 | 100% | NA | NA | 5.556% |  |  | 2018-11-12 | 2019-02-01 | Sous-poste | Sous-poste | 2018-11-15 | 2019-02-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 5 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2791556210 | 2018-09-18 | FABRICATION | SATAIR | 60 | 27915562 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-01-31 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-01 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 5 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2802333030 | 2019-01-07 | FABRICATION | SATAIR | 27 | 28023330 | NON-SPARES | 30 | 2 | EXP | D9551002700595 | IS0032094M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-02-01 | 2019-02-01 | Sous-poste | Sous-poste | 2019-02-06 | 2019-02-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 5 | 2 | 2019 | 0.72 | 9.8346 | 1.2293 | 11.0639 | COL | 0 | 0
2803368010 | 2019-01-15 | FABRICATION | SATAIR | 517 | 28033680 | NON-SPARES | 10 | 1 | AOG | WF417AFACAAE | 0 | NON PRESENT INDUS | 20792 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-04 | 100% | NA | NA | 5.556% |  |  | 2019-01-11 | 2019-02-04 | Sous-poste | Sous-poste | 2019-01-15 | 2019-02-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 6 | 2 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2804478910 | 2019-01-28 | HA/REVENTE | SATAIR | SEAL | 28044789 | NON-SPARES | 10 | 8 | CRIT | A9252483620000 | 1QME*16563 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-05 | NA | 100% | 2019-01-31 | 100% | NA | NA | 100% |  |  | 2019-02-04 | 2019-02-04 | Sous-poste | Sous-poste | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 6 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2793471210 | 2018-10-12 | HA/REVENTE | SATAIR | PLATE ASSY | 27934712 | NON-SPARES | 10 | 5 | EXP | L9251321500000 | 1STR*01089 | NA | 17880 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-05 | NA | 100% | 2019-01-29 | 100% | NA | NA | 100% |  |  | 2018-11-07 | 2019-02-05 | Sous-poste | Sous-poste | 2018-11-11 | 2019-02-08 | 2019-02-08 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2753000110 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530001 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3626 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2753000210 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530002 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3627 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2753000310 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530003 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3628 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2753000410 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530004 | NON-SPARES | 10 | 1 | EXP | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3629 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2753000510 | 2017-08-24 | FABRICATION | SATAIR | PLATE | 27530005 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3630 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2761048110 | 2017-11-21 | FABRICATION | SATAIR | PLATE | 27610481 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3631 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-05 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-06 | Sous-poste | Sous-poste | 2018-06-30 | 2019-02-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2017 | 6 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2740540910 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405409 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-07 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2740542010 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405420 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-07 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365510 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423655 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990026 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-07 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742365710 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423657 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990028 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-07 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2742364910 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423649 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990022 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-07 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2761048410 | 2017-11-21 | FABRICATION | SATAIR | 117 | 27610484 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990066 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2018-03-13 | 2019-02-07 | Sous-poste | Sous-poste | 2018-03-16 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2017 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2782332710 | 2018-06-15 | FABRICATION | SATAIR | 117 | 27823327 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990069 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-06 | 2019-02-07 | Sous-poste | Sous-poste | 2018-09-11 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 6 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2780860210 | 2018-06-05 | FABRICATION | SATAIR | 117 | 27808602 | NON-SPARES | 10 | 2 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 14180 | LTE990067 => LTE990068 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-06 | 100% | NA | NA | 5.556% |  |  | 2018-09-11 | 2019-02-07 | Sous-poste | Sous-poste | 2018-09-14 | 2019-02-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 6 | 2 | 2019 | 0.41 | 7.63 | 0.95375 | 8.5838 | COL | 0 | 0
2792613710 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926137 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-07 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-08 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792616310 | 2018-10-02 | FABRICATION | SATAIR | 60 | 27926163 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-07 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-08 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792618110 | 2018-10-02 | FABRICATION | SATAIR | 62 | 27926181 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-07 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-08 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2792844210 | 2018-10-05 | FABRICATION | SATAIR | 40 | 27928442 | NON-SPARES | 10 | 1 | RTN | D9551004000395 | 0 | NON PRESENT INDUS | 17823 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-02-07 | 100% | NA | NA | 5.556% |  |  | 2019-01-23 | 2019-02-08 | Sous-poste | Sous-poste | 2019-01-28 | 2019-02-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0.205 | 11.8819 | 2.9705 | 14.8524 | COL | 0 | 0
2794465210 | 2018-10-24 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 27944652 | NON-SPARES | 10 | 1 | EXP | D9251863200000 | 1STR*10676 | NA | 18234 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-08 | NA | 100% | 2019-01-07 | 100% | NA | NA | 100% |  |  | 2018-11-19 | 2019-02-08 | Sous-poste | Sous-poste | 2018-11-22 | 2019-02-13 | 2019-02-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 6 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2787431410 | 2018-08-08 | HA/REVENTE | SATAIR | FLANGE ASSY | 27874314 | NON-SPARES | 10 | 6 | RTN | D9251127600000 | IS0008826S | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-08 | NA | 100% | 2019-02-02 | 100% | NA | NA | 100% |  |  | 2019-02-08 | 2019-02-08 | Sous-poste | Sous-poste | 2019-02-13 | 2019-02-13 | 2019-02-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 6 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2804521910 | 2019-01-28 | FABRICATION | SATAIR | BUNDLE | 28045219 | NON-SPARES | 10 | 1 | AOG | D9000095029695 | 0 | NON PRESENT INDUS | NA | 263854-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-02-11 | 100% | NA | NA | 5.556% |  |  | 2019-01-25 | 2019-02-11 | Sous-poste | Sous-poste | 2019-01-29 | 2019-02-13 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792844110 | 2018-10-05 | FABRICATION | SATAIR | 40 | 27928441 | NON-SPARES | 10 | 1 | RTN | D9551004000395 | 0 | NON PRESENT INDUS | 17823 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-02-08 | 100% | NA | NA | 5.556% |  |  | 2019-01-16 | 2019-02-11 | Sous-poste | Sous-poste | 2019-01-21 | 2019-02-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 7 | 2 | 2019 | 0.205 | 11.8819 | 2.9705 | 14.8524 | COL | 0 | 0
490003724310 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE 23VU | 4900037243 | NON-SPARES | 10 | 2 | EXP | S9251059700100 | 3STR*00061 | NA | 20222 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-12 | NA | 100% | 2019-02-11 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-02-12 | Sous-poste | Sous-poste | 2019-02-15 | 2019-02-15 | 2019-02-15 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792617810 | 2018-10-02 | FABRICATION | SATAIR | 62 | 27926178 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-12 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-13 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 7 | 2 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2740543410 | 2017-04-07 | FABRICATION | SATAIR | 117 | 27405434 | NON-SPARES | 10 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | 10623 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-12 | 100% | NA | NA | 5.556% |  |  | 2017-11-16 | 2019-02-13 | Sous-poste | Sous-poste | 2017-11-21 | 2019-02-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 7 | 2 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
490003710510 | 2018-12-19 | FABRICATION | STELIA | CÂBLE | 4900037105 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 223523-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-02-12 | 100% | NA | NA | 5.556% |  |  | 2019-02-13 | 2019-02-13 | Sous-poste | Sous-poste | 2019-02-18 | 2019-02-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 7 | 2 | 2019 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2782123010 | 2018-06-14 | HA/REVENTE | SATAIR | PLATE ASSY | 27821230 | NON-SPARES | 10 | 8 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-13 | NA | 100% | 2019-02-06 | 100% | NA | NA | 100% |  |  | 2019-02-13 | 2019-02-13 | Sous-poste | Sous-poste | 2019-02-18 | 2019-02-18 | 2019-02-18 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003710520 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE SOUDÉE | 4900037105 | NON-SPARES | 20 | 6 | RTN | S9251080800100 | 1STR*10178 | NA | 20220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-13 | NA | 100% | 2019-01-24 | 100% | NA | NA | 100% |  |  | 2019-02-13 | 2019-02-13 | Sous-poste | Sous-poste | 2019-02-18 | 2019-02-18 | 2019-02-18 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792613510 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926135 | NON-SPARES | 10 | 1 | AOG | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-14 | 100% | NA | NA | 5.556% |  |  | 2018-12-27 | 2019-02-14 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 7 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792616210 | 2018-10-02 | FABRICATION | SATAIR | 60 | 27926162 | NON-SPARES | 10 | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-14 | 100% | NA | NA | 5.556% |  |  | 2018-12-27 | 2019-02-14 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 7 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
27847916 2796183610 | 2018-07-11 | FABRICATION | SATAIR | 119 | 27847916 27961836 | NON-SPARES | 10 | 1 | EXP | D9550011900195 | 0 | NON PRESENT INDUS | 15619 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-13 | 100% | NA | NA | 5.556% |  |  | 2018-12-07 | 2019-02-14 | Sous-poste | Sous-poste | 2018-12-12 | 2019-02-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 7 | 2 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2806854110 | 2019-02-18 | HA/REVENTE | SATAIR | CONNECTOR | 28068541 | NON-SPARES | 10 | 1 | AOG | E0165D16A40X | 1CON*01189 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-14 | 2019-02-15 | Sous-poste | Sous-poste | 2019-02-18 | 2019-02-19 | 2019-02-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2806854120 | 2019-02-18 | HA/REVENTE | SATAIR | CONNECTOR | 28068541 | NON-SPARES | 20 | 1 | AOG | E0165D16A00X | 1CON*01189 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-15 | 2019-02-15 | Sous-poste | Sous-poste | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2807203810 | 2019-02-19 | HA/REVENTE | SATAIR | PLATE ASSY-FRONT | 28072038 | NON-SPARES | 10 | 1 | CRIT | A9251000900000 | 1STR*11122 | NA | 22052 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-18 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-15 | 2019-02-15 | Sous-poste | Sous-poste | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 7 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792613910 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926139 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-18 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-19 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 8 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792616610 | 2018-10-02 | FABRICATION | SATAIR | 60 | 27926166 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 16961 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-18 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-19 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 8 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792618210 | 2018-10-02 | FABRICATION | SATAIR | 62 | 27926182 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-18 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-19 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 8 | 2 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2802320710 | 2019-01-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28023207 | NON-SPARES | 10 | 2 | RTN | A9251152500000 | IS0031658S | NA | 20645 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-20 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-20 | 2019-02-20 | Sous-poste | Sous-poste | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 8 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2802320910 | 2019-01-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28023209 | NON-SPARES | 10 | 1 | RTN | A9251151000000 | 1STR*11047 | NA | 20633 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-20 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-20 | 2019-02-20 | Sous-poste | Sous-poste | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 8 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2802321210 | 2019-01-07 | HA/REVENTE | SATAIR | PLATE ASSY-BLANKING | 28023212 | NON-SPARES | 10 | 1 | RTN | A9252235700000 | 1STR*11048 | NA | 20631 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-20 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-02-20 | 2019-02-20 | Sous-poste | Sous-poste | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 8 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2778713410 | 2018-05-18 | FABRICATION | SATAIR | 313 | 27787134 | NON-SPARES | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 13807 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 0 | 0% | NA | NA | 0% |  |  | 2018-08-10 | 2019-02-21 | Sous-poste | Sous-poste | 2018-08-15 | 2019-02-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2018 | 8 | 2 | 2019 | 0.51 | 3.85 | 0.9625 | 4.8125 | COL | 0 | 0
2796144910 | 2018-11-10 | FABRICATION | SATAIR | 119 | 27961449 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 18824 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-20 | 100% | NA | NA | 5.556% |  |  | 2018-12-19 | 2019-02-21 | Sous-poste | Sous-poste | 2018-12-23 | 2019-02-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 8 | 2 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2796145010 | 2018-11-10 | FABRICATION | SATAIR | 119 | 27961450 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 18824 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-20 | 100% | NA | NA | 5.556% |  |  | 2018-12-19 | 2019-02-21 | Sous-poste | Sous-poste | 2018-12-23 | 2019-02-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 8 | 2 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2792614110 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926141 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-22 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-25 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 9 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792617420 | 2018-10-02 | FABRICATION | SATAIR | 60 | 27926174 | NON-SPARES | 20 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-26 | 2019-02-25 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 9 | 2 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792618310 | 2018-10-02 | FABRICATION | SATAIR | 62 | 27926183 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-22 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-02-25 | Sous-poste | Sous-poste | 2018-12-31 | 2019-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 9 | 2 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2804965310 | 2019-02-01 | FABRICATION | SATAIR | 500 | 28049653 | NON-SPARES | 10 | 1 | RTN | D9551050000195 | 0 | NON PRESENT INDUS | 21535 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-02-22 | 100% | NA | NA | 5.556% |  |  | 2019-02-05 | 2019-02-25 | Sous-poste | Sous-poste | 2019-02-08 | 2019-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 9 | 2 | 2019 | 0.66 | 5.0503 | 1.2626 | 6.3129 | COL | 0 | 0
2788065610 | 2018-08-13 | FABRICATION | SATAIR | PROTECTION CAP | 27880656 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 17018 | 133555-1 => 133555-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-02-22 | 100% | NA | NA | 5.556% |  |  | 2019-02-25 | 2019-02-25 | Sous-poste | Sous-poste | 2019-02-28 | 2019-02-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 9 | 2 | 2019 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2799101010 | 2018-12-06 | HA/REVENTE | SATAIR | TUBE | 27991010 | NON-SPARES | 10 | 2 | RTN | F9251110800900 | 1STR*10658 | NA | 19824 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-27 | NA | 100% | 2019-02-14 | 100% | NA | NA | 100% |  |  | 2019-02-27 | 2019-02-27 | Sous-poste | Sous-poste | 2019-03-02 | 2019-03-02 | 2019-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 9 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2799101110 | 2018-12-06 | HA/REVENTE | SATAIR | TUBE | 27991011 | NON-SPARES | 10 | 2 | RTN | F9251110801200 | 1STR*00294 | NA | 19824 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-27 | NA | 100% | 2019-02-14 | 100% | NA | NA | 100% |  |  | 2019-02-27 | 2019-02-27 | Sous-poste | Sous-poste | 2019-03-02 | 2019-03-02 | 2019-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 9 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2799100910 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27991009 | NON-SPARES | 10 | 2 | RTN | F9251110800400 | 1STR*10657 | NA | 19824 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-27 | NA | 100% | 2019-02-14 | 100% | NA | NA | 100% |  |  | 2019-02-27 | 2019-02-27 | Sous-poste | Sous-poste | 2019-03-02 | 2019-03-02 | 2019-03-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 9 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2774443110 | 2018-04-12 | FABRICATION | SATAIR | PLATE | 27744431 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3696 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-02-28 | Sous-poste | Sous-poste | 2018-06-30 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2018 | 9 | 2 | 2019 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2780554210 | 2018-06-01 | FABRICATION | SATAIR | PLATE | 27805542 | NON-SPARES | 10 | 4 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3684 -> LTE3687 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-07-11 | 2019-02-28 | Sous-poste | Sous-poste | 2018-07-16 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 9 | 2 | 2019 | 0 | 12.5488 | 0.72 | 13.2688 | NA | 0 | 0
2787246710 | 2018-08-07 | FABRICATION | SATAIR | PLATE | 27872467 | NON-SPARES | 10 | 4 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3688 -> LTE3691 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-09-17 | 2019-02-28 | Sous-poste | Sous-poste | 2018-09-20 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 9 | 2 | 2019 | 0 | 12.5488 | 0.72 | 13.2688 | NA | 0 | 0
2790954510 | 2018-09-11 | FABRICATION | SATAIR | PLATE | 27909545 | NON-SPARES | 10 | 2 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3697 -> LTE3698 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-10-23 | 2019-02-28 | Sous-poste | Sous-poste | 2018-10-26 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 9 | 2 | 2019 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
2788187910 | 2018-08-14 | FABRICATION | SATAIR | PLATE | 27881879 | NON-SPARES | 10 | 2 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3692 -> LTE3693 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-10-24 | 2019-02-28 | Sous-poste | Sous-poste | 2018-10-27 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 9 | 2 | 2019 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
2791299610 | 2018-09-14 | FABRICATION | SATAIR | PLATE | 27912996 | NON-SPARES | 10 | 2 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 17974 | LTE3694 -> LTE3695 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-02-27 | 100% | NA | NA | 5.556% |  |  | 2018-10-24 | 2019-02-28 | Sous-poste | Sous-poste | 2018-10-29 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 9 | 2 | 2019 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
2795065310 | 2018-10-30 | FABRICATION | SATAIR | PLATE | 27950653 | NON-SPARES | 10 | 2 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 18833 | LTE3699 => LTE3700 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-06-16 | 100% | NA | NA | 5.556% |  |  | 2018-12-11 | 2019-02-28 | Sous-poste | Sous-poste | 2018-12-14 | 2019-03-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 9 | 2 | 2019 | 0 | 6.2744 | 0.72 | 6.9944 | NA | 0 | 0
2799101210 | 2018-12-06 | HA/REVENTE | SATAIR | COVER ASSY | 27991012 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 19825 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-02-28 | NA | 100% | 2019-02-25 | 100% | NA | NA | 100% |  |  | 2019-02-28 | 2019-02-28 | Sous-poste | Sous-poste | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 9 | 2 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2803629210 | 2014-01-01 | HA/REVENTE | SATAIR | CROSSBEAM | 28036292 | NON-SPARES | 10 | 1 | AOG | L9251266920001 | 1STR*10884 | NA | 20866 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-07 | NA | 100% | 2019-03-04 | 100% | NA | NA | 100% |  |  | 2019-02-06 | 2019-03-06 | Sous-poste | Sous-poste | 2019-02-08 | 2019-03-08 | 2019-03-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 10 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003715110 | 2018-12-21 | FABRICATION | STELIA | CÂBLE | 4900037151 | NON-SPARES | 10 | 4 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 226834-1 => 226834-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-06 | 100% | NA | NA | 5.556% |  |  | 2019-03-07 | 2019-03-07 | Sous-poste | Sous-poste | 2019-03-12 | 2019-03-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 10 | 3 | 2019 | 0.82 | 4 | 0.1 | 4.1 | NA | 0 | 0
2775609410 | 2018-04-20 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27756094 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-07 | NA | 100% | 2018-12-07 | 100% | NA | NA | 100% |  |  | 2018-12-14 | 2019-03-07 | Sous-poste | Sous-poste | 2018-12-19 | 2019-03-12 | 2019-03-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2018 | 10 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2775608810 | 2018-04-20 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27756088 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-07 | NA | 100% | 2018-12-11 | 100% | NA | NA | 100% |  |  | 2018-12-18 | 2019-03-07 | Sous-poste | Sous-poste | 2018-12-21 | 2019-03-12 | 2019-03-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2018 | 10 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003746110 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900037461 | NON-SPARES | 10 | 1 | RTN | S9251458000000 | 3STR*01167 | NA | 21492 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-08 | NA | 100% | 2019-03-08 | 100% | NA | NA | 100% |  |  | 2019-03-05 | 2019-03-08 | Sous-poste | Sous-poste | 2019-03-08 | 2019-03-13 | 2019-03-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 10 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003764020 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900037640 | NON-SPARES | 20 | 1 | EXP | S9251458000000 | 3STR*01167 | NA | 21492 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-08 | NA | 100% | 2019-03-08 | 100% | NA | NA | 100% |  |  | 2019-03-06 | 2019-03-08 | Sous-poste | Sous-poste | 2019-03-11 | 2019-03-13 | 2019-03-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 10 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2805778510 | 2019-02-11 | FABRICATION | SATAIR | 518 | 28057785 | NON-SPARES | 10 | 1 | AOG | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 21811 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-11 | Sous-poste | Sous-poste | 2019-02-12 | 2019-03-13 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 11 | 3 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
HNC200024503612 | 2014-01-01 | HA/REVENTE | SATAIR | ARINC | HNC2000245036 | NON-SPARES | 12 | 1 | RTN | E0165D18A01X | 1CON*23500 | NA | 21848 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-11 | NA | 100% | 2019-03-08 | 100% | NA | NA | 100% |  |  | 2019-03-11 | 2019-03-11 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 11 | 3 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2792614410 | 2018-10-02 | FABRICATION | SATAIR | 61 | 27926144 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 16961 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-03-12 | Sous-poste | Sous-poste | 2018-12-31 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792617550 | 2018-10-02 | FABRICATION | SATAIR | 60 | 27926175 | NON-SPARES | 50 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-12-26 | 2019-03-12 | Sous-poste | Sous-poste | 2018-12-31 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2792618410 | 2018-10-02 | FABRICATION | SATAIR | 62 | 27926184 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 16961 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2018-12-26 | 2019-03-12 | Sous-poste | Sous-poste | 2018-12-31 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2794710410 | 2018-10-26 | FABRICATION | SATAIR | 61 | 27947104 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 18362 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-12 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794720110 | 2018-10-26 | FABRICATION | SATAIR | 60 | 27947201 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 18362 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-03-12 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794742310 | 2018-10-26 | FABRICATION | SATAIR | 62 | 27947423 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 18362 | LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-03-12 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
490003724810 | 2019-01-08 | FABRICATION | STELIA | CÂBLE | 4900037248 | NON-SPARES | 10 | 2 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 241816-1 => 241816-2 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-03-12 | 2019-03-12 | Sous-poste | Sous-poste | 2019-03-15 | 2019-03-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 11 | 3 | 2019 | 0.41 | 2 | 0.1 | 2.1 | NA | 0 | 0
2805553410 | 2019-02-07 | FABRICATION | SATAIR | 318 | 28055534 | NON-SPARES | 10 | 1 | CRIT | WF409ACABAAB | 0 | NON PRESENT INDUS | 21855 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-13 | 100% | NA | NA | 5.556% |  |  | 2019-02-12 | 2019-03-13 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 11 | 3 | 2019 | 0 | 3.255 | 0.81375 | 4.0687 | COL | 0 | 0
2807301510 | 2019-02-20 | HA/REVENTE | SATAIR | CROSSBEAM | 28073015 | NON-SPARES | 10 | 4 | AOG | L9251266920001 | 1STR*10884 | NA | 22096 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-14 | NA | 100% | 2019-03-13 | 100% | NA | NA | 100% |  |  | 2019-03-06 | 2019-03-13 | Sous-poste | Sous-poste | 2019-03-08 | 2019-03-15 | 2019-03-15 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 11 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794710710 | 2018-10-26 | FABRICATION | SATAIR | 61 | 27947107 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 18362 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-12 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-13 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794721230 | 2018-10-26 | FABRICATION | SATAIR | 60 | 27947212 | NON-SPARES | 30 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-03-08 | 2019-03-13 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794743020 | 2018-10-26 | FABRICATION | SATAIR | 62 | 27947430 | NON-SPARES | 20 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-04-10 | 2019-03-13 | Sous-poste | Sous-poste | 2019-04-14 | 2019-03-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2798119510 | 2018-11-27 | HA/REVENTE | SATAIR | COVER ASSY | 27981195 | NON-SPARES | 10 | 1 | RTN | A9252597000800 | 1STR*01148 | NA | 19461 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-13 | NA | 100% | 2019-03-12 | 100% | NA | NA | 100% |  |  | 2019-02-20 | 2019-03-13 | Sous-poste | Sous-poste | 2019-02-24 | 2019-03-17 | 2019-03-17 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 11 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794780410 | 2018-10-26 | FABRICATION | SATAIR | 56 | 27947804 | NON-SPARES | 10 | 4 | RTN | D9551005600695 | 0 | NON PRESENT INDUS | 18566 | LTE990006 => LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-12 | 100% | NA | NA | 5.556% |  |  | 2019-03-06 | 2019-03-13 | Sous-poste | Sous-poste | 2019-03-12 | 2019-03-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 11 | 3 | 2019 | 0.82 | 7.4548 | 0.46593 | 7.9207 | COL | 0 | 0
2809104310 | 2019-03-08 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | 28091043 | NON-SPARES | 10 | 1 | AOG | F9252030900000 | IS0032162M | NON PRESENT INDUS | N/A | 299165-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-15 | 100% | NA | NA | 5.556% |  |  | 2019-03-07 | 2019-03-15 | Sous-poste | Sous-poste | 2019-03-09 | 2019-03-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 11 | 3 | 2019 | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
2806854210 | 2019-02-18 | HA/REVENTE | SATAIR | ANGLE | 28068542 | NON-SPARES | 10 | 1 | AOG | L9251267220001 | 1STR*10887 | NA | 21962 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-18 | NA | 100% | 2019-03-13 | 100% | NA | NA | 100% |  |  | 2019-02-26 | 2019-03-15 | Sous-poste | Sous-poste | 2019-02-28 | 2019-03-19 | 2019-03-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 11 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003666510 | 2018-11-12 | FABRICATION | STELIA | 63 | 4900036665 | NON-SPARES | 10 | 3 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 18837 | LTE990003 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-15 | 100% | NA | NA | 5.556% |  |  | 2018-11-28 | 2019-03-18 | Sous-poste | Sous-poste | 2018-12-03 | 2019-03-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 12 | 3 | 2019 | 0.615 | 11.8125 | 0.98438 | 12.7969 | COL | 0 | 0
2801710810 | 2018-12-27 | FABRICATION | SATAIR | 453 | 28017108 | NON-SPARES | 10 | 3 | EXP | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990001 => LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-15 | 100% | NA | NA | 5.556% |  |  | 2019-01-25 | 2019-03-18 | Sous-poste | Sous-poste | 2019-01-31 | 2019-03-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 12 | 3 | 2019 | 0.615 | 4.1376 | 0.3448 | 4.4824 | COL | 0 | 0
490003729610 | 2019-01-11 | FABRICATION | STELIA | CÂBLE | 4900037296 | NON-SPARES | 10 | 8 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 241818-1 => 241818-8 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-15 | 100% | NA | NA | 5.556% |  |  | 2019-03-18 | 2019-03-18 | Sous-poste | Sous-poste | 2019-03-21 | 2019-03-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 12 | 3 | 2019 | 1.64 | 8 | 0.1 | 8.1 | NA | 0 | 0
2794710510 | 2018-10-26 | FABRICATION | SATAIR | 61 | 27947105 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 18362 | LTE990016 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-18 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-19 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794720710 | 2018-10-26 | FABRICATION | SATAIR | 60 | 27947207 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 18362 | LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-18 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-03-19 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794742510 | 2018-10-26 | FABRICATION | SATAIR | 62 | 27947425 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 18362 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-18 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-03-19 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2807856510 | 2019-02-26 | FABRICATION | SATAIR | BUNDLE | 28078565 | NON-SPARES | 10 | 2 | CRIT | V9251243600096 | 0 | NON PRESENT INDUS | 22553 | 290124-1 290124-2 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-21 | 100% | NA | NA | 5.556% |  |  | 2019-03-06 | 2019-03-21 | Sous-poste | Sous-poste | 2019-03-08 | 2019-03-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 12 | 3 | 2019 | 0.41 | 2 | 0.1 | 2.1 | COL | 0 | 0
2809792810 | 2019-03-13 | FABRICATION | SATAIR | WIRE-BONDING | 28097928 | NON-SPARES | 10 | 2 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | N/A | 302523-1 => 302523-2 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-22 | 100% | NA | NA | 5.556% |  |  | 2019-03-22 | 2019-03-22 | Sous-poste | Sous-poste | 2019-03-27 | 2019-03-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 12 | 3 | 2019 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2809792910 | 2019-03-13 | FABRICATION | SATAIR | WIRE-BONDING | 28097929 | NON-SPARES | 10 | 1 | CRIT | F0003008100200 | IS0032147M | NON PRESENT INDUS | N/A | 302525-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-22 | 100% | NA | NA | 5.556% |  |  | 2019-03-22 | 2019-03-22 | Sous-poste | Sous-poste | 2019-03-27 | 2019-03-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 12 | 3 | 2019 | 0.2085 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2809793110 | 2019-03-13 | FABRICATION | SATAIR | LEAD-BONDING | 28097931 | NON-SPARES | 10 | 1 | CRIT | F0003008100300 | IS0032149M | NON PRESENT INDUS | N/A | 302528-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-03-22 | 100% | NA | NA | 5.556% |  |  | 2019-03-22 | 2019-03-22 | Sous-poste | Sous-poste | 2019-03-27 | 2019-03-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 12 | 3 | 2019 | 0.2075 | 0.2383 | 0.059575 | 0.29788 | NA | 0 | 0
2794709910 | 2018-10-26 | FABRICATION | SATAIR | 61 | 27947099 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 18362 | LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-21 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-22 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794720910 | 2018-10-26 | FABRICATION | SATAIR | 60 | 27947209 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 18362 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-21 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-03-22 | Sous-poste | Sous-poste | 2019-02-14 | 2019-03-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2801710910 | 2018-12-27 | FABRICATION | SATAIR | 453 | 28017109 | NON-SPARES | 10 | 2 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990004 => LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-21 | 100% | NA | NA | 5.556% |  |  | 2019-02-22 | 2019-03-22 | Sous-poste | Sous-poste | 2019-02-28 | 2019-03-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 12 | 3 | 2019 | 0.41 | 2.7584 | 0.3448 | 3.1032 | COL | 0 | 0
2794741910 | 2018-10-26 | FABRICATION | SATAIR | 62 | 27947419 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 18362 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-21 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-03-22 | Sous-poste | Sous-poste | 2019-03-14 | 2019-03-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 12 | 3 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
490003750310 | 2019-02-01 | FABRICATION | STELIA | FAISCEAU | 4900037503 | NON-SPARES | 10 | 1 | AOG | S9110302500195 | 0 | NON PRESENT INDUS | 21466 | 262431-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-25 | 100% | NA | NA | 5.556% |  |  | 2019-02-06 | 2019-03-25 | Sous-poste | Sous-poste | 2019-02-08 | 2019-03-27 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 13 | 3 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
2807906710 | 2019-02-26 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28079067 | NON-SPARES | 10 | 25 | EXP | D9251095400000 | IS0053354S | NA | 22343 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-25 | NA | 100% | 2019-03-20 | 100% | NA | NA | 100% |  |  | 2019-03-25 | 2019-03-25 | Sous-poste | Sous-poste | 2019-03-28 | 2019-03-28 | 2019-03-28 |  |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 13 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2807906810 | 2019-02-26 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28079068 | NON-SPARES | 10 | 25 | EXP | D9251095600000 | IS0053509S | NA | 22343 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-25 | NA | 100% | 2019-03-20 | 100% | NA | NA | 100% |  |  | 2019-03-25 | 2019-03-25 | Sous-poste | Sous-poste | 2019-03-28 | 2019-03-28 | 2019-03-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 13 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2782123310 | 2018-06-14 | HA/REVENTE | SATAIR | PLATE ASSY | 27821233 | NON-SPARES | 10 | 6 | RTN | D9251101900000 | 1STR*11007 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-03-27 | NA | 100% | 2019-03-20 | 100% | NA | NA | 100% |  |  | 2019-03-27 | 2019-03-27 | Sous-poste | Sous-poste | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 13 | 3 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003757810 | 2019-02-08 | FABRICATION | STELIA | FAISCEAU | 4900037578 | NON-SPARES | 10 | 4 | AOG | S9110302500195 | 0 | NON PRESENT INDUS | 21736 | 264177-1 => 264177-4 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-01 | 100% | NA | NA | 5.556% |  |  | 2019-02-14 | 2019-04-01 | Sous-poste | Sous-poste | 2019-02-18 | 2019-04-03 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 14 | 4 | 2019 | 1 | 2 | 0.05 | 2.05 | NA | 0 | 0
490003753610 | 2019-02-06 | FABRICATION | STELIA | CABLE COAXIAL | 4900037536 | NON-SPARES | 10 | 6 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 21689 | 263855-1 => 263855-6 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-03-29 | 100% | NA | NA | 5.556% |  |  | 2019-04-01 | 2019-04-01 | Sous-poste | Sous-poste | 2019-04-04 | 2019-04-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 14 | 4 | 2019 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
2799368110 | 2018-12-06 | HA/REVENTE | SATAIR | PLATE ASSY | 27993681 | NON-SPARES | 10 | 10 | RTN | L9251321500000 | 1STR*01089 | NA | 19826 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-01 | NA | 100% | 2019-03-22 | 100% | NA | NA | 100% |  |  | 2019-03-08 | 2019-04-01 | Sous-poste | Sous-poste | 2019-03-13 | 2019-04-04 | 2019-04-04 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003733020 | 2014-01-01 | HA/REVENTE | STELIA | ENSEMBLE COMPAS | 4900037330 | NON-SPARES | 20 | 1 | RTN | S9251340100100 | 1STR*11056 | NA | 20816 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-01 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-04-01 | 2019-04-01 | Sous-poste | Sous-poste | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794710610 | 2018-10-26 | FABRICATION | SATAIR | 61 | 27947106 | NON-SPARES | 10 | 1 | RTN | D9551006100295 | 0 | NON PRESENT INDUS | 18362 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-01 | 100% | NA | NA | 5.556% |  |  | 2019-02-08 | 2019-04-02 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 14 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794721410 | 2018-10-26 | FABRICATION | SATAIR | 60 | 27947214 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 18362 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-01 | 100% | NA | NA | 5.556% |  |  | 2019-03-08 | 2019-04-02 | Sous-poste | Sous-poste | 2019-03-14 | 2019-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 14 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2794743110 | 2019-10-14 | FABRICATION | SATAIR | 62 | 27947431 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 18362 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-01 | 100% | NA | NA | 5.556% |  |  | 2019-04-10 | 2019-04-02 | Sous-poste | Sous-poste | 2019-04-14 | 2019-04-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 14 | 4 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2791438310 | 2018-09-17 | HA/REVENTE | SATAIR | ROD-ADJUSTABLE | 27914383 | NON-SPARES | 10 | 1 | RTN | A0001072600100 | 1STR*10983 | NA | 16930 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-02 | NA | 100% | 2019-04-02 | 100% | NA | NA | 100% |  |  | 2018-09-12 | 2019-04-02 | Sous-poste | Sous-poste | 2018-09-17 | 2019-04-05 | 2019-04-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2791518610 | 2018-09-18 | HA/REVENTE | SATAIR | ROD-ADJUSTABLE | 27915186 | NON-SPARES | 10 | 1 | RTN | A0001072600100 | 1STR*10983 | NA | 16930 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-02 | NA | 100% | 2019-04-02 | 100% | NA | NA | 100% |  |  | 2018-09-13 | 2019-04-02 | Sous-poste | Sous-poste | 2018-09-18 | 2019-04-05 | 2019-04-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2788366610 | 2018-08-15 | HA/REVENTE | SATAIR | COVER ASSY | 27883666 | NON-SPARES | 10 | 2 | EXP | A9252597000900 | 1STR*01482 | NA | 16576 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-02 | NA | 100% | 2019-03-26 | 100% | NA | NA | 100% |  |  | 2018-09-11 | 2019-04-02 | Sous-poste | Sous-poste | 2018-09-14 | 2019-04-05 | 2019-04-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2018 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2809888410 | 2019-03-14 | FABRICATION | SATAIR | 511 | 28098884 | NON-SPARES | 10 | 2 | AOG | WF413SBAAAAB | 0 | NON PRESENT INDUS | 21810 | LTE990009 => LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-03 | 100% | NA | NA | 5.556% |  |  | 2019-03-19 | 2019-04-03 | Sous-poste | Sous-poste | 2019-03-21 | 2019-04-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 14 | 4 | 2019 | 1.02 | 1.9626 | 0.24533 | 2.2079 | COL | 0 | 0
2809374510 | 2019-03-11 | HA/REVENTE | SATAIR | TOLE FERMET. 1MCU EQ | 28093745 | NON-SPARES | 10 | 1 | CRIT | D9251863200000 | 1STR*10676 | NA | 22670 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-04 | NA | 100% | 2019-04-02 | 100% | NA | NA | 100% |  |  | 2019-03-08 | 2019-04-03 | Sous-poste | Sous-poste | 2019-03-12 | 2019-04-05 | 2019-04-05 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2811536910 | 2019-04-02 | HA/REVENTE | SATAIR | TRIM | 28115369 | NON-SPARES | 10 | 2 | AOG | F9251109620000 | N/A | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-04 | NA | 100% | 0 | 100% | NA | NA | 100% |  |  | 2019-04-01 | 2019-04-03 | Sous-poste | Sous-poste | 2019-04-03 | 2019-04-05 | 2019-04-05 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2811785810 | 2019-04-04 | HA/REVENTE | SATAIR | BAR | 28117858 | NON-SPARES | 10 | 1 | AOG | A9252602600000 | À faire | NA | 23645 | 0 | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | TBD | 100% | NA | NA | 100% |  |  | 2019-04-03 | 2019-04-03 | Sous-poste | Sous-poste | 2019-04-05 | 2019-04-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2802748110 | 2019-01-10 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28027481 | NON-SPARES | 10 | 1 | RTN | D9251490100000 | IS0032740S | NA | 20639 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-03 | NA | 100% | 2019-04-01 | 100% | NA | NA | 100% |  |  | 2019-04-03 | 2019-04-03 | Sous-poste | Sous-poste | 2019-04-06 | 2019-04-06 | 2019-04-06 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 14 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003757810 | 2019-02-08 | FABRICATION | STELIA | FAISCEAU | 4900037578 | NON-SPARES | 10 | 30 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 21736 | 264177-1 => 264177-4 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-01 | 100% | NA | NA | 5.556% |  |  | 2019-03-07 | 2019-04-03 | Sous-poste | Sous-poste | 2019-03-12 | 2019-04-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 14 | 4 | 2019 | 7.5 | 15 | 0.05 | 15.05 | NA | 0 | 0
2805292510 | 2019-02-05 | FABRICATION | SATAIR | 511 | 28052925 | NON-SPARES | 10 | 6 | EXP | WF413SBAAAAA | 0 | NON PRESENT INDUS | 21810 | LTE990001 => LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-03 | 100% | NA | NA | 5.556% |  |  | 2019-02-06 | 2019-04-04 | Sous-poste | Sous-poste | 2019-02-11 | 2019-04-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 14 | 4 | 2019 | 3.06 | 5.8878 | 0.24533 | 6.1331 | COL | 0 | 0
2801711010 | 2018-12-27 | FABRICATION | SATAIR | 453 | 28017110 | NON-SPARES | 10 | 2 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990006 => LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-03 | 100% | NA | NA | 5.556% |  |  | 2019-03-26 | 2019-04-04 | Sous-poste | Sous-poste | 2019-03-30 | 2019-04-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 14 | 4 | 2019 | 0.41 | 2.7584 | 0.3448 | 3.1032 | COL | 0 | 0
2808592510 | 2019-03-06 | FABRICATION | SATAIR | 40 | 28085925 | NON-SPARES | 10 | 1 | AOG | D9551004000495 | 0 | NON PRESENT INDUS | 22784 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-08 | 100% | NA | NA | 5.556% |  |  | 2019-03-07 | 2019-04-08 | Sous-poste | Sous-poste | 2019-03-11 | 2019-04-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 15 | 4 | 2019 | 0.205 | 11.8819 | 2.9705 | 14.8524 | COL | 0 | 0
2806360010 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 510VU | 28063600 | NON-SPARES | 10 | 2 | CRIT | A9251133500000 | 1STR*11105 | NA | 21868 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-09 | NA | 100% | 2019-04-04 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-08 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-10 | 2019-04-10 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 15 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2804729620 | 2019-01-30 | FABRICATION | SATAIR | 61 | 28047296 | NON-SPARES | 20 | 1 | EXP | D9551006100295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-02-20 | 2019-04-09 | Sous-poste | Sous-poste | 2019-02-25 | 2019-04-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 15 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2804729910 | 2019-01-30 | FABRICATION | SATAIR | 61 | 28047299 | NON-SPARES | 10 | 1 | EXP | D9551006100295 | 0 | NON PRESENT INDUS | 21431 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-08 | 100% | NA | NA | 5.556% |  |  | 2019-02-20 | 2019-04-09 | Sous-poste | Sous-poste | 2019-02-25 | 2019-04-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 15 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2804729810 | 2019-01-30 | FABRICATION | SATAIR | 61 | 28047298 | NON-SPARES | 10 | 1 | EXP | D9551006100295 | 0 | NON PRESENT INDUS | 21431 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-08 | 100% | NA | NA | 5.556% |  |  | 2019-02-20 | 2019-04-09 | Sous-poste | Sous-poste | 2019-02-25 | 2019-04-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 15 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
682320010 | 2019-02-01 | FABRICATION | AD&S | 12 | 6823200 | NON-SPARES | 10 | 1 | AOG | MB170ACAAAAB | IS0032212M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-02-20 | 2019-04-12 | Sous-poste | Sous-poste | 2019-02-22 | 2019-04-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 15 | 4 | 2019 | 0.205 | 8.3333 | 2.0833 | 10.4166 | COL | 0 | 0
2812689110 | 2019-04-12 | HA/REVENTE | SATAIR | SUPPLATE FRONT 301VU | 28126891 | NON-SPARES | 10 | 1 | AOG | D9251794200000 | 1STR*10670 | NA | 23901 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-16 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-04-10 | 2019-04-15 | Sous-poste | Sous-poste | 2019-04-12 | 2019-04-17 | 2019-04-17 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003758710 | 2014-01-01 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900037587 | NON-SPARES | 10 | 1 | RTN | S9251363300000 | IS0035424S | NA | 21304 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-16 | NA | 100% | 2019-04-15 | 100% | NA | NA | 100% |  |  | 2019-04-16 | 2019-04-16 | Sous-poste | Sous-poste | 2019-04-19 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806360410 | 2019-02-13 | FABRICATION | SATAIR | 510 | 28063604 | NON-SPARES | 10 | 2 | CRIT | A9550051000195 | 0 | NON PRESENT INDUS | 21884 | LTE990001 => LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-17 | 100% | NA | NA | 5.556% |  |  | 2019-02-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 7.1034 | 0.88793 | 7.9913 | COL | 0 | 0
2809820410 | 2019-03-13 | FABRICATION | SATAIR | 317 | 28098204 | NON-SPARES | 10 | 1 | CRIT | WF408ACABAAB | 0 | NON PRESENT INDUS | 23119 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-17 | 100% | NA | NA | 5.556% |  |  | 2019-03-18 | 2019-04-17 | Sous-poste | Sous-poste | 2019-03-21 | 2019-04-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 16 | 4 | 2019 | 0 | 3.255 | 0.81375 | 4.0687 | COL | 0 | 0
2809787110 | 2019-03-13 | FABRICATION | SATAIR | BUNDLE | 28097871 | NON-SPARES | 10 | 9 | CRIT | D9000095493095 | 0 | NON PRESENT INDUS | 23238 | 307414-1 307418-1 307422-1 307426-1 307430-1 307434-1 307438-1 307442-1 307446-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-17 | 100% | NA | NA | 5.556% |  |  | 2019-03-18 | 2019-04-17 | Sous-poste | Sous-poste | 2019-03-20 | 2019-04-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 16 | 4 | 2019 | 21.9366 | 100.233 | 1.1137 | 101.3467 | NA | 0 | 0
2806360710 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE | 28063607 | NON-SPARES | 10 | 1 | CRIT | A9253170100100 | 1STR*11101 | NA | 21868 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-18 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806360910 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE | 28063609 | NON-SPARES | 10 | 1 | CRIT | A9253170100000 | 1STR*11102 | NA | 21868 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-18 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806361310 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE 406VU | 28063613 | NON-SPARES | 10 | 1 | CRIT | A92529189000E00 | 1STR*11103 | NA | 21868 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-18 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806361110 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE ASSY | 28063611 | NON-SPARES | 10 | 1 | CRIT | A92530435000D00 | 1STR*11104 | NA | 21868 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-18 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806410110 | 2019-02-14 | FABRICATION | SATAIR | PLATINE | 28064101 | NON-SPARES | 10 | 1 | CRIT | A92529726000D00 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-02-13 | 2019-04-17 | Sous-poste | Sous-poste | 2019-02-15 | 2019-04-19 | 2019-04-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
27423652001 | 2017-04-27 | FABRICATION | SATAIR | 117 | 27423652 | NON-SPARES | 001 | 1 | EXP | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2017-11-16 | 2019-04-17 | Sous-poste | Sous-poste | 2017-11-21 | 2019-04-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2017 | 16 | 4 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2803585110 | 2019-01-17 | FABRICATION | SATAIR | 117 | 28035851 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 20982 | LTE990101 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-16 | 100% | NA | NA | 5.556% |  |  | 2019-03-12 | 2019-04-17 | Sous-poste | Sous-poste | 2019-03-15 | 2019-04-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 16 | 4 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2810671310 | 2019-03-22 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28106713 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 23158 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-17 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-04-17 | 2019-04-17 | Sous-poste | Sous-poste | 2019-04-21 | 2019-04-21 | 2019-04-21 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003758610 | 2014-01-01 | HA/REVENTE | STELIA | FRONT PLATE ASSY 110VU | 4900037586 | NON-SPARES | 10 | 3 | RTN | S9251038100000 | IS0035410S | NA | 20174 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-18 | NA | 100% | 2019-04-17 | 100% | NA | NA | 100% |  |  | 2019-04-18 | 2019-04-18 | Sous-poste | Sous-poste | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 16 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003769110 | 2019-02-21 | FABRICATION | STELIA | FAISCEAU | 4900037691 | NON-SPARES | 10 | 4 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 279876-1 => 279876-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-04-19 | 100% | NA | NA | 5.556% |  |  | 2019-04-22 | 2019-04-22 | Sous-poste | Sous-poste | 2019-04-25 | 2019-04-25 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 17 | 4 | 2019 | 0.82 | 2.8 | 0.07 | 2.87 | NA | 0 | 0
2798191910 | 2018-11-27 | HA/REVENTE | SATAIR | PLATE ASSY | 27981919 | NON-SPARES | 10 | 20 | RTN | D9251101900000 | 1STR*11007 | NA | 19460 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-22 | NA | 100% | 2019-04-16 | 100% | NA | NA | 100% |  |  | 2019-04-22 | 2019-04-22 | Sous-poste | Sous-poste | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 17 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2811895610 | 2019-04-05 | FABRICATION | SATAIR | 27 | 28118956 | NON-SPARES | 10 | 3 | AOG | D9551002700495 | 0 | NON PRESENT INDUS | 23791 | LTE990059 à LTE990061 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-10 | 2019-04-24 | Sous-poste | Sous-poste | 2019-04-12 | 2019-04-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 17 | 4 | 2019 | 0.615 | 14.7519 | 1.2293 | 15.9812 | COL | 0 | 0
2806359910 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE 423VU | 28063599 | NON-SPARES | 10 | 1 | CRIT | A9252793020200 | 1STR*11100 | NA | 22149 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-25 | NA | 100% | 2019-04-24 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-24 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-26 | 2019-04-26 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 17 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806360310 | 2019-02-13 | HA/REVENTE | SATAIR | FRONT PLATE 76VU | 28063603 | NON-SPARES | 10 | 1 | CRIT | A9251079000000 | 1STR*11106 | NA | 22149 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-25 | NA | 100% | 2019-04-24 | 100% | NA | NA | 100% |  |  | 2019-02-12 | 2019-04-24 | Sous-poste | Sous-poste | 2019-02-14 | 2019-04-26 | 2019-04-26 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 17 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2804605010 | 2019-01-29 | FABRICATION | SATAIR | 60 | 28046050 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 21431 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-25 | 2019-04-25 | Sous-poste | Sous-poste | 2019-04-30 | 2019-04-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 17 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2804605610 | 2019-01-29 | FABRICATION | SATAIR | 60 | 28046056 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 21431 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-25 | 2019-04-25 | Sous-poste | Sous-poste | 2019-04-30 | 2019-04-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 17 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2804605510 | 2019-01-29 | FABRICATION | SATAIR | 60 | 28046055 | NON-SPARES | 10 | 1 | RTN | D9551006000295 | 0 | NON PRESENT INDUS | 21431 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-25 | 2019-04-25 | Sous-poste | Sous-poste | 2019-04-30 | 2019-04-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 17 | 4 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2806846710 | 2019-02-18 | FABRICATION | SATAIR | 22 | 28068467 | NON-SPARES | 10 | 1 | RTN | D9551002201195 | 0 | NON PRESENT INDUS | 21960 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-25 | 2019-04-25 | Sous-poste | Sous-poste | 2019-04-30 | 2019-04-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 17 | 4 | 2019 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2806846610 | 2019-02-18 | FABRICATION | SATAIR | 22 | 28068466 | NON-SPARES | 10 | 1 | RTN | D9551002201195 | 0 | NON PRESENT INDUS | 21960 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-24 | 100% | NA | NA | 5.556% |  |  | 2019-04-25 | 2019-04-25 | Sous-poste | Sous-poste | 2019-04-30 | 2019-04-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 17 | 4 | 2019 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
490003777710 | 2019-03-04 | FABRICATION | STELIA | FAISCEAU | 4900037777 | NON-SPARES | 10 | 4 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 299144-1 => 299144-4 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-04-26 | 100% | NA | NA | 5.556% |  |  | 2019-04-29 | 2019-04-29 | Sous-poste | Sous-poste | 2019-05-02 | 2019-05-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 18 | 4 | 2019 | 0.82 | 2.8 | 0.07 | 2.87 | NA | 0 | 0
490003779210 | 2019-03-06 | FABRICATION | STELIA | FAISCEAU | 4900037792 | NON-SPARES | 10 | 6 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-04-29 | 2019-04-29 | Sous-poste | Sous-poste | 2019-05-02 | 2019-05-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 18 | 4 | 2019 | 1.23 | 4.2 | 0.07 | 4.27 | NA | 0 | 0
2803317610 | 2019-01-15 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28033176 | NON-SPARES | 10 | 13 | RTN | D9251095600000 | IS0053509S | NA | 20789 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-29 | NA | 100% | 2019-04-25 | 100% | NA | NA | 100% |  |  | 2019-04-29 | 2019-04-29 | Sous-poste | Sous-poste | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 18 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003771410 | 2014-01-01 | HA/REVENTE | STELIA | GOUPILLE | 4900037714 | NON-SPARES | 10 | 14 | RTN | S9251186120000 | 3STR*01339 | NA | 22354 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-04-29 | NA | 100% | 2019-04-25 | 100% | NA | NA | 100% |  |  | 2019-04-29 | 2019-04-29 | Sous-poste | Sous-poste | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 18 | 4 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2811803010 | 2019-04-04 | FABRICATION | SATAIR | BUNDLE | 28118030 | NON-SPARES | 10 | 1 | CRIT | D9000095477995 | IS0032050M | NON PRESENT INDUS | 23823 | 325035-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-01 | 100% | NA | NA | 5.556% |  |  | 2019-04-19 | 2019-05-01 | Sous-poste | Sous-poste | 2019-04-23 | 2019-05-03 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 18 | 5 | 2019 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0
2802068510 | 2019-01-03 | FABRICATION | SATAIR | 62 | 28020685 | NON-SPARES | 10 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | 20464 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-04-30 | 100% | NA | NA | 5.556% |  |  | 2019-05-01 | 2019-05-01 | Sous-poste | Sous-poste | 2019-05-06 | 2019-05-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 18 | 5 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2804730230 | 2019-01-30 | FABRICATION | SATAIR | 62 | 28047302 | NON-SPARES | 30 | 1 | RTN | D9551006200295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-05-01 | 2019-05-01 | Sous-poste | Sous-poste | 2019-05-06 | 2019-05-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 18 | 5 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2780517910 | 2018-06-01 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27805179 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-01 | NA | 100% | 2019-04-23 | 100% | NA | NA | 100% |  |  | 2019-05-01 | 2019-05-01 | Sous-poste | Sous-poste | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 18 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2805276910 | 2019-02-05 | HA/REVENTE | SATAIR | COVER ASSY | 28052769 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 21628 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-01 | NA | 100% | 2019-04-25 | 100% | NA | NA | 100% |  |  | 2019-05-01 | 2019-05-01 | Sous-poste | Sous-poste | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 18 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2803984610 | 2019-01-22 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28039846 | NON-SPARES | 10 | 12 | RTN | D9251095400000 | IS0053354S | NA | 21088 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-06 | NA | 100% | 2019-04-25 | 100% | NA | NA | 100% |  |  | 2019-05-06 | 2019-05-06 | Sous-poste | Sous-poste | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 19 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
28098884 2811802510 | 2019-03-14 | FABRICATION | SATAIR | 511 | 28098884 28118025 | NON-SPARES | 10 | 2 | AOG | WF413SBAAAAB | 0 | NON PRESENT INDUS | 22894 | LTE990011 => LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-08 | 100% | NA | NA | 5.556% |  |  | 2019-03-19 | 2019-05-08 | Sous-poste | Sous-poste | 2019-03-21 | 2019-05-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 19 | 5 | 2019 | 1.02 | 1.9626 | 0.24533 | 2.2079 | COL | 0 | 0
490003819510 | 2014-01-01 | HA/REVENTE | STELIA | PILLAR | 4900038195 | NON-SPARES | 10 | 5 | CRIT | F0003057821000 | 1QME*17052 | NA | 23771 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-09 | NA | 100% | 2019-05-09 | 100% | NA | NA | 100% |  |  | 2019-04-17 | 2019-05-08 | Sous-poste | Sous-poste | 2019-04-19 | 2019-05-10 | 2019-05-10 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 19 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806613010 | 2019-02-14 | HA/REVENTE | SATAIR | DIAPHRAGME | 28066130 | NON-SPARES | 10 | 3 | EXP | V9251111522200 | 1STR*10734 | NA | 21915 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-10 | NA | 100% | 2019-05-09 | 100% | NA | NA | 100% |  |  | 2019-03-13 | 2019-05-10 | Sous-poste | Sous-poste | 2019-03-16 | 2019-05-15 | 2019-05-15 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 19 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2806612810 | 2019-02-14 | HA/REVENTE | SATAIR | DIAPHRAGME | 28066128 | NON-SPARES | 10 | 3 | EXP | V9251111520600 | 1STR*10733 | NA | 21915 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-10 | NA | 100% | 2019-05-09 | 100% | NA | NA | 100% |  |  | 2019-03-13 | 2019-05-10 | Sous-poste | Sous-poste | 2019-03-16 | 2019-05-15 | 2019-05-15 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 19 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2806612910 | 2019-02-14 | HA/REVENTE | SATAIR | DIAPHRAGME | 28066129 | NON-SPARES | 10 | 3 | EXP | V9251111522600 | 1STR*10751 | NA | 21915 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-10 | NA | 100% | 2019-05-09 | 100% | NA | NA | 100% |  |  | 2019-03-13 | 2019-05-10 | Sous-poste | Sous-poste | 2019-03-16 | 2019-05-15 | 2019-05-15 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 19 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003770410 | 2019-02-27 | FABRICATION | STELIA | FAISCEAU | 4900037704 | NON-SPARES | 10 | 35 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 22403 | 283892-1 => 283892-35 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-15 | 100% | NA | NA | 5.556% |  |  | 2019-04-10 | 2019-05-13 | Sous-poste | Sous-poste | 2019-04-15 | 2019-05-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 20 | 5 | 2019 | 8.75 | 17.5 | 0.05 | 17.55 | NA | 0 | 0
2809447110 | 2019-03-11 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28094471 | NON-SPARES | 10 | 1 | RTN | D9251490100000 | IS0032740S | NA | 22637 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-16 | NA | 100% | 2019-05-14 | 100% | NA | NA | 100% |  |  | 2019-04-05 | 2019-05-16 | Sous-poste | Sous-poste | 2019-04-10 | 2019-05-21 | 2019-05-21 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 20 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2809675210 | 2019-03-13 | HA/REVENTE | SATAIR | DIAPHRAGME | 28096752 | NON-SPARES | 10 | 3 | EXP | V9251111522600 | 1STR*10751 | NA | 22783 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-17 | NA | 100% | 2019-05-15 | 100% | NA | NA | 100% |  |  | 2019-04-09 | 2019-05-17 | Sous-poste | Sous-poste | 2019-04-13 | 2019-05-22 | 2019-05-22 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 20 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2809675110 | 2019-03-13 | HA/REVENTE | SATAIR | DIAPHRAGME | 28096751 | NON-SPARES | 10 | 3 | EXP | V9251111520600 | 1STR*10733 | NA | 22783 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-17 | NA | 100% | 2019-05-15 | 100% | NA | NA | 100% |  |  | 2019-04-09 | 2019-05-17 | Sous-poste | Sous-poste | 2019-04-13 | 2019-05-22 | 2019-05-22 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 20 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2809675310 | 2019-03-13 | HA/REVENTE | SATAIR | DIAPHRAGME | 28096753 | NON-SPARES | 10 | 3 | EXP | V9251111522200 | 1STR*10734 | NA | 22783 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-17 | NA | 100% | 2019-05-15 | 100% | NA | NA | 100% |  |  | 2019-04-09 | 2019-05-17 | Sous-poste | Sous-poste | 2019-04-13 | 2019-05-22 | 2019-05-22 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 20 | 5 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2804522110 | 2019-01-28 | FABRICATION | SATAIR | WIRE-BONDING | 28045221 | NON-SPARES | 10 | 1 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | NA | 253995-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-05-16 | 100% | NA | NA | 5.556% |  |  | 2019-05-17 | 2019-05-17 | Sous-poste | Sous-poste | 2019-05-22 | 2019-05-22 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 20 | 5 | 2019 | 0.2059 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
490003811030 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900038110 | NON-SPARES | 30 | 1 | EXP | S9251458000000 | 3STR*01167 | NA | 23746 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-20 | NA | 100% | 2019-05-17 | 100% | NA | NA | 100% |  |  | 2019-05-20 | 2019-05-20 | Sous-poste | Sous-poste | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 21 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
630133696510 | 2019-05-27 | FABRICATION | SATAIR | 317 | 6301336965 | NON-SPARES | 10 | 1 | AOG | WF408AEAAAAC | 0 | NON PRESENT INDUS | NA | LTE990001 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-05-24 | 100% | NA | NA | 5.556% |  |  | 2019-05-22 | 2019-05-24 | Sous-poste | Sous-poste | 2019-05-24 | 2019-05-28 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 21 | 5 | 2019 | 0 | 3.255 | 0.81375 | 4.0687 | COL | 0 | 0
490003775610 | 2019-03-04 | FABRICATION | STELIA | CABLE COAXIAL | 4900037756 | NON-SPARES | 10 | 6 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 22582 | 299159-1 => 299159-6 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-28 | 100% | NA | NA | 5.556% |  |  | 2019-04-24 | 2019-05-24 | Sous-poste | Sous-poste | 2019-04-29 | 2019-05-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 21 | 5 | 2019 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
2809788910 | 2019-03-13 | FABRICATION | SATAIR | BUNDLE | 28097889 | NON-SPARES | 10 | 6 | RTN | D9000095493095 | 0 | NON PRESENT INDUS | 23238 | 307450-1 307454-1 307458-1 307462-1 307466-1 307470-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-23 | 100% | NA | NA | 5.556% |  |  | 2019-04-29 | 2019-05-24 | Sous-poste | Sous-poste | 2019-05-02 | 2019-05-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 21 | 5 | 2019 | 14.6244 | 66.822 | 1.1137 | 67.9357 | NA | 0 | 0
2809226810 | 2019-03-09 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28092268 | NON-SPARES | 10 | 1 | RTN | D9251490100000 | IS0032740S | NA | 22637 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-29 | NA | 100% | 2019-05-27 | 100% | NA | NA | 100% |  |  | 2019-05-29 | 2019-05-29 | Sous-poste | Sous-poste | 2019-06-01 | 2019-06-01 | 2019-06-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 22 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003831610 | 2019-05-02 | FABRICATION | STELIA | FAISCEAU | 4900038316 | NON-SPARES | 10 | 1 | EXP | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-05-14 | 2019-05-30 | Sous-poste | Sous-poste | 2019-05-17 | 2019-06-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 22 | 5 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
2801947510 | 2019-01-02 | FABRICATION | SATAIR | 453 | 28019475 | NON-SPARES | 10 | 2 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990008 => LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-08 | 100% | NA | NA | 5.556% |  |  | 2019-04-29 | 2019-05-31 | Sous-poste | Sous-poste | 2019-05-02 | 2019-06-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 22 | 5 | 2019 | 0.41 | 2.7584 | 0.3448 | 3.1032 | COL | 0 | 0
2810110310 | 2019-03-18 | HA/REVENTE | SATAIR | COVER ASSY | 28101103 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 22911 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-31 | NA | 100% | 2019-05-27 | 100% | NA | NA | 100% |  |  | 2019-04-12 | 2019-05-31 | Sous-poste | Sous-poste | 2019-04-18 | 2019-06-05 | 2019-06-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 22 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2810000710 | 2014-01-01 | HA/REVENTE | SATAIR | COVER ASSY | 28100007 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 22911 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-31 | NA | 100% | 2019-05-27 | 100% | NA | NA | 100% |  |  | 2019-04-10 | 2019-05-31 | Sous-poste | Sous-poste | 2019-04-15 | 2019-06-05 | 2019-06-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 22 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2810288110 | 2019-03-19 | HA/REVENTE | SATAIR | COVER ASSY | 28102881 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 22911 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-31 | NA | 100% | 2019-05-27 | 100% | NA | NA | 100% |  |  | 2019-04-15 | 2019-05-31 | Sous-poste | Sous-poste | 2019-04-18 | 2019-06-05 | 2019-06-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 22 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2810757810 | 2019-03-25 | HA/REVENTE | SATAIR | COVER ASSY | 28107578 | NON-SPARES | 10 | 2 | RTN | A9252597000800 | 1STR*01148 | NA | 22911 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-05-31 | NA | 100% | 2019-05-27 | 100% | NA | NA | 100% |  |  | 2019-03-25 | 2019-05-31 | Sous-poste | Sous-poste | 2019-03-28 | 2019-06-05 | 2019-06-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 22 | 5 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2810893110 | 2019-03-26 | HA/REVENTE | SATAIR | FRONT PLATE ASSY 426VU | 28108931 | NON-SPARES | 10 | 1 | EXP | A92524705001D00 | 1STR*11168 | NA | 23268 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-04 | NA | 100% | 2019-06-03 | 100% | NA | NA | 100% |  |  | 2019-04-22 | 2019-06-04 | Sous-poste | Sous-poste | 2019-04-25 | 2019-06-07 | 2019-06-07 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 23 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2813296010 | 2019-04-18 | HA/REVENTE | SATAIR | FRONT PLATE ASSY 426VU | 28132960 | NON-SPARES | 10 | 1 | EXP | A92524705001D00 | 1STR*11168 | NA | 23268 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-04 | NA | 100% | 2019-06-03 | 100% | NA | NA | 100% |  |  | 2019-05-15 | 2019-06-04 | Sous-poste | Sous-poste | 2019-05-18 | 2019-06-07 | 2019-06-07 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 23 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2809675410 | 2019-03-13 | HA/REVENTE | SATAIR | COVER ASSY | 28096754 | NON-SPARES | 10 | 1 | RTN | A9253115800000 | IS0031675S | NA | 22785 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-05 | NA | 100% | 2019-06-03 | 100% | NA | NA | 100% |  |  | 2019-06-05 | 2019-06-05 | Sous-poste | Sous-poste | 2019-06-11 | 2019-06-11 | 2019-06-11 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 23 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794780510 | 2018-10-26 | FABRICATION | SATAIR | 56 | 27947805 | NON-SPARES | 10 | 3 | RTN | D9551005600695 | 0 | NON PRESENT INDUS | 18566 | LTE990010 => LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-10 | 100% | NA | NA | 5.556% |  |  | 2019-05-01 | 2019-06-11 | Sous-poste | Sous-poste | 2019-05-07 | 2019-06-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 24 | 6 | 2019 | 0.615 | 5.5911 | 0.46593 | 6.057 | COL | 0 | 0
490003832310 | 2014-01-01 | HA/REVENTE | STELIA | SPHERE | 4900038323 | NON-SPARES | 10 | 2 | CRIT | S9251342320000 | 1STR*06202 | NA | 24346 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-13 | NA | 100% | 2019-06-11 | 100% | NA | NA | 100% |  |  | 2019-06-12 | 2019-06-12 | Sous-poste | Sous-poste | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 24 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2780518110 | 2018-06-01 | HA/REVENTE | SATAIR | ENS. TOLE APM | 27805181 | NON-SPARES | 10 | 1 | RTN | L9251355400000 | 1STR*10891 | NA | 13165 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-12 | NA | 100% | 2019-06-05 | 100% | NA | NA | 100% |  |  | 2019-06-12 | 2019-06-12 | Sous-poste | Sous-poste | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2018 | 24 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806044610 | 2019-02-12 | FABRICATION | SATAIR | 117 | 28060446 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 21862 | LTE990122 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-13 | 100% | NA | NA | 5.556% |  |  | 2019-05-29 | 2019-06-14 | Sous-poste | Sous-poste | 2019-06-01 | 2019-06-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 24 | 6 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816423810 | 2019-05-20 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28164238 | NON-SPARES | 10 | 1 | EXP | D9251490100000 | IS0032740S | NA | 24146 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-14 | NA | 100% | 2019-06-13 | 100% | NA | NA | 100% |  |  | 2019-06-14 | 2019-06-14 | Sous-poste | Sous-poste | 2019-06-19 | 2019-06-19 | 2019-06-19 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 24 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2806846010 | 2019-02-18 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 28068460 | NON-SPARES | 10 | 2 | AOG | F9251367800000 | 1STR*10672 | NA | 22351 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-18 | NA | 100% | 2019-06-17 | 100% | NA | NA | 100% |  |  | 2019-03-07 | 2019-06-17 | Sous-poste | Sous-poste | 2019-03-11 | 2019-06-19 | 2019-06-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 25 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2809294210 | 2019-06-17 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 28092942 | NON-SPARES | 10 | 3 | AOG | F9251367800000 | 1STR*10672 | NA | 22351 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-18 | NA | 100% | 2019-06-17 | 100% | NA | NA | 100% |  |  | 2019-04-04 | 2019-06-17 | Sous-poste | Sous-poste | 2019-04-08 | 2019-06-19 | 2019-06-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 25 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003836810 | 2019-05-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900038368 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 24700 | 342281-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-14 | 100% | NA | NA | 5.556% |  |  | 2019-06-17 | 2019-06-17 | Sous-poste | Sous-poste | 2019-06-20 | 2019-06-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 25 | 6 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
28052925 2811802330 | 2019-02-05 | FABRICATION | SATAIR | 511 | 28052925 28118023 | NON-SPARES | 30 | 2 | AOG | WF413SBAAAAA | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-02-07 | 2019-06-18 | Sous-poste | Sous-poste | 2019-02-11 | 2019-06-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 25 | 6 | 2019 | 1.02 | 1.9626 | 0.24533 | 2.2079 | COL | 0 | 0
2809790010 | 2019-03-13 | FABRICATION | SATAIR | BUNDLE | 28097900 | NON-SPARES | 10 | 7 | AOG | D9000095493095 | 0 | NON PRESENT INDUS | 23238 | 307474-1 307478-1 307482-1 307486-1 307490-1 307494-1 307498-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-14 | 100% | NA | NA | 5.556% |  |  | 2019-06-18 | 2019-06-18 | Sous-poste | Sous-poste | 2019-06-20 | 2019-06-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 25 | 6 | 2019 | 17.0618 | 77.959 | 1.1137 | 79.0727 | NA | 0 | 0
2819067010 | 2019-06-18 | HA/REVENTE | SATAIR | PLATE ASSY | 28190670 | NON-SPARES | 10 | 1 | AOG | A9251151000000 | 1STR*11047 | NA | 25817 | 0 | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | TBD | 100% | NA | NA | 100% |  |  | 2019-06-19 | 2019-06-19 | Sous-poste | Sous-poste | 2019-06-21 | 2019-06-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 25 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
49000381501 | 2019-04-17 | FABRICATION | STELIA | CÂBLE | 4900038150 | NON-SPARES | 1 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-06-21 | 2019-06-21 | Sous-poste | Sous-poste | 2019-06-26 | 2019-06-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 25 | 6 | 2019 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2816988810 | 2019-05-27 | HA/REVENTE | SATAIR | TUBE | 28169888 | NON-SPARES | 10 | 1 | CRIT | F9251110800800 | 1STR*00292 | NA | 25160 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-25 | NA | 100% | 2019-06-24 | 100% | NA | NA | 100% |  |  | 2019-05-24 | 2019-06-24 | Sous-poste | Sous-poste | 2019-05-28 | 2019-06-26 | 2019-06-26 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 26 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003779210 | 2019-03-06 | FABRICATION | STELIA | CABLE COAXIAL | 4900037792 | NON-SPARES | 10 | 6 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-04-29 | 2019-06-24 | Sous-poste | Sous-poste | 2019-05-02 | 2019-06-27 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 26 | 6 | 2019 | 1.1556 | 4.5078 | 0.07513 | 4.5829 | NA | 0 | 0
490003830110 | 2019-05-02 | FABRICATION | STELIA | CÂBLE | 4900038301 | NON-SPARES | 10 | 5 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 340219-1 => 340219-5 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-06-24 | 100% | NA | NA | 5.556% |  |  | 2019-06-25 | 2019-06-25 | Sous-poste | Sous-poste | 2019-06-28 | 2019-06-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 26 | 6 | 2019 | 1.025 | 5 | 0.1 | 5.1 | NA | 0 | 0
490003710570 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE SOUDÉE | 4900037105 | NON-SPARES | 70 | 6 | RTN | S9251080800100 | 1STR*10178 | NA | 20220 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-25 | NA | 100% | 2019-06-21 | 100% | NA | NA | 100% |  |  | 2019-06-25 | 2019-06-25 | Sous-poste | Sous-poste | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 26 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2813539110 | 2019-04-23 | HA/REVENTE | SATAIR | COVER ASSY | 28135391 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 24250 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-27 | NA | 100% | 2019-06-26 | 100% | NA | NA | 100% |  |  | 2019-05-20 | 2019-06-27 | Sous-poste | Sous-poste | 2019-05-23 | 2019-07-02 | 2019-07-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 26 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2813941010 | 2019-04-25 | HA/REVENTE | SATAIR | COVER ASSY | 28139410 | NON-SPARES | 10 | 1 | EXP | A9252597000800 | 1STR*01148 | NA | 24250 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-27 | NA | 100% | 2019-06-26 | 100% | NA | NA | 100% |  |  | 2019-05-22 | 2019-06-27 | Sous-poste | Sous-poste | 2019-05-25 | 2019-07-02 | 2019-07-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 26 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2814683510 | 2019-05-06 | HA/REVENTE | SATAIR | COVER ASSY | 28146835 | NON-SPARES | 10 | 1 | EXP | L9251394100000 | 1STR*10675 | NA | 24549 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-06-28 | NA | 100% | 2019-06-27 | 100% | NA | NA | 100% |  |  | 2019-05-31 | 2019-06-28 | Sous-poste | Sous-poste | 2019-06-05 | 2019-07-03 | 2019-07-03 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 26 | 6 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003865310 | 2019-06-14 | FABRICATION | STELIA | FAISCEAU | 4900038653 | NON-SPARES | 10 | 1 | EXP | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-03 | 2019-07-03 | Sous-poste | Sous-poste | 2019-07-08 | 2019-07-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 27 | 7 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
2806045110 | 2019-02-12 | FABRICATION | SATAIR | 117 | 28060451 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 21862 | LTE990103 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-04 | 100% | NA | NA | 5.556% |  |  | 2019-07-05 | 2019-07-05 | Sous-poste | Sous-poste | 2019-07-10 | 2019-07-10 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 27 | 7 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2810116710 | 2019-03-18 | FABRICATION | SATAIR | JACK ASSY | 28101167 | NON-SPARES | 10 | 8 | RTN | F7161001100001 | 0 | NON PRESENT INDUS | 23027 | 304849-1 => 304849-8 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-04 | 100% | NA | NA | 5.556% |  |  | 2019-06-07 | 2019-07-05 | Sous-poste | Sous-poste | 2019-06-12 | 2019-07-10 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 27 | 7 | 2019 | 1.4928 | 12.3008 | 0.15376 | 12.4546 | COL | 0 | 0
2812835610 | 2019-04-15 | FABRICATION | SATAIR | 63 | 28128356 | NON-SPARES | 10 | 1 | AOG | D9550006300295 | 0 | NON PRESENT INDUS | 24049 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-05 | 100% | NA | NA | 5.556% |  |  | 2019-04-11 | 2019-07-08 | Sous-poste | Sous-poste | 2019-04-15 | 2019-07-10 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 28 | 7 | 2019 | 0.205 | 3.007 | 0.75175 | 3.7587 | COL | 0 | 0
2809294220 | 2019-06-17 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 28092942 | NON-SPARES | 20 | 1 | RTN | F9251367800000 | 1STR*10672 | NA | 22351 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-08 | NA | 100% | 2019-07-08 | 100% | NA | NA | 100% |  |  | 2019-07-08 | 2019-07-08 | Sous-poste | Sous-poste | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2814631810 | 2019-05-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28146318 | NON-SPARES | 10 | 2 | AOG | F9251360500100 | 1STR*11187 | NA | 24532 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-10 | 100% | NA | NA | 100% |  |  | 2019-05-08 | 2019-07-09 | Sous-poste | Sous-poste | 2019-05-11 | 2019-07-11 | 2019-07-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2812097610 | 2019-04-08 | FABRICATION | SATAIR | 453 | 28120976 | NON-SPARES | 10 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 23793 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-08 | 100% | NA | NA | 5.556% |  |  | 2019-05-29 | 2019-07-09 | Sous-poste | Sous-poste | 2019-06-03 | 2019-07-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
2816548310 | 2019-05-21 | HA/REVENTE | SATAIR | PLATE ASSY | 28165483 | NON-SPARES | 10 | 1 | RTN | F9251176900000 | 4STR*01313 | NA | 25001 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-09 | NA | 100% | 2019-07-10 | 100% | NA | NA | 100% |  |  | 2019-06-26 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-01 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319210 | 2018-07-05 | HA/REVENTE | SATAIR | PLATE ASSY | 27843192 | NON-SPARES | 10 | 1 | RTN | F9251485300000 | 1STR*01521 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-02 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784320010 | 2014-01-01 | HA/REVENTE | SATAIR | TUBE | 27843200 | NON-SPARES | 10 | 1 | RTN | F9251110801200 | 1STR*00294 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-08 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784320410 | 2018-07-05 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 27843204 | NON-SPARES | 10 | 1 | RTN | F9251485400000 | 1STR*10825 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-02 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319610 | 2018-07-05 | HA/REVENTE | SATAIR/AIS | ANGLE | 27843196 | NON-SPARES | 10 | 2 | RTN | F9251445920000 | 1STR*01520 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-02 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784318910 | 2018-07-05 | HA/REVENTE | SATAIR | TUBE | 27843189 | NON-SPARES | 10 | 2 | RTN | F9251110800500 | 1STR*00297 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-08 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2784319810 | 2018-07-05 | HA/REVENTE | SATAIR | TUBE | 27843198 | NON-SPARES | 10 | 1 | RTN | F9251110800800 | 1STR*00292 | NA | 15226 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-10 | NA | 100% | 2019-07-08 | 100% | NA | NA | 100% |  |  | 2019-07-09 | 2019-07-09 | Sous-poste | Sous-poste | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2018 | 28 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2814128810 | 2019-04-29 | FABRICATION | SATAIR | 27 | 28141288 | NON-SPARES | 10 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 24548 | LTE990025 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-09 | 100% | NA | NA | 5.556% |  |  | 2019-07-03 | 2019-07-10 | Sous-poste | Sous-poste | 2019-07-08 | 2019-07-15 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 28 | 7 | 2019 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2809149110 | 2019-03-08 | FABRICATION | SATAIR | 60 | 28091491 | NON-SPARES | 10 | 1 | AOG | D9551006000195 | IS0032114M | NON PRESENT INDUS | 22807 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-15 |  |  | Allemagne | Bloqué BE client | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2809149510 | 2019-03-08 | FABRICATION | SATAIR | 60 | 28091495 | NON-SPARES | 10 | 1 | AOG | D9551006000195 | IS0032114M | NON PRESENT INDUS | 22807 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2809149810 | 2019-03-08 | FABRICATION | SATAIR | 60 | 28091498 | NON-SPARES | 10 | 1 | AOG | D9551006000195 | IS0032114M | NON PRESENT INDUS | 22807 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2809150110 | 2019-03-08 | FABRICATION | SATAIR | 60 | 28091501 | NON-SPARES | 10 | 1 | AOG | D9551006000195 | IS0032114M | NON PRESENT INDUS | 22807 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2810644910 | 2019-03-22 | FABRICATION | SATAIR | 61 | 28106449 | NON-SPARES | 10 | 1 | AOG | D9551006100195 | IS0032120M | NON PRESENT INDUS | 23349 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-26 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-30 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2810645110 | 2019-03-22 | FABRICATION | SATAIR | 61 | 28106451 | NON-SPARES | 10 | 1 | AOG | D9551006100195 | IS0032120M | NON PRESENT INDUS | 23349 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-26 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-30 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2810645210 | 2019-03-22 | FABRICATION | SATAIR | 61 | 28106452 | NON-SPARES | 10 | 1 | AOG | D9551006100195 | IS0032120M | NON PRESENT INDUS | 23349 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-26 | 2019-07-11 | Sous-poste | Sous-poste | 2019-04-30 | 2019-07-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2807271910 | 2019-02-20 | FABRICATION | SATAIR | JACK | 28072719 | NON-SPARES | 10 | 6 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 22133 | LTE990022 => LTE990027 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-12 | 100% | NA | NA | 5.556% |  |  | 2019-03-19 | 2019-07-11 | Sous-poste | Sous-poste | 2019-03-22 | 2019-07-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 28 | 7 | 2019 | 0 | 13.0116 | 0.54215 | 13.5537 | COL | 0 | 0
2808255910 | 2019-03-02 | FABRICATION | SATAIR | JACK | 28082559 | NON-SPARES | 10 | 2 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 22584 | LTE990028 => LTE990029 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-12 | 100% | NA | NA | 5.556% |  |  | 2019-05-27 | 2019-07-11 | Sous-poste | Sous-poste | 2019-05-30 | 2019-07-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0 | 4.3372 | 0.54215 | 4.8793 | COL | 0 | 0
490003810610 | 2019-04-08 | FABRICATION | STELIA | CÂBLE | 4900038106 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 324922-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-07-10 | 100% | NA | NA | 5.556% |  |  | 2019-06-27 | 2019-07-11 | Sous-poste | Sous-poste | 2019-07-02 | 2019-07-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 28 | 7 | 2019 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490003849710 | 2019-05-28 | FABRICATION | STELIA | CÂBLE | 4900038497 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 364204-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-07-10 | 100% | NA | NA | 5.556% |  |  | 2019-07-03 | 2019-07-11 | Sous-poste | Sous-poste | 2019-07-07 | 2019-07-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 28 | 7 | 2019 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2809165510 | 2019-03-08 | FABRICATION | SATAIR | 62 | 28091655 | NON-SPARES | 10 | 1 | RTN | D9551006200195 | IS0032126M | NON PRESENT INDUS | 22807 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-11 | 100% | NA | NA | 5.556% |  |  | 2019-04-02 | 2019-07-12 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 28 | 7 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2809792610 | 2019-03-13 | FABRICATION | SATAIR | BUNDLE | 28097926 | NON-SPARES | 10 | 8 | AOG | D9000095493095 | 0 | NON PRESENT INDUS | 23238 | 307502-1 307506-1 307510-1 307514-1 307518-1 307522-1 307526-1 307530-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-17 | 100% | NA | NA | 5.556% |  |  | 2019-07-17 | 2019-07-17 | Sous-poste | Sous-poste | 2019-07-19 | 2019-07-19 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 29 | 7 | 2019 | 19.4992 | 89.096 | 1.1137 | 90.2097 | NA | 0 | 0
490003854410 | 2014-01-01 | HA/REVENTE | STELIA | PILLAR | 4900038544 | NON-SPARES | 10 | 8 | RTN | F0003057821000 | 1QME*17052 | NA | 25363 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-18 | NA | 100% | 2019-07-17 | 100% | NA | NA | 100% |  |  | 2019-07-18 | 2019-07-18 | Sous-poste | Sous-poste | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 29 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003854010 | 2014-01-01 | HA/REVENTE | STELIA | SPHERE | 4900038540 | NON-SPARES | 10 | 2 | RTN | S9251342320000 | 1STR*06202 | NA | 25361 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-18 | NA | 100% | 2019-07-17 | 100% | NA | NA | 100% |  |  | 2019-07-18 | 2019-07-18 | Sous-poste | Sous-poste | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 29 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2812525410 | 2019-04-11 | HA/REVENTE | SATAIR | PLATE ASSY | 28125254 | NON-SPARES | 10 | 20 | RTN | D9251101900000 | 1STR*11007 | NA | 23922 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-19 | NA | 100% | 2019-07-17 | 100% | NA | NA | 100% |  |  | 2019-07-19 | 2019-07-19 | Sous-poste | Sous-poste | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 29 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2809165710 | 2019-03-08 | FABRICATION | SATAIR | 62 | 28091657 | NON-SPARES | 10 | 1 | AOG | D9551006200195 | IS0032126M | NON PRESENT INDUS | 22807 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-15 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-22 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 30 | 7 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2809165910 | 2019-03-08 | FABRICATION | SATAIR | 62 | 28091659 | NON-SPARES | 10 | 1 | AOG | D9551006200195 | IS0032126M | NON PRESENT INDUS | 22807 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-15 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-22 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 30 | 7 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2809166210 | 2019-03-08 | FABRICATION | SATAIR | 62 | 28091662 | NON-SPARES | 10 | 1 | AOG | D9551006200195 | IS0032126M | NON PRESENT INDUS | 22807 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-15 | 100% | NA | NA | 5.556% |  |  | 2019-04-03 | 2019-07-22 | Sous-poste | Sous-poste | 2019-04-05 | 2019-07-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 30 | 7 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2816548210 | 2019-05-21 | FABRICATION | SATAIR | 45 | 28165482 | NON-SPARES | 10 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | 25072 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-18 | 100% | NA | NA | 5.556% |  |  | 2019-06-27 | 2019-07-23 | Sous-poste | Sous-poste | 2019-07-01 | 2019-07-25 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 30 | 7 | 2019 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
490003882810 | 2019-07-05 | FABRICATION | STELIA | CÂBLE | 4900038828 | NON-SPARES | 10 | 3 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 386426-1 => 386426-3 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-06-22 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-07-23 | Sous-poste | Sous-poste | 2019-07-26 | 2019-07-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 30 | 7 | 2019 | 0.615 | 3 | 0.1 | 3.1 | NA | 0 | 0
2820316510 | 2019-07-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28203165 | NON-SPARES | 10 | 2 | EXP | D9251095600000 | IS0053509S | NA | 26247 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-24 | NA | 100% | 2019-07-22 | 100% | NA | NA | 100% |  |  | 2019-07-24 | 2019-07-24 | Sous-poste | Sous-poste | 2019-07-28 | 2019-07-28 | 2019-07-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 30 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2813275710 | 2019-04-18 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28132757 | NON-SPARES | 10 | 1 | RTN | D9251490100000 | IS0032740S | NA | 24988 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-07-25 | NA | 100% | 2019-07-23 | 100% | NA | NA | 100% |  |  | 2019-07-12 | 2019-07-25 | Sous-poste | Sous-poste | 2019-07-17 | 2019-07-30 | 2019-07-30 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 30 | 7 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003848910 | 2019-05-27 | FABRICATION | STELIA | CABLE COAXIAL | 4900038489 | NON-SPARES | 10 | 14 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 25296 | 364206-1 364206-14 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-26 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-07-29 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-01 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 31 | 7 | 2019 | 2.6964 | 10.5182 | 0.07513 | 10.5933 | NA | 0 | 0
2793828610 | 2018-10-17 | HA/REVENTE | SATAIR | BAR ASSY TORSION | 27938286 | NON-SPARES | 10 | 1 | RTN | V9251155800000 | 1STR*10747 | NA | 16567 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2018-11-20 | NA | 100% | 2018-11-12 | 100% | NA | NA | 100% |  |  | 2019-07-23 | 2019-07-30 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-02 | 2019-08-02 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 31 | 7 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2810645310 | 2019-03-22 | FABRICATION | SATAIR | 61 | 28106453 | NON-SPARES | 10 | 1 | AOG | D9551006100195 | IS0032120M | NON PRESENT INDUS | 23349 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-01 | 100% | NA | NA | 5.556% |  |  | TBD | 2019-07-31 | Sous-poste | Sous-poste |  | 2019-08-02 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 31 | 7 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2818614410 | 2019-06-14 | FABRICATION | SATAIR | BUNDLE | 28186144 | NON-SPARES | 10 | 1 | RTN | F9000095447895 | 0 | NON PRESENT INDUS | 26421 | 384330-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-17 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-07-31 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 31 | 7 | 2019 | 0.6 | 9.24 | 0.924 | 10.164 | NA | 0 | 0
2791106910 | 2018-09-12 | FABRICATION | SATAIR | PROTECTION CAP | 27911069 | NON-SPARES | 10 | 7 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 17018 | 133557-1 => 133557-7 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-06-30 | 100% | NA | NA | 5.556% |  |  | 2019-07-31 | 2019-07-31 | Sous-poste | Sous-poste | 2019-08-05 | 2019-08-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 31 | 7 | 2019 | 0.0175 | 0.7826 | 0.01118 | 0.79378 | NA | 0 | 0
2815099710 | 2019-05-09 | FABRICATION | SATAIR | 22 | 28150997 | NON-SPARES | 10 | 1 | AOG | D9551002200895 | 0 | NON PRESENT INDUS | 24697 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-19 | 100% | NA | NA | 5.556% |  |  | 2019-07-15 | 2019-08-01 | Sous-poste | Sous-poste | 2019-07-17 | 2019-08-05 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 31 | 8 | 2019 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2814055310 | 2019-04-27 | HA/REVENTE | SATAIR | COVER ASSY | 28140553 | NON-SPARES | 10 | 2 | RTN | A9252597000900 | 1STR*01482 | NA | 24526 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-01 | NA | 100% | 2019-07-29 | 100% | NA | NA | 100% |  |  | 2019-07-22 | 2019-08-01 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-06 | 2019-08-06 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 31 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2814857410 | 2019-05-07 | FABRICATION | SATAIR | 518 | 28148574 | NON-SPARES | 10 | 1 | CRIT | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 24699 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-08-01 | 100% | NA | NA | 5.556% |  |  | 2019-06-04 | 2019-08-02 | Sous-poste | Sous-poste | 2019-06-06 | 2019-08-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 31 | 8 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2821491210 | 2019-07-11 | FABRICATION | SATAIR | 511 | 28214912 | NON-SPARES | 10 | 1 | AOG | WF413SBAAAAA | 0 | NON PRESENT INDUS | 26660 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-29 | 100% | NA | NA | 5.556% |  |  | 2019-07-16 | 2019-08-02 | Sous-poste | Sous-poste | 2019-07-18 | 2019-08-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 31 | 8 | 2019 | 0.51 | 0.9813 | 0.24533 | 1.2266 | COL | 0 | 0
2822261710 | 2019-07-18 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | 28222617 | NON-SPARES | 10 | 1 | AOG | F9252030900000 | IS0032162M | NON PRESENT INDUS | 26892 | 395731-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-25 | 100% | NA | NA | 5.556% |  |  | 2019-07-16 | 2019-08-02 | Sous-poste | Sous-poste | 2019-07-18 | 2019-08-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 31 | 8 | 2019 | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
2820317610 | 2019-07-01 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 28203176 | NON-SPARES | 10 | 1 | AOG | F9251367800000 | 1STR*10672 | NA | 26240 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-05 | NA | 100% | 2019-07-30 | 100% | NA | NA | 100% |  |  | 2019-07-03 | 2019-08-02 | Sous-poste | Sous-poste | 2019-07-05 | 2019-08-06 | 2019-08-06 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 31 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2810408710 | 2019-03-20 | FABRICATION | SATAIR | JACK | 28104087 | NON-SPARES | 10 | 2 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 23073 | LTE990030 => LTE990031 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-05-11 | 100% | NA | NA | 5.556% |  |  | 2019-06-13 | 2019-08-05 | Sous-poste | Sous-poste | 2019-06-18 | 2019-08-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 32 | 8 | 2019 | 0 | 4.3372 | 0.54215 | 4.8793 | COL | 0 | 0
2793585610 | 2018-10-15 | FABRICATION | SATAIR | PROTECTION CAP | 27935856 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 18015 | 168314-1 => 168314-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-02 | 100% | NA | NA | 5.556% |  |  | 2019-08-05 | 2019-08-05 | Sous-poste | Sous-poste | 2019-08-08 | 2019-08-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 32 | 8 | 2019 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2815361010 | 2019-05-10 | HA/REVENTE | SATAIR | COVER ASSY | 28153610 | NON-SPARES | 10 | 1 | RTN | L9251394100000 | 1STR*10675 | NA | 24549 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-05 | NA | 100% | 2019-07-24 | 100% | NA | NA | 100% |  |  | 2019-08-05 | 2019-08-05 | Sous-poste | Sous-poste | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 32 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2819793710 | 2019-06-25 | FABRICATION | SATAIR | BUNDLE | 28197937 | NON-SPARES | 10 | 1 | RTN | F9000095448895 | 0 | NON PRESENT INDUS | 26443 | 384778-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-24 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-08-06 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 32 | 8 | 2019 | 0.4 | 10 | 1 | 11 | NA | 0 | 0
490003850110 | 2019-05-28 | FABRICATION | STELIA | FAISCEAU GENERATION (ATR72) | 4900038501 | NON-SPARES | 10 | 1 | RTN | S9110126000195 | 0 | NON PRESENT INDUS | 27387 | 364174-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-01 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-08-06 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 32 | 8 | 2019 | 0.205 | 0.5 | 0.125 | 0.625 | NA | 0 | 0
2769104710 | 2014-01-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27691047 | NON-SPARES | 10 | 6 | RTN | D9251095600000 | IS0053509S | NA | 11653 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-06 | NA | 100% | 2018-06-07 | 100% | NA | NA | 100% |  |  | 2018-07-27 | 2019-08-06 | Sous-poste | Sous-poste | 2018-08-01 | 2019-08-09 | 2019-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 32 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2791050310 | 2018-09-12 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 27910503 | NON-SPARES | 10 | 10 | RTN | D9251095600000 | IS0053509S | NA | 17174 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-06 | NA | 100% | 2018-12-03 | 100% | NA | NA | 100% |  |  | 2018-12-05 | 2019-08-06 | Sous-poste | Sous-poste | 2018-12-10 | 2019-08-09 | 2019-08-09 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 32 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2818499610 | 2019-06-13 | HA/REVENTE | SATAIR | BRACKET ASSY | 28184996 | NON-SPARES | 10 | 4 | AOG | D9251734300000 | 1STR*10118 | NA | 25683 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-08 | NA | 100% | 2019-08-07 | 100% | NA | NA | 100% |  |  | 2019-10-09 | 2019-08-07 | Sous-poste | Sous-poste | 2019-10-11 | 2019-08-09 | 2019-08-09 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 32 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2815830810 | 2019-05-15 | FABRICATION | SATAIR | 518 | 28158308 | NON-SPARES | 10 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 24699 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-07-31 | 100% | NA | NA | 5.556% |  |  | 2019-08-07 | 2019-08-07 | Sous-poste | Sous-poste | 2019-08-12 | 2019-08-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 32 | 8 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2806045310 | 2019-02-12 | FABRICATION | SATAIR | 117 | 28060453 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 21862 | LTE990104 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-06 | 100% | NA | NA | 5.556% |  |  | 2019-08-07 | 2019-08-07 | Sous-poste | Sous-poste | 2019-08-12 | 2019-08-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 32 | 8 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2806046110 | 2019-02-12 | FABRICATION | SATAIR | 117 | 28060461 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 21862 | LTE990105 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-06 | 100% | NA | NA | 5.556% |  |  | 2019-08-07 | 2019-08-07 | Sous-poste | Sous-poste | 2019-08-12 | 2019-08-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 32 | 8 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2806047310 | 2019-02-12 | FABRICATION | SATAIR | 117 | 28060473 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 21862 | LTE990106 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-06 | 100% | NA | NA | 5.556% |  |  | 2019-08-07 | 2019-08-07 | Sous-poste | Sous-poste | 2019-08-12 | 2019-08-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 32 | 8 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
28218908 630144494410 | 2019-07-15 | FABRICATION | SATAIR | 108 | 28218908 6301444944 | NON-SPARES | 10 | 1 | AOG | D9550010801295 | IS0032586M | NON PRESENT INDUS | 26774 | LTE990002 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-07-11 | 2019-08-14 | Sous-poste | Sous-poste | 2019-07-15 | 2019-08-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 33 | 8 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2825029710 | 2019-08-15 | FABRICATION | SATAIR | 27 | 28250297 | NON-SPARES | 10 | 1 | CRIT | D9551002700595 | IS0032094M | NON PRESENT INDUS | 27640 | LTE990026 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-11 | 100% | NA | NA | 5.556% |  |  | 2019-08-14 | 2019-08-14 | Sous-poste | Sous-poste | 2019-08-17 | 2019-08-16 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 33 | 8 | 2019 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2818205210 | 2019-06-12 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28182052 | NON-SPARES | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 25594 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-21 | NA | 100% | 2019-08-20 | 100% | NA | NA | 100% |  |  | 2019-08-12 | 2019-08-21 | Sous-poste | Sous-poste | 2019-08-15 | 2019-08-26 | 2019-08-26 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 34 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2819793610 | 2019-06-25 | FABRICATION | SATAIR | BUNDLE | 28197936 | NON-SPARES | 10 | 1 | EXP | F9000095448795 | 0 | NON PRESENT INDUS | 26437 | 384603-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-01 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-08-23 | Sous-poste | Sous-poste | 2019-07-26 | 2019-08-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 34 | 8 | 2019 | 0.4 | 10 | 1 | 11 | NA | 0 | 0
2816823610 | 2019-05-23 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28168236 | NON-SPARES | 10 | 5 | RTN | D9251095600000 | IS0053509S | NA | 25120 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-23 | NA | 100% | 2019-08-22 | 100% | NA | NA | 100% |  |  | 2019-08-23 | 2019-08-23 | Sous-poste | Sous-poste | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 34 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2816823710 | 2019-05-23 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28168237 | NON-SPARES | 10 | 4 | RTN | D9251095400000 | IS0053354S | NA | 25120 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-23 | NA | 100% | 2019-08-22 | 100% | NA | NA | 100% |  |  | 2019-08-23 | 2019-08-23 | Sous-poste | Sous-poste | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 34 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2818410810 | 2019-06-12 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28184108 | NON-SPARES | 10 | 4 | RTN | D9251095400000 | IS0053354S | NA | 25682 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-23 | NA | 100% | 2019-08-22 | 100% | NA | NA | 100% |  |  | 2019-08-23 | 2019-08-23 | Sous-poste | Sous-poste | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 34 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2826075330 | 2019-08-26 | FABRICATION | SATAIR | 27 | 28260753 | NON-SPARES | 30 | 6 | CRIT | D9551002700495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-26 | 2019-08-26 | Sous-poste | Sous-poste | 2019-08-28 | 2019-08-28 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 35 | 8 | 2019 | 1.23 | 29.5038 | 1.2293 | 30.7331 | COL | 0 | 0
490003863710 | 2019-06-13 | FABRICATION | STELIA | FAISCEAU | 4900038637 | NON-SPARES | 10 | 6 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 374768-1 => 374768-6 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-07-14 | 100% | NA | NA | 5.556% |  |  | 2019-08-15 | 2019-08-26 | Sous-poste | Sous-poste | 2019-08-20 | 2019-08-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 35 | 8 | 2019 | 1.23 | 4.2 | 0.07 | 4.27 | NA | 0 | 0
490003916310 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900039163 | NON-SPARES | 10 | 1 | CRIT | S9251302520000 | 1QEL*10071 | NA | 27658 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-27 | NA | 100% | 2019-08-27 | 100% | NA | NA | 100% |  |  | 2019-08-20 | 2019-08-27 | Sous-poste | Sous-poste | 2019-08-22 | 2019-08-29 | 2019-08-29 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 35 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823030110 | 2019-07-24 | FABRICATION | SATAIR | OPTICAL FIBER | 28230301 | NON-SPARES | 10 | 3 | RTN | D9291011200095 | 0 | NON PRESENT INDUS | 27165 | 402133-1 => 402133-3 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-07-31 | 100% | NA | NA | 5.556% |  |  | 2019-07-30 | 2019-08-27 | Sous-poste | Sous-poste | 2019-08-03 | 2019-08-30 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 35 | 8 | 2019 | 0 | 0 | 0 | 0 | COL | 0 | 0
490003896810 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900038968 | NON-SPARES | 10 | 1 | RTN | S9251458000000 | 3STR*01167 | NA | 27030 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-27 | NA | 100% | 2019-08-26 | 100% | NA | NA | 100% |  |  | 2019-08-16 | 2019-08-27 | Sous-poste | Sous-poste | 2019-08-21 | 2019-08-30 | 2019-08-30 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 35 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2826222410 | 2019-08-28 | FABRICATION | SATAIR | CONDUIT | 28262224 | NON-SPARES | 10 | 4 | CRIT | F9249270400500 | 0 | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-08-27 | 2019-08-29 | Sous-poste | Sous-poste | 2019-08-30 | 2019-09-02 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 35 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823625610 | 2019-07-31 | HA/REVENTE | SATAIR | FORK | 28236256 | NON-SPARES | 10 | 1 | AOG | F9251446020000 | 1QME*17096 | NA | 26959 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-08-30 | NA | 100% | 2019-08-28 | 100% | NA | NA | 100% |  |  | 2019-07-29 | 2019-08-29 | Sous-poste | Sous-poste | 2019-07-31 | 2019-09-02 | 2019-09-02 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 35 | 8 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003873920 | 2019-06-28 | FABRICATION | STELIA | CABLE COAXIAL | 4900038739 | NON-SPARES | 20 | 7 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-30 | 2019-08-30 | Sous-poste | Sous-poste | 2019-09-04 | 2019-09-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 35 | 8 | 2019 | 1.3482 | 5.2591 | 0.07513 | 5.3342 | NA | 0 | 0
2818410910 | 2019-06-12 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28184109 | NON-SPARES | 10 | 4 | RTN | D9251095600000 | IS0053509S | NA | 25682 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-03 | NA | 100% | 2019-08-30 | 100% | NA | NA | 100% |  |  | 2019-09-02 | 2019-09-02 | Sous-poste | Sous-poste | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 36 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2818650110 | 2019-06-14 | FABRICATION | SATAIR | JACK | 28186501 | NON-SPARES | 10 | 3 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 25762 | LTE990032 => LTE990034 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-01 | 100% | NA | NA | 5.556% |  |  | 2019-07-10 | 2019-09-03 | Sous-poste | Sous-poste | 2019-07-14 | 2019-09-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 36 | 9 | 2019 | 0 | 6.5058 | 0.54215 | 7.0479 | COL | 0 | 0
490003882410 | 2019-07-05 | FABRICATION | STELIA | FAISCEAU | 4900038824 | NON-SPARES | 10 | 7 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | N/A | 386457-1 => 386457-7 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-08-03 | 100% | NA | NA | 5.556% |  |  | 2019-09-04 | 2019-09-04 | Sous-poste | Sous-poste | 2019-09-09 | 2019-09-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 36 | 9 | 2019 | 1.435 | 4.9 | 0.07 | 4.97 | NA | 0 | 0
490003884110 | 2014-01-01 | HA/REVENTE | STELIA | PANNEAU FERMETURE ÉQUIPÉ | 4900038841 | NON-SPARES | 10 | 1 | RTN | S9251026100700 | 1STR*01138 | NA | 26577 | 0 | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | TBD | 100% | NA | NA | 100% |  |  | 2019-09-04 | 2019-09-04 | Sous-poste | Sous-poste | 2019-09-09 | 2019-09-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 36 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003875710 | 2019-07-03 | FABRICATION | STELIA | SUPPORT | 4900038757 | NON-SPARES | 10 | 1 | RTN | S9242302300000 | 0 | NON PRESENT INDUS | 4886 26677 | 387656-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-08-29 | 100% | NA | NA | 5.556% |  |  | 2019-07-23 | 2019-09-10 | Sous-poste | Sous-poste | 2019-07-26 | 2019-09-13 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 37 | 9 | 2019 | 0 | 0 | 0 | 0 | COL | 0 | 0
2823282410 | 2019-07-26 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28232824 | NON-SPARES | 10 | 1 | AOG | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 27316 | 402840-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-02 | 100% | NA | NA | 5.556% |  |  | 2019-07-24 | 2019-09-11 | Sous-poste | Sous-poste | 2019-07-26 | 2019-09-13 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 37 | 9 | 2019 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2824105310 | 2019-08-06 | FABRICATION | SATAIR | CONDUIT ASSY | 28241053 | NON-SPARES | 10 | 3 | RTN | D9249183305000 | 0 | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-09-02 | 2019-09-11 | Sous-poste | Sous-poste | 2019-09-06 | 2019-09-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 37 | 9 | 2019 | 0 | 0 | 0 | 0 | MEX | 0 | 0
2808066510 | 2019-02-28 | FABRICATION | SATAIR | 117 | 28080665 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22398 | LTE990114 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-12 | 100% | NA | NA | 5.556% |  |  | 2019-09-11 | 2019-09-11 | Sous-poste | Sous-poste | 2019-09-16 | 2019-09-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 37 | 9 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824105210 | 2019-08-06 | FABRICATION | SATAIR | CONDUIT ASSY | 28241052 | NON-SPARES | 10 | 2 | RTN | D9249183305000 | 0 | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-09-19 | 2019-09-11 | Sous-poste | Sous-poste | 2019-09-25 | 2019-09-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 37 | 9 | 2019 | 0 | 0 | 0 | 0 | MEX | 0 | 0
2823228410 | 2019-07-28 | FABRICATION | SATAIR | BUNDLE | 28232284 | NON-SPARES | 10 | 1 | RTN | F9000095447895 | 0 | NON PRESENT INDUS | 27285 | 402633-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-02 | 100% | NA | NA | 5.556% |  |  | 2019-08-13 | 2019-09-12 | Sous-poste | Sous-poste | 2019-08-16 | 2019-09-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 37 | 9 | 2019 | 0.6 | 9.24 | 0.924 | 10.164 | NA | 0 | 0
490003885110 | 2019-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900038851 | NON-SPARES | 10 | 5 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 26600 | 387498-1 => 387498-5 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-02 | 100% | NA | NA | 5.556% |  |  | 2019-09-09 | 2019-09-13 | Sous-poste | Sous-poste | 2019-09-12 | 2019-09-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 37 | 9 | 2019 | 0.963 | 3.7565 | 0.07513 | 3.8316 | NA | 0 | 0
2822512010 | 2019-07-19 | HA/REVENTE | SATAIR | FORK | 28225120 | NON-SPARES | 10 | 1 | CRIT | F9251446020000 | 1QME*17096 | NA | 26959 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-16 | NA | 100% | 2019-09-16 | 100% | NA | NA | 100% |  |  | 2019-08-19 | 2019-09-16 | Sous-poste | Sous-poste | 2019-08-21 | 2019-09-18 | 2019-09-18 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 38 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2794403810 | 2018-10-23 | FABRICATION | SATAIR | 517 | 27944038 | NON-SPARES | 10 | 1 | RTN | WF417AFACAAE | 0 | NON PRESENT INDUS | 18204 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-11 | 100% | NA | NA | 5.556% |  |  | 2019-01-16 | 2019-09-17 | Sous-poste | Sous-poste | 2019-01-21 | 2019-09-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 38 | 9 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2824476710 | 2019-08-08 | FABRICATION | SATAIR | 56 | 28244767 | NON-SPARES | 10 | 1 | AOG | D9551005600695 | 0 | NON PRESENT INDUS | 27542 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-12 | 100% | NA | NA | 5.556% |  |  | 2019-08-08 | 2019-09-18 | Sous-poste | Sous-poste | 2019-08-12 | 2019-09-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 38 | 9 | 2019 | 0.205 | 1.8637 | 0.46593 | 2.3296 | COL | 0 | 0
2820050510 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28200505 | NON-SPARES | 10 | 2 | RTN | D9251490100000 | IS0032740S | NA | 26176 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-20 | NA | 100% | 2019-09-19 | 100% | NA | NA | 100% |  |  | 2019-09-20 | 2019-09-20 | Sous-poste | Sous-poste | 2019-09-26 | 2019-09-25 | 2019-09-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 38 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2822036310 | 2019-07-16 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28220363 | NON-SPARES | 10 | 2 | EXP | D9251490100000 | IS0032740S | NA | 26810 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-20 | NA | 100% | 2019-09-19 | 100% | NA | NA | 100% |  |  | 2019-08-12 | 2019-09-20 | Sous-poste | Sous-poste | 2019-08-15 | 2019-09-25 | 2019-09-25 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 38 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2820142610 | 2019-06-28 | HA/REVENTE | SATAIR | PLATE ASSY | 28201426 | NON-SPARES | 10 | 2 | AOG | A9251152500000 | IS0031658S | NA | 26180 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-25 | NA | 100% | 2019-09-23 | 100% | NA | NA | 100% |  |  | 2019-08-22 | 2019-09-24 | Sous-poste | Sous-poste | 2019-08-27 | 2019-09-26 | 2019-09-26 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 39 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2820143110 | 2019-06-28 | HA/REVENTE | SATAIR | PLATE ASSY-BLANKING | 28201431 | NON-SPARES | 10 | 1 | AOG | A9252235700000 | 1STR*11048 | NA | 26180 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-09-25 | NA | 100% | 2019-09-23 | 100% | NA | NA | 100% |  |  | 2019-08-22 | 2019-09-24 | Sous-poste | Sous-poste | 2019-08-27 | 2019-09-26 | 2019-09-26 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 39 | 9 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2793585710 | 2018-10-15 | FABRICATION | SATAIR | PROTECTION CAP | 27935857 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 18015 | 168315-1 => 168315-10 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-09 | 100% | NA | NA | 5.556% |  |  | 2019-09-26 | 2019-09-26 | Sous-poste | Sous-poste | 2019-10-01 | 2019-10-01 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 39 | 9 | 2019 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2822994220 | 2019-07-24 | FABRICATION | SATAIR | 45 | 28229942 | NON-SPARES | 20 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-29 | 2019-09-27 | Sous-poste | Sous-poste | 2019-08-01 | 2019-10-01 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2019 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
2826837510 | 2019-09-04 | FABRICATION | SATAIR | 61 | 28268375 | NON-SPARES | 10 | 1 | AOG | D9551006100295 | 0 | NON PRESENT INDUS | 27959 | LTE990022 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-25 | 100% | NA | NA | 5.556% |  |  | 2019-09-18 | 2019-10-02 | Sous-poste | Sous-poste | 2019-09-21 | 2019-10-04 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 40 | 10 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
490003926110 | 2014-01-01 | HA/REVENTE | STELIA | RAMPE | 4900039261 | NON-SPARES | 10 | 1 | RTN | S9251458000000 | 3STR*01167 | NA | 28152 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-02 | NA | 100% | 2019-10-01 | 100% | NA | NA | 100% |  |  | 2019-10-02 | 2019-10-02 | Sous-poste | Sous-poste | 2019-10-05 | 2019-10-05 | 2019-10-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 40 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2825264310 | 2019-08-19 | FABRICATION | SATAIR | 45 | 28252643 | NON-SPARES | 10 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | 27639 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-16 | 100% | NA | NA | 5.556% |  |  | 2019-09-23 | 2019-10-07 | Sous-poste | Sous-poste | 2019-09-26 | 2019-10-09 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 41 | 10 | 2019 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
490003921110 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900039211 | NON-SPARES | 10 | 5 | AOG | S9252318000000 | 1STR*02063 | NA | 28063 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-09 | NA | 100% | 2019-10-08 | 100% | NA | NA | 100% |  |  | 2019-11-11 | 2019-10-08 | Sous-poste | Sous-poste | 2019-11-13 | 2019-10-10 | 2019-10-10 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 41 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003944110 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE | 4900039441 | NON-SPARES | 10 | 4 | CRIT | F0003057820200 | 3QME*00792 | NA | 27651 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-10 | NA | 100% | 2019-10-08 | 100% | NA | NA | 100% |  |  | 2019-10-07 | 2019-10-09 | Sous-poste | Sous-poste | 2019-10-09 | 2019-10-11 | 2019-10-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 41 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2822209410 | 2019-07-18 | FABRICATION | STE | COVER ASSY | 28222094 | NON-SPARES | 10 | 1 | RTN | D9251074200200 | 0 | NON PRESENT INDUS | 26875 | 420839-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-08 | 100% | NA | NA | 5.556% |  |  | 2019-10-09 | 2019-10-09 | Sous-poste | Sous-poste | 2019-10-12 | 2019-10-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 41 | 10 | 2019 | 0 | 0.0884 | 0.00884 | 0.09724 | NA | 0 | 0
2824105011 | 2019-08-06 | FABRICATION | SATAIR | CONDUIT ASSY | 28241050 | NON-SPARES | 11 | 4 | RTN | D9249183305000 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-09 | 2019-10-09 | Sous-poste | Sous-poste | 2019-10-14 | 2019-10-14 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 41 | 10 | 2019 | 0 | 0 | 0 | 0 | MEX | 0 | 0
2822209210 | 2019-07-18 | HA/REVENTE | SATAIR | HOOK | 28222092 | NON-SPARES | 10 | 10 | RTN | A9252236000000 | 1STR*01447 | NA | 26876 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-10 | NA | 100% | 2019-10-11 | 100% | NA | NA | 100% |  |  | 2019-10-10 | 2019-10-10 | Sous-poste | Sous-poste | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 41 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2816177410 | 2019-05-16 | FABRICATION | SATAIR | 518 | 28161774 | NON-SPARES | 10 | 1 | CRIT | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 24699 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-16 | 100% | NA | NA | 5.556% |  |  | 2019-06-13 | 2019-10-11 | Sous-poste | Sous-poste | 2019-06-15 | 2019-10-15 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 41 | 10 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2800709420 | 2018-12-14 | FABRICATION | SATAIR | PROTECTION CAP | 28007094 | NON-SPARES | 20 | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-14 | 2019-10-14 | Sous-poste | Sous-poste | 2019-10-17 | 2019-10-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2018 | 42 | 10 | 2019 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
2770215110 | 2018-03-05 | FABRICATION | SATAIR | PLATE | 27702151 | NON-SPARES | 10 | 25 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 12653 | LTE3659 -> LTE3683 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-16 | 100% | NA | NA | 5.556% |  |  | 2018-06-27 | 2019-10-15 | Sous-poste | Sous-poste | 2018-06-30 | 2019-10-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2018 | 42 | 10 | 2019 | 0 | 78.43 | 0.72 | 79.15 | NA | 0 | 0
2822209310 | 2019-07-18 | HA/REVENTE | SATAIR | COVER ASSY | 28222093 | NON-SPARES | 10 | 4 | RTN | A9252597000800 | 1STR*01148 | NA | 26877 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-16 | NA | 100% | 2019-10-14 | 100% | NA | NA | 100% |  |  | 2019-10-10 | 2019-10-15 | Sous-poste | Sous-poste | 2019-10-16 | 2019-10-18 | 2019-10-18 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 42 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2830185510 | 2019-10-11 | HA/REVENTE | SATAIR | CONNECTOR-RECEPTACLE | 28301855 | NON-SPARES | 10 | 2 | AOG | ABS2220SE0G04AT | 1CON*01630 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-16 | NA | 100% | 2019-10-10 | 100% | NA | NA | 100% |  |  | 2019-10-16 | 2019-10-16 | Sous-poste | Sous-poste | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 42 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2828106010 | 2019-09-17 | FABRICATION | SATAIR | PLACARD SET | 28281060 | NON-SPARES | 10 | 3 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | NA | 434654-1 => 434654-3 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-10-10 | 100% | NA | NA | 5.556% |  |  | 2019-10-16 | 2019-10-16 | Sous-poste | Sous-poste | 2019-10-21 | 2019-10-21 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 42 | 10 | 2019 | 0 | 0.615 | 0.0205 | 0.6355 | NA | 0 | 0
490003952510 | 2014-01-01 | HA/REVENTE | STELIA | SPHERE | 4900039525 | NON-SPARES | 10 | 2 | RTN | S9251342320000 | 1STR*06202 | NA | 29289 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-28 | NA | 100% | 2019-10-28 | 100% | NA | NA | 100% |  |  | 2019-10-10 | 2019-10-28 | Sous-poste | Sous-poste | 2019-10-15 | 2019-10-31 | 2019-10-31 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 44 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2826925710 | 2019-09-05 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28269257 | NON-SPARES | 10 | 7 | RTN | D9251805700000 | IS0032776S | NA | 28061 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-29 | NA | 100% | 2019-10-28 | 100% | NA | NA | 100% |  |  | 2019-10-10 | 2019-10-29 | Sous-poste | Sous-poste | 2019-10-16 | 2019-11-01 | 2019-11-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 44 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2826925910 | 2019-09-05 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28269259 | NON-SPARES | 10 | 7 | RTN | D9251805800000 | IS0032777S | NA | 28061 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-29 | NA | 100% | 2019-10-28 | 100% | NA | NA | 100% |  |  | 2019-10-10 | 2019-10-29 | Sous-poste | Sous-poste | 2019-10-16 | 2019-11-01 | 2019-11-01 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 44 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2770215230 | 2018-03-05 | FABRICATION | SATAIR | PLATE | 27702152 | NON-SPARES | 30 | 25 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-05-25 | 2019-10-30 | Sous-poste | Sous-poste | 2018-05-30 | 2019-11-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2018 | 44 | 10 | 2019 | 0 | 78.43 | 0.72 | 79.15 | NA | 0 | 0
2824070010 | 2014-01-01 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28240700 | NON-SPARES | 10 | 4 | RTN | D9251490100000 | IS0032740S | NA | 27626 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-30 | NA | 100% | 2019-10-28 | 100% | NA | NA | 100% |  |  | 2019-10-30 | 2019-10-30 | Sous-poste | Sous-poste | 2019-11-04 | 2019-11-03 | 2019-11-03 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 44 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2826859740 | 2019-09-04 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | 28268597 | NON-SPARES | 40 | 1 | RTN | F9252030900000 | IS0032162M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-10-30 | Sous-poste | Sous-poste | 2019-11-04 | 2019-11-04 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 44 | 10 | 2019 | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
2824182310 | 2019-08-06 | HA/REVENTE | SATAIR | COVER ASSY | 28241823 | NON-SPARES | 10 | 1 | RTN | L9251394100000 | 1STR*10675 | NA | 27632 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-10-30 | NA | 100% | 2019-10-28 | 100% | NA | NA | 100% |  |  | 2019-10-30 | 2019-10-30 | Sous-poste | Sous-poste | 2019-11-05 | 2019-11-04 | 2019-11-04 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 44 | 10 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2812313460 | 2019-04-10 | FABRICATION | SATAIR | 27 | 28123134 | NON-SPARES | 60 | 5 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | #N/A | LTE990020 => LTE990024 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-30 | 2019-11-01 | Sous-poste | Sous-poste | 2019-09-05 | 2019-11-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 44 | 11 | 2019 | 1.8 | 24.5865 | 1.2293 | 25.8158 | COL | 0 | 0
2807359510 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28073595 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990107 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-05 | 100% | NA | NA | 5.556% |  |  | 2019-09-04 | 2019-11-01 | Sous-poste | Sous-poste | 2019-09-09 | 2019-11-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 44 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807359610 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28073596 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990108 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-05 | 100% | NA | NA | 5.556% |  |  | 2019-09-04 | 2019-11-01 | Sous-poste | Sous-poste | 2019-09-09 | 2019-11-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 44 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807412610 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28074126 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990110 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-05 | 100% | NA | NA | 5.556% |  |  | 2019-09-04 | 2019-11-01 | Sous-poste | Sous-poste | 2019-09-09 | 2019-11-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 44 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807662210 | 2019-02-25 | FABRICATION | SATAIR | 117 | 28076622 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22398 | LTE990113 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-05 | 100% | NA | NA | 5.556% |  |  | 2019-09-05 | 2019-11-01 | Sous-poste | Sous-poste | 2019-09-10 | 2019-11-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 44 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2821976310 | 2019-07-16 | FABRICATION | SATAIR | 5130VE | 28219763 | NON-SPARES | 10 | 1 | CRIT | WG281ABABAAE | 0 | NON PRESENT INDUS | 27009 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-25 | 100% | NA | NA | 5.556% |  |  | 2019-07-18 | 2019-11-04 | Sous-poste | Sous-poste | 2019-07-21 | 2019-11-06 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0.36 | 6.16 | 1.54 | 7.7 | COL | 0 | 0
2831247910 | 2019-10-23 | FABRICATION | SATAIR | CONDUIT | 28312479 | NON-SPARES | 10 | 1 | AOG | F9249260803400 | 0 | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-10-21 | 2019-11-05 | Sous-poste | Sous-poste | 2019-10-23 | 2019-11-07 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2824115310 | 2019-08-06 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28241153 | NON-SPARES | 10 | 2 | RTN | D9251805700000 | IS0032776S | NA | 27629 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-05 | NA | 100% | 2019-11-04 | 100% | NA | NA | 100% |  |  | 2019-09-26 | 2019-11-05 | Sous-poste | Sous-poste | 2019-10-02 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823634610 | 2019-07-31 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28236346 | NON-SPARES | 10 | 4 | RTN | D9251805700000 | IS0032776S | NA | 27629 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-05 | NA | 100% | 2019-11-04 | 100% | NA | NA | 100% |  |  | 2019-10-29 | 2019-11-05 | Sous-poste | Sous-poste | 2019-11-02 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823635010 | 2019-07-31 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28236350 | NON-SPARES | 10 | 6 | RTN | D9251805800000 | IS0032777S | NA | 27629 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-05 | NA | 100% | 2019-11-04 | 100% | NA | NA | 100% |  |  | 2019-10-18 | 2019-11-05 | Sous-poste | Sous-poste | 2019-10-24 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2825831410 | 2019-08-23 | FABRICATION | SATAIR | 27 | 28258314 | NON-SPARES | 10 | 1 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | 27717 | LTE990068 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-02 | 100% | NA | NA | 5.556% |  |  | 2019-08-22 | 2019-11-06 | Sous-poste | Sous-poste | 2019-08-26 | 2019-11-08 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2825831410 | 2019-08-23 | FABRICATION | SATAIR | 27 | 28258314 | NON-SPARES | 10 | 1 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | 27717 | LTE990068 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-02 | 100% | NA | NA | 5.556% |  |  | 2019-08-22 | 2019-11-06 | Sous-poste | Sous-poste | 2019-08-26 | 2019-11-08 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2825831410 | 2019-08-23 | FABRICATION | SATAIR | 27 | 28258314 | NON-SPARES | 10 | 1 | CRIT | D9551002700695 | IS0032097M | NON PRESENT INDUS | 27717 | LTE990068 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-02 | 100% | NA | NA | 5.556% |  |  | 2019-08-22 | 2019-11-06 | Sous-poste | Sous-poste | 2019-08-26 | 2019-11-08 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2825332510 | 2019-08-19 | HA/REVENTE | SATAIR | TUBE | 28253325 | NON-SPARES | 10 | 1 | AOG | F9251110800500 | 1STR*00297 | NA | 27623 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-07 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2019-11-06 | 2019-11-06 | Sous-poste | Sous-poste | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2825332610 | 2019-08-19 | HA/REVENTE | SATAIR/AIS | ANGLE | 28253326 | NON-SPARES | 10 | 2 | AOG | F9251445920000 | 1STR*01520 | NA | 27624 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-07 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2019-11-06 | 2019-11-06 | Sous-poste | Sous-poste | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823990510 | 2019-08-05 | HA/REVENTE | SATAIR | TUBE | 28239905 | NON-SPARES | 10 | 9 | AOG | F9251110801200 | 1STR*00294 | NA | 27635 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-07 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2020-02-27 | 2019-11-06 | Sous-poste | Sous-poste | 2020-03-02 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823990710 | 2019-08-05 | HA/REVENTE | SATAIR | TUBE | 28239907 | NON-SPARES | 10 | 9 | AOG | F9251110800800 | 1STR*00292 | NA | 27635 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-07 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2020-02-27 | 2019-11-06 | Sous-poste | Sous-poste | 2020-03-02 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823990810 | 2019-08-05 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 28239908 | NON-SPARES | 10 | 9 | AOG | F9251485400000 | 1STR*10825 | NA | 27635 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-07 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2020-02-27 | 2019-11-06 | Sous-poste | Sous-poste | 2020-03-02 | 2019-11-08 | 2019-11-08 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2801947710 | 2019-01-02 | FABRICATION | SATAIR | 453 | 28019477 | NON-SPARES | 10 | 3 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990010 => LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-08 | 100% | NA | NA | 5.556% |  |  | 2019-06-19 | 2019-11-06 | Sous-poste | Sous-poste | 2019-06-25 | 2019-11-11 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 45 | 11 | 2019 | 0.615 | 4.1376 | 0.3448 | 4.4824 | COL | 0 | 0
2822091010 | 2019-07-17 | FABRICATION | SATAIR | 119 | 28220910 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 26814 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-09 | 100% | NA | NA | 5.556% |  |  | 2019-07-18 | 2019-11-07 | Sous-poste | Sous-poste | 2019-07-23 | 2019-11-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2822091011 | 2019-07-17 | FABRICATION | SATAIR | 119 | 28220910 | NON-SPARES | 11 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-18 | 2019-11-07 | Sous-poste | Sous-poste | 2019-07-23 | 2019-11-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2822091012 | 2019-07-17 | FABRICATION | SATAIR | 119 | 28220910 | NON-SPARES | 12 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-18 | 2019-11-07 | Sous-poste | Sous-poste | 2019-07-23 | 2019-11-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2822091010 | 2019-07-17 | FABRICATION | SATAIR | 119 | 28220910 | NON-SPARES | 10 | 1 | RTN | D9550011900195 | 0 | NON PRESENT INDUS | 26814 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-09 | 100% | NA | NA | 5.556% |  |  | 2019-07-18 | 2019-11-07 | Sous-poste | Sous-poste | 2019-07-23 | 2019-11-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
490003892910 | 2019-07-16 | FABRICATION | STELIA | FAISCEAU | 4900038929 | NON-SPARES | 10 | 19 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-28 | 2019-11-07 | Sous-poste | Sous-poste | 2019-09-02 | 2019-11-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 45 | 11 | 2019 | 4.75 | 9.5 | 0.05 | 9.55 | NA | 0 | 0
2824182210 | 2019-08-06 | HA/REVENTE | SATAIR | TUBE | 28241822 | NON-SPARES | 10 | 2 | RTN | F9251110800100 | 1STR*10656 | NA | 27631 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-08 | NA | 100% | 2019-11-06 | 100% | NA | NA | 100% |  |  | 2019-10-29 | 2019-11-07 | Sous-poste | Sous-poste | 2019-11-02 | 2019-11-12 | 2019-11-12 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 45 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2821301010 | 2019-07-10 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28213010 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 26586 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-13 | NA | 100% | 2019-11-08 | 100% | NA | NA | 100% |  |  | 2019-11-12 | 2019-11-12 | Sous-poste | Sous-poste | 2019-11-15 | 2019-11-15 | 2019-11-15 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 46 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2807413010 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28074130 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990111 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-12 | 100% | NA | NA | 5.556% |  |  | 2019-09-11 | 2019-11-13 | Sous-poste | Sous-poste | 2019-09-16 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807413110 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28074131 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990112 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-12 | 100% | NA | NA | 5.556% |  |  | 2019-09-11 | 2019-11-13 | Sous-poste | Sous-poste | 2019-09-16 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2808066610 | 2019-02-28 | FABRICATION | SATAIR | 117 | 28080666 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22398 | LTE990115 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-12 | 100% | NA | NA | 5.556% |  |  | 2019-09-12 | 2019-11-13 | Sous-poste | Sous-poste | 2019-09-17 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807359710 | 2019-02-21 | FABRICATION | SATAIR | 117 | 28073597 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 22171 | LTE990109 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-13 | 100% | NA | NA | 5.556% |  |  | 2019-09-13 | 2019-11-13 | Sous-poste | Sous-poste | 2019-09-18 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2807535930 | 2019-02-22 | FABRICATION | SATAIR | 453 | 28075359 | NON-SPARES | 30 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-22 | 2019-11-13 | Sous-poste | Sous-poste | 2019-10-25 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
490003919110 | 2019-08-22 | FABRICATION | STELIA | CÂBLE | 4900039191 | NON-SPARES | 10 | 3 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 420540-1 => 420540-3 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2019-09-23 | 100% | NA | NA | 5.556% |  |  | 2019-10-02 | 2019-11-13 | Sous-poste | Sous-poste | 2019-10-07 | 2019-11-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 46 | 11 | 2019 | 0.615 | 3 | 0.1 | 3.1 | NA | 0 | 0
27908564 2796146010 | 2018-09-10 | FABRICATION | SATAIR | 108 | 27908564 27961460 | NON-SPARES | 10 | 1 | EXP | D9550010800996 | IS0032069M | NON PRESENT INDUS | 16901 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2018-11-28 | 2019-11-14 | Sous-poste | Sous-poste | 2018-12-01 | 2019-11-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 46 | 11 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2796145410 | 2018-11-10 | FABRICATION | SATAIR | 108 | 27961454 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-04 | 100% | NA | NA | 5.556% |  |  | 2019-02-05 | 2019-11-14 | Sous-poste | Sous-poste | 2019-02-08 | 2019-11-19 |  |  | Allemagne | Bloqué BE client | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 46 | 11 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2796145410 | 2018-11-10 | FABRICATION | SATAIR | 108 | 27961454 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-03-04 | 100% | NA | NA | 5.556% |  |  | 2019-02-05 | 2019-11-14 | Sous-poste | Sous-poste | 2019-02-08 | 2019-11-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2018 | 46 | 11 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2807662332 | 2019-02-25 | FABRICATION | SATAIR | 117 | 28076623 | NON-SPARES | 32 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-01 | 2019-11-14 | Sous-poste | Sous-poste | 2019-10-04 | 2019-11-19 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 46 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2832849720 | 2019-11-13 | HA/REVENTE | SATAIR | CONNECTOR | 28328497 | NON-SPARES | 20 | 1 | AOG | EN3645M0HN54AA | 1CON*24527 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-15 | NA | 100% | 2019-11-13 | 100% | NA | NA | 100% |  |  | 2019-11-15 | 2019-11-15 | Sous-poste | Sous-poste | 2019-11-19 | 2019-11-19 | 2019-11-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 46 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2825332710 | 2019-08-19 | HA/REVENTE | SATAIR | PLATE ASSY | 28253327 | NON-SPARES | 10 | 1 | AOG | F9251485300000 | 1STR*01521 | NA | 27625 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-18 | NA | 100% | 2019-11-13 | 100% | NA | NA | 100% |  |  | 2020-02-21 | 2019-11-15 | Sous-poste | Sous-poste | 2020-02-26 | 2019-11-19 | 2019-11-19 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 46 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003961710 | 2014-01-01 | HA/REVENTE | STELIA | BRACKET | 4900039617 | NON-SPARES | 10 | 1 | RTN | S9251481920000 | À faire | NA | 29840 | 0 | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | TBD | 100% | NA | NA | 100% |  |  | 2019-11-15 | 2019-11-15 | Sous-poste | Sous-poste | 2019-11-20 | 2019-11-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 46 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003939670 | 2014-01-01 | HA/REVENTE | STELIA | SUPPORT | 4900039396 | NON-SPARES | 70 | 1 | EXP | S9251594420000 | 1STR*10668 | NA | 28606 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-22 | NA | 100% | 2019-11-21 | 100% | NA | NA | 100% |  |  | 2019-10-04 | 2019-11-22 | Sous-poste | Sous-poste | 2019-10-09 | 2019-11-27 | 2019-11-27 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 47 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003939680 | 2014-01-01 | HA/REVENTE | STELIA | PRISE SUP 82 VU | 4900039396 | NON-SPARES | 80 | 1 | EXP | S9251596820000 | 1STR*10666 | NA | 28606 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-11-22 | NA | 100% | 2019-11-21 | 100% | NA | NA | 100% |  |  | 2019-10-04 | 2019-11-22 | Sous-poste | Sous-poste | 2019-10-09 | 2019-11-27 | 2019-11-27 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 47 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2831661852 | 2019-10-29 | FABRICATION | SATAIR | CONDUIT | 28316618 | NON-SPARES | 52 | 1 | EXP | F9249262600800 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-11-25 | 2019-11-25 | Sous-poste | Sous-poste | 2019-11-28 | 2019-11-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 48 | 11 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2822399110 | 2019-07-18 | FABRICATION | SATAIR | 510 | 28223991 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 26927 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-09 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2019-11-26 | Sous-poste | Sous-poste | 2019-10-16 | 2019-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 48 | 11 | 2019 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2822399110 | 2019-07-18 | FABRICATION | SATAIR | 510 | 28223991 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 26927 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-09-09 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2019-11-26 | Sous-poste | Sous-poste | 2019-10-16 | 2019-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 48 | 11 | 2019 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2820619260 | 2019-07-17 | FABRICATION | SATAIR | 510 | 28206192 | NON-SPARES | 60 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-12 | 2019-11-26 | Sous-poste | Sous-poste | 2019-07-18 | 2019-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 48 | 11 | 2019 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2820619261 | 2019-07-17 | FABRICATION | SATAIR | 510 | 28206192 | NON-SPARES | 61 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-12 | 2019-11-26 | Sous-poste | Sous-poste | 2019-07-18 | 2019-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 48 | 11 | 2019 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
490003867310 | 2019-06-21 | FABRICATION | STELIA | 34 | 4900038673 | NON-SPARES | 10 | 1 | EXP | S9550003445795 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-29 | 2019-11-26 | Sous-poste | Sous-poste | 2019-08-01 | 2019-11-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 48 | 11 | 2019 | 0.205 | 4.1225 | 1.0306 | 5.1531 | COL | 0 | 0
2816997410 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990122 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997410 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990122 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997420 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 20 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990132 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997420 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 20 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990132 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997410 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990122 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997411 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990123 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997412 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990124 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne | Voir LSE pour justifier retard | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997413 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 13 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990125 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997414 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 14 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990126 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997415 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 15 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990127 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997416 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 16 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990128 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997417 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 17 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990129 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997418 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 18 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990130 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997419 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 19 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990131 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997420 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 20 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990132 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997421 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 21 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990133 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2816997422 | 2019-05-27 | FABRICATION | SATAIR | 117 | 28169974 | NON-SPARES | 22 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 25299 | LTE990134 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-10-23 | 100% | NA | NA | 5.556% |  |  | 2019-11-12 | 2019-11-27 | Sous-poste | Sous-poste | 2019-11-15 | 2019-12-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 | 48 | 11 | 2019 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
490003960023 | 2019-10-22 | FABRICATION | STELIA | CÂBLE | 4900039600 | NON-SPARES | 23 | 4 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-11-13 | 2019-11-28 | Sous-poste | Sous-poste | 2019-11-18 | 2019-12-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 48 | 11 | 2019 | 0.82 | 4 | 0.1 | 4.1 | NA | 0 | 0
2760454710 | 2017-11-14 | HA/REVENTE | SATAIR | DIAPHRAGME | 27604547 | NON-SPARES | 10 | 8 | EXP | V9251111521200 | 1STR*10663 | NA | 28257 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-02 | NA | 100% | 2019-12-02 | 100% | NA | NA | 100% |  |  | 2017-12-11 | 2019-12-02 | Sous-poste | Sous-poste | 2017-12-14 | 2019-12-05 | 2019-12-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2017 | 49 | 12 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490003923524 | 2019-09-04 | FABRICATION | STELIA | CÂBLE | 4900039235 | NON-SPARES | 24 | 2 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-11-21 | 2019-12-02 | Sous-poste | Sous-poste | 2019-11-26 | 2019-12-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 49 | 12 | 2019 | 0.41 | 2 | 0.1 | 2.1 | NA | 0 | 0
2823911726 | 2019-08-02 | FABRICATION | SATAIR | 518 | 28239117 | NON-SPARES | 26 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-07 | 2019-12-04 | Sous-poste | Sous-poste | 2019-08-13 | 2019-12-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 49 | 12 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2823263910 | 2019-08-27 | FABRICATION | SATAIR | 518 | 28232639 | NON-SPARES | 10 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 27648 27646 | LTE990007 |  |  |  | 0% | 0% | 0% | 100% | 0 | 100% | 100% | 2019-10-09 | 100% | NA | NA | 5.556% |  |  | 2019-10-21 | 2019-12-04 | Sous-poste | Sous-poste | 2019-10-24 | 2019-12-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 49 | 12 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2823263910 | 2019-08-27 | FABRICATION | SATAIR | 518 | 28232639 | NON-SPARES | 10 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 27648 27646 | LTE990007 |  |  |  | 0% | 0% | 0% | 100% | 0 | 100% | 100% | 2019-10-09 | 100% | NA | NA | 5.556% |  |  | 2019-10-21 | 2019-12-04 | Sous-poste | Sous-poste | 2019-10-25 | 2019-12-08 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 49 | 12 | 2019 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
490003935331 | 2019-09-26 | FABRICATION | STELIA | FAISCEAU | 4900039353 | NON-SPARES | 31 | 7 | RTN | S9110157200196 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-11-11 | 2019-12-04 | Sous-poste | Sous-poste | 2019-11-14 | 2019-12-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 49 | 12 | 2019 | 1.435 | 4.9 | 0.07 | 4.97 | NA | 0 | 0
2820470040 | 2019-09-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28204700 | NON-SPARES | 40 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 26335 | 383221-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-09-16 | 100% | 100% | 2019-10-07 | 100% | NA | NA | 5.556% |  |  | 2019-12-04 | 2019-12-04 | Sous-poste | Sous-poste | 2019-12-09 | 2019-12-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 49 | 12 | 2019 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2832911910 | 2019-11-14 | HA/REVENTE | SATAIR | CONNECTOR | 28329119 | NON-SPARES | 10 | 1 | AOG | EN3645M0HN54AA | 1CON*24527 | NA | 30384 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-10 | NA | 100% | 2019-12-06 | 100% | NA | NA | 100% |  |  | 2019-12-18 | 2019-12-09 | Sous-poste | Sous-poste | 2019-12-20 | 2019-12-11 | 2019-12-11 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 50 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2792645120 | 2018-10-03 | FABRICATION | SATAIR | 108 | 27926451 | NON-SPARES | 20 | 1 | EXP | D9550010800996 | IS0032069M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2018-10-30 | 2019-12-09 | Sous-poste | Sous-poste | 2018-11-02 | 2019-12-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2018 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2796145210 | 2019-07-17 | FABRICATION | SATAIR | 108 | 27961452 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-30 | 2019-12-09 | Sous-poste | Sous-poste | 2019-02-03 | 2019-12-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2796145210 | 2019-07-17 | FABRICATION | SATAIR | 108 | 27961452 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-30 | 2019-12-09 | Sous-poste | Sous-poste | 2019-02-04 | 2019-12-12 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2823990910 | 2019-08-05 | HA/REVENTE | SATAIR/AIS | ANGLE | 28239909 | NON-SPARES | 10 | 52 | RTN | F9251445920000 | 1STR*01520 | NA | 27624 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-10 | NA | 100% | 2019-11-25 | 100% | NA | NA | 100% |  |  | 2020-02-26 | 2019-12-10 | Sous-poste | Sous-poste | 2020-03-02 | 2019-12-13 | 2019-12-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 50 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2820355610 | 2019-07-01 | FABRICATION | SATAIR | 108 | 28203556 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 26355 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-09-25 | 2019-12-12 | Sous-poste | Sous-poste | 2019-09-29 | 2019-12-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2822091110 | 2019-07-17 | FABRICATION | SATAIR | 108 | 28220911 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 26355 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-09 | 2019-12-12 | Sous-poste | Sous-poste | 2019-10-14 | 2019-12-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2822091120 | 2019-07-17 | FABRICATION | SATAIR | 108 | 28220911 | NON-SPARES | 20 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 26355 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-09 | 2019-12-12 | Sous-poste | Sous-poste | 2019-10-14 | 2019-12-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 50 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
490003951910 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 10 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951910 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 10 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951910 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 10 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951920 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 20 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449288-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951920 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 20 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449288-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951921 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 21 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449290-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951922 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 22 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449292-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951923 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 23 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449294-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003951924 | 2019-10-11 | FABRICATION | STELIA | FAISCEAU | 4900039519 | NON-SPARES | 24 | 1 | RTN | S9110302500195 | 0 | NON PRESENT INDUS | 29349 | 449296-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-10-30 | 2019-12-13 | Sous-poste | Sous-poste | 2019-11-04 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.25 | 0.5 | 0.05 | 0.55 | NA | 0 | 0
490003957226 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 26 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | 464428-1 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003957227 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 27 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | 464426-1 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003957228 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 28 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | 464424-1 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003957220 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | 464422-1 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003957210 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464418-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003957211 | 2019-10-14 | FABRICATION | STELIA | CABLE COAXIAL | 4900039572 | NON-SPARES | 11 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464420-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-12 | 100% | NA | NA | 5.556% |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 50 | 12 | 2019 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
2828169910 | 2019-09-18 | HA/REVENTE | SATAIR | PLATE ASSY | 28281699 | NON-SPARES | 10 | 70 | RTN | D9251101900000 | 1STR*11007 | NA | 28445 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-13 | NA | 100% | 2019-12-02 | 100% | NA | NA | 100% |  |  | 2019-12-13 | 2019-12-13 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-18 | 2019-12-18 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 50 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2831142812 | 2019-10-22 | FABRICATION | SATAIR | 27 | 28311428 | NON-SPARES | 12 | 1 | AOG | D9551002700195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-12-16 | Sous-poste | Sous-poste | 2019-11-01 | 2019-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 51 | 12 | 2019 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2831142813 | 2019-10-22 | FABRICATION | SATAIR | 27 | 28311428 | NON-SPARES | 13 | 1 | AOG | D9551002700195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-30 | 2019-12-16 | Sous-poste | Sous-poste | 2019-11-01 | 2019-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 51 | 12 | 2019 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2831143014 | 2019-10-22 | FABRICATION | SATAIR | 119 | 28311430 | NON-SPARES | 14 | 1 | AOG | D9551011900195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-10-29 | 2019-12-16 | Sous-poste | Sous-poste | 2020-11-01 | 2019-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 51 | 12 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2831143015 | 2019-10-22 | FABRICATION | SATAIR | 119 | 28311430 | NON-SPARES | 15 | 1 | AOG | D9551011900195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-10-29 | 2019-12-16 | Sous-poste | Sous-poste | 2020-11-01 | 2019-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 51 | 12 | 2019 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2836079410 | 2019-12-18 | FABRICATION | SATAIR | CONDUIT ASSY | 28360794 | NON-SPARES | 10 | 1 | AOG | F9249263300100 | 0 | NON PRESENT INDUS | 0 | 0 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-12-17 | 2019-12-16 | Sous-poste | Sous-poste | 2019-12-19 | 2019-12-18 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 51 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2823990410 | 2019-08-05 | HA/REVENTE | SATAIR | TUBE | 28239904 | NON-SPARES | 10 | 34 | RTN | F9251110800500 | 1STR*00297 | NA | 27623 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-18 | NA | 100% | 2019-11-25 | 100% | NA | NA | 100% |  |  | 2020-02-26 | 2019-12-16 | Sous-poste | Sous-poste | 2020-03-02 | 2019-12-19 | 2019-12-19 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 51 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2819474210 | 2019-06-21 | FABRICATION | SATAIR | 453 | 28194742 | NON-SPARES | 10 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 26132 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-27 | 100% | NA | NA | 5.556% |  |  | 2019-12-17 | 2019-12-17 | Sous-poste | Sous-poste | 2019-12-20 | 2019-12-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 51 | 12 | 2019 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
2834410411 | 2019-11-29 | FABRICATION | SATAIR | 317 | 28344104 | NON-SPARES | 11 | 1 | CRIT | WF408AEAAAAC | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-02 | 2019-12-18 | Sous-poste | Sous-poste | 2019-12-04 | 2019-12-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 51 | 12 | 2019 | 0 | 3.255 | 0.81375 | 4.0687 | COL | 0 | 0
2832391910 | 2019-11-08 | FABRICATION | SATAIR | 22 | 28323919 | NON-SPARES | 10 | 1 | CRIT | D9551002201195 | 0 | NON PRESENT INDUS | 30181 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-25 | 100% | NA | NA | 5.556% |  |  | 2019-12-18 | 2019-12-18 | Sous-poste | Sous-poste | 2019-12-20 | 2019-12-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 51 | 12 | 2019 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2832347010 | 2019-11-07 | FABRICATION | SATAIR | 314 | 28323470 | NON-SPARES | 10 | 1 | CRIT | WF407ABAAAAB | 0 | NON PRESENT INDUS | 30335 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-12-10 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2019-12-18 | Sous-poste | Sous-poste | 2020-02-05 | 2019-12-20 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 51 | 12 | 2019 | 0.51 | 3.8675 | 0.96688 | 4.8344 | COL | 0 | 0
2832911910 | 2019-11-14 | HA/REVENTE | SATAIR | CONNECTOR | 28329119 | NON-SPARES | 10 | 8 | AOG | EN3645M0HN54AA | 1CON*24527 | NA | 30384 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-10 | NA | 100% | 2019-12-06 | 100% | NA | NA | 100% |  |  | 2019-11-27 | 2019-12-18 | Sous-poste | Sous-poste | 2019-11-29 | 2019-12-20 | 2019-12-20 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 51 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2835642110 | 2019-12-13 | HA/REVENTE | SATAIR | FLANGE ASSY | 28356421 | NON-SPARES | 10 | 2 | AOG | D9251127600000 | IS0008826S | NA | 31455 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-19 | NA | 100% | 2019-12-13 | 100% | NA | NA | 100% |  |  | 2019-12-11 | 2019-12-18 | Sous-poste | Sous-poste | 2019-12-13 | 2019-12-20 | 2019-12-20 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 51 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003964210 | 2014-01-01 | HA/REVENTE | STELIA | PLATINE ÉQUIPÉE | 4900039642 | NON-SPARES | 10 | 3 | RTN | S9252318000000 | 1STR*02063 | NA | 29857 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-18 | NA | 100% | 2019-12-16 | 100% | NA | NA | 100% |  |  | 2019-11-15 | 2019-12-18 | Sous-poste | Sous-poste | 2019-11-20 | 2019-12-23 | 2019-12-23 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 51 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2801947810 | 2019-01-02 | FABRICATION | SATAIR | 453 | 28019478 | NON-SPARES | 10 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-08 | 100% | NA | NA | 5.556% |  |  | 2019-07-17 | 2019-12-19 | Sous-poste | Sous-poste | 2019-07-23 | 2019-12-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 51 | 12 | 2019 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
2828532211 | 2019-09-20 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28285322 | NON-SPARES | 11 | 1 | RTN | A27912401006C11 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-13 | 2019-12-19 | Sous-poste | Sous-poste | 2019-12-18 | 2019-12-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 51 | 12 | 2019 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2826774710 | 2019-09-03 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28267747 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 27947 | 423706-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-15 | 100% | NA | NA | 5.556% |  |  | 2019-12-17 | 2019-12-19 | Sous-poste | Sous-poste | 2019-12-20 | 2019-12-24 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 51 | 12 | 2019 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2796145210 | 2019-07-17 | FABRICATION | SATAIR | 108 | 27961452 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-30 | 2019-12-23 | Sous-poste | Sous-poste | 2019-02-04 | 2019-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 52 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2822109610 | 2019-07-17 | FABRICATION | SATAIR | 108 | 28221096 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 22405 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2019-12-23 | Sous-poste | Sous-poste | 2019-10-16 | 2019-12-26 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 52 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2826832210 | 2019-09-04 | FABRICATION | SATAIR | 60 | 28268322 | NON-SPARES | 10 | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | 27959 | LTE990022 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-14 | 100% | NA | NA | 5.556% |  |  | 2019-09-18 | 2019-12-24 | Sous-poste | Sous-poste | 2019-09-20 | 2019-12-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 52 | 12 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2826839430 | 2019-09-04 | FABRICATION | SATAIR | 62 | 28268394 | NON-SPARES | 30 | 1 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-09-18 | 2019-12-24 | Sous-poste | Sous-poste | 2019-09-20 | 2019-12-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 52 | 12 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2826839910 | 2019-09-04 | FABRICATION | SATAIR | 62 | 28268399 | NON-SPARES | 10 | 1 | AOG | D9551006200295 | 0 | NON PRESENT INDUS | 27959 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-14 | 100% | NA | NA | 5.556% |  |  | 2019-09-18 | 2019-12-24 | Sous-poste | Sous-poste | 2019-09-20 | 2019-12-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 52 | 12 | 2019 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2826776710 | 2019-09-03 | FABRICATION | SATAIR | 60 | 28267767 | NON-SPARES | 10 | 1 | AOG | D9551006000295 | 0 | NON PRESENT INDUS | 27959 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-09 | 100% | NA | NA | 5.556% |  |  | 2019-09-26 | 2019-12-24 | Sous-poste | Sous-poste | 2019-09-30 | 2019-12-26 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 52 | 12 | 2019 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2823990610 | 2019-08-05 | HA/REVENTE | SATAIR | PLATE ASSY | 28239906 | NON-SPARES | 10 | 26 | RTN | F9251485300000 | 1STR*01521 | NA | 27625 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-20 | NA | 100% | 2019-12-12 | 100% | NA | NA | 100% |  |  | 2020-02-26 | 2019-12-24 | Sous-poste | Sous-poste | 2020-03-02 | 2019-12-27 | 2019-12-27 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 52 | 12 | 2019 | 0 | 0 | 0 | 0 | NA | 0 | 0
2837094710 | 2019-12-27 | FABRICATION | SATAIR | 313 | 28370947 | NON-SPARES | 10 | 1 | AOG | WF406ACAAAAB | IS0032177M | NON PRESENT INDUS | 0 | LTE990001 |  |  |  | 100% | 0% | 50% | 0% | 0 | NA | 0% | TBD | 100% | NA | NA | 5.556% |  |  | 2019-12-26 | 2019-12-26 | Sous-poste | Sous-poste | 2019-12-28 | 2019-12-28 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 52 | 12 | 2019 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
2829496710 | 2019-10-04 | FABRICATION | SATAIR | 108 | 28294967 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 29059 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-11-30 | 100% | NA | NA | 5.556% |  |  | 2019-12-30 | 2019-12-30 | Sous-poste | Sous-poste | 2020-01-02 | 2020-01-02 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 53 | 12 | 2019 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2796145220 | 2019-07-17 | FABRICATION | SATAIR | 108 | 27961452 | NON-SPARES | 20 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 18818 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-01-30 | 2020-01-06 | Sous-poste | Sous-poste | 2019-02-04 | 2020-01-09 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 2 | 1 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2823990410 | 2019-08-05 | HA/REVENTE | SATAIR | TUBE | 28239904 | NON-SPARES | 10 | 1 | RTN | F9251110800500 | 1STR*00297 | NA | 27623 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2019-12-18 | NA | 100% | 2019-11-25 | 100% | NA | NA | 100% |  |  | 2020-02-26 | 2020-01-06 | Sous-poste | Sous-poste | 2020-03-01 | 2020-01-09 | 2020-01-09 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 2 | 1 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2822109610 | 2019-07-17 | FABRICATION | SATAIR | 108 | 28221096 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 22405 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2020-01-13 | Sous-poste | Sous-poste | 2019-10-16 | 2020-01-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 3 | 1 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2822109610 | 2019-07-17 | FABRICATION | SATAIR | 108 | 28221096 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 22405 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-31 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2020-01-13 | Sous-poste | Sous-poste | 2019-10-16 | 2020-01-16 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 3 | 1 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2834778910 | 2019-12-04 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28347789 | NON-SPARES | 10 | 4 | CRIT | D9251805700000 | IS0032776S | NA | 31120 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-01-27 | NA | 100% | 2020-01-24 | 100% | NA | NA | 100% |  |  | 2019-12-11 | 2020-01-14 | Sous-poste | Sous-poste | 2019-12-13 | 2020-01-16 | 2020-01-16 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 3 | 1 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003958110 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464430-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-12-09 | 100% | NA | NA | 5.556% |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003958120 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003958130 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 30 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003958110 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464430-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-12-09 | 100% | NA | NA | 5.556% |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003958110 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464430-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-12-09 | 100% | NA | NA | 5.556% |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490003958111 | 2019-11-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900039581 | NON-SPARES | 11 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 29483 | 464432-1 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-12-09 | 100% | NA | NA | 5.556% |  |  | 2020-01-06 | 2020-01-14 | Sous-poste | Sous-poste | 2020-01-09 | 2020-01-17 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 3 | 1 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004023110 | 2020-01-15 | HA/REVENTE | STELIA | BARRE | 4900040231 | NON-SPARES | 10 | 1 | AOG | S9251302420100 | 1QEL*00019 | NA | N/A | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-01-16 | NA | 100% | 2020-01-14 | 100% | NA | NA | 100% |  |  | 2020-01-15 | 2020-01-15 | Sous-poste | Sous-poste | 2020-01-17 | 2020-01-17 | 2020-01-17 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 3 | 1 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2808066712 | 2019-02-28 | FABRICATION | SATAIR | 117 | 28080667 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-02 | 2020-01-15 | Sous-poste | Sous-poste | 2019-10-07 | 2020-01-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 3 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2828169713 | 2019-09-18 | FABRICATION | SATAIR | WIRE-BONDING | 28281697 | NON-SPARES | 13 | 2 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-15 | 2020-01-15 | Sous-poste | Sous-poste | 2020-01-20 | 2020-01-20 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 3 | 1 | 2020 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2831610510 | 2019-10-29 | FABRICATION | SATAIR | 45 | 28316105 | NON-SPARES | 10 | 1 | CRIT | D9551004500595 | 0 | NON PRESENT INDUS | 30080 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-12-20 | 100% | NA | NA | 5.556% |  |  | 2020-01-22 | 2020-01-22 | Sous-poste | Sous-poste | 2020-01-24 | 2020-01-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 4 | 1 | 2020 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
2834354910 | 2019-11-28 | FABRICATION | SATAIR | 27 | 28343549 | NON-SPARES | 10 | 1 | AOG | D9551002700795 | 0 | NON PRESENT INDUS | 31031 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2020-01-10 | 100% | NA | NA | 5.556% |  |  | 2019-12-09 | 2020-01-22 | Sous-poste | Sous-poste | 2019-12-11 | 2020-01-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 4 | 1 | 2020 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
283435491 | 2019-11-28 | FABRICATION | SATAIR | 27 | 28343549 | NON-SPARES | 1 | 1 | AOG | D9551002700795 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-09 | 2020-01-22 | Sous-poste | Sous-poste | 2019-12-11 | 2020-01-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 4 | 1 | 2020 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
283435502 | 2019-11-28 | FABRICATION | SATAIR | 119 | 28343550 | NON-SPARES | 2 | 1 | AOG | D9551011900295 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-09 | 2020-01-22 | Sous-poste | Sous-poste | 2019-12-11 | 2020-01-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 4 | 1 | 2020 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2834355010 | 2019-11-28 | FABRICATION | SATAIR | 119 | 28343550 | NON-SPARES | 10 | 1 | AOG | D9551011900295 | 0 | NON PRESENT INDUS | 31031 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2020-01-10 | 100% | NA | NA | 5.556% |  |  | 2019-12-09 | 2020-01-22 | Sous-poste | Sous-poste | 2019-12-11 | 2020-01-24 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 4 | 1 | 2020 | 0.205 | 3.385 | 0.84625 | 4.2312 | COL | 0 | 0
2834415310 | 2019-11-29 | FABRICATION | SATAIR | 54 | 28344153 | NON-SPARES | 10 | 1 | AOG | D9551005400195 | IS0032110M | NON PRESENT INDUS | 31086 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2020-01-15 | 100% | NA | NA | 5.556% |  |  | 2019-11-29 | 2020-01-22 | Sous-poste | Sous-poste | 2019-12-03 | 2020-01-24 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 4 | 1 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2809883221 | 2019-03-14 | FABRICATION | SATAIR | 117 | 28098832 | NON-SPARES | 21 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-09 | 2020-01-23 | Sous-poste | Sous-poste | 2019-10-14 | 2020-01-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 4 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2812312710 | 2019-04-10 | FABRICATION | SATAIR | 117 | 28123127 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 23839 | LTE990120 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-09-16 | 100% | NA | NA | 5.556% |  |  | 2019-10-10 | 2020-01-23 | Sous-poste | Sous-poste | 2019-10-16 | 2020-01-28 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 4 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2801947811 |  | FABRICATION | SATAIR | 453 | 28019478 | NON-SPARES | 11 | 2 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-07-17 | 2020-01-23 | Sous-poste | Sous-poste | 2019-07-23 | 2020-01-28 |  |  | Allemagne | Report non communiqué LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 4 | 1 | 2020 | 0.41 | 2.7584 | 0.3448 | 3.1032 | COL | 0 | 0
2836317910 | 2019-12-18 | FABRICATION | SATAIR | 518 | 28363179 | NON-SPARES | 10 | 1 | CRIT | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 31345 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2020-01-22 | 100% | NA | NA | 5.556% |  |  | 2019-12-18 | 2020-01-24 | Sous-poste | Sous-poste | 2019-12-20 | 2020-01-28 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 4 | 1 | 2020 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2834778910 | 2019-12-04 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28347789 | NON-SPARES | 10 | 1 | CRIT | D9251805700000 | IS0032776S | NA | 31120 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-01-27 | NA | 100% | 2020-01-24 | 100% | NA | NA | 100% |  |  | 2019-12-11 | 2020-01-24 | Sous-poste | Sous-poste | 2019-12-13 | 2020-01-28 | 2020-01-28 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 4 | 1 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2801947910 |  | FABRICATION | SATAIR | 453 | 28019479 | NON-SPARES | 10 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | 20452 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-08-08 | 100% | NA | NA | 5.556% |  |  | 2019-08-20 | 2020-01-24 | Sous-poste | Sous-poste | 2019-08-24 | 2020-01-29 |  |  | Allemagne | Report non communiqué LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 4 | 1 | 2020 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
2801947911 | 2019-01-02 | FABRICATION | SATAIR | 453 | 28019479 | NON-SPARES | 11 | 1 | RTN | D9551045300195 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-08-20 | 2020-01-24 | Sous-poste | Sous-poste | 2019-08-24 | 2020-01-29 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 | 4 | 1 | 2020 | 0.205 | 1.3792 | 0.3448 | 1.724 | COL | 0 | 0
2822350410 | 2019-07-18 | HA/REVENTE | SATAIR | COVER ASSY | 28223504 | NON-SPARES | 10 | 2 | RTN | A9252597000900 | 1STR*01482 | NA | 26898 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-01-27 | NA | 100% | 2020-01-24 | 100% | NA | NA | 100% |  |  | 2019-10-11 | 2020-01-27 | Sous-poste | Sous-poste | 2019-10-16 | 2020-01-30 | 2020-01-30 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 5 | 1 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003960710 | 2019-10-24 | FABRICATION | STELIA | 34 | 4900039607 | NON-SPARES | 10 | 1 | AOG | S9550003494095 | IS0032230M | NON PRESENT INDUS | #N/A | LTE990001 |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-12-19 | 2020-01-29 | Sous-poste | Sous-poste | 2019-12-23 | 2020-01-31 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 5 | 1 | 2020 | 0.205 | 4.1225 | 1.0306 | 5.1531 | COL | 0 | 0
490003968518 | 2019-11-13 | FABRICATION | STELIA | CÂBLE | 4900039685 | NON-SPARES | 18 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-09 | 2020-01-29 | Sous-poste | Sous-poste | 2020-01-14 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 5 | 1 | 2020 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490003968519 | 2019-11-13 | FABRICATION | STELIA | CÂBLE | 4900039685 | NON-SPARES | 19 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-09 | 2020-01-29 | Sous-poste | Sous-poste | 2020-01-14 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 5 | 1 | 2020 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490003968520 | 2019-11-13 | FABRICATION | STELIA | CÂBLE | 4900039685 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-09 | 2020-01-29 | Sous-poste | Sous-poste | 2020-01-14 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 5 | 1 | 2020 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2826519810 | 2019-08-30 | FABRICATION | SATAIR | WIRE-BONDING | 28265198 | NON-SPARES | 10 | 2 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | NA | 423372-1 => 423372-2 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2020-09-06 | 100% | NA | NA | 5.556% |  |  | 2020-02-11 | 2020-01-29 | Sous-poste | Sous-poste | 2020-02-15 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2826520020 | 2019-08-30 | FABRICATION | SATAIR | WIRE-BONDING | 28265200 | NON-SPARES | 20 | 1 | RTN | F0003008100200 | IS0032147M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-02-11 | 2020-01-29 | Sous-poste | Sous-poste | 2020-02-15 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.2085 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2826520210 | 2019-08-30 | FABRICATION | SATAIR | LEAD-BONDING | 28265202 | NON-SPARES | 10 | 1 | RTN | F0003008100300 | IS0032149M | NON PRESENT INDUS | NA | 423378-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2020-09-06 | 100% | NA | NA | 5.556% |  |  | 2020-02-11 | 2020-01-29 | Sous-poste | Sous-poste | 2020-02-15 | 2020-02-03 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.2075 | 0.2383 | 0.059575 | 0.29788 | NA | 0 | 0
2839321010 | 2020-01-23 | FABRICATION | SATAIR | PLACARD | 28393210 | NON-SPARES | 10 | 1 | CRIT | D5211034722900 | 0 | NON PRESENT INDUS | N/A | 496647-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2020-01-28 | 100% | NA | NA | 5.556% |  |  | TBD | 2020-01-30 | Sous-poste | Sous-poste |  | 2020-02-02 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 5 | 1 | 2020 | 0.205 | 0 | 0 | 0 | NA | 0 | 0
2839320810 | 2020-01-23 | FABRICATION | SATAIR | PLACARD | 28393208 | NON-SPARES | 10 | 1 | CRIT | D5211034722800 | 0 | NON PRESENT INDUS | N/A | 496648-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2020-01-28 | 100% | NA | NA | 5.556% |  |  | TBD | 2020-01-30 | Sous-poste | Sous-poste |  | 2020-02-02 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 5 | 1 | 2020 | 0.205 | 0 | 0 | 0 | NA | 0 | 0
490003980110 | 2019-11-26 | FABRICATION | STELIA | CÂBLE | 4900039801 | NON-SPARES | 10 | 3 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 484384-1 => 484384-3 |  |  |  | 0% | 0% | 0% | 100% | 2020-01-10 | NA | 100% | 2020-01-10 | 100% | NA | 1OUIOUI | 10.53% |  |  | 2020-01-30 | 2020-01-30 | Sous-poste | Sous-poste | 2020-02-04 | 2020-02-04 | 2020-02-11 |  | Allemagne | Retard non communiqué LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 5 | 1 | 2020 | 0.615 | 3 | 0.1 | 3.1 | NA | 0 | 0
2824116310 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990139 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116310 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990139 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116362 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 62 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116350 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 50 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116310 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990139 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116311 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990140 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116312 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990141 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116313 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 13 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990142 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116314 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 14 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990143 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116315 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 15 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990144 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116316 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 16 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990145 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824116317 | 2019-08-06 | FABRICATION | SATAIR | 117 | 28241163 | NON-SPARES | 17 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 27642 | LTE990146 |  |  |  | 100% | 0% | 50% | 100% | 0 | NA | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2020-01-01 | 2020-01-31 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-05 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 5 | 1 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2809756810 | 2019-03-13 | FABRICATION | SATAIR | 313 | 28097568 | NON-SPARES | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 22837 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 0 | 100% | 100% | 2019-10-30 | 100% | NA | NA | 5.556% |  |  | 2019-06-05 | 2020-02-03 | Sous-poste | Sous-poste | 2019-06-10 | 2020-02-06 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2019 | 6 | 2 | 2020 | 0.51 | 3.85 | 0.9625 | 4.8125 | COL | 0 | 0
2824070110 | 2019-08-06 | HA/REVENTE | SATAIR | PLATE ASSY | 28240701 | NON-SPARES | 10 | 32 | RTN | D9251101900000 | 1STR*11007 | NA | 27628 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-04 | NA | 100% | 2020-01-29 | 100% | NA | NA | 100% |  |  | 2019-10-30 | 2020-02-04 | Sous-poste | Sous-poste | 2019-11-04 | 2020-02-07 | 2020-02-07 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 6 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2837565710 | 2020-01-08 | FABRICATION | SATAIR | BUNDLE | 28375657 | NON-SPARES | 10 | 1 | RTN | V9253110000098 | 0 | NON PRESENT INDUS | N/A | 496444-1 |  |  |  | 0% | 0% | 0% | 100% | 0 | NA | 100% | 2020-01-23 | 100% | NA | NA | 5.556% |  |  | 2020-01-30 | 2020-02-06 | Sous-poste | Sous-poste | 2020-02-04 | 2020-02-11 | 2020-02-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 6 | 2 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
2837566012 | 2020-01-08 | FABRICATION | SATAIR | BUNDLE | 28375660 | NON-SPARES | 12 | 1 | RTN | V9253120000097 | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2020-01-30 | 2020-02-06 | Sous-poste | Sous-poste | 2020-02-04 | 2020-02-11 | 2020-02-05 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 6 | 2 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
2832156610 | 2019-11-06 | HA/REVENTE | SATAIR | PLATE ASSY | 28321566 | NON-SPARES | 10 | 30 | RTN | D9251101900000 | 1STR*11007 | NA | 30194 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-03 | NA | 100% | 2020-02-03 | 100% | NA | NA | 100% |  |  | 2020-02-10 | 2020-02-10 | Sous-poste | Sous-poste | 2020-02-13 | 2020-02-13 | 2020-02-13 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838950310 | 2020-01-20 | FABRICATION | SATAIR | 45 | 28389503 | NON-SPARES | 10 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | 32408 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-03 | NA | 100% | 2020-01-31 | 100% | NA | NA | 5.556% |  |  | 2020-01-22 | 2020-02-11 | Sous-poste | Sous-poste | 2020-01-24 | 2020-02-13 | 2020-02-13 |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 7 | 2 | 2020 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
2840844410 | 2020-02-07 | HA/REVENTE | SATAIR | PLUS-BLANKING | 28408444 | NON-SPARES | 10 | 6 | CRIT | ASNA267911 | 1ACC*00002 | NA | NA | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-12 | NA | 100% | 2020-02-12 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-14 | 2020-02-14 |  | OK | Allemagne | N°420108 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003990810 | 2014-01-01 | HA/REVENTE | SATAIR | COLONNETTE | 4900039908 | NON-SPARES | 10 | 6 | RTN | F0003057820200 | 3QME*00792 | NA | 31264 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-10 | NA | 100% | 2020-02-11 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-16 | 2020-02-16 |  |  | Allemagne | N°420066 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003992410 | 2014-01-01 | HA/REVENTE | STELIA | SPHERE | 4900039924 | NON-SPARES | 10 | 3 | RTN | S9251342320000 | 1STR*06202 | NA | 31264 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-10 | NA | 100% | 2020-02-11 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-16 | 2020-02-16 |  |  | Allemagne | N°420066 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003992210 | 2014-01-01 | HA/REVENTE | STELIA | BARRE | 4900039922 | NON-SPARES | 10 | 2 | RTN | S9251302520000 | 1QEL*10071 | NA | 31264 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-10 | NA | 100% | 2020-02-11 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-16 | 2020-02-16 |  |  | Allemagne | N°420066 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2014 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838854210 | 2020-01-17 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28388542 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 32335 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-11 | NA | 100% | 2020-02-12 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-16 | 2020-02-16 |  |  | Allemagne | N°420074 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838854710 | 2020-01-17 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28388547 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 32335 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-11 | NA | 100% | 2020-02-12 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-02-12 | Sous-poste | Sous-poste | 2020-02-16 | 2020-02-16 |  |  | Allemagne | N°420074 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490003961810 | 2019-10-25 | FABRICATION | STELIA | 63 | 4900039618 | NON-SPARES | 10 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 29970 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-20 | NA | 100% | 2020-01-20 | 100% | NA | 1OUIOUI | 10.53% |  |  | 2019-11-15 | 2020-02-13 | Sous-poste | Sous-poste | 2019-11-20 | 2020-02-18 | 2020-02-11 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 7 | 2 | 2020 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
2833373810 | 2019-11-18 | FABRICATION | STE | COVER ASSY | 28333738 | NON-SPARES | 10 | 1 | RTN | D9251074200200 | 0 | NON PRESENT INDUS | 30537 | 481813-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-21 | NA | 100% | 2020-01-21 | 100% | NA | NA | 5.556% |  |  | 2020-02-13 | 2020-02-13 | Sous-poste | Sous-poste | 2020-02-19 | 2020-02-19 | 2020-02-17 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 7 | 2 | 2020 | 0 | 0.0884 | 0.00884 | 0.09724 | NA | 0 | 0
2834779110 | 2019-12-04 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28347791 | NON-SPARES | 10 | 2 | RTN | D9251805700000 | IS0032776S | NA | 31120 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-17 | NA | 100% | 2020-02-17 | 100% | NA | NA | 100% |  |  | 2020-01-10 | 2020-02-14 | Sous-poste | Sous-poste | 2020-01-15 | 2020-02-19 | 2020-02-19 | OK | Allemagne | N°420074 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 7 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2824069910 | 2019-08-06 | HA/REVENTE | SATAIR | COVER ASSY | 28240699 | NON-SPARES | 10 | 4 | RTN | A9252597000900 | 1STR*01482 | NA | 27627 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-01 | NA | 100% | 2020-02-17 | 100% | NA | NA | 100% |  |  | 2019-10-30 | 2020-02-18 | Sous-poste | Sous-poste | 2019-11-04 | 2020-02-21 | 2020-02-19 | OK | Allemagne | N°420299 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 8 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2828169610 | 2019-09-18 | FABRICATION | SATAIR | PROTECTION CAP | 28281696 | NON-SPARES | 10 | 7 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 28441 | 435479-1 => 435479-7 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-04 | NA | 100% | 2020-02-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-15 | 2020-02-19 | Sous-poste | Sous-poste | 2020-01-20 | 2020-02-22 | 2020-02-19 | OK | Allemagne | Manque 1CON*01083 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 8 | 2 | 2020 | 0.0175 | 0.7826 | 0.01118 | 0.79378 | NA | 0 | 0
2835194110 | 2019-12-10 | FABRICATION | SATAIR | 620 | 28351941 | NON-SPARES | 10 | 1 | AOG | D9551062000195 | 0 | NON PRESENT INDUS | 31449 | LTE990001 |  |  |  | 100% | 0% | 50% | 83% | 2020-03-03 | NA | 83% | 2020-02-18 | 100% | NA | NA | 5.556% |  |  | 2020-01-03 | 2020-02-21 | Sous-poste | Sous-poste | 2020-01-07 | 2020-02-25 | 2020-02-24 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.205 | 1.4123 | 0.35308 | 1.7654 | COL | 0 | 0
2835222710 | 2019-12-10 | FABRICATION | SATAIR | 619 | 28352227 | NON-SPARES | 10 | 1 | AOG | D9551061900195 | 0 | NON PRESENT INDUS | 31449 | LTE990001 |  |  |  | 100% | 0% | 50% | 83% | 2020-03-03 | NA | 83% | 2020-02-18 | 100% | NA | NA | 5.556% |  |  | 2020-01-08 | 2020-02-21 | Sous-poste | Sous-poste | 2020-01-10 | 2020-02-25 | 2020-02-24 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.205 | 1.4105 | 0.35263 | 1.7631 | COL | 0 | 0
490004007510 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 10 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491014-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007511 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 11 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491016-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007512 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 12 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491018-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007513 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 13 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491020-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007514 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 14 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491022-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007515 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 15 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491024-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007516 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 16 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491026-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004007517 | 2019-12-13 | FABRICATION | STELIA | CABLE COAXIAL | 4900040075 | NON-SPARES | 17 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 31514 | 491028-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-24 | NA | 100% | 2020-01-24 | 100% | NA | OUI | 5.263% |  |  | 2020-02-21 | 2020-02-21 | Sous-poste | Sous-poste | 2020-02-26 | 2020-02-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 8 | 2 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
2839970410 | 2020-01-30 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28399704 | NON-SPARES | 10 | 2 | EXP | D9251490100000 | IS0032740S | NA | 32715 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-01 | NA | 100% | 2020-02-24 | 100% | NA | NA | 100% |  |  | 2020-02-25 | 2020-02-25 | Sous-poste | Sous-poste | 2020-02-28 | 2020-02-28 | 2020-02-26 | OK | Allemagne | N°420703 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 9 | 2 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2840446110 | 2020-02-04 | FABRICATION | SATAIR | BUNDLE | 28404461 | NON-SPARES | 10 | 1 | RTN | V9253110000098 | 0 | NON PRESENT INDUS | N/A | 500993-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-02-07 | NA | 100% | 2020-02-07 | 100% | NA | NA | 5.556% |  |  | 2020-02-24 | 2020-02-26 | Sous-poste | Sous-poste | 2020-02-27 | 2020-02-28 | 2020-02-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 9 | 2 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
2840446310 | 2020-02-04 | FABRICATION | SATAIR | BUNDLE | 28404463 | NON-SPARES | 10 | 1 | RTN | V9253120000097 | 0 | NON PRESENT INDUS | N/A | 500995-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-02-07 | NA | 100% | 2020-02-07 | 100% | NA | NA | 5.556% |  |  | 2020-02-24 | 2020-02-26 | Sous-poste | Sous-poste | 2020-02-27 | 2020-02-28 | 2020-02-28 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 9 | 2 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
2832699510 | 2019-11-12 | FABRICATION | SATAIR | JACK | 28326995 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 30336 | LTE990035 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-29 | NA | 100% | 2020-01-29 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-02-29 | 2020-02-29 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 9 | 2 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2832699511 | 2019-11-12 | FABRICATION | SATAIR | JACK | 28326995 | NON-SPARES | 11 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 30336 | LTE990036 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-29 | NA | 100% | 2020-01-29 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-02-29 | 2020-02-29 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 9 | 2 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2832699512 | 2019-11-12 | FABRICATION | SATAIR | JACK | 28326995 | NON-SPARES | 12 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 30336 | LTE990037 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-29 | NA | 100% | 2020-01-29 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-02-29 | 2020-02-29 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 9 | 2 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2819535010 | 2019-06-24 | FABRICATION | SATAIR | 40 | 28195350 | NON-SPARES | 10 | 1 | RTN | D9551004000395 | 0 | NON PRESENT INDUS | 26134 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-13 | NA | 100% | 2020-01-13 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-03-02 | 2020-03-02 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 9 | 2 | 2020 | 0.205 | 11.8819 | 2.9705 | 14.8524 | COL | 0 | 0
2819535011 | 2019-06-24 | FABRICATION | SATAIR | 40 | 28195350 | NON-SPARES | 11 | 1 | RTN | D9551004000395 | 0 | NON PRESENT INDUS | 26134 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-13 | NA | 100% | 2020-01-13 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-03-02 | 2020-03-02 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 9 | 2 | 2020 | 0.205 | 11.8819 | 2.9705 | 14.8524 | COL | 0 | 0
2837422810 | 2020-01-07 | FABRICATION | SATAIR | PLACARD SET | 28374228 | NON-SPARES | 10 | 1 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | NA | 493826-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-01-13 | NA | 100% | 2020-01-13 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-02-26 | Sous-poste | Sous-poste | 2020-03-02 | 2020-03-02 | 2020-02-27 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 9 | 2 | 2020 | 0 | 0.205 | 0.0205 | 0.2255 | NA | 0 | 0
2777990020 | 2020-01-06 | FABRICATION | SATAIR | 27 | 27779900 | NON-SPARES | 20 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 31904 | LTE990071 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-07 | NA | 100% | 2020-02-07 | 100% | NA | NA | 5.556% |  |  | 2020-01-28 | 2020-02-27 | Sous-poste | Sous-poste | 2020-01-31 | 2020-03-03 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 9 | 2 | 2020 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
490003999310 | 2019-12-10 | FABRICATION | STELIA | CÂBLE | 4900039993 | NON-SPARES | 10 | 2 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | N/A | 490769-1 => 490769-2 |  |  |  | 0% | 0% | 0% | 100% | 2020-01-10 | NA | 100% | 2020-01-10 | 100% | NA | OUI | 5.263% |  |  | 2020-02-17 | 2020-02-28 | Sous-poste | Sous-poste | 2020-02-20 | 2020-03-04 | 2020-03-04 |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 9 | 2 | 2020 | 0.41 | 2 | 0.1 | 2.1 | NA | 0 | 0
2836726510 | 2019-12-20 | FABRICATION | SATAIR | 22 | 28367265 | NON-SPARES | 10 | 1 | CRIT | D9551002201195 | 0 | NON PRESENT INDUS | 31896 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-13 | 100% | 100% | 2020-02-20 | 100% | NA | NA | 5.556% |  |  | 2019-12-19 | 2020-03-02 | Sous-poste | Sous-poste | 2019-12-22 | 2020-03-04 | 2020-03-04 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2837952410 | 2020-01-14 | HA/REVENTE | SATAIR | PLATE ASSY | 28379524 | NON-SPARES | 10 | 4 | EXP | D9251101900000 | 1STR*11007 | NA | 32085 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-10 | NA | 100% | 2020-02-28 | 100% | NA | NA | 100% |  |  | 2020-02-05 | 2020-03-02 | Sous-poste | Sous-poste | 2020-02-09 | 2020-03-05 | 2020-03-03 | OK | Allemagne | N°421073 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 10 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2832798410 | 2019-11-13 | FABRICATION | SATAIR | 22 | 28327984 | NON-SPARES | 10 | 1 | RTN | D9551002201695 | 0 | NON PRESENT INDUS | 30369 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-17 | 100% | 100% | 2020-02-17 | 100% | NA | NA | 5.556% |  |  | 2020-02-06 | 2020-03-04 | Sous-poste | Sous-poste | 2020-02-11 | 2020-03-07 | 2020-03-05 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 10 | 3 | 2020 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2833860110 | 2019-11-22 | FABRICATION | SATAIR | 60 | 28338601 | NON-SPARES | 10 | 1 | AOG | D9551006000395 | 0 | NON PRESENT INDUS | 30818 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-24 | 100% | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-16 | 2020-03-05 | Sous-poste | Sous-poste | 2020-01-20 | 2020-03-06 | 2020-03-07 | OK | Allemagne | Manquant 4STR*00879 (Réception le 02/03) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 10 | 3 | 2020 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2833860610 | 2019-11-22 | FABRICATION | SATAIR | 61 | 28338606 | NON-SPARES | 10 | 1 | AOG | D9551006100395 | 0 | NON PRESENT INDUS | 30818 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-24 | 100% | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-16 | 2020-03-05 | Sous-poste | Sous-poste | 2020-01-20 | 2020-03-06 | 2020-03-07 | OK | Allemagne | Manquant 4STR*00880 (Réception le 02/03) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 10 | 3 | 2020 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2833860710 | 2019-11-22 | FABRICATION | SATAIR | 62 | 28338607 | NON-SPARES | 10 | 1 | AOG | D9551006200395 | 0 | NON PRESENT INDUS | 30818 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-24 | 100% | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-16 | 2020-03-05 | Sous-poste | Sous-poste | 2020-01-20 | 2020-03-06 | 2020-03-07 | OK | Allemagne | Manquant 4STR*00881 (Réception le 02/03) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 10 | 3 | 2020 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2832798420 | 2019-11-13 | FABRICATION | SATAIR | 22 | 28327984 | NON-SPARES | 20 | 1 | RTN | D9551002201695 | 0 | NON PRESENT INDUS | 30369 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-17 | 100% | 100% | 2020-02-17 | 100% | NA | NA | 5.556% |  |  | 2020-02-06 | 2020-03-05 | Sous-poste | Sous-poste | 2020-02-11 | 2020-03-24 | 2020-03-09 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 10 | 3 | 2020 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2835194111 | 2019-12-10 | FABRICATION | SATAIR | 620 | 28351941 | NON-SPARES | 11 | 1 | AOG | D9551062000195 | 0 | NON PRESENT INDUS | 31449 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-03 | NA | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-03 | 2020-03-06 | Sous-poste | Sous-poste | 2020-01-07 | 2020-03-10 | 2020-03-07 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0.205 | 1.4123 | 0.35308 | 1.7654 | COL | 0 | 0
2835194112 | 2019-12-10 | FABRICATION | SATAIR | 620 | 28351941 | NON-SPARES | 12 | 1 | AOG | D9551062000195 | 0 | NON PRESENT INDUS | 31449 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-03 | NA | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-03 | 2020-03-06 | Sous-poste | Sous-poste | 2020-01-07 | 2020-03-10 | 2020-03-07 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0.205 | 1.4123 | 0.35308 | 1.7654 | COL | 0 | 0
2835222711 | 2019-12-10 | FABRICATION | SATAIR | 619 | 28352227 | NON-SPARES | 11 | 1 | AOG | D9551061900195 | 0 | NON PRESENT INDUS | 31449 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-03 | NA | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-08 | 2020-03-06 | Sous-poste | Sous-poste | 2020-01-10 | 2020-03-10 | 2020-03-07 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0.205 | 1.4105 | 0.35263 | 1.7631 | COL | 0 | 0
2835222712 | 2019-12-10 | FABRICATION | SATAIR | 619 | 28352227 | NON-SPARES | 12 | 1 | AOG | D9551061900195 | 0 | NON PRESENT INDUS | 31449 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-03 | NA | 100% | 2020-03-04 | 100% | NA | NA | 5.556% |  |  | 2020-01-08 | 2020-03-06 | Sous-poste | Sous-poste | 2020-01-10 | 2020-03-10 | 2020-03-07 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0.205 | 1.4105 | 0.35263 | 1.7631 | COL | 0 | 0
2835693510 | 2019-12-13 | HA/REVENTE | SATAIR | COVER ASSY | 28356935 | NON-SPARES | 10 | 4 | RTN | A9252597000900 | 1STR*01482 | NA | 31464 | 36211 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-01 | NA | 100% | 2020-03-04 | 100% | NA | NA | 100% |  |  | 2020-03-06 | 2020-03-06 | Sous-poste | Sous-poste | 2020-03-11 | 2020-03-11 | 2020-03-07 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 10 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2841272710 | 2020-02-13 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28412727 | NON-SPARES | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 33158 | 245684 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-05 | NA | 100% | 2020-03-06 | 100% | NA | NA | 100% |  |  | 2020-02-12 | 2020-03-09 | Sous-poste | Sous-poste | 2020-02-14 | 2020-02-14 | 2020-03-10 | OK | Allemagne | ACHF60240 - PO penalisée (livraison > 5 jours) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 11 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2842292110 | 2020-02-24 | FABRICATION | SATAIR | 117 | 28422921 | NON-SPARES | 10 | 1 | CRIT | D9550011700295 | IS0032071M | NON PRESENT INDUS | 29344 | LTE990154 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-21 | NA | 100% | 2020-01-31 | 100% | NA | NA | 5.556% |  |  | 2020-02-21 | 2020-03-10 | Sous-poste | Sous-poste | 2020-02-25 | 2020-03-12 | 2020-03-11 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 11 | 3 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2827848810 | 2019-09-16 | FABRICATION | SATAIR | WIRE-BONDING | 28278488 | NON-SPARES | 10 | 2 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | 28440 | 434647-1 => 434647-2 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-09 | NA | 100% | 2020-02-09 | 100% | NA | NA | 5.556% |  |  | 2020-03-10 | 2020-03-10 | Sous-poste | Sous-poste | 2020-03-13 | 2020-03-13 | 2020-03-11 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 11 | 3 | 2020 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2827849010 | 2019-09-16 | FABRICATION | SATAIR | WIRE-BONDING | 28278490 | NON-SPARES | 10 | 1 | RTN | F0003008100200 | IS0032147M | NON PRESENT INDUS | 28440 | 434649-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-09 | NA | 100% | 2020-02-09 | 100% | NA | NA | 5.556% |  |  | 2020-03-10 | 2020-03-10 | Sous-poste | Sous-poste | 2020-03-13 | 2020-03-13 | 2020-03-11 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 11 | 3 | 2020 | 0.2085 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2827849110 | 2019-09-16 | FABRICATION | SATAIR | LEAD-BONDING | 28278491 | NON-SPARES | 10 | 1 | RTN | F0003008100300 | IS0032149M | NON PRESENT INDUS | 28440 | 434651-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-09 | NA | 100% | 2020-02-09 | 100% | NA | NA | 5.556% |  |  | 2020-03-10 | 2020-03-10 | Sous-poste | Sous-poste | 2020-03-13 | 2020-03-13 | 2020-03-11 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 11 | 3 | 2020 | 0.2075 | 0.2383 | 0.059575 | 0.29788 | NA | 0 | 0
490004049020 | 2020-02-12 | HA/REVENTE | STELIA | RAMPE | 4900040490 | NON-SPARES | 20 | 2 | EXP | S9251446520000 | 1STR*11044 | NA | 33188 | 8003FA9E0/DA | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-04 | NA | 100% | 2020-03-18 | 100% | NA | NA | 100% |  |  | 2020-02-20 | 2020-03-20 | Sous-poste | Sous-poste | 2020-02-25 | 2020-03-25 | 2020-03-18 | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 12 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004049060 | 2020-02-12 | HA/REVENTE | STELIA | PLATINE ARRIERE 26VU | 4900040490 | NON-SPARES | 60 | 2 | EXP | S9251590500000 | IS0035439S | NA | 33188 | OF002969 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-17 | NA | 100% | 2020-03-18 | 100% | NA | NA | 100% |  |  | 2020-02-20 | 2020-03-20 | Sous-poste | Sous-poste | 2020-02-25 | 2020-03-25 | 2020-03-18 | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 12 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2814141910 | 2019-04-29 | FABRICATION | SATAIR | PROTECTION CAP | 28141419 | NON-SPARES | 10 | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 24551 | 340198-1 => 340198-15 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-24 | NA | 100% | 2020-02-24 | 100% | NA | NA | 5.556% |  |  | 2020-03-18 | 2020-03-25 | Sous-poste | Sous-poste | 2020-03-23 | 2020-03-30 | 2020-03-26 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 | 13 | 3 | 2020 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
490004041710 | 2020-02-05 | HA/REVENTE | STELIA | RAMPE | 4900040417 | NON-SPARES | 10 | 1 | RTN | S9251458000000 | 3STR*01167 | NA | 32910 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-06 | NA | 100% | 2020-03-25 | 100% | NA | NA | 100% |  |  | 2020-03-30 | 2020-03-30 | Sous-poste | Sous-poste | 2020-04-02 | 2020-04-02 | 2020-03-26 | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 14 | 3 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 102
2795002310 | 2018-09-18 | FABRICATION | SATAIR | 419 | 27950023 | NON-SPARES | 10 | 1 | CRIT | A95500419000AA | 0 | NON PRESENT INDUS | 17485 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2019-02-19 | NA | 100% | 2019-02-19 | 100% | NA | NA | 5.556% |  |  | 2018-10-16 | 2020-04-02 | Sous-poste | Sous-poste | 2018-10-18 | 2020-04-03 | 2020-04-03 | OK | Allemagne | Décalée du 27/03 au 31/03 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2018 | 14 | 4 | 2020 | 0.36 | 7.347 | 1.8367 | 9.1837 | COL | 0 | 0 | 4085
2835824010 | 2019-12-14 | FABRICATION | SATAIR | JACK | 28358240 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 31515 | LTE990038 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-10 | NA | 100% | 2020-03-10 | 100% | NA | NA | 5.556% |  |  | 2020-03-26 | 2020-04-02 | Sous-poste | Sous-poste | 2020-03-31 | 2020-04-07 | 2020-04-06 | OK | Allemagne | Au contrôle | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 14 | 4 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 808
2835824011 | 2019-12-14 | FABRICATION | SATAIR | JACK | 28358240 | NON-SPARES | 11 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 31515 | LTE990039 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-10 | NA | 100% | 2020-03-10 | 100% | NA | NA | 5.556% |  |  | 2020-03-26 | 2020-04-02 | Sous-poste | Sous-poste | 2020-03-31 | 2020-04-07 | 2020-04-06 | OK | Allemagne | Au contrôle | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 14 | 4 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 808
490004057210 | 2020-02-18 | HA/REVENTE | STELIA | PILLAR | 4900040572 | NON-SPARES | 10 | 1 | RTN | F0003057821000 | 1QME*17052 | NA | 33461 | OF003616 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-16 | NA | 100% | 2020-03-18 | 100% | NA | NA | 100% |  |  | 2020-03-25 | 2020-04-07 | Sous-poste | Sous-poste | 2020-03-29 | 2020-04-10 | 2020-03-19 | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 15 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2835654310 | 2019-12-13 | HA/REVENTE | SATAIR | PLATE | 28356543 | NON-SPARES | 10 | 1 | RTN | D9251746700000 | 1STR*11241 | NA | 31465 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-02-24 | NA | 100% | 2020-03-25 | 100% | NA | NA | 100% |  |  | 2020-03-27 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-14 | 2020-04-10 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 15 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2843850110 | 2020-03-09 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28438501 | NON-SPARES | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 33917 | 20031217 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-30 | NA | 100% | 2020-03-31 | 100% | NA | NA | 100% |  |  | 2020-03-06 | 2020-04-09 | Sous-poste | Sous-poste | 2020-03-10 | 2020-04-14 | 2020-04-09 | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 15 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838916610 | 2020-01-20 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28389166 | NON-SPARES | 10 | 2 | RTN | D9251805800000 | IS0032777S | NA | 32392 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-27 | NA | 100% | 2020-03-25 | 100% | NA | NA | 100% |  |  | 2020-02-17 | 2020-04-09 | Sous-poste | Sous-poste | 2020-02-20 | 2020-04-14 | 2020-04-10 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838917110 | 2020-01-20 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28389171 | NON-SPARES | 10 | 2 | RTN | D9251805700000 | IS0032776S | NA | 32392 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-03-27 | NA | 100% | 2020-03-25 | 100% | NA | NA | 100% |  |  | 2020-02-17 | 2020-04-09 | Sous-poste | Sous-poste | 2020-02-20 | 2020-04-14 | 2020-04-10 | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
284535251 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453525 | NON-SPARES | 1 | 1 | AOG | V9253110000096 | IS0032170M | NON PRESENT INDUS | NA | 517565-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535252 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453525 | NON-SPARES | 2 | 1 | AOG | V9253110000096 | IS0032170M | NON PRESENT INDUS | NA | 517567-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535253 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453525 | NON-SPARES | 3 | 1 | AOG | V9253110000096 | IS0032170M | NON PRESENT INDUS | NA | 517569-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535254 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453525 | NON-SPARES | 4 | 1 | AOG | V9253110000096 | IS0032170M | NON PRESENT INDUS | NA | 517571-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535255 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453525 | NON-SPARES | 5 | 1 | AOG | V9253110000096 | IS0032170M | NON PRESENT INDUS | NA | 517573-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535271 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453527 | NON-SPARES | 1 | 1 | AOG | V9253120000096 | IS0032173M | NON PRESENT INDUS | NA | 517575-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535272 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453527 | NON-SPARES | 2 | 1 | AOG | V9253120000096 | IS0032173M | NON PRESENT INDUS | NA | 517577-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535273 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453527 | NON-SPARES | 3 | 1 | AOG | V9253120000096 | IS0032173M | NON PRESENT INDUS | NA | 517579-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535274 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453527 | NON-SPARES | 4 | 1 | AOG | V9253120000096 | IS0032173M | NON PRESENT INDUS | NA | 517581-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
284535275 | 2020-04-01 | FABRICATION | SATAIR | BUNDLE | 28453527 | NON-SPARES | 5 | 1 | AOG | V9253120000096 | IS0032173M | NON PRESENT INDUS | NA | 517583-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-04-01 | NA | 100% | 2020-04-03 | 100% | NA | NA | 5.556% |  |  | 2020-03-30 | 2020-04-09 | Sous-poste | Sous-poste | 2020-04-01 | 2020-04-16 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 15 | 4 | 2020 | 0.1289 | 0.1455 | 0.1 | 0.2455 | COL | 0 | 0
2838590910 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385909 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591010 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385910 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591110 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385911 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591210 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385912 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591410 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385914 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591510 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385915 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591810 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385918 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838591910 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385919 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838592210 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385922 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838592410 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385924 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-10 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 15 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2838592710 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385927 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838593910 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385939 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838594010 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385940 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838594810 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385948 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838594910 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385949 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990016 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838595010 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385950 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990017 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838595110 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385951 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838595210 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385952 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838595310 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385953 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2838595410 | 2020-01-16 | FABRICATION | SATAIR | 54 | 28385954 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 32359 | LTE990021 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | 100% | 100% | 2020-03-16 | 100% | NA | NA | 5.556% |  |  | 2020-02-03 | 2020-04-17 | Sous-poste | Sous-poste | 2020-02-07 | 2020-04-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 16 | 4 | 2020 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0 | 890
2836594910 | 2019-12-19 | HA/REVENTE | SATAIR | COVER ASSY | 28365949 | NON-SPARES | 10 | 2 | RTN | A9252597000900 | 1STR*01482 | NA | 31805 | 36211 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-06 | NA | 100% | 2020-04-10 | 100% | NA | NA | 100% |  |  | 2020-03-19 | 2020-04-20 | Sous-poste | Sous-poste | 2020-03-25 | 2020-04-23 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 17 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2844279810 | 2020-03-13 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28442798 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 34056 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-16 | NA | 100% | 2020-04-22 | 100% | NA | NA | 100% |  |  | 2020-03-12 | 2020-04-21 | Sous-poste | Sous-poste | 2020-03-14 | 2020-04-23 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 17 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 57
2833951510 | 2019-11-25 | FABRICATION | SATAIR | 117 | 28339515 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 33459 | LTE990158 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-26 | NA | 100% | 2020-04-10 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-04-21 | Sous-poste | Sous-poste | 2020-03-02 | 2020-04-24 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 17 | 4 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2839701010 | 2020-01-29 | FABRICATION | SATAIR | BUNDLE | 28397010 | NON-SPARES | 10 | 1 | RTN | D9000095477995 | IS0032050M | NON PRESENT INDUS | 32747 | 499745-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-04 | NA | 100% | 2020-03-09 | 100% | NA | NA | 5.556% |  |  | 2020-03-10 | 2020-04-22 | Sous-poste | Sous-poste | 2020-03-13 | 2020-04-27 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 17 | 4 | 2020 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0 | 7106
2839701011 | 2020-01-30 | FABRICATION | SATAIR | BUNDLE | 28397010 | NON-SPARES | 11 | 1 | RTN | D9000095477995 | IS0032050M | NON PRESENT INDUS | 32747 | 499755-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-04 | NA | 100% | 2020-03-09 | 100% | NA | NA | 5.556% |  |  | 2020-03-10 | 2020-04-22 | Sous-poste | Sous-poste | 2020-03-13 | 2020-04-27 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 17 | 4 | 2020 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0 | 7106
2844965210 | 2020-03-19 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28449652 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 34138 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-16 | NA | 100% | 2020-04-22 | 0% | NA | NA | 0% |  |  | 2020-03-18 | 2020-04-23 | Sous-poste | Sous-poste | 2020-03-20 | 2020-04-27 |  | OK | Allemagne | Commande annulée | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 17 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0
2844676610 | 2020-03-17 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28446766 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 34104 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-16 | NA | 100% | 2020-04-22 | 100% | NA | NA | 100% |  |  | 2020-04-10 | 2020-04-23 | Sous-poste | Sous-poste | 2020-04-15 | 2020-04-28 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 17 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838021110 | 2020-01-13 | FABRICATION | SATAIR | 108 | 28380211 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 32020 | LTE990018 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-28 | 100% | 100% | 2020-03-09 | 100% | NA | NA | 5.556% |  |  | 2020-04-08 | 2020-04-24 | Sous-poste | Sous-poste | 2020-04-12 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 17 | 4 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0 | 3495
2830117810 | 2019-10-11 | FABRICATION | SATAIR | 117 | 28301178 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 30752 | LTE990157 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-26 | NA | 100% | 2020-03-27 | 100% | NA | NA | 5.556% |  |  | 2020-02-18 | 2020-04-24 | Sous-poste | Sous-poste | 2020-02-21 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 17 | 4 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2830117811 | 2019-10-11 | FABRICATION | SATAIR | 117 | 28301178 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 29344 | LTE990155 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-21 | NA | 100% | 2020-01-31 | 100% | NA | NA | 5.556% |  |  | 2020-02-18 | 2020-04-24 | Sous-poste | Sous-poste | 2020-02-21 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 17 | 4 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2830117812 | 2019-10-11 | FABRICATION | SATAIR | 117 | 28301178 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 29344 | LTE990156 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-26 | NA | 100% | 2020-03-26 | 100% | NA | NA | 5.556% |  |  | 2020-02-18 | 2020-04-24 | Sous-poste | Sous-poste | 2020-02-21 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 17 | 4 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2838030810 | 2020-01-13 | FABRICATION | SATAIR | 108 | 28380308 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 32020 | LTE990019 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-28 | 100% | 100% | 2020-03-09 | 100% | NA | NA | 5.556% |  |  | 2020-04-08 | 2020-04-24 | Sous-poste | Sous-poste | 2020-04-12 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 17 | 4 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0 | 3495
2838041110 | 2020-01-13 | FABRICATION | SATAIR | 108 | 28380411 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 32020 | LTE990020 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-28 | 100% | 100% | 2020-03-09 | 100% | NA | NA | 5.556% |  |  | 2020-04-08 | 2020-04-24 | Sous-poste | Sous-poste | 2020-04-12 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 17 | 4 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0 | 3495
2836739510 | 2019-12-20 | FABRICATION | SATAIR | PROTECTION CAP | 28367395 | NON-SPARES | 10 | 60 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 31898 | 491953-1 => 491953-60 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-21 | NA | 100% | 2020-03-20 | 100% | NA | NA | 5.556% |  |  | 2020-04-17 | 2020-04-24 | Sous-poste | Sous-poste | 2020-04-23 | 2020-04-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 17 | 4 | 2020 | 0.15 | 6.708 | 0.01118 | 6.7192 | NA | 0 | 0
49000408001 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 1 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517174-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408002 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 2 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517176-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408003 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 3 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517178-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408004 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 4 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517180-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408005 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 5 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517182-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408006 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 6 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517184-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408007 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 7 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517186-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408008 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 8 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517188-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
49000408009 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 9 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517190-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080010 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 10 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517192-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080011 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 11 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517194-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080012 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 12 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517196-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080013 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 13 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517198-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080014 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 14 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517200-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
490004080015 | 2020-03-17 | FABRICATION | STELIA | CABLE COAXIAL | 4900040800 | NON-SPARES | 15 | 1 | RTN | S9110104500295 | 0 | NON PRESENT INDUS | 34140 | 517202-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-06 | NA | 100% | 2020-04-14 | 100% | NA | OUI | 5.263% |  |  | 2020-04-23 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-28 | 2020-04-30 |  | OK | Rochefort | Manque EASA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 214.45
2844676810 | 2020-03-17 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28446768 | NON-SPARES | 10 | 2 | EXP | D9251095600000 | IS0053509S | NA | 34104 | 20033112 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-21 | NA | 100% | 2020-04-22 | 100% | NA | NA | 100% |  |  | 2020-04-10 | 2020-04-27 | Sous-poste | Sous-poste | 2020-04-15 | 2020-04-30 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 18 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 113
2818503410 | 2019-06-13 | FABRICATION | SATAIR | PROTECTION CAP | 28185034 | NON-SPARES | 10 | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 25765 | 374771-1 => 374771-15 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-01 | NA | 100% | 2020-04-01 | 100% | NA | NA | 5.556% |  |  | 2020-04-29 | 2020-04-29 | Sous-poste | Sous-poste | 2020-05-04 | 2020-05-04 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 18 | 4 | 2020 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
490004093710 | 2020-04-10 | HA/REVENTE | STELIA | SUPPLATE FRONT 27VU | 4900040937 | NON-SPARES | 10 | 2 | RTN | S9251428800100 | 3STR*01418 | NA | 34501 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-16 | NA | 100% | 2020-04-22 | 100% | NA | NA | 100% |  |  | 2020-04-30 | 2020-04-30 | Sous-poste | Sous-poste | 2020-05-05 | 2020-05-05 |  | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 18 | 4 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 390
2845102010 | 2020-04-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28451020 | NON-SPARES | 10 | 1 | AOG | D9251805800000 | IS0032777S | NA | 34350 | OF432768 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-25 | NA | 100% | 2020-05-06 | 100% | NA | NA | 100% |  |  | 2020-04-02 | 2020-05-18 | Sous-poste | Sous-poste | 2020-04-05 | 2020-05-20 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 373
2842390810 | 2020-02-24 | HA/REVENTE | SATAIR | COVER ASSY | 28423908 | NON-SPARES | 10 | 1 | RTN | A9252597000800 | 1STR*01148 | NA | 33538 | 032807 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-18 | NA | 100% | 2020-05-18 | 100% | NA | NA | 100% |  |  | 2020-05-21 | 2020-05-21 | Sous-poste | Sous-poste | 2020-05-26 | 2020-05-26 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 508
2843784710 | 2020-03-09 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28437847 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 33918 | OF469803 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-15 | NA | 100% | 2020-05-14 | 100% | NA | NA | 100% |  |  | 2020-05-20 | 2020-05-22 | Sous-poste | Sous-poste | 2020-05-25 | 2020-05-27 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 312
2843784610 | 2020-03-09 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28437846 | NON-SPARES | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 33918 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-27 | NA | 100% | 2020-05-14 | 100% | NA | NA | 100% |  |  | 2020-05-20 | 2020-05-22 | Sous-poste | Sous-poste | 2020-05-25 | 2020-05-27 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 372
2844577010 | 2020-03-16 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28445770 | NON-SPARES | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 34104 | OF432768 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-27 | NA | 100% | 2020-05-14 | 100% | NA | NA | 100% |  |  | 2020-05-20 | 2020-05-22 | Sous-poste | Sous-poste | 2020-05-25 | 2020-05-27 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 372
490004060510 | 2020-02-20 | HA/REVENTE | STELIA | PLATINE ARRIERE 26VU | 4900040605 | NON-SPARES | 10 | 2 | RTN | S9251590500000 | IS0035439S | NA | 33188 | OF000754 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-07 | NA | 100% | 2020-05-07 | 100% | NA | NA | 100% |  |  | 2020-04-14 | 2020-05-22 | Sous-poste | Sous-poste | 2020-04-17 | 2020-05-27 |  | OK | Rochefort | Pièces perdues | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 21 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 698
2838347710 | 2019-06-19 | FABRICATION | SATAIR | PROTECTION CAP | 28383477 | NON-SPARES | 10 | 30 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 32404 | 496646-1 => 496646-30 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-03 | NA | 100% | 2020-05-04 | 100% | NA | NA | 5.556% |  |  | 2020-05-27 | 2020-05-27 | Sous-poste | Sous-poste | 2020-06-02 | 2020-06-01 |  | OK | Allemagne | Switch avec PO 28191383 - Manque 1CON*01083 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 | 22 | 5 | 2020 | 0.075 | 3.354 | 0.01118 | 3.3652 | NA | 0 | 0 | 4020
2823883310 | 2019-08-02 | FABRICATION | SATAIR | PROTECTION CAP | 28238833 | NON-SPARES | 10 | 30 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 27645 | 420539-1 => 420539-30 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-04 | NA | 100% | 2020-05-04 | 100% | NA | NA | 5.556% |  |  | 2020-05-27 | 2020-05-27 | Sous-poste | Sous-poste | 2020-06-02 | 2020-06-01 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 22 | 5 | 2020 | 0.075 | 3.354 | 0.01118 | 3.3652 | NA | 0 | 0 | 4020
2846247610 | 2020-04-21 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28462476 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 34599 | 248395 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-14 | NA | 100% | 2020-05-15 | 100% | NA | NA | 100% |  |  | 2020-04-20 | 2020-05-27 | Sous-poste | Sous-poste | 2020-04-22 | 2020-05-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2846247210 | 2020-04-21 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28462472 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 34599 | 248395 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-14 | NA | 100% | 2020-05-15 | 100% | NA | NA | 100% |  |  | 2020-04-20 | 2020-05-27 | Sous-poste | Sous-poste | 2020-04-22 | 2020-05-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2845933510 | 2020-04-14 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28459335 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 34514 | 248395 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-07 | NA | 100% | 2020-05-14 | 100% | NA | NA | 100% |  |  | 2020-04-17 | 2020-05-27 | Sous-poste | Sous-poste | 2020-04-21 | 2020-05-29 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
49000409291 | 2020-04-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900040929 | NON-SPARES | 1 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 34497 | 518299-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-30 | NA | 100% | 2020-05-05 | 100% | 0% | OUI | 5% |  |  | 2020-04-22 | 2020-05-27 | Sous-poste | Sous-poste | 2020-04-27 | 2020-05-29 |  | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 234
49000409292 | 2020-04-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900040929 | NON-SPARES | 2 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 34497 | 518301-2 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-30 | NA | 100% | 2020-05-05 | 100% | 0% | OUI | 5% |  |  | 2020-04-22 | 2020-05-27 | Sous-poste | Sous-poste | 2020-04-27 | 2020-05-29 |  | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0 | 234
2846882710 | 2020-05-12 | FABRICATION | SATAIR | BUNDLE | 28468827 | NON-SPARES | 10 | 1 | AOG | D9000095029895 | 0 | NON PRESENT INDUS | NA | 518920-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-05-18 | NA | 100% | TBD | 0% | NA | NA | 0% |  |  | 2020-05-08 | 2020-05-28 | Sous-poste | Sous-poste | 2020-05-12 | 2020-06-01 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 22 | 5 | 2020 | 0 | 0 | 0 | 0 | COL | 0 | 0 | 686
2846585210 | 2020-04-30 | FABRICATION | SATAIR | OPTICAL FIBER | 28465852 | NON-SPARES | 10 | 1 | AOG | D9000095029495 | IS0032047M | NON PRESENT INDUS | NA | 518829-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-05-18 | NA | 100% | TBD | 0% | NA | NA | 0% |  |  | 2020-04-28 | 2020-05-28 | Sous-poste | Sous-poste | 2020-04-30 | 2020-06-01 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 22 | 5 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 686
490004086610 | 2020-04-01 | HA/REVENTE | SATAIR | VOYANT DE SIGNALISATION | 4900040866 | NON-SPARES | 10 | 2 | RTN | E0070B023 | 1CPR*15182 | NA | 34351 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-20 | NA | 100% | 2020-06-05 | 100% | NA | NA | 100% |  |  | 2020-05-21 | 2020-06-04 | Sous-poste | Sous-poste | 2020-05-26 | 2020-06-09 |  | OK | Rochefort | Stock cannibalisé par SAP => résa saisie et article reçu en attente reloc SILOG (Tanguy) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 23 | 6 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 160
2828658710 | 2019-09-23 | FABRICATION | SATAIR | 435 | 28286587 | NON-SPARES | 10 | 1 | RTN | A95500435000AA | 0 | NON PRESENT INDUS | 25899 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | 100% | 100% | 2020-03-11 | 100% | NA | NA | 5.556% |  |  | 2019-12-18 | 2020-06-05 | Sous-poste | Sous-poste | 2019-12-22 | 2020-06-10 |  | OK | Allemagne | Questions techniques à valider entre David et Greg | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 23 | 6 | 2020 | 0.36 | 6.3224 | 1.5806 | 7.903 | COL | 0 | 0 | 2944
490004031110 | 2020-01-31 | FABRICATION | STELIA | CÂBLE | 4900040311 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 33474 | 499802-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-05 | NA | 100% | 2020-05-06 | 100% | NA | OUI | 5.263% |  |  | 2020-04-22 | 2020-06-05 | Sous-poste | Sous-poste | 2020-04-26 | 2020-06-10 |  | OK | Rochefort | Prêt attente BE Étienne (dde le 30/05) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 23 | 6 | 2020 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0 | 245
2841192410 | 2020-02-14 | FABRICATION | SATAIR | PLACARD SET | 28411924 | NON-SPARES | 10 | 11 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | 34756 | 504177-1 => 504177-11 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-24 | NA | 100% | 2020-05-27 | 100% | NA | NA | 5.556% |  |  | 2020-03-27 | 2020-06-05 | Sous-poste | Sous-poste | 2020-04-01 | 2020-06-10 |  | OK | Allemagne | Manque 1ETI*00200 (AR 24/05/2020) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 23 | 6 | 2020 | 0 | 2.255 | 0.0205 | 2.2755 | NA | 0 | 0 | 1100
2839334110 | 2020-01-23 | HA/REVENTE | SATAIR | PLATE ASSY | 28393341 | NON-SPARES | 10 | 10 | RTN | L9251321500000 | 1STR*01089 | NA | 32531 | 511162 (QTE 8) 465666 (QTE 2) | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-12 | NA | 100% | 2020-06-05 | 100% | NA | NA | 100% |  |  | 2020-04-21 | 2020-06-10 | Sous-poste | Sous-poste | 2020-04-24 | 2020-06-15 |  | OK | Allemagne | Retard FRS | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 24 | 6 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 980
2827634210 | 2019-09-12 | FABRICATION | SATAIR | 419 | 28276342 | NON-SPARES | 10 | 1 | RTN | A95500419000AA | 0 | NON PRESENT INDUS | 28270 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-27 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2019-12-06 | 2020-06-12 | Sous-poste | Sous-poste | 2019-12-12 | 2020-06-17 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 24 | 6 | 2020 | 0.36 | 7.347 | 1.8367 | 9.1837 | COL | 0 | 0 | 2944
2842463210 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 10 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518513-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463211 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 11 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518515-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463212 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 12 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518517-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463213 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 13 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518519-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463214 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 14 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518521-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463215 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 15 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518523-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463216 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 16 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518525-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463217 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 17 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518527-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463218 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 18 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518529-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2842463219 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28424632 | NON-SPARES | 19 | 1 | CRIT | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518531-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-02-26 | 2020-06-12 | Sous-poste | Sous-poste | 2020-02-28 | 2020-06-16 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 24 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2840771710 | 2020-02-07 | FABRICATION | SATAIR | 22 | 28407717 | NON-SPARES | 10 | 1 | AOG | D9551002200395 | 0 | NON PRESENT INDUS | 33398 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-10 | 100% | 100% | 2020-05-11 | 100% | NA | NA | 5.556% |  |  | 2020-02-21 | 2020-06-18 | Sous-poste | Sous-poste | 2020-02-25 | 2020-06-21 |  | OK | Allemagne | Matière canibalisée par chantier 22VU | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 25 | 6 | 2020 | 0.205 | 10.54 | 2.63 | 13.17 | COL | 0 | 0 | 4480
PREV_KITS_PEGASUS2 |  | FABRICATION | LATECOERE | 9000 | PREV_KITS_PEGASUS | NON-SPARES | 2 | 6 | RTN | A320EL050000-EPA | 0 | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | OUI | NA |  |  | 2020-04-10 | 2020-06-18 | Sous-poste | Sous-poste | 2020-04-15 | 2020-06-23 |  | OK | Labège | 3VU expédiés le 18/06 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 25 | 6 | 2020 | 1.23 | 17.1 | 0.7125 | 17.8125 | COL | 0 | 0
2796891220 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 20 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-06-19 | Sous-poste | Sous-poste | 2020-01-22 | 2020-06-24 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 25 | 6 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
2796891230 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 30 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-06-19 | Sous-poste | Sous-poste | 2020-01-22 | 2020-06-24 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 25 | 6 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
2796891240 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 40 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-06-19 | Sous-poste | Sous-poste | 2020-01-22 | 2020-06-24 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 25 | 6 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
284286951 | 2020-02-28 | FABRICATION | SATAIR | JACK | 28428695 | NON-SPARES | 1 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 33706 | LTE990043 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-10 | NA | 100% | 2020-06-16 | 100% | NA | NA | 5.556% |  |  | 2020-03-25 | 2020-06-19 | Sous-poste | Sous-poste | 2020-03-28 | 2020-06-24 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 25 | 6 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 1617
284286952 | 2020-02-28 | FABRICATION | SATAIR | JACK | 28428695 | NON-SPARES | 2 | 1 | EXP | A0041114100095 | IS0032651M | NON PRESENT INDUS | 33706 | LTE990044 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-10 | NA | 100% | 2020-06-16 | 100% | NA | NA | 5.556% |  |  | 2020-03-25 | 2020-06-19 | Sous-poste | Sous-poste | 2020-03-28 | 2020-06-24 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 25 | 6 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 1617
2820470040 | 2019-09-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28204700 | NON-SPARES | 40 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 26335 | 383221-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-09-16 | 100% | 100% | 2019-10-07 | 100% | NA | NA | 5.556% |  |  | 2019-12-04 | 2020-06-23 | Sous-poste | Sous-poste | 2019-12-09 | 2020-06-24 |  | OK | Allemagne | Attente envoi derog | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 26 | 6 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2815867860 | 2019-09-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28158678 | NON-SPARES | 60 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 21430 | 261769-2 |  |  |  | 100% | 0% | 50% | 100% | 2019-05-26 | 100% | 100% | 2019-05-26 | 100% | NA | NA | 5.556% |  |  | 2019-12-04 | 2020-06-23 | Sous-poste | Sous-poste | 2019-12-09 | 2020-06-24 |  | OK | Allemagne | Attente envoi derog | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 26 | 6 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2815867830 | 2019-09-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28158678 | NON-SPARES | 30 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 21430 | 402840-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-05-26 | 100% | 100% | 2019-05-26 | 100% | NA | NA | 5.556% |  |  | 2019-08-28 | 2020-06-23 | Sous-poste | Sous-poste | 2019-08-31 | 2020-06-24 |  | OK | Allemagne | Attente envoi derog | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 26 | 6 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2828532220 | 2019-09-20 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28285322 | NON-SPARES | 20 | 1 | RTN | A27912401006C11 | 0 | NON PRESENT INDUS | 28701 | 437392-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-11-11 | 100% | 100% | 2019-11-11 | 100% | NA | NA | 5.556% |  |  | 2019-12-13 | 2020-06-23 | Sous-poste | Sous-poste | 2019-12-18 | 2020-06-24 |  | OK | Allemagne | Attente envoi derog | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 26 | 6 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2826157310 | 2019-08-27 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28261573 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 27643 | 421049-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-10-21 | 100% | 100% | 2019-10-21 | 100% | NA | NA | 5.556% |  |  | 2021-03-02 | 2020-06-23 | Sous-poste | Sous-poste | 2021-03-05 | 2020-06-26 |  |  | Allemagne | Attente envoi derog | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 26 | 6 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2845110810 | 2020-04-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28451108 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 34350 | OF469803 | NA | NA | NA | NA | NA | 100% | 100% | 2020-04-03 | NA | 100% | 2020-06-23 | 100% | NA | NA | 100% |  |  | 2020-06-24 | 2020-06-24 | Sous-poste | Sous-poste | 2020-06-29 | 2020-06-29 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 26 | 6 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 322
2845712810 | 2020-04-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28457128 | NON-SPARES | 10 | 1 | CRIT | F9251360500100 | 1STR*11187 | NA | 34474 | 569860 | NA | NA | NA | NA | NA | 100% | 100% | 2020-06-18 | NA | 100% | 2020-06-23 | 100% | NA | NA | 100% |  |  | 2020-04-17 | 2020-06-25 | Sous-poste | Sous-poste | 2020-04-21 | 2020-06-29 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 26 | 6 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 521
2819138310 | 2020-01-15 | FABRICATION | SATAIR | PROTECTION CAP | 28191383 | NON-SPARES | 10 | 40 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 26133 | 388030-1 => 388030-40 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-04 | NA | 100% | 2020-05-04 | 100% | NA | NA | 5.556% |  |  | 2020-06-26 | 2020-06-26 | Sous-poste | Sous-poste | 2020-07-01 | 2020-07-01 |  | OK | Allemagne | Switch avec PO 28383477 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 26 | 6 | 2020 | 0.1 | 4.472 | 0.01118 | 4.4832 | NA | 0 | 0 | 5360
2831808510 | 2019-11-01 | FABRICATION | SATAIR | 22 | 28318085 | NON-SPARES | 10 | 1 | RTN | D9551002201795 | 0 | NON PRESENT INDUS | 30517 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-04 | 100% | 100% | 2020-05-05 | 100% | NA | NA | 5.556% |  |  | 2020-05-27 | 2020-06-26 | Sous-poste | Sous-poste | 2020-06-01 | 2020-07-01 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 26 | 6 | 2020 | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0 | 4490
2838629110 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 10 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518493-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629111 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 11 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518495-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629112 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 12 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518497-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629113 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 13 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518499-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629114 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 14 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518501-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629115 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 15 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518503-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629116 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 16 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518505-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629117 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 17 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518507-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629118 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 18 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518509-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
2838629119 | 2020-03-31 | FABRICATION | SATAIR | BUNDLE | 28386291 | NON-SPARES | 19 | 1 | RTN | D9000095029295 | 0 | NON PRESENT INDUS | 34377 | 518511-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-05-19 | NA | 100% | 2020-05-25 | 100% | NA | NA | 5.556% |  |  | 2020-04-10 | 2020-06-26 | Sous-poste | Sous-poste | 2020-04-15 | 2020-07-01 |  | OK | Allemagne | Manque 1CNT*00020 - Résa saisie | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 26 | 6 | 2020 | 0.6718 | 2.9382 | 0.293 | 3.2312 | COL | 0 | 0 | 225
284297661 | 2020-02-28 | FABRICATION | SATAIR | JACK | 28429766 | NON-SPARES | 1 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 33706 | LTE990040 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-10 | NA | 100% | 2020-06-16 | 100% | NA | NA | 5.556% |  |  | 2020-06-26 | 2020-06-26 | Sous-poste | Sous-poste | 2020-07-01 | 2020-07-01 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 26 | 6 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 1617
284297662 | 2020-02-28 | FABRICATION | SATAIR | JACK | 28429766 | NON-SPARES | 2 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 33706 | LTE990041 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-10 | NA | 100% | 2020-06-16 | 100% | NA | NA | 5.556% |  |  | 2020-06-26 | 2020-06-26 | Sous-poste | Sous-poste | 2020-07-01 | 2020-07-01 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 26 | 6 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 1617
284297663 | 2020-02-28 | FABRICATION | SATAIR | JACK | 28429766 | NON-SPARES | 3 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 33706 | LTE990042 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-10 | NA | 100% | 2020-06-16 | 100% | NA | NA | 5.556% |  |  | 2020-06-26 | 2020-06-26 | Sous-poste | Sous-poste | 2020-07-01 | 2020-07-01 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 26 | 6 | 2020 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0 | 1617
2796891250 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 50 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-06-30 | Sous-poste | Sous-poste | 2020-01-22 | 2020-07-03 |  |  | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 27 | 6 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
2796891260 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 60 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-06-30 | Sous-poste | Sous-poste | 2020-01-22 | 2020-07-03 |  |  | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 27 | 6 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
2843353110 | 2020-03-04 | FABRICATION | SATAIR | 313 | 28433531 | NON-SPARES | 10 | 1 | CRIT | WF406ACAAAAB | IS0032177M | NON PRESENT INDUS | 33000 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | TBD | 100% | 100% | 2020-06-19 | 100% | NA | NA | 5.556% |  |  | 2020-02-28 | 2020-07-03 | Sous-poste | Sous-poste | 2020-03-03 | 2020-07-06 |  | OK | Allemagne | STR reçue le 17/06 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 27 | 7 | 2020 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
2796891270 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 70 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-07-03 | Sous-poste | Sous-poste | 2020-01-22 | 2020-07-08 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 27 | 7 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0
2796891280 | 2019-10-04 | FABRICATION | SATAIR | 429 | 27968912 | NON-SPARES | 80 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 19400 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-30 | 100% | 100% | 2020-04-14 | 100% | NA | NA | 5.556% |  |  | 2020-01-17 | 2020-07-03 | Sous-poste | Sous-poste | 2020-01-22 | 2020-07-08 |  | OK | Allemagne | Pb carte capa LATE4000 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 27 | 7 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0
2839741110 | 2020-01-28 | HA/REVENTE | SATAIR | COVER ASSY | 28397411 | NON-SPARES | 10 | 1 | EXP | L9251394100000 | 1STR*10675 | NA | 32576 | 38663 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-27 | NA | 100% | 2020-07-06 | 100% | NA | NA | 100% |  |  | 2020-02-24 | 2020-07-08 | Sous-poste | Sous-poste | 2020-02-27 | 2020-07-13 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 28 | 7 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2839532610 | 2020-01-27 | HA/REVENTE | SATAIR | COVER ASSY | 28395326 | NON-SPARES | 10 | 6 | RTN | L9251394100000 | 1STR*10675 | NA | 32576 | 38663 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-27 | NA | 100% | 2020-07-06 | 100% | NA | NA | 100% |  |  | 2020-04-22 | 2020-07-08 | Sous-poste | Sous-poste | 2020-04-25 | 2020-07-13 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 28 | 7 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2829473610 | 2019-10-04 | FABRICATION | SATAIR | 429 | 28294736 | NON-SPARES | 10 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 28962 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | 100% | 100% | 2020-05-07 | 100% | NA | NA | 5.556% |  |  | 2021-03-02 | 2020-07-10 | Sous-poste | Sous-poste | 2021-03-05 | 2020-07-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 28 | 7 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0
2829473620 | 2019-10-04 | FABRICATION | SATAIR | 429 | 28294736 | NON-SPARES | 20 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 28962 | LTE990011 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | 100% | 100% | 2020-05-07 | 100% | NA | NA | 5.556% |  |  | 2021-03-02 | 2020-07-10 | Sous-poste | Sous-poste | 2021-03-05 | 2020-07-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 28 | 7 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0
2829473630 | 2019-10-04 | FABRICATION | SATAIR | 429 | 28294736 | NON-SPARES | 30 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 28962 | LTE990012 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | 100% | 100% | 2020-05-07 | 100% | NA | NA | 5.556% |  |  | 2021-03-02 | 2020-07-10 | Sous-poste | Sous-poste | 2021-03-05 | 2020-07-15 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 28 | 7 | 2020 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0
2844804910 | 2020-03-18 | HA/REVENTE | SATAIR | COVER ASSY | 28448049 | NON-SPARES | 10 | 3 | EXP | A9253115800000 | IS0031675S | NA | 34139 | L224907 | NA | NA | NA | NA | NA | 100% | 100% | 2020-07-09 | NA | 100% | 2020-07-09 | 33% | NA | NA | 33% |  |  | 2020-04-14 | 2020-07-13 | Sous-poste | Sous-poste | 2020-04-17 | 2020-07-16 |  |  | Allemagne | Blocage ERP côté LIS - Envoi partiel d'une pcs le 06/07/2020 - Réception qté 2 le 09/07 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 29 | 7 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2834416910 | 2019-11-29 | FABRICATION | SATAIR | 108 | 28344169 | NON-SPARES | 10 | 1 | CRIT | D9551010800195 | 0 | NON PRESENT INDUS | 31089 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-01 | 100% | 100% | 2020-07-06 | 100% | NA | NA | 5.556% |  |  | 2020-03-18 | 2020-07-17 | Sous-poste | Sous-poste | 2020-03-20 | 2020-07-21 |  |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 29 | 7 | 2020 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2842300410 | 2020-02-24 | FABRICATION | SATAIR | PLACARD SET | 28423004 | NON-SPARES | 10 | 1 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | NA | 519782-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-08 | NA | 100% | 2020-07-13 | 100% | NA | NA | 5.556% |  |  | 2020-05-20 | 2020-07-17 | Sous-poste | Sous-poste | 2020-05-25 | 2020-07-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 29 | 7 | 2020 | 0 | 0.205 | 0.0205 | 0.2255 | NA | 0 | 0
2826528310 | 2019-08-30 | FABRICATION | SATAIR | PROTECTION CAP | 28265283 | NON-SPARES | 10 | 50 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 28008 | 423382-1 => 423382-50 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-08 | NA | 100% | 2020-05-04 | 100% | NA | NA | 5.556% |  |  | 2020-07-08 | 2020-07-21 | Sous-poste | Sous-poste | 2020-07-13 | 2020-07-25 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2019 | 30 | 7 | 2020 | 0.125 | 5.59 | 0.01118 | 5.6012 | NA | 0 | 0
2828029010 | 2019-09-17 | FABRICATION | SATAIR | PROTECTION CAP | 28280290 | NON-SPARES | 10 | 40 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 28441 | 434653-1 => 434653-40 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-21 | NA | 100% | 2020-05-04 | 100% | NA | NA | 5.556% |  |  | 2020-07-21 | 2020-07-28 | Sous-poste | Sous-poste | 2020-07-24 | 2020-07-31 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 31 | 7 | 2020 | 0.1 | 4.472 | 0.01118 | 4.4832 | NA | 0 | 0
2845505610 | 2020-04-01 | FABRICATION | SATAIR | 45 | 28455056 | NON-SPARES | 10 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | 34348 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-24 | NA | 100% | 2020-07-27 | 100% | NA | NA | 5.556% |  |  | 2020-04-01 | 2020-07-29 | Sous-poste | Sous-poste | 2020-04-03 | 2020-07-31 |  | OK | Allemagne | Attente AR MECAHERS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 31 | 7 | 2020 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
490004110810 | 2020-07-22 | HA/REVENTE | STELIA | BARRE | 4900041108 | NON-SPARES | 10 | 1 | AOG | S9251302220000 | IS0013882S | NA | 35317 | E/G26-68614 | NA | NA | NA | NA | NA | 100% | 100% | 2020-07-24 | NA | 100% | 2020-07-30 | 100% | NA | NA | 100% |  |  | 2020-07-29 | 2020-07-29 | Sous-poste | Sous-poste | 2020-07-31 | 2020-07-31 |  | OK | Rochefort |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 31 | 7 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2847784610 | 2020-06-24 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28477846 | NON-SPARES | 10 | 2 | EXP | D9251095400000 | IS0053354S | NA | 35408 | 250066 | NA | NA | NA | NA | NA | 100% | 100% | 2020-07-24 | NA | 100% | 2020-08-06 | 100% | NA | NA | 100% |  |  | 2020-07-20 | 2020-08-06 | Sous-poste | Sous-poste | 2020-07-23 | 2020-08-11 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 | 32 | 8 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
450083338120 |  | FABRICATION | LATECOERE | 9000 | 4500833381 | NON-SPARES | 20 | 4 | RTN | A320EL050000-EPA | 0 | NON PRESENT INDUS | 33412 | LTE990028=>LTE990031 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-23 | NA | 100% | 2020-07-16 | 100% | NA | 1OUIOUI | 10.53% |  |  | 2020-06-10 | 2020-08-07 | Sous-poste | Sous-poste | 2020-06-15 | 2020-08-13 |  | OK | Labège | Manque ETEC 4STR*00982 (AR 24/07) => Non reçu (DA relancée le 30/07) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 32 | 8 | 2020 | 0.82 | 11.4 | 0.7125 | 12.1125 | COL | 0 | 0
2841549910 | 2020-02-18 | FABRICATION | SATAIR | PROTECTION CAP | 28415499 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 33389 | 504179-1 => 504179-10 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | NA | 100% | 2020-07-13 | 100% | NA | NA | 5.556% |  |  | 2020-08-10 | 2020-08-07 | Sous-poste | Sous-poste | 2020-08-13 | 2020-08-13 |  | OK | Allemagne | Manque 1COS*16104 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 32 | 8 | 2020 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2836905510 | 2019-12-23 | FABRICATION | SATAIR | PROTECTION CAP | 28369055 | NON-SPARES | 10 | 20 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 31898 | 491962-1 => 491962-20 |  |  |  | 100% | 0% | 50% | 100% | 2020-01-21 | NA | 100% | 2020-07-24 | 100% | NA | NA | 5.556% |  |  | 2020-11-13 | 2020-08-07 | Sous-poste | Sous-poste | 2020-11-19 | 2020-08-18 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 32 | 8 | 2020 | 0.05 | 2.236 | 0.01118 | 2.2472 | NA | 0 | 0
2846303210 | 2020-04-22 | HA/REVENTE | SATAIR/AIS | PLATE ASSY | 28463032 | NON-SPARES | 10 | 1 | AOG | F9251487400000 | 1STR*01468 | NA | 34731 | OF009130 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-03 | NA | 100% | 2020-08-04 | 100% | NA | NA | 100% |  |  | 2020-08-13 | 2020-08-07 | Sous-poste | Sous-poste | 2020-08-17 | 2020-08-17 |  | OK | Allemagne | Attente MAJ prix | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 32 | 8 | 2020 | #VALUE! | 0 | 0 | 0 | NA | 0 | 0
P28369205 |  | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | P2836920 | NON-SPARES | 5 | 4 | RTN | F9252030900000 | IS0032162M | NON PRESENT INDUS | 34731 | 519115-1 => 519115-4 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-24 | NA | 100% | 2020-07-27 | 100% | NA | NA | 5.556% |  |  | 2020-07-16 | 2020-08-10 | Sous-poste | Sous-poste | 2020-07-21 | 2020-08-12 |  | OK |  | Pièces transmises à Tanguy - Tanguy s'arrange avec Ludo pour expédier en CW33 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 33 | 8 | 2020 | 0 | 0.4 | 0.015 | 0.415 | NA | 0 | 0
P28369201 |  | HA/REVENTE | SATAIR/AIS | ANGLE | P2836920 | NON-SPARES | 1 | 8 | RTN | F9251445920000 | 1STR*01520 | NA | 34731 | OF008943 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-03 | NA | 100% | 2020-08-04 | 100% | NA | NA | 100% |  |  | 2020-07-16 | 2020-08-10 | Sous-poste | Sous-poste | 2020-07-21 | 2020-08-12 |  | OK |  | Pièces transmises à Tanguy - Tanguy s'arrange avec Ludo pour expédier en CW33 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 33 | 8 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
P28369202 |  | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | P2836920 | NON-SPARES | 2 | 4 | RTN | F9251485400000 | 1STR*10825 | NA | 34731 | OF008944 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-03 | NA | 100% | 2020-08-04 | 100% | NA | NA | 100% |  |  | 2020-07-16 | 2020-08-10 | Sous-poste | Sous-poste | 2020-07-21 | 2020-08-12 |  | OK |  | Pièces transmises à Tanguy - Tanguy s'arrange avec Ludo pour expédier en CW33 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 33 | 8 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
P28369203 |  | HA/REVENTE | SATAIR/AIS | PLATE ASSY | P2836920 | NON-SPARES | 3 | 4 | RTN | F9251487400000 | 1STR*01468 | NA | 34731 | OF008952 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-03 | NA | 100% | 2020-08-04 | 100% | NA | NA | 100% |  |  | 2020-07-16 | 2020-08-10 | Sous-poste | Sous-poste | 2020-07-21 | 2020-08-12 |  | OK |  | Pièces transmises à Tanguy - Tanguy s'arrange avec Ludo pour expédier en CW33 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 33 | 8 | 2020 | #VALUE! | 0 | NA | 0 | NA | 0 | 0
P28369204 |  | HA/REVENTE | SATAIR/AIS | PLATE ASSY | P2836920 | NON-SPARES | 4 | 4 | RTN | F9252029300000 | 1STR*11290 | NA | 34731 |  | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-10 | NA | 100% | 2020-08-11 | 0% | NA | NA | 0% |  |  | 2020-07-16 | 2020-08-12 | Sous-poste | Sous-poste | 2020-07-21 | 2020-08-14 |  | OK |  | Tanguy s'arrange avec Ludo pour faire la DS + expédier en CW33 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 33 | 8 | 2020 | #VALUE! | 0 | NA | 0 | NA | 0 | 0
490004046110 | 2020-02-07 | FABRICATION | STELIA | CÂBLE | 4900040461 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 33474 | 504346-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-07 | NA | 100% | 2020-03-30 | 100% | NA | OUI | 5.263% |  |  | 2020-04-20 | 2020-08-18 | Sous-poste | Sous-poste | 2020-04-23 | 2020-08-21 |  | OK | Rochefort | Manque matière autosoudeur (réception 03/08) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 34 | 8 | 2020 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0 | 245
490004051110 | 2020-02-12 | FABRICATION | STELIA | CÂBLE | 4900040511 | NON-SPARES | 10 | 2 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 33474 | 504287-1 => 504287-2 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-13 | NA | 100% | 2020-03-30 | 100% | NA | OUI | 5.263% |  |  | 2020-04-14 | 2020-08-18 | Sous-poste | Sous-poste | 2020-04-17 | 2020-08-21 |  | OK | Rochefort | Manque matière autosoudeur (réception 03/08) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 34 | 8 | 2020 | 0.41 | 2 | 0.1 | 2.1 | NA | 0 | 0 | 490
2847897910 | 2020-06-29 | HA/REVENTE | SATAIR/AIS | PLATE ASSY | 28478979 | NON-SPARES | 10 | 1 | AOG | F9252029300000 | 1STR*11290 | NA | 35093 | L230254 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-10 | NA | 100% | 2020-08-19 | 100% | NA | NA | 100% |  |  | 2020-07-02 | 2020-08-20 | Sous-poste | Sous-poste | 2020-07-06 | 2020-08-21 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 | 34 | 8 | 2020 | #VALUE! | 0 | NA | 0 | NA | 0 | 0
2820478220 | 2019-10-09 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28204782 | NON-SPARES | 20 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 26335 | 342258-1 |  |  |  | 100% | 0% | 50% | 100% | 2019-10-04 | 100% | 100% | 2020-08-03 | 100% | NA | NA | 5.556% |  |  | 2020-01-22 | 2020-08-25 | Sous-poste | Sous-poste | 2020-01-25 | 2020-08-28 |  | OK | Allemagne | Attente FIP - Informer Qualité (avant livraison derog) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 35 | 8 | 2020 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
68397402 | 2019-07-31 | FABRICATION | AD&S | 49 | 6839740 | NON-SPARES | 2 | 1 | RTN | MB042ACABAAA | IS0032206M | NON PRESENT INDUS | 28329 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-06-20 | 100% | NA | 1OUIOUI | 10.53% |  |  | 2019-10-04 | 2020-08-27 | Sous-poste | Sous-poste | 2019-10-09 | 2020-09-01 |  | OK | Allemagne | Attente confié - Litige commercial (Prix) -VU posé sur mon bureau avec EASA incluse | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 35 | 8 | 2020 | 0.205 | 2.39 | 0.5975 | 2.9875 | COL | 0 | 0
2846818510 | 2020-05-11 | FABRICATION | SATAIR | PLACARD SET | 28468185 | NON-SPARES | 10 | 5 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | 33388 | 518830-1 => 518830-5 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-07 | NA | 100% | 2020-08-20 | 100% | NA | NA | 5.556% |  |  | 2020-08-28 | 2020-08-28 | Sous-poste | Sous-poste | 2020-09-02 | 2020-09-02 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 35 | 8 | 2020 | 0 | 1.025 | 0.0205 | 1.0455 | NA | 0 | 0
2835585710 | 2019-12-12 | FABRICATION | SATAIR | PROTECTION CAP | 28355857 | NON-SPARES | 10 | 30 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 31512 | 490989-1 => 490989-30 |  |  |  | 100% | 0% | 50% | 100% | 2020-08-01 | NA | 100% | 2020-08-03 | 100% | NA | NA | 5.556% |  |  | 2020-09-01 | 2020-09-01 | Sous-poste | Sous-poste | 2020-09-04 | 2020-09-04 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 36 | 9 | 2020 | 0.075 | 3.354 | 0.01118 | 3.3652 | NA | 0 | 0
2845588510 | 2020-04-01 | HA/REVENTE | SATAIR | ENS. TOLE 3MCU | 28455885 | NON-SPARES | 10 | 2 | CRIT | F9251367800000 | 1STR*10672 | NA | 34474 | 529885 | NA | NA | NA | NA | NA | 100% | 100% | 2020-08-12 | NA | 100% | 2020-09-01 | 100% | NA | NA | 100% |  |  | 2020-04-16 | 2020-09-02 | Sous-poste | Sous-poste | 2020-04-20 | 2020-09-04 |  | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 36 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2848045910 | 2020-07-06 | FABRICATION | SATAIR | BUNDLE | 28480459 | NON-SPARES | 10 | 1 | RTN | V9253110000095B | 0 | NON PRESENT INDUS | NA | 519801-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-09 | NA | 100% | 2020-08-24 | 100% | NA | NA | 5.556% |  |  | 2020-09-08 | 2020-09-11 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-16 |  | OK | Allemagne | Attente MAJ prix | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 37 | 9 | 2020 | 0 | 0.1455 | 0.01455 | 0.16005 | COL | 0 | 0
2848045911 | 2020-07-06 | FABRICATION | SATAIR | BUNDLE | 28480459 | NON-SPARES | 11 | 1 | RTN | V9253110000095B | 0 | NON PRESENT INDUS | NA | 519802-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-09 | NA | 100% | 2020-08-24 | 100% | NA | NA | 5.556% |  |  | 2020-09-08 | 2020-09-11 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-16 |  | OK | Allemagne | Attente MAJ prix | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 37 | 9 | 2020 | 0 | 0.1455 | 0.01455 | 0.16005 | COL | 0 | 0
2848045912 | 2020-07-06 | FABRICATION | SATAIR | BUNDLE | 28480459 | NON-SPARES | 12 | 1 | RTN | V9253110000095B | 0 | NON PRESENT INDUS | NA | 519803-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-09 | NA | 100% | 2020-08-24 | 100% | NA | NA | 5.556% |  |  | 2020-09-08 | 2020-09-11 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-16 |  | OK | Allemagne | Attente MAJ prix | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 37 | 9 | 2020 | 0 | 0.1455 | 0.01455 | 0.16005 | COL | 0 | 0
2848045913 | 2020-07-06 | FABRICATION | SATAIR | BUNDLE | 28480459 | NON-SPARES | 13 | 1 | RTN | V9253110000095B | 0 | NON PRESENT INDUS | NA | 519804-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-09 | NA | 100% | 2020-08-24 | 100% | NA | NA | 5.556% |  |  | 2020-09-08 | 2020-09-11 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-16 |  | OK | Allemagne | Attente MAJ prix | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 37 | 9 | 2020 | 0 | 0.1455 | 0.01455 | 0.16005 | COL | 0 | 0
2848045914 | 2020-07-06 | FABRICATION | SATAIR | BUNDLE | 28480459 | NON-SPARES | 14 | 1 | RTN | V9253110000095B | 0 | NON PRESENT INDUS | NA | 519805-1 |  |  |  | 0% | 0% | 0% | 100% | 2020-07-09 | NA | 100% | 2020-08-24 | 100% | NA | NA | 5.556% |  |  | 2020-09-08 | 2020-09-11 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-16 |  | OK | Allemagne | Attente MAJ prix | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 37 | 9 | 2020 | 0 | 0.1455 | 0.01455 | 0.16005 | COL | 0 | 0
2848223510 | 2020-07-13 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28482235 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 35919 | 247843 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-03 | NA | 100% | 2020-09-14 | 100% | NA | NA | 100% |  |  | 2020-08-05 | 2020-09-15 | Sous-poste | Sous-poste | 2020-08-08 | 2020-09-18 |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2847485210 | 2020-06-10 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28474852 | NON-SPARES | 10 | 4 | EXP | D9251095600000 | IS0053509S | NA | 35345 | 250067 - DMF 22/07/2020 | NA | NA | NA | NA | NA | 100% | 100% | 2020-07-24 | NA | 100% | 2020-09-16 | 100% | NA | NA | 100% |  |  | 2020-09-17 | 2020-09-17 | Sous-poste | Sous-poste | 2020-09-22 | 2020-09-22 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
P28466201 | 2020-07-10 | HA/REVENTE | AIS | DIAPHRAGME | P2846620 | NON-SPARES | 1 | 1 | RTN | MD501-211102-01A | 1STR*10647 | NA | 35859 | OF220795 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-14 | NA | 100% | 2020-09-15 | 100% | NA | OUI | 50% |  |  | 2020-08-05 | 2020-09-17 | Sous-poste | Sous-poste | 2020-08-10 | 2020-09-22 |  |  |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P28466202 | 2020-07-10 | HA/REVENTE | AIS | DIAPHRAGME | P2846620 | NON-SPARES | 2 | 1 | RTN | MD501-211102-02A | 1STR*10648 | NA | 35859 |  | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | OUI | 0% |  |  | 2020-09-14 | 2020-09-17 | Sous-poste | Sous-poste | 2020-09-17 | 2020-09-22 |  |  |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2848479410 | 2020-07-21 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28484794 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 36076 | 250066 - DMF 22/07/2020 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-10 | NA | 100% | 2020-09-16 | 100% | NA | NA | 100% |  |  | 2020-08-14 | 2020-09-18 | Sous-poste | Sous-poste | 2020-08-19 | 2020-09-23 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849091510 | 2020-08-19 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28490915 | NON-SPARES | 10 | 1 | RTN | D9251095400000 | IS0053354S | NA | 36076 | 250066 - DMF 22/07/2020 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-10 | NA | 100% | 2020-09-16 | 100% | NA | NA | 100% |  |  | 2020-09-08 | 2020-09-18 | Sous-poste | Sous-poste | 2020-09-11 | 2020-09-23 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 38 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
68397408 | 2019-07-31 | FABRICATION | AD&S | 42 | 6839740 | NON-SPARES | 8 | 1 | RTN | MB038ADAAAAB | IS0032200M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-09-25 | Sous-poste | Sous-poste | 2019-10-09 | 2020-09-30 |  | OK | Allemagne | Ok prêt | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2020 | 0.205 | 1.5116 | 0.3779 | 1.8895 | COL | 0 | 0
68397409 | 2019-07-31 | FABRICATION | AD&S | 47 | 6839740 | NON-SPARES | 9 | 1 | RTN | MB040ADAAAAB | IS0032202M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-09-25 | Sous-poste | Sous-poste | 2019-10-09 | 2020-09-30 |  | OK | Allemagne | Ok prêt | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2020 | 0.205 | 2.96 | 0.74 | 3.7 | COL | 0 | 0
683974010 | 2019-07-31 | FABRICATION | AD&S | 48 | 6839740 | NON-SPARES | 10 | 1 | RTN | MB041ADAAAAB | IS0032205M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-09-25 | Sous-poste | Sous-poste | 2019-10-09 | 2020-09-30 |  | OK | Allemagne | Ok prêt | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2020 | 0.205 | 2.96 | 0.74 | 3.7 | COL | 0 | 0
68397401 | 2019-07-31 | FABRICATION | AD&S | 32 | 6839740 | NON-SPARES | 1 | 1 | RTN | MB036ACAAAAC | IS0032198M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-09-25 | Sous-poste | Sous-poste | 2019-10-10 | 2020-09-30 |  | OK | Allemagne | TEST EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2020 | 0.36 | 4.6255 | 1.1564 | 5.7819 | COL | 0 | 0
68428491 | 2019-09-16 | FABRICATION | AD&S | 11 | 6842849 | NON-SPARES | 1 | 1 | RTN | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 28871 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-25 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-11-26 | 2020-09-25 | Sous-poste | Sous-poste | 2019-11-29 | 2020-09-30 |  | OK | Allemagne | Attente confié - TEST EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 39 | 9 | 2020 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
68428492 | 2019-09-16 | FABRICATION | AD&S | 46 | 6842849 | NON-SPARES | 2 | 1 | RTN | MB039ACAAAAB | IS0032201M | NON PRESENT INDUS | 28871 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-25 | 100% | 100% | 2020-09-14 | 100% | NA | OUI | 5.263% |  |  | 2019-11-26 | 2020-09-25 | Sous-poste | Sous-poste | 2019-11-29 | 2020-09-30 |  | OK | Allemagne | Attente confié - TEST EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 39 | 9 | 2020 | 0.205 | 5.6343 | 1.4086 | 7.0429 | COL | 0 | 0
2831322810 | 2019-10-24 | FABRICATION | SATAIR | PROTECTION CAP | 28313228 | NON-SPARES | 10 | 40 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 29975 | 475801-1 => 475801-40 |  |  |  | 100% | 0% | 50% | 100% | 2020-06-29 | NA | 100% | 2020-07-06 | 100% | NA | NA | 5.556% |  |  | 2020-07-29 | 2020-09-30 | Sous-poste | Sous-poste | 2020-08-03 | 2020-10-05 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 40 | 9 | 2020 | 0.1 | 4.472 | 0.01118 | 4.4832 | NA | 0 | 0
2846624910 | 2020-05-04 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28466249 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 34675 | OR18761 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-26 | NA | 100% | 2020-09-28 | 100% | NA | NA | 100% |  |  | 2020-09-30 | 2020-09-30 | Sous-poste | Sous-poste | 2020-10-05 | 2020-10-05 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 40 | 9 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2848479510 | 2020-07-21 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28484795 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 36076 |  | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-04 | NA | 100% | 2020-09-07 | 100% | NA | NA | 100% |  |  | 2020-08-14 | 2020-10-01 | Sous-poste | Sous-poste | 2020-08-19 | 2020-10-06 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 40 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2847116310 | 2020-05-22 | FABRICATION | SATAIR | 117 | 28471163 | NON-SPARES | 10 | 1 | AOG | D9550011700295 | IS0032071M | NON PRESENT INDUS | 35090 | LTE990161 |  |  |  | 100% | 0% | 50% | 100% | 2020-09-17 | NA | 100% | 2020-09-28 | 100% | NA | NA | 5.556% |  |  | 2020-08-25 | 2020-10-01 | Sous-poste | Sous-poste | 2020-08-27 | 2020-10-03 |  | OK | Allemagne | Attente RFQ HA | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 40 | 10 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2848987710 | 2020-08-17 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28489877 | NON-SPARES | 10 | 1 | RTN | D9251095600000 | IS0053509S | NA | 36464 | 426016 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-17 | NA | 100% | 2020-09-29 | 100% | NA | NA | 100% |  |  | 2020-09-07 | 2020-10-01 | Sous-poste | Sous-poste | 2020-09-10 | 2020-10-06 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 40 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
68428241 | 2019-09-17 | FABRICATION | AD&S | 31 | 6842824 | NON-SPARES | 1 | 1 | RTN | MB035ACAAAAC | IS0032197M | NON PRESENT INDUS | 30172 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-10 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-11-26 | 2020-10-02 | Sous-poste | Sous-poste | 2019-11-29 | 2020-10-07 |  | OK | Allemagne | Contrôle + test EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 40 | 10 | 2020 | 0.36 | 4.1408 | 1.0352 | 5.176 | COL | 0 | 0
682405910 | 2019-02-12 | FABRICATION | AD&S | 12 | 6824059 | NON-SPARES | 10 | 1 | RTN | MB170ACAAAAB | IS0032212M | NON PRESENT INDUS | 22399 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 2019-09-20 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-03-13 | 2020-10-02 | Sous-poste | Sous-poste | 2019-03-18 | 2020-10-07 |  | OK | Allemagne | Attente confié - Contrôle + test EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2019 | 40 | 10 | 2020 | 0.205 | 8.3333 | 2.0833 | 10.4166 | COL | 0 | 0
68397405 | 2019-07-31 | FABRICATION | AD&S | 15 | 6839740 | NON-SPARES | 5 | 1 | RTN | MB032ADAAAAB | IS0032194M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-10-02 | Sous-poste | Sous-poste | 2019-10-09 | 2020-10-07 |  | OK | Allemagne | Attente confié - Contrôle + test EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 40 | 10 | 2020 | 0.51 | 7.1148 | 1.7787 | 8.8935 | COL | 0 | 0
68397403 | 2019-07-31 | FABRICATION | AD&S | 39 | 6839740 | NON-SPARES | 3 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 28332 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-10-02 | Sous-poste | Sous-poste | 2019-10-09 | 2020-10-07 |  | OK | Allemagne | Attente confié - Contrôle + test EC LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 40 | 10 | 2020 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
2846357610 | 2020-04-23 | FABRICATION | SATAIR | 117 | 28463576 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 34595 | LTE990159 |  |  |  | 100% | 0% | 50% | 100% | 2020-09-17 | NA | 100% | 2020-09-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-16 | 2020-10-02 | Sous-poste | Sous-poste | 2020-09-21 | 2020-10-07 |  | OK | Allemagne | Attente RFQ HA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 40 | 10 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2846357610 | 2020-04-23 | FABRICATION | SATAIR | 117 | 28463576 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 34595 | LTE990160 |  |  |  | 100% | 0% | 50% | 100% | 2020-09-17 | NA | 100% | 2020-09-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-16 | 2020-10-02 | Sous-poste | Sous-poste | 2020-09-21 | 2020-10-07 |  | OK | Allemagne | Attente RFQ HA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 | 40 | 10 | 2020 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2850137710 | 2020-09-29 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | 28501377 | NON-SPARES | 10 | 1 | AOG | F9252030900000 | IS0032162M | NON PRESENT INDUS | STOCK | 522188 |  |  |  | 0% | 0% | 0% | 100% | 2020-09-29 | NA | 100% | 2020-10-01 | 100% | NA | NA | 5.556% |  |  | 2020-09-30 | 2020-10-05 | Sous-poste | Sous-poste | 2020-10-02 | 2020-10-07 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 41 | 10 | 2020 | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
490004119310 | 2020-08-31 | HA/REVENTE | STELIA | PILLAR | 4900041193 | NON-SPARES | 10 | 5 | RTN | F0003057821000 | 1QME*17052 | NA | 36667 | OF004429 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-28 | NA | 100% | 2020-10-08 | 100% | NA | NA | 100% |  |  | 2020-10-09 | 2020-10-07 | Sous-poste | Sous-poste | 2020-10-14 | 2020-10-10 |  | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 41 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
68397407 | 2019-07-31 | FABRICATION | AD&S | 41 | 6839740 | NON-SPARES | 7 | 1 | RTN | MB037ADAAAAB | IS0032199M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 99% | NA | OUI | 5.211% |  |  | 2019-10-04 | 2020-10-13 | Sous-poste | Sous-poste | 2019-10-09 | 2020-10-16 |  | OK | Allemagne | Attente ré appro confié | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 42 | 10 | 2020 | 0.205 | 1.5116 | 0.3779 | 1.8895 | COL | 0 | 0
2842421710 | 2020-02-25 | HA/REVENTE | SATAIR | PLATE ASSY-CLOSING | 28424217 | NON-SPARES | 10 | 6 | RTN | F9251338800000 | 1STR*11274 | NA | 33536 | I146739 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-23 | NA | 100% | 2020-10-12 | 100% | NA | NA | 100% |  |  | 2020-10-14 | 2020-10-14 | Sous-poste | Sous-poste | 2020-10-19 | 2020-10-19 |  | OK | Allemagne | Offre MECACHROME en attente de validation Étienne | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 42 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2848657710 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486577 | NON-SPARES | 10 | 1 | AOG | V9253120000095 | 0 | NON PRESENT INDUS | 36661 | 521107-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-07 | NA | 100% | 2020-10-09 | 100% | NA | NA | 5.556% |  |  | 2020-07-30 | 2020-10-15 | Sous-poste | Sous-poste | 2020-08-03 | 2020-10-19 | Early collab | OK | Allemagne | Attente données SSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 42 | 10 | 2020 | 0.036 | 1.06 | 0.106 | 1.166 | COL | 0 | 0
2848658310 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486583 | NON-SPARES | 10 | 1 | AOG | V9253110000097 | 0 | NON PRESENT INDUS | 36663 | 521117-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-07 | NA | 100% | 2020-10-09 | 100% | NA | NA | 5.556% |  |  | 2020-07-30 | 2020-10-15 | Sous-poste | Sous-poste | 2020-08-03 | 2020-10-19 | Early collab | OK | Allemagne | Attente données SSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 42 | 10 | 2020 | 0.0735 | 1.55 | 0.15 | 1.7 | COL | 0 | 0
2848657910 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486579 | NON-SPARES | 10 | 1 | CRIT | V9253120000095 | 0 | NON PRESENT INDUS | 36661 | 521109-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-07 | NA | 100% | 2020-10-09 | 100% | NA | NA | 5.556% |  |  | 2020-08-05 | 2020-10-15 | Sous-poste | Sous-poste | 2020-08-07 | 2020-10-19 | Early collab | OK | Allemagne | Attente données SSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 42 | 10 | 2020 | 0.036 | 1.06 | 0.106 | 1.166 | COL | 0 | 0
2848658410 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486584 | NON-SPARES | 10 | 1 | CRIT | V9253110000097 | 0 | NON PRESENT INDUS | 36663 | 521119-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-07 | NA | 100% | 2020-10-09 | 100% | NA | NA | 5.556% |  |  | 2020-08-05 | 2020-10-15 | Sous-poste | Sous-poste | 2020-08-07 | 2020-10-19 | Early collab | OK | Allemagne | Attente données SSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 42 | 10 | 2020 | 0.0735 | 1.55 | 0.15 | 1.7 | COL | 0 | 0
2842466810 | 2020-02-25 | FABRICATION | SATAIR | 441 | 28424668 | NON-SPARES | 10 | 1 | RTN | A95500441000AA | 0 | NON PRESENT INDUS | 27864 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-09-03 | 100% | 100% | 2020-09-28 | 100% | NA | NA | 5.556% |  |  | 2020-05-26 | 2020-10-20 | Sous-poste | Sous-poste | 2020-05-29 | 2020-10-22 |  | OK | Allemagne | DS N°425925 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 43 | 10 | 2020 | 0.205 | 5.6471 | 1.4118 | 7.0589 | COL | 0 | 0
2848658010 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486580 | NON-SPARES | 10 | 1 | AOG | V9253120000095 | 0 | NON PRESENT INDUS | 36661 | 521111-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-08-26 | 2020-10-23 | Sous-poste | Sous-poste | 2020-08-28 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.036 | 1.06 | 0.106 | 1.166 | COL | 0 | 0
2848658011 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486580 | NON-SPARES | 11 | 1 | AOG | V9253120000095 | 0 | NON PRESENT INDUS | 36661 | 521113-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-08-26 | 2020-10-23 | Sous-poste | Sous-poste | 2020-08-28 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.036 | 1.06 | 0.106 | 1.166 | COL | 0 | 0
2848658610 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486586 | NON-SPARES | 10 | 1 | AOG | V9253110000097 | 0 | NON PRESENT INDUS | 36663 | 521121-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-08-26 | 2020-10-23 | Sous-poste | Sous-poste | 2020-08-28 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.0735 | 1.55 | 0.15 | 1.7 | COL | 0 | 0
2848658611 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486586 | NON-SPARES | 11 | 1 | AOG | V9253110000097 | 0 | NON PRESENT INDUS | 36663 | 521123-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-08-26 | 2020-10-23 | Sous-poste | Sous-poste | 2020-08-28 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.0735 | 1.55 | 0.15 | 1.7 | COL | 0 | 0
2848658110 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486581 | NON-SPARES | 10 | 1 | AOG | V9253120000095 | 0 | NON PRESENT INDUS | 36661 | 521115-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-09-25 | 2020-10-23 | Sous-poste | Sous-poste | 2020-09-29 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.036 | 1.06 | 0.106 | 1.166 | COL | 0 | 0
2848658710 | 2020-07-29 | FABRICATION | SATAIR | BUNDLE | 28486587 | NON-SPARES | 10 | 1 | AOG | V9253110000097 | 0 | NON PRESENT INDUS | 36663 | 521125-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-09 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-09-25 | 2020-10-23 | Sous-poste | Sous-poste | 2020-09-29 | 2020-10-27 | Early collab | OK | Allemagne | Attente données SSD - Ctrl en retard | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 43 | 10 | 2020 | 0.0735 | 1.55 | 0.15 | 1.7 | COL | 0 | 0
2833399410 | 2019-11-18 | FABRICATION | SATAIR | PROTECTION CAP | 28333994 | NON-SPARES | 10 | 40 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 30535 | 481798-1 => 481798-40 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-14 | NA | 100% | 2020-10-15 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-10-23 | Sous-poste | Sous-poste | 2020-10-01 | 2020-11-03 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 | 43 | 10 | 2020 | 0.1 | 4.472 | 0.01118 | 4.4832 | NA | 0 | 0
2835850310 | 2019-12-16 | FABRICATION | SATAIR | PROTECTION CAP | 28358503 | NON-SPARES | 10 | 20 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 31512 | 490990-1 => 490990-20 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-14 | NA | 100% | 2020-10-19 | 100% | NA | NA | 5.556% |  |  | 2020-11-06 | 2020-10-23 | Sous-poste | Sous-poste | 2020-11-11 | 2020-11-02 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2019 | 43 | 10 | 2020 | 0.05 | 2.236 | 0.01118 | 2.2472 | NA | 0 | 0
2848947710 | 2020-08-17 | FABRICATION | SATAIR | 117 | 28489477 | NON-SPARES | 10 | 1 | AOG | D9550011700195 | 0 | NON PRESENT INDUS | 36652 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-22 | NA | 100% | 2020-10-20 | 99% | NA | NA | 5.5% |  |  | 2020-08-27 | 2020-10-23 | Sous-poste | Sous-poste | 2020-08-31 | 2020-10-27 |  | OK | Allemagne | À LAB le 23/10 pour test + contrôle - PLACARD à monter à réception | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 43 | 10 | 2020 | 0 | 4.08 | 1.02 | 5.1 | COL | 0 | 0
2850899110 | 2020-10-22 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28508991 | NON-SPARES | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 38167 | 252256 | NA | NA | NA | NA | NA | 100% | 100% | 2020-10-30 | NA | 100% | 2020-11-02 | 100% | NA | NA | 100% |  |  | 2020-10-20 | 2020-10-29 | Sous-poste | Sous-poste | 2020-10-22 | 2020-11-02 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 44 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2847485110 | 2020-06-10 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28474851 | NON-SPARES | 10 | 4 | EXP | D9251095400000 | IS0053354S | NA | 35345 |  | NA | NA | NA | NA | NA | 100% | 0% | 2020-07-24 | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-09-17 | 2020-10-29 | Sous-poste | Sous-poste | 2020-09-22 | 2020-11-03 |  |  | Allemagne | Ligne réactivée suite NC | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 | 44 | 10 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2850795910 | 2020-10-20 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28507959 | NON-SPARES | 10 | 4 | CRIT | D9251095600000 | IS0053509S | NA | 38056 |  | NA | NA | NA | NA | NA | 100% | 100% | 2020-10-26 | NA | 100% | 2020-11-03 | 0% | NA | NA | 0% |  |  | 2020-10-19 | 2020-11-03 | Sous-poste | Sous-poste | 2020-10-21 | 2020-11-05 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 45 | 11 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838603110 | 2020-01-16 | FABRICATION | SATAIR | PROTECTION CAP | 28386031 | NON-SPARES | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 32404 | 496645-1 => 496645-10 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-11 | NA | 100% | 2020-10-11 | 100% | NA | NA | 5.556% |  |  | 2020-11-06 | 2020-11-06 | Sous-poste | Sous-poste | 2020-11-12 | 2020-11-12 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 45 | 11 | 2020 | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
284673201 | 2020-05-07 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 1 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-03 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-06 | Sous-poste | Sous-poste | 2020-08-20 | 2020-11-10 | Early collab | OK | Allemagne | Sortir KLS en DS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 45 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
490004120010 | 2020-08-31 | HA/REVENTE | STELIA | GOUPILLE | 4900041200 | NON-SPARES | 10 | 11 | RTN | S9251186120000 | 3STR*01339 | NA | 36668 |  | NA | NA | NA | NA | NA | 100% | 100% | 2020-11-02 | NA | 100% | 2020-11-09 | 0% | NA | NA | 0% |  |  | 2020-10-09 | 2020-11-10 | Sous-poste | Sous-poste | 2020-10-14 | 2020-11-13 |  |  | Rechefort | Expédition faite par EAU pdt mes vacs | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 46 | 11 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
683974011 | 2019-07-31 | FABRICATION | AD&S | 37 | 6839740 | NON-SPARES | 11 | 1 | RTN | MB137ADAAAAC | IS0032210M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-11-12 | Sous-poste | Sous-poste | 2019-10-09 | 2020-11-17 |  | OK | Allemagne | Attente ré appro confié => Reçu le 23/10/2020 - Envoyé à LAB pour Ctrl + test le 02/11/2020 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 46 | 11 | 2020 | 0.205 | 1.43 | 0.3575 | 1.7875 | COL | 0 | 0
284673202 | 2020-05-08 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 2 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-03 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-13 | Sous-poste | Sous-poste | 2020-08-20 | 2020-11-17 | Early collab | OK | Allemagne | Sortir KLS en DS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 46 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
2848662010 | 2020-07-29 | FABRICATION | SATAIR | SHEET ASSY | 28486620 | NON-SPARES | 10 | 1 | AOG | F9252035500000 | IS0059353M | NON PRESENT INDUS | 36247 | 520461-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-02 | NA | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-08-03 | 2020-11-13 | Sous-poste | Sous-poste | 2020-08-05 | 2020-11-17 | Early collab | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 46 | 11 | 2020 | 0 | 0.1 | 0.015 | 0.115 | COL | 0 | 0
2848662110 | 2020-07-29 | FABRICATION | SATAIR | SHEET ASSY | 28486621 | NON-SPARES | 10 | 1 | AOG | F9252035500000 | IS0059353M | NON PRESENT INDUS | 36247 | 520462-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-02 | NA | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-13 | Sous-poste | Sous-poste | 2020-08-20 | 2020-11-17 | Early collab | OK | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 46 | 11 | 2020 | 0 | 0.1 | 0.015 | 0.115 | COL | 0 | 0
2848426410 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484264 | NON-SPARES | 10 | 1 | AOG | V9253110000095A | 0 | NON PRESENT INDUS | 37849 | 522484 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-10-22 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 - NC prod => 4CNT*00133 à commander | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL | 0 | 0
2848426410 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484264 | NON-SPARES | 10 | 1 | AOG | V9253110000095A | 0 | NON PRESENT INDUS | 37849 | 522486 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-10-22 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 - NC prod => 4CNT*00133 à commander | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL | 0 | 0
2848426410 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484264 | NON-SPARES | 10 | 1 | AOG | V9253110000095A | 0 | NON PRESENT INDUS | 37849 | 522488 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-10-22 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 - NC prod => 4CNT*00133 à commander | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL | 0 | 0
2848426410 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484264 | NON-SPARES | 10 | 1 | AOG | V9253110000095A | 0 | NON PRESENT INDUS | 37849 | 522490 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-10-22 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 - NC prod => 4CNT*00133 à commander | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL | 0 | 0
2848426410 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484264 | NON-SPARES | 10 | 1 | AOG | V9253110000095A | 0 | NON PRESENT INDUS | 37849 | 522492 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-10-22 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 - NC prod => 4CNT*00133 à commander | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL | 0 | 0
2848426310 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484263 | NON-SPARES | 10 | 1 | AOG | V9253100000095A | 0 | NON PRESENT INDUS | 37849 | 522607 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-11-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL | 0 | 0
2848426310 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484263 | NON-SPARES | 10 | 1 | AOG | V9253100000095A | 0 | NON PRESENT INDUS | 37849 | 522609 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-11-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL | 0 | 0
2848426310 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484263 | NON-SPARES | 10 | 1 | AOG | V9253100000095A | 0 | NON PRESENT INDUS | 37849 | 522611 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-11-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL | 0 | 0
2848426310 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484263 | NON-SPARES | 10 | 1 | AOG | V9253100000095A | 0 | NON PRESENT INDUS | 37849 | 522613 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-11-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL | 0 | 0
2848426310 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484263 | NON-SPARES | 10 | 1 | AOG | V9253100000095A | 0 | NON PRESENT INDUS | 37849 | 522615 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-11-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-11-18 | Early collab | OK | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL | 0 | 0
490004120210 | 2020-08-31 | FABRICATION | STELIA | 63 | 4900041202 | NON-SPARES | 10 | 1 | RTN | S9550006320095 | 0 | NON PRESENT INDUS | 37004 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-13 | NA | 100% | 2020-11-12 | 100% | NA | OUI | 5.263% |  |  | 2020-09-14 | 2020-11-16 | Sous-poste | Sous-poste | 2020-09-17 | 2020-11-19 |  |  | Rechefort | BDO saisie le 14/09/2020 - Attente cumul sécurisé - Attente réception étiquette commerciale | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 47 | 11 | 2020 | 0 | 2.87 | 0.7175 | 3.5875 | COL | 0 | 0
2851571610 | 2020-11-16 | FABRICATION | SATAIR | PLACARD | 28515716 | NON-SPARES | 10 | 1 | AOG | F1131170400000 | 0 | NON PRESENT INDUS | NA | 523012 |  |  |  | 0% | 0% | 0% | 100% | 2020-11-18 | NA | 100% | 2020-11-18 | 0% | NA | NA | 0% |  |  | 2020-11-17 | 2020-11-17 | Sous-poste | Sous-poste | 2020-11-19 | 2020-11-19 |  |  | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 47 | 11 | 2020 | 0 | 0.205 | 0.02 | 0.225 | NA | 0 | 0
2848229510 | 2020-07-13 | FABRICATION | SATAIR | 45 | 28482295 | NON-SPARES | 10 | 1 | AOG | D9551004500495 | 0 | NON PRESENT INDUS | 35920 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-13 | NA | 100% | 2020-10-20 | 100% | NA | NA | 5.556% |  |  | 2020-08-25 | 2020-11-18 | Sous-poste | Sous-poste | 2020-08-27 | 2020-11-20 |  | OK | Allemagne | Manque 1PRO*10084 - Prêt en zone mise à dispo | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 47 | 11 | 2020 | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
68397404 | 2019-07-31 | FABRICATION | AD&S | 25 | 6839740 | NON-SPARES | 4 | 1 | RTN | MB034ACAEAAA | IS0032196M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-11-19 | Sous-poste | Sous-poste | 2019-10-09 | 2020-11-24 |  | OK | Allemagne | 3 FIP endommagés en prod. => Qté 2 reçus le 03/11/2020 + qté 1 reçu le 09/11 - Expédié à LAB pour test le 16/11 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 47 | 11 | 2020 | 0.205 | 2.023 | 0.50575 | 2.5288 | COL | 0 | 0
284673203 | 2020-05-09 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 3 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-03 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-20 | Sous-poste | Sous-poste | 2020-08-20 | 2020-11-24 | Early collab | OK | Allemagne | Sortir KLS en DS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 47 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
284673204 | 2020-05-10 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 4 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-03 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-20 | Sous-poste | Sous-poste | 2020-08-20 | 2020-11-24 | Early collab | OK | Allemagne | Sortir KLS en DS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 47 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
2849261510 | 2020-08-24 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28492615 | NON-SPARES | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 36619 | OF422768 | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-03 | NA | 100% | 2020-11-18 | 100% | NA | NA | 100% |  |  | 2020-11-23 | 2020-11-23 | Sous-poste | Sous-poste | 2020-11-26 | 2020-11-26 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 48 | 11 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004138510 | 2020-10-27 | HA/REVENTE | STELIA | BARRE | 4900041385 | NON-SPARES | 10 | 5 | RTN | S9251302620000 | 1QEL*10072 | NA | 38243 | 1383711 | NA | NA | NA | NA | NA | 100% | 100% | 2020-11-17 | NA | 100% | 2020-11-23 | 100% | NA | NA | 100% |  |  | 2020-11-11 | 2020-11-27 | Sous-poste | Sous-poste | 2020-11-16 | 2020-12-02 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 48 | 11 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
284673205 | 2020-05-11 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 5 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-27 | Sous-poste | Sous-poste | 2020-08-20 | 2020-12-01 | Early collab | OK | Allemagne | Sortir KLS en DS - Manque KLS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 48 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
284673206 | 2020-05-12 | FABRICATION | SATAIR | 30 | 28467320 | NON-SPARES | 6 | 1 | AOG | D9551003000195 | 0 | NON PRESENT INDUS | 35085 | LTE990006 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-19 | 100% | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-08-18 | 2020-11-30 | Sous-poste | Sous-poste | 2020-08-20 | 2020-12-02 | Early collab |  | Allemagne | Sortir KLS en DS - Manque KLS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 | 49 | 11 | 2020 | 0.205 | 10.43 | 2.6 | 13.03 | COL | 0 | 0
2848230910 | 2020-07-13 | HA/REVENTE | SATAIR | PLATE ASSY | 28482309 | NON-SPARES | 10 | 8 | RTN | A9251152500000 | IS0031658S | NA | 35921 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-09-14 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-03 | 2020-12-03 | Sous-poste | Sous-poste | 2020-12-08 | 2020-12-08 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 49 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
P28553201 |  | FABRICATION | AIS | 265 | P2855320 | NON-SPARES | 1 | 1 | RTN | MD504-311101-01B | 0 | NON PRESENT INDUS | 36279 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-30 | NA | 100% | 2020-12-01 | 100% | NA | OUI | 5.263% |  |  | 2020-11-17 | 2020-12-03 | Sous-poste | Sous-poste | 2020-11-20 | 2020-12-04 | Early collab | OK |  | Complément matière en YP09 => 5118694 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 49 | 12 | 2020 | 0.205 | 5 | 1 | 6 | COL | 0 | 0
68397406 | 2019-07-31 | FABRICATION | AD&S | 21 | 6839740 | NON-SPARES | 6 | 1 | RTN | MB033ADACAAB | IS0032195M | NON PRESENT INDUS | 28412 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-19 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-10-04 | 2020-12-03 | Sous-poste | Sous-poste | 2019-10-09 | 2020-12-08 |  | OK | Allemagne | Réception 4PRO*00037 le 16/11 => YP09 5118767 - Expé to LAB 30/11/2020 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 49 | 12 | 2020 | 0.36 | 2.1766 | 0.54415 | 2.7208 | COL | 0 | 0
2848231910 | 2020-07-13 | HA/REVENTE | SATAIR | BRACKET | 28482319 | NON-SPARES | 10 | 8 | RTN | A9252496620200 | IS0053087S | NA | 35924 | OF010720 | NA | NA | NA | NA | NA | 100% | 100% | 2020-11-17 | NA | 100% | 2020-12-04 | 100% | NA | NA | 100% |  |  | 2020-12-03 | 2020-12-03 | Sous-poste | Sous-poste | 2020-12-08 | 2020-12-08 | Early collab | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 49 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
68428493 | 2019-09-16 | FABRICATION | AD&S | 34 | 6842849 | NON-SPARES | 3 | 1 | RTN | MB136ABAAAAD | IS0032209M | NON PRESENT INDUS | 28871 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2020-02-25 | 100% | 100% | 2020-09-07 | 100% | NA | OUI | 5.263% |  |  | 2019-11-26 | 2020-12-03 | Sous-poste | Sous-poste | 2019-11-29 | 2020-12-04 |  | OK | Allemagne | TEST to do LAB - Manque platine M8753623500000 => Reçue le 26/11 => Départ LAB le 26/11 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2019 | 49 | 12 | 2020 | 0.205 | 3.2522 | 0.81305 | 4.0653 | COL | 0 | 0
490004134810 | 2020-10-19 | HA/REVENTE | STELIA | SUPPLATE FRONT 22VU | 4900041348 | NON-SPARES | 10 | 1 | RTN | S9252502200000 | 4STR*01412 | NA | 37985 | OF004077 | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-03 | NA | 100% | 2020-12-03 | 100% | NA | NA | 100% |  |  | 2020-11-23 | 2020-12-07 | Sous-poste | Sous-poste | 2020-11-26 | 2020-12-10 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 50 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2850479410 | 2020-10-13 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28504794 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 37834 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-03 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-11-11 | 2020-12-08 | Sous-poste | Sous-poste | 2020-11-16 | 2020-12-11 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 50 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2847842010 | 2020-06-25 | FABRICATION | SATAIR | 510 | 28478420 | NON-SPARES | 10 | 1 | AOG | A9550051000296 | IS0031992M | NON PRESENT INDUS | 35607 | LTE990007 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-29 | 100% | 100% | 2020-12-02 | 99% | NA | NA | 5.5% |  |  | 2020-11-02 | 2020-12-09 | Sous-poste | Sous-poste | 2020-11-04 | 2020-12-11 |  | OK | Allemagne | IS0031648S - OF 5119198 / Manque KLS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 | 50 | 12 | 2020 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2850036810 | 2020-09-24 | FABRICATION | SATAIR | BUNDLE | 28500368 | NON-SPARES | 10 | 1 | AOG | V9293110100095A | IS0059303M | NON PRESENT INDUS | 37653 | 3671810-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-12-18 | NA | 100% | 2020-12-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-12-10 | Sous-poste | Sous-poste | 2020-09-30 | 2020-12-14 | Early collab | OK | KIT FACTORY | Sent to HBG 09/12/2020 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 50 | 12 | 2020 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA | 0 | 0
2850036810 | 2020-09-24 | FABRICATION | SATAIR | BUNDLE | 28500368 | NON-SPARES | 10 | 1 | AOG | V9293110100095A | IS0059303M | NON PRESENT INDUS | 37653 | 3671810-2 |  |  |  | 100% | 0% | 50% | 100% | 2020-12-18 | NA | 100% | 2020-12-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-12-10 | Sous-poste | Sous-poste | 2020-09-30 | 2020-12-14 | Early collab | OK | KIT FACTORY | Sent to HBG 09/12/2020 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 50 | 12 | 2020 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA | 0 | 0
2850036810 | 2020-09-24 | FABRICATION | SATAIR | BUNDLE | 28500368 | NON-SPARES | 10 | 1 | AOG | V9293110100095A | IS0059303M | NON PRESENT INDUS | 37653 | 3671810-3 |  |  |  | 100% | 0% | 50% | 100% | 2020-12-18 | NA | 100% | 2020-12-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-12-10 | Sous-poste | Sous-poste | 2020-09-30 | 2020-12-14 | Early collab | OK | KIT FACTORY | Sent to HBG 09/12/2020 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 50 | 12 | 2020 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA | 0 | 0
2850036810 | 2020-09-24 | FABRICATION | SATAIR | BUNDLE | 28500368 | NON-SPARES | 10 | 1 | AOG | V9293110100095A | IS0059303M | NON PRESENT INDUS | 37653 | 3671810-4 |  |  |  | 100% | 0% | 50% | 100% | 2020-12-18 | NA | 100% | 2020-12-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-12-10 | Sous-poste | Sous-poste | 2020-09-30 | 2020-12-14 | Early collab | OK | KIT FACTORY | Sent to HBG 09/12/2020 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 50 | 12 | 2020 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA | 0 | 0
2850036810 | 2020-09-24 | FABRICATION | SATAIR | BUNDLE | 28500368 | NON-SPARES | 10 | 1 | AOG | V9293110100095A | IS0059303M | NON PRESENT INDUS | 37653 | 3671810-5 |  |  |  | 100% | 0% | 50% | 100% | 2020-12-18 | NA | 100% | 2020-12-21 | 100% | NA | NA | 5.556% |  |  | 2020-09-28 | 2020-12-10 | Sous-poste | Sous-poste | 2020-09-30 | 2020-12-14 | Early collab | OK | KIT FACTORY | Sent to HBG 09/12/2020 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 50 | 12 | 2020 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA | 0 | 0
2845355510 | 2020-03-25 | FABRICATION | SATAIR | BUNDLE | 28453555 | NON-SPARES | 10 | 1 | AOG | V9292604200095 | IS0059304M | NON PRESENT INDUS | 35465 | 3678584 |  |  |  | 100% | 0% | 50% | 100% | 2021-02-01 | NA | 100% | 2020-12-07 | 100% | NA | NA | 5.556% |  |  | 2020-06-26 | 2020-12-11 | Sous-poste | Sous-poste | 2020-06-30 | 2020-12-15 | Early collab | OK | Allemagne | Sent to HBG 09/12/2020 - Attente réception IS0031900S (envoyer aussi ABS1381-09F2024) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 50 | 12 | 2020 | 0.4664 | 1.3764 | 0.137 | 1.5134 | COL | 0 | 0
2845355610 | 2020-03-25 | FABRICATION | SATAIR | BUNDLE | 28453556 | NON-SPARES | 10 | 1 | AOG | V9292604200095 | IS0059304M | NON PRESENT INDUS | 35465 | 3678586 |  |  |  | 100% | 0% | 50% | 100% | 2021-02-01 | NA | 100% | 2020-12-07 | 100% | NA | NA | 5.556% |  |  | 2020-08-05 | 2020-12-11 | Sous-poste | Sous-poste | 2020-08-07 | 2020-12-15 | Early collab | OK | Allemagne | Sent to HBG 09/12/2020 - Attente réception IS0031900S (envoyer aussi ABS1381-09F2024) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 50 | 12 | 2020 | 0.4664 | 1.3764 | 0.137 | 1.5134 | COL | 0 | 0
2845355610 | 2020-03-25 | FABRICATION | SATAIR | BUNDLE | 28453556 | NON-SPARES | 10 | 1 | AOG | V9292604200095 | IS0059304M | NON PRESENT INDUS | 35465 | 3678587 |  |  |  | 100% | 0% | 50% | 100% | 2021-02-01 | NA | 100% | 2020-12-07 | 100% | NA | NA | 5.556% |  |  | 2020-08-05 | 2020-12-11 | Sous-poste | Sous-poste | 2020-08-07 | 2020-12-15 | Early collab | OK | Allemagne | Sent to HBG 09/12/2020 - Attente réception IS0031900S (envoyer aussi ABS1381-09F2024) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 50 | 12 | 2020 | 0.4664 | 1.3764 | 0.137 | 1.5134 | COL | 0 | 0
2846357910 | 2020-04-23 | FABRICATION | SATAIR | BUNDLE | 28463579 | 151103 | 10 | 1 | AOG | V9292604200095 | IS0059304M | NON PRESENT INDUS | 35465 | 3678588 |  |  |  | 100% | 0% | 50% | 100% | 2021-02-01 | NA | 100% | 2020-12-07 | 100% | NA | NA | 5.556% |  |  | 2020-09-17 | 2020-12-11 |  |  | 2020-09-21 | 2020-12-15 | Early collab | OK | Allemagne | Sent to HBG 09/12/2020 - Attente réception IS0031900S (envoyer aussi ABS1381-09F2024) | O |  | 0 | #VALUE! | #VALUE! | N |  |  | 4 | 2020 | 50 | 12 | 2020 | 0.4664 | 1.3764 | 0.137 | 1.5134 | COL | 0 | 0
2851833410 | 2020-11-23 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28518334 | NON-SPARES | 10 | 5 | CRIT | D9251095600000 | IS0053509S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-11-20 | 2020-12-15 | Sous-poste | Sous-poste | 2020-11-24 | 2020-12-17 | Early collab | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 51 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849341010 | 2020-08-27 | FABRICATION | SATAIR | PROTECTION CAP | 28493410 | NON-SPARES | 10 | 8 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 36620 | 3676942-1 => 3676942-8 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-15 | NA | 100% | 2020-11-30 | 100% | NA | NA | 5.556% |  |  | 2020-09-16 | 2020-12-15 | Sous-poste | Sous-poste | 2020-09-19 | 2020-12-18 | Early collab |  | Allemagne | Cosse cassée au sertissage - Pince à retrouver | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 51 | 12 | 2020 | 0.02 | 0.8944 | 0.01118 | 0.90558 | NA | 0 | 0
2848426610 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484266 | NON-SPARES | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | 37849 | 3671808-1 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-12-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-12-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-12-18 | Early collab |  | Allemagne |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2848426610 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484266 | NON-SPARES | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | 37849 | 3671808-2 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-12-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-12-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-12-18 | Early collab |  | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD - Coverage AZA => Manque 1CON*01064 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2848426610 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484266 | NON-SPARES | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | 37849 | 3671808-3 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-12-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-12-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-12-18 | Early collab |  | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD - Coverage AZA => Manque 1CON*01064 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2848426610 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484266 | NON-SPARES | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | 37849 | 3671808-4 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-12-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-12-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-12-18 | Early collab |  | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD - Coverage AZA => Manque 1CON*01064 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2848426610 | 2020-07-16 | FABRICATION | SATAIR | BUNDLE | 28484266 | NON-SPARES | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | 37849 | 3671808-5 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2020-12-02 | 100% | NA | NA | 5.556% |  |  | 2020-09-09 | 2020-12-16 | Sous-poste | Sous-poste | 2020-09-11 | 2020-12-18 | Early collab |  | Allemagne | Attente STS à jour - Attente DI GIDT 486989 + retour FRANCESSD - Coverage AZA => Manque 1CON*01064 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2848683920 | 2020-07-30 | FABRICATION | SATAIR | 510 | 28486839 | NON-SPARES | 20 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 35607 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-02 | 100% | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-10-23 | 2020-12-17 | Sous-poste | Sous-poste | 2020-10-28 | 2020-12-22 | Early collab |  | Allemagne | Attente servitude KLS magasin - IS0031648S à re order OF 5119198 - Envoyé à LAB le 21/12 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2849846410 | 2020-09-21 | HA/REVENTE | SATAIR | PLATE ASSY | 28498464 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 37251 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-16 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-03 | 2020-12-18 | Sous-poste | Sous-poste | 2020-12-08 | 2020-12-23 |  | OK | KIT FACTORY | Attente Étienne (Pb ADV mail JGI du 23/12) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 51 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849846310 | 2020-09-21 | HA/REVENTE | SATAIR | PLATE ASSY | 28498463 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 37251 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-16 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-03 | 2020-12-18 | Sous-poste | Sous-poste | 2020-12-08 | 2020-12-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 51 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2848051310 | 2020-07-06 | FABRICATION | SATAIR | 510 | 28480513 | NON-SPARES | 10 | 1 | AOG | A9550051000196 | IS0032621M | NON PRESENT INDUS | 35719 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-02 | 100% | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-11-04 | 2020-12-18 | Sous-poste | Sous-poste | 2020-11-06 | 2020-12-22 | Early collab |  | Allemagne | IS0053082S à re order OF - OF impossible attente DI PURCHASES - Envoyé à LAB le 21/12 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 51 | 12 | 2020 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2851837410 | 2020-11-23 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28518374 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-18 | 2020-12-18 | Sous-poste | Sous-poste | 2020-12-23 | 2020-12-23 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 51 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2850195410 | 2020-10-01 | FABRICATION | SATAIR | 27 | 28501954 | NON-SPARES | 10 | 1 | EXP | D9551002700595 | IS0032094M | NON PRESENT INDUS | 37524 | LTE990027 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-26 | NA | 100% | 2020-11-30 | 50% | NA | NA | 2.778% |  |  | 2020-11-17 | 2020-12-21 | Sous-poste | Sous-poste | 2020-11-20 | 2020-12-24 |  |  | KIT FACTORY | Manque stock BDC + structure + T3S | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 52 | 12 | 2020 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2852549910 | 2020-12-14 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28525499 | NON-SPARES | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-11 | 2020-12-21 | Sous-poste | Sous-poste | 2020-12-15 | 2020-12-23 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 52 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852174710 | 2020-12-03 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28521747 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-30 | 2020-12-30 | Sous-poste | Sous-poste | 2021-01-02 | 2021-01-02 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 53 | 12 | 2020 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849000410 | 2020-08-17 | HA/REVENTE | SATAIR | PLATE ASSY | 28490004 | NON-SPARES | 10 | 8 | RTN | A9251152500000 | IS0031658S | NA | 36608 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-11-30 | NA | 100% | 2021-02-05 | 0% | NA | NA | 0% |  |  | 2021-01-07 | 2021-01-07 | Sous-poste | Sous-poste | 2021-01-12 | 2021-01-12 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 2 | 1 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849324310 | 2020-08-26 | HA/REVENTE | SATAIR | BRACKET | 28493243 | NON-SPARES | 10 | 8 | RTN | A9252496620200 | IS0053087S | NA | 35924 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-04 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2021-01-07 | 2021-01-07 | Sous-poste | Sous-poste | 2021-01-12 | 2021-01-12 | Early collab | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 2 | 1 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2850450810 | 2020-10-12 | FABRICATION | SATAIR | PROTECTION CAP | 28504508 | NON-SPARES | 10 | 4 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 36620 | 3676943-1 => 3676943-4 |  |  |  | 100% | 0% | 50% | 100% | 2020-10-15 | NA | 100% | 2020-12-14 | 100% | NA | NA | 5.556% |  |  | 2021-01-07 | 2021-01-07 | Sous-poste | Sous-poste | 2021-01-12 | 2021-01-12 |  | OK | SPARES | Attente réappro IS0030528S (TA1601) - Réception le 04/01 - Transmises en production le 08/01 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 2 | 1 | 2021 | 0.01 | 0.4472 | 0.01118 | 0.45838 | NA | 0 | 0
2850155310 | 2020-09-30 | FABRICATION | SATAIR | 60 | 28501553 | NON-SPARES | 10 | 1 | CRIT | D9551006000195 | IS0032114M | NON PRESENT INDUS | 37459 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | TBD | 0% | 90% | 2020-12-16 | 100% | NA | NA | 5.556% |  |  | 2020-10-05 | 2021-01-07 | Sous-poste | Sous-poste | 2020-10-07 | 2021-01-09 |  |  | KIT FACTORY | Manque stock BDC + FIP 6963402800 + MECAHERS | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 2 | 1 | 2021 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
490004137010 | 2020-10-19 | FABRICATION | STELIA | 34 | 4900041370 | NON-SPARES | 10 | 1 | RTN | S9550003494095 | IS0032230M | NON PRESENT INDUS | 37986 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | TBD | 0% | NA | OUI | 0% |  |  | 2020-12-14 | 2021-01-08 | Sous-poste | Sous-poste | 2020-12-17 | 2021-01-11 |  |  | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 2 | 1 | 2021 | 0.205 | 4.1225 | 1.0306 | 5.1531 | COL | 0 | 0
2837434910 | 2020-01-07 | FABRICATION | SATAIR | 432 | 28374349 | 150970 | 10 | 1 | RTN | A95500432000AB | IS0031989M | NON PRESENT INDUS | 31957 | LTE990002 |  | O | O | 100% | 0% | 50% | 100% | 2020-10-06 | 100% | 100% | 2020-10-08 | 100% | NA | NA | 5.556% |  |  | 2020-03-02 | 2021-01-12 |  |  | 2020-03-05 | 2021-01-15 |  | OK | Allemagne | Attente confié + RFQ HA Manque 4ETI*00589 (Réception 06/11/2020) - Attente réponse FRSSD - NC étiquettes ST (OF5119909) | C |  | 1 | #VALUE! | O | O | 1 | 1900 | 1 | 2020 | 3 | 1 | 2021 | 0.36 | 18.8965 | 4.7241 | 23.6206 | COL | 0 | 0
PO20000831 | 2020-11-21 | FABRICATION | PMVE | KITS PMVE | PO2000083 | NON-SPARES | 1 | 2 |  | AVI-00322-PL003-R01 | IS0059289M | NON PRESENT INDUS | 37944 | 3678891-1 à 3678891-2 |  |  |  | 100% | 0% | 50% | 100% | 2021-01-12 | NA | 100% | TBD | 0% | NA | NA | 0% |  |  | 2020-12-18 | 2021-01-12 | Sous-poste | Sous-poste | 2020-12-23 | 2021-01-13 |  |  |  | Faire la version de FAB - OF impossible attente DI PURCHASES - Ok dossier livré | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 3 | 1 | 2021 | 2.5 | 24.7 | 5.44 | 30.14 | NA | 0 | 0
2852126810 | 2020-12-02 | HA/REVENTE | SATAIR | SEAL | 28521268 | NON-SPARES | 10 | 1 | CRIT | F2121202620000 | IS0053199S | NA | 38554 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-16 | NA | 100% | NA | 0% | NA | NA | 0% |  |  | 2020-12-21 | 2021-01-15 | Sous-poste | Sous-poste | 2020-12-23 | 2021-01-19 |  |  | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 3 | 1 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849784010 | 2020-09-16 | FABRICATION | SATAIR | PLACARD SET | 28497840 | NON-SPARES | 10 | 6 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | 37173 | 3671802-1 => 3671802-6 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-18 | NA | 100% | 2020-11-30 | 90% | NA | NA | 5% |  |  | 2020-12-17 | 2021-01-15 | Sous-poste | Sous-poste | 2020-12-22 | 2021-01-20 | Early collab |  | KIT FACTORY | Message DA ok pour re order IS0035087S (MT1200) via OF 5119314 (Réception 06/01) - Reçu à LAB le 07/01 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 3 | 1 | 2021 | 0 | 1.23 | 0.0205 | 1.2505 | NA | 0 | 0
2845355610 | 2020-03-25 | FABRICATION | SATAIR | BUNDLE | 28453556 | NON-SPARES | 10 | 1 | AOG | V9292604200095 | IS0059304M | NON PRESENT INDUS | 35465 | 3678585 |  |  |  | 100% | 0% | 50% | 100% | 2021-02-01 | NA | 100% | 2020-12-07 | 100% | NA | NA | 5.556% |  |  | 2020-08-05 | 2021-01-15 | Sous-poste | Sous-poste | 2020-08-07 | 2021-01-22 | Early collab |  | Allemagne | Sent to HBG 09/12/2020 - Attente réception IS0031900S (envoyer aussi ABS1381-09F2024) - PO 28463579 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 | 3 | 1 | 2021 | 0.4664 | 1.3764 | 0.137 | 1.5134 | COL | 0 | 0
2850155510 | 2020-09-30 | FABRICATION | SATAIR | 62 | 28501555 | NON-SPARES | 10 | 1 | CRIT | D9551006200195 | IS0032126M | NON PRESENT INDUS | 37459 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | TBD | 0% | 90% | 2020-12-16 | 100% | NA | NA | 5.556% |  |  | 2020-10-05 | 2021-01-20 | Sous-poste | Sous-poste | 2020-10-07 | 2021-01-22 |  |  | KIT FACTORY | Manque stock BDC + FIP 6963402800 + MECAHERS + T3S - Manque 2 prises IS0013381S & IS0013383S - Ok le 20/01 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 4 | 1 | 2021 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2850155410 | 2020-09-30 | FABRICATION | SATAIR | 61 | 28501554 | NON-SPARES | 10 | 1 | CRIT | D9551006100195 | IS0032120M | NON PRESENT INDUS | 37459 | LTE990005 |  |  |  | 100% | 0% | 50% | 100% | TBD | 0% | 90% | 2020-12-16 | 100% | NA | NA | 5.556% |  |  | 2020-10-05 | 2021-01-20 | Sous-poste | Sous-poste | 2020-10-07 | 2021-01-22 |  |  | KIT FACTORY | Manque stock BDC + FIP 6963402800 + MECAHERS - Manque 1 prise - Ok le 20/01 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 4 | 1 | 2021 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2848683910 | 2020-07-30 | FABRICATION | SATAIR | 510 | 28486839 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 35607 | LTE990009 |  |  |  | 100% | 0% | 50% | 100% | 2020-11-02 | 100% | 100% | 2020-11-10 | 100% | NA | NA | 5.556% |  |  | 2020-10-23 | 2021-01-26 | Sous-poste | Sous-poste | 2020-10-28 | 2021-01-29 | Early collab |  | Allemagne | Attente servitude KLS magasin - IS0031648S à re order OF 5119198 (Réception le 15/01) - Manque voyant | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2020 | 5 | 1 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
490004170010 | 2021-01-29 |  | TBD |  | 4900041700 | NON-SPARES | 10 | 1 | AOG | E0276AN0N132 |  | NON PRESENT INDUS | 41213 | NA |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-02-02 | 2021-01-28 | Sous-poste | Sous-poste | 2021-02-04 | 2021-02-01 |  |  | ROCHEFORT |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 5 | 1 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004152610 | 2020-12-08 | HA/REVENTE | STELIA | PLATINE AVANT 22VU | 4900041526 | NON-SPARES | 10 | 1 | CRIT | S9251454400100 | IS0053336S | NA | 38850 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-02-02 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-01-19 | 2021-02-03 | Sous-poste | Sous-poste | 2021-01-21 | 2021-02-05 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 6 | 2 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852572810 | 2020-12-14 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28525728 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-01-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2020-12-11 | 2021-02-03 | Sous-poste | Sous-poste | 2020-12-15 | 2021-02-05 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 6 | 2 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004115710 | 2020-08-19 | FABRICATION | STELIA | CÂBLE | 4900041157 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 36614 | OF3697502 |  | O | O | 100% | 0% | 50% | 100% | 2021-01-12 | NA | 100% | 2021-01-25 | 100% | NA | OUI | 5.263% |  |  | 2020-10-14 | 2021-02-04 | Sous-poste | Sous-poste | 2020-10-19 | 2021-02-09 |  | OK | Rochefort |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 6 | 2 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2849000510 | 2020-08-17 | HA/REVENTE | SATAIR | PLATE ASSY | 28490005 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 36608 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-11-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-02-04 | 2021-02-04 | Sous-poste | Sous-poste | 2021-02-09 | 2021-02-09 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 6 | 2 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2849868210 | 2020-09-22 | HA/REVENTE | SATAIR | BRACKET | 28498682 | NON-SPARES | 10 | 4 | RTN | A9252496620200 | IS0053087S | NA | 37251 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-01-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-02-04 | 2021-02-04 | Sous-poste | Sous-poste | 2021-02-09 | 2021-02-09 | Early collab | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 6 | 2 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2854069510 | 2021-01-28 | FABRICATION | SATAIR | 108 | 28540695 | NON-SPARES | 10 | 1 | AOG | D9550010801295 | IS0032586M | NON PRESENT INDUS | 41126 | LTE990003 |  | O | O | 100% | 0% | 50% | 100% | 2021-02-09 | 0% | 90% | 2021-02-08 | 100% | NA | NA | 5.556% |  |  | 2021-01-27 | 2021-02-11 | Sous-poste | Sous-poste | 2021-01-29 | 2021-02-11 |  |  | SPARES | Bom + gamme + VFAB ok - Attente DI AF | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 7 | 2 | 2021 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2852872410 | 2020-12-22 | FABRICATION | SATAIR | 54 | 28528724 | NON-SPARES | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 40409 | LTE990022 |  | O | O | 100% | 0% | 50% | 100% | 2021-02-08 | 100% | 100% | 2021-02-10 | 100% | NA | NA | 5.556% |  |  | 2021-02-15 | 2021-02-15 | Sous-poste | Sous-poste | 2021-02-18 | 2021-02-18 |  |  | KIT FACTORY | ISS et ISM en statu 05 OK | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 8 | 2 | 2021 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
68707011 | 2020-08-17 | FABRICATION | AD&S | 39 | 6870701 | NON-SPARES | 1 | 1 | AOG | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 36610 | LTE990004 |  | O | O | 100% | 0% | 50% | 100% | 2020-11-03 | 50% | 95% | 2021-02-08 | 100% | NA | OUI | 5.263% |  |  | 2020-09-02 | 2021-02-15 | Sous-poste | Sous-poste | 2020-09-04 | 2021-02-17 |  | OK | Seville |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2020 | 8 | 2 | 2021 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68760561 | 2020-10-13 | FABRICATION | AD&S | 49 | 6876056 | NON-SPARES | 1 | 1 | AOG | MB042ACABAAA | IS0032206M | NON PRESENT INDUS | 37836 | LTE990003 |  | O | O | 100% | 0% | 50% | 100% | TBD | 100% | 100% | 2020-12-14 | 100% | NA | OUI | 5.263% |  |  | 2020-10-16 | 2021-02-26 | Sous-poste | Sous-poste | 2020-10-20 | 2021-03-02 | Early collab | OK | SPARES | De IS0034122S vers IS0053636S - Manquant IS0006678S (réception 16/02) - Envoyé à LAB le 17/02 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 9 | 2 | 2021 | 0.205 | 2.39 | 0.5975 | 2.9875 | COL | 0 | 0
2850479510 | 2020-10-13 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28504795 | NON-SPARES | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 37834 | NA | NA | NA | NA | NA | NA | 100% | 0% | 2020-12-03 | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-03-02 | 2021-03-02 | Sous-poste | Sous-poste | 2021-03-05 | 2021-03-05 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 10 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2854354710 | 2021-02-04 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28543547 | NON-SPARES | 10 | 1 | RTN | D9251095600000 | IS0053509S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-03-03 | 2021-03-03 | Sous-poste | Sous-poste | 2021-03-06 | 2021-03-06 |  |  |  | Attente GO EAU pou saisie DA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 10 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2854353910 | 2021-02-04 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28543539 | NON-SPARES | 10 | 1 | RTN | D9251095600000 | IS0053509S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-03-03 | 2021-03-03 | Sous-poste | Sous-poste | 2021-03-06 | 2021-03-06 |  |  |  | Attente GO EAU pou saisie DA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 10 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852106410 | 2020-12-02 | FABRICATION | SATAIR | BUNDLE | 28521064 | NON-SPARES | 10 | 1 | AOG | D9000095477995 | IS0032050M | NON PRESENT INDUS | 40985 | OF3700552 |  | O | O | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2021-02-15 | 100% | NA | NA | 5.556% |  |  | 2021-02-17 | 2021-03-04 | Sous-poste | Sous-poste | 2021-02-19 | 2021-03-05 |  |  | KIT FACTORY | Manquant PX2203 (réception CW08) - Réception ok, rajout sur OF le 01/03 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 10 | 3 | 2021 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0
2854354610 | 2021-02-04 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28543546 | NON-SPARES | 10 | 1 | RTN | D9251095400000 | IS0053354S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-03-03 | 2021-03-05 | Sous-poste | Sous-poste | 2021-03-06 | 2021-03-10 |  |  |  | Attente GO EAU pou saisie DA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 10 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2854353810 | 2021-02-04 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28543538 | NON-SPARES | 10 | 1 | RTN | D9251095400000 | IS0053354S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-03-03 | 2021-03-05 | Sous-poste | Sous-poste | 2021-03-06 | 2021-03-10 |  |  |  | Attente GO EAU pou saisie DA | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 10 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2851837510 | 2020-11-23 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28518375 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2020-12-18 | 2021-03-09 | Sous-poste | Sous-poste | 2020-12-23 | 2021-03-12 |  | OK | SPARES | Réactivée suite NC 20248470 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 11 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2851885810 | 2020-11-24 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28518858 | NON-SPARES | 10 | 3 | CRIT | D9251095400000 | IS0053354S | NA | 39182 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-08 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-01-13 | 2021-03-10 | Sous-poste | Sous-poste | 2021-01-15 | 2021-03-12 | Early collab | OK | SPARES | Réactivée pour qté 1 en NC 20248470 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 11 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852572830 | 2021-03-02 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28525728 | NON-SPARES | 30 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 42244 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-03-08 | 2021-03-12 | Sous-poste | Sous-poste | 2021-03-10 | 2021-03-16 |  |  |  |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 | 11 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004191210 | 2021-03-10 |  | TBD |  | 4900041912 | NON-SPARES | 10 | 1 | AOG | E0276AN0N132 |  | NON PRESENT INDUS | STOCK |  |  |  |  | 0% | 0% | 0% | 100% | 2021-03-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-03-15 | 2021-03-15 | Sous-poste | Sous-poste | 2021-03-17 | 2021-03-17 |  |  |  |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 | 12 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
450098612410 | 2020-10-12 | FABRICATION | DES | KITS 9119VU | 4500986124 | NON-SPARES | 10 | 5 |  | A320EL061-EPA | IS0059318M | NON PRESENT INDUS | 37948 | 3684051-1 => 3684051-5 |  | O | O | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2021-01-12 | 100% | NA | OUI | 5.263% |  |  |  | 2021-03-16 | Sous-poste | Sous-poste | TBD | 2021-03-19 |  | OK |  | 2 KITS livrés | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 12 | 3 | 2021 | 1.75 | 13.5 | 0.27 | 13.77 | NA | 0 | 0
2849868310 | 2020-09-22 | HA/REVENTE | SATAIR | BRACKET | 28498683 | NON-SPARES | 10 | 4 | RTN | A9252496620200 | IS0053087S | NA | 37251 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-01-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-03-05 | 2021-03-22 | Sous-poste | Sous-poste | 2021-03-10 | 2021-03-25 | Early collab |  | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 | 13 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2838205610 | 2020-01-15 | FABRICATION | SATAIR | PLATE | 28382056 | NON-SPARES | 10 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 32405 | LTE990001 |  | O | O | 100% | 0% | 50% | 99% | 2020-11-05 | NA | 99% | 2021-02-08 | 100% | NA | NA | 5.556% |  |  | 2020-10-23 | 2021-03-23 | Sous-poste | Sous-poste | 2020-10-28 | 2021-03-26 |  | OK | Allemagne | Coverage à refaire - Attente paramétrage AF | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 13 | 3 | 2021 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2851333610 | 2020-11-10 | FABRICATION | SATAIR | 510 | 28513336 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 39340 |  |  |  |  | 100% | 0% | 50% | 100% | 2021-02-16 | 0% | 90% | 2021-03-04 | 0% | NA | NA | 0% |  |  | 2020-12-07 | 2021-03-23 | Sous-poste | Sous-poste | 2020-12-10 | 2021-03-26 |  |  | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 13 | 3 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2851333620 | 2020-11-10 | FABRICATION | SATAIR | 510 | 28513336 | NON-SPARES | 20 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 39340 |  |  |  |  | 100% | 0% | 50% | 100% | 2021-02-16 | 0% | 90% | 2021-03-04 | 0% | NA | NA | 0% |  |  | 2020-12-07 | 2021-03-23 | Sous-poste | Sous-poste | 2020-12-10 | 2021-03-26 |  |  | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 13 | 3 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2838205611 | 2020-01-15 | FABRICATION | SATAIR | PLATE | 28382056 | NON-SPARES | 11 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 32405 | LTE990002 |  | O | O | 100% | 0% | 50% | 99% | 2020-11-05 | NA | 99% | 2021-02-08 | 100% | NA | NA | 5.556% |  |  | 2020-10-23 | 2021-03-23 | Sous-poste | Sous-poste | 2020-10-28 | 2021-03-26 |  | OK | Allemagne | Coverage à refaire - Attente paramétrage AF - Casse 2 résistances IS0007538S (stock - OF updated) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 13 | 3 | 2021 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2838205612 | 2020-01-15 | FABRICATION | SATAIR | PLATE | 28382056 | NON-SPARES | 12 | 1 | RTN | D9251719400095 | IS0030400M | NON PRESENT INDUS | 32405 | LTE990003 |  | O | O | 100% | 0% | 50% | 99% | 2020-11-05 | NA | 99% | 2021-02-08 | 100% | NA | NA | 5.556% |  |  | 2020-10-23 | 2021-03-23 | Sous-poste | Sous-poste | 2020-10-28 | 2021-03-26 |  | OK | Allemagne | Coverage à refaire - Attente paramétrage AF Casse 2 résistances IS0007538S (No stock - to re order) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 | 13 | 3 | 2021 | 0 | 3.1372 | 0.72 | 3.8572 | NA | 0 | 0
2852386910 | 2020-12-09 | HA/REVENTE | SATAIR | DIAPHRAGM ASSY | 28523869 | NON-SPARES | 10 | 1 | EXP | L9251229301500 | IS0053337S | NA | 39788 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-02-16 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-01-05 | 2021-03-24 | Sous-poste | Sous-poste | 2021-01-08 | 2021-03-29 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 13 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852386810 | 2020-12-09 | HA/REVENTE | SATAIR | DIAPHRAGM ASSY | 28523868 | NON-SPARES | 10 | 3 | EXP | L9251229301400 | IS0053338S | NA | 39788 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-02-16 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-01-05 | 2021-03-24 | Sous-poste | Sous-poste | 2021-01-08 | 2021-03-29 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 13 | 3 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2822399010 | 2019-07-18 | FABRICATION | SATAIR | 108 | 28223990 | NON-SPARES | 10 | 1 | RTN | D9550010800996 | IS0032069M | NON PRESENT INDUS | 42160 | LTE990016 |  | O | O | 100% | 0% | 50% | 100% | 2021-03-15 | 100% | 100% | 2021-03-17 | 100% | NA | NA | 5.556% |  |  | 2021-02-24 | 2021-03-30 | Sous-poste | Sous-poste | 2021-02-28 | 2021-04-02 |  | OK | Allemagne | Attente confié - Couverture SILOG via DA 26926 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 14 | 3 | 2021 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0 | 3495
2853102410 | 2021-01-04 | FABRICATION | SATAIR | 108 | 28531024 | NON-SPARES | 10 | 2 | AOG | D9550010801195 | IS0059763M | NON PRESENT INDUS | 40724 | LTE990001 - LTE990002 |  | O | O | 100% | 0% | 50% | 100% | 2021-03-15 | 100% | 100% | 2021-03-17 | 100% | NA | NA | 5.556% |  |  | 2021-02-23 | 2021-03-31 | Sous-poste | Sous-poste | 2021-02-25 | 2021-04-02 |  | OK | KIT FACTORY | - Attente paramétrage confié - Attente DI pour OP => OF / Ajouter la note prep au PP | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 14 | 3 | 2021 | 0.72 | 15.9638 | 1.9955 | 17.9593 | COL | 0 | 0
2855811810 | 2021-03-11 | FABRICATION | SATAIR | 27 | 28558118 | NON-SPARES | 10 | 1 | AOG | D9551002700595 | IS0032094M | NON PRESENT INDUS | 42417 | LTE990028 |  | O | O | 100% | 0% | 50% | 100% | 2021-03-19 | NA | 100% | 2021-03-24 | 100% | NA | NA | 5.556% |  |  | 2021-03-12 | 2021-04-01 | Sous-poste | Sous-poste | 2021-03-16 | 2021-04-05 |  | OK |  |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 | 14 | 4 | 2021 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
490004180210 | 2021-02-19 | HA/REVENTE | STELIA | BARRE | 4900041802 | NON-SPARES | 10 | 2 | RTN | S9251302220000 | IS0013882S | NA | 41768 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-04-02 | 2021-04-02 | Sous-poste | Sous-poste | 2021-04-07 | 2021-04-07 |  | OK | ROCHEFORT | DI paramétrage statut 12 vers 05 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 14 | 4 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004180220 | 2021-02-19 | HA/REVENTE | STELIA | CAPOT | 4900041802 | NON-SPARES | 20 | 2 | RTN | S9251363300100 | IS0054056S | NA | 41768 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-15 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-04-02 | 2021-04-02 | Sous-poste | Sous-poste | 2021-04-07 | 2021-04-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 14 | 4 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
450098612420 | 2020-10-12 | FABRICATION | DES | KITS 9119VU | 4500986124 | NON-SPARES | 20 | 5 |  | A320EL061-EPA | IS0059318M | NON PRESENT INDUS | 37948 | 3684052-1 => 3684052-5 |  | O | O | 100% | 0% | 50% | 100% | 2021-03-01 | NA | 100% | 2021-03-01 | 95% | NA | OUI | 5% |  |  |  | 2021-04-06 | Sous-poste | Sous-poste | TBD | 2021-04-09 |  |  |  | STRUT qté 4 perdus (ajout dans OF3684052 OK) - 3684052-3 livré le 18/03 - Réception colonnettes le 30/03 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 | 15 | 4 | 2021 | 1.75 | 13.5 | 0.27 | 13.77 | NA | 0 | 0
2820491010 | 2019-07-02 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28204910 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 26335 | 5123372 |  | O | O | 100% | 0% | 50% | 100% | 2019-09-16 | 0% | 90% | 2019-10-07 | 100% | NA | NA | 5.556% |  |  | 2021-02-03 | 2021-04-08 | Sous-poste | Sous-poste | 2021-02-08 | 2021-04-13 |  | OK | Allemagne | Attente FIP - Informer Qualité (avant livraison derog) - YP09 ok pour conso matière - Casse manette to re order - ligne à annuler | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 15 | 4 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
2856815410 | 2021-04-07 | FABRICATION | SATAIR | WIRE-BONDING | 28568154 | NON-SPARES | 10 | 9 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | 43239 | 3734885 |  | O | O | 100% | 0% | 50% | 100% | 2021-04-07 | NA | 100% | 2021-04-09 | 100% | NA | NA | 5.556% |  |  | 2021-04-06 | 2021-04-12 | Sous-poste | Sous-poste | 2021-04-08 | 2021-04-14 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 16 | 4 | 2021 | 1.8531 | 2.1447 | 0.02383 | 2.1685 | NA | 0 | 0
2856815510 | 2021-04-07 | FABRICATION | SATAIR | WIRE-BONDING | 28568155 | NON-SPARES | 10 | 9 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | 43239 | 3734885 |  | O | O | 100% | 0% | 50% | 100% | 2021-04-07 | NA | 100% | 2021-04-09 | 100% | NA | NA | 5.556% |  |  | 2021-04-06 | 2021-04-12 | Sous-poste | Sous-poste | 2021-04-08 | 2021-04-14 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 16 | 4 | 2021 | 1.8531 | 2.1447 | 0.02383 | 2.1685 | NA | 0 | 0
2856207710 | 2021-03-23 | HA/REVENTE | SATAIR | PLATE ASSY-CLOSING | 28562077 | NON-SPARES | 10 | 2 | AOG | F9251339200000 | IS0054706S | NA | 42782 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-04-27 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-03-19 | 2021-04-23 | Sous-poste | Sous-poste | 2021-03-23 | 2021-04-27 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 | 17 | 4 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2856893110 | 2021-04-08 | FABRICATION | SATAIR | PLACARD SET | 28568931 | NON-SPARES | 10 | 1 | CRIT | D9100095600395 | IS0032064M | NON PRESENT INDUS | 43326 | 3736212 |  | O | O | 100% | 0% | 50% | 100% | 2021-04-12 | NA | 100% | 2021-04-26 | 100% | NA | NA | 5.556% |  |  | 2021-05-06 | 2021-04-30 | Sous-poste | Sous-poste | 2021-05-08 | 2021-05-01 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 18 | 4 | 2021 | 0 | 0.205 | 0.0205 | 0.2255 | NA | 0 | 0
2851125610 | 2020-11-02 | HA/REVENTE | SATAIR | PLATE ASSY | 28511256 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 38333 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2020-12-16 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-05-05 | 2021-05-05 | Sous-poste | Sous-poste | 2021-05-10 | 2021-05-10 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 19 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004214510 | 2021-04-12 | FABRICATION | STELIA | CÂBLE | 4900042145 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 43397 | 3739866 |  | O | O | 100% | 0% | 50% | 100% | 2021-04-16 | NA | 100% | 2021-04-27 | 100% | NA | OUI | 5.263% |  |  | 2021-05-05 | 2021-05-05 | Sous-poste | Sous-poste | 2021-05-09 | 2021-05-09 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 19 | 5 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
630211524810 | 2021-05-03 | FABRICATION | SATAIR | OPTICAL FIBER | 6302115248 | NON-SPARES | 10 | 1 | AOG | V9271701020000 | IS0060645M | NON PRESENT INDUS | NA | 3748236 |  | O | O | 0% | 0% | 0% | 100% | 2021-05-03 | NA | 100% | 2021-05-04 | 0% | NA | NA | 0% |  |  | 2021-05-05 | 2021-05-05 | Sous-poste | Sous-poste | 2021-05-07 | 2021-05-07 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 19 | 5 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
2858284910 | 2021-04-29 | HA/REVENTE | SATAIR | BACKSHELL | 28582849 | NON-SPARES | 10 | 2 | AOG | ABS22621820 | IS0006854S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-04-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-04-29 | 2021-05-05 | Sous-poste | Sous-poste | 2021-05-01 | 2021-05-05 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 19 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2852872510 | 2020-12-22 | FABRICATION | SATAIR | BUNDLE | 28528725 | NON-SPARES | 10 | 1 | AOG | D9000095477995 | IS0032050M | NON PRESENT INDUS | 40985 | OF3700553 |  | O | O | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2021-03-22 | 100% | NA | NA | 5.556% |  |  | 2021-04-13 | 2021-05-07 | Sous-poste | Sous-poste | 2021-04-15 | 2021-05-11 |  | OK | KIT FACTORY | Manquants IS0007386S qté 2 (Intraco LIP ok- réception le 22/03 & IS0032081S qté 3 to order (Réception 03/05) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 19 | 5 | 2021 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0
2858194910 | 2021-04-29 | FABRICATION | SATAIR | PROTECTION CAP | 28581949 | NON-SPARES | 10 | 2 | CRIT | F0003003000000 | IS0032144M | NON PRESENT INDUS | 43923 | 3748488 |  | O | O | 100% | 0% | 50% | 100% | 2021-05-04 | NA | 100% | TBD | 0% | NA | NA | 0% |  |  | 2021-04-28 | 2021-05-10 | Sous-poste | Sous-poste | 2021-04-30 | 2021-05-11 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 20 | 5 | 2021 | 0.005 | 0.2236 | 0.01118 | 0.23478 | NA | 0 | 0
2853608610 | 2021-01-18 | HA/REVENTE | SATAIR | PLATE ASSY | 28536086 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 40959 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-05-14 | 2021-05-14 | Sous-poste | Sous-poste | 2021-05-19 | 2021-05-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 20 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2857568810 | 2021-04-20 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28575688 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 43787 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-05-17 | 2021-05-17 | Sous-poste | Sous-poste | 2021-05-21 | 2021-05-20 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 21 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858534510 | 2021-05-06 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28585345 | NON-SPARES | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 43787 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-05-05 | 2021-05-18 | Sous-poste | Sous-poste | 2021-05-07 | 2021-05-20 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 21 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858347710 | 2021-04-30 | HA/REVENTE | SATAIR | PLACARD | 28583477 | NON-SPARES | 10 | 1 | AOG | D9251117900000 | IS0055779S | NA | 44001 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-05-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-05-20 | 2021-05-20 | Sous-poste | Sous-poste | 2021-05-24 | 2021-05-24 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 21 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858347810 | 2021-04-30 | HA/REVENTE | SATAIR | PLACARD | 28583478 | NON-SPARES | 10 | 1 | AOG | D9251117700000 | IS0055780S | NA | 44001 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-05-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-05-20 | 2021-05-20 | Sous-poste | Sous-poste | 2021-05-24 | 2021-05-24 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 21 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858347910 | 2021-04-30 | HA/REVENTE | SATAIR | PLACARD | 28583479 | NON-SPARES | 10 | 1 | AOG | D9251118100000 | IS0055781S | NA | 44001 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-05-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-05-20 | 2021-05-20 | Sous-poste | Sous-poste | 2021-05-24 | 2021-05-24 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 21 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858042710 | 2021-04-27 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28580427 | NON-SPARES | 10 | 3 | EXP | D9251095400000 | IS0053354S | NA | 43787 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-05-24 | 2021-05-24 | Sous-poste | Sous-poste | 2021-05-27 | 2021-05-27 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 22 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858042810 | 2021-04-27 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28580428 | NON-SPARES | 10 | 3 | EXP | D9251095600000 | IS0053509S | NA | 43787 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-05-24 | 2021-05-24 | Sous-poste | Sous-poste | 2021-05-27 | 2021-05-27 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 22 | 5 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2851502410 | 2020-11-12 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28515024 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 40960 | 3735627 |  | O | O | 100% | 0% | 50% | 100% | 2021-05-03 | 100% | 100% | 2019-10-07 | 0% | NA | NA | 0% |  |  | 2021-02-24 | 2021-05-25 | Sous-poste | Sous-poste | 2021-02-28 | 2021-05-28 |  | OK | SPARES | Paramétrage article EC - Lancé initialement sur OF 5123372 (YP09) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 22 | 5 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2854493710 | 2021-02-11 | FABRICATION | SATAIR | 27 | 28544937 | NON-SPARES | 10 | 1 | RTN | D9551002700895 | IS0059907M | NON PRESENT INDUS | 41641 | LTE990001 |  | O | O | 100% | 0% | 50% | 100% | 2021-04-29 | NA | 100% | 2021-05-17 | 100% | NA | NA | 5.556% |  |  | 2021-05-28 | 2021-05-28 | Sous-poste | Sous-poste | 2021-06-02 | 2021-06-02 |  | OK | KIT FACTORY | Attente structure méca | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 22 | 5 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
490004249910 | 2021-06-09 | HA/REVENTE | STELIA | PLATINE ARRIERE 26VU | 4900042499 | NON-SPARES | 10 | 1 |  | S9251590500000 | IS0035439S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-06-10 | 2021-06-10 | Sous-poste | Sous-poste | 2021-06-15 | 2021-06-15 |  |  |  | Accepté par EAU | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 24 | 6 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2857604010 | 2021-04-21 | FABRICATION | SATAIR | 22 | 28576040 | NON-SPARES | 10 | 1 | AOG | D9551002201895 | IS0060617M | NON PRESENT INDUS | 44188 | LTE990001 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-07 | 100% | 100% | 2021-06-03 | 100% | NA | NA | 5.556% |  |  | 2021-06-08 | 2021-06-16 | Sous-poste | Sous-poste | 2021-06-11 | 2021-06-18 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 25 | 6 | 2021 | 0.205 | 10.54 | 2.63 | 13.17 | COL | 0 | 0
2857604010 | 2021-04-21 | FABRICATION | SATAIR | 22 | 28576040 | NON-SPARES | 10 | 1 | AOG | D9551002201895 | IS0060617M | NON PRESENT INDUS | 44188 | LTE990002 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-07 | 100% | 100% | 2021-06-03 | 100% | NA | NA | 5.556% |  |  | 2021-06-08 | 2021-06-16 | Sous-poste | Sous-poste | 2021-06-11 | 2021-06-18 |  | OK | KIT FACTORY | Manque IS0007035S Qté 1 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 25 | 6 | 2021 | 0.205 | 10.54 | 2.63 | 13.17 | COL | 0 | 0
2853795410 | 2021-01-21 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28537954 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 40960 | 3735628 |  | O | O | 100% | 0% | 50% | 100% | 2021-05-03 | 100% | 100% | 2021-05-31 | 100% | NA | NA | 5.556% |  |  | 2021-06-16 | 2021-06-21 | Sous-poste | Sous-poste | 2021-06-20 | 2021-06-24 |  | OK | SPARES | Paramétrage article EC | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 26 | 6 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2853795420 | 2021-01-21 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28537954 | NON-SPARES | 20 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 40960 | 3735629 |  | O | O | 100% | 0% | 50% | 100% | 2021-05-03 | 100% | 100% | 2021-05-31 | 100% | NA | NA | 5.556% |  |  | 2021-06-16 | 2021-06-21 | Sous-poste | Sous-poste | 2021-06-20 | 2021-06-24 |  | OK | SPARES | Paramétrage article EC | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 26 | 6 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2860407310 | 2021-06-16 | HA/REVENTE | SATAIR | CONNECTOR | 28604073 | NON-SPARES | 10 | 2 | AOG | ABS2208AP11S | IS0006786S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-06-25 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-06-22 | 2021-06-22 | Sous-poste | Sous-poste | 2021-06-24 | 2021-06-24 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 26 | 6 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2859654510 | 2021-05-31 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28596545 | NON-SPARES | 10 | 2 | EXP | D9251095400000 | IS0053354S | NA | 44880 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-06-16 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-06-25 | 2021-06-28 | Sous-poste | Sous-poste | 2021-06-30 | 2021-07-01 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 27 | 6 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004224010 | 2021-04-30 | HA/REVENTE | STELIA | CAPOT | 4900042240 | NON-SPARES | 10 | 2 | RTN | S9251363300100 | IS0054056S | NA | 43981 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-07-02 | 2021-07-05 | Sous-poste | Sous-poste | 2021-07-07 | 2021-07-08 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 28 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
450104454720 | 2021-01-21 | FABRICATION | DES | KITS 9119VU | 4501044547 | NON-SPARES | 20 | 5 | RTN | A320EL061-EPA | IS0059318M | NON PRESENT INDUS | 41406 | 3750512 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-28 | NA | 100% | 2021-06-30 | 100% | NA | OUI | 5.263% |  |  | 2021-04-16 | 2021-07-06 | Sous-poste | Sous-poste | 2021-04-21 | 2021-07-09 |  |  |  | Manquant SELA (IS0053085S) attente nouvel AR vu avec appro | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 28 | 7 | 2021 | 1.75 | 13.5 | 0.27 | 13.77 | NA | 0 | 0
450104454721 | 2021-01-21 | FABRICATION | DES | KITS 9119VU | 4501044547 | NON-SPARES | 21 | 5 | RTN | A320EL061-EPA | IS0059318M | NON PRESENT INDUS | 41406 | 3780139 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-28 | NA | 100% | 2021-06-30 | 100% | NA | OUI | 5.263% |  |  | 2022-02-02 | 2021-07-06 | Sous-poste | Sous-poste | 2022-02-05 | 2021-07-09 |  |  |  | Manquant SELA (IS0053085S) attente nouvel AR vu avec appro | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2021 | 28 | 7 | 2021 | 1.75 | 13.5 | 0.27 | 13.77 | NA | 0 | 0
2860313710 | 2021-06-14 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28603137 | NON-SPARES | 10 | 2 | CRIT | D9251095600000 | IS0053509S | NA | 45391 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-07-12 | 2021-07-07 | Sous-poste | Sous-poste | 2021-07-14 | 2021-07-09 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 28 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2860736810 |  | HA/REVENTE | SATAIR | PLATE ASSY | 28607368 | NON-SPARES | 10 | 2 | CRIT | A9251152500000 | IS0031658S | NA | 45643 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-06-23 | 2021-07-09 | Sous-poste | Sous-poste | 2021-06-25 | 2021-07-13 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 28 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2860736710 |  | HA/REVENTE | SATAIR | PLATE ASSY | 28607367 | NON-SPARES | 10 | 4 | CRIT | A9251152500000 | IS0031658S | NA | 45643 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-12 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-06-23 | 2021-07-09 | Sous-poste | Sous-poste | 2021-06-25 | 2021-07-13 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 28 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
P29051211 | 2021-07-07 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | P2905121 | NON-SPARES | 1 | 1 | RTN | F9252030900000 | IS0032162M | NON PRESENT INDUS | NA | 3786964 |  | O | O | 0% | 0% | 0% | 100% | 2021-07-09 | NA | 100% | 2021-07-12 | 100% | NA | NA | 5.556% |  |  | 2021-07-14 | 2021-07-14 | Sous-poste | Sous-poste | 2021-07-19 | 2021-07-19 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 29 | 7 | 2021 | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990045 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990046 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990047 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990048 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990049 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
2857596110 | 2021-04-21 | FABRICATION | SATAIR | JACK | 28575961 | NON-SPARES | 10 | 1 | RTN | A0041114100095 | IS0032651M | NON PRESENT INDUS | 43807 | LTE990050 |  | O | O | 100% | 0% | 50% | 98% | TBD | NA | 98% | 2021-06-21 | 100% | NA | NA | 5.556% |  |  | 2021-07-16 | 2021-07-16 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-21 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 29 | 7 | 2021 | 0 | 2.1686 | 0.54215 | 2.7107 | COL | 0 | 0
68797723 | 2020-11-18 | FABRICATION | AD&S | 49 | 6879772 | NON-SPARES | 3 | 1 |  | MB042ACABAAA | IS0032206M | NON PRESENT INDUS | 39527 | LTE990004 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-22 | NA | 100% | 2021-06-28 | 100% | NA | OUI | 5.263% |  |  | 2021-06-18 | 2021-07-20 | Sous-poste | Sous-poste | 2021-06-23 | 2021-07-23 |  | OK | SEVILLE |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2020 | 30 | 7 | 2021 | 0.205 | 2.39 | 0.5975 | 2.9875 | COL | 0 | 0
2858023110 | 2021-04-27 | FABRICATION | SATAIR | 54 | 28580231 | NON-SPARES | 10 | 1 | AOG | D9551005400195 | IS0032110M | NON PRESENT INDUS | 43832 | LTE990023 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-16 | 100% | 100% | 2021-07-05 | 100% | NA | NA | 5.556% |  |  | 2021-07-20 | 2021-07-26 | Sous-poste | Sous-poste | 2021-07-22 | 2021-07-28 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 31 | 7 | 2021 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2854358010 | 2021-02-04 | HA/REVENTE | SATAIR | PLATE ASSY | 28543580 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 41393 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-06-16 | 2021-07-26 | Sous-poste | Sous-poste | 2021-06-21 | 2021-07-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 31 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2855163110 | 2021-02-24 | HA/REVENTE | SATAIR | PLATE ASSY | 28551631 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 42007 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-07-16 | 2021-07-26 | Sous-poste | Sous-poste | 2021-07-21 | 2021-07-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 31 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2861143610 | 2021-07-01 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28611436 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 45923 | NA | NA | NA | NA | NA | NA | 100% | 0% | 2021-07-14 | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-07-27 | 2021-07-27 | Sous-poste | Sous-poste | 2021-07-30 | 2021-07-30 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 31 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2860736510 |  | HA/REVENTE | SATAIR | PLATE ASSY | 28607365 | NON-SPARES | 10 | 18 | CRIT | A9251152500000 | IS0031658S | NA | 45643 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-06-23 | 2021-07-27 | Sous-poste | Sous-poste | 2021-06-25 | 2021-07-29 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 31 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2861455710 | 2021-07-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28614557 | 162831 | 10 | 8 | RTN | A9251152500000 | IS0031658S | NA | 46170 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-19 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-07-27 | 2021-07-27 | 22/07/2021 | 80816934 | 2021-07-30 | 2021-07-30 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 7 | 2021 | 7 | 2021 | 31 | 7 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2862464310 | 2021-07-29 | FABRICATION | SATAIR | PLACARD SET | 28624643 | NON-SPARES | 10 | 1 | CRIT | D9100095600395 | IS0032064M | NON PRESENT INDUS | STOCK | 3801571 |  | O | O | 0% | 0% | 0% | 100% | TBD | NA | 100% | 2021-08-02 | 100% | NA | NA | 5.556% |  |  | 2021-07-28 | 2021-08-03 | Sous-poste | Sous-poste | 2021-07-30 | 2021-08-05 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 32 | 8 | 2021 | 0 | 0.205 | 0.0205 | 0.2255 | NA | 0 | 0
68457941 | 2019-10-16 | FABRICATION | AD&S | 39 | 6845794 | NON-SPARES | 1 | 1 | AOG | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 29978 | LTE990003 |  | O | O | 100% | 0% | 50% | 100% | 2020-03-11 | 100% | 100% | 2021-03-15 | 100% | NA | OUI | 5.263% |  |  | 2021-12-23 | 2021-08-16 | Sous-poste | Sous-poste | 2021-12-25 | 2021-08-18 |  | OK | Allemagne | Envoyé à LAB le 05/08 pour contrôle/test/EASA F1 - Retour LAB attendu le 13/08 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2019 | 34 | 8 | 2021 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
2855733710 | 2021-03-10 | HA/REVENTE | SATAIR | PLATE ASSY | 28557337 | 155537 | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 44290 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-05 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-08-16 | 2021-08-16 | 22/07/2021 | 80816935 | 2021-08-19 | 2021-08-19 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 7 | 2021 | 3 | 2021 | 34 | 8 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004250350 | 2021-06-09 | FABRICATION | STELIA | 63 | 4900042503 | NON-SPARES | 50 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 45368 | LTE990007 |  | O | O | 100% | 0% | 50% | 72% | 2021-07-20 | NA | 72% | 2021-07-20 | 90% | NA | OUI | 4.737% |  |  | 2021-06-28 | 2021-08-17 | Sous-poste | Sous-poste | 2021-07-01 | 2021-08-20 |  | OK | ROCHEFORT | Manquants: IS0041195S (réception 09/08) IS0034631S IS0031748S (réception TBD à voir avec appros) - Prévoir Contrôle/test EASA à LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 34 | 8 | 2021 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
490004250350 | 2021-06-09 | FABRICATION | STELIA | 63 | 4900042503 | NON-SPARES | 50 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 45368 | LTE990008 |  | O | O | 100% | 0% | 50% | 72% | 2021-07-20 | NA | 72% | 2021-07-20 | 90% | NA | OUI | 4.737% |  |  | 2021-06-28 | 2021-08-17 | Sous-poste | Sous-poste | 2021-07-01 | 2021-08-20 |  | OK | ROCHEFORT | Manquants: IS0041195S (réception 09/08) IS0034631S IS0031748S (réception TBD à voir avec appros) - Prévoir Contrôle/test EASA à LAB | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 34 | 8 | 2021 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990002 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990003 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990004 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990005 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990006 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990007 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990008 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990009 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990010 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990011 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990012 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990013 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990014 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990015 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2861455110 | 2021-07-07 | FABRICATION | SATAIR | 27 | 28614551 | NON-SPARES | 10 | 1 | CRIT | D9551002700895 | IS0059907M | NON PRESENT INDUS | 46169 | LTE990016 |  | O | O | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2021-08-02 | 80% | NA | NA | 4.444% |  |  | 2021-07-30 | 2021-08-18 | Sous-poste | Sous-poste | 2021-08-03 | 2021-08-20 |  | OK | KIT FACTORY | Manquants : IS0006465S IS0009597S IS0012701S(réception 10/08) - Prévoir contrôle + test à LAB car pas de ressource LATE400 COL | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
490004288010 | 2021-07-29 | HA/REVENTE | STELIA | RAMPE 23VU | 4900042880 | NON-SPARES | 10 | 1 | RTN | S9251059700100 | 3STR*00061 | NA | STOCK | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-08-19 | 2021-08-19 | Sous-poste | Sous-poste | 2021-08-24 | 2021-08-24 |  | OK | ROCHEFORT | Prévenir magasin 2 jours avant date d'expé (colonne AL) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 34 | 8 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
68810621 | 2020-12-02 | FABRICATION | AD&S | 31 | 6881062 | NON-SPARES | 1 | 1 | CRIT | MB035ACAAAAC | IS0032197M | NON PRESENT INDUS | 39527 | LTE990002 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-22 | 100% | 100% | 2021-06-28 | 99% | NA | OUI | 5.211% |  |  | 2020-12-07 | 2021-08-23 | Sous-poste | Sous-poste | 2020-12-09 | 2021-08-25 |  | OK | SPARES | Envoyé à LAB pour test le 30/07 - retour courant CW32 avec EASA faite par LAB | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2020 | 35 | 8 | 2021 | 0.36 | 4.1408 | 1.0352 | 5.176 | COL | 0 | 0
490004254120 | 2021-06-18 | FABRICATION | STELIA | FAISCEAU | 4900042541 | 161634 | 20 | 24 | RTN | S9110305200195 | IS0060894M | NON PRESENT INDUS | 45370 | 3780098 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-06-23 | 100% | NA | OUI | 5.263% |  |  | 2021-07-13 | 2021-08-25 |  |  | 2021-07-16 | 2021-08-30 |  | OK | ROCHEFORT | Bloquée EASA validation données | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2021 | 35 | 8 | 2021 | 3.6 | 23.76 | 0.12 | 23.88 | COL | 0 | 0
490004254120 | 2021-06-18 | FABRICATION | STELIA | FAISCEAU | 4900042541 | 161634 | 20 | 36 | RTN | S9110305200195 | IS0060894M | NON PRESENT INDUS | 45370 | 3780333 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-06-23 | 100% | NA | OUI | 5.263% |  |  | 2021-07-13 | 2021-08-25 |  |  | 2021-07-16 | 2021-08-30 |  | OK | ROCHEFORT | Manque câble DL22 - Bloquée EASA validation données | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2021 | 35 | 8 | 2021 | 5.4 | 35.64 | 0.12 | 35.76 | COL | 0 | 0
490004254120 | 2021-06-10 | FABRICATION | STELIA | FAISCEAU | 4900042541 | 161634 | 20 | 25 | RTN | S9110305200195 | IS0060894M | NON PRESENT INDUS | 45370 | 3780334 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-07-05 | 100% | NA | OUI | 5.263% |  |  | 2021-07-19 | 2021-08-25 |  |  | 2021-07-22 | 2021-08-30 |  | OK | ROCHEFORT | Bloquée EASA validation données | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2021 | 35 | 8 | 2021 | 3.75 | 24.75 | 0.12 | 24.87 | COL | 0 | 0
2861839910 | 2021-07-15 | FABRICATION | SATAIR | BUNDLE | 28618399 | NON-SPARES | 10 | 7 | RTN | V9253120000096 | IS0032173M | NON PRESENT INDUS | 46483 | 3798867 |  | O | O | 100% | 0% | 50% | 100% | 2021-07-23 | NA | 100% | 2021-08-02 | 0% | NA | NA | 0% |  |  | 2021-09-06 | 2021-09-06 | Sous-poste | Sous-poste | 2021-09-09 | 2021-09-09 |  | OK | KIT FACTORY | OF en prod - Stock BDL | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 37 | 9 | 2021 | 0.9023 | 1.0185 | 0.1 | 1.1185 | COL | 0 | 0
2861840010 | 2021-07-15 | FABRICATION | SATAIR | BUNDLE | 28618400 | NON-SPARES | 10 | 7 | RTN | V9253110000096 | IS0032170M | NON PRESENT INDUS | 46483 | 3802647 |  | O | O | 100% | 0% | 50% | 100% | 2021-07-23 | NA | 100% | 2021-08-02 | 0% | NA | NA | 0% |  |  | 2021-09-06 | 2021-09-06 | Sous-poste | Sous-poste | 2021-09-09 | 2021-09-09 |  | OK | KIT FACTORY | OF en prod - Stock BDL | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 37 | 9 | 2021 | 0.9023 | 1.0185 | 0.1 | 1.1185 | COL | 0 | 0
490004176010 | 2021-02-15 | FABRICATION | STELIA | 22 | 4900041760 | NON-SPARES | 10 | 1 | RTN | S9251279400056 | IS0060073M | NON PRESENT INDUS | 40862 | LTE990001 |  | O | O | 100% | 0% | 50% | 100% | 2021-03-29 | NA | 100% | 2021-03-26 | 100% | NA | OUI | 5.263% |  |  | 2021-03-15 | 2021-09-07 | Sous-poste | Sous-poste | 2021-03-18 | 2021-09-10 |  | OK | ROCHEFORT | Attente réception dépannage client | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2021 | 37 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004289210 | 2021-08-16 | FABRICATION | STELIA | HARNAIS | 4900042892 | NON-SPARES | 10 | 2 | CRIT | S956G1120108451 | IS0061723M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | 0% |  |  | 2021-09-08 | 2021-09-08 | Sous-poste | Sous-poste | 2021-09-10 | 2021-09-10 |  | OK | ROCHEFORT |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 37 | 9 | 2021 | 0.74 | 6 | 1.16 | 7.16 | LIP | 0 | 0
2859675310 | 2021-05-12 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28596753 | NON-SPARES | 10 | 1 | EXP | A27912401007C10 | IS0032628M | NON PRESENT INDUS | 44454 | 3782529 |  | O | O | 100% | 0% | 50% | 100% | 2021-05-26 | 100% | 100% | 2021-07-28 | 100% | NA | NA | 5.556% |  |  | 2021-06-08 | 2021-09-09 | Sous-poste | Sous-poste | 2021-06-11 | 2021-09-14 |  | OK | SPARES | Servitude en prod non commencé le 05/08 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 37 | 9 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2859739510 | 2021-05-31 | FABRICATION | SATAIR | 313 | 28597395 | NON-SPARES | 10 | 1 | EXP | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 44881 | LTE990007 |  | O | O | 100% | 0% | 50% | 94% | TBD | 100% | 94.6% | 2021-07-19 | 100% | NA | NA | 5.556% |  |  | 2021-08-26 | 2021-09-13 | Sous-poste | Sous-poste | 2021-08-31 | 2021-09-16 |  | OK | SPARES | Étiquette PN à demander à LAB - TEST LAB à prévoir/organiser | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 38 | 9 | 2021 | 0.51 | 3.85 | 0.9625 | 4.8125 | COL | 0 | 0
2858630810 | 2021-05-10 | FABRICATION | SATAIR | PROTECTION CAP | 28586308 | NON-SPARES | 10 | 100 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 44241 | 3800592 |  | O | O | 100% | 0% | 50% | 100% | 2021-06-15 | NA | 100% | 2021-08-05 | 100% | NA | NA | 5.556% |  |  | 2021-08-30 | 2021-09-16 | Sous-poste | Sous-poste | 2021-09-02 | 2021-09-21 |  | OK | KIT FACTORY | Servitude en prod | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 38 | 9 | 2021 | 0.25 | 11.18 | 0.01118 | 11.1912 | NA | 0 | 0
2856742010 | 2021-04-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28567420 | 157896 | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 43228 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-05-20 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-16 | 2021-09-16 | 22/07/2021 | 80816936 | 2021-09-21 | 2021-09-21 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 7 | 2021 | 4 | 2021 | 38 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817063 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817064 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817065 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817066 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817067 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
prev COAX_FFK | 2021-08-31 | FABRICATION | STELIA | CÂBLE | prev COAX_FFK | NON-SPARES |  | 1 |  | S9291306500000 | IS0032228M | NON PRESENT INDUS | NA | 3817068 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-08 | NA | 100% | 2021-09-15 | 100% | NA | NA | 5.556% |  |  | 2021-09-17 | 2021-09-17 | Sous-poste | Sous-poste | 2021-09-22 | 2021-09-22 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 38 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2864800210 | 2021-09-15 | FABRICATION | SATAIR | OPTICAL FIBER | 28648002 | NON-SPARES | 10 | 1 | CRIT | V9271700820000 | IS0061276M | NON PRESENT INDUS | NA | 3822060 |  | O | O | 0% | 0% | 0% | 100% | 2021-09-15 | NA | 100% | 2021-09-16 | 100% | NA | NA | 5.556% |  |  | 2021-09-14 | 2021-09-21 | Sous-poste | Sous-poste | 2021-09-16 | 2021-09-23 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 39 | 9 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
2822209510 | 2019-07-18 | FABRICATION | SATAIR | 429 | 28222095 | NON-SPARES | 10 | 1 | RTN | A9550042972695 | IS0032613M | NON PRESENT INDUS | 42169 | LTE990009 |  | O | O | 100% | 0% | 50% | 100% | 2021-07-19 | 100% | 100% | 2021-07-05 | 100% | NA | NA | 5.556% |  |  | 2021-03-02 | 2021-09-21 | Sous-poste | Sous-poste | 2021-03-05 | 2021-09-24 |  | OK | Allemagne | Confié cassé - Attente refourniture par le client | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 | 39 | 9 | 2021 | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
P2915221 1 | 2021-06-03 | FABRICATION | AIS | 265 | P2915221 | NON-SPARES | 1 | 1 | RTN | MD501-311101-01B | IS0032603M | NON PRESENT INDUS | 45065 | LTE990008 |  | O | O | 100% | 0% | 50% | 100% | TBD | 100% | 100% | 2021-08-02 | 100% | NA | OUI | 5.263% |  |  | 2021-09-01 | 2021-09-23 | Sous-poste | Sous-poste | 2021-09-06 | 2021-09-28 |  |  |  | TEST en cours LAB - Retour attendu le 23/09 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 39 | 9 | 2021 | 0.205 | 1.16 | 0.38 | 1.54 | COL | 0 | 0
P2915221 2 | 2021-06-03 | FABRICATION | AIS | 265 | P2915221 | NON-SPARES | 2 | 1 | RTN | MD501-311101-01B | IS0032603M | NON PRESENT INDUS | 45065 | LTE990009 |  | O | O | 100% | 0% | 50% | 100% | TBD | 100% | 100% | 2021-08-02 | 100% | NA | OUI | 5.263% |  |  | 2021-09-01 | 2021-09-23 | Sous-poste | Sous-poste | 2021-09-06 | 2021-09-28 |  |  |  | TEST en cours LAB - Retour attendu le 23/09 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 39 | 9 | 2021 | 0.205 | 1.16 | 0.38 | 1.54 | COL | 0 | 0
2862720610 | 2021-08-06 | FABRICATION | SATAIR | 313 | 28627206 | 163879 | 10 | 1 | EXP | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 47579 | LTE990008 |  | O | O | 100% | 0% | 50% | 100% | 2021-09-10 | 0% | 90% | 2021-09-13 | 90% | NA | NA | 5% |  |  | 2021-08-31 | 2021-09-27 |  |  | 2021-09-03 | 2021-09-30 |  |  | SPARES | Manquant IS0006729S - IS0007482S - IS0056380S (FIP) | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2021 | 40 | 9 | 2021 | 0.51 | 3.85 | 0.9625 | 4.8125 | COL | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816027 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816028 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816029 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816030 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816031 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004277610 | 2021-07-09 | FABRICATION | STELIA | CÂBLE | 4900042776 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816032 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-09-27 | Sous-poste | Sous-poste | 2021-09-15 | 2021-09-30 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2861845010 | 2021-07-15 | HA/REVENTE | SATAIR | RACEWAY ASSY | 28618450 | NON-SPARES | 10 | 1 | AOG | V9247233800000 | IS0057051S | NA | 44483 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-09-08 | 2021-09-28 | Sous-poste | Sous-poste | 2021-09-10 | 2021-09-30 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2862096910 | 2021-07-22 | HA/REVENTE | SATAIR | RACEWAY ASSY | 28620969 | NON-SPARES | 10 | 1 | AOG | V9247239600000 | IS0057090S | NA | 44483 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-09-08 | 2021-09-28 | Sous-poste | Sous-poste | 2021-09-10 | 2021-09-30 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 40 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2864283110 | 2021-09-06 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28642831 | NON-SPARES | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 47584 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-09-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-03 | 2021-09-29 | Sous-poste | Sous-poste | 2021-09-07 | 2021-10-01 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 40 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2864174310 | 2021-09-02 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28641743 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 47584 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-09-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-29 | 2021-09-29 | Sous-poste | Sous-poste | 2021-10-02 | 2021-10-02 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 40 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2864247610 | 2021-09-06 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28642476 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 47584 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-09-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-29 | 2021-09-29 | Sous-poste | Sous-poste | 2021-10-03 | 2021-10-03 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 40 | 9 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816033 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816034 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816035 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816036 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816037 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004280920 | 2021-07-15 | FABRICATION | STELIA | CÂBLE | 4900042809 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 46251 | 3816038 |  | O | O | 100% | 0% | 50% | 100% | 2021-08-10 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-04 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2861209010 | 2021-07-01 | FABRICATION | SATAIR | 109 | 28612090 | NON-SPARES | 10 | 1 | AOG | D9251076700400 | IS0061064M | NON PRESENT INDUS | 44968 | 3829641 |  | O | O | 100% | 0% | 50% | 100% | 2021-09-29 | NA | 100% | 2021-09-28 | 100% | NA | NA | 5.556% |  |  | 2021-07-13 | 2021-10-04 | Sous-poste | Sous-poste | 2021-07-15 | 2021-10-06 |  | OK | KIT FACTORY | OP à convertir/lancer + dossier prod à faire suivant exemple | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 41 | 10 | 2021 | 0 | 0.4 | 0.1 | 0.5 | COL | 0 | 0
490004291020 | 2021-08-28 | FABRICATION | STELIA | CÂBLE | 4900042910 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 47583 | 3819486 |  | 0 | 0 | 100% | 100% | 100% | 94% | TBD | NA | 94% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-10-01 | 2021-10-05 | Sous-poste | Sous-poste | 2021-10-06 | 2021-10-08 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004291020 | 2021-08-18 | FABRICATION | STELIA | CÂBLE | 4900042910 | NON-SPARES | 20 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 47583 | 3819487 |  | 0 | 0 | 100% | 100% | 100% | 94% | TBD | NA | 94% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-10-01 | 2021-10-05 | Sous-poste | Sous-poste | 2021-10-06 | 2021-10-08 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 41 | 10 | 2021 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
2858631010 | 2021-05-10 | FABRICATION | SATAIR | PROTECTION CAP | 28586310 | NON-SPARES | 10 | 29 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 44241 | 3828739 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-03 | NA | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-11 | 2021-10-11 | Sous-poste | Sous-poste | 2021-10-14 | 2021-10-14 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 42 | 10 | 2021 | 0.0725 | 3.2422 | 0.01118 | 3.2534 | NA | 0 | 0
2862161010 | 2021-07-23 | FABRICATION | SATAIR | BUNDLE | 28621610 | NON-SPARES | 10 | 1 | RTN | D9000095477995 | IS0032050M | NON PRESENT INDUS | 46692 | 3815931 |  | 0 | 0 | 100% | 100% | 100% | 80% | TBD | NA | 80% | 2021-09-13 | 100% | NA | NA | 5.556% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-14 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0
490004277620 | 2021-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900042776 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3815988 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004277620 | 2021-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900042776 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3815989 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004277620 | 2021-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900042776 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3815990 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004277620 | 2021-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900042776 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3815991 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004277620 | 2021-07-09 | FABRICATION | STELIA | CABLE COAXIAL | 4900042776 | NON-SPARES | 20 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3815992 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-13 | 100% | NA | OUI | 5.263% |  |  | 2021-09-10 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004280910 | 2021-07-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900042809 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3819488 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004280910 | 2021-07-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900042809 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3819489 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004280910 | 2021-07-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900042809 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3819490 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004280910 | 2021-07-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900042809 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3819491 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004280910 | 2021-07-15 | FABRICATION | STELIA | CABLE COAXIAL | 4900042809 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 46248 | 3819492 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-28 | NA | 100% | 2021-09-20 | 100% | NA | OUI | 5.263% |  |  | 2021-09-16 | 2021-10-11 | Sous-poste | Sous-poste | 2021-09-21 | 2021-10-12 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 42 | 10 | 2021 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
2866469610 | 2021-10-19 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28664696 | NON-SPARES | 10 | 1 | AOG | D9251095600000 | IS0053509S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-10-15 | 2021-10-19 | Sous-poste | Sous-poste | 2021-10-19 | 2021-10-21 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858764510 | 2021-05-11 | HA/REVENTE | SATAIR | PLATE ASSY | 28587645 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 44290 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-05 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-10-19 | 2021-10-19 | Sous-poste | Sous-poste | 2021-10-22 | 2021-10-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2860108610 | 2021-06-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28601086 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 | 3819412 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-13 | 100% | 100% | 2021-09-20 | 100% | NA | NA | 5.556% |  |  | 2021-09-01 | 2021-10-19 | Sous-poste | Sous-poste | 2021-09-06 | 2021-10-22 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 43 | 10 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2860108620 | 2021-08-16 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28601086 | NON-SPARES | 20 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 | 3819413 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-13 | 100% | 100% | 2021-09-20 | 100% | NA | NA | 5.556% |  |  | 2021-09-01 | 2021-10-19 | Sous-poste | Sous-poste | 2021-09-06 | 2021-10-22 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 43 | 10 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2860108630 | 2021-08-16 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28601086 | NON-SPARES | 30 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 | 3819414 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-13 | 100% | 100% | 2021-09-20 | 100% | NA | NA | 5.556% |  |  | 2021-09-01 | 2021-10-19 | Sous-poste | Sous-poste | 2021-09-06 | 2021-10-22 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 43 | 10 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2865115210 | 2021-09-28 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28651152 | NON-SPARES | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 48382 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-10-19 | 2021-10-19 | Sous-poste | Sous-poste | 2021-10-22 | 2021-10-22 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2864026310 | 2021-08-31 | FABRICATION | SATAIR | 612 | 28640263 | NON-SPARES | 10 | 1 | AOG | WF426AEAAAAE | IS0061230M | NON PRESENT INDUS | 47784 | LTE990001 |  | 0 | 0 | 100% | 100% | 100% | 68% | TBD | 100% | 71.2% | 2021-10-11 | 95% | NA | NA | 5.278% |  |  | 2021-09-27 | 2021-10-20 | Sous-poste | Sous-poste | 2021-09-29 | 2021-10-22 |  | OK | SPARES | Manquant IS0007482S qté 2 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 43 | 10 | 2021 | 0.205 | 2.09 | 0.51 | 2.6 | NA | 0 | 0
490004254110 | 2021-06-10 | FABRICATION | STELIA | FAISCEAU | 4900042541 | 161634 | 10 | 100 | RTN | S9110305200195 | IS0060894M | NON PRESENT INDUS | 45370 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2021-10-11 | 0% | NA | OUI | 0% |  |  | 2021-07-19 | 2021-10-21 |  |  | 2021-07-22 | 2021-10-26 |  | OK | ROCHEFORT |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2021 | 43 | 10 | 2021 | 15 | 99 | 0.12 | 99.12 | COL | 0 | 0
2862161020 | 2021-07-23 | FABRICATION | SATAIR | BUNDLE | 28621610 | NON-SPARES | 20 | 1 | RTN | D9000095477995 | IS0032050M | NON PRESENT INDUS | 46692 | 3815932 |  | 0 | 0 | 100% | 100% | 100% | 80% | TBD | NA | 80% | 2021-09-13 | 100% | NA | NA | 5.556% |  |  | 2021-09-10 | 2021-10-22 | Sous-poste | Sous-poste | 2021-09-15 | 2021-10-27 |  | OK | KIT FACTORY | Attente reponse SSD - Manquant IS0032081S (Réception le 22/10) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 43 | 10 | 2021 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA | 0 | 0
2865117510 | 2021-09-22 | HA/REVENTE | SATAIR | RACEWAY ASSY | 28651175 | NON-SPARES | 10 | 1 | AOG | V9247240400000 | IS0057700S | NA | 48211 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-09-21 | 2021-10-22 | Sous-poste | Sous-poste | 2021-09-23 | 2021-10-26 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865148110 | 2021-09-28 | HA/REVENTE | SATAIR | RACEWAY ASSY | 28651481 | NON-SPARES | 10 | 1 | AOG | V9247239800000 | IS0057804S | NA | 48211 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-09-21 | 2021-10-22 | Sous-poste | Sous-poste | 2021-09-23 | 2021-10-26 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865148910 | 2021-09-28 | HA/REVENTE | SATAIR | RACEWAY ASSY | 28651489 | NON-SPARES | 10 | 1 | AOG | V9247240100000 | IS0057805S | NA | 48211 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-09-21 | 2021-10-22 | Sous-poste | Sous-poste | 2021-09-23 | 2021-10-26 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 43 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2862828910 | 2021-08-09 | FABRICATION | SATAIR | 27 | 28628289 | NON-SPARES | 10 | 2 | AOG | D9551002700595 | IS0032094M | NON PRESENT INDUS | 47014 | LTE990031 - LTE990032 |  | 0 | 0 | 100% | 100% | 100% | 85% | 2021-09-15 | NA | 85% | 2021-09-14 | 100% | NA | NA | 5.556% |  |  | 2021-08-12 | 2021-10-25 | Sous-poste | Sous-poste | 2021-08-16 | 2021-10-27 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 44 | 10 | 2021 | 0.72 | 9.8346 | 1.2293 | 11.0639 | COL | 0 | 0
490004301410 | 2021-09-02 | FABRICATION | STELIA | HARNAIS | 4900043014 | NON-SPARES | 10 | 4 | RTN | S956G1120108451 | IS0061723M | NON PRESENT INDUS |  | NA |  | NA | NA | 0% | 0% | 0% | 100% | TBD | NA | 100% | NA | NA | NA | OUI | 0% |  |  | 2021-10-26 | 2021-10-26 | Sous-poste | Sous-poste | 2021-10-29 | 2021-10-29 |  | OK | ROCHEFORT | Réception de LIP le 15/10 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 44 | 10 | 2021 | 1.48 | 12 | 1.16 | 13.16 | LIP | 0 | 0
490004300810 | 2021-09-01 | HA/REVENTE | STELIA | CAPOT | 4900043008 | NON-SPARES | 10 | 2 | RTN | S9251363300100 | IS0054056S | NA | 47588 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-10-26 | 2021-10-26 | Sous-poste | Sous-poste | 2021-10-29 | 2021-10-29 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 44 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866410510 | 2021-10-18 | FABRICATION | SATAIR | OPTICAL FIBER | 28664105 | NON-SPARES | 10 | 1 | AOG | D9000095029495 | IS0032047M | NON PRESENT INDUS | NA | 3844337 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2021-10-20 | NA | 100% | 2021-10-21 | 100% | NA | NA | 5.556% |  |  | 2021-10-14 | 2021-10-26 | Sous-poste | Sous-poste | 2021-10-18 | 2021-10-28 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 44 | 10 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866932610 | 2021-10-27 | FABRICATION | SATAIR | PLACARD SET | 28669326 | NON-SPARES | 10 | 10 | CRIT | D9100095600395 | IS0032064M | NON PRESENT INDUS | NA | 3848471 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2021-10-27 | NA | 100% | 2021-10-27 | 100% | NA | NA | 5.556% |  |  | 2021-11-01 | 2021-10-27 | Sous-poste | Sous-poste | 2021-11-03 | 2021-10-29 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 44 | 10 | 2021 | 0 | 2.05 | 0.0205 | 2.0705 | NA | 0 | 0
2865966510 | 2021-10-11 | FABRICATION | SATAIR | BUNDLE | 28659665 | 167002 | 10 | 1 | AOG | V9253120000095A | IS0059305M | NON PRESENT INDUS | NA | 3838212 |  | 0 | 0 | 0% | 100% | 50% | 0% | TBD | NA | 0% | 2021-10-20 | 0% | NA | NA | 0% |  |  | 2021-10-13 | 2021-10-27 |  |  | 2021-10-15 | 2021-10-29 |  |  | SPARES |  | C |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2021 | 44 | 10 | 2021 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL | 0 | 0
2859723310 | 2021-06-03 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28597233 | NON-SPARES | 10 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 | 3832333 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 100% | 100% | 2021-10-11 | 100% | NA | NA | 5.556% |  |  | 2021-10-27 | 2021-10-27 | Sous-poste | Sous-poste | 2021-10-30 | 2021-10-30 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 44 | 10 | 2021 | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
28653773 630227508110 | 2021-09-29 | FABRICATION | SATAIR | EQPT PLATE | 28653773 6302275081 | NON-SPARES | 10 | 1 | AOG | F9252036900000 | IS0061420M | NON PRESENT INDUS | 47907 | 3847377 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-29 | NA | 100% | 2021-10-29 | 0% | NA | NA | 0% |  |  | 2021-10-27 | 2021-11-01 | Sous-poste | Sous-poste | 2021-10-29 | 2021-11-03 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 45 | 11 | 2021 | 0 | 0.1 | 0 | 0.1 | NA | 0 | 0
28653772 630227508210 | 2021-09-29 | FABRICATION | SATAIR | EQPT PLATE | 28653772 6302275082 | NON-SPARES | 10 | 1 | AOG | F9252036900000 | IS0061420M | NON PRESENT INDUS | 47907 | 3847378 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-29 | NA | 100% | 2021-10-29 | 0% | NA | NA | 0% |  |  | 2021-10-27 | 2021-11-01 | Sous-poste | Sous-poste | 2021-10-29 | 2021-11-03 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 45 | 11 | 2021 | 0 | 0.1 | 0 | 0.1 | NA | 0 | 0
2866284610 | 2021-10-14 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28662846 | NON-SPARES | 10 | 5 | AOG | D9251095600000 | IS0053509S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-10-18 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-10-13 | 2021-11-02 | Sous-poste | Sous-poste | 2021-10-15 | 2021-11-04 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2862462410 | 2021-07-29 | FABRICATION | SATAIR | BUNDLE | 28624624 | NON-SPARES | 10 | 7 | RTN | V9253110000096 | IS0032170M | NON PRESENT INDUS | 46483 | 3836976 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-18 | NA | 100% | 2021-10-18 | 100% | NA | NA | 5.556% |  |  | 2021-11-03 | 2021-11-03 | Sous-poste | Sous-poste | 2021-11-08 | 2021-11-08 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0.9023 | 1.0185 | 0.1 | 1.1185 | COL | 0 | 0
2862462510 | 2021-07-29 | FABRICATION | SATAIR | BUNDLE | 28624625 | NON-SPARES | 10 | 7 | RTN | V9253120000096 | IS0032173M | NON PRESENT INDUS | 46483 | 3836977 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-18 | NA | 100% | 2021-10-18 | 100% | NA | NA | 5.556% |  |  | 2021-11-03 | 2021-11-03 | Sous-poste | Sous-poste | 2021-11-08 | 2021-11-08 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0.9023 | 1.0185 | 0.1 | 1.1185 | COL | 0 | 0
P29311211 | 2021-09-06 | FABRICATION | AIS | 265 | P2931121 | NON-SPARES | 1 | 1 | RTN | MD501-311101-01B | IS0032603M | NON PRESENT INDUS | 45065 | LTE900010 |  | 0 | 0 | 100% | 100% | 100% | 90% | TBD | NA | 90% | 2021-10-18 | 90% | NA | OUI | 4.737% |  |  | 2021-11-04 | 2021-11-04 | Sous-poste | Sous-poste | 2021-11-09 | 2021-11-09 |  | OK |  | Manquants IS0012641S (NAS1102E066) qté 2 et confié IS0056373S (ABS1643ACSB007) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 45 | 11 | 2021 | 0.205 | 1.16 | 0.38 | 1.54 | COL | 0 | 0
450113435810 | 2021-07-02 | FABRICATION | LATECOERE | FDVESS-L3 | 4501134358 | NON-SPARES | 10 | 1 |  | 1288L3000010 | IS0033482M | NON PRESENT INDUS | 45443 | 71130011 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-09-22 | 80% | 0% | NA | 4.211% |  |  | 2021-09-07 | 2021-11-04 | Sous-poste | Sous-poste | 2021-09-10 | 2021-11-09 |  |  |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
2867156510 | 2021-11-01 | HA/REVENTE | SATAIR | FLANGE ASSY | 28671565 | NON-SPARES | 10 | 2 | CRIT | D9251127600000 | IS0008826S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-10-29 | 2021-11-04 | Sous-poste | Sous-poste | 2021-11-02 | 2021-11-08 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
450113435820 | 2021-07-02 | FABRICATION | LATECOERE | FDVESS-L3 | 4501134358 | NON-SPARES | 20 | 1 |  | 1288L3000010 | IS0033482M | NON PRESENT INDUS | 45443 | 71130012 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-09-22 | 80% | NA | NA | 4.444% |  |  | 2021-10-19 | 2021-11-04 | Sous-poste | Sous-poste | 2021-10-22 | 2021-11-09 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
450113435820 | 2021-07-02 | FABRICATION | LATECOERE | FDVESS-L3 | 4501134358 | NON-SPARES | 20 | 1 |  | 1288L3000010 | IS0033482M | NON PRESENT INDUS | 45443 | 71130013 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-09-22 | 80% | NA | NA | 4.444% |  |  | 2021-10-19 | 2021-11-04 | Sous-poste | Sous-poste | 2021-10-22 | 2021-11-09 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
450113435820 | 2021-07-02 | FABRICATION | LATECOERE | FDVESS-L3 | 4501134358 | NON-SPARES | 20 | 1 |  | 1288L3000010 | IS0033482M | NON PRESENT INDUS | 45443 | 71130014 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-09-22 | 80% | NA | NA | 4.444% |  |  | 2021-10-19 | 2021-11-04 | Sous-poste | Sous-poste | 2021-10-22 | 2021-11-09 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
450113435820 | 2021-07-02 | FABRICATION | LATECOERE | FDVESS-L3 | 4501134358 | NON-SPARES | 20 | 1 |  | 1288L3000010 | IS0033482M | NON PRESENT INDUS | 45443 | 71130015 |  | 0 | 0 | 100% | 100% | 100% | 0% | TBD | NA | 0% | 2021-09-22 | 80% | NA | NA | 4.444% |  |  | 2021-10-19 | 2021-11-04 | Sous-poste | Sous-poste | 2021-10-22 | 2021-11-09 |  | OK |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 45 | 11 | 2021 | 0 | 0 | 0 | 0 | COL | 0 | 0
2856742710 | 2021-04-07 | FABRICATION | SATAIR | 117 | 28567427 | NON-SPARES | 10 | 1 | AOG | D9550011700295 | IS0032071M | NON PRESENT INDUS | 43229 | LTE990162 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-05 | NA | 100% | 2021-10-11 | 100% | NA | NA | 5.556% |  |  | 2021-10-27 | 2021-11-08 | Sous-poste | Sous-poste | 2021-10-29 | 2021-11-10 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 46 | 11 | 2021 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2860605010 | 2021-06-18 | FABRICATION | SATAIR | 60 | 28606050 | NON-SPARES | 10 | 1 | AOG | D9551006000195 | IS0032114M | NON PRESENT INDUS | 45564 | LTE990006 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 0% | 90% | 2021-10-12 | 100% | NA | NA | 5.556% |  |  | 2021-10-28 | 2021-11-08 | Sous-poste | Sous-poste | 2021-11-01 | 2021-11-10 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 46 | 11 | 2021 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2860605110 | 2021-06-18 | FABRICATION | SATAIR | 61 | 28606051 | NON-SPARES | 10 | 1 | AOG | D9551006100195 | IS0032120M | NON PRESENT INDUS | 45564 | LTE990006 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 0% | 90% | 2021-10-12 | 100% | NA | NA | 5.556% |  |  | 2021-10-28 | 2021-11-08 | Sous-poste | Sous-poste | 2021-11-01 | 2021-11-10 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 46 | 11 | 2021 | 0.205 | 1.3425 | 0.33563 | 1.6781 | COL | 0 | 0
2860605210 | 2021-06-18 | FABRICATION | SATAIR | 62 | 28606052 | NON-SPARES | 10 | 1 | AOG | D9551006200195 | IS0032126M | NON PRESENT INDUS | 45564 | LTE990006 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 0% | 90% | 2021-10-12 | 100% | NA | NA | 5.556% |  |  | 2021-10-28 | 2021-11-08 | Sous-poste | Sous-poste | 2021-11-01 | 2021-11-10 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 46 | 11 | 2021 | 0.205 | 1.8647 | 0.46618 | 2.3309 | COL | 0 | 0
2862282610 | 2021-07-27 | FABRICATION | SATAIR | 510 | 28622826 | NON-SPARES | 10 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 46727 | LTE990010 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-09 | 100% | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-20 | 2021-11-10 | Sous-poste | Sous-poste | 2021-10-24 | 2021-11-15 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 46 | 11 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2862282620 | 2021-07-27 | FABRICATION | SATAIR | 510 | 28622826 | NON-SPARES | 20 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 46727 | LTE990011 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-09 | 100% | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-20 | 2021-11-10 | Sous-poste | Sous-poste | 2021-10-24 | 2021-11-15 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 46 | 11 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2862282630 | 2021-07-27 | FABRICATION | SATAIR | 510 | 28622826 | NON-SPARES | 30 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 46727 | LTE990012 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-09 | 100% | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-20 | 2021-11-10 | Sous-poste | Sous-poste | 2021-10-24 | 2021-11-15 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 46 | 11 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2862282640 | 2021-07-27 | FABRICATION | SATAIR | 510 | 28622826 | NON-SPARES | 40 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 46727 | LTE990013 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-09 | 100% | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-20 | 2021-11-10 | Sous-poste | Sous-poste | 2021-10-24 | 2021-11-15 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 46 | 11 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2862282650 | 2021-07-27 | FABRICATION | SATAIR | 510 | 28622826 | NON-SPARES | 50 | 1 | RTN | A9550051000296 | IS0031992M | NON PRESENT INDUS | 46727 | LTE990014 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-09 | 100% | 100% | 2021-10-04 | 100% | NA | NA | 5.556% |  |  | 2021-10-20 | 2021-11-10 | Sous-poste | Sous-poste | 2021-10-24 | 2021-11-15 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2021 | 46 | 11 | 2021 | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2863279110 | 2021-08-18 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28632791 | NON-SPARES | 10 | 6 | RTN | D9251490100000 | IS0032740S | NA | 47543 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-10-20 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-12 | 2021-11-12 | Sous-poste | Sous-poste | 2021-11-17 | 2021-11-17 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 46 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2859052110 | 2021-05-19 | FABRICATION | SATAIR | PROTECTION CAP | 28590521 | NON-SPARES | 10 | 70 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 44241 | 3832331 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-03 | NA | 100% | 2021-10-11 | 98% | NA | NA | 5.444% |  |  | 2021-10-18 | 2021-11-15 | Sous-poste | Sous-poste | 2021-10-21 | 2021-11-18 |  | OK | KIT FACTORY | Manquant IS0013090S qté 2 - réception 09/11 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 47 | 11 | 2021 | 0.175 | 7.826 | 0.01118 | 7.8372 | NA | 0 | 0
2858816110 | 2021-05-12 | HA/REVENTE | SATAIR | BRACKET | 28588161 | NON-SPARES | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 44390 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-10-18 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-16 | 2021-11-16 | Sous-poste | Sous-poste | 2021-11-19 | 2021-11-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 47 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858816010 | 2021-05-12 | HA/REVENTE | SATAIR | PLATE ASSY | 28588160 | NON-SPARES | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 44290 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-07-05 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-18 | 2021-11-18 | Sous-poste | Sous-poste | 2021-11-23 | 2021-11-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 47 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2863508810 | 2021-08-20 | HA/REVENTE | SATAIR | PLATE ASSY | 28635088 | NON-SPARES | 10 | 5 | RTN | A9251152500000 | IS0031658S | NA | 47580 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-10-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-18 | 2021-11-18 | Sous-poste | Sous-poste | 2021-11-23 | 2021-11-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 47 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866284620 | 2021-10-14 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28662846 | NON-SPARES | 20 | 1 | AOG | D9251095600000 | IS0053509S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-23 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-23 | 2021-11-23 | Sous-poste | Sous-poste | 2021-11-25 | 2021-11-25 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 48 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004254130 | 2021-06-10 | FABRICATION | STELIA | FAISCEAU | 4900042541 | 161634 | 30 | 15 | RTN | S9110305200195 | IS0060894M | NON PRESENT INDUS | 45370 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2021-11-15 | 0% | NA | OUI | 0% |  |  | 2021-11-23 | 2021-11-23 |  |  | 2021-11-26 | 2021-11-26 |  | OK | ROCHEFORT |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2021 | 48 | 11 | 2021 | 2.25 | 14.85 | 0.12 | 14.97 | COL | 0 | 0
490004326410 | 2021-10-21 | FABRICATION | STELIA | HARNAIS | 4900043264 | NON-SPARES | 10 | 2 | EXP | S956G1120108451 | IS0061723M | NON PRESENT INDUS | NA |  |  |  |  | 0% | 0% | 0% | 100% | 2021-10-25 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-11 | 2021-11-29 | Sous-poste | Sous-poste | 2021-11-16 | 2021-12-02 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 49 | 11 | 2021 | 0.74 | 6 | 1.16 | 7.16 | LIP | 0 | 0
2865514410 | 2021-10-01 | HA/REVENTE | SATAIR | BRACKET ASSY | 28655144 | NON-SPARES | 10 | 2 | CRIT | V9251162200000 | IS0057853S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-29 | 2021-11-30 | Sous-poste | Sous-poste | 2021-10-01 | 2021-12-02 |  | OK | KIT FACTORY | Lot QM | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 49 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865514710 | 2021-10-01 | HA/REVENTE | SATAIR | GUTTER ASSY | 28655147 | NON-SPARES | 10 | 2 | CRIT | V9251162300000 | IS0057854S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-29 | 2021-11-30 | Sous-poste | Sous-poste | 2021-10-01 | 2021-12-02 |  | OK | KIT FACTORY | Lot QM | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 49 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865514910 | 2021-10-01 | HA/REVENTE | SATAIR | BRACKET ASSY | 28655149 | NON-SPARES | 10 | 2 | CRIT | V9251162600000 | IS0057855S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-09-29 | 2021-11-30 | Sous-poste | Sous-poste | 2021-10-01 | 2021-12-02 |  | OK | KIT FACTORY | Lot QM | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 49 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865058610 | 2021-09-22 | HA/REVENTE | SATAIR | COVER ASSY | 28650586 | NON-SPARES | 10 | 3 | EXP | A9253115800000 | IS0031675S | NA | 48203 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-08 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-10-18 | 2021-11-30 | Sous-poste | Sous-poste | 2021-10-21 | 2021-12-03 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2021 | 49 | 11 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004322270 | 2021-10-13 | HA/REVENTE | STELIA | PLATINE ARRIERE 26VU | 4900043222 | NON-SPARES | 70 | 2 | RTN | S9251590500000 | IS0035439S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-02 | 2021-12-07 | Sous-poste | Sous-poste | 2021-12-07 | 2021-12-10 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 50 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004328910 | 2021-10-21 | HA/REVENTE | STELIA | RONDELLE | 4900043289 | NON-SPARES | 10 | 8 | RTN | S0003012600000 | IS0013828S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-09 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-09 | 2021-12-09 | Sous-poste | Sous-poste | 2021-12-14 | 2021-12-14 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 50 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2858816910 | 2021-05-12 | FABRICATION | SATAIR | 117 | 28588169 | NON-SPARES | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 44392 | LTE990163 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-09-29 | NA | 100% | 2021-11-02 | 98% | NA | NA | 5.444% |  |  | 2021-11-17 | 2021-12-14 | Sous-poste | Sous-poste | 2021-11-22 | 2021-12-17 |  | OK | KIT FACTORY | Réception ETEC IS0032555S le 14/12ou le 15/12 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2021 | 51 | 12 | 2021 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2865514510 | 2021-10-01 | HA/REVENTE | SATAIR | BRACKET ASSY | 28655145 | NON-SPARES | 10 | 2 | RTN | V9251162200000 | IS0057853S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-14 | 2021-12-14 | Sous-poste | Sous-poste | 2021-12-17 | 2021-12-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865514810 | 2021-10-01 | HA/REVENTE | SATAIR | GUTTER ASSY | 28655148 | NON-SPARES | 10 | 2 | RTN | V9251162300000 | IS0057854S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-14 | 2021-12-14 | Sous-poste | Sous-poste | 2021-12-17 | 2021-12-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868431810 | 2021-11-17 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28684318 | NON-SPARES | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-14 | 2021-12-14 | Sous-poste | Sous-poste | 2021-12-17 | 2021-12-17 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868951210 | 2021-11-24 | HA/REVENTE | SATAIR | BRACKET | 28689512 | NON-SPARES | 10 | 1 | AOG | A9253116020000 | IS0031653S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-12-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-22 | 2021-12-15 | Sous-poste | Sous-poste | 2021-11-24 | 2021-12-17 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868951110 | 2021-11-24 | HA/REVENTE | SATAIR | HINGE | 28689511 | NON-SPARES | 10 | 1 | AOG | A9253116220000 | IS0031676S | NA | NA | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-12-10 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-22 | 2021-12-15 | Sous-poste | Sous-poste | 2021-11-24 | 2021-12-17 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2859697610 | 2021-06-02 | HA/REVENTE | SATAIR | BRACKET | 28596976 | NON-SPARES | 10 | 12 | RTN | A9252496620200 | IS0053087S | NA | 44945 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-10-18 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-16 | 2021-12-16 | Sous-poste | Sous-poste | 2021-12-21 | 2021-12-21 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
2859697710 | 2021-06-02 | HA/REVENTE | SATAIR | PLATE ASSY | 28596977 | NON-SPARES | 10 | 5 | RTN | A9251152500000 | IS0031658S | NA | 44945 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-16 | 2021-12-16 | Sous-poste | Sous-poste | 2021-12-21 | 2021-12-21 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 | 51 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004322260 | 2021-10-13 | FABRICATION | STELIA | 63 | 4900043222 | NON-SPARES | 60 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 48842 | LTE990009 |  | 0 | 0 | 100% | 100% | 100% | 0% | 2021-12-09 | NA | 0% | 2021-12-13 | 100% | NA | OUI | 5.263% |  |  | 2021-12-02 | 2021-12-20 | Sous-poste | Sous-poste | 2021-12-07 | 2021-12-23 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 52 | 12 | 2021 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
2868441310 | 2021-11-17 | FABRICATION | SATAIR | PROTECTION CAP | 28684413 | NON-SPARES | 10 | 8 | EXP | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 | 3871170 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-12-08 | NA | 100% | 2021-12-10 | 100% | NA | NA | 5.556% |  |  | 2021-12-14 | 2021-12-20 | Sous-poste | Sous-poste | 2021-12-17 | 2021-12-23 |  | OK | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 52 | 12 | 2021 | 0.02 | 0.8944 | 0.01118 | 0.90558 | NA | 0 | 0
490004322260 | 2021-10-13 | FABRICATION | STELIA | 63 | 4900043222 | NON-SPARES | 60 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS | 48842 | LTE990010 |  | 0 | 0 | 100% | 100% | 100% | 0% | 2021-12-09 | NA | 0% | 2021-12-13 | 100% | NA | OUI | 5.263% |  |  | 2021-12-02 | 2021-12-20 | Sous-poste | Sous-poste | 2021-12-07 | 2021-12-23 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 52 | 12 | 2021 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
490004331910 | 2021-11-02 | HA/REVENTE | STELIA | CAPOT | 4900043319 | NON-SPARES | 10 | 2 | RTN | S9251363300100 | IS0054056S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-11-08 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-10 | 2021-12-21 | Sous-poste | Sous-poste | 2021-12-15 | 2021-12-24 |  | OK | ROCHEFORT | Erreur de stock (attente retour JGI) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 52 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004323710 | 2021-10-18 | HA/REVENTE | SATAIR | RAMPE 121VU | 4900043237 | NON-SPARES | 10 | 4 | EXP | S9252350700000 | IS0058054S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-12-20 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-11-02 | 2021-12-21 | Sous-poste | Sous-poste | 2021-11-05 | 2021-12-24 |  | OK | ROCHEFORT | Collab Étienne | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 52 | 12 | 2021 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004291010 | 2021-08-18 | FABRICATION | STELIA | CABLE COAXIAL | 4900042910 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 47583 | 3868293 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-11-15 | NA | 100% | 2021-12-06 | 100% | NA | OUI | 5.263% |  |  | 2021-10-01 | 2022-01-04 | Sous-poste | Sous-poste | 2021-10-06 | 2022-01-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 2 | 1 | 2022 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004291010 | 2021-08-18 | FABRICATION | STELIA | CABLE COAXIAL | 4900042910 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 47583 | 3868294 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-11-15 | NA | 100% | 2021-12-06 | 100% | NA | OUI | 5.263% |  |  | 2021-10-01 | 2022-01-04 | Sous-poste | Sous-poste | 2021-10-06 | 2022-01-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 2 | 1 | 2022 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
490004291010 | 2021-08-18 | FABRICATION | STELIA | CABLE COAXIAL | 4900042910 | NON-SPARES | 10 | 1 | RTN | S9110104500195 | IS0032220M | NON PRESENT INDUS | 47583 | 3868295 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-11-15 | NA | 100% | 2021-12-06 | 100% | NA | OUI | 5.263% |  |  | 2021-10-01 | 2022-01-04 | Sous-poste | Sous-poste | 2021-10-06 | 2022-01-07 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 | 2 | 1 | 2022 | 0.1926 | 0.7513 | 0.07513 | 0.82643 | NA | 0 | 0
68727191 | 2020-09-04 | FABRICATION | AD&S | 11 | 6872719 | 151636 | 1 | 1 | EXP | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 37054 | LTE990002 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 100% | 100% | 2021-12-20 | 100% | NA | OUI | 5.263% |  |  | 2021-11-25 | 2022-01-07 | 14/01/2022 | 80860456 | 2021-11-30 | 2022-01-12 |  | OK | SEVILLE |  | O |  | 1 | N | N | N | 1 | 2022 | 9 | 2020 | 2 | 1 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
68752671 | 2020-09-30 | FABRICATION | AD&S | 39 | 6875267 | 151147 | 1 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 37837 | LTE990006 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | 100% | 100% | 2021-11-02 | 100% | NA | OUI | 5.263% |  |  | 2021-11-25 | 2022-01-07 | 10/01/2022 | 80859007 | 2021-11-30 | 2022-01-12 |  | OK | SPARES |  | O |  | 1 | O | N | N | 1 | 2022 | 9 | 2020 | 2 | 1 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68782752 | 2020-11-03 | FABRICATION | AD&S | 39 | 6878275 | 152443 | 2 | 1 |  | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990012 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 100% | NA | OUI | 5.263% |  |  | 2021-11-25 | 2022-01-07 | 10/01/2022 | 80859006 | 2021-11-30 | 2022-01-12 |  | OK | SPARES |  | O |  | 1 | O | N | N | 1 | 2022 | 11 | 2020 | 2 | 1 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68795611 | 2020-11-16 | FABRICATION | AD&S | 39 | 6879561 | 152444 | 1 | 1 |  | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990010 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 98% | NA | OUI | 5.158% |  |  | 2021-11-25 | 2022-01-07 | 10/01/2022 | 80859008 | 2021-11-30 | 2022-01-12 |  | OK | SPARES | Manquant IS0024924M (réception le 13/12) | O |  | 1 | O | N | N | 1 | 2022 | 11 | 2020 | 2 | 1 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68782751 | 2020-11-03 | FABRICATION | AD&S | 39 | 6878275 | 152443 | 1 | 1 |  | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990011 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 98% | NA | OUI | 5.158% |  |  | 2021-11-25 | 2022-01-07 | 10/01/2022 | 80859006 | 2021-11-30 | 2022-01-12 |  | OK | SPARES | Manquant IS0024924M (réception le 13/12) | O |  | 1 | O | N | N | 1 | 2022 | 11 | 2020 | 2 | 1 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68858611 | 2021-02-03 | FABRICATION | AD&S | 39 | 6885861 | 153720 | 1 | 1 | CRIT | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 41395 | LTE990005 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-08-04 | 100% | 100% | 2021-12-15 | 100% | NA | OUI | 5.263% |  |  | 2021-08-12 | 2022-01-10 | 10/01/2022 | 80859010 | 2021-08-16 | 2022-01-12 |  | OK | SEVILLE | Manquant IS0024924M (réception le 13/12) | O |  | 0 | O | N | N | 1 | 2022 | 2 | 2021 | 3 | 1 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68803281 | 2021-11-24 | FABRICATION | AD&S | 49 | 6880328 | 157777 | 1 | 1 | RTN | MB042ACABAAA | IS0032206M | NON PRESENT INDUS | 43040 | LTE990005 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-15 | 100% | 100% | 2021-11-02 | 100% | NA | OUI | 5.263% |  |  | 2021-06-25 | 2022-01-11 | 14/01/2022 | 80860457 | 2021-06-30 | 2022-01-14 |  | OK | SEVILLE | Manquant IS0006713S (réception le 13/12) | O |  | 1 | O | N | N | 1 | 2022 | 11 | 2021 | 3 | 1 | 2022 | 0.205 | 2.39 | 0.5975 | 2.9875 | COL | 0 | 0
68578381 | 2020-02-28 | FABRICATION | AD&S | 15 | 6857838 | 144336 | 1 | 1 | CRIT | MB032ADAAAAB | IS0032194M | NON PRESENT INDUS | 33723 | LTE990002 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2020-07-24 | 100% | 100% | 2021-10-14 | 100% | NA | OUI | 5.263% |  |  | 2021-12-23 | 2022-01-12 | Sous-poste | 80860458 | 2021-12-27 | 2022-01-14 |  | OK | SEVILLE |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 | 3 | 1 | 2022 | 0.51 | 7.1148 | 1.7787 | 8.8935 | COL | 0 | 0
2872035010 | 2022-01-06 | HA/REVENTE | SATAIR | PLATE | 28720350 | 170874 | 10 | 2 | AOG | D9251118520000 | IS0008825S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-01-05 | 2022-01-12 | 11/01/2022 | 80859458 | 2022-01-07 | 2022-01-14 |  | OK | SPARES |  | O |  | 0 | O | N | N | 1 | 2022 | 1 | 2022 | 3 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2870430610 | 2021-12-10 | FABRICATION | SATAIR | 518 | 28704306 | 169807 | 10 | 1 | AOG | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990010 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-10 | 100% | 100% | 2022-01-11 | 100% | NA | NA | 5.556% |  |  | 2021-12-08 | 2022-01-14 | 17/01/2022 | 80861207 | 2021-12-10 | 2022-01-18 |  | OK | SPARES |  | O |  | 0 | O | N | N | 1 | 2022 | 12 | 2021 | 3 | 1 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2870622710 | 2021-12-13 | FABRICATION | SATAIR | 518 | 28706227 | 169961 | 10 | 1 | AOG | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990011 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-10 | 100% | 100% | 2022-01-11 | 100% | NA | NA | 5.556% |  |  | 2021-12-09 | 2022-01-14 | 17/01/2022 | 80861208 | 2021-12-13 | 2022-01-18 |  | OK | SPARES |  | O |  | 0 | O | N | N | 1 | 2022 | 12 | 2021 | 3 | 1 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2870884610 | 2021-12-15 | FABRICATION | SATAIR | 518 | 28708846 | 170166 | 10 | 1 | AOG | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990012 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-10 | 100% | 100% | 2022-01-11 | 100% | NA | NA | 5.556% |  |  | 2021-12-13 | 2022-01-14 | 26/01/2022 | 80863744 | 2021-12-15 | 2022-01-18 |  | OK | SPARES |  | O |  | 0 | N | N | N | 1 | 2022 | 12 | 2021 | 3 | 1 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2869514310 | 2021-12-01 | HA/REVENTE | SATAIR | PLACARD SET | 28695143 | 169411 | 10 | 5 | CRIT | V1131450300095A | IS0058454S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-01 | 2022-01-17 | 13/01/2022 | 80860046 | 2021-12-03 | 2022-01-19 |  | OK | KIT FACTORY |  | O |  | 0 | O | N | N | 1 | 2022 | 12 | 2021 | 4 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871560310 | 2021-12-26 | HA/REVENTE | SATAIR | FLANGE ASSY | 28715603 | 170665 | 10 | 1 | AOG | D9251127600000 | IS0008826S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-23 | 2022-01-17 | 17/01/2022 | 80861060 | 2021-12-26 | 2022-01-18 |  |  | SPARES |  | O |  | 0 | O | N | N | 1 | 2022 | 12 | 2021 | 4 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868582710 | 2021-11-18 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28685827 | 168930 | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-15 | 2022-01-18 | 17/01/2022 | 80861059 | 2021-12-18 | 2022-01-21 |  | OK | Allemagne |  | O |  | 1 | O | N | N | 1 | 2022 | 11 | 2021 | 4 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2860767610 |  | HA/REVENTE | SATAIR | PLATE ASSY | 28607676 | NON-SPARES | 10 | 7 | RTN | A9251152500000 | IS0031658S | NA | 45643 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-12-16 | 2022-01-19 | Sous-poste | Sous-poste | 2021-12-21 | 2022-01-24 |  | OK |  |  | O |  | 1 | #VALUE! | O | N | 12 | 2021 | 1 | 1900 | 4 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872564510 | 2022-01-17 | FABRICATION | SATAIR | Optical Fiber 3435-0153 | 28725645 | 171218 | 10 | 1 | RTN | D9000095028495 | IS0032654M | NON PRESENT INDUS | NA | 3891372 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-01-17 | NA | 100% | 2022-01-18 | 100% | NA | NA | 5.556% |  |  | 2022-01-13 | 2022-01-20 | 21/01/2022 | 80862761 | 2022-01-18 | 2022-01-25 |  | OK | SPARES |  | O |  | 1 | O | N | N | 1 | 2022 | 1 | 2022 | 4 | 1 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2869461310 | 2021-12-01 | FABRICATION | SATAIR | PROTECTION CAP | 28694613 | 169356 | 10 | 18 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 | 3883446 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-06 | NA | 100% | 2022-01-10 | 100% | NA | NA | 5.556% |  |  | 2022-01-24 | 2022-01-24 | 26/01/2022 | 80863982 | 2022-01-27 | 2022-01-27 |  | OK | SPARES |  | O |  | 1 | O | O | N | 1 | 2022 | 12 | 2021 | 5 | 1 | 2022 | 0.045 | 2.0124 | 0.01118 | 2.0236 | NA | 0 | 0
2868575410 | 2021-11-18 | FABRICATION | SATAIR | 313 | 28685754 | 168905 | 10 | 1 | EXP | WF406ACAAAAB | IS0032177M | NON PRESENT INDUS | 48842 | LTE990003 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-20 | 100% | 100% | 2022-01-24 | 100% | NA | NA | 5.556% |  |  | 2021-12-15 | 2022-02-02 | 4/02/2022 | 80866561 | 2021-12-18 | 2022-02-07 |  | OK | SPARES | Commande LAB à faire | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 6 | 2 | 2022 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
2864756510 | 2021-09-15 | FABRICATION | SATAIR | 108 | 28647565 | 165855 | 10 | 1 | RTN | D9550010801195 | IS0059763M | NON PRESENT INDUS | 48019 | LTE990003 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-12-02 | 100% | 100% | 2022-01-17 | 100% | NA | NA | 5.556% |  |  | 2022-02-01 | 2022-02-02 | 03/02/2022 | 80866399 | 2022-02-04 | 2022-02-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 2 | 2022 | 9 | 2021 | 6 | 2 | 2022 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
490004379310 | 2022-01-25 | HA/REVENTE | STELIA | FRONT PLATE ASSY 110VU | 4900043793 | 171557 | 10 | 1 | CRIT | S9251038100000 | IS0035410S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-01-31 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-04 | 2022-02-04 | 31/01/2022 | 80865361 | 2022-02-08 | 2022-02-08 |  | OK | ROCHEFORT |  | O |  | 0 | O | O | N | 1 | 2022 | 1 | 2022 | 6 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865515010 | 2021-10-01 | HA/REVENTE | SATAIR | BRACKET ASSY | 28655150 | 166508 | 10 | 2 | RTN | V9251162600000 | IS0057855S | NA | 48555 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2021-12-14 | 2022-02-08 | 08/02/2022 | 80867481 | 2021-12-17 | 2022-02-11 |  | OK | KIT FACTORY | Litige levé - Attente expé | O |  | 1 | O | N | N | 2 | 2022 | 10 | 2021 | 7 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873515810 | 2022-01-28 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28735158 | 171952 | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-27 | 2022-02-09 | 10/02/2022 | 80868100 | 2022-01-29 | 2022-02-11 |  | OK | SPARES |  | O |  | 0 | O | N | N | 2 | 2022 | 1 | 2022 | 7 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873516910 | 2022-01-28 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28735169 | 171972 | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-27 | 2022-02-09 | 10/02/2022 | 80868101 | 2022-01-29 | 2022-02-11 |  | OK | SPARES |  | O |  | 0 | O | N | N | 2 | 2022 | 1 | 2022 | 7 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873643410 | 2022-01-31 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28736434 | 172014 | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-28 | 2022-02-09 | 10/02/2022 | 80868102 | 2022-02-01 | 2022-02-11 |  | OK | SPARES |  | O |  | 0 | O | N | N | 2 | 2022 | 1 | 2022 | 7 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
68990011 | 2021-06-23 | FABRICATION | AD&S | 11 | 6899001 | 162086 | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990007 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | 100% | 100% | 2022-02-18 | 100% | NA | OUI | 5.263% |  |  | 2021-12-06 | 2022-02-10 | 16/02/2022 | 80869416 | 2021-12-08 | 2022-02-14 |  | OK | SEVILLE |  | O |  | 0 | N | N | N | 2 | 2022 | 6 | 2021 | 7 | 2 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2873643310 | 2022-01-31 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28736433 | 172013 | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-28 | 2022-02-14 | 15/02/2022 | 80869504 | 2022-02-01 | 2022-02-16 |  | OK | SPARES |  | O |  | 0 | O | N | N | 2 | 2022 | 1 | 2022 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872013110 | 2022-01-06 | FABRICATION | SATAIR | BUNDLE | 28720131 | 170858 | 10 | 1 | AOG | V9297986100095A | IS0062201M | NON PRESENT INDUS | 48842 | 3887170 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-12 | NA | 100% | 2022-01-12 | 100% | NA | NA | NA |  |  | 2022-01-05 | 2022-02-14 | 10/02/2022 | 80868230 | 2022-01-07 | 2022-02-16 |  | OK | KIT FACTORY | Réception IS0058892S & IS0058893S le 27/01/2022 - Attente retour Juliano dispo câble | O |  | 0 | O | N | N | 2 | 2022 | 1 | 2022 | 8 | 2 | 2022 | 0.53 | 2.67 | 0.148 | 2.818 | NA | 0 | 0
2871631410 | 2021-12-28 | FABRICATION | SATAIR | OPTICAL FIBER | 28716314 | 170666 | 10 | 1 | EXP | D9000095029495 | IS0032047M | NON PRESENT INDUS |  | 3889545 |  | O | O | 0% | 0% | 0% | 100% | 2022-02-10 | NA | 100% | 2022-02-11 | 100% | NA | NA | NA |  |  | 2022-01-24 | 2022-02-14 | 17/02/2022 | 80870208 | 2022-01-27 | 2022-02-17 |  | OK | SPARES |  | O |  | 1 | N | N | N | 2 | 2022 | 12 | 2021 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868621510 | 2021-11-19 | FABRICATION | SATAIR | WIRE-BONDING | 28686215 | 168906 | 10 | 3 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS | 48842 | 3900106 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-12-08 | NA | 100% | 2022-02-04 | 100% | NA | NA | NA |  |  | 2022-02-15 | 2022-02-15 | 15/02/2022 | 80869419 | 2022-02-18 | 2022-02-18 |  | OK | Allemagne |  | O |  | 1 | O | O | N | 2 | 2022 | 11 | 2021 | 8 | 2 | 2022 | 0.6177 | 0.7149 | 0.02383 | 0.73873 | NA | 0 | 0
2872763910 | 2022-01-19 | HA/REVENTE | SATAIR | BRACKET | 28727639 | 171426 | 10 | 6 | EXP | A9253116020000 | IS0031653S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-15 | 2022-02-15 | 17/02/2022 | 80870180 | 2022-02-18 | 2022-02-18 |  | OK | SPARES | Commande à saisir | O |  | 1 | O | O | N | 2 | 2022 | 1 | 2022 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872764010 | 2022-01-19 | HA/REVENTE | SATAIR | HINGE | 28727640 | 171427 | 10 | 1 | EXP | A9253116220000 | IS0031676S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-15 | 2022-02-15 | 17/02/2022 | 80870181 | 2022-02-18 | 2022-02-18 |  | OK | SPARES | Commande à saisir | O |  | 1 | O | O | N | 2 | 2022 | 1 | 2022 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2861458410 | 2021-07-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28614584 | 162823 | 10 | 2 | RTN | A9251152500000 | IS0031658S | NA | 46170 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-19 | 2022-02-16 | 17/02/2022 | 80870178 | 2022-01-24 | 2022-02-21 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 2 | 2022 | 7 | 2021 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2863128110 | 2021-08-16 | HA/REVENTE | SATAIR | BRACKET | 28631281 | 163894 | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 47578 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2021-02-17 | 2022-02-16 | 17/02/2022 | 80870179 | 2021-02-21 | 2022-02-21 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 2 | 2022 | 8 | 2021 | 8 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2874315310 | 2022-02-09 | FABRICATION | SATAIR | WIRE-BONDING | 28743153 | 172318 | 10 | 2 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | 48843 | 3909562 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-02-17 | 100% | NA | NA | NA |  |  | 2022-03-03 | 2022-02-21 | 24/02/2022 | 80872363 | 2022-03-07 | 2022-02-23 |  | OK | KIT FACTORY |  | O |  | 0 | N | O | N | 2 | 2022 | 2 | 2022 | 9 | 2 | 2022 | 0.4118 | 0.4766 | 0.02383 | 0.50043 | NA | 0 | 0
2874315610 | 2022-02-09 | FABRICATION | SATAIR | WIRE-BONDING | 28743156 | 172319 | 10 | 1 | CRIT | F0003008100200 | IS0032147M | NON PRESENT INDUS | 48843 | 3909565 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-02-17 | 100% | NA | NA | NA |  |  | 2022-03-03 | 2022-02-21 | 24/02/2022 | 80872167 | 2022-03-07 | 2022-02-23 |  | OK | KIT FACTORY |  | O |  | 0 | N | O | N | 2 | 2022 | 2 | 2022 | 9 | 2 | 2022 | 0.2085 | 0.2383 | 0.02383 | 0.26213 | NA | 0 | 0
2874315710 | 2022-02-09 | FABRICATION | SATAIR | LEAD-BONDING | 28743157 | 172320 | 10 | 1 | CRIT | F0003008100300 | IS0032149M | NON PRESENT INDUS | 48843 | 3909564 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-02-17 | 100% | NA | NA | NA |  |  | 2022-03-03 | 2022-02-21 | 24/02/2022 | 80872166 | 2022-03-07 | 2022-02-23 |  | OK | KIT FACTORY |  | O |  | 0 | N | O | N | 2 | 2022 | 2 | 2022 | 9 | 2 | 2022 | 0.2075 | 0.2383 | 0.059575 | 0.29788 | NA | 0 | 0
2869461110 | 2021-12-01 | FABRICATION | SATAIR | PLACARD SET | 28694611 | 169354 | 10 | 4 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | 48842 | 6001335 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-10 | NA | 100% | 2022-02-21 | 100% | NA | NA | NA |  |  | 2022-02-25 | 2022-02-25 | 24/02/2022 | 80872168 | 2022-03-02 | 2022-03-02 |  | OK | SPARES |  | O |  | 1 | O | O | N | 2 | 2022 | 12 | 2021 | 9 | 2 | 2022 | 0 | 0.82 | 0.0205 | 0.8405 | NA | 0 | 0
2874312110 | 2022-02-09 | FABRICATION | SATAIR | OPTICAL FIBER 3028VB | 28743121 | 172339 | 10 | 1 | EXP | D9000095030495 | IS0062462M | NON PRESENT INDUS | 48843 | 3909563 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-02-18 | 100% | NA | NA | NA |  |  | 2022-02-09 | 2022-02-25 | 24/02/2022 | 80872330 | 2022-02-13 | 2022-03-02 |  | OK | SPARES |  | O |  | 1 | O | N | N | 2 | 2022 | 2 | 2022 | 9 | 2 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872624910 | 2022-01-18 | HA/REVENTE | SATAIR | PLACARD SET | 28726249 | 172620 | 10 | 7 | CRIT | V1132043700095A | IS0059284S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-25 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-11 | 2022-03-01 | 25.02.2022 | 80873133 | 2022-03-15 | 2022-03-03 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 10 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872625010 | 2022-01-18 | HA/REVENTE | SATAIR | PLACARD SET | 28726250 | 172621 | 10 | 7 | CRIT | V1132043900095A | IS0059285S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-25 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-11 | 2022-03-01 | 25.02.2022 | 80873127 | 2022-03-15 | 2022-03-03 |  | OK | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 10 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004368610 | 2022-01-07 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900043686 | 170901 | 10 | 2 | RTN | S9251363300000 | IS0035424S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-01-26 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-03 | 2022-03-04 | 08/03/2022 | 80875903 | 2022-03-08 | 2022-03-09 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 3 | 2022 | 1 | 2022 | 10 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004368630 | 2022-01-07 | HA/REVENTE | STELIA | FRONT PLATE ASSY 110VU | 4900043686 | 170901 | 30 | 2 | RTN | S9251038100000 | IS0035410S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-03 | 2022-03-04 | 08/03/2022 | 80875903 | 2022-03-08 | 2022-03-09 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 3 | 2022 | 1 | 2022 | 10 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2876107410 | 2022-03-03 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28761074 | 173530 | 10 | 1 | AOG | D9251805700000 | IS0032776S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-03-01 | 2022-03-08 | 09/03/2022 | 80876360 | 2022-03-03 | 2022-03-10 |  | OK | SPARES |  | O |  | 0 | O | N | N | 3 | 2022 | 3 | 2022 | 11 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2874975310 | 2022-02-17 | FABRICATION | SATAIR | OPTICAL FIBER 3031VB | 28749753 | 172693 | 10 | 1 | EXP | D9000095030595 | IS0062516M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-02-18 | NA | 100% | 2022-03-01 | 100% | NA | NA | NA |  |  | 2022-03-15 | 2022-03-15 | 21/03/2022 | 80879700 | 2022-03-18 | 2022-03-18 |  | OK | SPARES |  | O |  | 1 | N | N | N | 3 | 2022 | 2 | 2022 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
69255731 | 2022-03-14 | FABRICATION | AD&S | 402 | 6925573 | 174078 | 1 | 1 | RTN | MB045ACAAAAB | IS0062403M | NON PRESENT INDUS | 48842 | LTE990003 | 6141492 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-29 | 100% | 100% | 2022-09-26 | 100% | NA | OUI |  |  |  | 2022-09-27 | 2022-10-11 | 20/10/2022 | 80945784 | 2022-09-30 | 2022-10-14 |  | OK | SEVILLE |  | O |  | 1 | N | N | N | 10 | 2022 | 3 | 2022 | 42 | 10 | 2022 | 0.62 | 9.77 | 3.06 | 12.83 | COL
2869677710 | 2021-12-03 | HA/REVENTE | SATAIR | GUTTER ASSY | 28696777 | 169446 | 10 | 14 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-16 | 2022-03-15 |  |  | 2022-02-21 | 2022-03-18 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 12 | 2021 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2870605610 | 2021-12-13 | FABRICATION | SATAIR | 54 | 28706056 | 169965 | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 48842 | LTE990024 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-02-04 | 100% | 100% | 2022-03-07 | 100% | NA | NA | NA |  |  | 2022-03-18 | 2022-03-18 | 21/03/2022 | 80879730 | 2022-03-23 | 2022-03-23 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 3 | 2022 | 12 | 2021 | 12 | 3 | 2022 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2872591210 | 2022-01-17 | HA/REVENTE | SATAIR | BRACKET ASSY | 28725912 | 171247 | 10 | 12 | CRIT | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-03-16 | 2022-03-16 |  |  | 2022-03-18 | 2022-03-18 |  |  | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872592910 | 2022-01-17 | HA/REVENTE | SATAIR | GUTTER ASSY | 28725929 | 171249 | 10 | 12 | CRIT | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-03-16 | 2022-03-16 |  |  | 2022-03-18 | 2022-03-18 |  |  | KIT FACTORY |  | O |  | 0 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873521510 | 2022-01-28 | FABRICATION | SATAIR | OPTICAL FIBER 3029VB | 28735215 | 172012 | 10 | 1 | EXP | D9000095030395 | IS0062395M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | Stock | NA | 100% | 2022-03-10 | 100% | NA | NA | NA |  |  | 2022-03-24 | 2022-03-24 | 21/03/2022 | 80879707 | 2022-03-29 | 2022-03-29 |  | OK | SPARES | Paramétrage en cours à vérifier le 07/02 | O |  | 1 | O | O | N | 3 | 2022 | 1 | 2022 | 13 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865363310 | 2021-09-28 | HA/REVENTE | SATAIR | BRACKET | 28653633 | 166327 | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 48471 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-18 | 2022-03-18 | 15/03/2022 | 80877863 | 2022-03-23 | 2022-03-23 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 3 | 2022 | 9 | 2021 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2865363110 | 2021-09-28 | HA/REVENTE | SATAIR | PLATE ASSY | 28653631 | 166325 | 10 | 6 | RTN | A9251152500000 | IS0031658S | NA | 48471 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-18 | 2022-03-18 | 15/03/2022 | 80877862 | 2022-03-23 | 2022-03-23 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 3 | 2022 | 9 | 2021 | 12 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2869677810 | 2021-12-03 | HA/REVENTE | SATAIR | BRACKET ASSY | 28696778 | 169447 | 10 | 14 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-03-18 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-16 | 2022-03-22 |  |  | 2022-02-21 | 2022-03-25 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 12 | 2021 | 13 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2869677910 | 2021-12-03 | HA/REVENTE | SATAIR | BRACKET ASSY | 28696779 | 169448 | 10 | 14 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-03-18 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-02-16 | 2022-03-22 |  |  | 2022-02-21 | 2022-03-25 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 12 | 2021 | 13 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873762310 | 2022-02-01 | FABRICATION | SATAIR | 27 | 28737623 | 172059 | 10 | 1 | EXP | D9551002700895 | IS0059907M | NON PRESENT INDUS |  | LTE990017 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-10 | NA | 100% | 2022-03-16 | 100% | NA | NA | NA |  |  | 2022-03-30 | 2022-03-30 | 30/03/2022 | 80882608 | 2022-04-04 | 2022-04-04 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 3 | 2022 | 2 | 2022 | 14 | 3 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
490004390730 | 2022-02-10 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900043907 | 172403 | 30 | 1 | RTN | S9251363300000 | IS0035424S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-24 | 2022-03-24 | 05/04/2022 | 80884287 | 2022-03-29 | 2022-03-29 |  | OK | SPARES |  | O |  | 1 | N | N | N | 4 | 2022 | 2 | 2022 | 13 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866828110 | 2021-10-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28668281 | 167618 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-01-18 | 2022-03-28 | 29.03.2022 | 80882090 | 2022-01-21 | 2022-03-31 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 14 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866828210 | 2021-10-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28668282 | 167619 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-18 | 2022-03-28 | 29.03.2022 | 80882091 | 2022-01-21 | 2022-03-31 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 14 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866827910 | 2021-10-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28668279 | 167617 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-01-18 | 2022-03-28 | 29.03.2022 | 80882089 | 2022-01-21 | 2022-03-31 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 14 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866057310 | 2021-10-12 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28660573 | 171598 | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-30 | 2022-03-30 | 29.03.2022 | 80882093 | 2022-04-04 | 2022-04-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 14 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873762311 | 2022-02-01 | FABRICATION | SATAIR | 27 | 28737623 | NON-SPARES | 11 | 1 | EXP | D9551002700895 | IS0059907M | NON PRESENT INDUS |  | LTE990018 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-10 | NA | 100% | 2022-03-16 | 100% | NA | NA | NA |  |  | 2022-03-30 | 2022-03-30 | Sous-poste | Sous-poste | 2022-04-04 | 2022-04-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 14 | 3 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2872574410 | 2022-01-17 | FABRICATION | SATAIR | BUNDLE | 28725744 | 171243 | 10 | 2 | RTN | V9253110000096 | IS0032170M | NON PRESENT INDUS | 48842 | 6024072 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-18 | NA | 100% | 2022-03-28 | 100% | NA | NA | NA |  |  | 2022-04-11 | 2022-04-11 | 08/04/2022 | 80885449 | 2022-04-14 | 2022-04-14 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 4 | 2022 | 1 | 2022 | 16 | 4 | 2022 | 0.2578 | 0.291 | 0.1 | 0.391 | COL | 0 | 0
2866057210 | 2021-10-12 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28660572 | 171597 | 10 | 2 | RTN | D9251805800000 | IS0032777S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-30 | 2022-03-30 | 29.03.2022 | 80882092 | 2022-04-04 | 2022-04-04 |  |  | KIT FACTORY | Attente AR | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 14 | 3 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872574510 | 2022-01-17 | FABRICATION | SATAIR | BUNDLE | 28725745 | 171244 | 10 | 2 | RTN | V9253120000096 | IS0032173M | NON PRESENT INDUS | 48842 | 6024073 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-18 | NA | 100% | 2022-03-28 | 100% | NA | NA | NA |  |  | 2022-04-11 | 2022-04-11 | 08/04/2022 | 80885450 | 2022-04-14 | 2022-04-14 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 4 | 2022 | 1 | 2022 | 16 | 4 | 2022 | 0.2578 | 0.291 | 0.1 | 0.391 | COL | 0 | 0
490004389210 | 2022-02-09 | FABRICATION | STELIA | 63 | 4900043892 | 172338 | 10 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS |  | LTE990011 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-24 | NA | 100% | 2022-03-21 | 100% | NA | OUI | NA |  |  | 2022-04-04 | 2022-04-21 | 15/04/2022 | 80887720 | 2022-04-07 | 2022-04-26 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 4 | 2022 | 2 | 2022 | 17 | 4 | 2022 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
430002875120 | 2022-02-17 | HA/REVENTE | STELIA | VOYANT DE SIGNALISATION | 4300028751 | 172692 | 20 | 1 | RTN | E0276AN0-N132 | IS0007292S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-03-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-12 | 2022-04-12 | 05.04.2022 | 80884288 | 2022-04-15 | 2022-04-15 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2877412210 | 2022-03-17 | HA/REVENTE | SATAIR | PLATE 809VU | 28774122 | 173885 | 10 | 2 | CRIT | F9251431120000 | IS0059720S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-05 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-03-16 | 2022-04-12 | 12.04.2022 | 80886242 | 2022-03-18 | 2022-04-14 |  | OK | SPARES | Pcs en contrôle qualité (FAI) - AZA demande de ne pas prendre en compte FAI le 31/03 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2875011910 | 2022-02-17 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28750119 | 172694 | 10 | 1 | EXP | D9251095400000 | IS0053354S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-03-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-14 | 2022-04-14 | 12.04.2022 | 80886243 | 2022-04-19 | 2022-04-19 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878245210 | 2022-03-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28782452 | 174301 | 10 | 8 | EXP | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-14 | 2022-04-14 | 12.04.2022 | 80886244 | 2022-04-19 | 2022-04-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878247310 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782473 | 174306 | 10 | 8 | EXP | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-14 | 2022-04-14 | 12.04.2022 | 80886245 | 2022-04-19 | 2022-04-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248410 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782484 | 174311 | 10 | 8 | EXP | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-14 | 2022-04-14 | 12.04.2022 | 80886246 | 2022-04-19 | 2022-04-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 16 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866603910 | 2021-10-21 | HA/REVENTE | SATAIR | PLATE ASSY | 28666039 | 167538 | 10 | 6 | RTN | A9251152500000 | IS0031658S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-19 | 2022-04-19 | 19.04.2022 | 80888244 | 2022-04-22 | 2022-04-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 17 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866604010 | 2021-10-21 | HA/REVENTE | SATAIR | BRACKET | 28666040 | 167539 | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-19 | 2022-04-19 | 19.04.2022 | 80888245 | 2022-04-22 | 2022-04-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 17 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004389211 | 2022-02-09 | FABRICATION | STELIA | 63 | 4900043892 | NON-SPARES | 11 | 1 | RTN | S9550006345795 | IS0032232M | NON PRESENT INDUS |  | LTE990012 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-24 | NA | 100% | 2022-03-21 | 100% | NA | OUI | NA |  |  | 2022-04-04 | 2022-04-21 | Sous-poste | Sous-poste | 2022-04-07 | 2022-04-26 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 17 | 4 | 2022 | 0.205 | 3.9375 | 0.98438 | 4.9219 | COL | 0 | 0
2880880910 |  | FABRICATION | SATAIR | BUNDLE | 28808809 | 176017 | 10 | 3 | AOG | V9297404002895 | IS0060809M | NON PRESENT INDUS | 48842 | 6057520 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-17 | NA | 100% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-04-29 | 2022-04-29 | 31/05/2022 | 80897977 | 2022-05-03 | 2022-05-03 |  | OK | SPARES |  | O |  | 0 | N | N | N | 5 | 2022 | 1 | 1900 | 18 | 4 | 2022 | 1.305 | 18.633 | 3.07 | 21.703 | NA | 0 | 0
490004419710 | 2022-04-04 | HA/REVENTE | STELIA | LANGUETTE | 4900044197 | 174850 | 10 | 1 | AOG | S9251097200100 | IS0059938S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-19 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-13 | 2022-04-21 | 22.04.2022 | 80889416 | 2022-04-15 | 2022-04-25 | , | OK | ROCHEFORT | Attente AR 12/04 | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 17 | 4 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2880881010 |  | FABRICATION | SATAIR | BUNDLE | 28808810 | 176018 | 10 | 3 | AOG | V9297400001095 | IS0061660M | NON PRESENT INDUS | 48842 | 6057523 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-17 | NA | 100% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-04-29 | 2022-04-29 | 17/06/2022 | 80897978 | 2022-05-03 | 2022-05-03 |  | OK | SPARES | Dépannage AIB IS0006846S qté 2 + HBG qté 1 | O |  | 0 | N | N | N | 6 | 2022 | 1 | 1900 | 18 | 4 | 2022 | 1.305 | 8.88 | 2.155 | 11.035 | NA | 0 | 0
2880881110 |  | FABRICATION | SATAIR | BUNDLE | 28808811 | 176019 | 10 | 3 | AOG | V9297400101295 | IS0061659M | NON PRESENT INDUS | 48842 | 6057522 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-17 | NA | 100% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-04-29 | 2022-04-29 | 31/05/2022 | 80897979 | 2022-05-03 | 2022-05-03 |  | OK | SPARES |  | O |  | 0 | N | N | N | 5 | 2022 | 1 | 1900 | 18 | 4 | 2022 | 1.305 | 8.88 | 2.155 | 11.035 | NA | 0 | 0
2880881210 |  | FABRICATION | SATAIR | BUNDLE | 28808812 | 176020 | 10 | 3 | AOG | V9297404108695 | IS0060810M | NON PRESENT INDUS | 48842 | 6057524 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-17 | NA | 100% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-04-29 | 2022-04-29 | 31/05/2022 | 80897980 | 2022-05-03 | 2022-05-03 |  | OK | SPARES |  | O |  | 0 | N | N | N | 5 | 2022 | 1 | 1900 | 18 | 4 | 2022 | 1.305 | 18.633 | 3.07 | 21.703 | NA | 0 | 0
2873968010 | 2022-02-04 | FABRICATION | SATAIR | WIRE-BONDING | 28739680 | 172118 | 10 | 3 | RTN | F0003008100000 | IS0032145M | NON PRESENT INDUS |  | 6043397 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-14 | NA | 100% | 2022-04-18 | 100% | NA | NA | NA |  |  | 2022-05-02 | 2022-05-06 | 09/05/2022 | 80894085 | 2022-05-05 | 2022-05-11 |  | OK | SPARES |  | O |  | 1 | O | N | N | 5 | 2022 | 2 | 2022 | 19 | 5 | 2022 | 0.6177 | 0.7149 | 0.02383 | 0.73873 | NA | 0 | 0
490004394010 | 2022-02-15 | HA/REVENTE | STELIA | FRONT PLATE ASSY 110VU | 4900043940 | 172560 | 10 | 2 | RTN | S9251038100000 | IS0035410S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-03 | 2022-05-03 | 26.04.2022 | 80890338 | 2022-05-06 | 2022-05-06 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 19 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2876455110 | 2022-03-07 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28764551 | 173577 | 10 | 2 | EXP | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-25 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-03 | 2022-05-03 | 26.04.2022 | 80890339 | 2022-05-06 | 2022-05-06 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 19 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2877440210 | 2022-03-19 | FABRICATION | SATAIR | PROTECTION CAP | 28774402 | 174079 | 10 | 21 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 | 6043399 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-04-27 | 100% | NA | NA | NA |  |  | 2022-05-11 | 2022-05-13 | 2022-05-16 | 80896508 | 2022-05-14 | 2022-05-18 |  | OK | SPARES |  | O |  | 1 | O | N | N | 5 | 2022 | 3 | 2022 | 20 | 5 | 2022 | 0.0525 | 2.3478 | 0.01118 | 2.359 | NA | 0 | 0
2872582010 | 2022-01-17 | HA/REVENTE | SATAIR | BRACKET ASSY | 28725820 | 171245 | 10 | 12 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-05-09 | 2022-05-09 |  |  | 2022-05-12 | 2022-05-12 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 20 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878174510 | 2022-03-25 | FABRICATION | SATAIR | 518 | 28781745 | 174291 | 10 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990013 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-30 | 0% | 90% | 2022-05-05 | 90% | NA | NA | NA |  |  | 2022-05-04 | 2022-05-18 | 20/07/2022 | 80915381 | 2022-05-08 | 2022-05-21 |  | OK | SPARES | IS0006704S Réception 01/07 | O |  | 1 | N | N | N | 7 | 2022 | 3 | 2022 | 21 | 5 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2878245310 | 2022-03-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28782453 | 174302 | 10 | 8 | EXP | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-13 | 2022-05-13 | 09.05.2022 | 80894316 | 2022-05-18 | 2022-05-18 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 20 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878247810 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782478 | 174307 | 10 | 8 | EXP | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-13 | 2022-05-13 | 09.05.2022 | 80894318 | 2022-05-18 | 2022-05-18 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 20 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248510 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782485 | 174312 | 10 | 8 | EXP | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-13 | 2022-05-13 | 09.05.2022 | 80894319 | 2022-05-18 | 2022-05-18 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 20 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868770010 | 2021-11-22 | HA/REVENTE | SATAIR | PLATE ASSY | 28687700 | 168923 | 10 | 6 | RTN | A9251152500000 | IS0031658S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-17 | 2022-05-17 | 09.05.2022 | 80894321 | 2022-05-20 | 2022-05-20 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 21 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2868769910 | 2021-11-22 | HA/REVENTE | SATAIR | BRACKET | 28687699 | 168922 | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-03-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-17 | 2022-05-17 | 09.05.2022 | 80894320 | 2022-05-20 | 2022-05-20 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2021 | 21 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878174520 | 2022-03-25 | FABRICATION | SATAIR | 518 | 28781745 | 174291 | 20 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990014 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-04 | 0% | 90% | 2022-05-05 | 90% | NA | NA | NA |  |  | 2022-05-04 | 2022-05-18 | 20/07/2022 | 80915381 | 2022-05-08 | 2022-05-21 |  | OK | SPARES | IS0006704S Réception 01/07 | O |  | 1 | N | N | N | 7 | 2022 | 3 | 2022 | 21 | 5 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
2878174530 | 2022-03-25 | FABRICATION | SATAIR | 518 | 28781745 | 174291 | 30 | 1 | RTN | WF418AFACAAE | IS0032185M | NON PRESENT INDUS | 48842 | LTE990015 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-04 | 0% | 90% | 2022-05-05 | 90% | NA | NA | NA |  |  | 2022-05-04 | 2022-05-18 | 20/07/2022 | 80915381 | 2022-05-08 | 2022-05-21 |  | OK | SPARES | IS0006704S Réception 01/07 | O |  | 1 | N | N | N | 7 | 2022 | 3 | 2022 | 21 | 5 | 2022 | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL | 0 | 0
490004441010 | 2022-05-12 | FABRICATION | STELIA | OPTICAL FIBER | 4900044410 | 176759 | 10 | 1 | AOG | S954A1184158052 | IS0062875M | NON PRESENT INDUS | NA |  |  | 0 | 0 | 0% | 100% | 50% | 100% | TBD | NA | 100% | 2022-05-16 | 100% | NA | OUI | NA |  |  | 2022-05-17 | 2022-05-19 | 01/06/2022 | 80901692 | 2022-05-19 | 2022-05-23 |  | OK | ROCHEFORT |  | O |  | 0 | N | N | N | 6 | 2022 | 5 | 2022 | 21 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2866604210 | 2021-10-21 | FABRICATION | SATAIR | PROTECTION CAP | 28666042 | 167541 | 10 | 8 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 | 6051251 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-06 | NA | 100% | 2022-05-09 | 100% | NA | NA | NA |  |  | 2022-05-19 | 2022-05-19 | 23.05.2022 | 80898350 | 2022-05-24 | 2022-05-24 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2021 | 21 | 5 | 2022 | 0.02 | 0.8944 | 0.01118 | 0.90558 | NA | 0 | 0
69224051 | 2022-02-09 | FABRICATION | AD&S | 11 | 6922405 | 172558 | 1 | 1 | EXP | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | 100% | 100% | 2022-05-09 | 0% | NA | OUI | NA |  |  | 2022-06-30 | 2022-05-20 | 10/05/2022 | 80894668 | 2022-07-05 | 2022-05-25 |  | OK | SEVILLE |  | O |  | 1 | O | O | N | 5 | 2022 | 2 | 2022 | 21 | 5 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2872424510 | 2022-01-13 | FABRICATION | SATAIR | PROTECTION CAP | 28724245 | 170997 | 10 | 1 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 | 6051255 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-31 | NA | 100% | 2022-05-16 | 0% | NA | NA | NA |  |  | 2022-05-27 | 2022-05-27 | 23/05/2022 | 80898353 | 2022-06-01 | 2022-06-01 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 5 | 2022 | 1 | 2022 | 22 | 5 | 2022 | 0.0025 | 0.1118 | 0.01118 | 0.12298 | NA | 0 | 0
2878245510 | 2022-03-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28782455 | 174304 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-15 | 2022-05-24 | 25.05.2022 | 80899307 | 2022-06-20 | 2022-05-27 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 22 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878247910 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782479 | 174308 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-15 | 2022-05-24 | 25.05.2022 | 80899306 | 2022-06-20 | 2022-05-27 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 22 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248610 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782486 | 174313 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-15 | 2022-05-24 | 23.05.2022 | 80898665 | 2022-06-20 | 2022-05-27 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 22 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2879290510 | 2022-04-08 | HA/REVENTE | SATAIR | RAMP | 28792905 | 175095 | 10 | 1 | AOG | V9251129900000 | IS0059956S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-05-26 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-04-06 | 2022-05-27 | 25/04/2022 | 80890127 | 2022-04-08 | 2022-05-31 |  | OK | SPARES | Retard de traitement de la commande côté LBG | O |  | 0 | O | N | N | 4 | 2022 | 4 | 2022 | 22 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004413710 | 2022-03-22 | FABRICATION | STELIA | 34 | 4900044137 | 174522 | 10 | 1 | RTN | S9550003456395 | IS0032566M | NON PRESENT INDUS |  | LTE990001 |  | 0 | 0 | 0% | 100% | 50% | 80% | TBD | NA | 80% | 2022-04-27 | 100% | NA | OUI | NA |  |  | 2022-05-11 | 2022-05-31 | 09/06/2022 | 80904334 | 2022-05-16 | 2022-06-03 |  | OK | ROCHEFORT | SAFRAN IS0032217S dépanné par AATL - ROSSI IS0060003S réception le 20/05 | O |  | 1 | N | N | N | 6 | 2022 | 3 | 2022 | 23 | 5 | 2022 | 0.205 | 4.1225 | 1.0306 | 5.1531 | COL | 0 | 0
2882322310 | 2022-05-23 | FABRICATION | SATAIR | OPTICAL FIBER 3030VB | 28823223 | 177206 | 10 | 1 | CRIT | D9000095030695 | IS0062902M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-05-23 | NA | 100% | 2022-05-30 | 100% | NA | NA | NA |  |  | 2022-05-18 | 2022-06-02 | 10/06/2022 | 80904805 | 2022-05-20 | 2022-06-06 |  | OK | SPARES |  | O |  | 0 | N | N | N | 6 | 2022 | 5 | 2022 | 23 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2876446810 | 2022-03-07 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28764468 | 173576 | 10 | 2 | RTN | D9251490100000 | IS0032740S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-31 | 2022-05-31 | 25.05.2022 | 80899308 | 2022-06-03 | 2022-06-03 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 23 | 5 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2879292010 |  | FABRICATION | SATAIR | BUNDLE | 28792920 | 175096 | 10 | 1 | EXP | V9297404002895 | IS0060809M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-05-25 | NA | 100% | TBD | 0% | NA | NA | NA |  |  | 2022-06-01 | 2022-06-01 |  |  | 2022-06-06 | 2022-06-06 |  | OK | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 1900 | 23 | 6 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2867280810 |  | FABRICATION | SATAIR | BUNDLE | 28672808 | 168029 | 10 | 2 | RTN | V9297400001095 | IS0061660M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-05-25 | NA | 100% | TBD | 0% | NA | NA | NA |  |  | 2022-06-02 | 2022-06-02 | 31/05/2022 | 80901025 | 2022-06-07 | 2022-06-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 5 | 2022 | 1 | 1900 | 23 | 6 | 2022 | 0.87 | 5.92 | 2.155 | 8.075 | NA | 0 | 0
2874554010 | 2022-02-14 | FABRICATION | SATAIR | BUNDLE | 28745540 | 172505 | 10 | 9 | RTN | V9297986100095A | IS0062201M | NON PRESENT INDUS | 48843 | 6043398 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-04-20 | 100% | NA | NA | NA |  |  | 2022-05-04 | 2022-06-03 | 02/06/2022 | 80902191 | 2022-05-09 | 2022-06-08 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 6 | 2022 | 2 | 2022 | 23 | 6 | 2022 | 4.77 | 24.03 | 0.148 | 24.178 | NA | 0 | 0
2881684610 | 2022-05-11 | FABRICATION | SATAIR | BUNDLE | 28816846 | 176766 | 10 | 2 | RTN | V9297986100095A | IS0062201M | NON PRESENT INDUS | 48843 | 6043398 |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-06-14 | 0% | NA | NA | NA |  |  | 2022-05-17 | 2022-06-03 | 02/06/2022 | 80902192 | 2022-05-20 | 2022-06-08 |  | OK | KIT FACTORY | Réception IS0058892S IS0058893S le 22/06 (A2C) | O |  | 1 | O | N | N | 6 | 2022 | 5 | 2022 | 23 | 6 | 2022 | 1.06 | 5.34 | 0.148 | 5.488 | NA | 0 | 0
2869775810 | 2021-12-06 | FABRICATION | SATAIR | BUNDLE | 28697758 | 172289 | 10 | 1 | RTN | V9297404108495 | IS0062439M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 0% | TBD | NA | 0% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-06-06 | 2022-06-06 | 17.06.2022 | 80907207 | 2022-06-09 | 2022-06-09 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2021 | 24 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2869776110 | 2021-12-06 | FABRICATION | SATAIR | BUNDLE | 28697761 | 172290 | 10 | 1 | RTN | V9297404002695 | IS0062440M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 0% | TBD | NA | 0% | 2022-05-23 | 100% | NA | NA | NA |  |  | 2022-06-06 | 2022-06-06 | 17.06.2022 | 80907208 | 2022-06-09 | 2022-06-09 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2021 | 24 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2874650510 | 2022-02-15 | FABRICATION | SATAIR | 54 | 28746505 | 172561 | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 48842 | LTE990025 |  | 0 | 0 | 100% | 100% | 100% | 99% | 2022-03-14 | NA | 99% | 2022-06-02 | 100% | NA | NA | NA |  |  | 2022-05-19 | 2022-06-15 | 17/06/2022 | 80907082 | 2022-05-24 | 2022-06-20 |  | OK | KIT FACTORY | TE IS0008878S à réceptionner à COL | O |  | 1 | O | N | N | 6 | 2022 | 2 | 2022 | 25 | 6 | 2022 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2879823710 | 2022-04-14 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28798237 | 175469 | 10 | 1 | EXP | D9251095600000 | IS0053509S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-05-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-08 | 2022-06-08 | 08.06.2022 | 80903916 | 2022-06-12 | 2022-06-12 |  | OK | SPARES | Cmde T3S à saisir | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 24 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004425810 | 2022-04-14 | HA/REVENTE | STELIA | PROTECTION | 4900044258 | 175468 | 10 | 2 | EXP | S9251047420000 | IS0060011S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-02 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-03 | 2022-06-10 | 13.06.2022 | 80905184 | 2022-05-06 | 2022-06-15 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 24 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004425820 | 2022-06-16 | HA/REVENTE | STELIA | PROTECTION | 4900044258 | 175468 | 20 | 3 | EXP | S9251047420000 | IS0060011S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-14 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-03 | 2022-06-10 | 13.06.2022 | 80905184 | 2022-05-06 | 2022-06-15 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 24 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872591310 | 2022-01-17 | HA/REVENTE | SATAIR | BRACKET ASSY | 28725913 | 171248 | 10 | 10 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-06-13 | 2022-06-13 |  |  | 2022-06-16 | 2022-06-16 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 25 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2877560010 | 2022-03-19 | FABRICATION | SATAIR | PLACARD SET | 28775600 | 174080 | 10 | 12 | RTN | D9100095600395 | IS0032064M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-31 | NA | 100% | 2022-06-01 | 100% | NA | NA | NA |  |  | 2022-06-15 | 2022-06-15 | 09/06/2022 | 80904301 | 2022-06-18 | 2022-06-18 |  | OK | SPARES |  | O |  | 1 | O | O | N | 6 | 2022 | 3 | 2022 | 25 | 6 | 2022 | 0 | 2.46 | 0.0205 | 2.4805 | NA | 0 | 0
2871442410 | 2021-12-22 | FABRICATION | SATAIR | 117 | 28714424 | 170672 | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990164 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-21 | NA | 100% | 2022-06-06 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 16/06/2022 | 80906412 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 6 | 2022 | 12 | 2021 | 26 | 6 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2871442411 | 2021-12-22 | FABRICATION | SATAIR | 117 | 28714424 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990165 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-21 | NA | 100% | 2022-06-06 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 16/06/2022 | 80906412 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 6 | 2022 | 12 | 2021 | 26 | 6 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2871442110 | 2021-12-22 | HA/REVENTE | SATAIR | BRACKET | 28714421 | 170669 | 10 | 6 | RTN | A9252496620200 | IS0053087S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 13.06.2022 | 80905186 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2021 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871442210 | 2021-12-22 | HA/REVENTE | SATAIR | PLATE ASSY | 28714422 | 170670 | 10 | 6 | RTN | A9251152500000 | IS0031658S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 13.06.2022 | 80905187 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 12 | 2021 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871442412 | 2021-12-22 | FABRICATION | SATAIR | 117 | 28714424 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990166 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-21 | NA | 100% | 2022-06-06 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 16/06/2022 | 80906412 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #REF! | O | N | 6 | 2022 | 12 | 2021 | 26 | 6 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2871442413 | 2021-12-22 | FABRICATION | SATAIR | 117 | 28714424 | NON-SPARES | 13 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990167 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-21 | NA | 100% | 2022-06-06 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 16/06/2022 | 80906412 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #REF! | O | N | 6 | 2022 | 12 | 2021 | 26 | 6 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2873474810 | 2022-01-28 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28734748 | 171958 | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 13.06.2022 | 80905188 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873474910 | 2022-01-28 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28734749 | 171959 | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-20 | 2022-06-20 | 13.06.2022 | 80905189 | 2022-06-23 | 2022-06-23 |  | OK | KIT FACTORY | Attente AR | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2879033710 | 2022-04-05 | FABRICATION | SATAIR | PROTECTION CAP | 28790337 | 175020 | 10 | 20 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-07 | NA | 100% | 2022-06-13 | 100% | NA | NA | NA |  |  | 2022-06-27 | 2022-06-20 | 22.06.2022 | 80908214 | 2022-06-30 | 2022-06-23 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 26 | 6 | 2022 | 0.05 | 2.236 | 0.01118 | 2.2472 | NA | 0 | 0
2883538810 | 2022-06-14 | FABRICATION | SATAIR | 313 | 28835388 | 178051 | 10 | 1 | AOG | WF406ACAAAAB | IS0032177M | NON PRESENT INDUS | 48842 | LTE990005 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-30 | 0% | 90% | 2022-06-22 | 0% | NA | NA | NA |  |  | 2022-06-13 | 2022-06-22 | 27/07/2022 | 80917905 | 2022-06-15 | 2022-06-24 |  |  | SPARES | Confié prélevé sur 28725640 / Voir CAP délai réappro platine avant | O |  | 0 | N | N | N | 7 | 2022 | 6 | 2022 | 26 | 6 | 2022 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
68797721 | 2020-11-18 | FABRICATION | AD&S | 39 | 6879772 | 152445 | 1 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990007 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 100% | NA | OUI | NA |  |  | 2021-12-10 | 2022-06-22 | 2022-06-22 | 80908304 | 2021-12-15 | 2022-06-27 |  | OK | SEVILLE | Confié cassé, attente réappro - Réception possible fin MAI 2022 | O |  | 1 | O | N | O | 6 | 2022 | 11 | 2020 | 26 | 6 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
450116875110 |  |  | TBD |  | 4501168751 | NON-SPARES | 10 | 5 | RTN | A320EL061-EPA |  | NON PRESENT INDUS | 54561 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-16 | NA | 100% | 2022-06-13 | 100% | NA | OUI | NA |  |  | 2022-02-24 | 2022-06-22 | Sous-poste | Sous-poste | 2022-03-01 | 2022-06-27 |  |  |  |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
68797721_1 | 2020-11-18 | FABRICATION | AD&S | 39 | 6879772 | NON-SPARES | 1_1 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990008 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 100% | NA | OUI | NA |  |  | 2021-12-10 | 2022-06-22 | 2022-06-22 | Sous-poste | 2021-12-15 | 2022-06-27 |  | OK | SEVILLE | Confié cassé, attente réappro - Réception possible fin MAI 2022 | O |  | 1 | O | N | O | 6 | 2022 | 11 | 2020 | 26 | 6 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68797722 | 2020-11-18 | FABRICATION | AD&S | 39 | 6879772 | 152445 | 2 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 39527 | LTE990009 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-06-22 | 100% | 100% | 2021-11-02 | 100% | NA | OUI | NA |  |  | 2021-12-10 | 2022-06-22 | 2022-06-22 | 80908304 | 2021-12-15 | 2022-06-27 |  | OK | SEVILLE | Confié cassé, attente réappro - Réception possible fin MAI 2022 | O |  | 1 | O | N | O | 6 | 2022 | 11 | 2020 | 26 | 6 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
2881908310 | 2022-05-13 | FABRICATION | SATAIR | BUNDLE | 28819083 | 176809 | 10 | 1 | EXP | V9297400001095 | IS0061660M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-06-23 | 100% | NA | NA | NA |  |  | 2022-07-07 | 2022-06-24 | 28.06.2022 | 80909716 | 2022-07-12 | 2022-06-29 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 26 | 6 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2871943210 | 2022-01-05 | FABRICATION | SATAIR | BUNDLE | 28719432 | 172291 | 10 | 1 | RTN | V9297404002695 | IS0062440M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-07-13 | 100% | NA | NA | NA |  |  | 2022-07-27 | 2022-06-24 | 28.06.2022 | 80909713 | 2022-08-01 | 2022-06-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2880901510 | 2022-05-10 | HA/REVENTE | SATAIR | BRACKET | 28809015 | 176367 | 10 | 2 | EXP | A9252496620200 | IS0053087S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-03-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-23 | 2022-06-23 | 22.06.2022 | 80908210 | 2022-06-28 | 2022-06-28 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872020010 | 2022-01-06 | FABRICATION | SATAIR | BUNDLE | 28720200 | 172292 | 10 | 1 | RTN | V9297404108495 | IS0062439M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-07-13 | 100% | NA | NA | NA |  |  | 2022-07-27 | 2022-06-24 | 28.06.2022 | 80909715 | 2022-08-01 | 2022-06-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 26 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2867280910 |  | FABRICATION | SATAIR | BUNDLE | 28672809 | 168030 | 10 | 2 | RTN | V9297400101295 | IS0061659M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | TBD | 100% | NA | NA | NA |  |  | 2022-08-09 | 2022-06-24 | 28.06.2022 | 80909717 | 2022-08-12 | 2022-06-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 | 26 | 6 | 2022 | 0.87 | 5.92 | 2.155 | 8.075 | NA | 0 | 0
2873583510 | 2022-01-31 | FABRICATION | SATAIR | 27 | 28735835 | 172016 | 10 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990072 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-06-07 | 100% | NA | NA | NA |  |  | 2022-06-21 | 2022-06-27 | 2022-06-30 | 80910813 | 2022-06-24 | 2022-06-30 |  | OK | KIT FACTORY |  | O |  | 1 | N | N | N | 6 | 2022 | 1 | 2022 | 27 | 6 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2873583511 | 2022-01-31 | FABRICATION | SATAIR | 27 | 28735835 | NON-SPARES | 11 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990073 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-06-07 | 100% | NA | NA | NA |  |  | 2022-06-21 | 2022-06-27 | 2022-06-30 | Sous-poste | 2022-06-24 | 2022-06-30 |  | OK | KIT FACTORY |  | O |  | 1 | O | #REF! | N | 6 | 2022 | 1 | 2022 | 27 | 6 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2877850910 | 2022-03-22 | FABRICATION | SATAIR | 27 | 28778509 | 0 | 10 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990033 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-06-07 | 100% | NA | NA | NA |  |  | 2022-06-21 | 2022-06-27 | 24/06/2022 | 80908662 | 2022-06-24 | 2022-06-30 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 6 | 2022 | 3 | 2022 | 27 | 6 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2877850910_1 | 2022-03-22 | FABRICATION | SATAIR | 27 | 28778509 | NON-SPARES | 10_1 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990034 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-06-07 | 100% | NA | NA | NA |  |  | 2022-06-21 | 2022-06-27 | 24/06/2022 | 80908662 | 2022-06-24 | 2022-06-30 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 6 | 2022 | 3 | 2022 | 27 | 6 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2879152110 | 2022-04-06 | FABRICATION | SATAIR | PROTECTION CAP | 28791521 | 175026 | 10 | 20 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-04-07 | NA | 100% | 2022-06-21 | 100% | NA | NA | NA |  |  | 2022-09-21 | 2022-06-28 | 30.06.2022 | 80910766 | 2022-09-26 | 2022-07-01 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 27 | 6 | 2022 | 0.05 | 2.236 | 0.01118 | 2.2472 | NA | 0 | 0
2873839110 | 2022-02-02 | FABRICATION | SATAIR | 27 | 28738391 | 172062 | 10 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990074 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-06-15 | 100% | NA | NA | NA |  |  | 2022-06-29 | 2022-06-29 | 2022-06-30 | 80910814 | 2022-07-04 | 2022-07-04 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 6 | 2022 | 2 | 2022 | 27 | 6 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2884340210 | 2022-06-25 | HA/REVENTE | SATAIR | POTENTIOMETRE | 28843402 | 178765 | 10 | 1 | AOG | ABS2208AP08S | IS0006784S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-27 | NA | 100% | TBD | 0% | NA | NA | NA |  |  | 2022-06-27 | 2022-06-27 | 27.06.2022 | 8090941 | 2022-06-29 | 2022-06-29 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 27 | 6 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2875657310 | 2022-02-25 | FABRICATION | SATAIR | PROTECTION CAP | 28756573 | 173538 | 10 | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-10 | NA | 100% | 2022-06-15 | 100% | NA | NA | NA |  |  | 2022-06-29 | 2022-06-29 | 22.06.2022 | 80908210 | 2022-07-04 | 2022-07-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 27 | 6 | 2022 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
2872582110 | 2022-01-17 | HA/REVENTE | SATAIR | BRACKET ASSY | 28725821 | 171246 | 10 | 10 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-06-29 | 2022-06-29 |  |  | 2022-07-04 | 2022-07-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 27 | 6 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873839111 | 2022-02-02 | FABRICATION | SATAIR | 27 | 28738391 | NON-SPARES | 11 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990075 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-06-15 | 100% | NA | NA | NA |  |  | 2022-06-29 | 2022-06-29 | 2022-06-30 | Sous-poste | 2022-07-04 | 2022-07-04 |  | OK | KIT FACTORY |  | O |  | 1 | O | O | N | 6 | 2022 | 2 | 2022 | 27 | 6 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2872564010 | 2022-01-17 | FABRICATION | SATAIR | 313 | 28725640 | 171217 | 10 | 1 | AOG | WF406ACAAAAB | IS0032177M | NON PRESENT INDUS | 48842 | LTE990004 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-02-02 | 100% | 100% | 2022-06-22 | 95% | NA | NA | NA |  |  | 2022-01-14 | 2022-07-01 | 27.06.2022 | 80909404 | 2022-01-18 | 2022-07-05 |  |  | SPARES | Unicut manquants IS0007595S & IS0007596S | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 27 | 7 | 2022 | 0.205 | 3.5 | 0.875 | 4.375 | COL | 0 | 0
2881165410 | 2022-05-10 | FABRICATION | SATAIR | PROTECTION CAP | 28811654 | 176393 | 10 | 40 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-16 | NA | 100% | 2022-06-21 | 95% | NA | NA | NA |  |  | 2022-09-26 | 2022-07-05 | 30.06.2022 | 80910767 | 2022-09-29 | 2022-07-08 |  | OK | KIT FACTORY | Manquant connecteur IS0009402S (réception 04/08) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 28 | 7 | 2022 | 0.1 | 4.472 | 0.01118 | 4.4832 | NA | 0 | 0
2874554110 | 2022-02-14 | FABRICATION | SATAIR | BUNDLE | 28745541 | 172506 | 10 | 12 | AOG | V9297986100095A | IS0062201M | NON PRESENT INDUS | 48843 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-10 | NA | 100% | 2022-06-23 | 100% | NA | NA | NA |  |  | 2022-07-01 | 2022-07-12 | 12.07.2022 | 80913756 | 2022-07-05 | 2022-07-12 |  | OK | KIT FACTORY | Voir A2C date réception IS0058892S IS0058893S | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 29 | 7 | 2022 | 6.36 | 32.04 | 0.148 | 32.188 | NA | 0 | 0
490004441910 | 2022-05-13 | HA/REVENTE | STELIA | LANGUETTE | 4900044419 | 176807 | 10 | 2 | RTN | S9251097200100 | IS0059938S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-05 | 2022-07-05 | 06.07.2022 | 80912643 | 2022-07-08 | 2022-07-08 |  | OK | ROCHEFORT | Commande placée le 24/05 / Attente AR | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878245410 | 2022-03-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28782454 | 174303 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-13 | 2022-07-05 | 18.07.2022 | 80915223 | 2022-07-18 | 2022-07-08 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248010 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782480 | 174309 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-13 | 2022-07-05 | 18.07.2022 | 80915224 | 2022-07-18 | 2022-07-08 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248710 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782487 | 174314 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-13 | 2022-07-05 | 18.07.2022 | 80915225 | 2022-07-18 | 2022-07-08 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
69181481 | 2021-12-28 | FABRICATION | AD&S | 11 | 6918148 | 170688 | 1 | 1 | RTN | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 48842 | LTE990012 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | NA | 100% | 2022-07-01 | 100% | NA | OUI | NA |  |  | 2022-01-14 | 2022-07-20 | 22/07/2022 | 80916412 | 2022-01-19 | 2022-07-25 |  | OK | SEVILLE | Expédié 22/07 | O |  | 1 | O | N | N | 7 | 2022 | 12 | 2021 | 30 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2871796910 | 2022-01-03 | HA/REVENTE | SATAIR | GUTTER ASSY | 28717969 | 170695 | 10 | 10 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-02-04 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-06 | 2022-07-06 |  |  | 2022-07-11 | 2022-07-11 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871797110 | 2022-01-03 | HA/REVENTE | SATAIR | BRACKET ASSY | 28717971 | 170696 | 10 | 10 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-06 | 2022-07-06 |  |  | 2022-07-11 | 2022-07-11 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871797210 | 2022-01-03 | HA/REVENTE | SATAIR | BRACKET ASSY | 28717972 | 170697 | 10 | 10 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-06 | 2022-07-06 |  |  | 2022-07-11 | 2022-07-11 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872593110 | 2022-01-17 | HA/REVENTE | SATAIR | GUTTER ASSY | 28725931 | 171250 | 10 | 10 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-06 | 2022-07-06 |  |  | 2022-07-11 | 2022-07-11 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 28 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872641010 | 2022-01-18 | HA/REVENTE | SATAIR | BRACKET ASSY | 28726410 | 171291 | 10 | 20 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-11 | 2022-07-11 |  |  | 2022-07-14 | 2022-07-14 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2872641310 | 2022-01-18 | HA/REVENTE | SATAIR | BRACKET ASSY | 28726413 | 171292 | 10 | 20 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-11 | 2022-07-11 |  |  | 2022-07-14 | 2022-07-14 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884512610 | 2022-06-28 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28845126 | 178809 | 10 | 1 | CRIT | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-11 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-27 | 2022-07-11 | 04.08.2022 | 80920114 | 2022-06-29 | 2022-07-13 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884513510 | 2022-06-28 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28845135 | 178810 | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-11 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-27 | 2022-07-11 | 04.08.2022 | 80920115 | 2022-06-29 | 2022-07-13 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884662210 | 2022-06-30 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28846622 | 179007 | 10 | 2 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-11 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-29 | 2022-07-11 | 04.08.2022 | 80920116 | 2022-07-01 | 2022-07-13 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884664210 | 2022-06-30 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28846642 | 179008 | 10 | 2 | CRIT | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-11 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-06-29 | 2022-07-11 | 04.08.2022 | 80920117 | 2022-07-01 | 2022-07-13 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
69181481_1 | 2021-12-28 | FABRICATION | AD&S | 11 | 6918148 | 170688 | 1_1 | 1 | RTN | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 48842 | LTE990015 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 100% | 100% | 2022-07-01 | 100% | NA | OUI | NA |  |  | 2022-01-14 | 2022-07-20 | 22/07/2022 | 80916412 | 2022-01-19 | 2022-07-25 |  | OK | SEVILLE | Expédié 22/07 | O |  | 1 | O | N | N | 7 | 2022 | 12 | 2021 | 30 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2872640910 | 2022-01-18 | HA/REVENTE | SATAIR | GUTTER ASSY | 28726409 | 171290 | 10 | 20 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-13 | 2022-07-13 |  |  | 2022-07-18 | 2022-07-18 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 29 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2880181210 | 2022-04-21 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28801812 | 175653 | 10 | 4 | RTN | D9251490100000 | IS0032740S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-18 | 2022-07-18 | 18.07.2022 | 80915230 | 2022-07-21 | 2022-07-21 |  | OK | SPARES | Commande de 8U placée le 24/05 /Attente AR | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 30 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004451010 | 2022-05-30 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900044510 | 177667 | 10 | 1 | RTN | S9251363300000 | IS0035424S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-18 | 2022-07-18 | 18.07.2022 | 80915229 | 2022-07-21 | 2022-07-21 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 30 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2871798210 | 2022-01-03 | HA/REVENTE | SATAIR | PLATE ASSY | 28717982 | 170699 | 10 | 4 | RTN | A9251152500000 | IS0031658S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-04-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-19 | 2022-07-19 | 18.07.2022 | 80915231 | 2022-07-22 | 2022-07-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 30 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2881723410 | 2022-05-11 | HA/REVENTE | SATAIR | PLACARD SET | 28817234 | 176769 | 10 | 192 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-14 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-05 | 2022-07-19 | 25.07.2022 | 80916847 | 2022-07-08 | 2022-07-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 30 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2881724710 | 2022-05-11 | HA/REVENTE | SATAIR | PLACARD SET | 28817247 | 176773 | 10 | 192 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-14 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-05 | 2022-07-19 | 25.07.2022 | 80916848 | 2022-07-08 | 2022-07-22 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 30 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004452210 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | 177739 | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_1 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_1 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_2 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_2 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_3 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_3 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_4 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_4 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_5 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_5 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_6 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_6 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_7 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_7 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_8 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_8 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_9 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_9 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_10 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_11 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_11 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_12 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_12 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_13 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_13 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
490004452210_14 | 2022-06-01 | FABRICATION | STELIA | CÂBLE | 4900044522 | NON-SPARES | 10_14 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-14 | NA | 100% | 2022-06-27 | 100% | NA | NA | NA |  |  | 2022-07-18 | 2022-07-22 | 26/07/2022 | 80917703 | 2022-07-21 | 2022-07-27 |  | OK | ROCHEFORT |  | O |  | 1 | O | N | N | 7 | 2022 | 6 | 2022 | 30 | 7 | 2022 | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
68981911_1 | 2021-06-02 | FABRICATION | AD&S | 11 | 6898191 | NON-SPARES | 1_1 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990004 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | NA | 100% | 2022-07-06 | 100% | NA | OUI | NA |  |  | 2021-11-26 | 2022-07-25 | 2022-07-26 | Sous-poste | 2021-11-30 | 2022-07-27 |  | OK | SEVILLE | Expédition le 26/07 | O |  | 0 | O | N | N | 7 | 2022 | 6 | 2021 | 31 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
68981911 | 2021-06-02 | FABRICATION | AD&S | 11 | 6898191 | 161630 | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990003 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | 100% | 100% | 2022-07-06 | 100% | NA | OUI | NA |  |  | 2021-11-26 | 2022-07-25 | 2022-07-22 | 80916086 | 2021-11-30 | 2022-07-27 |  | OK | SEVILLE | Expédié 22/07 | O |  | 0 | O | N | O | 7 | 2022 | 6 | 2021 | 31 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
68981911_3 | 2021-06-02 | FABRICATION | AD&S | 11 | 6898191 | NON-SPARES | 1_3 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990006 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | NA | 100% | 2022-07-06 | 99% | NA | OUI | NA |  |  | 2021-11-26 | 2022-07-25 | 2022-07-26 | Sous-poste | 2021-11-30 | 2022-07-27 |  | OK | SEVILLE | Expédition le 26/07 | O |  | 0 | O | N | N | 7 | 2022 | 6 | 2021 | 31 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
68981911_2 | 2021-06-02 | FABRICATION | AD&S | 11 | 6898191 | NON-SPARES | 1_2 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990005 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | NA | 100% | 2022-07-06 | 99% | NA | OUI | NA |  |  | 2021-11-26 | 2022-07-25 | 2022-07-22 | Sous-poste | 2021-11-30 | 2022-07-27 |  | OK | SEVILLE | Expédié 22/07 | O |  | 0 | O | N | O | 7 | 2022 | 6 | 2021 | 31 | 7 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2873478010 | 2022-01-28 | FABRICATION | SATAIR | 117 | 28734780 | 171963 | 10 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990168 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-15 | NA | 100% | 2022-07-29 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-08-12 | 04.08.2022 | 80920166 | 2022-06-23 | 2022-08-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 33 | 8 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2873478011 | 2022-01-28 | FABRICATION | SATAIR | 117 | 28734780 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990169 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-15 | NA | 100% | 2022-07-29 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-08-12 | 04.08.2022 | 80920166 | 2022-06-23 | 2022-08-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 33 | 8 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2878245610 | 2022-03-25 | HA/REVENTE | SATAIR | GUTTER ASSY | 28782456 | 174305 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-15 | 2022-07-26 | 18.07.2022 | 80915226 | 2022-08-18 | 2022-07-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 31 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248110 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782481 | 174310 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-15 | 2022-07-26 | 18.07.2022 | 80915227 | 2022-08-18 | 2022-07-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 31 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878248810 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782488 | 174315 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-15 | 2022-07-26 | 18.07.2022 | 80915228 | 2022-08-18 | 2022-07-29 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 31 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004461910 | 2022-06-17 | HA/REVENTE | STELIA | GOUPILLE | 4900044619 | 178383 | 10 | 14 | RTN | S9251186120000 | IS0035418S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-26 | 2022-07-26 | 04.08.2022 | 80920113 | 2022-07-29 | 2022-07-29 |  | OK | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 31 | 7 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2877992210 | 2022-03-23 | FABRICATION | SATAIR | BUNDLE | 28779922 | 174211 | 10 | 3 | RTN | D9000095477995 | IS0032050M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 100% | 2022-03-24 | NA | 100% | 2022-07-06 | 0% | NA | NA | NA |  |  | 2022-07-27 | 2022-07-27 |  |  | 2022-08-01 | 2022-08-01 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 3 | 2022 | 31 | 7 | 2022 | 5.193 | 61.653 | 2.0551 | 63.7081 | NA | 0 | 0
2871797310 | 2022-01-03 | HA/REVENTE | SATAIR | BRACKET | 28717973 | 170698 | 10 | 4 | RTN | A9252496620200 | IS0053087S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-29 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-07-19 | 2022-08-01 | 03.08.2022 | 80920019 | 2022-07-22 | 2022-08-04 |  |  | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 32 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2886604610 | 2022-07-21 | HA/REVENTE | SATAIR | CONNECTOR | 28866046 | 181650 | 10 | 6 | CRIT | EN2997SE61005D6 | IS0060811S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-08-24 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-17 | 2022-08-24 |  |  | 2022-08-19 | 2022-08-26 |  | OK | SPARES | Réception 24/08 - Regarder si expédié | C |  | 0 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 35 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884372210 | 2022-06-27 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28843722 | 178804 | 10 | 1 | RTN | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-21 | 2022-09-21 | 04.10.2022 | 80939280 | 2022-09-25 | 2022-09-25 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884372310 | 2022-06-27 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28843723 | 178805 | 10 | 5 | RTN | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-21 | 2022-09-21 | 04.10.2022 | 80939281 | 2022-09-25 | 2022-09-25 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2873478012 | 2022-01-28 | FABRICATION | SATAIR | 117 | 28734780 | NON-SPARES | 12 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990170 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-15 | NA | 100% | 2022-07-29 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-08-12 | 04.08.2022 | 80920166 | 2022-06-23 | 2022-08-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 33 | 8 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2873478013 | 2022-01-28 | FABRICATION | SATAIR | 117 | 28734780 | NON-SPARES | 13 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | 48842 | LTE990171 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-15 | NA | 100% | 2022-07-29 | 100% | NA | NA | NA |  |  | 2022-06-20 | 2022-08-12 | 04.08.2022 | 80920166 | 2022-06-23 | 2022-08-17 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 | 33 | 8 | 2022 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
614916910 | 2021-11-30 | FABRICATION | AD&S | 39 | 6149169 | 172502 | 10 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | NA | PB10052 | 5152308 | 0 | 0 | 0% | 100% | 50% | 100% | 2022-03-10 | NA | 100% | 2022-02-24 | 0% | NA | OUI |  |  |  | 2022-05-25 | 2022-10-12 | 17/10/2022 | 80944115 | 2022-05-30 | 2022-10-17 |  | OK | SEVILLE |  | O |  | 1 | N | N | N | 10 | 2022 | 11 | 2021 | 42 | 10 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL
2882227510 | 2022-05-19 | FABRICATION | SATAIR | 108 | 28822275 | 176935 | 10 | 1 | RTN | D9550010801195 | IS0059763M | NON PRESENT INDUS | 48842 | LTE990004 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-29 | NA | 100% | 2022-07-04 | 100% | NA | NA | NA |  |  | 2022-09-12 | 2022-08-23 | 29/08/2022 | 80925544 | 2022-09-15 | 2022-08-26 |  | OK | KIT FACTORY | RAS | O |  | 1 | N | O | N | 8 | 2022 | 5 | 2022 | 35 | 8 | 2022 | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2882346010 | 2022-05-21 | HA/REVENTE | SATAIR | FRONT PLATE 110VU | 28823460 | 177020 | 10 | 4 | RTN | D9251490100000 | IS0032740S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-06-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-15 | 2022-08-15 | 05.09.2022 | 80928849 | 2022-08-18 | 2022-08-18 |  | OK | SPARES | Stock ok regarder si expédié | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 34 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004458210 | 2022-06-13 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900044582 | 178070 | 10 | 2 | RTN | S9251363300000 | IS0035424S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-15 | 2022-08-15 | 24.08.2022 | 80924398 | 2022-08-18 | 2022-08-18 |  | OK | ROCHEFORT | Stock ok regarder si expédié | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 34 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2890469110 | 2022-09-30 | FABRICATION | SATAIR | WIRE-BONDING | 28904691 | 184506 | 10 | 23 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-10-03 | NA | 100% | 2022-10-04 | 100% | NA | NA |  |  |  | 2022-09-29 | 2022-10-06 | 11/10/2022 | 80942120 | 2022-10-01 | 2022-10-10 |  | OK | SPARES |  | O |  | 0 | N | N | N | 10 | 2022 | 9 | 2022 | 41 | 10 | 2022 | 4.7357 | 5.4809 | 0.02383 | 5.5047 | NA
2887132010 | 2022-08-01 | FABRICATION | SATAIR | 513 | 28871320 | 182116 | 10 | 1 | AOG | WF415ABAAAAB | IS0063340M | NON PRESENT INDUS |  | LTE990001 |  | 0 | 0 | 0% | 100% | 50% | 100% | 2022-08-24 | NA | 100% | 2022-08-22 | 0% | NA | NA | NA |  |  | 2022-08-08 | 2022-09-06 | 20/09/2022 | 80933922 | 2022-08-10 | 2022-09-08 |  | OK | SPARES | Demande d'impression LIP faite pour IS0013980S - Les relancer si besoin (mail transféré à Sonia) | O |  | 0 | N | N | N | 9 | 2022 | 8 | 2022 | 37 | 9 | 2022 | 0 | 0 | 0 | 0 | COL | 0 | 0
2884569510 | 2022-06-29 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28845695 | 178990 | 10 | 1 | RTN | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-22 | 2022-09-22 | 04.10.2022 | 80939282 | 2022-09-27 | 2022-09-27 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004464910 | 2022-06-27 | HA/REVENTE | STELIA | COVER ASSY 114VU | 4900044649 | 178803 | 10 | 2 | RTN | S9251363300000 | IS0035424S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-28 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-25 | 2022-08-25 | 24.08.2022 | 80924399 | 2022-08-30 | 2022-08-30 |  | OK | ROCHEFORT | Stock ok regarder si expédié | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 35 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2887522810 | 2022-08-08 | HA/REVENTE | SATAIR | SWITCH-DOUBLE POLE TOGGLE | 28875228 | 182171 | 10 | 2 |  | NSA931432A4BA0A | IS0034858S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | STOCK | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-31 | 2022-08-31 | 05.09.2022 | 80928850 | 2022-09-05 | 2022-09-05 |  | OK | SPARES |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 36 | 8 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
490004450610 | 2022-05-30 | HA/REVENTE | STELIA | FRONT PLATE ASSY 110VU | 4900044506 | 177666 | 10 | 1 | RTN | S9251038100000 | IS0035410S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-08-25 | 2022-09-01 | 05.09.2022 | 80928847 | 2022-08-30 | 2022-09-06 |  | OK | ROCHEFORT | Stock ok regarder si expédié | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 36 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884569610 | 2022-06-29 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28845696 | 178991 | 10 | 1 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-21 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-23 | 2022-09-23 | 04.10.2022 | 80939283 | 2022-09-27 | 2022-09-27 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
P29728221 | 2022-02-21 | FABRICATION | AIS | 265 | P2972822 | NON-SPARES | 1 | 1 | RTN | MD501-311101-01B | IS0032603M | NON PRESENT INDUS | 52674 | LTE900011 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-05 | NA | 100% | 2022-07-11 | 100% | NA | OUI | NA |  |  | 2022-08-05 | 2022-09-06 | Sous-poste | Sous-poste | 2022-08-10 | 2022-09-09 |  | OK |  | Blocage qualité / Mauvais numéro de plan sur platine avant (action qualité / pas de retour sur action en cours le 10/08) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 37 | 9 | 2022 | 0.205 | 1.16 | 0.38 | 1.54 | COL | 0 | 0
2890534410 | 2022-10-03 | FABRICATION | SATAIR | WIRE-BONDING | 28905344 | 184511 | 10 | 5 | CRIT | F0003008100000 | IS0032145M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-10-03 | NA | 100% | 2022-10-04 | 100% | NA | NA |  |  |  | 2022-09-30 | 2022-10-06 | 11/10/2022 | 80942120 | 2022-10-04 | 2022-10-10 |  | OK | SPARES |  | O |  | 0 | N | N | N | 10 | 2022 | 10 | 2022 | 41 | 10 | 2022 | 1.0295 | 1.1915 | 0.02383 | 1.2153 | NA
P29728221_1 | 2022-02-21 | FABRICATION | AIS | 265 | P2972822 | NON-SPARES | 1_1 | 1 | RTN | MD501-311101-01B | IS0032603M | NON PRESENT INDUS | 52674 | LTE990012 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-05 | NA | 100% | 2022-07-11 | 100% | NA | OUI | NA |  |  | 2022-08-05 | 2022-09-06 | Sous-poste | Sous-poste | 2022-08-10 | 2022-09-09 |  | OK |  | Blocage qualité / Mauvais numéro de plan sur platine avant (action qualité / pas de retour sur action en cours le 10/08) | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 | 37 | 9 | 2022 | 0.205 | 1.16 | 0.38 | 1.54 | COL | 0 | 0
2878498910 | 2022-03-30 | FABRICATION | SATAIR | 54 | 28784989 | 174712 | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 48842 | LTE990026 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-10 | NA | 90% | 2022-08-03 | 100% | NA | NA | NA |  |  | 2022-08-17 | 2022-09-07 | 12.09.2022 | 80931249 | 2022-08-22 | 2022-09-12 |  |  | KIT FACTORY | RAS | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 37 | 9 | 2022 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2878652510 | 2022-03-31 | FABRICATION | SATAIR | 54 | 28786525 | 174766 | 10 | 1 | RTN | D9551005400195 | IS0032110M | NON PRESENT INDUS | 48842 | LTE990027 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-10 | NA | 90% | 2022-08-03 | 100% | NA | NA | NA |  |  | 2022-08-17 | 2022-09-07 | 12/10/2022 | 80931250 | 2022-08-22 | 2022-09-12 |  |  | KIT FACTORY | RAS | O |  | 1 | N | N | N | 10 | 2022 | 3 | 2022 | 37 | 9 | 2022 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
450120113010 |  | FABRICATION | DES | KITS 9119VU | 4501201130 | NON-SPARES | 10 | 10 |  | A320EL061000-EPA | IS0059318M | NON PRESENT INDUS | 52677 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-16 | NA | 100% | 2022-09-13 | 100% | NA | OUI |  |  |  | 2022-07-15 | 2022-09-27 | 2022-10-11 | Sous-poste | 2022-07-20 | 2022-09-30 |  | OK |  |  | O |  | 1 | N | N | N | 10 | 2022 | 1 | 1900 | 40 | 9 | 2022 | 3.5 | 27 | 0.27 | 27.27 | NA
490004466610 | 2022-06-30 | FABRICATION | STELIA | OPTICAL FIBER | 4900044666 | 179064 | 10 | 2 | RTN | S954A1184158052 | IS0062875M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | Stock | NA | 100% | 2022-08-08 | 100% | NA | OUI | NA |  |  | 2022-09-01 | 2022-09-27 | 03/10/2022 | 80938787 | 2022-09-06 | 2022-09-30 |  | OK | ROCHEFORT | Fibre optique: OF lancé / Envoyer deossier de prod à P. BLANCO + suivre l'expé vers COL | O |  | 1 | N | N | N | 10 | 2022 | 6 | 2022 | 40 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2880035510 | 2022-04-19 | HA/REVENTE | SATAIR | PLACARD SET | 28800355 | 175566 | 10 | 2 | RTN | V1132043700095A | IS0059284S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-08-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-09 | 2022-09-09 | 05.09.2022 | 80928851 | 2022-09-14 | 2022-09-14 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 37 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2880035610 | 2022-04-19 | HA/REVENTE | SATAIR | PLACARD SET | 28800356 | 175567 | 10 | 2 | RTN | V1132043900095A | IS0059285S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-08-01 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-09 | 2022-09-09 | 05.09.2022 | 80928852 | 2022-09-14 | 2022-09-14 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 37 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878249010 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782490 | 174316 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-14 | 2022-09-14 | 14.09.2022 | 80932227 | 2022-09-19 | 2022-09-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 38 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878344710 | 2022-03-28 | HA/REVENTE | SATAIR | GUTTER ASSY | 28783447 | 174523 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-14 | 2022-09-14 | 14.09.2022 | 80932228 | 2022-09-19 | 2022-09-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 38 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878345410 | 2022-03-28 | HA/REVENTE | SATAIR | BRACKET ASSY | 28783454 | 174525 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-14 | 2022-09-14 | 14.09.2022 | 80932229 | 2022-09-19 | 2022-09-19 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 38 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2889955710 | 2022-09-20 | FABRICATION | SATAIR | OPTICAL FIBER 3030VB | 28899557 | 184012 | 10 | 1 | AOG | D9000095030695 | IS0062902M | NON PRESENT INDUS |  |  |  | 0 | 0 | 0% | 100% | 50% | 100% | STOCK | NA | 100% | 2022-09-26 | 100% | NA | NA |  | LAB |  | 2022-09-19 | 2022-09-28 | 06.10.2022 | 80940884 | 2022-09-21 | 2022-09-30 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 40 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2877995810 | 2022-03-23 | FABRICATION | SATAIR | SHEET ASSY | 28779958 | 174217 | 10 | 1 | RTN | F9252035500000 | IS0059353M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-08-30 | NA | 100% | 2022-09-14 | 100% | NA | NA |  |  |  | 2022-09-28 | 2022-10-03 | 05.10.2022 | 80939977 | 2022-10-03 | 2022-10-06 |  | OK | KIT FACTORY | ISM statut 35 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 41 | 10 | 2022 | 0 | 0.1 | 0.015 | 0.115 | COL | 0 | 0
68936651 | 2021-04-26 | FABRICATION | AD&S | 61 | 6893665 | 159107 | 1 | 1 | AOG | MB259ADABAAC | IS0060618M | NON PRESENT INDUS | 46111 | LTE990001 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-27 | 100% | 100% | 2022-03-15 | 100% | OUI | OUI |  |  |  | 2021-11-26 | 2022-10-03 | 04.10.2022 | 80939388 | 2021-11-30 | 2022-10-05 |  | OK | SEVILLE | NC composant Amphenol IS0056897S (réception 18/11/2022) | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 | 41 | 10 | 2022 | 0 | 1.54 | 0.4 | 1.94 | COL | 0 | 0
490004490510 | 2022-08-25 | HA/REVENTE | STELIA | BOUCHON EQUIPEE | 4900044905 | 183279 | 10 | 1 | CRIT | S9252360300000 | IS0061053S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-08-26 | 2022-09-21 | 21.09.2022 | 80934487 | 2022-08-30 | 2022-09-23 |  | OK | ROCHEFORT |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2881378610 | 2022-05-10 | HA/REVENTE | SATAIR | PLACARD SET | 28813786 | 176397 | 10 | 34 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-22 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-21 | 2022-09-21 | 25.07.2022 | 80916849 | 2022-09-26 | 2022-09-26 |  | OK | KIT FACTORY | Risque NC - Date courte | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2881379310 | 2022-05-10 | HA/REVENTE | SATAIR | PLACARD SET | 28813793 | 176398 | 10 | 34 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-22 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-21 | 2022-09-21 | 25.07.2022 | 80916850 | 2022-09-26 | 2022-09-26 |  | OK | KIT FACTORY | Risque NC - Date courte | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 39 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2883134910 | 2022-06-07 | FABRICATION | SATAIR | 27 | 28831349 | 177858 | 10 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990035 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-28 | NA | 100% | 2022-07-18 | 100% | NA | NA |  |  |  | 2022-08-16 | 2022-10-04 | 06/10/2022 | 80940786 | 2022-08-19 | 2022-10-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 41 | 10 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883134910_1 | 2022-06-07 | FABRICATION | SATAIR | 27 | 28831349 | NON-SPARES | 10_1 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990036 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-28 | NA | 100% | 2022-07-18 | 100% | NA | NA |  |  |  | 2022-08-16 | 2022-10-04 | 06/10/2022 | 80940786 | 2022-08-19 | 2022-10-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 41 | 10 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883134910_2 | 2022-06-07 | FABRICATION | SATAIR | 27 | 28831349 | NON-SPARES | 10_2 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990037 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-28 | NA | 100% | 2022-07-18 | 100% | NA | NA |  |  |  | 2022-08-16 | 2022-10-04 | 06/10/2022 | 80940786 | 2022-08-19 | 2022-10-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 41 | 10 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883134910_3 | 2022-06-07 | FABRICATION | SATAIR | 27 | 28831349 | NON-SPARES | 10_3 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990038 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-28 | NA | 100% | 2022-07-18 | 100% | NA | NA |  |  |  | 2022-08-16 | 2022-10-04 | 06/10/2022 | 80940786 | 2022-08-19 | 2022-10-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 41 | 10 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2884573410 | 2022-06-29 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28845734 | 178994 | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-29 | 2022-09-29 | 04.10.2022 | 80939279 | 2022-10-04 | 2022-10-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 40 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884573510 | 2022-06-29 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28845735 | 178995 | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-08-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-29 | 2022-09-29 | 04.10.2022 | 80939284 | 2022-10-04 | 2022-10-04 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 40 | 9 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2883134910_4 | 2022-06-07 | FABRICATION | SATAIR | 27 | 28831349 | NON-SPARES | 10_4 | 1 | RTN | D9551002700595 | IS0032094M | NON PRESENT INDUS | 48842 | LTE990039 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-06-28 | NA | 100% | 2022-07-18 | 100% | NA | NA |  |  |  | 2022-08-16 | 2022-10-04 | 06/10/2022 | 80940786 | 2022-08-19 | 2022-10-07 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 41 | 10 | 2022 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2884669110 | 2022-06-30 | HA/REVENTE | SATAIR | PLACARD | 28846691 | 179077 | 10 | 2 | RTN | D9100095455395 | IS0060691S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-08-30 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-10-03 | 2022-10-03 | 04.10.2022 | 80939285 | 2022-10-06 | 2022-10-06 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 41 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
614306310 | 2021-08-27 | FABRICATION | AD&S | 39 | 6143063 | 172501 | 10 | 1 | RTN | MB135ABAAAAC | IS0032207M | Terminé | NA | PB10020 | 5152308 | 0 | 0 | 0% | 100% | 50% | 100% | 2022-10-10 | NA | 100% | 2022-02-24 | 0% | NA | OUI |  |  |  | 2022-05-25 | 2022-10-12 |  |  | 2022-05-30 | 2022-10-17 |  | OK | SEVILLE | Screws ETEC cassé x3 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2021 | 42 | 10 | 2022 | 0.205 | 4.38 | 1.095 | 5.475 | COL
490004487210 | 2022-08-19 | HA/REVENTE | STELIA | GOUPILLE | 4900044872 | 182864 | 10 | 17 | RTN | S9251186120000 | IS0035418S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-10-04 | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-10-03 | 2022-10-04 | 05.10.2022 | 80940548 | 2022-10-06 | 2022-10-07 |  |  | ROCHEFORT | DD 28/10 - Aymene tente de raccourcir le LT | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 41 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2889913110 | 2022-09-20 | FABRICATION | SATAIR | OPTICAL FIBER 3031VB | 28899131 | 184011 | 10 | 1 | AOG | D9000095030595 | IS0062516M | NON PRESENT INDUS |  |  | 6146063 | 0 | 0 | 0% | 100% | 50% | 100% | STOCK | NA | 100% | 2022-09-26 | 0% | NA | NA |  | LAB |  | 2022-09-16 | 2022-10-17 | 24/10/2022 | 80947016 | 2022-09-20 | 2022-10-19 |  | OK | SPARES |  | O |  | 0 | N | N | N | 10 | 2022 | 9 | 2022 | 43 | 10 | 2022 | 0 | 0 | 0 | 0 | NA
2876244610_2 | 2022-03-04 | FABRICATION | SATAIR | BUNDLE | 28762446 | NON-SPARES | 10_2 | 1 | RTN | D9000095477995 | IS0032050M | Terminé | 48842 |  | 6090469 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-07-06 | 100% | NA | NA |  |  |  | 2022-07-27 | 2022-10-18 | Sous-poste | Sous-poste | 2022-08-01 | 2022-10-21 |  | OK | KIT FACTORY | RAS Prod en cours |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 43 | 10 | 2022 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA
2876244610_1 | 2022-03-04 | FABRICATION | SATAIR | BUNDLE | 28762446 | NON-SPARES | 10_1 | 1 | RTN | D9000095477995 | IS0032050M | Terminé | 48842 |  | 6090468 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-07-06 | 100% | NA | NA |  |  |  | 2022-07-27 | 2022-10-18 | Sous-poste | Sous-poste | 2022-08-01 | 2022-10-21 |  | OK | KIT FACTORY | RAS Prod en cours |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 43 | 10 | 2022 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA
2876244610 | 2022-03-04 | FABRICATION | SATAIR | BUNDLE | 28762446 | 173548 | 10 | 1 | RTN | D9000095477995 | IS0032050M | Terminé | 48842 |  | 6090467 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-03-24 | NA | 100% | 2022-07-06 | 100% | NA | NA |  | 06/10 : problème QR à analyser | 2022-10-21 | 2022-07-27 | 2022-10-18 |  |  | 2022-08-01 | 2022-10-21 |  | OK | KIT FACTORY | RAS Prod en cours |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 3 | 2022 | 43 | 10 | 2022 | 1.731 | 20.551 | 2.0551 | 22.6061 | NA
2878385010 | 2022-03-28 | FABRICATION | SATAIR | PLATE ASSY | 28783850 | 174528 | 10 | 1 | RTN | F9252020200000 | IS0032657M | Terminé | 48842 | 6145011 | 6145011 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-03 | NA | 100% | 2022-10-05 | 100% | NA | NA |  | 06/10 : non commencé manque IS0010150S | 2022-10-14 | 2022-09-29 | 2022-10-21 |  |  | 2022-10-04 | 2022-10-26 |  |  | KIT FACTORY | IS0010150S sorti le 21/10 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 3 | 2022 | 43 | 10 | 2022 | 0 | 0.1789 | 0.01789 | 0.19679 | NA
2884573210 | 2022-06-29 | FABRICATION | SATAIR | 116 | 28845732 | 178992 | 10 | 1 | RTN | D9551011600195 | IS0032594M | Terminé | 48842 | LTE990024 | 6132378 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-08-22 | NA | 100% | 2022-08-16 | 95% | OUI | NA |  | 06/10 : CT en cours manque etiquettes | 2022-10-14 | 2022-09-05 | 2022-10-21 | reste = 2) | LIVRAISO | 2022-09-08 | 2022-10-26 |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 43 | 10 | 2022 | 0.205 | 1.4 | 0.35 | 1.75 | COL
2883367410 | 2022-06-10 | FABRICATION | SATAIR | 27 | 28833674 | 177995 | 10 | 1 | AOG | D9551002700695 | IS0032097M | Terminé | 48842 | LTE990079 | 6145367 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-11 | NA | 100% | 2022-10-10 | 100% | NA | NA |  | 11/10 : CT/TEST | 2022-10-20 | 2022-08-17 | 2022-10-24 |  |  | 2022-08-19 | 2022-10-26 |  |  | KIT FACTORY |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 6 | 2022 | 44 | 10 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL
2883367410_1 | 2022-06-10 | FABRICATION | SATAIR | 27 | 28833674 | NON-SPARES | 10_1 | 1 | AOG | D9551002700695 | IS0032097M | Terminé | 48842 | LTE990080 | 6145368 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-11 | NA | 100% | 2022-10-10 | 100% | NA | NA |  |  |  | 2022-08-17 | 2022-10-24 | Sous-poste | Sous-poste | 2022-08-19 | 2022-10-26 |  |  | KIT FACTORY |  |  |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 44 | 10 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL
2883638610 | 2022-06-15 | FABRICATION | SATAIR | PROTECTION CAP | 28836386 | 178149 | 10 | 35 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | TBD | NA | 100% | 2022-09-28 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-10-18 | 17/10/2022 | 80944161 | 2022-10-10 | 2022-10-21 |  | OK | KIT FACTORY |  | O |  | 1 | O | N | N | 10 | 2022 | 6 | 2022 | 43 | 10 | 2022 | 0.0875 | 3.913 | 0.01118 | 3.9242 | NA
2878249210 | 2022-03-25 | HA/REVENTE | SATAIR | BRACKET ASSY | 28782492 | 174317 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-10-13 | 2022-10-25 | 21.10.2022 | 80946440 | 2022-10-18 | 2022-10-28 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA
2878344810 | 2022-03-28 | HA/REVENTE | SATAIR | GUTTER ASSY | 28783448 | 174524 | 10 | 8 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-10-13 | 2022-10-13 | 05.10.2022 | 80940550 | 2022-10-18 | 2022-10-18 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 42 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2878345510 | 2022-03-28 | HA/REVENTE | SATAIR | BRACKET ASSY | 28783455 | 174526 | 10 | 8 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-10-14 | 2022-10-25 | 21.10.2022 | 80946441 | 2022-10-19 | 2022-10-28 |  | OK | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA
2888708710 | 2022-08-26 | FABRICATION | SATAIR | BUNDLE | 28887087 | 182867 | 10 | 1 | AOG | V9297400001095 | IS0061660M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-14 | NA | 100% | 2022-09-12 | 100% | NA | NA | NA |  |  | 2022-08-29 | 2022-10-14 | 03/10/2022 | 80938517 | 2022-08-31 | 2022-10-18 |  | OK | KIT FACTORY |  | O |  | 0 | O | N | N | 10 | 2022 | 8 | 2022 | 42 | 10 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2888708710_1 | 2022-08-26 | FABRICATION | SATAIR | BUNDLE | 28887087 | NON-SPARES | 10_1 | 1 | AOG | V9297400001095 | IS0061660M | NON PRESENT INDUS | 48842 |  |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-14 | NA | 100% | 2022-09-12 | 100% | NA | NA | NA |  |  | 2022-08-29 | 2022-10-14 | 03/10/2022 | 80938517 | 2022-08-31 | 2022-10-18 |  | OK | KIT FACTORY |  | O |  | 0 | O | N | N | 10 | 2022 | 8 | 2022 | 42 | 10 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2882879910 | 2022-06-01 | FABRICATION | SATAIR | 27 | 28828799 | 177742 | 10 | 1 | AOG | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990076 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-11 | NA | 100% | 2022-09-14 | 100% | NA | NA |  |  |  | 2022-09-06 | 2022-10-20 | 2022-10-14 | 80943493 | 2022-09-08 | 2022-10-23 |  | OK | KIT FACTORY | Manquant IS0006431S (SAFRAN) - Réception 11/10/2022 | O |  | 0 | O | N | O | 10 | 2022 | 6 | 2022 | 43 | 10 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL
2856387410 | 2021-03-26 | FABRICATION | SATAIR | 511 | 28563874 | 157439 | 10 | 1 | EXP | A9550051100395 | IS0060409M | NON PRESENT INDUS | 43112 | LTE990001 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2021-12-01 | NA | 100% | 2022-01-17 | 100% | OUI | NA |  |  |  | 2021-04-21 | 2022-10-14 | 07.10.2022 | 80941091 | 2021-04-25 | 2022-10-19 |  | OK | SPARES | Réception YMCA le 07/10 | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 | 42 | 10 | 2022 | 0.37 | 4.01 | 1.07 | 5.08 | COL | 0 | 0
2882879910_1 | 2022-06-01 | FABRICATION | SATAIR | 27 | 28828799 | NON-SPARES | 10_1 | 1 | AOG | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990077 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-11 | NA | 100% | 2022-09-14 | 100% | NA | NA |  |  |  | 2022-09-06 | 2022-10-20 | 2022-10-14 | 80943493 | 2022-09-08 | 2022-10-23 |  | OK | KIT FACTORY | Manquant IS0006431S (SAFRAN) - Réception 11/10/2022 | O |  | 0 | #REF! | #REF! | O | 10 | 2022 | 6 | 2022 | 43 | 10 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL
2882879910_2 | 2022-06-01 | FABRICATION | SATAIR | 27 | 28828799 | NON-SPARES | 10_2 | 1 | AOG | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990078 |  | 0 | 0 | 100% | 100% | 100% | 100% | 2022-10-11 | NA | 100% | 2022-09-14 | 100% | NA | NA |  |  |  | 2022-09-06 | 2022-10-20 | 2022-10-14 | 80943493 | 2022-09-08 | 2022-10-23 |  | OK | KIT FACTORY | Manquant IS0006431S (SAFRAN) - Réception 11/10/2022 | O |  | 0 | O | N | O | 10 | 2022 | 6 | 2022 | 43 | 10 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL
2890544410 | 2022-10-03 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28905444 | 184522 | 10 | 2 | CRIT | D9251095600000 | IS0053509S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-10-24 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-30 | 2022-10-25 |  |  | 2022-10-04 | 2022-10-27 |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA
2890544510 | 2022-10-03 | HA/REVENTE | SATAIR | PLACARD SET 301VU | 28905445 | 184523 | 10 | 2 | CRIT | D9251095400000 | IS0053354S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-10-24 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-09-30 | 2022-10-25 |  |  | 2022-10-04 | 2022-10-27 |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA
2891712110 | 2022-10-19 | FABRICATION | SATAIR | Optical Fiber 3435-0153 | 28917121 | 185170 | 10 | 5 | CRIT | D9000095028495 | IS0032654M | Terminé |  |  | 6157703 |  |  | 0% | 0% | 0% | 100% | 2022-10-19 | NA | 100% | 2022-10-20 | 0% | NA | NA | NA |  |  | 2022-10-25 | 2022-10-25 |  |  | 2022-10-27 | 2022-10-27 |  | OK | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2891851510 | 2022-10-20 | FABRICATION | SATAIR | BUNDLE | 28918515 | 185325 | 10 | 7 | AOG | V9253120000096 | IS0032173M | Terminé |  |  | 6158610 |  |  | 0% | 0% | 0% | 100% | Stock | NA | 100% | 2022-10-21 | 0% | NA | NA | NA |  |  | 2022-10-25 | 2022-10-25 |  |  | 2022-10-27 | 2022-10-27 |  | OK | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 44 | 10 | 2022 | 0.9023 | 1.0185 | 0.1 | 1.1185 | COL | 0 | 0
2874388910 | 2022-02-10 | FABRICATION | SATAIR | 412 | 28743889 | 172405 | 10 | 1 | CRIT | WF412ADACAAF | IS0062465M | Terminé | 48842 | LTE990001 | 0 |  |  | 100% | 0% | 50% | 95% | TBD | 0% | 85.5% | TBD | 0% | NA | NA |  |  |  | 2022-02-09 | 2022-10-27 |  |  | 2022-02-11 | 2022-10-31 |  | OK | SPARES | Dépannage CASA ok 4 articles (articles sortie 04/08 toujours pas réceptionné) - Réception structure le 28/10 - IS0006726S 19/11 - IS0006722S 22/11 - IS0006714S 17/10 - IS0006723S 27/10 |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 44 | 10 | 2022 | 0.23 | 6.42 | 2.34 | 8.76 | COL
2884573210_1 | 2022-06-29 | FABRICATION | SATAIR | 116 | 28845732 | NON-SPARES | 10_1 | 1 | AOG | D9551011600195 | IS0032594M | Terminé | 48842 | LTE990025 | 6132379 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-08-22 | NA | 100% | 2022-08-16 | 95% | NA | NA |  |  |  | 2022-09-06 | 2022-10-31 | Sous-poste | Sous-poste | 2022-09-08 | 2022-11-02 |  | OK | KIT FACTORY | T3S départ 24/10 - Livraison 25/10 |  |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 45 | 10 | 2022 | 0.205 | 1.4 | 0.35 | 1.75 | COL
2889072410 | 2022-09-01 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28890724 | 183284 | 10 | 2 | CRIT | D9251805700000 | IS0032776S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-08-31 | 2022-10-25 | 26.09.2022 | 80936125 | 2022-09-02 | 2022-10-27 |  | OK | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 44 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2884573210_2 | 2022-06-29 | FABRICATION | SATAIR | 116 | 28845732 | NON-SPARES | 10_2 | 1 | AOG | D9551011600195 | IS0032594M | Terminé | 48842 | LTE990026 | 6132420 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-08-22 | NA | 100% | 2022-08-16 | 95% | NA | NA |  |  |  | 2022-09-06 | 2022-10-31 | Sous-poste | Sous-poste | 2022-09-08 | 2022-11-02 |  | OK | KIT FACTORY | T3S départ 24/10 - Livraison 25/10 |  |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 45 | 10 | 2022 | 0.205 | 1.4 | 0.35 | 1.75 | COL
2878652510_1 | 2022-03-31 | FABRICATION | SATAIR | 54 | 28786525 | NON-SPARES | 10_1 | 1 | RTN | D9551005400195 | IS0032110M | Terminé | 48842 | LTE990028 | 6092795 | 0 | 0 | 100% | 100% | 100% | 100% | 2023-06-23 | NA | 90% | 2022-08-03 | 100% | NA | NA |  |  |  | 2022-08-17 | 2022-10-28 | Sous-poste | Sous-poste | 2022-08-22 | 2022-11-02 |  |  | KIT FACTORY |  | Stand-By |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2022 | 44 | 10 | 2022 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL | 0 | 0
2891537110 | 2022-10-17 | FABRICATION | SATAIR | OPTICAL FIBER | 28915371 | 185113 | 10 | 1 | AOG | V9271700920800 | IS0063805M | Terminé | 48842 |  | 6158077 |  |  | 100% | 0% | 50% | 100% | 2022-10-17 | NA | 100% | 2022-10-20 | 0% | NA | NA | NA |  |  | 2022-10-13 | 2022-10-31 |  |  | 2022-10-17 | 2022-11-02 |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 45 | 10 | 2022 | 0 | 0 | 0 | 0 | COL | 0 | 0
2885058410 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | 179235 | 10 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132427 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  | 2022-11-04 | 2022-10-05 | 2022-11-01 |  |  | 2022-10-08 | 2022-11-04 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 45 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885058410_1 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_1 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132428 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-01 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-04 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 45 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
69225001 | 2022-02-09 | FABRICATION | AD&S | 402 | 6922500 | 172559 | 1 | 1 | RTN | MB045ACAAAAB | IS0062403M | Terminé | 48842 | LTE990002 | 6142994 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-05-16 | 100% | 100% | 2022-10-03 | 100% | NA | OUI |  | 06/10 : non commencé, manque compo | 2022-11-04 | 2022-09-27 | 2022-11-01 |  |  | 2022-09-30 | 2022-11-04 |  | OK | SEVILLE |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 45 | 11 | 2022 | 0.62 | 9.77 | 3.06 | 12.83 | COL
69169071 | 2021-12-10 | FABRICATION | AD&S | 11 | 6916907 | 169806 | 1 | 1 | RTN | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990011 | 6089315 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-01-26 | 100% | 100% | 2022-07-01 | 99% | NA | OUI |  | 19/09 : prod OK manque IS0007461S x2 | 2022-11-01 | 2021-12-14 | 2022-11-01 |  |  | 2021-12-17 | 2022-11-04 |  | OK | SEVILLE | Manque IS0007461S x2 - Réception 27/10 qté 2 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 12 | 2021 | 45 | 11 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
2884675210 | 2022-06-30 | FABRICATION | SATAIR | 313 | 28846752 | 179009 | 10 | 1 | AOG | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990006 | 6132426 | 0 | 0 | 100% | 100% | 100% | 100% | 2023-01-16 | 100% | 100% | 2022-09-12 | 90% | NA | NA |  | 06/10 : non commencé manque structure | 2022-10-21 | 2022-06-28 | 2022-11-02 |  |  | 2022-06-30 | 2022-11-04 |  |  | SPARES | Structure servie le 19/10 |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 6 | 2022 | 45 | 11 | 2022 | 0.205 | 3.5 | 0.875 | 4.375 | COL
2885058410_2 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_2 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132429 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-04 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-09 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 45 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885058410_3 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_3 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132430 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-04 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-09 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 45 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885058510 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850585 | 179236 | 10 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6132435 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-28 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  | 2022-11-10 | 2022-10-05 | 2022-11-08 |  |  | 2022-10-08 | 2022-11-11 |  | OK | SPARES | Proposer échéancier |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 46 | 11 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
69212731 | 2022-01-28 | FABRICATION | AD&S | 402 | 6921273 | 172011 | 1 | 1 | AOG | MB045ACAAAAB | IS0062403M | Terminé | 48842 | LTE990001 | 6160333 |  |  | 100% | 0% | 50% | 100% | 2022-03-14 | 100% | 100% | 2022-11-01 | 0% | NA | OUI |  |  |  | 2022-09-13 | 2022-11-11 |  |  | 2022-09-15 | 2022-11-15 |  | OK | SEVILLE |  |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 1 | 2022 | 46 | 11 | 2022 | 0.62 | 9.77 | 3.06 | 12.83 | COL
2886775910 | 2022-07-26 | FABRICATION | SATAIR | PROTECTION CAP | 28867759 | 181705 | 10 | 4 | RTN | F0003003000100 | IS0063331M | Terminé |  |  | 6158733 |  |  | 0% | 0% | 0% | 100% | Stock | NA | 100% | 2022-10-31 | 0% | NA | NA |  |  | 2022-11-14 | 2022-11-14 | 2022-11-14 |  |  | 2022-11-17 | 2022-11-17 |  | OK | KIT FACTORY | Paramétrage en cours |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 47 | 11 | 2022 | 0 | 0 | 0 | 0 | COL
2885058510_1 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850585 | NON-SPARES | 10_1 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6132436 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-28 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-15 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-18 |  | OK | SPARES | Proposer échéancier |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 47 | 11 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2885058410_4 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_4 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132431 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-15 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-18 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 47 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2881631610 | 2022-05-10 | HA/REVENTE | SATAIR | PLACARD SET | 28816316 | 176429 | 10 | 4 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-22 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-11-10 | 2022-11-10 | 25.07.2022 | 80916852 | 2022-11-15 | 2022-11-15 |  | OK | KIT FACTORY | Risque NC - Date courte | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 46 | 11 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2881633010 | 2022-05-10 | HA/REVENTE | SATAIR | PLACARD SET | 28816330 | 176430 | 10 | 4 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-07-22 | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-11-10 | 2022-11-10 | 25.07.2022 | 80916853 | 2022-11-15 | 2022-11-15 |  | OK | KIT FACTORY | Risque NC - Date courte | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 | 46 | 11 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
2885058410_5 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_5 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 6132432 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-09-19 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-15 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-18 |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 47 | 11 | 2022 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2882071810 | 2022-05-17 | FABRICATION | SATAIR | PROTECTION CAP | 28820718 | 176878 | 10 | 15 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | 2022-11-08 | 0% | NA | NA | NA |  |  | 2022-11-22 | 2022-11-22 |  |  | 2022-11-25 | 2022-11-25 |  | OK | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 5 | 2022 | 48 | 11 | 2022 | 0.0375 | 1.677 | 0.01118 | 1.6882 | NA | 0 | 0
69224052 | 2022-02-09 | FABRICATION | AD&S | 11 | 6922405 | 172557 | 2 | 1 | EXP | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990010 | 6159019 |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | 100% | 100% | 2022-10-31 | 0% | NA | OUI |  |  |  | 2022-07-06 | 2022-11-15 |  |  | 2022-07-09 | 2022-11-18 |  |  | SEVILLE |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 47 | 11 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
2885058510_2 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850585 | NON-SPARES | 10_2 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6132437 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-28 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-22 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-25 |  | OK | SPARES | Proposer échéancier |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 48 | 11 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2886517010 | 2022-07-20 | FABRICATION | SATAIR | 27 | 28865170 | 181359 | 10 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990084 |  |  |  | 100% | 0% | 50% | 100% | 2022-11-14 | NA | 100% | 2022-11-15 | 0% | NA | NA | NA |  |  | 2022-09-16 | 2022-11-25 |  |  | 2022-09-21 | 2022-11-30 |  | OK | KIT FACTORY | IS0006465S SAFRAN délai 14-11-2022 / Attente AR MECAHERS / commande placée au 13/09 (saisie le 06/07) | C |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 48 | 11 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2886517010_1 | 2022-07-20 | FABRICATION | SATAIR | 27 | 28865170 | NON-SPARES | 10_1 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 | LTE990085 |  |  |  | 100% | 0% | 50% | 100% | 2022-11-14 | NA | 100% | 2022-11-15 | 0% | NA | NA | NA |  |  | 2022-09-16 | 2022-11-25 | Sous-poste | Sous-poste | 2022-09-21 | 2022-11-30 |  | OK | KIT FACTORY | IS0006465S SAFRAN délai 14-11-2022 / Attente AR MECAHERS / commande placée au 13/09 (saisie le 06/07) | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 48 | 11 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883367410_2 | 2022-06-10 | FABRICATION | SATAIR | 27 | 28833674 | NON-SPARES | 10_2 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-11-14 | NA | 100% | 2022-11-15 | 0% | NA | NA | NA |  |  | 2022-08-16 | 2022-11-25 | Sous-poste | Sous-poste | 2022-08-19 | 2022-11-30 |  | OK | KIT FACTORY | IS0006465S dépannage AIB départ HBG le 08/09 / MECAHERS 13/09 | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 48 | 11 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883367410_3 | 2022-06-10 | FABRICATION | SATAIR | 27 | 28833674 | NON-SPARES | 10_3 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-11-14 | NA | 100% | 2022-11-15 | 0% | NA | NA | NA |  |  | 2022-08-16 | 2022-11-25 | Sous-poste | Sous-poste | 2022-08-19 | 2022-11-30 |  | OK | KIT FACTORY | IS0006465S dépannage AIB départ HBG le 08/09 / MECAHERS 13/09 | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 48 | 11 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2883367410_4 | 2022-06-10 | FABRICATION | SATAIR | 27 | 28833674 | NON-SPARES | 10_4 | 1 | RTN | D9551002700695 | IS0032097M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-11-14 | NA | 100% | 2022-11-15 | 0% | NA | NA | NA |  |  | 2022-08-16 | 2022-11-25 | Sous-poste | Sous-poste | 2022-08-19 | 2022-11-30 |  | OK | KIT FACTORY | IS0006465S dépannage AIB départ HBG le 08/09 / MECAHERS 13/09 | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 48 | 11 | 2022 | 0.205 | 4.9173 | 1.2293 | 6.1466 | COL | 0 | 0
2885058510_3 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850585 | NON-SPARES | 10_3 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6132438 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-07-28 | NA | 100% | 2022-09-12 | 100% | NA | NA |  |  |  | 2022-10-05 | 2022-11-22 | Sous-poste | Sous-poste | 2022-10-08 | 2022-11-25 |  | OK | SPARES | Proposer échéancier |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 48 | 11 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
430002900920 | 2022-05-13 | HA/REVENTE | STELIA | VOYANT CARRE | 4300029009 | 176806 | 20 | 1 | RTN | E0276CN3FP007 | IS0032217S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-11-21 | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-07-08 | 2022-11-23 |  |  | 2022-07-13 | 2022-11-28 |  | OK | ROCHEFORT |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 5 | 2022 | 48 | 11 | 2022 | 0 | 0 | 0 | 0 | NA
68936652 | 2021-04-26 | FABRICATION | AD&S | 61 | 6893665 | 159107 | 2 | 1 | AOG | MB259ADABAAC | IS0060618M | Terminé | 46111 | LTE990002 | 6017056 | 0 | 0 | 100% | 100% | 100% | 100% | 2021-10-27 | 100% | 100% | 2022-03-15 | 100% | OUI | OUI |  | 06/10 : CT OK manque ETEC | 2022-11-25 | 2021-11-26 | 2022-11-25 |  |  | 2021-11-30 | 2022-11-29 |  | OK | SEVILLE | Attente ETEC |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 4 | 2021 | 48 | 11 | 2022 | 0 | 1.54 | 0.4 | 1.94 | COL
69220491 | 2022-02-04 | FABRICATION | AD&S | 11 | 6922049 | 172288 | 1 | 1 | RTN | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990013 | 6089318 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 100% | 100% | 2022-07-01 | 99% | NA | OUI |  | 19/09 : prod OK manque IS0007461S x2 | 2022-12-01 | 2022-02-10 | 2022-12-01 |  |  | 2022-02-15 | 2022-12-06 |  | OK | SEVILLE | Manque IS0007461S x2 - Problèmes SAFRAN - réception 27/10 qty 1 + qty 1 le 29/11 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 49 | 12 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
69220492 | 2022-02-04 | FABRICATION | AD&S | 11 | 6922049 | 172288 | 2 | 1 | RTN | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990016 | 6139644 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 100% | 100% | 2022-09-28 | 95% | NA | OUI |  | 06/10 : non commencé manquant | 2022-12-01 | 2022-09-07 | 2022-12-01 |  |  | 2022-09-10 | 2022-12-06 |  | OK | SEVILLE | Manquant IS0007461S (SAFRAN) - Réception 2U le 29/11 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 49 | 12 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
69220493 | 2022-02-04 | FABRICATION | AD&S | 11 | 6922049 | 172288 | 3 | 1 | RTN | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990017 | 6139645 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 100% | 100% | 2022-09-28 | 95% | NA | OUI |  | 06/10 : non commencé manquant | 2022-12-01 | 2022-09-07 | 2022-12-01 |  |  | 2022-09-10 | 2022-12-06 |  | OK | SEVILLE | Manquant IS0007461S (SAFRAN) - Réception 2U le 29/11 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 2 | 2022 | 49 | 12 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
69266781 | 2022-03-25 | FABRICATION | AD&S | 11 | 6926678 | 174521 | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990018 | 6139643 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 100% | 100% | 2022-09-21 | 99% | NA | OUI |  | 06/10 : complet, vérifier pour prélèvement | 2022-12-01 | 2022-04-06 | 2022-12-02 |  |  | 2022-04-08 | 2022-12-06 |  |  | SEVILLE | Manquant IS0007461S (SAFRAN) - Réception 2U le 29/11 |  |  | 0 | #VALUE! | #VALUE! | N |  |  | 3 | 2022 | 49 | 12 | 2022 | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
2887725710 | 2022-08-11 | FABRICATION | SATAIR | BUNDLE | 28877257 | 183216 | 10 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6157390 |  |  | 100% | 0% | 50% | 100% | 2022-09-22 | NA | 100% | 2022-10-24 | 0% | NA | NA |  |  | 2022-12-09 | 2022-11-09 | 2022-12-06 |  |  | 2022-11-14 | 2022-12-09 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 50 | 12 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2887725710_1 | 2022-08-11 | FABRICATION | SATAIR | BUNDLE | 28877257 | NON-SPARES | 10_1 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6157391 |  |  | 100% | 0% | 50% | 100% | 2022-09-22 | NA | 100% | 2022-10-24 | 0% | NA | NA |  |  |  | 2022-11-09 | 2022-12-06 | Sous-poste | Sous-poste | 2022-11-14 | 2022-12-09 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 50 | 12 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2887725710_2 | 2022-08-11 | FABRICATION | SATAIR | BUNDLE | 28877257 | NON-SPARES | 10_2 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6157392 |  |  | 100% | 0% | 50% | 100% | 2022-09-22 | NA | 100% | 2022-10-24 | 0% | NA | NA |  |  |  | 2022-11-09 | 2022-12-06 | Sous-poste | Sous-poste | 2022-11-14 | 2022-12-09 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 50 | 12 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2887725710_3 | 2022-08-11 | FABRICATION | SATAIR | BUNDLE | 28877257 | NON-SPARES | 10_3 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6157393 |  |  | 100% | 0% | 50% | 100% | 2022-09-22 | NA | 100% | 2022-10-24 | 0% | NA | NA |  |  |  | 2022-11-09 | 2022-12-06 | Sous-poste | Sous-poste | 2022-11-14 | 2022-12-09 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 50 | 12 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2887725710_4 | 2022-08-11 | FABRICATION | SATAIR | BUNDLE | 28877257 | NON-SPARES | 10_4 | 1 | RTN | V9297404108695 | IS0060810M | Terminé | 48842 |  | 6157394 |  |  | 100% | 0% | 50% | 100% | 2022-09-22 | NA | 100% | 2022-10-24 | 0% | NA | NA |  |  |  | 2022-11-09 | 2022-12-06 | Sous-poste | Sous-poste | 2022-11-14 | 2022-12-09 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 50 | 12 | 2022 | 0.435 | 6.211 | 3.07 | 9.281 | NA
490004447720 | 2022-05-23 | HA/REVENTE | STELIA | PROTECTION | 4900044477 | 177205 | 20 | 3 | EXP | S9251047420000 | IS0060011S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-09-08 | NA | 100% | NA | NA |  | NA |  |  |  | 2022-12-07 | 2022-12-07 |  |  | 2022-12-12 | 2022-12-12 |  | OK | ROCHEFORT |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 5 | 2022 | 50 | 12 | 2022 | 0 | 0 | 0 | 0 | NA
2883313210 | 2022-06-09 | HA/REVENTE | SATAIR | PLATE-BLANKING | 28833132 | 177919 | 10 | 2 | RTN | A9252842100000 | IS0006167S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | [5 empty] | 2022-12-27 | 2022-12-27 |  |  | 2022-12-30 | 2022-12-30 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2022 | 53 | 12 | 2022 | 0 | 0 | 0 | 0 | NA
2886776510 | 2022-07-26 | HA/REVENTE | SATAIR | PLACARD | 28867765 | 181707 | 10 | 2 | RTN | D9251081700000 | IS0060818S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-12-22 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-01-02 | 2023-01-02 |  |  | 2023-01-05 | 2023-01-05 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0 | 0 | 0 | 0 | NA
2889642410 | 2022-09-13 | HA/REVENTE | SATAIR | PLATE-BLANKING | 28896424 | 183921 | 10 | 3 | RTN | A9252842100000 | IS0006167S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2022-12-22 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-01-02 | 2023-01-02 |  |  | 2023-01-05 | 2023-01-05 |  | OK | KIT FACTORY | 2 PO SAP - Fouchana (pas sortie du stock) et MECAHERS (AR 22/12) |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 1 | 1 | 2023 | 0 | 0 | 0 | 0 | NA
2885058410_6 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_6 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-05 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-08 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885058410_7 | 2022-07-05 | FABRICATION | SATAIR | BUNDLE | 28850584 | NON-SPARES | 10_7 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-05 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-08 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | 179587 | 10 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 |  |  | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_1 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_1 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_2 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_2 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_3 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_3 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_4 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_4 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_5 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_5 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_6 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_6 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_7 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_7 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2885696310_8 | 2022-07-12 | FABRICATION | SATAIR | BUNDLE | 28856963 | NON-SPARES | 10_8 | 1 | RTN | V9297400001095 | IS0061660M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-12-16 | NA | 100% | 2022-12-16 | 0% | NA | NA |  |  |  | 2022-10-12 | 2023-01-03 | Sous-poste | Sous-poste | 2022-10-15 | 2023-01-06 |  | OK | SPARES | IS0006846S (réception 14/09) & IS0009213S (réception 16/12) Dde dépannage AIB faite / IS0006912S réception 19/09 |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.435 | 2.96 | 2.155 | 5.115 | NA
2883643710 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | 178347 | 10 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  | 0 | 2023-01-03 | 2023-01-03 |  |  | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_1 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_1 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_2 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_2 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_3 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_3 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_4 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_4 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_5 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_5 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_6 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_6 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_7 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_7 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2883643710_8 | 2022-06-15 | FABRICATION | SATAIR | BUNDLE | 28836437 | NON-SPARES | 10_8 | 1 | RTN | V9253110000095B | IS0063136M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-13 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 1 | 1 | 2023 | 0 | 0.1455 | 0.01455 | 0.16005 | COL
2885490310 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | 179588 | 10 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 |  |  | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2885490310_1 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | NON-SPARES | 10_1 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2885490310_2 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | NON-SPARES | 10_2 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2885490310_3 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | NON-SPARES | 10_3 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2885490310_4 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | NON-SPARES | 10_4 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2885490310_5 | 2022-07-08 | FABRICATION | SATAIR | BUNDLE | 28854903 | NON-SPARES | 10_5 | 1 | RTN | V9293110100095A | IS0059303M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-09 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.478 | 1.1088 | 0.1108 | 1.2196 | NA
2886583710 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | 181653 | 10 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 |  |  | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_1 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_1 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_2 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_2 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_3 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_3 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_4 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_4 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_5 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_5 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_6 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_6 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_7 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_7 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583710_8 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865837 | NON-SPARES | 10_8 | 1 | RTN | V9253110000095A | IS0063329M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0706 | 3.2027 | 0.3202 | 3.5229 | COL
2886583810 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | 181654 | 10 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 |  |  | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_1 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_1 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_2 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_2 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_3 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_3 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_4 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_4 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_5 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_5 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_6 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_6 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_7 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_7 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583810_8 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865838 | NON-SPARES | 10_8 | 1 | RTN | V9253100000095A | IS0059357M | En cours | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.0411 | 3.7333 | 0.373 | 4.1063 | COL
2886583910 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | 181655 | 10 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 |  |  | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_1 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_1 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_2 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_2 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_3 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_3 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_4 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_4 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_5 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_5 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_6 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_6 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_7 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_7 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2886583910_8 | 2022-07-21 | FABRICATION | SATAIR | BUNDLE | 28865839 | NON-SPARES | 10_8 | 1 | RTN | V9253120000095A | IS0059305M | Terminé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 100% | 2022-08-01 | NA | 100% | 2022-12-05 | 0% | NA | NA |  |  |  | 2023-01-03 | 2023-01-03 | Sous-poste | Sous-poste | 2023-01-06 | 2023-01-06 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 | 1 | 1 | 2023 | 0.5418 | 12.1435 | 1.21 | 13.3535 | COL
2889657410_1 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_1 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_2 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_2 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_3 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_3 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_4 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_4 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_5 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_5 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_6 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_6 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_7 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_7 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_8 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_8 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_9 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_9 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_10 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_10 | 1 | RTN | V9297404002895 | IS0060809M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_11 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_11 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_12 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_12 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_13 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_13 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_14 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_14 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2889657410_15 | 2022-09-14 | FABRICATION | SATAIR | BUNDLE | 28896574 | NON-SPARES | 10_15 | 1 | RTN | V9297404002895 | IS0060809M | Terminé |  |  | 0 |  |  | 0% | 0% | 0% | 100% | 2022-10-03 | NA | 100% | 2022-12-12 | 0% | NA | NA |  |  |  | 2023-01-09 | 2023-01-09 | Sous-poste | Sous-poste | 2023-01-12 | 2023-01-12 |  | OK | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 | 2 | 1 | 2023 | 0.435 | 6.211 | 3.07 | 9.281 | NA
2887345810 | 2022-08-04 | FABRICATION | SATAIR | 54 | 28873458 | 182144 | 10 | 1 | RTN | D9551005400195 | IS0032110M | Terminé |  | LTE990030 | 0 |  |  | 0% | 0% | 0% | 99% | TBD | NA | 99% | 2023-01-02 | 0% | NA | NA |  |  |  | 2023-01-16 | 2023-01-16 |  |  | 2023-01-19 | 2023-01-19 |  | OK | KIT FACTORY | Reception Mecahers 09/12 - Article KORRY IS0007478S |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 3 | 1 | 2023 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL
2887345810_1 | 2022-08-04 | FABRICATION | SATAIR | 54 | 28873458 | NON-SPARES | 10_1 | 1 | RTN | D9551005400195 | IS0032110M | Terminé |  | LTE990031 | 0 |  |  | 0% | 0% | 0% | 99% | TBD | NA | 99% | 2023-01-02 | 0% | NA | NA |  |  |  | 2023-01-16 | 2023-01-16 | Sous-poste | Sous-poste | 2023-01-19 | 2023-01-19 |  | OK | KIT FACTORY | Reception Mecahers 09/12 - Article KORRY IS0007478S trouver une autre source |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2022 | 3 | 1 | 2023 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL
2889426210 | 2022-09-08 | FABRICATION | SATAIR | 27 | 28894262 | 183387 | 10 | 1 | RTN | D9551002700595 | IS0032094M | Terminé | 48843 | LTE990040 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-29 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2023-01-16 | 2023-01-16 |  |  | 2023-01-19 | 2023-01-19 |  | OK | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 3 | 1 | 2023 | 0.36 | 4.9173 | 1.2293 | 6.1466 | COL
2888209310 | 2022-08-18 | HA/REVENTE | SATAIR | BRACKET ASSY | 28882093 | 183232 | 10 | 4 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-01-30 | 2023-01-30 |  |  | 2023-02-02 | 2023-02-02 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 5 | 1 | 2023 | 0 | 0 | 0 | 0 | NA
2888209410 | 2022-08-18 | HA/REVENTE | SATAIR | BRACKET ASSY | 28882094 | 183233 | 10 | 4 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-01-30 | 2023-01-30 |  |  | 2023-02-02 | 2023-02-02 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 5 | 1 | 2023 | 0 | 0 | 0 | 0 | NA
2888209510 | 2022-08-18 | HA/REVENTE | SATAIR | GUTTER ASSY | 28882095 | 183234 | 10 | 4 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-01-30 | 2023-01-30 |  |  | 2023-02-02 | 2023-02-02 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 5 | 1 | 2023 | 0 | 0 | 0 | 0 | NA
2890764310 | 2022-10-07 | HA/REVENTE | SATAIR | GUTTER ASSY | 28907643 | 184877 | 10 | 30 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-02-01 | 2023-02-01 |  |  | 2023-02-06 | 2023-02-06 |  | OK | KIT FACTORY | Replacer les commandes en fonction des dates de besoin |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 5 | 2 | 2023 | 0 | 0 | 0 | 0 | NA
2889642510 | 2022-09-13 | HA/REVENTE | SATAIR | BRACKET ASSY | 28896425 | 183922 | 10 | 4 | RTN | D9251734300000 | IS0032771S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-02-09 | 2023-02-09 |  |  | 2023-02-14 | 2023-02-14 |  | OK | KIT FACTORY | Attente chiffrage ROSSI - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 6 | 2 | 2023 | 0 | 0 | 0 | 0 | NA
2887282010 | 2022-08-03 | FABRICATION | SATAIR | 54 | 28872820 | 182131 | 10 | 1 | RTN | D9551005400195 | IS0032110M | Terminé | 48842 | LTE990029 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | 2023-01-30 | 0% | NA | NA |  |  |  | 2023-02-13 | 2023-02-13 |  |  | 2023-02-16 | 2023-02-16 |  | OK | KIT FACTORY | Reception - M ecahers 09/12 - Attente AR confié SATAIR - À relancer - |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 7 | 2 | 2023 | 0.205 | 3.0297 | 0.75743 | 3.7871 | COL
2891674910 | 2022-10-19 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 28916749 | 185171 | 10 | 2 | RTN | F9251485400000 | IS0033627S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-03-16 | 2023-03-16 |  |  | 2022-03-21 | 2023-03-21 |  | OK | KIT FACTORY | PO placée mais pas signé |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 11 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2890872310 | 2022-10-07 | HA/REVENTE | SATAIR | PLATE ASSY | 28908723 | 184880 | 10 | 2 | RTN | F9251487400000 | IS0033628S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-03-16 | 2023-03-16 |  |  | 2023-03-21 | 2023-03-21 |  | OK | KIT FACTORY | RFQ à envoyer ROSSI et LBG |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 10 | 2022 | 11 | 3 | 2023 | 0 | 0 | 0 | 0 | NA
2887346110 | 2022-08-04 | HA/REVENTE | SATAIR | GUTTER ASSY | 28873461 | 182145 | 10 | 4 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-03-17 | 2023-03-17 |  |  | 2023-03-22 | 2023-03-22 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 11 | 3 | 2023 | 0 | 0 | 0 | 0 | NA
2833373710 | 2019-11-18 | FABRICATION | SATAIR | LEAD-BONDING | 28333737 | NON-SPARES | 10 | 2 | RTN | A9252282400400 | 0 | NON PRESENT INDUS | 30750 | 484394-1 = > 484394-2 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-13 | NA | 100% | 2020-03-13 | 100% | NA | NA | 5.556% |  |  | 2020-02-13 |  | Sous-poste | Sous-poste | 2020-02-19 |  |  |  | Allemagne | Attente HA pince / LT 12W - Demande dep à AIB EC | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 |  |  |  | 0 | 0.766 | 0.0383 | 0.8043 | NA | 0 | 0 | 277
2812312811 | 2019-04-10 | FABRICATION | SATAIR | 117 | 28123128 | NON-SPARES | 11 | 1 | RTN | D9550011700295 | IS0032071M | NON PRESENT INDUS | #N/A | #N/A |  |  |  | 0% | 0% | 0% | #N/A | #N/A | NA | #N/A | #N/A | #N/A | NA | NA | NA |  |  | 2019-10-11 |  | Sous-poste | Sous-poste | 2019-10-17 |  |  |  | Allemagne |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 |  |  |  | 0.205 | 3.815 | 0.95375 | 4.7687 | COL | 0 | 0
2824111210 | 2019-08-06 | FABRICATION | SATAIR | 441 | 28241112 | NON-SPARES | 10 | 1 | EXP | A95500441000AA | 0 | NON PRESENT INDUS | 27864 | 0 |  |  |  | 100% | 0% | 50% | 100% | 0 | 0% | 90% | 0 | 0% | NA | NA | 0% |  |  | 2019-09-03 |  | Sous-poste | Sous-poste | 2019-09-07 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | O | N |  |  | 8 | 2019 |  |  |  | 0.205 | 5.6471 | 1.4118 | 7.0589 | COL | 0 | 0
2830266910 | 2019-10-14 | FABRICATION | SATAIR | 429 | 28302669 | NON-SPARES | 10 | 3 | EXP | A9550042972695 | IS0032613M | NON PRESENT INDUS | 29478 | LTE990013 LTE990014 LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-09 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2019-10-28 |  | Sous-poste | Sous-poste | 2019-10-31 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | O | N |  |  | 10 | 2019 |  |  |  | 0 | 90.7476 | 7.5623 | 98.3099 | COL | 0 | 0
2820033310 | 2019-06-27 | FABRICATION | SATAIR | 409 | 28200333 | NON-SPARES | 10 | 0 | RTN | A9551040900195 | 0 | NON PRESENT INDUS | 26518 | 0 |  |  |  | 100% | 0% | 50% | 97% | 0 | NA | 97% | 0 | 0% | NA | NA | 0% |  |  | 2020-02-05 |  | Sous-poste | Sous-poste | 2020-02-11 |  |  |  | Allemagne | Attente RFQ HA | C |  | 1 | #VALUE! | O | N |  |  | 6 | 2019 |  |  |  | 0 | 0 | 0 | 0 | LAB | 0 | 0
2820033410 | 2019-06-27 | FABRICATION | SATAIR | 409 | 28200334 | NON-SPARES | 10 | 0 | RTN | A9551040900195 | 0 | NON PRESENT INDUS | 26518 | 0 |  |  |  | 100% | 0% | 50% | 97% | 0 | NA | 97% | 0 | 0% | NA | NA | 0% |  |  | 2020-04-03 |  | Sous-poste | Sous-poste | 2020-04-09 |  |  |  | Allemagne | Attente RFQ HA | C |  | 1 | #VALUE! | O | N |  |  | 6 | 2019 |  |  |  | 0 | 0 | 0 | 0 | LAB | 0 | 0
2836687610 | 2019-12-20 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28366876 | NON-SPARES | 10 | 2 | AOG | D9251805800000 | IS0032777S | NA | 31804 | 0 | NA | NA | NA | NA | NA | 100% | 100% | 2020-05-06 | NA | 0% | 2020-05-12 | 0% | NA | NA | 0% |  |  | 2019-12-19 |  | Sous-poste | Sous-poste | 2019-12-23 |  |  |  | Allemagne |  | C |  | 0 | #VALUE! | O | N |  |  | 12 | 2019 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2843533710 | 2020-03-06 | HA/REVENTE | SATAIR | PLACARD SET 500VU | 28435337 | NON-SPARES | 10 | 2 | EXP | D9251095600000 | IS0053509S | NA | 33842 | 0 | NA | NA | NA | NA | NA | 100% | 0% | 0 | NA | 0% | 0 | 0% | NA | NA | 0% |  |  | 2020-03-31 |  | Sous-poste | Sous-poste | 2020-04-03 |  |  |  | Allemagne | Impact T3S | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2842136810 | 2020-02-20 | FABRICATION | SATAIR | 22 | 28421368 | NON-SPARES | 10 | 1 | RTN | D9551002201195 | 0 | NON PRESENT INDUS | 33448 | LTE990007 |  |  |  | 100% | 0% | 50% | 0% | 0 | 0% | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-06-23 |  | Sous-poste | Sous-poste | 2020-06-26 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | O | N |  |  | 2 | 2020 |  |  |  | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2843350010 | 2020-03-06 | FABRICATION | SATAIR | 419 | 28433500 | NON-SPARES | 10 | 1 | CRIT | A95500419000AA | 0 | NON PRESENT INDUS | 33833 | LTE990004 |  |  |  | 100% | 0% | 50% | 90% | 0 | 0% | 81% | TBD | 0% | NA | NA | 0% |  |  | TBD |  | Sous-poste | Sous-poste |  |  |  |  | Allemagne |  | C |  | 0 | #VALUE! | O | N |  |  | 3 | 2020 |  |  |  | 0.36 | 7.347 | 1.8367 | 9.1837 | COL | 0 | 0
2811409210 | 2019-04-01 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28114092 | NON-SPARES | 10 | 8 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 23642 | 320729-1 => 320729-8 |  |  |  | 100% | 0% | 50% | 100% | 2019-08-30 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-01-28 |  | Sous-poste | Sous-poste | 2020-01-31 |  |  |  | Allemagne | Attente envoi derog + Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2019 |  |  |  | 0.0048 | 4.86 | 0.15188 | 5.0119 | COL | 0 | 0 | 36733
2837641010 | 2020-01-08 | FABRICATION | SATAIR | 426 | 28376410 | NON-SPARES | 10 | 1 | EXP | A95500426000AB | 0 | NON PRESENT INDUS | 32022 | LTE990003 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-18 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-02-04 |  | Sous-poste | Sous-poste | 2020-02-07 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 |  |  |  | 0.205 | 22.38 | 5.595 | 27.975 | COL | 0 | 0
2837641110 | 2020-01-08 | FABRICATION | SATAIR | 426 | 28376411 | NON-SPARES | 10 | 1 | EXP | A95500426000AB | 0 | NON PRESENT INDUS | 32022 | LTE990004 |  |  |  | 100% | 0% | 50% | 100% | 2020-07-18 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-02-04 |  | Sous-poste | Sous-poste | 2020-02-07 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 |  |  |  | 0.205 | 22.38 | 5.595 | 27.975 | COL | 0 | 0
490004049030 | 2020-02-12 | HA/REVENTE | STELIA | SUPPORT | 4900040490 | NON-SPARES | 30 | 2 | EXP | S9251083800000 | 1CMP*16129 | NA | 33188 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-02-20 |  | Sous-poste | Sous-poste | 2020-02-25 |  |  |  | Rochefort | Attente DP | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2839532510 | 2020-01-27 | FABRICATION | SATAIR | LEAD-BONDING | 28395325 | NON-SPARES | 10 | 3 | RTN | A9252282400400 | 0 | NON PRESENT INDUS | 32574 | 496777-1 => 496777-3 |  |  |  | 100% | 0% | 50% | 100% | 2020-04-17 | NA | 100% | TBD | 0% | NA | NA | 0% |  |  | 2020-04-22 |  | Sous-poste | Sous-poste | 2020-04-25 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2020 |  |  |  | 0 | 1.149 | 0.0383 | 1.1873 | NA | 0 | 0
2842869110 | 2020-02-28 | FABRICATION | SATAIR | 441 | 28428691 | NON-SPARES | 10 | 1 | EXP | A95500441000AA | 0 | NON PRESENT INDUS | 33721 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2020-03-28 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-03-09 |  | Sous-poste | Sous-poste | 2020-03-12 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0.205 | 5.6471 | 1.4118 | 7.0589 | COL | 0 | 0
2817791610 | 2019-06-05 | HA/REVENTE | SATAIR | STRUCTURE ASSY | 28177916 | NON-SPARES | 10 | 1 | CRIT | A9253171800100 | 1STR*01640 | NA | 25498 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2019-07-03 |  | Sous-poste | Sous-poste | 2019-07-05 |  |  |  | Allemagne | Attente AR | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2019 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2814871910 | 2019-05-07 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28148719 | NON-SPARES | 10 | 1 | EXP | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 24698 | 342258-1 |  |  |  | 100% | 0% | 50% | 100% | 2020-08-30 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2019-06-03 |  | Sous-poste | Sous-poste | 2019-06-06 |  |  |  | Allemagne | Attente envoi derog + Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0 | 4592
490004064810 | 2020-02-27 | HA/REVENTE | STELIA | SUPPORT 1020VC | 4900040648 | NON-SPARES | 10 | 3 | RTN | S9242302600000 | 1STR*11279 | NA | 35115 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-03-16 |  | Sous-poste | Sous-poste | 2020-03-19 |  |  |  | Rochefort |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
490004064710 | 2020-02-27 | HA/REVENTE | STELIA | SUPPORT | 4900040647 | NON-SPARES | 10 | 6 | RTN | S9242320300200 | 1STR*11280 | NA | 35115 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-03-16 |  | Sous-poste | Sous-poste | 2020-03-19 |  |  |  | Rochefort |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
490004075310 | 2020-03-10 | HA/REVENTE | STELIA | GOUPILLE | 4900040753 | NON-SPARES | 10 | 14 | RTN | S9251186120000 | 3STR*01339 | NA | 33918 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-04-29 |  | Sous-poste | Sous-poste | 2020-05-04 |  |  |  | Rochefort |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2802674810 | 2019-01-09 | FABRICATION | SATAIR | 429 | 28026748 | NON-SPARES | 10 | 1 | EXP | A9550042972695 | IS0032613M | NON PRESENT INDUS | 20734 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2019-10-30 | 33% | 93.3% | TBD | 0% | NA | NA | 0% |  |  | 2019-12-17 |  | Sous-poste | Sous-poste | 2019-12-20 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2019 |  |  |  | 0 | 30.2492 | 7.5623 | 37.8115 | COL | 0 | 0 | 11397
2845377110 | 2020-04-01 | HA/REVENTE | SATAIR | TUBE | 28453771 | NON-SPARES | 10 | 3 | RTN | F9251110800100 | 1STR*10656 | NA | 34349 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-06-23 |  | Sous-poste | Sous-poste | 2020-06-26 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2846331310 | 2020-04-23 | FABRICATION | AIS | SHEET FOMAX SHEET EQUIP | 28463313 | NON-SPARES | 10 | 1 | CRIT | F9252030900000 | IS0032162M | NON PRESENT INDUS | 34597 | 518638-1 |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-05-01 |  | Sous-poste | Sous-poste | 2020-05-05 |  |  |  | Allemagne |  | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 |  |  |  | 0 | 0.1 | 0.015 | 0.115 | NA | 0 | 0
2846303110 | 2020-04-22 | HA/REVENTE | SATAIR/AIS | PLATE ANGLE ASSY | 28463031 | NON-SPARES | 10 | 1 | RTN | F9251485400000 | 1STR*10825 | NA | 34577 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-08-12 |  | Sous-poste | Sous-poste | 2020-08-17 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2020 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2846961110 | 2020-05-14 | HA/REVENTE | SATAIR/AIS | PLATE ASSY | 28469611 | NON-SPARES | 10 | 1 | CRIT | F9252029300000 | 1STR*11290 | NA | 35093 | 0 | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% |  |  | 0% |  |  | 2020-05-19 |  | Sous-poste | Sous-poste | 2020-05-21 |  |  |  | Allemagne |  | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2020 |  |  |  | #VALUE! | #VALUE! | NA | #VALUE! | NA | 0 | 0
2847953210 | 2020-06-30 | FABRICATION | SATAIR | 510 | 28479532 | NON-SPARES | 10 | 1 | EXP | A9550051000296 | IS0031992M | NON PRESENT INDUS | 35607 | LTE990007 |  |  |  | 100% | 0% | 50% | 88% | TBD | 0% | 79.2% |  | 0% | NA | NA | 0% |  |  | 2020-07-27 |  | Sous-poste | Sous-poste | 2020-07-30 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 |  |  |  | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
2847953211 | 2020-06-30 | FABRICATION | SATAIR | 510 | 28479532 | NON-SPARES | 11 | 1 | EXP | A9550051000296 | IS0031992M | NON PRESENT INDUS | 35607 | LTE990008 |  |  |  | 100% | 0% | 50% | 88% | TBD | 0% | 79.2% |  | 0% | NA | NA | 0% |  |  | 2020-07-27 |  | Sous-poste | Sous-poste | 2020-07-30 |  |  |  | Allemagne |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2020 |  |  |  | 0 | 3.5517 | 0.88793 | 4.4396 | COL | 0 | 0
68486991 | 2019-11-13 | FABRICATION | AD&S | 15 | 6848699 | NON-SPARES | 1 | 1 | EXP | MB032ACAAAAB | IS0032193M | NON PRESENT INDUS | 30680 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2019-03-11 | 0% | 90% | TBD | 0% | NA | OUI | 0% |  |  | 2020-01-17 |  | Sous-poste | Sous-poste | 2020-01-22 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 11 | 2019 |  |  |  | 0.51 | 7.1148 | 1.7787 | 8.8935 | COL | 0 | 0
2815217810 | 2019-05-09 | FABRICATION | SATAIR | 426 | 28152178 | NON-SPARES | 10 | 1 | EXP | A95500426000AB | 0 | NON PRESENT INDUS | 24884 | LTE990001 |  |  |  | 100% | 0% | 50% | 100% | 2019-10-28 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-01-28 |  | Sous-poste | Sous-poste | 2020-01-31 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 |  |  |  | 0.205 | 22.38 | 5.595 | 27.975 | COL | 0 | 0
2816808210 | 2019-05-23 | FABRICATION | SATAIR | 432 | 28168082 | NON-SPARES | 10 | 1 | EXP | A95500432000AB | IS0031989M | NON PRESENT INDUS | 25891 | LTE990001 |  |  |  | 100% | 0% | 50% | 97% | 2020-02-06 | 0% | 87.3% | TBD | 0% | NA | NA | 0% |  |  | 2020-02-25 |  | Sous-poste | Sous-poste | 2020-02-28 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2019 |  |  |  | 0.36 | 18.8965 | 4.7241 | 23.6206 | COL | 0 | 0
2820520710 | 2019-07-02 | FABRICATION | SATAIR | 426 | 28205207 | NON-SPARES | 10 | 1 | EXP | A95500426000AB | 0 | NON PRESENT INDUS | 26446 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2019-12-18 | 0% | 90% | TBD | 0% | NA | NA | 0% |  |  | 2020-01-28 |  | Sous-poste | Sous-poste | 2020-01-31 |  |  |  | Allemagne | Attente confié | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2019 |  |  |  | 0.205 | 22.38 | 5.595 | 27.975 | COL | 0 | 0
68735431 | 2020-09-14 | FABRICATION | AD&S | 11 | 6873543 | NON-SPARES | 1 | 1 | CRIT | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 37054 |  |  |  |  | 100% | 0% | 50% | 100% | TBD | 0% | 90% | TBD | 0% | NA | OUI | 0% |  |  | 2021-03-18 |  | Sous-poste | Sous-poste | 2021-03-22 |  |  |  | Séville |  | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
2843030710 | 2020-02-28 | FABRICATION | SATAIR | BUNDLE | 28430307 | NON-SPARES | 10 | 1 | EXP | L9000095410095 | 0 | NON PRESENT INDUS | 34589 | 519051-1 |  |  |  | 100% | 0% | 50% | 82% | TBD | NA | 82% | TBD | 0% | NA | NA | 0% |  |  | 2021-12-02 |  | Sous-poste | Sous-poste | 2021-12-07 |  |  |  | Allemagne | Attente RFQ HA | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | COL | 0 | 0
2843030910 | 2020-02-28 | FABRICATION | SATAIR | BUNDLE | 28430309 | NON-SPARES | 10 | 1 | RTN | L9000095410095 | 0 | NON PRESENT INDUS | 34589 | 519054-1 |  |  |  | 100% | 0% | 50% | 82% | TBD | NA | 82% | TBD | 0% | NA | NA | 0% |  |  | 2021-12-22 |  | Sous-poste | Sous-poste | 2021-12-27 |  |  |  | Allemagne | Attente RFQ HA | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | COL | 0 | 0
2843031010 | 2020-02-28 | FABRICATION | SATAIR | BUNDLE | 28430310 | NON-SPARES | 10 | 1 | RTN | L9000095410095 | 0 | NON PRESENT INDUS | 34589 | 519057-1 |  |  |  | 100% | 0% | 50% | 82% | TBD | NA | 82% | TBD | 0% | NA | NA | 0% |  |  | 2021-12-22 |  | Sous-poste | Sous-poste | 2021-12-27 |  |  |  | Allemagne | Attente RFQ HA | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0 | 0 | 0 | 0 | COL | 0 | 0
2849839910 | 2020-09-21 | FABRICATION | SATAIR | 45 | 28498399 | NON-SPARES | 10 | 1 | RTN | D9551004500495 | 0 | NON PRESENT INDUS | 37174 |  |  |  |  | 100% | 0% | 50% | 88% | TBD | NA | 88% | TBD | 0% | NA | NA | 0% |  |  | 2020-11-19 |  | Sous-poste | Sous-poste | 2020-11-24 |  |  |  | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 |  |  |  | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
2849839911 | 2020-09-21 | FABRICATION | SATAIR | 45 | 28498399 | NON-SPARES | 11 | 1 | RTN | D9551004500495 | 0 | NON PRESENT INDUS | 37174 |  |  |  |  | 100% | 0% | 50% | 88% | TBD | NA | 88% | TBD | 0% | NA | NA | 0% |  |  | 2020-11-19 |  | Sous-poste | Sous-poste | 2020-11-24 | [5 empty] | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2020 |  |  |  | 0.205 | 13.1082 | 3.2771 | 16.3852 | COL | 0 | 0
2850315110 | 2020-10-07 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28503151 | NON-SPARES | 10 | 1 | EXP | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 37835 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA | 0% |  |  | 2020-11-03 |  | Sous-poste | Sous-poste | 2020-11-06 |  |  |  | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 10 | 2020 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
490004062710 | 2020-02-27 | FABRICATION | STELIA | CÂBLE | 4900040627 | NON-SPARES | 10 | 1 | RTN | S9291306500000 | IS0032228M | NON PRESENT INDUS | 33722 | 507390-1 |  |  |  | 100% | 0% | 50% | 100% | TBD | NA | 100% | TBD | 0% | NA | OUI | 0% |  |  | 2020-05-14 |  | Sous-poste | Sous-poste | 2020-05-19 |  |  |  | Rochefort | Action LSE pour retrouver stock autosoudeur en zone quarantaine | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2020 |  |  |  | 0.205 | 1 | 0.1 | 1.1 | NA | 0 | 0
Pré-Appro STE1 |  | FABRICATION | STE | 9205 | Pré-Appro STE | NON-SPARES | 1 | 10 | RTN | D925R445000000 | 0 | NON PRESENT INDUS | 34915 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | OUI | 0% |  |  |  |  | Sous-poste | Sous-poste | TBD | [5 empty] | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2857660310 | 2021-04-21 | FABRICATION | SATAIR | 511 | 28576603 | NON-SPARES | 10 | 5 | RTN | A9550051100295 | IS0060616M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-08-05 |  | Sous-poste | Sous-poste | 2021-08-11 |  |  |  | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 |  |  |  | 1.85 | 20.05 | 1.07 | 21.12 | COL | 0 | 0
2854069520 | 2021-03-18 | FABRICATION | SATAIR | 108 | 28540695 | NON-SPARES | 20 | 1 | AOG | D9550010801395 | IS0060338M | NON PRESENT INDUS | NA | LTE990001 |  |  |  | 0% | 0% | 0% | 100% | 2021-03-18 | NA | 100% | 2021-03-22 | 0% | NA | NA | 0% |  |  | TBD |  | Sous-poste | Sous-poste | TBD | [5 empty] | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 |  |  |  | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL | 0 | 0
2857183110 | 2021-04-14 | FABRICATION | SATAIR | 110 | 28571831 | NON-SPARES | 10 | 1 | AOG | A95500110000AA | IS0060587M | NON PRESENT INDUS | 43641 | LTE990001 |  |  |  | 100% | 0% | 50% | 68% | TBD | 0% | 61.2% | TBD | 0% | NA | NA | 0% |  |  | 2021-04-29 |  | Sous-poste | Sous-poste | 2021-05-03 |  |  |  | SPARES |  | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2021 |  |  |  | 1.525 | 34.83 | 9.4 | 44.23 | COL | 0 | 0
TBD | 2021-03-08 | HA/REVENTE | DES | PLATE | TBD | NON-SPARES |  | 5 |  | 128810319201 | IS0053339S | NA | 39184 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2021-05-03 | NA | 100% | NA | NA | NA | NA | NA |  |  |  |  | Sous-poste | Sous-poste | TBD | [5 empty] | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 3 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2860108611 | 2021-06-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28601086 | NON-SPARES | 11 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-09-01 |  | Sous-poste | Sous-poste | 2021-09-06 |  |  |  | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2860108612 | 2021-06-10 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28601086 | NON-SPARES | 12 | 1 | RTN | A27912401007C11 | IS0032635M | NON PRESENT INDUS | 44997 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-09-01 |  | Sous-poste | Sous-poste | 2021-09-06 |  |  |  | SPARES |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2021 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL | 0 | 0
2861712510 | 2021-07-13 | FABRICATION | SATAIR | BUNDLE | 28617125 | 163020 | 10 | 1 | CRIT | D9001095411495 | IS0061093M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-07-20 |  |  |  | 2021-07-22 |  |  |  | KIT FACTORY |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2861712510 | 2021-07-13 | FABRICATION | SATAIR | BUNDLE | 28617125 | 163020 | 10 | 1 | CRIT | D9001095411495 | IS0061093M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-07-20 |  |  |  | 2021-07-22 |  |  |  | KIT FACTORY |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2861712510 | 2021-07-13 | FABRICATION | SATAIR | BUNDLE | 28617125 | 163020 | 10 | 1 | CRIT | D9001095411495 | IS0061093M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | 0% |  |  | 2021-07-20 |  |  |  | 2021-07-22 |  |  |  | KIT FACTORY |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2862954310 | 2021-08-11 | FABRICATION | SATAIR | 27 | 28629543 | NON-SPARES | 10 | 2 | AOG | D9551002700595 | IS0032094M | NON PRESENT INDUS | 47014 | LTE990029 => LTE990030 |  |  |  | 100% | 0% | 50% |  |  | NA | 0% |  |  |  |  | 0% |  |  | TBD |  | Sous-poste | Sous-poste |  |  |  |  | SPARES |  | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 |  |  |  | 0.72 | 9.8346 | 1.2293 | 11.0639 | COL | 0 | 0
68714601 | 2020-08-19 | FABRICATION | AD&S | 34 | 6871460 | 150072 | 1 | 1 | RTN | MB136ABAAAAD | IS0032209M | NON PRESENT INDUS | 36612 |  |  |  |  | 100% | 0% | 50% | 100% | 2020-11-07 | 0% | 90% | TBD | 0% | NA | OUI | 0% |  |  | 2020-10-26 |  |  |  | 2020-10-29 |  |  |  | Séville |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 8 | 2020 |  |  |  | 0.205 | 3.2522 | 0.81305 | 4.0653 | COL | 0 | 0
2863708910 | 2021-08-24 |  | TBD |  | 28637089 | NON-SPARES | 10 | 18 | AOG | EN4165A20A221NA |  | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | 0% |  |  | TBD |  | Sous-poste | Sous-poste | [6 empty] | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2863709110 | 2021-08-24 |  | TBD |  | 28637091 | NON-SPARES | 10 | 18 | AOG | EN4165A20A221NB |  | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | 0% |  |  | TBD |  | Sous-poste | Sous-poste | [6 empty] | O |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 8 | 2021 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
68680821 | 2020-07-09 | FABRICATION | AD&S | 51 | 6868082 | 150448 | 1 | 1 | EXP | MB043ABAAAAB | IS0032575M | NON PRESENT INDUS | 36956 | LTE990002 |  |  |  | 100% | 0% | 50% | 100% | 2021-03-03 | 0% | 90% | TBD | 0% | NA | OUI | 0% |  |  | 2020-11-26 |  |  |  | 2020-12-01 |  |  |  | Séville | Bom non intégrée SAP - Attente paramétrage MRPC | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2020 |  |  |  | 0.205 | 3.3066 | 0.82665 | 4.1333 | COL | 0 | 0
68964071 | 2021-05-20 | FABRICATION | AD&S | 51 | 6896407 | 161659 | 1 | 1 | RTN | MB043ACAAAAD | IS0060760M | NON PRESENT INDUS | 45017 |  |  |  |  | 100% | 0% | 50% | 90% | TBD | 0% | 81% | TBD | 0% | NA | OUI | 0% |  |  | 2021-06-10 |  |  |  | 2021-06-15 |  |  |  | SEVILLE | Attente BDO | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2021 |  |  |  | 0.36 | 3.3 | 0 | 3.3 | COL | 0 | 0
68964072 | 2021-05-20 | FABRICATION | AD&S | 33 | 6896407 | 161659 | 2 | 1 | RTN | MB030AAAAAAA | IS0060759M | NON PRESENT INDUS | 44961 |  |  |  |  | 100% | 0% | 50% | 90% | TBD | 0% | 81% | TBD | 0% | NA | OUI | 0% |  |  | 2021-06-10 |  |  |  | 2021-06-15 |  |  |  | SEVILLE | Attente BDO | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2021 |  |  |  | 0.36 | 4.2 | 0.83 | 5.03 | COL | 0 | 0
69091251 | 2021-09-29 | FABRICATION | AD&S | 11 | 6909125 | 166359 | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 48478 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | OUI | 0% |  |  | 2021-10-06 |  |  |  | 2021-10-08 |  |  |  | SEVILLE |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 9 | 2021 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
69091241 | 2021-09-29 | FABRICATION | AD&S | 21 | 6909124 | 166510 | 1 | 1 | AOG | MB033ACAAAAB | IS0061439M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | OUI | 0% |  |  | 2021-10-06 |  |  |  | 2021-10-08 |  |  |  | SEVILLE |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 9 | 2021 |  |  |  | 0.36 | 2.1766 | 0.54415 | 2.7208 | COL | 0 | 0
2870039210 | 2021-12-08 | FABRICATION | SATAIR | PROTECTION CAP | 28700392 | 169728 | 10 | 25 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-04-18 | 0% | NA | NA | NA |  |  | 2022-04-29 |  |  |  | 2022-05-04 |  |  |  | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 12 | 2021 |  |  |  | 0.0625 | 2.795 | 0.01118 | 2.8062 | NA | 0 | 0
2870039310 | 2021-12-08 | FABRICATION | SATAIR | PROTECTION CAP | 28700393 | 169729 | 10 | 10 | RTN | F0003003000000 | IS0032144M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | 2022-05-09 | 0% | NA | NA | NA |  |  | 2022-05-19 |  |  |  | 2022-05-24 |  |  |  | KIT FACTORY |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 12 | 2021 |  |  |  | 0.025 | 1.118 | 0.01118 | 1.1292 | NA | 0 | 0
2873577510 | 2022-01-31 | FABRICATION | SATAIR | 313 | 28735775 | 171966 | 10 | 1 | AOG | WF406ABAAAAB | IS0032176M | NON PRESENT INDUS | 48842 |  |  |  |  | 100% | 0% | 50% | 100% | 2022-02-17 | 0% | 90% | TBD | 0% | NA | NA | NA |  |  | 2022-01-28 |  |  |  | 2022-02-01 |  |  |  | SPARES | RAS | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 1 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL | 0 | 0
68953951 | 2021-05-07 | FABRICATION | AD&S | 39 | 6895395 | 165049 | 1 | 1 | AOG | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 44158 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | NA | 100% | TBD | 0% | NA | OUI | NA |  |  | 2021-10-21 |  |  |  | 2021-10-24 |  |  |  | SEVILLE |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 5 | 2021 |  |  |  | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
69007341 | 2021-07-05 | FABRICATION | AD&S | 11 | 6900734 | 169509 | 1 | 1 | CRIT | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 45371 | LTE990008 |  |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | NA | 100% | TBD | 0% | NA | OUI | NA |  |  | 2022-03-17 |  |  |  | 2022-03-19 |  |  |  | SEVILLE |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2021 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
69102711 | 2021-10-11 | FABRICATION | AD&S | 11 | 6910271 | 166986 | 1 | 1 | EXP | MB031ADAEAAB | IS0032192M | NON PRESENT INDUS | 48842 | LTE990010 |  |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | NA | 100% | TBD | 0% | NA | OUI | NA |  |  | 2021-10-26 |  |  |  | 2021-10-29 |  |  |  | SEVILLE |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2021 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL | 0 | 0
69164121 | 2021-12-10 | FABRICATION | AD&S | 21 | 6916412 | 169805 | 1 | 1 | RTN | MB033ACAAAAB | IS0061439M | NON PRESENT INDUS |  | LTE990001 |  |  |  | 0% | 0% | 0% | 90% | TBD | 0% | 81% | TBD | 0% | NA | OUI | NA |  |  | 2022-02-14 |  |  |  | 2022-02-17 |  |  |  | SEVILLE | 2 articles statut 36 (mail envoyé à Tushar 15/04) | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 12 | 2021 |  |  |  | 0.36 | 2.1766 | 0.54415 | 2.7208 | COL | 0 | 0
68942301 | 2021-04-23 | FABRICATION | AD&S | 39 | 6894230 | 158834 | 1 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 43788 | LTE990014 |  |  |  | 100% | 0% | 50% | 100% | 2021-05-21 | 90% | 99% | TBD | 0% | NA | OUI | NA |  |  | 2021-12-30 |  |  |  | 2022-01-04 |  |  |  | SEVILLE |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 4 | 2021 |  |  |  | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
68888831 | 2021-03-03 | FABRICATION | AD&S | 39 | 6888883 | 155359 | 1 | 1 | RTN | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 42243 | LTE990013 |  |  |  | 100% | 0% | 50% | 100% | 2021-07-29 | 90% | 99% | TBD | 0% | NA | OUI | NA |  |  | 2021-11-25 |  |  |  | 2021-11-30 |  |  |  | SEVILLE |  | C |  | 1 | #VALUE! | #VALUE! | O |  |  | 3 | 2021 |  |  |  | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
2873287110 | 2022-01-26 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 301VU | 28732871 | 171635 | 10 | 1 | RTN | D9251805700000 | IS0032776S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | Stock | NA | 100% | NA | NA | NA | NA | NA |  |  | 2022-05-20 |  | 17.05.2022 | 80896718 | 2022-05-25 |  |  |  | KIT FACTORY |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2873287310 | 2022-01-26 | HA/REVENTE | SATAIR | PLATE ASSY FRONT 500VU | 28732873 | 171636 | 10 | 1 | RTN | D9251805800000 | IS0032777S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA |  |  | NA |  |  | 2022-05-20 |  | 17.05.2022 | 80896719 | 2022-05-25 |  |  |  | KIT FACTORY | Attente AR | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
69224041 | 2022-02-09 | FABRICATION | AD&S | 39 | 6922404 | 172556 | 1 | 1 | AOG | MB135ABAAAAC | IS0032207M | NON PRESENT INDUS | 44158 | LTE990015 |  |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | 0% | 90% | TBD | 0% | NA | OUI | NA |  |  | 2022-03-29 |  |  |  | 2022-03-31 |  |  |  | SEVILLE |  | C |  | 0 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.205 | 4.38 | 1.095 | 5.475 | COL | 0 | 0
2878959510 |  | FABRICATION | SATAIR | BUNDLE | 28789595 | 174852 | 10 | 1 | AOG | V9297404108695 | IS0060810M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 07/04/2022 | 80885108 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2878959610 |  | FABRICATION | SATAIR | BUNDLE | 28789596 | 174853 | 10 | 1 | AOG | V9297404002895 | IS0060809M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 07/04/2022 | 80885068 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2878959710 |  | FABRICATION | SATAIR | BUNDLE | 28789597 | 174854 | 10 | 1 | AOG | V9297400001095 | IS0061660M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 11/04/2022 | 80885826 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2879314110 |  | FABRICATION | SATAIR | BUNDLE | 28793141 | 175097 | 10 | 1 | AOG | V9297404002895 | IS0060809M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 12/04/2022 | 80886217 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2879314210 |  | FABRICATION | SATAIR | BUNDLE | 28793142 | 175098 | 10 | 1 | AOG | V9297404108695 | IS0060810M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 12/04/2022 | 80886218 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2879314310 |  | FABRICATION | SATAIR | BUNDLE | 28793143 | 175099 | 10 | 1 | AOG | V9297404108695 | IS0060810M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 12/04/2022 | 80886219 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2879314510 |  | FABRICATION | SATAIR | BUNDLE | 28793145 | 175100 | 10 | 1 | AOG | V9297404002895 | IS0060809M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 12/04/2022 | 80886220 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 6.211 | 3.07 | 9.281 | NA | 0 | 0
2879663110 |  | FABRICATION | SATAIR | BUNDLE | 28796631 | 175245 | 10 | 1 | AOG | V9297400001095 | IS0061660M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 14/04/2022 | 80887121 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2879865410 |  | FABRICATION | SATAIR | BUNDLE | 28798654 | 175470 | 10 | 1 | AOG | V9297400101295 | IS0061659M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  | TBD |  | 25/04/2022 | 80889867 | [6 empty] | O |  | 0 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
2880655110 |  | FABRICATION | SATAIR | BUNDLE | 28806551 | 175805 | 10 | 2 |  | V9297400001095 | IS0061660M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  |  |  | 09/05/2022 | 80893506 | [6 empty] | O |  | 1 | N | N | N | 5 | 2022 | 1 | 1900 |  |  |  | 0.87 | 5.92 | 2.155 | 8.075 | NA | 0 | 0
2880655010 |  | FABRICATION | SATAIR | BUNDLE | 28806550 | 175804 | 10 | 2 |  | V9297404002895 | IS0060809M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  |  |  | 09/05/2022 | 80893505 | [6 empty] | O |  | 1 | N | N | N | 5 | 2022 | 1 | 1900 |  |  |  | 0.87 | 12.422 | 3.07 | 15.492 | NA | 0 | 0
2880654910 |  | FABRICATION | SATAIR | BUNDLE | 28806549 | 175803 | 10 | 2 |  | V9297404108695 | IS0060810M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  |  |  | 09/05/2022 | 80893504 | [6 empty] | O |  | 1 | N | N | N | 5 | 2022 | 1 | 1900 |  |  |  | 0.87 | 12.422 | 3.07 | 15.492 | NA | 0 | 0
2879291910 |  | FABRICATION | SATAIR | BUNDLE | 28792919 | 175095 | 10 | 1 |  | V9297400001095 | IS0061660M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% |  |  | NA | 0% |  |  |  |  | NA |  |  |  |  | 25/04/2022 | 80890127 | [6 empty] | O |  | 1 | N | N | N | 4 | 2022 | 1 | 1900 |  |  |  | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
490004447710 | 2022-05-23 | HA/REVENTE | STELIA | PROTECTION | 4900044477 | 177205 | 10 | 2 | EXP | S9251047420000 | IS0060011S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% |  |  | NA |  |  | 2022-06-10 |  | 13.06.2022 | 80905185 | 2022-06-15 |  |  |  | ROCHEFORT |  | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2882461210 | 2022-05-24 |  | TBD |  | 28824612 | NON-SPARES | 10 | 1 | AOG | D9000095030795 |  | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | NA |  |  | 2022-05-27 |  | Sous-poste | Sous-poste | 2022-05-31 |  |  |  | SPARES |  | C |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
693724010 | 2022-07-12 | FABRICATION | AD&S | 15 | 6937240 | NON-SPARES | 10 | 1 | RTN | MB032ADAAAAB | IS0032194M | NON PRESENT INDUS | 48842 | LTE990003 |  |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | OUI | NA |  |  | 2022-12-05 |  | Sous-poste | Sous-poste | 2022-12-08 |  |  |  | SEVILLE |  | C |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 7 | 2022 |  |  |  | 0.51 | 7.1148 | 1.7787 | 8.8935 | COL | 0 | 0
2887346210 | 2022-08-04 | HA/REVENTE | SATAIR | BRACKET ASSY | 28873462 | 182146 | 10 | 4 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-03-17 | 2023-03-17 |  |  | 2023-03-22 | 2023-03-22 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 11 | 3 | 2023 | 0 | 0 | 0 | 0 | NA
2887346310 | 2022-08-04 | HA/REVENTE | SATAIR | BRACKET ASSY | 28873463 | 182147 | 10 | 4 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-03-17 | 2023-03-17 |  |  | 2023-03-22 | 2023-03-22 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 11 | 3 | 2023 | 0 | 0 | 0 | 0 | NA
2883744210 | 2022-06-16 | FABRICATION | SATAIR | 117 | 28837442 | 178352 | 10 | 1 | RTN | D9550011700295 | IS0032071M | Terminé | 48842 | LTE990172 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-05-12 | NA | 100% | 2023-06-19 | 0% | NA | NA |  |  | 0 | 2022-12-19 | 2023-04-27 |  |  | 2022-12-22 | 2023-05-02 |  |  | KIT FACTORY | MECAHERS/T3S 28-11 / Réception SATAIR IS0032555S 12/05/2023 / AR SATAIR IS0032554Sle 20/12/2022 |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 6 | 2022 | 17 | 4 | 2023 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL
2889290410 | 2022-09-06 | HA/REVENTE | SATAIR | PLACARD SET | 28892904 | 183350 | 10 | 14 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-03-24 | 2023-03-24 |  |  | 2023-03-29 | 2023-03-29 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 12 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2889294110 | 2022-09-06 | HA/REVENTE | SATAIR | PLACARD SET | 28892941 | 183351 | 10 | 1 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-03-27 | 2023-03-24 |  |  | 2023-03-30 | 2023-03-29 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 12 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2887348310 | 2022-08-04 | HA/REVENTE | SATAIR | PLACARD SET | 28873483 | 182149 | 10 | 16 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-03-30 | 2023-03-30 |  |  | 2023-04-04 | 2023-04-04 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 13 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2887663310 | 2022-08-10 | HA/REVENTE | SATAIR | PLACARD SET | 28876633 | 183220 | 10 | 16 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-03-30 | 2023-03-30 |  |  | 2023-04-04 | 2023-04-04 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 13 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2887663710 | 2022-08-10 | HA/REVENTE | SATAIR | PLACARD SET | 28876637 | 183222 | 10 | 200 | RTN | V1132035500095A | IS0059842S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-04-05 | 2023-03-30 |  |  | 2023-04-10 | 2023-04-04 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 13 | 3 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2887663510 | 2022-08-10 | HA/REVENTE | SATAIR | PLACARD SET | 28876635 | 183221 | 10 | 200 | RTN | V1132035600095A | IS0059841S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA |  |  |  | 2023-04-21 | 2023-04-12 |  |  | 2023-04-26 | 2023-04-17 |  | OK | KIT FACTORY | Cmde à placer début 2023 | Stand-By |  | 1 | #VALUE! | #VALUE! | N |  |  | 8 | 2022 | 15 | 4 | 2023 | 0 | 0 | 0 | 0 | NA | 0 | 0
2883744210_1 | 2022-06-16 | FABRICATION | SATAIR | 117 | 28837442 | NON-SPARES | 10_1 | 1 | RTN | D9550011700295 | IS0032071M | Terminé | 48842 | LTE990173 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-05-12 | NA | 100% | 2023-06-19 | 0% | NA | NA |  |  |  | 2022-12-19 | 2023-04-27 | Sous-poste | Sous-poste | 2022-12-22 | 2023-05-02 |  |  | KIT FACTORY | MECAHERS/T3S 28-11 / Réception SATAIR IS0032555S 12/05/2023 (AR sur le mauvais poste) / Attente AR SATAIR IS0032554S (dde si alternate ok auprès d'AIB) |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 6 | 2022 | 17 | 4 | 2023 | 0.205 | 3.815 | 0.95375 | 4.7687 | COL
2890155310 | 2022-09-23 | HA/REVENTE | SATAIR | GUTTER ASSY | 28901553 | 184207 | 10 | 3 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-06-06 | 2023-06-06 |  |  | 2023-06-09 | 2023-06-09 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 23 | 6 | 2023 | 0 | 0 | 0 | 0 | NA
2890155410 | 2022-09-23 | HA/REVENTE | SATAIR | BRACKET ASSY | 28901554 | 184208 | 10 | 6 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-06-06 | 2023-06-06 |  |  | 2023-06-09 | 2023-06-09 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 23 | 6 | 2023 | 0 | 0 | 0 | 0 | NA
2890155510 | 2022-09-23 | HA/REVENTE | SATAIR | BRACKET ASSY | 28901555 | 184209 | 10 | 6 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 100% | 2023-01-20 | NA | 100% | NA | NA | NA | NA |  |  |  | 2023-06-06 | 2023-06-06 |  |  | 2023-06-09 | 2023-06-09 |  | OK | KIT FACTORY | Chiffrage en cours LBG - À relancer le 13/10 si pas d'offre |  |  | 1 | #VALUE! | #VALUE! | N |  |  | 9 | 2022 | 23 | 6 | 2023 | 0 | 0 | 0 | 0 | NA
68141141 | 2018-10-25 | FABRICATION | AD&S | 12 | 6814114 | 111164 | 1 | 1 | EXP | MB170ACAAAAA | IS0032211M | Terminé | 18554 | LTE990004 | 0 |  |  | 100% | 0% | 50% | 100% | 2019-09-20 | 90% | 99% | TBD | 0% | NA | OUI |  |  |  | 2022-06-27 |  |  |  | 2022-06-30 |  |  |  | SEVILLE |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2018 |  |  |  | 0.205 | 8.3333 | 2.0833 | 10.4166 | COL
68936653 | 2021-04-26 | FABRICATION | AD&S | 61 | 6893665 | 159107 | 3 | 1 | AOG | MB259ADABAAC | IS0060618M | Terminé | 46111 | LTE990003 | 0 |  |  | 100% | 0% | 50% | 100% | 2021-10-27 | 80% | 98% | TBD | 0% | NA | OUI |  |  |  | 2021-11-26 |  |  |  | 2021-11-30 |  |  |  | SEVILLE | Attente plan EQUI demandé à AIB - Template ok avec plan EQUI/MECA Casse IS0056896S (Cmde à placer par AKA) + Attente ETEC |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 4 | 2021 |  |  |  | 0 | 1.54 | 0.4 | 1.94 | COL
69034361 | 2021-07-22 | FABRICATION | AD&S | 11 | 6903436 | 163366 | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | Terminé | 45371 | LTE990009 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | 0% | 90% | TBD | 0% | NA | OUI |  |  |  | 2021-12-16 |  |  |  | 2021-12-20 |  |  |  | SEVILLE |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2021 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
2870776010 | 2021-12-14 | FABRICATION | SATAIR | 108 | 28707760 | 170132 | 10 | 1 | RTN | D9550010800996 | IS0032069M | Terminé | 48842 | LTE990021 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-01-28 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-02 |  |  |  | 2022-03-06 |  |  |  | SPARES | DI MRPC pour rendre confié achetable IS0035674S |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 12 | 2021 |  |  |  | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL
2870776020 | 2021-12-14 | FABRICATION | SATAIR | 108 | 28707760 | 170132 | 20 | 1 | RTN | D9550010800996 | IS0032069M | Terminé | 48842 | LTE990022 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-01-28 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-02 |  |  |  | 2022-03-06 |  |  |  | SPARES | DI MRPC pour rendre confié achetable IS0035674S |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 12 | 2021 |  |  |  | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL
69201431 | 2022-01-20 | FABRICATION | AD&S | 11 | 6920143 | NON-SPARES | 1 | 1 | AOG | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990014 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-01-26 | 95% | 99.5% | TBD | 0% | NA | OUI |  |  |  | 2023-02-01 |  | Sous-poste | Sous-poste | 2023-02-03 |  |  |  | SEVILLE |  |  |  | 0 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 2022 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
2874319210 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28743192 | 172404 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990009 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  |  |  | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2874319211 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28743192 | NON-SPARES | 11 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990010 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  | Sous-poste | Sous-poste | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890425610 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28904256 | 184452 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990011 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  |  |  | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890425710 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28904257 | 184453 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990012 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  |  |  | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890425810 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28904258 | 184454 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990013 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  |  |  | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890425910 | 2022-02-10 | FABRICATION | SATAIR | 313 | 28904259 | 184455 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990014 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-03-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-03-24 |  |  |  | 2022-03-29 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 2 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2877628810 | 2022-03-21 | FABRICATION | SATAIR | 110 | 28776288 | 174109 | 10 | 1 | AOG | D9550011000295 | IS0062642M | Terminé | 48842 | LTE990001 | 6030408 | 0 | 0 | 100% | 100% | 100% | 100% | 2022-04-12 | 0% | 90% | 2022-04-04 | 90% | NA | NA |  | 22/06 : manquant | 2022-10-21 | 2022-03-29 |  |  |  | 2022-03-31 |  |  |  | SPARES | Attente confiés |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 3 | 2022 |  |  |  | 0.24 | 2.56 | 0.99 | 3.55 | NA
2880240210 | 2022-04-21 | FABRICATION | SATAIR | 108 | 28802402 | 175654 | 10 | 1 | RTN | D9550010800996 | IS0032069M | Terminé | 48842 | LTE990023 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-06-28 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2022-06-09 |  |  |  | 2022-06-14 |  |  |  | SPARES | Confiés à demander au client |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 4 | 2022 |  |  |  | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL
2880240220 | 2022-04-21 | FABRICATION | SATAIR | 108 | 28802402 | 175654 | 20 | 1 | RTN | D9550010800996 | IS0032069M | Terminé | 48842 | LTE990024 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-06-28 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2022-06-09 |  |  |  | 2022-06-14 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 4 | 2022 |  |  |  | 0.36 | 7.9819 | 1.9955 | 9.9774 | COL
2881858410 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | 176808 | 10 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  |  |  | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2881858410_1 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | NON-SPARES | 10_1 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  | Sous-poste | Sous-poste | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2881858410_2 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | NON-SPARES | 10_2 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  | Sous-poste | Sous-poste | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2881858410_3 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | NON-SPARES | 10_3 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  | Sous-poste | Sous-poste | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2881858410_4 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | NON-SPARES | 10_4 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  | Sous-poste | Sous-poste | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2881858410_5 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28818584 | NON-SPARES | 10_5 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  | Sous-poste | Sous-poste | 2022-07-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2890430310 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28904303 | 184458 | 10 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  |  |  | 2022-07-25 |  |  |  | SPARES | Attente expédition IS0053035S pour STT ROSSI AERO |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2890429910 | 2022-05-13 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28904299 | 184457 | 10 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA |  |  |  | 2022-07-20 |  |  |  | 2022-07-25 |  |  |  | SPARES | Attente expédition IS0053035S pour STT ROSSI AERO |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2882346110 | 2022-05-21 | FABRICATION | SATAIR | 517 | 28823461 | 177021 | 10 | 1 | RTN | WF417AFACAAE | IS0032184M | Non commencé | 48842 | LTE990007 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-15 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2022-06-09 |  |  |  | 2022-06-14 |  |  |  | SPARES | AR MECAHERS 15/09 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL
2882346120 | 2022-05-21 | FABRICATION | SATAIR | 517 | 28823461 | 177021 | 20 | 1 | RTN | WF417AFACAAE | IS0032184M | Non commencé | 48842 | LTE990008 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-15 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2022-06-09 |  |  |  | 2022-06-14 |  |  |  | SPARES | AR MECAHERS 15/09 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL
69328361 | 2022-05-26 | FABRICATION | AD&S | 11 | 6932836 | 178062 | 1 | 1 | CRIT | MB031ADAEAAB | IS0032192M | Terminé | 48842 | LTE990019 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-06-28 | 0% | 90% | TBD | 0% | NA | OUI |  |  |  | 2022-06-28 |  |  |  | 2022-06-30 |  |  |  | SEVILLE |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 5 | 2022 |  |  |  | 0.205 | 8.0513 | 2.0128 | 10.0641 | COL
69344341 | 2022-06-13 | FABRICATION | AD&S | 42 | 6934434 | 178437 | 1 | 1 | CRIT | MB038ADAAAAB | IS0032200M | Non commencé |  |  | 0 |  |  | 0% | 0% | 0% | 0% | TBD | 0% | 0% | TBD | 0% | NA | OUI |  |  |  | 2022-06-28 |  |  |  | 2022-06-30 |  |  |  | SEVILLE |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 6 | 2022 |  |  |  | 0.205 | 1.5116 | 0.3779 | 1.8895 | COL
2884110810 | 2022-06-22 | FABRICATION | SATAIR | 400 | 28841108 | 178463 | 10 | 1 | AOG | A95500400000AA | IS0063213M | Non commencé | 58464 | LTE990001 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | OUI | NA |  |  |  | 2022-06-29 |  |  |  | 2022-07-01 |  |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 6 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2885017010 | 2022-07-05 | FABRICATION | SATAIR | 517 | 28850170 | 179234 | 10 | 1 | RTN | WF417AFACAAE | IS0032184M | Non commencé | 48842 | LTE990009 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-09-15 | NA | 100% | TBD | 0% | NA | NA |  |  |  | 2022-07-27 |  |  |  | 2022-07-30 |  |  |  | SPARES | AR MECAHERS 15/09 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL
2890427610 | 2022-07-05 | FABRICATION | SATAIR | 517 | 28904276 | 184456 | 10 | 1 | RTN | WF417AFACAAE | IS0032184M | Terminé | 48842 | LTE990010 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-10-03 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-11-25 |  |  |  | 2022-11-30 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 1.7325 | 0.43312 | 2.1656 | COL
2885522410 | 2022-07-08 | FABRICATION | SATAIR | JACK | 28855224 | 179586 | 10 | 1 | RTN | B23521038000D00 | IS0063322M | Non commencé | 48842 | LTE990001 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | OUI | NA |  |  |  | 2022-10-03 |  |  |  | 2022-10-06 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 2.1686 | 0.54215 | 2.7107 | COL
450119751110 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 10 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140051 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Manquants LUS IS0002551S/IS0002552S/IS0053339S/IS0056744S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751110_1 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 10_1 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140052 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751110_2 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 10_2 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140053 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751110_3 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 10_3 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140054 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751110_4 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 10_4 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140055 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751120 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 20 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140056 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751120_1 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 20_1 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140057 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751120_2 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 20_2 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140058 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751120_3 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 20_3 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140059 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450119751120_4 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501197511 | NON-SPARES | 20_4 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 52677 | 71140060 | 0 |  |  | 100% | 0% | 50% | 99% | TBD | NA | 99% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | Attente coverage en norme militaire IS0012505S |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
2885016910 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28850169 | 179321 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990007 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-28 |  |  |  | 2022-10-03 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889982710 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899827 | 183979 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990008 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-28 |  |  |  | 2022-10-03 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889982910 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899829 | 183980 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990009 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-28 |  |  |  | 2022-10-03 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889983010 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899830 | 183981 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990010 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-28 |  |  |  | 2022-10-03 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2885256510 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28852565 | 179322 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990011 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-29 |  |  |  | 2022-10-04 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889983210 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899832 | 183982 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990012 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-29 |  |  |  | 2022-10-04 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889983310 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899833 | 183983 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990013 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-29 |  |  |  | 2022-10-04 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2889983410 | 2022-07-05 | FABRICATION | SATAIR | 313 | 28899834 | 183984 | 10 | 1 | RTN | WF406ACAAAAB | IS0032177M | Terminé | 48842 | LTE990014 | 0 |  |  | 100% | 0% | 50% | 100% | 2023-01-16 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-09-29 |  |  |  | 2022-10-04 |  |  |  | SPARES | IS0007019S & IS0007003S articles SAFRAN livraison 16/01/2023 |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0.205 | 3.5 | 0.875 | 4.375 | COL
2886705410 | 2022-07-26 | FABRICATION | SATAIR | 406 | 28867054 | 181699 | 10 | 1 | AOG | A95500406000AA | IS0063330M | Non commencé |  | LTE990001 | 0 |  |  | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-08-16 |  |  |  | 2022-08-18 |  |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | COL
45011991941 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501199194 | NON-SPARES | 1 | 2 |  | 1288L4000010B | IS0033483M | Non commencé |  | 71140030 (RETROFIT) | 0 |  |  | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-09-15 |  | Sous-poste | Sous-poste | 2022-09-20 |  |  |  |  | RETROFIT indice B |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
2880645310 | 2022-04-27 | HA/REVENTE | SATAIR | PLATE ASSY-CLOSING | 28806453 | 175833 | 10 | 1 | RTN | F9251338800000 | IS0041081S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-08-29 | 2022-10-06 | 05.10.2022 | 80940549 | 2022-09-01 | 2022-10-11 |  | OK | KIT FACTORY | Article statut 07 en 2000 - Demander la duplication en 2010 - Créer DI MRPC | O |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 4 | 2022 | 41 | 10 | 2022 | 0 | 0 | 0 | 0 | NA | 0 | 0
450121072120 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501210721 | NON-SPARES | 20 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 59372 | 71140061 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2023-01-11 |  | Sous-poste | Sous-poste | 2023-01-15 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121072120_1 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501210721 | NON-SPARES | 20_1 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 59372 | 71140062 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2023-01-11 |  | Sous-poste | Sous-poste | 2023-01-15 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121072120_2 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501210721 | NON-SPARES | 20_2 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 59372 | 71140063 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2023-01-11 |  | Sous-poste | Sous-poste | 2023-01-15 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121072120_3 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501210721 | NON-SPARES | 20_3 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 59372 | 71140064 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2023-01-11 |  | Sous-poste | Sous-poste | 2023-01-15 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121072120_4 |  | FABRICATION | LATECOERE | FDVESS L4 | 4501210721 | NON-SPARES | 20_4 | 1 |  | 1288L4000010B | IS0033483M | Terminé | 59372 | 71140065 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2023-01-11 |  | Sous-poste | Sous-poste | 2023-01-15 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121601110 |  | FABRICATION | LATECOERE | FDVESS-L3 | 4501216011 | NON-SPARES | 10 | 1 |  | 1288L3000010 | IS0033482M | Terminé | 59373 | 71130016 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-10-31 |  | Sous-poste | Sous-poste | 2022-11-03 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121601110_1 |  | FABRICATION | LATECOERE | FDVESS-L3 | 4501216011 | NON-SPARES | 10_1 | 1 |  | 1288L3000010 | IS0033482M | Terminé | 59373 | 71130017 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-10-31 |  | Sous-poste | Sous-poste | 2022-11-03 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121601110_2 |  | FABRICATION | LATECOERE | FDVESS-L3 | 4501216011 | NON-SPARES | 10_2 | 1 |  | 1288L3000010 | IS0033482M | Terminé | 59373 | 71130018 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-10-31 |  | Sous-poste | Sous-poste | 2022-11-03 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121601110_3 |  | FABRICATION | LATECOERE | FDVESS-L3 | 4501216011 | NON-SPARES | 10_3 | 1 |  | 1288L3000010 | IS0033482M | Terminé | 59373 | 71130019 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-10-31 |  | Sous-poste | Sous-poste | 2022-11-03 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
450121601110_4 |  | FABRICATION | LATECOERE | FDVESS-L3 | 4501216011 | NON-SPARES | 10_4 | 1 |  | 1288L3000010 | IS0033482M | Terminé | 59373 | 71130020 | 0 |  |  | 100% | 0% | 50% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA |  |  |  | 2022-10-31 |  | Sous-poste | Sous-poste | 2022-11-03 | [7 empty] | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL
2890225410 | 2022-09-28 | HA/REVENTE | SATAIR | FLANGE ASSY | 28902254 | 184419 | 10 | 5 | RTN | D9251127600000 | IS0008826S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 100% | TBD | NA | 100% | NA | NA | NA | NA |  |  |  | 2022-12-21 |  |  |  | 2022-12-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 9 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2889076210 | 2022-09-01 | FABRICATION | SATAIR | 313 | 28890762 | 183285 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990015 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-10-12 | 0% | 90% | TBD | 0% | NA | NA |  |  |  | 2022-11-25 |  |  |  | 2022-11-30 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 9 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890442410 | 2022-09-29 | FABRICATION | SATAIR | 313 | 28904424 | 184459 | 10 | 1 | RTN | WF406ABAAAAB | IS0032176M | Terminé | 48842 | LTE990016 | 0 |  |  | 100% | 0% | 50% | 100% | TBD | 0% | 90% | TBD | 0% | NA | NA |  | 0% | 0 | 2022-12-23 |  |  |  | 2022-12-28 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 9 | 2022 |  |  |  | 0.51 | 3.85 | 0.9625 | 4.8125 | COL
2890429910 | 2022-09-29 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28904299 | 184457 | 10 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA |  |  |  | 2022-11-22 |  |  |  | 2022-11-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 9 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
2890430310 | 2022-09-29 | FABRICATION | SATAIR | CONTROL UNIT-HP FUEL | 28904303 | 184458 | 10 | 1 | RTN | A27912401007C11 | IS0032635M | Non commencé | 48842 |  | 0 |  |  | 100% | 0% | 50% | 0% | TBD | 0% | 0% | TBD | 0% | NA | NA |  |  |  | 2022-11-22 |  |  |  | 2022-11-25 |  |  |  | SPARES |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 9 | 2022 |  |  |  | 0.0006 | 0.6075 | 0.15188 | 0.75938 | COL
69455441 | 2022-09-27 | FABRICATION | AD&S | 15 | 6945544 | NON-SPARES | 1 | 1 | RTN | MB032ADAAAAB | IS0032194M | Terminé | 48842 | LTE990004 | 0 |  |  | 100% | 0% | 50% | 100% | 2022-11-29 | 0% | 90% | TBD | 0% | NA | OUI |  | 0% | 0 | 2022-11-02 |  | Sous-poste | Sous-poste | 2022-11-07 |  |  |  | SEVILLE | AR SAFRAN 29/11 (IS0006679S) |  |  | 1 | #VALUE! | #VALUE! | N | #VALUE! | #VALUE! | 9 | 2022 |  |  |  | 0.51 | 7.1148 | 1.7787 | 8.8935 | COL
2890678510 | 2022-07-06 | HA/REVENTE | SATAIR | GUTTER ASSY | 28906785 | 184772 | 10 | 4 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-12-14 |  |  |  | 2022-12-19 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890678610 | 2022-07-06 | HA/REVENTE | SATAIR | GUTTER ASSY | 28906786 | 184773 | 10 | 2 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-12-15 |  |  |  | 2022-12-20 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890678710 | 2022-07-06 | HA/REVENTE | SATAIR | GUTTER ASSY | 28906787 | 184774 | 10 | 6 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-01-27 |  |  |  | 2023-02-01 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890680710 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28906807 | 184775 | 10 | 6 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-12-15 |  |  |  | 2022-12-20 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890681010 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28906810 | 184776 | 10 | 6 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-12-15 |  |  |  | 2022-12-20 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890681110 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28906811 | 184777 | 10 | 8 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-12-15 |  |  |  | 2022-12-20 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890681210 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28906812 | 184778 | 10 | 4 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-01-27 |  |  |  | 2023-02-01 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890764410 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28907644 | 184814 | 10 | 30 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-02-01 |  |  |  | 2023-02-06 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
2890764510 | 2022-07-06 | HA/REVENTE | SATAIR | BRACKET ASSY | 28907645 | 184815 | 10 | 30 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-02-01 |  |  |  | 2023-02-06 |  |  |  | KIT FACTORY | Pas de besoin SAP (mail envoyé ADV) |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 7 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA
|  | FABRICATION | LATECOERE | FDVESS L4 |  |  |  | 1 |  | 1288L4000010B | IS0033483M | NON PRESENT INDUS |  | 71140050 (RETROFIT) |  |  |  | 0% | 0% | 0% | 100% | 2022-10-14 | NA | 100% | 2022-10-17 | 0% | NA | NA | NA |  |  | 2022-10-18 |  |  |  | 2022-10-21 | [7 empty] | 1 | #VALUE! | #VALUE! | O |  |  | 1 | 1900 |  |  |  | 0 | 0 | 0 | 0 | COL | 0 | 0
2891308310 | 2022-10-12 | HA/REVENTE | SATAIR | BRACKET ASSY | 28913083 | 184958 | 10 | 6 | RTN | V9251162200000 | IS0057853S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-07 |  |  |  | 2022-07-12 |  |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2891308510 | 2022-10-12 | HA/REVENTE | SATAIR | BRACKET ASSY | 28913085 | 184959 | 10 | 6 | RTN | V9251162600000 | IS0057855S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-07 |  |  |  | 2022-07-12 |  |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2891308610 | 2022-10-12 | HA/REVENTE | SATAIR | GUTTER ASSY | 28913086 | 184960 | 10 | 6 | RTN | V9251162300000 | IS0057854S | NA | 48843 | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2022-07-07 |  |  |  | 2022-07-12 |  |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2891874310 | 2022-10-20 | FABRICATION | SATAIR | 22 | 28918743 | 185326 | 10 | 1 | RTN | D9551002201195 | IS0032080M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | NA |  |  | 2023-01-02 |  |  |  | 2023-01-05 |  |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2891936910 | 2022-10-21 | FABRICATION | SATAIR | 22 | 28919369 | 185364 | 10 | 1 | RTN | D9551002201195 | IS0032080M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | NA |  |  | 2023-01-02 |  |  |  | 2023-01-05 |  |  |  | KIT FACTORY |  |  |  | 1 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0.205 | 10.5369 | 2.6342 | 13.1711 | COL | 0 | 0
2891993110 | 2022-10-24 | HA/REVENTE | SATAIR | VOYANT | 28919931 | 185406 | 10 | 1 | AOG | NSA933677F224 | IS0061411S | NA |  | NA | NA | NA | NA | NA | NA | 100% | 0% | TBD | NA | 0% | NA | NA | NA | NA | NA |  |  | 2023-08-17 |  |  |  | 2023-08-20 |  |  |  | SPARES |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0 | 0 | 0 | 0 | NA | 0 | 0
2891981210 | 2022-10-24 | FABRICATION | SATAIR | BUNDLE | 28919812 | 185409 | 10 | 1 | AOG | V9297400101295 | IS0061659M | NON PRESENT INDUS | [5 empty] | 0% | 0% | 0% | 0% | TBD | NA | 0% | TBD | 0% | NA | NA | NA |  |  | 2022-10-25 |  |  |  | 2022-10-27 |  |  |  | KIT FACTORY |  |  |  | 0 | #VALUE! | #VALUE! | O |  |  | 10 | 2022 |  |  |  | 0.435 | 2.96 | 2.155 | 5.115 | NA | 0 | 0
Formulas:
CHARGE = IFERROR(WEEKNUM(Tableau3[[#This Row],[Reforecasted shipment]]),"")
PROGRAMME = IFERROR(VLOOKUP(Tableau3[[#This Row],[CONCAT]],'[3]RECHANGES Satair-Stelia'!$A4:U200,16,FALSE),"")

## Confiés
CONCAT | PO number | Item | PN | Qty 1 | CMS 1 | PN 1 | Qty 2 | CMS 2 | PN 2 | Qty 3 | CMS 3 | PN 3 | Qty 4 | CMS 4 | PN 4 | Qty 5 | CMS 5 | PN 5 | Qté 6 | CMS 6 | PN 6 | Qté 7 | CMS 7 | PN 7 | Qté 8 | CMS 8 | PN 8 | Comments | État Confiés | État Commandes
2772277910 | 27722779 | 10 | D9551002201595 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
27737148 2774173710 | 27737148 27741737 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
490003478310 | 4900034783 | 10 | S9251279900057 | 1 | 6839605200 | 097-033-00 | [20 empty] | IEC Electronique |  | 100%
2709509810 | 27095098 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2708435310 | 27084353 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2759972310 | 27599723 | 10 | A95500423000AA | 1 | 6574926600 | A31111938A00 | [20 empty] | Paulstra |  | 100%
2740510210 | 27405102 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740515910 | 27405159 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740519810 | 27405198 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740525210 | 27405252 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740527810 | 27405278 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740530310 | 27405303 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740532210 | 27405322 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740537610 | 27405376 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740540910 | 27405409 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740542010 | 27405420 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2740543410 | 27405434 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364210 | 27423642 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364310 | 27423643 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364410 | 27423644 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364610 | 27423646 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364710 | 27423647 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364810 | 27423648 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742364910 | 27423649 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365010 | 27423650 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365310 | 27423653 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365510 | 27423655 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365610 | 27423656 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365710 | 27423657 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742365910 | 27423659 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366010 | 27423660 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366110 | 27423661 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366210 | 27423662 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366310 | 27423663 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366410 | 27423664 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366510 | 27423665 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366610 | 27423666 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366710 | 27423667 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2742366810 | 27423668 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [17 empty] | Sirio Panel |  | 100%
2752903910 | 27529039 | 10 | D9551002200895 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2753000710 | 27530007 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753000610 | 27530006 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753013610 | 27530136 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753012610 | 27530126 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753010310 | 27530103 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753012110 | 27530121 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753012310 | 27530123 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753000810 | 27530008 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753001610 | 27530016 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753012510 | 27530125 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753011210 | 27530112 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753013010 | 27530130 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753011610 | 27530116 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753012810 | 27530128 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753011010 | 27530110 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753013810 | 27530138 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753011910 | 27530119 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753013410 | 27530134 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753000910 | 27530009 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753011310 | 27530113 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753009810 | 27530098 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2755347710 | 27553477 | 10 | D9551002201495 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2761893910 | 27618939 | 10 | D9551004100195 | 3 | 6939600700 | 058-014-00 | [22 empty] | 100%
2761048310 | 27610483 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761048410 | 27610484 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761048510 | 27610485 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761048610 | 27610486 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761048810 | 27610488 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761048910 | 27610489 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2761049010 | 27610490 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2763437310 | 27634373 | 10 | D9550010802895 | 1 | 6963469200 | 723-1051-02 | [22 empty] | 100%
2764897110 | 27648971 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899210 | 27648992 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899310 | 27648993 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899410 | 27648994 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899510 | 27648995 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899610 | 27648996 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899710 | 27648997 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2764899810 | 27648998 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2753000010 | 27530000 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2753000110 | 27530001 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2753000210 | 27530002 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2753000310 | 27530003 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2753000410 | 27530004 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2753000510 | 27530005 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2761048110 | 27610481 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2766302210 | 27663022 | 10 | A9550051000196 | 1 | 6530207600 | A31112112B00 | [20 empty] | Paulstra |  | 100%
2766568110 | 27665681 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
E8791708L10 | E8791708L | 10 | MB136ABAAAAC | 1 | 6M90079100 | [23 empty] | 100%
E8789829L10 | E8789829L | 10 | MB170ACAAAAA | 1 | 6M90005100 | 360-001 | 1 | 6M90005200 | 33-455 | 1 | 6M90005300 | 27-457 | 1 | 6M90079400 | 723-6212-01 | [13 empty] | 100%
2772073510 | 27720735 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
490003509510 | 4900035095 | 10 | S9251279900051 | 1 | 6808101600 | 2136-315-8011 | [22 empty] | 100%
2770215110 | 27702151 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2777079910 | 27770799 | 10 | B2352101700200 | 1 | 6574872200 | C4FP5266A01 | [22 empty] | 100%
2782278410 | 27822784 | 10 | D9551002200595 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
2782332710 | 27823327 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2782332810 | 27823328 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2782332910 | 27823329 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2782333010 | 27823330 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
27847916 2796183610 | 27847916 27961836 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
2784880110 | 27848801 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
27896375 2794012910 | 27896375 27940129 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
27879924 2794012010 | 27879924 27940120 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
2791346710 | 27913467 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04 | [22 empty] | 100%
2791376210 | 27913762 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04 | [22 empty] | 100%
27859375 2793994310 | 27859375 27939943 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
27908564 2796146010 | 27908564 27961460 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2791439010 | 27914390 | 10 | D9551002200595 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
2791426810 | 27914268 | 10 | D9551002201695 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
2791427010 | 27914270 | 10 | D9551002201695 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
2791555510 | 27915555 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2791555810 | 27915558 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2791555910 | 27915559 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2791556010 | 27915560 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2791556210 | 27915562 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2791557510 | 27915575 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2791557810 | 27915578 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2791558110 | 27915581 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2791558510 | 27915585 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2791558710 | 27915587 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
681137810 | 6811378 | 10 | MB041ACAAAAE | 1 | 6M90080000 | [23 empty] | 100%
2780860210 | 27808602 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2783049110 | 27830491 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2783049510 | 27830495 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2783049410 | 27830494 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2783049610 | 27830496 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2783049710 | 27830497 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2784044610 | 27840446 | 10 | D9550011700295 | 1 | 6963576200 | D11312633A00 | 1 | 6963582600 | D11312851A00 | [19 empty] | 100%
2792616210 | 27926162 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792616310 | 27926163 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792616610 | 27926166 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792617810 | 27926178 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2792618110 | 27926181 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2792618210 | 27926182 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2792618310 | 27926183 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2792618410 | 27926184 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2792607710 | 27926077 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792607910 | 27926079 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792608810 | 27926088 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792609610 | 27926096 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792612810 | 27926128 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792613110 | 27926131 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792613510 | 27926135 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792613710 | 27926137 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792613910 | 27926139 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792614110 | 27926141 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2792614410 | 27926144 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2780554210 | 27805542 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2787246710 | 27872467 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2788187910 | 27881879 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2791299610 | 27912996 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2774443110 | 27744431 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2790954510 | 27909545 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
490003645110 | 4900036451 | 10 | S9550081192795 | 1 | 6853820100 | SC628ANPR | [22 empty] | 100%
2794403810 | 27944038 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04 | [22 empty] | 100%
2794720110 | 27947201 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794720710 | 27947207 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794720910 | 27947209 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794721410 | 27947214 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794709910 | 27947099 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794710410 | 27947104 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794710510 | 27947105 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794710610 | 27947106 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794710710 | 27947107 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2794741910 | 27947419 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2794742310 | 27947423 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2794742510 | 27947425 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2794743110 | 27947431 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2796145410 | 27961454 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2796145210 | 27961452 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2796144910 | 27961449 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
2796145010 | 27961450 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
2795065310 | 27950653 | 10 | D9251719400095 | 2 | 6925002700 | 530AL01CN | [20 empty] | Zodiac |  | 100%
2802068510 | 28020685 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2803363210 | 28033632 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04 | [22 empty] | 100%
2803368010 | 28033680 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04 | [22 empty] | 100%
2804605010 | 28046050 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2804605610 | 28046056 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2804605510 | 28046055 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2804729810 | 28047298 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2804729910 | 28047299 | 10 | D9551006100295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2805292510 | 28052925 | 10 | WF413SBAAAAA | 1 | 6V00588500 | [23 empty] | 100%
2805778510 | 28057785 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2805553410 | 28055534 | 10 | WF409ACABAAB | 1 | 6V90079500 | 723-5561-02 | [22 empty] | 100%
2806360410 | 28063604 | 10 | A9550051000195 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2806846710 | 28068467 | 10 | D9551002201195 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2806846610 | 28068466 | 10 | D9551002201195 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2809149110 | 28091491 | 10 | D9551006000195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | [19 empty] | 100%
2809149510 | 28091495 | 10 | D9551006000195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | [19 empty] | 100%
2809149810 | 28091498 | 10 | D9551006000195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | [19 empty] | 100%
2809150110 | 28091501 | 10 | D9551006000195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | [19 empty] | 100%
2809165510 | 28091655 | 10 | D9551006200195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2809165710 | 28091657 | 10 | D9551006200195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2809165910 | 28091659 | 10 | D9551006200195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2809166210 | 28091662 | 10 | D9551006200195 | 1 | 6963402800 | 002078-01 | 1 | 6963403000 | 002079-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2809756810 | 28097568 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
2809820410 | 28098204 | 10 | WF408ACABAAB | 1 | 6V00205900 | 723-5560-03 | [22 empty] | 100%
2810644910 | 28106449 | 10 | D9551006100195 | 1 | 6963402800 |  | 1 | 6963403000 | [20 empty] | 100%
2810645110 | 28106451 | 10 | D9551006100195 | 1 | 6963402800 |  | 1 | 6963403000 | [20 empty] | 100%
2810645210 | 28106452 | 10 | D9551006100195 | 1 | 6963402800 |  | 1 | 6963403000 | [20 empty] | 100%
2810645310 | 28106453 | 10 | D9551006100195 | 1 | 6963402800 |  | 1 | 6963403000 | [20 empty] | 100%
2812835610 | 28128356 | 10 | D9550006300295 | 1 | 6963403900 | [23 empty] | 100%
2815099710 | 28150997 | 10 | D9551002200895 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2814857410 | 28148574 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2815830810 | 28158308 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2816177410 | 28161774 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2820355610 | 28203556 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2822091010 | 28220910 | 10 | D9550011900195 | 1 | 6963382700 | D33110232A00 | [22 empty] | 100%
2822091110 | 28220911 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2822091120 | 28220911 | 20 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2796145220 | 27961452 | 20 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2822109610 | 28221096 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2822399110 | 28223991 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [20 empty] | Paulstra |  | 100%
2821976310 | 28219763 | 10 | WG281ABABAAE | 1 | 6V00514700 | [23 empty] | 100%
2823282410 | 28232824 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2823263910 | 28232639 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2826774710 | 28267747 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2826776710 | 28267767 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2826832210 | 28268322 | 10 | D9551006000295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | [19 empty] | 100%
2826837510 | 28268375 | 10 | D9551006100295 | 1 | 6963402800 |  | 1 | 6963403000 | [20 empty] | 100%
2826839910 | 28268399 | 10 | D9551006200295 | 1 | 6963455500 | 007164-01 | 1 | 6963455400 | 007165-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 100%
2829496710 | 28294967 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2832391910 | 28323919 | 10 | D9551002201195 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2832347010 | 28323470 | 10 | WF407ABAAAAB | 1 | 6V90079100 | 723-5559-02 | [22 empty] | 100%
2834415310 | 28344153 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2836317910 | 28363179 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2836726510 | 28367265 | 10 | D9551002201195 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2832798410 | 28327984 | 10 | D9551002201695 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
2824111210 | 28241112 | 10 | A95500441000AA | 1 | 6574820900 | C4E32166$A | [22 empty] | 0%
2842136810 | 28421368 | 10 | D9551002201195 | 1 | 6939600100 | 058-001-00 | [22 empty] | 0%
2802674810 | 28026748 | 10 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [15 empty] | PN 3 RECU | 33%
682405910 | 6824059 | 1 | MB170ACAAAAB | 1 | 6M90005100 | 360-001 | 1 | 6M90005200 | 33-455 | 1 | 6M90005300 | 27-457 | 1 | 6M90079400 | 723-6212-01 | 1 | M8753611300000 | 4STR*01151 | [9 empty] | PN1/PN2/PN3/PN4/PN5 reçu | 100%
2811409210 | 28114092 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
2814871910 | 28148719 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
2815217810 | 28152178 | 10 | A95500426000AB | 1 | 6574929100 | A31111969A00 | [22 empty] | 0%
2828658710 | 28286587 | 10 | A95500435000AA | 2 | 6527212000 | 444-00521-300 | 4 | 6527211900 | 444-00522-300 | 1 | 6574930800 | A31111970A00 | [15 empty] | recu: PN1, PN2, PN3 | 100%
2816808210 | 28168082 | 10 | A95500432000AB | 1 | 6584513300 | 82300A0101 | 2 | 6584516400 | 83002C0102 | 1 | 6574803900 | C4E32024-01 | 1 | 6595665200 | 31588-00000 | [13 empty] | 0%
2820491010 | 28204910 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
2820520710 | 28205207 | 10 | A95500426000AB | 1 | 6574929100 | A31111969A00 | [22 empty] | 0%
2822209510 | 28222095 | 10 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [15 empty] | PN3 RECU | 100%
2822399010 | 28223990 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2826157310 | 28261573 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2815867830 | 28158678 | 30 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2820470040 | 28204700 | 40 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2815867860 | 28158678 | 60 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
68397402 | 6839740 | 2 | MB042ACABAAA | 1 | 6M90079500 |  | 1 | 4STR*01314 | [20 empty] | 100%
68397403 | 6839740 | 3 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | 4STR*01310 | M8753613900000 | [18 empty] | PN1/PN2 reçu | 100%
68397401 | 6839740 | 1 | MB036ACAAAAC | 1 | 6M90080200 |  | 1 | 4STR*01388 | M8753613200000 | [18 empty] | PN1/PN2 reçu | 100%
68397404 | 6839740 | 4 | MB034ACAEAAA | 1 | 6M00402600 |  | 1 | 6M00725800 |  | 2 | 6M00726300 |  | 1 | 4STR*01389 | M8753612600000 | [12 empty] | PN1/PN2/PN3/PN4 reçu | 100%
68397405 | 6839740 | 5 | MB032ADAAAAB | 1 | 6M90079300 | 723-6209-01 | 1 | 4STR*01390 |  | 1 | 6M00238500 | [16 empty] | PN1/PN2/PN3 reçu | 100%
68397406 | 6839740 | 6 | MB033ADACAAB | 1 | 6M00724800 |  | 1 | 6M90079200 |  | 1 | 4STR*01391 |  | 1 | 6M90018800 | [13 empty] | PN1/PN2/PN3/PN4 recu | 100%
68397407 | 6839740 | 7 | MB037ADAAAAB | 1 | 6M90079600 |  | 1 | 4STR*01392 | M8753614100000 | [18 empty] | PN1/PN2 reçu | 100%
68397408 | 6839740 | 8 | MB038ADAAAAB | 1 | 6M90079900 |  | 1 | 4STR*01393 | M8753614200000 | [18 empty] | PN1/PN2 reçu | 100%
68397409 | 6839740 | 9 | MB040ADAAAAB | 1 | 6M90079700 |  | 1 | 4STR*01394 | M8753615700000 | [18 empty] | PN1/PN2 reçu | 100%
683974010 | 6839740 | 10 | MB041ADAAAAB | 1 | 6M90080000 |  | 1 | 4STR*01395 | M8753615800000 | [18 empty] | PN1/PN2 recu | 100%
683974011 | 6839740 | 11 | MB137ADAAAAC | 1 | 6M90080400 |  | 1 | 4STR*01396 | M8753613700000 | [18 empty] | PN1/PN2 reçu | 100%
2828532220 | 28285322 | 20 | A27912401006C11 | 1 | 6595684900 | [23 empty] | 100%
2827634210 | 28276342 | 10 | A95500419000AA | 1 | 6599807700 | DRT25LDC7AP68 | 1 | 6504421000 | P11S2VBAPSYT503 | 1 | 6586901800 | PA1RT25L150DB7 | 1 | 6504420500 | P11S1VBAPSYT461 | 1 | 6574907800 | C4FP5404A01 | [9 empty] | Recu PN2 + PN3 + PN4 + PN5 | 100%
68428491 | 6842849 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 | 4STR*01397 | M8753611400000 | 1 | 6M00660400 |  | 1 |  | M8753622100000 | [9 empty] | PN1/PN2/PN3/PN4 reçu | 100%
68428492 | 6842849 | 2 | MB039ACAAAAB | 1 | 6M00097600 |  | 2 | 6M00122800 |  | 1 | 6M90079800 |  | 1 | 4STR*01399 | M8753616600000 | [12 empty] | PN1/PN2/PN3/PN4 reçu | 100%
68428493 | 6842849 | 3 | MB136ABAAAAD | 1 | 6M90079100 |  | 1 | 4STR*01398 | M8753613400000 | [18 empty] | PN1/PN2 reçu | 100%
2796891220 | 27968912 | 20 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891230 | 27968912 | 30 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891240 | 27968912 | 40 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891250 | 27968912 | 50 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891260 | 27968912 | 60 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891270 | 27968912 | 70 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2796891280 | 27968912 | 80 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 100%
2829473610 | 28294736 | 10 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 |  | 6574907200 | C4FP5406A01 | [15 empty] | Recu PN1 (À prélevé sur PO 27968912 /10) / Recu PN2 | 100%
2829473620 | 28294736 | 20 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 |  | 6574907200 | C4FP5406A01 | [15 empty] | Recu PN1 / Recu PN2 | 100%
2829473630 | 28294736 | 30 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 |  | 6574907200 | C4FP5406A01 | [15 empty] | Recu PN1 / Recu PN2 | 100%
2820478220 | 28204782 | 20 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2830266910 | 28302669 | 10 | A9550042972695 | 1 | 6539607700 | A300B09606027B | 2 | 6539603600 | A300B0961066 | 1 | 6574907200 | C4FP5406A01 | [16 empty] | 0%
68457941 | 6845794 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | 4STR*01310 | M8753613900000 | [18 empty] | PN1/PN2 reçu | 100%
68428241 | 6842824 | 1 | MB035ACAAAAC | 1 | 6M90080100 |  | 1 | M87536215000 |  | 1 | M87536216000 |  | 4 | F00030578209 | [13 empty] | PN1/PN2 reçu | 100%
2831808510 | 28318085 | 10 | D9551002201795 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2832798420 | 28327984 | 20 | D9551002201695 | 1 | 6939600100 | 058-001-00 | 1 | 6944100100 | 7530334 | [19 empty] | 100%
68486991 | 6848699 | 1 | MB032ACAAAAB | 1 | 6M90079300 | 723-6209-01 | 1 | 4STR*01390 | [20 empty] | 0%
2833860110 | 28338601 | 10 | D9551006000395 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [18 empty] | PN 1 et PN 2 OK | 100%
2833860610 | 28338606 | 10 | D9551006100395 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [18 empty] | PN 2 OK; PN 1 OK | 100%
2833860710 | 28338607 | 10 | D9551006200395 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | 1 | 6963403400 | 002077-01 | [15 empty] | PN 2 OK; PN 3 OK; PN 1 | 100%
2834416910 | 28344169 | 10 | D9551010800195 | 1 | 6963469200 | 002045-02 | [22 empty] | 100%
2837434910 | 28374349 | 10 | A95500432000AB | 1 | 6584513300 | 82300A0101 | 2 | 6584516400 | 83002C0102 | 1 | 6574803900 | C4E32024-01 | 1 | 6595665200 | 31588-00000 | [12 empty] | PN1/PN2/PN3/PN4 reçus | 100%
2838021110 | 28380211 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2838030810 | 28380308 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2838041110 | 28380411 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 100%
2837641010 | 28376410 | 10 | A95500426000AB | 1 | 6574929100 | A31111969A00 | [22 empty] | 0%
2837641110 | 28376411 | 10 | A95500426000AB | 1 | 6574929100 | A31111969A00 | [22 empty] | 0%
2838590910 | 28385909 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591010 | 28385910 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591110 | 28385911 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591210 | 28385912 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591410 | 28385914 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591510 | 28385915 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591810 | 28385918 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838591910 | 28385919 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838592210 | 28385922 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838592410 | 28385924 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838592710 | 28385927 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838593910 | 28385939 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838594010 | 28385940 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838594810 | 28385948 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838594910 | 28385949 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838595010 | 28385950 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838595110 | 28385951 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838595210 | 28385952 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838595310 | 28385953 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2838595410 | 28385954 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2843353110 | 28433531 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [21 empty] | Confié prélever sur une commande annulée | 100%
2840771710 | 28407717 | 10 | D9551002200395 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2842466810 | 28424668 | 10 | A95500441000AA | 1 | 6574820900 | C4E32166$A | [22 empty] | 100%
2842869110 | 28428691 | 10 | A95500441000AA | 1 | 6574820900 | C4E32166$A | [22 empty] | 0%
68578381 | 6857838 | 1 | MB032ADAAAAB | 1 | 6M90079300 | 723-6209-01 | 1 | IS0055818S | M8753624400000 | 1 | IS0055819S | M8753620520000 | 1 | IS0055820S | F0003057822200 | 3 | IS0055821S | F0003057822100 | 1 | IS0055822S | M8753620600000 | [6 empty] | CMS1/CMS2/CMS3/CMS4/CMS5/CMS6 | 100%
68141141 | 6814114 | 1 | MB170ACAAAAA | 1 | 6M90005100 | 360-001 | 1 | 6M90005200 | 33-455 | 1 | 6M90005300 | 27-457 | 1 | 6M90079400 | 723-6212-01 | 1 | M8753611300000 | 4STR*01151 | [9 empty] | CMS 2 missing | 90%
2843350010 | 28433500 | 10 | A95500419000AA | 1 | 6599807700 | DRT25LDC7AP68 | 1 | 6504421000 | P11S2VBAPSYT503 | 1 | 6586901800 | PA1RT25L150DB7 | 1 | 6504420500 | P11S1VBAPSYT461 | 1 | 6574907800 | C4FP5404A01 | [10 empty] | 0%
284673201 | 28467320 | 1 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
284673202 | 28467320 | 2 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
284673203 | 28467320 | 3 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
284673204 | 28467320 | 4 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
284673205 | 28467320 | 5 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
284673206 | 28467320 | 6 | D9551003000195 | 2 | 6939600000 | 058-003-00 | 3 | 6946299300 | 777B0000-02 | [18 empty] | PN1 et PN2 reçus | 100%
2847953210 | 28479532 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00
2847953211 | 28479532 | 11 | A9550051000296 | 1 | 6530207600 | A31112112B00
2847842010 | 28478420 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2848051310 | 28480513 | 10 | A9550051000196 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2848683910 | 28486839 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2848683920 | 28486839 | 20 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
68727191 | 6872719 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 | IS0003192S | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | PN1/PN2/PN3//PN4/PN5/PN6/PN7/PN8 received | 100%
68735431 | 6873543 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 | 4STR*01397 | M8753611400000 | 1 | 6M00660400 |  | 1 |  | M8753622100000 | [10 empty] | 0%
68680821 | 6868082 | 1 | MB043ABAAAAB | 1 |  | M87536151000
2850315110 | 28503151 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01
68760561 | 6876056 | 1 | MB042ACABAAA | 1 | 6M90079500 |  | 1 | 4STR*01314 | M8753614900000 | [18 empty] | CMS 1 RECEIVED/CMS 2 IN STOCK | 100%
68752671 | 6875267 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3/PN4 reçus | 100%
2850155510 | 28501555 | 10 | D9551006200195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 0%
2850155410 | 28501554 | 10 | D9551006100195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [19 empty] | 0%
2850155310 | 28501553 | 10 | D9551006000195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [19 empty] | 0%
68707011 | 6870701 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | 4STR*01310 | M8753613900000 | [18 empty] | PN2 reçu | 50%
68714601 | 6871460 | 1 | MB136ABAAAAD | 1 | 6M90079100 |  | 1 | 4STR*01398 | M8753613400000 | [19 empty] | 0%
2851502410 | 28515024 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [21 empty] | Received | 100%
2851333610 | 28513336 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 0%
2851333620 | 28513336 | 20 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 0%
2852872410 | 28528724 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2853102410 | 28531024 | 10 | D9550010801195 | 2 | 6963510300 | D11311784A00 | [22 empty] | 100%
68810621 | 6881062 | 1 | MB035ACAAAAC | 1 | 6M90080100 |  | 1 | M87536215000 |  | 1 | M87536216000 |  | 4 | F00030578209 | [13 empty] | PN2 reçu | 100%
68797721 | 6879772 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3 received | 100%
68797722 | 6879772 | 2 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3/PN4 received sous ensemble ST complet IS0053799S | 100%
68795611 | 6879561 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3/PN4 received sous ensemble ST complet IS0053799S) | 100%
68782751 | 6878275 | 1 | MB135ABAAAAC | 1 | 6M90080300 | IS0003212S | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3/PN4 received | 100%
68782752 | 6878275 | 2 | MB135ABAAAAC | 1 | 6M90080300 | IS0003212S | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3/PN4 received | 100%
2854069510 | 28540695 | 10 | D9550010801295 | 1 | 6963469200 | 723-1051-02 | [22 empty] | 0%
2853795410 | 28537954 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2853795420 | 28537954 | 20 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
68858611 | 6885861 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | 4STR*01310 | M8753613900000 | [18 empty] | CM2 received | 100%
68888831 | 6888883 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | CMS 1 missing | 90%
68803281 | 6880328 | 1 | MB042ACABAAA | 1 | 6M90079500 |  | 1 | 4STR*01314 | M8753614900000 | [18 empty] | CMS1/CM2 RECEIVED | 100%
2857604010 | 28576040 | 10 | D9551002201895 | 1 | 6939600100 | 058-001-00 | [22 empty] | 100%
2858023110 | 28580231 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
2857183110 | 28571831 | 10 | A95500110000AA | 1 | 6583308600 | 1421KID1-1 | 1 | 6539335700 | 768-380
68936651 | 6893665 | 1 | MB259ADABAAC | 1 |  | M8753627200000 | 1 |  | M8753627300000 | 1 |  | F0003057820900 | 2 | 6M00946500 | [13 empty] | CMS 4 missing | 100%
68936652 | 6893665 | 2 | MB259ADABAAC | 1 |  | M8753627200000 | 1 |  | M8753627300000 | 1 |  | F0003057820900 | 2 | 6M00946500 | [13 empty] | CMS 4 missing | 100%
68936653 | 6893665 | 3 | MB259ADABAAC | 1 |  | M8753627200000 | 1 |  | M8753627300000 | 1 |  | F0003057820900 | 2 | 6M00946500 | [13 empty] | PN 3 et CMS 4 missing | 80%
68942301 | 6894230 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | CMS 1 missing | 90%
69224041 | 6922404 | 1 | MB135ABAAAAC | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [13 empty] | 0%
2859739510 | 28597395 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
68964071 | 6896407 | 1 | MB043ACAAAAD | 1 |  | M8753626800000 | 1 |  | M8753626900000 | 4 |  | F0003057820900 | [16 empty] | 0%
68964072 | 6896407 | 2 | MB030AAAAAAA | 1 | 6M00932700 | IS0056090S | 1 | M8753627000000 |  | 1 | M8753627100000 |  | 3 | F0003057820900 | [14 empty] | 0%
2859723310 | 28597233 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2859675310 | 28596753 | 10 | A27912401007C10 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
P2915221 1 | P2915221 | 1 | MD501-311101-01B |  |  | H72362730101 |  |  | ABS1643ACSB007 |  |  | SCI535B5F48X05N | [16 empty] | 100%
P2915221 2 | P2915221 | 2 | MD501-311101-01B |  |  | H72362730101 |  |  | ABS1643ACSB007 |  |  | SCI535B5F48X05N | [16 empty] | 100%
2860108610 | 28601086 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2860108620 | 28601086 | 20 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
2860108630 | 28601086 | 30 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 100%
68981911 | 6898191 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | Missing CMS 2 et CMS 4 | 100%
2860605010 | 28606050 | 10 | D9551006000195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [19 empty] | 0%
2860605110 | 28606051 | 10 | D9551006100195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | [19 empty] | 0%
2860605210 | 28606052 | 10 | D9551006200195 | 1 | 6963402800 | 002079-01 | 1 | 6963403000 | 002078-01 | 1 | 6963403400 | 002077-01 | [16 empty] | 0%
68990011 | 6899001 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 |  | M8753626600000 | PN1/PN2/PN3/PN4/PN5/PN6/PN7/PN8 received | 100%
69224051 | 6922405 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | PN3/PN5/PN6/PN7/PN8 received | 100%
2862282610 | 28622826 | 10 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2862282620 | 28622826 | 20 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2862282630 | 28622826 | 30 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2862282640 | 28622826 | 40 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
2862282650 | 28622826 | 50 | A9550051000296 | 1 | 6530207600 | A31112112B00 | [22 empty] | 100%
69034361 | 6903436 | 1 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 |  | 0%
2864026310 | 28640263 | 10 | WF426AEAAAAE | 1 | 6V90081300 | 723-1334-02 | [22 empty] | 100%
2862720610 | 28627206 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2864756510 | 28647565 | 10 | D9550010801195 | 2 | 6963510300 | D11311784A00 | [22 empty] | 100%
69091251 | 6909125 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 |  | 0%
69224052 | 6922405 | 2 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 | PN7 & PN5 missing | 100%
2868575410 | 28685754 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2870430610 | 28704306 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
69164121 | 6916412 | 1 | MB033ACAAAAB | 1 | 6M00724800 |  | 1 | 6M90079200 |  | 1 |  | M87536122000 | 1 | 6M90018800 | [14 empty] | 0%
69169071 | 6916907 | 1 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 |  | 100%
2870605610 | 28706056 | 10 | D9551005400195 | 1 | 6997012100 | 2LA455226-67 | [22 empty] | 100%
69181481_1 | 6918148 | 1_1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 |  | 100%
2870622710 | 28706227 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2870884610 | 28708846 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 100%
2870776010 | 28707760 | 10 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 0%
2872564010 | 28725640 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
69201431 | 6920143 | 1 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 | PN5 missing | 95%
2873577510 | 28735775 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2874319210 | 28743192 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2874319211 | 28743192 | 11 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2874319220 | 28743192 | 20 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2874319221 | 28743192 | 21 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2874319222 | 28743192 | 22 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2874319223 | 28743192 | 23 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
69212731 | 6921273 | 1 | MB045ACAAAAB | 1 | IS0059157S | M87536252000 | 1 | IS0059158S | M87536253200 | 1 | IS0059159S | M87536197000 | [16 empty] | 100%
69220491 | 6922049 | 1 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 |  | 100%
69220492 | 6922049 | 2 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 | CMS 2 received | 100%
69220493 | 6922049 | 3 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 | IS0056044S | F0003057822800 | 1 | IS0056045S | M8753626600000 |  | 100%
68981911.2 | 6898191 | 1.2 | #N/A | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | Missing CMS 4 | 100% | Livré
68981911.3 | 6898191 | 1.3 | #N/A | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | Missing CMS 4 | 100% | Livré
68981911.1 | 6898191 | 1.1 | #N/A | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 | Missing CMS 4 | 100% | Livré
69225001 | 6922500 | 1 | MB045ACAAAAB | 1 | IS0059157S | M87536252000 | 1 | IS0059158S | M87536253200 | 1 | IS0059159S | M87536197000 | [16 empty] | 100%
2870776020 | 28707760 | 20 | D9550010800996 | 1 | 6963403800 | 002045-01 | [22 empty] | 0%
68797721.1 | 6879772 | 1.1 | #N/A | 1 | 6M90080300 |  | 1 | IS0055787S | M8753621900000 | 1 | IS0055786S | M8753623700000 | 4 | IS0054723S | F0003057820900 | [12 empty] | PN1/PN2/PN3 received | 100% | Livré
69181481.1 | 6918148 | 1.1 | #N/A | 1 | 6M90110600 |  | 1 | 6M00635400 |  | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 |  | M8753626520000 | 3 |  | F0003057822800 | 1 |  | M8753626600000 |  | 0% | Livré
69255731 | 6925573 | 1 | MB045ACAAAAB | 1 | IS0059157S | M87536252000 | 1 | IS0059158S | M87536253200 | 1 | IS0059159S | M87536197000 | [16 empty] | 100%
2874388910 | 28743889 | 10 | WF412ADACAAF | [25 empty] | 0%
2877628810 | 28776288 | 10 | D9550011000295 | 1 | 6984400200 |  | 1 | 6925008700 |  | 1 | 6939600500 | [17 empty] | 0%
2878174510 | 28781745 | 10 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 0%
2878174520 | 28781745 | 20 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 0%
2878174530 | 28781745 | 30 | WF418AFACAAE | 1 | 6V01448300 | 723-1337-03 | [22 empty] | 0%
69266781 | 6926678 | 1 | MB031ADAEAAB | 1 | 6M90110600 |  | 1 | 6M00635400 | IS0060909S | 1 |  | M8753622100000 | 1 | 6M00660400 |  | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 |  | F0003057822800 | 1 | IS0056045S | M8753626600000 | CMS 2&4 received | 100%
2881858410 | 28818584 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
2881858410.1 | 28818584 | 10.1 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.2 | 28818584 | 10.2 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.3 | 28818584 | 10.3 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.4 | 28818584 | 10.4 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.5 | 28818584 | 10.5 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.6 | 28818584 | 10.6 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2881858410.7 | 28818584 | 10.7 | #N/A | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0% | Livré
2883538810 | 28835388 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
69328361 | 6932836 | 1 | MB031ADAEAAB | 1 | 6M90110600 | IS0060931S | 1 | 6M00635400 | IS0060909S | 1 | IS0055890S | M8753622100000 | 1 | 6M00660400 | IS0060910S | 1 | IS0056042S | M8753626400000 | 1 | IS0056043S | M8753626520000 | 3 |  | F0003057822800 | 1 | IS0056045S | M8753626600000 |  | 0%
69344341 | 6934434 | 1 | MB038ADAAAAB | 1 | 6M90079900 | [23 empty] | 0%
2884675210 | 28846752 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 100%
2885016910 | 28850169 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2885016910.1 | 28850169 | 10.1 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2885016910.2 | 28850169 | 10.2 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2885016910.3 | 28850169 | 10.3 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2885256510 | 28852565 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2885256510.1 | 28852565 | 10.1 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2885256510.2 | 28852565 | 10.2 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2885256510.3 | 28852565 | 10.3 | #N/A | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0% | Livré
2889076210 | 28890762 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2885016910 | 28850169 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889982710 | 28899827 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889982910 | 28899829 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889983010 | 28899830 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2885256510 | 28852565 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889983210 | 28899832 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889983310 | 28899833 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2889983410 | 28899834 | 10 | WF406ACAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890425610 | 28904256 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890425710 | 28904257 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890425810 | 28904258 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890425910 | 28904259 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890442410 | 28904424 | 10 | WF406ABAAAAB | 1 | 6V90079000 | 723-5558-02 | [22 empty] | 0%
2890427610 | 28904276 | 10 | WF417AFACAAE | 1 | 6V01965900 | 723-1331-04
2890429910 | 28904299 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
2890430310 | 28904303 | 10 | A27912401007C11 | 1 | 6595685000 | C4E31832-01 | [22 empty] | 0%
69455441 | 6945544 | 1 | MB032ADAAAAB | 1 | 6M90079300 | 723-6209-01 | 1 | IS0055818S | M8753624400000 | 1 | IS0055819S | M8753620520000 | 1 | IS0055820S | F0003057822200 | 3 | IS0055821S | F0003057822100 | 1 | IS0055822S | M8753620600000 | [7 empty] | 0%

## OTD 2022
Period | Delivery planned | Delivery On Time | OTD | Target | Contractual Delivery | Delivery On Time | OTD | Target | Production delivery | Delivery On Time | OTD | Target
2022-01-01 | 39 | 37 | 94.87% | 97.5% | 39 | 19 | 48.72% | 97.5% | 29 | 0 | 0% | 97.5%
2022-02-01 | 37 | 31 | 83.78% | 97.5% | 37 | 19 | 51.35% | 97.5% | 16 | 0 | 0% | 97.5%
2022-03-01 | 21 | 20 | 95.24% | 97.5% | 21 | 15 | 71.43% | 97.5% | 4 | 0 | 0% | 97.5%
2022-04-01 | 13 | 2 | 15.38% | 97.5% | 13 | 0 | 0% | 97.5% | 11 | 0 | 0% | 97.5%
2022-05-01 | 43 | 28 | 65.12% | 97.5% | 43 | 4 | 9.302% | 97.5% | 43 | 0 | 0% | 97.5%
2022-06-01 | 42 | 34 | 80.95% | 97.5% | 42 | 19 | 45.24% | 97.5% | 42 | 3 | 7.143% | 97.5%
2022-07-01 | 25 | 21 | 84% | 97.5% | 25 | 0 | 0% | 97.5% | 25 | 2 | 8% | 97.5%
2022-08-01 | 1 | 0 | 0% | 97.5% | 1 | 1 | 100% | 97.5% | 1 | 0 | 0% | 97.5%
2022-09-01 | 1 | 0 | 0% | 97.5% | 1 | 0 | 0% | 97.5% | 1 | 0 | 0% | 97.5%
2022-10-01 | 89 | 44 | 49.44% | 97.5% | 89 | 0 | 0% | 97.5% | 89 | 3 | 3.371% | 97.5%
2022-11-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2022-12-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
Note on C1: ZARCONE Anthony: Basée sur dates collaborées
Note on G1: ZARCONE Anthony: Basée sur dates contactuelles initiales
Note on K1: ZARCONE Anthony: Basée sur dates d'expéditions

## OTD 2021
Period | Delivery planned | Delivery On Time | OTD | Target | Contractual Delivery | Delivery On Time | OTD | Target | Production delivery | Delivery On Time | OTD | Target
2021-01-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-02-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-03-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-04-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-05-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-06-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-07-01 | 16 | 16 | 100% | 97.5% | 16 | 16 | 100% | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-08-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-09-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-10-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-11-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2021-12-01 | 7 | 0 | 0% | 97.5% | 7 | 7 | 100% | 97.5% | 0 | 0 | #DIV/0! | 97.5%
Note on C1: ZARCONE Anthony: Basée sur dates collaborées
Note on G1: ZARCONE Anthony: Basée sur dates contactuelles initiales
Note on K1: ZARCONE Anthony: Basée sur dates d'expéditions

## OTD 2020
Period | Delivery planned | Delivery On Time | OTD | Target | Contractual Delivery | Delivery On Time | OTD | Target | Production delivery | Delivery On Time | OTD | Target
2020-01-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-02-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-03-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-04-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-05-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-06-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-07-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-08-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-09-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-10-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-11-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
2020-12-01 | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5% | 0 | 0 | #DIV/0! | 97.5%
Note on C1: ZARCONE Anthony: Basée sur dates collaborées
Note on G1: ZARCONE Anthony: Basée sur dates contactuelles initiales
Note on K1: ZARCONE Anthony: Basée sur dates d'expéditions

## PO VOLUME
Period | Volume Order 2018 | Volume Order 2019 | Volume Order 2020 | Volume Order 2021
2018-01-01 | 36 |  |  |  | Janvier
2018-02-01 | 11 |  |  |  | Février
2018-03-01 | 80 |  |  |  | Mars
2018-04-01 | 32 |  |  |  | Avril
2018-05-01 | 110 |  |  |  | Mai
2018-06-01 | 91 |  |  |  | Juin
2018-07-01 | 54 |  |  |  | Juillet
2018-08-01 | 352 |  |  |  | Août
2018-09-01 | 168 |  |  |  | Septembre
2018-10-01 | 124 |  |  |  | Octobre
2018-11-01 | 86 |  |  |  | Novembre
2018-12-01 | 61 |  |  |  | Décembre
2019-01-01 |  | 88
2019-02-01 |  | 199
2019-03-01 |  | 93
2019-04-01 |  | 69
2019-05-01 |  | 65
2019-06-01 |  | 91
2019-07-01 |  | 113
2019-08-01 |  | 304
2019-09-01 |  | 168
2019-10-01 |  | 89
2019-11-01 |  | 115
2019-12-01 |  | 170
2020-01-01 |  |  | 122
2020-02-01 |  |  | 75
2020-03-01 |  |  | 69
2020-04-01 |  |  | 35
2020-05-01 |  |  | 15
2020-06-01 |  |  | 14
2020-07-01 |  |  | 59
2020-08-01 |  |  | 52
2020-09-01 |  |  | 36
2020-10-01 |  |  | 31
2020-11-01 |  |  | 27
2020-12-01 |  |  | 13
2021-01-01 |  |  |  | 20
2021-02-01 |  |  |  | 19
2021-03-01 |  |  |  | 17
2021-04-01 |  |  |  | 54
2021-05-01 |  |  |  | 223
2021-06-01 |  |  |  | 238
2021-07-01 |  |  |  | 99
2021-08-01 |  |  |  | 75
2021-09-01 |  |  |  | 35
2021-10-01 |  |  |  | 97
2021-11-01 |  |  |  | 34
2021-12-01 |  |  |  | 134
2022-01-01 |  |  |  | 216
2022-02-01 |  |  |  | 73
2022-03-01 |  |  |  | 91
2022-04-01 |  |  |  | 56
2022-05-01 |  |  |  | 545
2022-06-01 |  |  |  | 125
2022-07-01 |  |  |  | 81
2022-08-01 |  |  |  | 31
2022-09-01 |  |  |  | 87
2022-10-01 |  |  |  | 78
2022-11-01 |  |  |  | 0
2022-12-01 |  |  |  | 0

## Database
PN | VU | PO TYPE | Confiés | Qté confiés | EASA FORM1 | USER | CLIENT | TEST | Temps alloués total (h) | Temps TMS | TEMPS LASER | TMPS LUV | TEMPS MECA | TEMPS CABLAGE | TEMPS PROD | TEMPS CTRL | TEMPS TEST | CONTRÔLE/TEST | CLIENT | ISM/ISS | LDF VALIDE | Vis peintes
S9252300600000 | 3 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252301100000 | 4 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252310400000 | 4 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252310600000 | 4 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252301600000 | 5 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
MB031ADAEAAC | 11 | FABRICATION | 6M90110600 6M00635400 6M00660400 | Qté 1 | OUI |  | SATAIR | COL | 10.2691 | 0.205 | 0 | 0.205 | 1.5899 | 6.4614 | 8.0513 | 0.80513 | 1.2077 | 2.0128 | AD&S | IS0032544M | N | NA
MB170ACAAAAA | 12 | FABRICATION | 6M90005200 6M90005100 6M90005300 6M90079400 | Qté 1 Qté 1 Qté 1 Qté 1 | OUI | MB2061D | SATAIR | COL | 10.6216 | 0.205 | 0 | 0.205 | 1.85 | 6.4833 | 8.3333 | 0.83333 | 1.25 | 2.0833 | AD&S | IS0032211M | N | NA
MB170ACAAAAB | 12 | FABRICATION | 6M90005200 6M90005100 6M90005300 6M90079400 | Qté 1 Qté 1 Qté 1 Qté 1 | OUI | MB2061D | SATAIR | COL | 10.6216 | 0.205 | 0 | 0.205 | 1.85 | 6.4833 | 8.3333 | 0.83333 | 1.25 | 2.0833 | AD&S | IS0032212M | N | NA
S9252501100251 | 13 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252501100252 | 13 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252303200051 | 13 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9550001500195 | 15 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 1.15 | 0 | 0 | 0 | 0.21 | 0.71 | 0.92 | 0.092 | 0.138 | 0.23 | SATAIR |  | N
D9551001600196 | 16 | FABRICATION | 6925015800 6963400000 6963397500 | Qté 1 Qté 1 Qté 1 | NON | NB01881P | SATAIR | COL | 2.6189 | 0 | 0 | 0 | 0.4921 | 1.603 | 2.0951 | 0.20951 | 0.31426 | 0.52377 | SATAIR |  | N
D9551001700195 | 17 | FABRICATION | 6925015800 6963400000 6963397500 | Qté 1 Qté 1 Qté 1 | NON | NB01881P | SATAIR | COL | 2.8239 | 0.205 | 0 | 0.205 | 0.4921 | 1.603 | 2.0951 | 0.20951 | 0.31426 | 0.52377 | SATAIR |  | N
D9251543900100 | 21 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9550002100195 | 21 | FABRICATION | 6939600100 | Qté 1 | NON | NA | SATAIR | COL | 31.03 | 0.205 | 0 | 0.205 | 2.87 | 21.79 | 24.66 | 2.466 | 3.699 | 6.165 | SATAIR |  | N
D9551002200595 | 22 | FABRICATION | 6939600100 6944100100 | Qté 1 Qté 1 | NON | NB3762P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201395 | 22 | FABRICATION | 6939600100 6944100100 | Qté 1 Qté 1 | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002200495 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201495 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | NR6980P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201095 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201195 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | NB4371P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR | IS0032080M | N
S9251279400055 | 22 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279400054 | 22 | FABRICATION | 6800800300 6808100400 6839605100 6827214800 | Qté 2 Qté 1 Qté 1 Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9551002200895 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | NR1727P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002200295 | 22 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201295 | 22 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
S9251279400051 | 22 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279400052 | 22 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9551002200995 | 22 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9550002201695 | 22 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9251110700000 | 22 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9251527800000 | 22 | FABRICATION | N/A | N/A | NON | NB04007P | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551002201595 | 22 | FABRICATION | 6939600100 6944100100 | Qté 1 Qté 1 | NON | NB02135P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
D9551002201695 | 22 | FABRICATION | 6939600100 6944100100 | Qté 1 Qté 1 | NON | NB06482P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
S9251279500054 | 23 | FABRICATION | 6839605100 | Qté 1 | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279500051 | 23 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279500052 | 23 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251171600751 | 23 | FABRICATION | N/A | N/A | OUI | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279500055 | 23 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9251513300000 | 23 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
S9251279600055 | 24 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279600054 | 24 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279600051 | 24 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279600052 | 24 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9251513500000 | 24 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
S9251279700055 | 25 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279700054 | 25 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279700051 | 25 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279700052 | 25 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9251740300000 | 25 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
S9251279800055 | 26 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279800054 | 26 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279800051 | 26 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279800052 | 26 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279900051 | 27 | FABRICATION | 6839605200 | Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9550002700195 | 27 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 6.1466 | 0 | 0 | 0 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
S9251279900056 | 27 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279900055 | 27 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251279900054 | 27 | FABRICATION | 6839605200 | Qté 1 | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9550002700196 | 27 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 6.1466 | 0 | 0 | 0 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
D9551002700295 | 27 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 6.1466 | 0 | 0 | 0 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
S9251279900052 | 27 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9551070000195 | 27 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 6.5066 | 0.36 | 0 | 0.36 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
D9251587700000 | 27 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551002700595 | 27 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 6.5066 | 0.36 | 0 | 0.36 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR | IS0032094M | N
D9551002700495 | 27 | FABRICATION | N/A | N/A | NON | NB03483P | SATAIR | COL | 6.3516 | 0.205 | 0 | 0.205 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
D9551002700695 | 27 | FABRICATION | N/A | N/A | NON | NB03010P | SATAIR | COL | 6.3516 | 0.205 | 0 | 0.205 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR | IS0032097M | N
S9251279900057 | 27 | FABRICATION | 6839605200 | Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280000055 | 28 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280000054 | 28 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9550002847395 | 28 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | 2.8656 | 0 | 0 | 0 | 0.21 | 2.0825 | 2.2925 | 0.22925 | 0.34387 | 0.57312 | STELIA |  | N
S9251280000051 | 28 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280000052 | 28 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280100055 | 29 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280100054 | 29 | FABRICATION | 6808101600 | Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280100000 | 29 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280100051 | 29 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280100052 | 29 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9251606900000 | 30 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
MB035ACAAAAC | 31 | FABRICATION | 6M90080100 | Qté 1 | OUI | TBD | SATAIR | COL | 5.536 | 0.36 | 0 | 0.36 | 1.372 | 2.7688 | 4.1408 | 0.41408 | 0.62112 | 1.0352 | AD&S | IS0032197M | N | OK
S9251280200055 | 34 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280200054 | 34 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280200051 | 34 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251280200052 | 34 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9550003494095 | 34 | FABRICATION | N/A | N/A | OUI | RR0940C | STELIA | COL | 5.3581 | 0.205 | 0 | 0.205 | 0.36 | 3.7625 | 4.1225 | 0.41225 | 0.61838 | 1.0306 | STELIA | IS0032230M | N
S9550003461595 | 34 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | 5.3581 | 0.205 | 0 | 0.205 | 0.36 | 3.7625 | 4.1225 | 0.41225 | 0.61838 | 1.0306 | STELIA |  | N
S9550003456395 | 34 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | 5.3581 | 0.205 | 0 | 0.205 | 0.36 | 3.7625 | 4.1225 | 0.41225 | 0.61838 | 1.0306 | STELIA |  | N
MB136ABAAAAC | 34 | FABRICATION | 6M90079100 | Qté 1 | OUI | MB2030D | SATAIR | COL | 4.2702 | 0.205 | 0 | 0.205 | 1.1074 | 2.1448 | 3.2522 | 0.32522 | 0.48783 | 0.81305 | AD&S | IS0032208M | N | OK
D9251537400000 | 35 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
MB135ABAAAAC | 39 | FABRICATION | 6M90080300 | Qté 1 | OUI | MB2038D | SATAIR | COL | 5.68 | 0.205 | 0 | 0.205 | 2.38 | 2 | 4.38 | 0.438 | 0.657 | 1.095 | AD&S | IS0032207M | O | OK
D9550004000195 | 40 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9551004000195 | 40 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9551004000196 | 40 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9251519600000 | 40 | FABRICATION | N/A | N/A | NON | NB05834P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551004000295 | 40 | FABRICATION | N/A | N/A | NON | NB06767P | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9551004000395 | 40 | FABRICATION | N/A | N/A | NON | NB04112P | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9551004000495 | 40 | FABRICATION | N/A | N/A | NON | NB07003P | SATAIR | COL | 15.0574 | 0.205 | 0 | 0.205 | 1.3171 | 10.5649 | 11.8819 | 1.1882 | 1.7823 | 2.9705 | SATAIR |  | N
D9551004100195 | 41 | FABRICATION | 6939600700 | Qté 3 | NON | NB05635P | SATAIR | COL | 10.2436 | 0.51 | 0 | 0.51 | 0.9856 | 6.8013 | 7.7869 | 0.77869 | 1.168 | 1.9467 | SATAIR |  | N
D9551004500395 | 45 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 16.5903 | 0.205 | 0 | 0.205 | 1.1844 | 11.9238 | 13.1082 | 1.3108 | 1.9662 | 3.2771 | SATAIR |  | N
D9551004500495 | 45 | FABRICATION | N/A | N/A | NON | NB07663 | SATAIR | COL | 16.5903 | 0.205 | 0 | 0.205 | 1.1844 | 11.9238 | 13.1082 | 1.3108 | 1.9662 | 3.2771 | SATAIR |  | N
MB041ACAAAAE | 48 | FABRICATION | 6M90080000 | Qté 1 | OUI | MB2052D | SATAIR | COL | 3.905 | 0.205 | 0 | 0.205 | 0.84 | 2.12 | 2.96 | 0.296 | 0.444 | 0.74 | AD&S | IS0032204M | N | NA
D9251513900000 | 48 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
MB041ACAAAAB | 48 | FABRICATION | 6M90080000 | Qté 1 | OUI | MB2052D | SATAIR | COL | 3.905 | 0.205 | 0 | 0.205 | 0.84 | 2.12 | 2.96 | 0.296 | 0.444 | 0.74 | AD&S | IS0032203M | N | NA
MB042ACABAAA | 49 | FABRICATION | 6M90079500 | Qté 1 | OUI | MB2008D | SATAIR | COL | 3.1925 | 0.205 | 0 | 0.205 | 0.64 | 1.75 | 2.39 | 0.239 | 0.3585 | 0.5975 | AD&S | IS0032206M | O | NA
D9251514300000 | 50 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551005100295 | 51 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.866 | 0.205 | 0 | 0.205 | 0.6018 | 3.127 | 3.7288 | 0.37288 | 0.55932 | 0.9322 | SATAIR |  | N
D9550005100395 | 51 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.866 | 0.205 | 0 | 0.205 | 0.6018 | 3.127 | 3.7288 | 0.37288 | 0.55932 | 0.9322 | SATAIR |  | N
MB043ABAAAAB | 51 | FABRICATION | N/A | N/A | OUI | MB0080D | SATAIR | COL | 4.3383 | 0.205 | 0 | 0.205 | 1.5272 | 1.7794 | 3.3066 | 0.33066 | 0.49599 | 0.82665 | AD&S | IS0032575M | N | NA
D9551005100395 | 51 | FABRICATION | N/A | N/A | NON | NB07323P | SATAIR | COL | 4.866 | 0.205 | 0 | 0.205 | 0.6018 | 3.127 | 3.7288 | 0.37288 | 0.55932 | 0.9322 | SATAIR |  | N
D9550005400195 | 54 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 3.9921 | 0.205 | 0 | 0.205 | 0.8191 | 2.2106 | 3.0297 | 0.30297 | 0.45445 | 0.75743 | SATAIR |  | N
D9251514500000 | 54 | FABRICATION | N/A | N/A | NON | NB05129P |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551005600195 | 56 | FABRICATION | N/A | N/A | NON | NB4871P | SATAIR | COL | 2.5346 | 0.205 | 0 | 0.205 | 0.4282 | 1.4355 | 1.8637 | 0.18637 | 0.27955 | 0.46593 | SATAIR |  | N
D9551005600495 | 56 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 2.5346 | 0.205 | 0 | 0.205 | 0.4282 | 1.4355 | 1.8637 | 0.18637 | 0.27955 | 0.46593 | SATAIR |  | N
D9550005600295 | 56 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 2.5346 | 0.205 | 0 | 0.205 | 0.4282 | 1.4355 | 1.8637 | 0.18637 | 0.27955 | 0.46593 | SATAIR |  | N
D9551005600695 | 56 | FABRICATION | N/A | N/A | NON | NB02155 | SATAIR | COL | 2.5346 | 0.205 | 0 | 0.205 | 0.4282 | 1.4355 | 1.8637 | 0.18637 | 0.27955 | 0.46593 | SATAIR |  | N
D9550006000295 | 60 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006000295 | 60 | FABRICATION | 6963455500 6963455400 | Qté 1 Qté 1 | NON | NB6251P | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006000195 | 60 | FABRICATION | 6963402800 6963403000 | Qté 1 Qté 1 | NON | NB01707P | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR | IS0032114M | N
D9550006100295 | 61 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006100295 | 61 | FABRICATION | 6963455500 6963455400 | Qté 1 Qté 1 | NON | TBD | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006100195 | 61 | FABRICATION | 6963402800 6963403000 | Qté 1 Qté 1 | NON | NB01707P | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR | IS0032120M | N
D9550006200295 | 62 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 2.5359 | 0.205 | 0 | 0.205 | 0.5444 | 1.3203 | 1.8647 | 0.18647 | 0.2797 | 0.46618 | SATAIR |  | N
D9551006200295 | 62 | FABRICATION | 6963455500 6963455400 6963403400 | Qté 1 Qté 1 Qté 1 | NON | TBD | SATAIR | COL | 2.5359 | 0.205 | 0 | 0.205 | 0.5444 | 1.3203 | 1.8647 | 0.18647 | 0.2797 | 0.46618 | SATAIR |  | N
D9551006200195 | 62 | FABRICATION | 6963402800 6963403000 6963403400 | Qté 1 Qté 1 Qté 1 | NON | NB01707P | SATAIR | COL | 2.5359 | 0.205 | 0 | 0.205 | 0.5444 | 1.3203 | 1.8647 | 0.18647 | 0.2797 | 0.46618 | SATAIR | IS0032126M | N
S9550006345795 | 63 | FABRICATION | N/A | N/A | OUI | RR0457C | STELIA | COL | 5.1269 | 0.205 | 0 | 0.205 | 0.4375 | 3.5 | 3.9375 | 0.39375 | 0.59062 | 0.98438 | STELIA | IS0032232M | N
S9550006376895 | 63 | FABRICATION | N/A | N/A | OUI | RB0768C | STELIA | COL | 5.1269 | 0.205 | 0 | 0.205 | 0.4375 | 3.5 | 3.9375 | 0.39375 | 0.59062 | 0.98438 | STELIA |  | N
S9251282200056 | 101 | FABRICATION | 6839605400 6839315000 | Qté 1 Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251282200054 | 101 | FABRICATION | 6839605400 6839315000 | Qté 1 Qté 1 | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251282200055 | 101 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251282200052 | 101 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251282200051 | 101 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9251282200053 | 101 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9550010801096 | 108 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9550010801295 | 108 | FABRICATION | 6963469200 | Qté 1 | NON | NB3526P | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR | IS0032586M | O
D9550010802195 | 108 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9550010802095 | 108 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9550010800996 | 108 | FABRICATION | 6963403800 | Qté 1 | NON | NB01424P | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR | IS0032069M | N
D9550010801495 | 108 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9251504300000 | 108 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551010800195 | 108 | FABRICATION | N/A | N/A | NON | NR01887P | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9251524300000 | 108 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9550010802795 | 108 | FABRICATION | 6963469200 | Qté 1 | NON | NB03718P | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
D9550010802895 | 108 | FABRICATION | 6963469200 | Qté 1 | NON | NB05045P | SATAIR | COL | 10.3374 | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR |  | N
S9251282400051 | 110 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9550011049395 | 110 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9110011049395 | 110 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9550011100195 | 111 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 2.1244 | 0 | 0 | 0 | 0.4933 | 1.2062 | 1.6995 | 0.16995 | 0.25493 | 0.42488 | SATAIR |  | N
S9251282700051 | 114 | FABRICATION | N/A | N/A | NON | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9551011600195 | 116 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 1.955 | 0.205 | 0 | 0.205 | 0.48 | 0.92 | 1.4 | 0.14 | 0.21 | 0.35 | SATAIR | IS0032594M | N
D9550011700295 | 117 | FABRICATION | N/A | N/A | NON | NB5457P | SATAIR | COL | 4.9737 | 0.205 | 0 | 0.205 | 0.4025 | 3.4125 | 3.815 | 0.3815 | 0.57225 | 0.95375 | SATAIR | IS0032071M | N
D9551011700195 | 117 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.9737 | 0.205 | 0 | 0.205 | 0.4025 | 3.4125 | 3.815 | 0.3815 | 0.57225 | 0.95375 | SATAIR |  | N
D9551060000195 | 117 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551011700196 | 117 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.9737 | 0.205 | 0 | 0.205 | 0.4025 | 3.4125 | 3.815 | 0.3815 | 0.57225 | 0.95375 | SATAIR |  | N
D9550011900195 | 119 | FABRICATION | 6963382700 | Qté 1 | NON | NR1624P | SATAIR | COL | 4.4362 | 0.205 | 0 | 0.205 | 0.6853 | 2.6997 | 3.385 | 0.3385 | 0.50775 | 0.84625 | SATAIR |  | N
D9550011900295 | 119 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.4362 | 0.205 | 0 | 0.205 | 0.6853 | 2.6997 | 3.385 | 0.3385 | 0.50775 | 0.84625 | SATAIR |  | N
D9551011900195 | 119 | FABRICATION | N/A | N/A | NON | NR01790P | SATAIR | COL | 4.4362 | 0.205 | 0 | 0.205 | 0.6853 | 2.6997 | 3.385 | 0.3385 | 0.50775 | 0.84625 | SATAIR |  | N
D9551013000195 | 130 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 6.8063 | 0.36 | 0 | 0.36 | 0.7152 | 4.4418 | 5.157 | 0.5157 | 0.77356 | 1.2893 | SATAIR |  | N
D9251505100000 | 130 | FABRICATION | N/A | N/A | NON | TBD |  | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9550013000195 | 130 | FABRICATION | N/A | N/A | NON | NB04660P | SATAIR | COL | 6.8063 | 0.36 | 0 | 0.36 | 0.7152 | 4.4418 | 5.157 | 0.5157 | 0.77356 | 1.2893 | SATAIR |  | N
D9551013100295 | 131 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 6.8063 | 0.36 | 0 | 0.36 | 0.7152 | 4.4418 | 5.157 | 0.5157 | 0.77356 | 1.2893 | SATAIR |  | N
MD501-311101-01A | 265 | FABRICATION | H72362730101 ABS1643ACSB007 (Dépannage) 6V90061800 (Dépannage) | Qté 1 Qté 1 Qté 1 | OUI | N/A | AIS | COL | 0 | 0.205 | 0 | 0.205 | 0 | 0 | 1.16 | 0.23 | 0.15 | 0.38 | AIS |  | N
MD501-311101-01B | 265 | FABRICATION | H72362730101 ABS1643ACSB007 (Dépannage) SCI535B5F48X05N (Dépannage) | Qté 1 Qté 1 Qté 1 | OUI | N/A | AIS | COL | 0 | 0.205 | 0 | 0.205 | 0 | 0 | 1.16 | 0.23 | 0.15 | 0.38 | AIS | IS0032603M | N
D9551030100195 | 301 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.6247 | 0.36 | 0 | 0.36 | 0.7196 | 4.2922 | 5.0118 | 0.50118 | 0.75177 | 1.253 | SATAIR |  | N
D9551030100295 | 301 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.6247 | 0.36 | 0 | 0.36 | 0.7196 | 4.2922 | 5.0118 | 0.50118 | 0.75177 | 1.253 | SATAIR |  | N
D9551030100296 | 301 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.6247 | 0.36 | 0 | 0.36 | 0.7196 | 4.2922 | 5.0118 | 0.50118 | 0.75177 | 1.253 | SATAIR |  | N
WF406ABAAAAB | 313 | FABRICATION | 6V90079000 | Qté 1 | NON | VB0268D | SATAIR | COL | 5.3225 | 0.51 | 0 | 0.51 | 0.91 | 2.94 | 3.85 | 0.385 | 0.5775 | 0.9625 | SATAIR | IS0032176M | N
WF407ABAAAAB | 314 | FABRICATION | 6V90079100 | Qté 1 | NON | VB0197D | SATAIR | COL | 5.3444 | 0.51 | 0 | 0.51 | 0.91 | 2.9575 | 3.8675 | 0.38675 | 0.58013 | 0.96688 | SATAIR |  | N
WF408ADAAAAC | 317 | FABRICATION | 6V00205900 | Qté 1 | NON | VB0020D | SATAIR | COL | 4.0687 | 0 | 0 | 0 | 0.7525 | 2.5025 | 3.255 | 0.3255 | 0.48825 | 0.81375 | SATAIR |  | N
WF408ACABAAB | 317 | FABRICATION | 6V00205900 | Qté 1 | NON | VB0043D | SATAIR | COL | 4.0687 | 0 | 0 | 0 | 0.7525 | 2.5025 | 3.255 | 0.3255 | 0.48825 | 0.81375 | SATAIR |  | N
WF409ACABAAB | 318 | FABRICATION | 6V90079500 | Qté 1 | NON | V00043D | SATAIR | COL | 4.0687 | 0 | 0 | 0 | 0.7525 | 2.5025 | 3.255 | 0.3255 | 0.48825 | 0.81375 | SATAIR |  | N
D9550040300395 | 403 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 2.1871 | 0.205 | 0 | 0.205 | 0.4263 | 1.1594 | 1.5857 | 0.15857 | 0.23786 | 0.39643 | SATAIR |  | N
A9550041272695 | 412 | FABRICATION | 6504420600 6504420800 6574819100 | Qté 1 Qté 1 Qté 1 | NON | TBD | SATAIR | COL | #VALUE! | Manque USER | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
A95500419000AA | 419 | FABRICATION | 6599807700 6504421000 6586901800 6504420500 6574907800 | Qté 1 Qté 1 Qté 1 Qté 1 Qté 1 | NON | RR0827Z | SATAIR | COL | 9.5437 | 0.36 | 0 | 0.36 | 1.994 | 5.353 | 7.347 | 0.7347 | 1.102 | 1.8367 | SATAIR |  | N
A95500423000AA | 423 | FABRICATION | 6574926600 | Qté 1 | NON | RR0827Z | SATAIR | COL | 16.8675 | 0.205 | 0 | 0.205 | 2.73 | 10.6 | 13.33 | 1.333 | 1.9995 | 3.3325 | SATAIR |  | N
A95500426000AB | 426 | FABRICATION | 6574929100 | 1 | NON | RR0829Z | SATAIR | COL | 28.18 | 0.205 | 0 | 0.205 | 3.16 | 19.22 | 22.38 | 2.238 | 3.357 | 5.595 | SATAIR |  | N
A9550042972695 | 429 | FABRICATION | 6539607700 6539603600 6574907200 | Qté 1 Qté 2 Qté 1 | NON | RR0726Z | SATAIR | COL | 37.8115 | 0 | 0 | 0 | 2.8839 | 27.3653 | 30.2492 | 3.0249 | 4.5374 | 7.5623 | SATAIR | IS0032613M | N
A9550043077195 | 430 | FABRICATION | 6574861800 | Qté 1 | NON | RR0759Z | SATAIR | COL | 51.5769 | 0 | 0 | 0 | 2.1791 | 39.0824 | 41.2615 | 4.1261 | 6.1892 | 10.3154 | SATAIR |  | N
D9551045200195 | 452 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9550045300195 | 453 | FABRICATION | N/A | N/A | NON | NR3171P | SATAIR | COL | 1.929 | 0.205 | 0 | 0.205 | 0.3978 | 0.9814 | 1.3792 | 0.13792 | 0.20688 | 0.3448 | SATAIR |  | N
D9551045300195 | 453 | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 1.929 | 0.205 | 0 | 0.205 | 0.3978 | 0.9814 | 1.3792 | 0.13792 | 0.20688 | 0.3448 | SATAIR |  | N
A9551046300196 | 463 | FABRICATION | N/A | N/A | NON | RR9463C | SATAIR | COL | 4.3195 | 0.205 | 0 | 0.205 | 1.1783 | 2.1133 | 3.2916 | 0.32916 | 0.49374 | 0.8229 | SATAIR |  | N
D9551050000195 | 500 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.9729 | 0.66 | 0 | 0.66 | 0.7581 | 4.2922 | 5.0503 | 0.50503 | 0.75755 | 1.2626 | SATAIR |  | N
D9551050000295 | 500 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.9729 | 0.66 | 0 | 0.66 | 0.7581 | 4.2922 | 5.0503 | 0.50503 | 0.75755 | 1.2626 | SATAIR |  | N
D9551050000296 | 500 | FABRICATION | N/A | N/A | NON | NB04436P | SATAIR | COL | 6.9729 | 0.66 | 0 | 0.66 | 0.7581 | 4.2922 | 5.0503 | 0.50503 | 0.75755 | 1.2626 | SATAIR |  | N
A9550051000296 | 510 | FABRICATION | 6530207600 | Qté 1 | NON | N/A | SATAIR | COL | 4.4396 | 0 | 0 | 0 | 1.0708 | 2.4809 | 3.5517 | 0.35517 | 0.53275 | 0.88793 | SATAIR | IS0031992M | N
A9550051000196 | 510 | FABRICATION | 6530207600 | Qté 1 | NON | N/A | SATAIR | COL | 4.4396 | 0 | 0 | 0 | 1.0708 | 2.4809 | 3.5517 | 0.35517 | 0.53275 | 0.88793 | SATAIR | IS0032621M | N
A9550051000195 | 510 | FABRICATION | 6530207600 | Qté 1 | NON | N/A | SATAIR | COL | 4.4396 | 0 | 0 | 0 | 1.0708 | 2.4809 | 3.5517 | 0.35517 | 0.53275 | 0.88793 | SATAIR |  | N
WF413SBAAAAA | 511 | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 1.7366 | 0.51 | 0 | 0.51 | 0.459 | 0.5223 | 0.9813 | 0.09813 | 0.14719 | 0.24533 | SATAIR |  | N
WF413SBAAAAB | 511 | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 1.7366 | 0.51 | 0 | 0.51 | 0.459 | 0.5223 | 0.9813 | 0.09813 | 0.14719 | 0.24533 | SATAIR |  | N
WF417AFACAAE | 517 | FABRICATION | 6V01965900 | Qté 1 | NON | VB0044D | SATAIR | COL | 2.3706 | 0.205 | 0 | 0.205 | 0.7175 | 1.015 | 1.7325 | 0.17325 | 0.25987 | 0.43312 | SATAIR | IS0032184M | N
WF418AFACAAE | 518 | FABRICATION | 6V01448300 | Qté 1 | NON | VB0204D | SATAIR | COL | 2.3706 | 0.205 | 0 | 0.205 | 0.7175 | 1.015 | 1.7325 | 0.17325 | 0.25987 | 0.43312 | SATAIR | IS0032185M | N
S9251023300100 | 520 | FABRICATION | N/A | N/A | OUI | TBD | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
WF435ADAAAAC | 613 | FABRICATION | N/A | N/A | NON | VB0251D | SATAIR | COL | 2.3925 | 0.205 | 0 | 0.205 | 0.525 | 1.225 | 1.75 | 0.175 | 0.2625 | 0.4375 | SATAIR |  | N
S9252309900051 | 702 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252309900055 | 702 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252309900054 | 702 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252309900053 | 702 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9550081192795 | 811 | FABRICATION | 6853820100 | Qté 1 | OUI | RR0927C | STELIA | COL | 5.1152 | 0.36 | 0 | 0.36 | 0.706 | 3.0982 | 3.8042 | 0.38042 | 0.57063 | 0.95105 | STELIA |  | N
S9251285300000 | 910 | FABRICATION | N/A | N/A | NON | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
A320EL050000-EPA | 9000 | FABRICATION | N/A | N/A | OUI | N/A | LATECOERE | COL | 3.7675 | 0.205 | 0 | 0.205 | 0.35 | 2.5 | 2.85 | 0.285 | 0.4275 | 0.7125 | LATECOERE |  | N
D925R445000200 | 9205 | FABRICATION | D925R445120000 | Qté 1 | OUI | NA | ST Engineering | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STE |  | N
L9297715001000 | 7150VB Harness for A380 Customized harness AIG | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
A27912401006C10 | CONTROL UNIT-HP FUEL | FABRICATION | 6595684900 | Qté 1 | NON | N/A | SATAIR | COL | 0.75998 | 0 | 0.0006 | 0.0006 | 0.3627 | 0.2448 | 0.6075 | 0.06075 | 0.091125 | 0.15188 | SATAIR |  | N
A27912401006C11 | CONTROL UNIT-HP FUEL | FABRICATION | 6595684900 | Qté 1 | NON | N/A | SATAIR | COL | 0.75998 | 0 | 0.0006 | 0.0006 | 0.3627 | 0.2448 | 0.6075 | 0.06075 | 0.091125 | 0.15188 | SATAIR |  | N
A27912401007C10 | CONTROL UNIT-HP FUEL | FABRICATION | 6595685000 | Qté 1 | NON | N/A | SATAIR | COL | 0.75998 | 0 | 0.0006 | 0.0006 | 0.3627 | 0.2448 | 0.6075 | 0.06075 | 0.091125 | 0.15188 | SATAIR | IS0032628M | N
V9251241700095 | BUNDLE | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 1.305 | 0.205 | 0 | 0.205 | 0 | 1 | 1 | 0.1 | 0 | 0.1 | SATAIR |  | N
V9251243600095 | BUNDLE | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 1.305 | 0.205 | 0 | 0.205 | 0 | 1 | 1 | 0.1 | 0 | 0.1 | SATAIR |  | N
D9000095478695 | BUNDLE | FABRICATION | N/A | N/A | NON | NA | SATAIR | NA | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9000095029695 | BUNDLE | FABRICATION | N/A | N/A | NON | NA | SATAIR | NA | #VALUE! | Fibre optique | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
V9251243600096 | BUNDLE | FABRICATION | N/A | N/A | NON |  | SATAIR | COL | 1.305 | 0.205 | 0 | 0.205 | 0 | 1 | 1 | 0.1 | 0 | 0.1 | SATAIR |  | N
D9000095493095 | BUNDLE | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 14.6881 | 0.65 | 1.7874 | 2.4374 | 0 | 11.137 | 11.137 | 1.1137 | 0 | 1.1137 | SATAIR |  | N
S9291306500000 | CÂBLE | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 1.305 | 0.205 | 0 | 0.205 | 0 | 1 | 1 | 0.1 | 0 | 0.1 | STELIA | IS0032228M | O
S9110139700195 | CÂBLE | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 1.65 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0.15 | 0 | 0.15 | STELIA |  | N
S9291302300100 | CÂBLE | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9110118700395 | CÂBLE | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 1.305 | 0.205 | 0 | 0.205 | 0 | 1 | 1 | 0.1 | 0 | 0.1 | STELIA |  | N
S9110118700295 | CÂBLE | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 1.074 | 0.205 | 0 | 0.205 | 0 | 0.79 | 0.79 | 0.079 | 0 | 0.079 | STELIA |  | N
S9110187500195 | Câble 2431-2530 pour MSN 0717 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | STELIA |  | N
S9110104500195 | CABLE COAXIAL | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 1.019 | 0.1866 | 0.006 | 0.1926 | 0 | 0.7513 | 0.7513 | 0.07513 | 0 | 0.07513 | STELIA | IS0032220M | N
S9110104500295 | CABLE COAXIAL | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 1.019 | 0.1866 | 0.006 | 0.1926 | 0 | 0.7513 | 0.7513 | 0.07513 | 0 | 0.07513 | STELIA |  | N
A27912401007C11 | CONTROL UNIT-HP FUEL | FABRICATION | 6595685000 | Qté 1 | NON | N/A | SATAIR | COL | 0.75998 | 0 | 0.0006 | 0.0006 | 0.3627 | 0.2448 | 0.6075 | 0.06075 | 0.091125 | 0.15188 | SATAIR | IS0032635M | N
S9251585900000 | ENS. EQUIPEMENT 61VU | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 21.1469 | 0.3 | 0 | 0.3 | 1.6625 | 15.015 | 16.6775 | 1.6678 | 2.5016 | 4.1694 | STELIA |  | N
S9252326800051 | ENS. ÉQUIPEMENT 84VU | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9252336100051 | ENS. ÉQUIPEMENT 85VU | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
S9110157200196 | FAISCEAU | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 0.975 | 0.205 | 0 | 0.205 | 0 | 0.7 | 0.7 | 0.07 | 0 | 0.07 | STELIA |  | N
S9110169500395 | FAISCEAU | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | STELIA |  | N
S9110302500195 | FAISCEAU | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 0.8 | 0.25 | 0 | 0.25 | 0 | 0.5 | 0.5 | 0.05 | 0 | 0.05 | STELIA |  | N
A9000095408295 | Faisceau 600VU | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
A9000095408895 | Faisceau 600VU | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
A9000095408395 | Faisceau 600VU | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
A9000095408195 | Faisceau 600VU | FABRICATION | N/A | N/A | NON | NA | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
S9110129300295 | FAISCEAU AOG | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | STELIA |  | N
S9110125900195 | FAISCEAU GENERATION (ATR42) | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 0.755 | 0.205 | 0 | 0.205 | 0 | 0.5 | 0.5 | 0.05 | 0 | 0.05 | STELIA |  | N
S9110126000195 | FAISCEAU GENERATION (ATR72) | FABRICATION | N/A | N/A | OUI | N/A | STELIA | NA | 0.83 | 0.205 | 0 | 0.205 | 0 | 0.5 | 0.5 | 0.05 | 0.075 | 0.125 | STELIA |  | N
F9000095023795 | FAISCEAU STRAP-ON | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 2.2 | 0 | 0 | 0 | 0 | 2 | 2 | 0.2 | 0 | 0.2 | SATAIR |  | N
F9000095023895 | FAISCEAU STRAP-ON | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 2.5 | 0 | 0 | 0 | 0 | 2 | 2 | 0.2 | 0.3 | 0.5 | SATAIR |  | N
1323L1000010 | FDCP-L1 | FABRICATION | N/A | N/A | N/A | N/A | LATECOERE | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | LATECOERE |  | N
1288L3000010 | FDVESS-L3 | FABRICATION | N/A | N/A | NON | N/A | LATECOERE | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | LATECOERE | IS0033482M | N
1288L4000010 | FDVESS L4 | FABRICATION | N/A | N/A | NON | N/A | LATECOERE | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | LATECOERE | IS0033483M | N
F7161001200001 | HARNAIS 1 P2T2 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 2.7953 | 0.1866 | 0.0063 | 0.1929 | 0 | 2.0819 | 2.0819 | 0.20819 | 0.31228 | 0.52048 | SATAIR |  | N
F7161001300001 | HARNAIS 2 P2T2 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 4.0244 | 0.1866 | 0.0042 | 0.1908 | 0 | 3.0669 | 3.0669 | 0.30669 | 0.46003 | 0.76672 | SATAIR |  | N
V9251207600295 | HARNESS 5R-6R 1000VU | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 4.58 | 0.205 | 0 | 0.205 | 0 | 3.5 | 3.5 | 0.35 | 0.525 | 0.875 | SATAIR |  | N
L9297725700000 | HARNESS ASSY CABLE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
B2352101700200 | JACK | FABRICATION | 6574872200 | Qté 1 | NON | N/A | SATAIR | COL | 2.7107 | 0 | 0 | 0 | 0.8512 | 1.3174 | 2.1686 | 0.21686 | 0.32529 | 0.54215 | SATAIR |  | N
A0041114100095 | JACK | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 2.7107 | 0 | 0 | 0 | 0.8512 | 1.3174 | 2.1686 | 0.21686 | 0.32529 | 0.54215 | SATAIR | IS0032651M | N
B23521038000D00 | JACK | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 2.7107 | 0 | 0 | 0 | 0.8512 | 1.3174 | 2.1686 | 0.21686 | 0.32529 | 0.54215 | SATAIR | IS0063322M | N
F7161001100001 | JACK ASSY | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 1.878 | 0.1866 | 0 | 0.1866 | 0 | 1.5376 | 1.5376 | 0.15376 | 0 | 0.15376 | SATAIR |  | N
D5211034722800 | PLACARD | FABRICATION | N/A | N/A | NA | NA | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D5211034722900 | PLACARD | FABRICATION | N/A | N/A | NA | NA | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
M1133306800000 | LABEL PLATE 1115VU | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
M1133301800000 | LABEL PLATE 1155VU | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F0003008100300 | LEAD-BONDING | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.50538 | 0.205 | 0.0025 | 0.2075 | 0 | 0.2383 | 0.2383 | 0.02383 | 0.035745 | 0.059575 | SATAIR | IS0032149M | N
D9000095029495 | OPTICAL FIBER | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR | IS0032047M | N
D9550303100195 | OPTICAL FIBER | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9000095028495 | Optical Fiber 3435-0153 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR | IS0032654M | N
D9000095028595 | Optical Fiber 3435-0154 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
S9550061144495 | 61 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | STELIA |  | N
S9251486100052 | 120 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
D9100095010095 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010295 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010395 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010495 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010595 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010695 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010795 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095010895 | PLACARD SET | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.205 | 0.205 | 0 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D9100095600395 | PLACARD SET | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0.205 |  | 0 | 0 | 0 | 0 | 0.205 | 0.0205 | 0 | 0.0205 | SATAIR | IS0032064M | N
D9251719400095 | PLATE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 |  | 0 | 0 | 0 | 0 | 3.1372 | 0.52 | 0.2 | 0.72 | SATAIR | IS0030400M | O
F9252020200000 | PLATE ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0.19679 | 0 | 0 | 0 | 0.1789 | 0 | 0.1789 | 0.01789 | 0 | 0.01789 | SATAIR | IS0032657M | N
F9252008100000 | PLATE ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0.52712 | 0 | 0 | 0 | 0.4792 | 0 | 0.4792 | 0.04792 | 0 | 0.04792 | SATAIR |  | N
A92529726000D00 | PLATINE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
S9550096235395 | 962 | FABRICATION | N/A | N/A | OUI | TBD | STELIA | COL | #VALUE! | Manque USER | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | STELIA |  | N
F0003003000000 | PROTECTION CAP | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0.33048 | 0 | 0.0025 | 0.0025 | 0 | 0.1118 | 0.1118 | 0.01118 | 0 | 0.01118 | SATAIR | IS0032144M | N
F0003008100000 | WIRE-BONDING | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.46803 | 0.205 | 0.0009 | 0.2059 | 0 | 0.2383 | 0.2383 | 0.02383 | 0 | 0.02383 | SATAIR | IS0032145M | N
F0003008101000 | WIRE-BONDING | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.46743 | 0.205 | 0.0003 | 0.2053 | 0 | 0.2383 | 0.2383 | 0.02383 | 0 | 0.02383 | SATAIR |  | N
F0003008100200 | WIRE-BONDING | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.47063 | 0.205 | 0.0035 | 0.2085 | 0 | 0.2383 | 0.2383 | 0.02383 | 0 | 0.02383 | SATAIR | IS0032147M | N
D9000095477995 | BUNDLE | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 24.3371 | 0.492 | 1.239 | 1.731 | 0 | 20.551 | 20.551 | 2.0551 | 0 | 2.0551 | SATAIR | IS0032050M | N
F9295002200400 | HARNESS | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9295002400000 | HARNESS | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9295002500200 | HARNESS | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249260410800 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249270401700 | CONDUIT ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249265310100 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249265410400 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249260501800 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249271110500 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249263004500 | CONDUIT ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249265710700 | CONDUIT ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9550006300295 | 63 | FABRICATION | 6963403900 | Qté 1 | NON | NB05045P | SATAIR | COL | 3.9637 | 0.205 | 0 | 0.205 | 0.5367 | 2.4703 | 3.007 | 0.3007 | 0.45105 | 0.75175 | SATAIR |  | N
A9550042572695 | 425 | FABRICATION | 6508101300 6508101400 6508101500 6508101600 6508101700 6539608600 6595663900 | Qté 1 Qté 1 Qté 1 Qté 1 Qté 1 Qté 2 Qté 1 | NON | RR0726Z | SATAIR | COL | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
WF408AEAAAAC | 317 | FABRICATION | 6V00205900 | Qté 1 | NON | VB0020D | SATAIR | COL | 4.0687 | 0 | 0 | 0 | 0.7525 | 2.5025 | 3.255 | 0.3255 | 0.48825 | 0.81375 | SATAIR |  | N
A9550042872695 | 428 | FABRICATION | 6574823700 | Qté 1 | NON | RR0726Z | SATAIR | COL | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
A95500432000AB | 432 | FABRICATION | 6584513300 6584516400 6574803900 6595665200 | Qté 1 Qté 2 Qté 1 Qté 1 | NON | RR0851Z | SATAIR | COL | 23.9806 | 0.36 | 0 | 0.36 | 1.6732 | 17.2233 | 18.8965 | 1.8897 | 2.8345 | 4.7241 | SATAIR | IS0031989M | N
A95500435000AA | 435 | FABRICATION | 6527212000 6527211900 6574930800 | Qté 2 Qté 4 Qté 1 | NON | RR0827Z | SATAIR | COL | 8.263 | 0.36 | 0 | 0.36 | 1.74 | 4.5824 | 6.3224 | 0.63224 | 0.94836 | 1.5806 | SATAIR |  | N
S9550003445795 | 34 | FABRICATION | 6863437600 | Qté 1 | NON | RB0457C | STELIA | COL | 5.3581 | 0.205 | 0 | 0.205 | 0.36 | 3.7625 | 4.1225 | 0.41225 | 0.61838 | 1.0306 | STELIA |  | N
F9000095448795 | BUNDLE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 11.4 | 0.4 | 0 | 0.4 | 0 | 10 | 10 | 1 | 0 | 1 | SATAIR |  | N
F9000095447995 | BUNDLE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | #VALUE! | Non fabriqué | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
F9000095448895 | BUNDLE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 11.4 | 0.4 | 0 | 0.4 | 0 | 10 | 10 | 1 | 0 | 1 | SATAIR |  | N
F9000095447895 | BUNDLE | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 10.764 | 0.6 | 0 | 0.6 | 0 | 9.24 | 9.24 | 0.924 | 0 | 0.924 | SATAIR |  | N
A9551040900195 | 409 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | #VALUE! | Manque USER | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
A9551060000195 | 600 | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
S9242302300000 | SUPPORT | FABRICATION | N/A | N/A | NON | TBD | SATAIR | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STELIA |  | N
WG281ABABAAE | 5130VE | FABRICATION | 6V005147000 | Qté 1 | NON | VB0180G | SATAIR | COL | 8.06 | 0.36 | 0 | 0.36 | 1.0325 | 5.1275 | 6.16 | 0.616 | 0.924 | 1.54 | SATAIR |  | N
D9291011200095 | OPTICAL FIBER | FABRICATION | N/A | N/A | NON | N/A | SATAIR | COL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SATAIR |  | N
D925R445000000 | 9205 | FABRICATION | D925R445120000 | Qté 1 | OUI | N/A | ST Engineering | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | STE |  | N
D9251074200200 | COVER ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0.09724 | 0 | 0 | 0 | 0.0884 | 0 | 0.0884 | 0.00884 | 0 | 0.00884 | STE |  | N
D9249183305000 | CONDUIT ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | MEX | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
A95500441000AA | 441 | FABRICATION | 6574820900 | Qté 1 | NON | RR0816Z | SATAIR | COL | 7.2639 | 0.205 | 0 | 0.205 | 0.8267 | 4.8204 | 5.6471 | 0.56471 | 0.84706 | 1.4118 | SATAIR |  | N
F9249270400500 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
MB036ACAAAAC | 32 | FABRICATION | 6M90080200 | Qté 1 | OUI | MB0111D | SATAIR | COL | 6.1419 | 0.36 | 0 | 0.36 | 1.6531 | 2.9724 | 4.6255 | 0.46255 | 0.69382 | 1.1564 | AD&S | IS0032198M | N | OK
MB034ACAEAAA | 25 | FABRICATION | 6M00402600 6M00725800 6M00726300 | Qté 1 Qté 1 Qté 2 | OUI | MB0111D | SATAIR | COL | 2.7338 | 0.205 | 0 | 0.205 | 1.0139 | 1.0091 | 2.023 | 0.2023 | 0.30345 | 0.50575 | AD&S | IS0032196M | N | NA
MB032ADAAAAB | 15 | FABRICATION | 6M90079300 6M00238500 | Qté 1 Qté 1 | OUI | MB0111D | SATAIR | COL | 9.4035 | 0.51 | 0 | 0.51 | 1.4104 | 5.7044 | 7.1148 | 0.71148 | 1.0672 | 1.7787 | AD&S | IS0032194M | N | NA
MB033ADACAAB | 21 | FABRICATION | 6M00724800 6M90079200 | Qté 1 Qté 1 | OUI | MB0111D | SATAIR | COL | 3.0808 | 0.36 | 0 | 0.36 | 0.8095 | 1.3671 | 2.1766 | 0.21766 | 0.32649 | 0.54415 | AD&S | IS0032195M | N | NA
MB037ADAAAAB | 41 | FABRICATION | 6M90079600 | Qté 1 | OUI | MB0111D | SATAIR | COL | 2.0945 | 0.205 | 0 | 0.205 | 0.4817 | 1.0299 | 1.5116 | 0.15116 | 0.22674 | 0.3779 | AD&S | IS0032199M | N | NA
MB038ADAAAAB | 42 | FABRICATION | 6M90079900 | Qté 1 | OUI | MB0111D | SATAIR | COL | 2.0945 | 0.205 | 0 | 0.205 | 0.4817 | 1.0299 | 1.5116 | 0.15116 | 0.22674 | 0.3779 | AD&S | IS0032200M | N | NA
MB040ADAAAAB | 47 | FABRICATION | 6M90079700 | Qté 1 | OUI | MB0111D | SATAIR | COL | 3.905 | 0.205 | 0 | 0.205 | 0.84 | 2.12 | 2.96 | 0.296 | 0.444 | 0.74 | AD&S | IS0032202M | N | NA
MB041ADAAAAB | 48 | FABRICATION | 6M90080000 | Qté 1 | OUI | MB0111D | SATAIR | COL | 3.905 | 0.205 | 0 | 0.205 | 0.84 | 2.12 | 2.96 | 0.296 | 0.444 | 0.74 | AD&S | IS0032205M | N | NA
MB137ADAAAAC | 37 | FABRICATION | 6M90080400 | Qté 1 | OUI | MB0111D | SATAIR | COL | 1.9925 | 0.205 | 0 | 0.205 | 0.48 | 0.95 | 1.43 | 0.143 | 0.2145 | 0.3575 | AD&S | IS0032210M | N | NA
MB031ADAEAAB | 11 | FABRICATION | 6M90110600 6M00635400 | Qté 1 Qté 1 | OUI | MB0111D | SATAIR | COL | 10.2691 | 0.205 | 0 | 0.205 | 1.5899 | 6.4614 | 8.0513 | 0.80513 | 1.2077 | 2.0128 | AD&S | IS0032192M | N | OK
MB039ACAAAAB | 46 | FABRICATION | 6M00097600 6M00122800 6M90079800 | Qté 1 Qté 2 Qté 1 | OUI | MB0111D | SATAIR | COL | 7.2479 | 0.205 | 0 | 0.205 | 1.1197 | 4.5146 | 5.6343 | 0.56343 | 0.84514 | 1.4086 | AD&S | IS0032201M | N | NA
MB136ABAAAAD | 34 | FABRICATION | 6M90079100 | Qté 1 | OUI | MB0111D | SATAIR | COL | 4.2702 | 0.205 | 0 | 0.205 | 1.1074 | 2.1448 | 3.2522 | 0.32522 | 0.48783 | 0.81305 | AD&S | IS0032209M | N | OK
D9551002700195 | 27 | FABRICATION | N/A | N/A | NON | NB09482P | SATAIR | COL | 6.3516 | 0.205 | 0 | 0.205 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
F9249262600800 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
F9249260803400 | CONDUIT | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551004500595 | 45 | FABRICATION | N/A | N/A | NON | NB05869P | SATAIR | COL | 16.5903 | 0.205 | 0 | 0.205 | 1.1844 | 11.9238 | 13.1082 | 1.3108 | 1.9662 | 3.2771 | SATAIR |  | N
1323L1000010A | FDCP-L1 | FABRICATION | N/A | N/A | N/A | N/A | LATECOERE | COL | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | LATECOERE |  | N
D9551002201795 | 22 | FABRICATION | 6939600100 | Qté 1 | NON | NR03524P | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.9198 | 9.6171 | 10.5369 | 1.0537 | 1.5805 | 2.6342 | SATAIR |  | N
A9252282400400 | LEAD-BONDING | FABRICATION | N/A | N/A | NON | TBD | SATAIR | NA | 0.4213 | 0 | 0 | 0 | 0 | 0.383 | 0.383 | 0.0383 | 0 | 0.0383 | SATAIR |  | N
D9551006000395 | 60 | FABRICATION | 6963402800 6963403000 | Qté 1 Qté 1 | NON | NR05122P | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006100395 | 61 | FABRICATION | 6963402800 6963403000 | Qté 1 Qté 1 | NON | NR05122P | SATAIR | COL | 1.8831 | 0.205 | 0 | 0.205 | 0.3963 | 0.9462 | 1.3425 | 0.13425 | 0.20137 | 0.33563 | SATAIR |  | N
D9551006200395 | 62 | FABRICATION | 6963402800 6963403000 6963403400 | Qté 1 Qté 1 Qté 1 | NON | NR05122P | SATAIR | COL | 2.5359 | 0.205 | 0 | 0.205 | 0.5444 | 1.3203 | 1.8647 | 0.18647 | 0.2797 | 0.46618 | SATAIR |  | N
D9551002700795 | 27 | FABRICATION | N/A | N/A | NON | NR06833P | SATAIR | COL | 6.3516 | 0.205 | 0 | 0.205 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR |  | N
D9551011900295 | 119 | FABRICATION | N/A | N/A | NON | NR06833P | SATAIR | COL | 4.4362 | 0.205 | 0 | 0.205 | 0.6853 | 2.6997 | 3.385 | 0.3385 | 0.50775 | 0.84625 | SATAIR |  | N
D9551005400195 | 54 | FABRICATION | 6997012100 | Qté 1 | NON | NR01212P | SATAIR | COL | 3.9921 | 0.205 | 0 | 0.205 | 0.8191 | 2.2106 | 3.0297 | 0.30297 | 0.45445 | 0.75743 | SATAIR | IS0032110M | O
MB032ACAAAAB | 15 | FABRICATION | 6M90079300 6M00238500 | Qté 1 Qté 1 | OUI | MR0069D | SATAIR | COL | 9.4035 | 0.51 | 0 | 0.51 | 1.4104 | 5.7044 | 7.1148 | 0.71148 | 1.0672 | 1.7787 | AD&S | IS0032193M | N | NA
D925R445000400 | 9205 | FABRICATION | D925R445120000 | Qté 1 | OUI | N/A | ST Engineering | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
D9551062000195 | 620 | FABRICATION | N/A | N/A | NON | NR03257P | SATAIR | COL | 1.9704 | 0.205 | 0 | 0.205 | 0.4589 | 0.9534 | 1.4123 | 0.14123 | 0.21185 | 0.35308 | SATAIR |  | N
D9551061900195 | 619 | FABRICATION | N/A | N/A | NON | NR03257P | SATAIR | COL | 1.9681 | 0.205 | 0 | 0.205 | 0.4571 | 0.9534 | 1.4105 | 0.14105 | 0.21158 | 0.35263 | SATAIR |  | N
F9249263300100 | CONDUIT ASSY | FABRICATION | N/A | N/A | NON | N/A | SATAIR | NA | 0 | 0,00 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0 | 0,00 | 0 | SATAIR |  | N
WF406ACAAAAB | 313 | FABRICATION | 6V90079000 | Qté 1 | NON |  | SATAIR | COL | 0 | 0.205 | 0,00 | 0.205 | 0.5 | 3 | 3.5 | 0.35 | 0.525 | 0.875 | SATAIR | IS0032177M | N
V9253120000097 | BUNDLE | FABRICATION | N/A | N/A | NON |  | SATAIR | COL | 0.3744 | 0.1244 | 0.0045 | 0.1289 | 0 | 0.1455 | 0.1455 | 0.1 | 0 | 0.1 | SATAIR |  | N
V9253110000098 | BUNDLE | FABRICATION | N/A | N/A | NON |  | SATAIR | COL | 0.3744 | 0.1244 | 0.0045 | 0.1289 | 0 | 0.1455 | 0.1455 | 0.1 | 0 | 0.1 | SATAIR |  | N
D9551002200395 | 22 | FABRICATION | 6939600100 | Qté 1 | NON |  | SATAIR | COL | 10.745 | 0.205 | 0 | 0.205 | 0.92 | 9.62 | 10.54 | 1.05 | 1.58 | 2.63 | SATAIR |  | N
L9000095410095 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 0 |  |  | 0 |  |  | 0 |  |  | 0 | SATAIR |  | N
L9000095410595 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 0 |  |  | 0 |  |  | 0 |  |  | 0 | SATAIR |  | N
D9000095029295 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 3.61 | 0.2488 | 0.423 | 0.6718 | 0 | 2.9382 | 2.9382 | 0.293 | 0 | 0.293 | SATAIR |  | N
V9253110000096 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 0.2744 | 0.1244 | 0.0045 | 0.1289 | 0 | 0.1455 | 0.1455 | 0.1 | 0 | 0.1 | SATAIR | IS0032170M | N
V9253120000096 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 0.5199 | 0.1244 | 0.0045 | 0.1289 | 0 | 0.1455 | 0.1455 | 0.1 | 0 | 0.1 | SATAIR | IS0032173M | N
D9000095029895 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL |  |  |  | 0 | [5 empty] | 0 | SATAIR |  | N
D9551003000195 | 30 | FABRICATION | 6939600000 6946311800 | Qté 2 Qté 3 | NON |  | SATAIR | COL |  | 0.205 | 0 | 0.205 |  |  | 10.43 | 1.04 | 1.56 | 2.6 | SATAIR |  | N
V9292604200095 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0.1244 | 0.342 | 0.4664 | 0 | 1.3764 | 1.3764 | 0.137 | 0 | 0.137 | SATAIR | IS0059304M | N
V9253110000095B | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | [6 empty] | 0.1455 | 0.01455 | 0 | 0.01455 | SATAIR | IS0063136M | N
V9253120000095A | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0.1866 | 0.3552 | 0.5418 | 0 | 12.1435 | 12.1435 | 1.21 | 0 | 1.21 | SATAIR | IS0059305M | N
V9253110000095A | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0 | 0.0706 | 0.0706 | 0 | 3.2027 | 3.2027 | 0.3202 | 0 | 0.3202 | SATAIR | IS0063329M | N
V9253100000095A | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0 | 0.0411 | 0.0411 | 0 | 3.7333 | 3.7333 | 0.373 | 0 | 0.373 | SATAIR | IS0059357M | N
V9253120000095 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 1.202 | 0 | 0.036 | 0.036 | 0 | 1.06 | 1.06 | 0.106 | 0 | 0.106 | SATAIR |  | N
V9253110000097 | BUNDLE | FABRICATION | NA | NA | NON |  | SATAIR | COL | 1.7735 | 0 | 0.0735 | 0.0735 | 0 | 1.55 | 1.55 | 0.15 | 0 | 0.15 | SATAIR |  | N
F9252035500000 | SHEET ASSY | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.015 | 0 | 0.015 | SATAIR | IS0059353M | N
D9550011700195 | 117 | FABRICATION | 6963467000 | Qté 1 | NON |  | SATAIR | COL |  | 0.205 | 0 | 0 | 0.38 | 3.7 | 4.08 | 0.408 | 0.612 | 1.02 | SATAIR |  | N
S9550006320095 | 63 | FABRICATION | TBD | TBD | NON |  | STELIA | COL |  |  | 0 | 0 | 0.43 | 2.44 | 2.87 | 0.287 | 0.4305 | 0.7175 | STELIA |  | N
MD504-311101-01B | 265 | FABRICATION | H72362730101 ABS1643ACSB007 (Dépannage) SCI535B5F48X05N (Dépannage) | Qté 1 Qté 1 Qté 1 | OUI | N/A | AIS | COL |  | 0.205 | 0 | 0.205 |  |  | 5 | 0.5 | 0.5 | 1 | AIS |  | N
V9293110100095A | BUNDLE | FABRICATION | NA |  |  |  | SATAIR | NA |  | 0.2488 | 0.2292 | 0.478 | 0 | 1.1088 | 1.1088 | 0.1108 | 0 | 0.1108 | SATAIR | IS0059303M | N
F1131170400000 | PLACARD | FABRICATION | NA | NA | NON |  | SATAIR | NA |  | 0.205 | 0 | 0 | 0 | 0 | 0.205 | 0.02 | 0 | 0.02 | SATAIR |  | N
AVI-00322-PL003-R01 | KITS PMVE | FABRICATION | NA | NA | OUI |  | PMVE | NA |  |  |  | 1.25 |  |  | 12.35 |  |  | 5.44 | PMVE | IS0059289M | N
A320EL061000-EPA | KITS 9119VU | FABRICATION | NA | NA | OUI |  | LATECOERE | NA |  | 0.25 | 0.1 | 0.35 |  |  | 2.7 | 0.27 | 0 | 0.27 | DES | IS0059318M | O
D9550010801195 | 108 | FABRICATION | 6963510300 | Qté 1 | NON |  | SATAIR | COL |  | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR | IS0059763M | N
D9551002700895 | 27 | FABRICATION | NA | NA | NON | NB03891P | SATAIR | COL |  | 0.205 | 0.118 | 0.205 | 0.5964 | 4.3209 | 4.9173 | 0.49173 | 0.7376 | 1.2293 | SATAIR | IS0059907M | N
S9251279400056 | 22 | FABRICATION | 6808108700 6839605100 6827214800 | Qté 1 Qté 1 Qté 1 | OUI |  | STELIA | NA | [10 empty] | STELIA | IS0060073M | N
D9550010801395 | 108 | FABRICATION | 6963469200 | Qté 1 | NON |  | SATAIR | COL |  | 0.36 | 0 | 0.36 | 0.7308 | 7.2511 | 7.9819 | 0.79819 | 1.1973 | 1.9955 | SATAIR | IS0060338M | N
A9550051100395 | 511 | FABRICATION | NA | NA | NON |  | SATAIR | COL |  | 0.25 | 0.12 | 0.37 | 1.1 | 2.91 | 4.01 | 0.45 | 0.62 | 1.07 | SATAIR | IS0060409M | N
A95500110000AA | 110 | FABRICATION |  |  | NON |  | SATAIR | COL |  | 0.205 | 1.32 | 1.525 | 4.74 | 30.09 | 34.83 | 3.98 | 5.42 | 9.4 | SATAIR | IS0060587M | N
A9550051100295 | 511 | FABRICATION |  |  | NON |  | SATAIR | COL |  | 0.25 | 0.12 | 0.37 | 1.1 | 2.91 | 4.01 | 0.45 | 0.62 | 1.07 | SATAIR | IS0060616M | N
MB259ADABAAC | 61 | FABRICATION |  |  | NON |  | AD&S | COL |  | 0 | 0 | 0 | 0.4 | 1.14 | 1.54 | 0.15 | 0.25 | 0.4 | AD&S | IS0060618M | N | OK
D9551002201895 | 22 | FABRICATION |  |  | NON |  | SATAIR | COL | 13.3761 | 0.205 | 0 | 0.205 | 0.92 | 9.62 | 10.54 | 1.05 | 1.58 | 2.63 | SATAIR | IS0060617M | N
V9271701020000 | OPTICAL FIBER | FABRICATION | [5 empty] | COL | [10 empty] | SATAIR | IS0060645M | O
MB043ACAAAAD | 51 | FABRICATION |  |  | OUI |  | AD&S | COL |  | 0.36 |  | 0.36 |  |  | 3.3 | 0.3 | 0.49 |  | AD&S | IS0060760M | N
MB030AAAAAAA | 33 | FABRICATION |  |  | OUI |  | AD&S | COL |  | 0.36 |  | 0.36 |  |  | 4.2 | 0.3 | 0.53 | 0.83 | AD&S | IS0060759M | N
S9110305200195 | FAISCEAU | FABRICATION |  |  | OUI |  | STELIA | COL |  | 0.205 | 0.048 | 0.15 | 0 | 0.99 | 0.99 | 0.12 | NA | 0.12 | STELIA | IS0060894M
D9251076700400 | 109 | FABRICATION |  |  | NON |  | SATAIR | COL |  | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0.1 | 0 | 0.1 | SATAIR | IS0061064M | N
F9252030900000 | SHEET FOMAX SHEET EQUIP | FABRICATION |  |  | NON |  | AIS | NA |  | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.015 | 0 | 0.015 | AIS | IS0032162M | O
D9001095411495 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0061093M | N
WF426AEAAAAE | 612 | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0.205 | 0 | 0.205 | 0.49 | 1.6 | 2.09 | 0.2 | 0.31 | 0.51 | SATAIR | IS0061230M | N
V9271700820000 | OPTICAL FIBER | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0061276M | O
F9252036900000 | EQPT PLATE | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.015 | 0 |  | SATAIR | IS0061420M | O
MB033ACAAAAB | 21 | FABRICATION |  |  | OUI |  | SATAIR | COL | 3.0808 | 0.36 | 0 | 0.36 | 0.8095 | 1.3671 | 2.1766 | 0.21766 | 0.32649 | 0.54415 | AD&S | IS0061439M |  | NA
S956G1120108451 | HARNAIS | FABRICATION |  |  | OUI |  | STELIA | LIP |  | 0.25 | 0.12 | 0.37 | 0 | 3 | 3 | 0.16 | 1 | 1.16 | STELIA | IS0061723M | O
V9297986100095A | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA | 2.818 | 0.43 | 0.1 | 0.53 | 0 | 2.14 | 2.67 | 0.148 | 0 | 0.148 | SATAIR | IS0062201M | N
D9000095030395 | OPTICAL FIBER 3029VB | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062395M | N
MB045ACAAAAB | 402 | FABRICATION |  |  | OUI |  | AD&S | COL | TBD | 0.62 | 0 | 0.62 | 1.74 | 8.03 | 9.77 | 1.14 | 1.92 | 3.06 | AD&S | IS0062403M | N | OK
V9297404108495 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062439M
V9297404002695 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062440M
D9000095030495 | OPTICAL FIBER 3028VB | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062462M
WF412ADACAAF | 412 | FABRICATION |  |  | NON |  | SATAIR | COL |  | 0.07 | 0.17 | 0.23 |  |  | 6.42 | 0.73 | 1.61 | 2.34 | SATAIR | IS0062465M
V9251313300095A | HARNESS ASSY CABLE | FABRICATION | N/A | N/A | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062514M
V9251313700095A | HARNESS ASSY CABLE | FABRICATION | N/A | N/A | NON | NA | SATAIR | NA | [10 empty] | SATAIR | IS0062515M
D9000095030595 | OPTICAL FIBER 3031VB | FABRICATION |  |  | NON | NA | SATAIR | NA | [10 empty] | SATAIR | IS0062516M
D9550011000295 | 110 | FABRICATION |  |  | NON | NA | SATAIR | NA |  | 0.12 | 0.12 | 0.24 | 0.302 | 2.261 | 2.56 | 0.25 | 0.74 | 0.99 | SATAIR | IS0062642M
S9550003456395 | 34 | FABRICATION |  |  | OUI | NA | STELIA | COL | [10 empty] | SATAIR | IS0032566M
V9297404108695 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0.36 | 0.075 | 0.435 | 0 | 6.211 | 6.211 | 2.5 | 0.57 | 3.07 | SATAIR | IS0060810M
V9297404002895 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0.36 | 0.075 | 0.435 | 0 | 6.211 | 6.211 | 2.5 | 0.57 | 3.07 | SATAIR | IS0060809M
V9297400001095 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0.36 | 0.075 | 0.435 | 0 | 2.96 | 2.96 | 1.093 | 1.062 | 2.155 | SATAIR | IS0061660M
V9297400101295 | BUNDLE | FABRICATION |  |  | NON |  | SATAIR | NA |  | 0.36 | 0.075 | 0.435 | 0 | 2.96 | 2.96 | 1.093 | 1.062 | 2.155 | SATAIR | IS0061659M
S954A1184158052 | OPTICAL FIBER | FABRICATION |  |  | OUI |  | STELIA | NA | [10 empty] | STELIA | IS0062875M
D9000095030695 | OPTICAL FIBER 3030VB | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0062902M
A95500400000AA | 400 | FABRICATION |  |  | NON |  | SATAIR | NA | [10 empty] | SATAIR | IS0063213M
1288L4000010B | FDVESS L4 | FABRICATION |  |  | NON |  | LATECOERE | COL | [10 empty] | LATECOERE | IS0033483M
A95500406000AA | 406 | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0063330M
WF415ABAAAAB | 513 | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0063340M
F0003003000100 | PROTECTION CAP | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0063331M
D9000095030995 | OPTICAL FIBER 3031VB | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0063725M
V9271700920800 | OPTICAL FIBER | FABRICATION |  |  | NON |  | SATAIR | COL | [10 empty] | SATAIR | IS0063805M
EN2997SE01212AN | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*00559
EN2997SE61212BN | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*00557
| BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10652
A9251050600000 | SUPPLATE ASSY 429VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10727
A9251080820000 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16559
A9251080820200 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16560
A9251080820800 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16561
A9251080821000 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16558
A9251080821200 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16562
A9252236000000 | HOOK | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01447
A9252250526300 | COLONNETTE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10660
A9252427220000 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16762
A9252483620000 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16563
A9252597000800 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01148
A9252597000900 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01482
A9252842100000 | PLATE-BLANKING | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0006167S
A9252882500400 | ENS TOLE LATERALE INF G | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 3STR*01342
A9252882500700 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10638
A9253115800000 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0031675S
A9253116020000 | BRACKET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0031653S
A9253116220000 | HINGE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0031676S
A9253172120000 | FOAM SILICONE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
ABS2208AP08S | POTENTIOMETRE | HA/REVENTE | [16 empty] | SATAIR | IS0006784S
E0165D18A01X | ARINC | HA/REVENTE | [16 empty] | SATAIR | 1CON*23500
ASNE0416-02 | SOPORTE | HA/REVENTE | [16 empty] | SATAIR | 4QEL*00001
ASNE0464A6AA | GUARD SWITCH | HA/REVENTE | [16 empty] | SATAIR | 4CPR*00281
D9100095010195 | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10715
D9251041101400 | PLATEAU ASPIRANT | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00135
D9251095400000 | PLACARD SET 301VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053354S
D9251095600000 | PLACARD SET 500VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053509S
D9251101900000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11007
D9251127600000 | FLANGE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0008826S
D9251335500000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00012
D9251551000100 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00201
D9251626900100 | PANEL-ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
D9251655400000 | PLATE ASSY 52VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10725
D9251794200000 | SUPPLATE FRONT 301VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10670
D9251794600000 | SUPPLATE FRONT 500VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10671
D9251805700000 | PLATE ASSY FRONT 301VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0032776S
D9251805800000 | PLATE ASSY FRONT 500VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0032777S
D9251863200000 | TOLE FERMET. 1MCU EQ | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10676
E0070B023 | VOYANT DE SIGNALISATION | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1CPR*15182
E0070B027 | VOYANT DE SIGNALISATION | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1CPR*15183
E0165D13A27X | CONNECTEUR ARINC 600 | HA/REVENTE | [16 empty] | SATAIR | 1CON*00242
EN3545E12MXB00A | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*00230
EN3645K0GL75AB | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*01514
EN3646A02041AN | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 4CON*00019
F0003057820900 | COLONNETTE POST | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10679
F0003057822100 | COLONNETTE POST | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10680
F0003057822800 | COLONNETTE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*16553
F0041428900000 | PLATINE 807VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
F9241259500000 | SUPPORT ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
F9251110720000 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
F9251110800100 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10656
F9251110800300 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10653
F9251110800400 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10657
F9251110800500 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00297
F9251110800600 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10659
F9251110800800 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00292
F9251110800900 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10658
F9251110801200 | TUBE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*00294
F9251216800200 | ENS PLATINE AR INF | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10655
F9251259220000 | MOUNT | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10706
F9251259500100 | SUPPORT ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01489
F9251339200000 | PLATE ASSY-CLOSING | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0054706S
F9251367800000 | ENS. TOLE 3MCU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10672
F9251423320000 |  | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
F9251423500000 | PIECE COUDÉE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR
F9251445920000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR/AIS | 1STR*01520
F9251485300000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01521
F9251485400000 | PLATE ANGLE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR/AIS | IS0033627S
F9252018800000 | TÔLE EQUIPÉE APM | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10493
L9251266800000 | CROSSBEAM ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10883
L9251266800001 | CROSSBEAM ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10883
L9251266920000 | CROSSBEAM | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10884
L9251266920001 | CROSSBEAM | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10884
L9251267020000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10885
L9251267020001 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10885
L9251267120000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10886
L9251267120001 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10886
L9251267220000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10887
L9251267220001 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10887
L9251267320000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10888
L9251267320001 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10888
L9251267420000 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10889
L9251267420001 | ANGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10889
L9251298020000 | WASHER | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*00812
L9251321500000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01089
L9251355400000 | ENS. TOLE APM | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10891
L9251394100000 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*10675
M1133301800000 | LABEL PLATE 1155VU | HA/REVENTE | [16 empty] | AD&S | N/A
M1133306800000 | LABEL SHELF 1115VU | HA/REVENTE | [16 empty] | AD&S | N/A
M8753333600000 | TOLE FERMETURE LTMS | HA/REVENTE | [16 empty] | AD&S
M8753333900000 | TOLE FERMETURE LTMS | HA/REVENTE | [16 empty] | AD&S
M8753310300000 | PLATE | HA/REVENTE | [16 empty] | AD&S | 1STR*11236
M8753310500000 | CALE DE RACK MC5 | HA/REVENTE | [16 empty] | AD&S | 1STR*01106
M8753486220000 | SHIM | HA/REVENTE | [16 empty] | AD&S | 1QME*01207
M8753486620000 | SHIM | HA/REVENTE | [16 empty] | AD&S | 1QME*01211
MD501-211102-01A | DIAPHRAGME | HA/REVENTE | [16 empty] | AIS | 1STR*10647
MD501-211102-02A | DIAPHRAGME | HA/REVENTE | [16 empty] | AIS | 1STR*10648
S0003012600000 | RONDELLE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0013828S
S0003027000000 | SUPPORT FIXE SUPERPOSE | HA/REVENTE | [16 empty] | STELIA | 1STR*01261
S2521656820000 | PLATINE HAUT-PARLEUR | HA/REVENTE | [16 empty] | STELIA | 4STR*00771
S2523044600000 | STRUCTURE 755 VU | HA/REVENTE | [16 empty] | STELIA | 1STR*10632
S9241304100000 | ENS.MECANIQUE ECLAIRAGE | HA/REVENTE | [16 empty] | STELIA
S9251019520700 | DIAPHRAGME | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251020300100 | CARTER EQUIPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251022100000 | RAMPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 4ACC*00710
S9251022200000 | RAMPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 4ACC*00711
S9251026100700 | PANNEAU FERMETURE ÉQUIPÉ | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*01138
S9251038100100 | PLATINE AVANT 110VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251054820000 | JOINT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QME*16550
S9251059600000 | RAMPE 23VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00944
S9251059700000 | RAMPE 23VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00945
S9251059700100 | RAMPE 23VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00061
S9251083800000 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1CMP*16129
S9251090300000 | RAMPE 122VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10677
S9251090300100 | RAMPE 122VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10179
S9251107820000 | RAMPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251112620000 | VIS 114VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00810
S9251165200000 | PLATINE AV 23VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251165200200 | PLATINE AVANT 23VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10664
S9251179200000 | ADAPTATEUR DME | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*01293
S9251303020000 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QEL*00025
S9251303120000 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QEL*00029
S9251304020200 | GOUJON | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251306420100 | PLATINE LISEUSE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*00283
S9251324700400 | PANNEAU DE FERMETURE 120VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*01147
S9251340100100 | ENSEMBLE COMPAS | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*11056
S9251353500100 | PLAQUE 5VU(MARRON) | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00931
S9251363300100 | CAPOT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0054056S
S9251372600000 | PLATINE AVANT 112VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00947
S9251380900000 | PLATINE ARRIERE 112VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*01340
S9251418100000 | RAMPE H1 | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10890
S9251428800100 | SUPPLATE FRONT 27VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*01418
S9251446520000 | RAMPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*11044
S9251451700100 | PANNEAU DE FERMETURE ÉQUIPÉ | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*01133
S9251593120000 | PLATINE ARRIERE 5VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*00145
S9251594420000 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10668
S9251596820000 | PRISE SUP 82 VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10666
S9251597520000 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10667
S9251598400000 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*01599
S9251598400100 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*01600
S9252318000000 | PLATINE ÉQUIPÉE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*02063
S9252333600000 | SUPPORT EQUIPE 91VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10937
S9252333700000 | RAMPE 91VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10936
S9252335520000 | CALE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 4STR*00688
S9252347900000 | STRUCTURE 27VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251130520900 | Colonette | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251130521300 | Colonette | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
S9251130521400 | Colonette | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA
V1132026800000 | PLACARD | HA/REVENTE | [16 empty] | SATAIR | 1ETI*17179
V1132030400000 | PLACARD | HA/REVENTE | [16 empty] | SATAIR | 1ETI*17180
V9251014003600 | RAMP ASSY | HA/REVENTE | [16 empty] | SATAIR | 1STR*10688
V9251040720000 | FITTING | HA/REVENTE | [16 empty] | SATAIR | N/A
V9251040720201 | FITTING | HA/REVENTE | [16 empty] | SATAIR | 1STR*10694
V9251111520000 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10661
V9251111520600 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10733
V9251111521200 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10663
V9251111522200 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10734
V9251111522400 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10662
V9251111522600 | DIAPHRAGME | HA/REVENTE | [16 empty] | SATAIR | 1STR*10751
V9251115500000 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | N/A
V9251115500001 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10693
V9251115600000 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | N/A
V9251115600001 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10692
V9251115700000 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | N/A
V9251115700001 | EQUIPED BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10691
V9251140000001 | BRACKET ASSY | HA/REVENTE | [16 empty] | SATAIR | 1STR*10690
V9251140400001 | EQ. BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10689
V9251149100000 | PANEL ASSY | HA/REVENTE | [16 empty] | SATAIR
ASNE033901C | BUTTON | HA/REVENTE | [16 empty] | SATAIR | 4QEL*00071
EN2997RS61415BN | CONNECTEUR | HA/REVENTE | [16 empty] | SATAIR | 1CON*06435
EN2997RS61415AN | CONNECTEUR | HA/REVENTE | [16 empty] | SATAIR | 1CON*01377
M390295115 | CONTACT | HA/REVENTE | [16 empty] | SATAIR | 8CNT*00132
M390294110 | CONTACT | HA/REVENTE | [16 empty] | SATAIR | 1CNT*18523
M8753367020000 | SWITCH PLATE | HA/REVENTE | [16 empty] | AD&S | 1STR*11061
M11332311000 | LABEL | HA/REVENTE | [16 empty] | AD&S | 1ETI*17147
F9251176900000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 4STR*01313
L9251391200000 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01134
L9251391300000 | COVER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01135
D9251490100000 | FRONT PLATE 110VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0032740S
V9251137920000 | BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10969
V9251155800000 | BAR ASSY TORSION | HA/REVENTE | [16 empty] | SATAIR | 1STR*10747
V9251156200000 | ANGLE ASSY | HA/REVENTE | [16 empty] | SATAIR | 1STR*10970
V9251155600000 | BAR ASSY TORSION | HA/REVENTE | [16 empty] | SATAIR | 1STR*10746
V9251157800000 | BAR ASSY TORSION | HA/REVENTE | [16 empty] | SATAIR | 1STR*10749
V9251156000000 | BAR ASSY TORSION | HA/REVENTE | [16 empty] | SATAIR | 1STR*10748
V9251128220000 | BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10971
V9251156800000 | EQ. ANGLE | HA/REVENTE | [16 empty] | SATAIR | 1STR*10972
V9251157500000 | EQ. TORSION BAR | HA/REVENTE | [16 empty] | SATAIR | 1STR*10750
V9251156900000 | EQ. TORSION BAR | HA/REVENTE | [16 empty] | SATAIR | 1STR*10973
V9251157220000 | BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10974
V9251157100000 | EQ. ANGLE | HA/REVENTE | [16 empty] | SATAIR | 1STR*10975
V9251147720000 | PLATE | HA/REVENTE | [16 empty] | SATAIR | 1STR*10976
V9251120300000 | EQ. BRACKET | HA/REVENTE | [16 empty] | SATAIR | 1STR*10977
V9251155500000 | EQ. ANGLE | HA/REVENTE | [16 empty] | SATAIR | 1STR*10978
V9251157300000 | EQ. TORSION BAR | HA/REVENTE | [16 empty] | SATAIR | 1STR*10979
E0163D21-45X | ARINC | HA/REVENTE | [16 empty] | SATAIR | 1CON*01139
A0001072600100 | ROD-ADJUSTABLE | HA/REVENTE | [16 empty] | SATAIR | 1STR*10983
E0423-01E | LIGHT BODY | HA/REVENTE | [16 empty] | SATAIR | 4QEL*00034
S9251425000000 | PLATINE AVANT 24VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10985
S9251317700100 | RAMPE SOUDÉE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10988
S9251080800100 | RAMPE SOUDÉE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*10178
ABS1343P28-67F | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*23145
S9251450300000 | PLAQUE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QME*00169
S9251450200000 | EMBASE ÉQUIPÉE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QME*00170
A9252487900700 | DUCT ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11045
M87612404000 | LABEL FIN 404VU | HA/REVENTE | [16 empty] | SATAIR | N/A
A9251152500000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0031658S
A9251151000000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11047
A9252235700000 | PLATE ASSY-BLANKING | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11048
S9251458000000 | RAMPE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 3STR*01167
S9251363300000 | COVER ASSY 114VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0035424S
S9251038100000 | FRONT PLATE ASSY 110VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0035410S
A9252793020200 | FRONT PLATE 423VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11100
A9253170100100 | FRONT PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11101
A9253170100000 | FRONT PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11102
A92529189000E00 | FRONT PLATE 406VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11103
A92530435000D00 | FRONT PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11104
A9251133500000 | FRONT PLATE 510VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11105
A9251079000000 | FRONT PLATE 76VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11106
A92529726000D00 | PLATE ASSY-FRONT 414VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11107
E0165D16A40X | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*01189
E0165D16A00X | CONNECTOR | HA/REVENTE | [16 empty] | SATAIR | 1CON*01189
A9251000900000 | PLATE ASSY-FRONT | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11122
S9251186120000 | GOUPILLE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0035418S
A92524705001D00 | FRONT PLATE ASSY 426VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11168
F9251109620000 | TRIM | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | N/A
A9252602600000 | BAR | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | À faire
F0003057821000 | PILLAR | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QME*17052
F9251360500100 | BRACKET ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11187
M1133605220000 | LABEL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1ETI*17577
S9251342320000 | SPHERE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*06202
A9253171800100 | STRUCTURE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*01640
D9251734300000 | BRACKET ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0032771S
ASNE046806A | ROTATORY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 4QEL*00111
F9251446020000 | FORK | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1QME*17096
S9251302520000 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QEL*10071
F0003057820200 | COLONNETTE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 3QME*00792
ABS2220SE0G04AT | CONNECTOR-RECEPTACLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1CON*01630
S9251481920000 | BRACKET | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | À faire
EN3645M0HN54AA | CONNECTOR | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1CON*24527
D9251746700000 | PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1STR*11241
S9251302420100 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QEL*00019
ASNA267911 | PLUS-BLANKING | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | 1ACC*00002
S9251590500000 | PLATINE ARRIERE 26VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0035439S
F9251338800000 | PLATE ASSY-CLOSING | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0041081S
S9242302600000 | SUPPORT 1020VC | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*11279
S9242320300200 | SUPPORT | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1STR*11280
F9252029300000 | PLATE ASSY | HA/REVENTE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | SATAIR/AIS | 1STR*11290
A9252496620200 | BRACKET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053087S
S9251302220000 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0013882S
S9252502200000 | SUPPLATE FRONT 22VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 4STR*01412
S9251302620000 | BARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | 1QEL*10072
F2121202620000 | SEAL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053199S
S9251454400100 | PLATINE AVANT 22VU | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0053336S
L9251229301500 | DIAPHRAGM ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053337S
L9251229301400 | DIAPHRAGM ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0053338S
E0276AN0-N132 | VOYANT DE SIGNALISATION | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0007292S
128810319201 | PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | DES | IS0053339S
D9251117900000 | PLACARD | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0055779S
D9251117700000 | PLACARD | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0055780S
D9251118100000 | PLACARD | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0055781S
ABS22621820 | BACKSHELL | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0006854S
ABS2208AP11S | CONNECTOR | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0006786S
V9247233800000 | RACEWAY ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057051S
V9247239600000 | RACEWAY ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057090S
V9247240400000 | RACEWAY ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057700S
V9247239800000 | RACEWAY ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057804S
V9247240100000 | RACEWAY ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057805S
F9252036900000 | EQPT PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0061420M
V9251162200000 | BRACKET ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057853S
V9251162300000 | GUTTER ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057854S
V9251162600000 | BRACKET ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0057855S
S9252350700000 | RAMPE 121VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0058054S
V1131450300095A | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0058454S
D9251118520000 | PLATE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0008825S
V1132043700095A | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059284S
V1132043900095A | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059285S
F9251431120000 | PLATE 809VU | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059720S
V1132035600095A | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059841S
V1132035500095A | PLACARD SET | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059842S
S9251097200100 | LANGUETTE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0059938S
V9251129900000 | RAMP | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0059956S
S9251047420000 | PROTECTION | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0060011S
E0276CN3FP007 | VOYANT CARRE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0032217S
EN2997SE61005D6 | CONNECTOR | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0060811S
D9100095455395 | PLACARD | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0060691S
D9251081700000 | PLACARD | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0060818S
NSA931432A4BA0A | SWITCH-DOUBLE POLE TOGGLE | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0034858S
S9252360300000 | BOUCHON EQUIPEE | HA/REVENTE | [5 empty] | NA | [10 empty] | STELIA | IS0061053S
D9000095030995 | OPTICAL FIBER 3031VB | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | TBD
F9251487400000 | PLATE ASSY | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0033628S
NSA933677F224 | VOYANT | HA/REVENTE | [5 empty] | NA | [10 empty] | SATAIR | IS0061411S

## Settings
Attente confié | KIT FACTORY
Attente BE client | ROCHEFORT
Attente AR | SEVILLE
Attente RFQ HA | SPARES
Envoyé à LAB le