## Sheet1
| Mechanical Engineer | [23 empty] | Procurement
Quote Number | Projet number | PROJECT DESCRIPTION | CLIENT | Beam line | DATE OF REQUEST | DELIVERY DATE WISHED | Delvery date (Ordered) | PROJECT COMPLETED ON | Budget code | Vac. Cleaning chamber | Chamber bakeout | Chamber Rga | Chamber leaktest | Inspection by third party | Material certificates | 100% Inspection supplier | UHV Mechanics cleaned | UHV Mechanics bakeout | UHV Mechanics Rga | Assembly | Wiring | Functional testing required on site | All invac. Screws silver coated | ESTIMATED PRICE (PROJECT MANAGER) | Bidders | Date of quotation | Order date | Supplier Country | Delivery time | alert dead line date | ACTUAL PRICE | NUMBER OF ORDERS PLACED | ESRF Order No. | Fraisage,tournage | Erosion enfonçage, a file = EE ou EF | mecano-soudé | Découpe jet d'eau | Assemblage | COMMENTS | Percentage spent
| RFQ - 2804 | Spacer for Girders | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 49000 | EML normandie | 2018-11-20 |  | FR | [5 empty] | No | No | No | Yes | No | Spacers for girders dwg no. 88.60.0307 & 88.61.0308
| RFQ - 2804 | Spacer for Girders | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 49000 | Deville Rectification | 2018-11-20 |  | FR | [5 empty] | No | No | No | Yes | No | Spacers for girders dwg no. 88.60.0307 & 88.61.0308
| RFQ - 2804 | Spacer for Girders | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 49000 | Allier Decoupe+ | 2018-11-20 |  | FR | [5 empty] | No | No | No | Yes | No | Spacers for girders dwg no. 88.60.0307 & 88.61.0308
| RFQ - 2804 | Spacer for Girders | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 49000 | Ranoldsway aircraft company Ltd | 2018-11-20 |  | GB | [5 empty] | No | No | No | Yes | No | Spacers for girders dwg no. 88.60.0307 & 88.61.0308
| RFQ - 2804 | Spacer for Girders | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 49000 | Lucassen | 2018-11-20 |  | NL | [5 empty] | No | No | No | Yes | No | Spacers for girders dwg no. 88.60.0307 & 88.61.0308
| RFQ - 2804 | Fixed block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 800 | OMG Fontanil | 2018-11-23 |  | FR |  |  | 840 |  |  | Yes | No | No | No | No | 88.61.0303
| RFQ - 2804 | Fixed block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 800 | Atelier du Fontanil | 2018-11-23 |  | FR |  |  | 747 | 1 |  | Yes | No | No | No | No | 88.61.0303
| RFQ - 2804 | Fixed block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 800 | Atelier Peyronnard | 2018-11-23 |  | ES |  |  | 730 | 0 |  | Yes | No | No | No | No | 88.61.0303
| RFQ - 2804 | Adjusting block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1500 | OMG Fontanil | 2018-11-23 |  | FR |  |  | 1200 | 1 |  | Yes | No | No | No | No | 88.61.0177
| RFQ - 2804 | Adjusting block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1500 | Atelier du Fontanil | 2018-11-23 |  | BS |  |  | 441 | 1 |  | Yes | No | No | No | No | 88.61.0177
| RFQ - 2804 | Adjusting block | T.Brochard | storage ring | 2018-10-12 | 2018-02-15 |  |  | 89CCFT | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1500 | Atelier Peyronnard | 2018-11-23 |  | FR |  |  | 730 | 0 |  | Yes | No | No | No | No | 88.61.0177
18-0000 | TL2 Floor plates | TL2 Floor plates | T.Mairs | storage ring | 2018-10-09 | 2018-12-20 |  |  | ZM0130 | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | OMG Fontanil | 2018-11-16 |  | DE |  |  | 7659 | 1 |  | Yes | No | No | No | Yes | TL2 Floor plates
| TL2 Floor plates | TL2 Floor plates | T.Mairs | storage ring | 2018-10-09 | 2018-12-20 |  |  | ZM0130 | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | SMGOP Mecanique general | 2018-11-16 |  | FR |  |  | 6000 | 0 |  | Yes | No | No | No | Yes | TL2 Floor plates
| TL2 Floor plates | TL2 Floor plates | T.Mairs | storage ring | 2018-10-09 | 2018-12-20 | 2019-01-11 |  | ZM0130 | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | SCM Technology SRL | 2018-11-16 | 2018-11-23 | IT | 2019-01-11 | 2019-01-04 | 4137.73 | 1 | 71720 | Yes | No | No | No | Yes | TL2 Floor plates
18-0001 | 6-Gev Transfer Line 2 | 6-Gev Transfer Line 2 | B.Ogier | Extraction booster | 2018-11-22 | 2018-01-18 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 3000 | AJBS | 2018-11-27 |  | FR | [5 empty] | Yes | No | Yes | No | Yes
| 6-Gev Transfer Line 2 | 6-Gev Transfer Line 2 | B.Ogier | Extraction booster | 2018-11-22 | 2018-01-18 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 3000 | SCM Technology SRL | 2018-11-27 |  | IT | [5 empty] | Yes | No | Yes | No | Yes
| 6-Gev Transfer Line 2 | 6-Gev Transfer Line 2 | B.Ogier | Extraction booster | 2018-11-22 | 2018-01-18 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 3000 | Proactive | 2018-11-27 |  | ES | [5 empty] | Yes | No | Yes | No | Yes
| 6-Gev Transfer Line 2 | 6-Gev Transfer Line 2 | B.Ogier | Extraction booster | 2018-11-22 | 2018-01-18 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 3000 | Nortemecanica | 2018-11-27 |  | ES |  |  | 3950 | 1 |  | Yes | No | Yes | No | Yes
18-0002 | Support Wiggler | Support Wiggler | F.Villar | storage ring | 2018-11-26 | 2019-02-01 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 900 | SMGOP Mecanique general | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
| Support Wiggler | Support Wiggler | F.Villar | storage ring | 2018-11-26 | 2019-02-01 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 900 | Atelier Peyronnard | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
| Support Wiggler | Support Wiggler | F.Villar | storage ring | 2018-11-26 | 2019-02-01 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 900 | OMG Fontanil | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
| Support Wiggler | Support Wiggler | F.Villar | storage ring | 2018-11-26 | 2019-02-01 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 900 | ljindustrie | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
18-0003 | Scooter | Scooter | L.Goirand | storage ring | 2018-11-27 |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | Atelier du Fontanil | 2018-11-30 |  | FR | [5 empty] | Yes | No | Yes | No | Yes
| Scooter | Scooter | L.Goirand | storage ring | 2018-11-27 |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | Satil | 2018-11-30 |  | FR | [5 empty] | Yes | No | Yes | No | Yes
| Scooter | Scooter | L.Goirand | storage ring | 2018-11-27 |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 5000 | SMGOP Mecanique general | 2018-11-30 |  | FR | [5 empty] | Yes | No | Yes | No | Yes
18-0004 | Kicker general assembly | Kicker general assembly | F.Villar | storage ring | 2018-11-26 | 2018-04-15 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2000 | SMGOP Mecanique general | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
18-0004 | Kicker general assembly | Kicker general assembly | F.Villar | storage ring | 2018-11-26 | 2018-04-15 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2000 | OMG Fontanil | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
18-0004 | Kicker general assembly | Kicker general assembly | F.Villar | storage ring | 2018-11-26 | 2018-04-15 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2000 | Nortemecanica | 2018-11-30 |  | ES | [5 empty] | Yes | No | No | No | Yes
18-0004 | Kicker general assembly | Kicker general assembly | F.Villar | storage ring | 2018-11-26 | 2018-04-15 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2000 | ljindustrie | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes
18-0004 | Kicker general assembly | Kicker general assembly | F.Villar | storage ring | 2018-11-26 | 2018-04-15 |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1000 | Isotac | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | Yes | Résine FR4
18-0005 | Granit Assy | Granit Assy | F.Cianciosi | ID19 | 2018-11-27 |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1500 | SCM Technology SRL | 2018-11-30 |  | IT | [5 empty] | Yes | No | No | No | No
18-0005 | Granit Assy | Granit Assy | F.Cianciosi | ID19 | 2018-11-27 |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 1500 | Satil | 2018-11-30 |  | FR | [5 empty] | Yes | No | No | No | No
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
[10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | [10 empty] | - | - |  | - | -
Formulas:
alert dead line date = IF([Delivery time]="","",[Delivery time]-7)

## Sheet3
FR | DE | IT | UK | RU | BS | NS | ES | CH | IL | AT | CS | PL | PT | IN | ZA
747 | 7659 | 4137.73 |  |  |  |  | 3950
1200
Mise à jour

## Sheet2 (hidden)
-
Yes
No