## Cover sheet
Document number
Master Document Register (MDR)
[5 empty] | Revision: 1.0 |  | Status: IFR
Document type: REG |  | System: N_NAP |  | Discipline: PJM | Rev Date: | 16/11/2022
Project ID: |  |  |  |  | Page 1 of 3
Rev. | Status | Date | Revision description |  |  | Issued by | Reviewed by | Approved by
1.0 | IFR | 2022-11-16 | Issue For Review |  |  | N.MOMODU | K.YAFRNI | B.BELLET

## MDR Phase 1 0.1
15
ProjectID | DocumentID | Title | Country | Site | Sector | OriginatorCompany | Discipline | DocumentType | DocumentGroup | ProjectContractNo | PlantNo | Phase | System | SubSystem | Functional Class | Physical Class | ReviewClass | Planned IFR | Planned IFA | Planned IFD | Planned IFC | Planned IAB | Planned IFI | Weighting | Criticality | Contractor Document ID | PO Number | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000001 | Master Document Register (MDR) | NG | AKP |  | SPIE | PJM | REG | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-25 | 2022-12-10 |  | 2022-12-25 |  |  | 3% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000002 | Document Control Procedure | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-30 | 2022-12-15 |  | 2022-12-30 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000003 | Organization Chart (Preparation) | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-30 | 2022-12-15 |  | 2022-12-30 |  |  | 2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000004 | Meeting Procedure | NG | AKP |  | SPIE | PJM | PLN | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-30 | 2022-12-15 |  | 2022-12-30 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000005 | Progress Control Procedure | NG | AKP |  | SPIE | PJM | CRT | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-30 | 2022-12-15 |  | 2022-12-30 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000006 | Training Matrix For Offshore Personnel | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-17 | 2023-03-04 |  | 2023-03-19 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000007 | Planning, Scheduling and Progress Measurement Plan | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-11-30 | 2022-12-15 |  | 2022-12-30 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000008 | List of Spares and Contingency Materials for FFSD Activities | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000009 | PTS & POB Management plan | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-10 | 2023-04-25 |  | 2023-05-10 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000010 | Preparation Phase Schedule | NG | AKP |  | SPIE | PJM | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-05 | 2022-12-20 |  | 2023-01-04 |  |  | 0.5% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000011 | Execution Phase Schedule (Level 3) | NG | AKP |  | SPIE | PJM | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-05 | 2023-01-20 |  | 2023-02-04 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000012 | Execution Phase Schedule (level 4) | NG | AKP |  | SPIE | PJM | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000013 | Quality Plan | NG | AKP |  | SPIE | QUA | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000014 | Inspection & Test Plan Procedure | NG | AKP |  | SPIE | QUA | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000015 | Quality Assurance Plan | NG | AKP |  | SPIE | QUA | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000016 | Materials Inspection and Management Procedure | NG | AKP |  | SPIE | QUA | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000017 | Non Conformance Procedure | NG | AKP |  | SPIE | QUA | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000018 | Confined Space Entry Procedure | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000019 | Waste & Environmental Management Procedure | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000020 | Quality Control Plan | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000021 | MEDEVAC Procedure | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000022 | Emergency Response Plan | NG | AKP |  | SPIE | HSE | SCH | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000023 | HSE Plan | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000024 | Scaffolding Procedure and Management System | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000025 | Lifting Operation Procedure | NG | AKP |  | SPIE | HSE | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000026 | Handling and Transfer Procedure for Materials and Equipment (including containers) | NG | AKP |  | SPIE | PVV | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.5% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000027 | Job Risk Analysis | NG | AKP |  | SPIE | HSE | FOR | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-18 | 2023-06-02 |  | 2023-06-17 |  |  | 2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000028 | Personnel Competency and Fit to Work (FTW) certificates. | NG | AKP |  | SPIE | HSE | CHT | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-13 | 2023-06-28 |  | 2023-07-13 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000029 | PTW procedure | NG | AKP |  | SPIE | HSE | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-13 | 2023-06-28 |  | 2023-07-13 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000030 | Performance Measurement and Monitoring Procedure (productive time and downtime) | NG | AKP |  | SPIE | PJM | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-13 | 2023-06-28 |  | 2023-07-13 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000031 | Job Card Template | NG | AKP |  | SPIE | PVV | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-18 | 2023-06-02 |  | 2023-06-17 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000032 | Flanges/Bolts Torquing Procedure | NG | AKP |  | SPIE | PVV | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-13 | 2023-06-28 |  | 2023-07-13 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000033 | Handling and Transfer procedure for materials and equipment (including containers) | NG | AKP |  | SPIE | PVV | PRC | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-14 | 2023-06-29 |  | 2023-07-14 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000034 | Cleaning and drying procedure for Scrubber and Drum | NG | AKP |  | SPIE | PVV | CRT | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-14 | 2023-06-29 |  | 2023-07-14 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000035 | Spading, De-Spading and Spool Management Procedure | NG | AKP |  | SPIE | PVV | PLN | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-14 | 2023-06-29 |  | 2023-07-14 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000036 | Cleaning and Drying Procedure for exchangers | NG | AKP |  | SPIE | PVV | PLN | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-14 | 2023-06-29 |  | 2023-07-14 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000037 | Cleaning and Drying Procedure for crude oil Vessels separators | NG | AKP |  | SPIE | PVV | PLN | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-14 | 2023-06-29 |  | 2023-07-14 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000038 | Pickling and Passivation Procedure | NG | AKP |  | SPIE | PVV | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-18 | 2023-06-02 |  | 2023-06-17 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000039 | Flushing & Pressure testing procedure for piping | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-18 | 2023-06-02 |  | 2023-06-17 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000040 | Pressure testing procedure for Heat Exchangers | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-18 | 2023-06-02 |  | 2023-06-17 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000041 | Job Cards General Register | NG | AKP |  | SPIE | PVV | REP | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-19 | 2023-06-03 |  | 2023-06-18 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000042 | [Spading-Cat1 SITE SURVEY ] CARGO OIL HEADERS (1/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000043 | [Spading-Cat1 SITE SURVEY ] CARGO OIL HEADERS (2/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000044 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL HEATERS | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000045 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL METERING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000046 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING IN BUOY MODE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000047 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING PUMPS (1/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000048 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING PUMPS (2/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000049 | [Spading-Cat1 SITE SURVEY ] CRUDE RECIRCULATION HEATER | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000050 | [Spading-Cat1 SITE SURVEY ] GAS EXPORT METERING AND EXPORT LINE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000051 | [Spading-Cat1 SITE SURVEY ] GAS INJECTION MANIFOLD | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000052 | [Spading-Cat1 SITE SURVEY ] HULL GAS VENT BLOWER | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000053 | [Spading-Cat1 SITE SURVEY ] LIQUID HANDLING PUMPS - COT NETWORK | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000054 | [Spading-Cat1 SITE SURVEY ] METHANOL STORAGE TANK B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000055 | [Spading-Cat1 SITE SURVEY ] METHANOL SUBSEA DISTRIBUTION HEADER INJECTION LINES | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000056 | [Spading-Cat1 SITE SURVEY ] METHANOL SUBSEA DISTRIBUTION HEADER PRODUCTION LOOP | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000057 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P10L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000058 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P10R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000059 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P20L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000060 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P20R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000061 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P30L - PID WAS WRONG | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000062 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P30R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000063 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P40L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000064 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P40R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000065 | [Spading-Cat1 DOSSIER FINAL] CARGO OIL HEADERS (1/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000066 | [Spading-Cat1 DOSSIER FINAL] CARGO OIL HEADERS (2/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000067 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL HEATERS | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000068 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL METERING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000069 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING IN BUOY MODE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000070 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING PUMPS (1/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000071 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING PUMPS (2/2) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000072 | [Spading-Cat1 DOSSIER FINAL] CRUDE RECIRCULATION HEATER | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000073 | [Spading-Cat1 DOSSIER FINAL] GAS EXPORT METERING AND EXPORT LINE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000074 | [Spading-Cat1 DOSSIER FINAL] GAS INJECTION MANIFOLD | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000075 | [Spading-Cat1 DOSSIER FINAL] HULL GAS VENT BLOWER | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000076 | [Spading-Cat1 DOSSIER FINAL] LIQUID HANDLING PUMPS - COT NETWORK | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000077 | [Spading-Cat1 DOSSIER FINAL] METHANOL STORAGE TANK B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000078 | [Spading-Cat1 DOSSIER FINAL] METHANOL SUBSEA DISTRIBUTION HEADER INJECTION LINES | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000079 | [Spading-Cat1 DOSSIER FINAL] METHANOL SUBSEA DISTRIBUTION HEADER PRODUCTION LOOP | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000080 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P10L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000081 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P10R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000082 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P20L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000083 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P20R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000084 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P30L - PID WAS WRONG | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000085 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P30R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000086 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P40L | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000087 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P40R | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.0972% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000088 | [Spading Cat-2 SITE SURVEY] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000089 | [Spading Cat-2 SITE SURVEY] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000090 | [Spading Cat-2 SITE SURVEY] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000091 | [Spading Cat-2 SITE SURVEY] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000092 | [Spading Cat-2 SITE SURVEY] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000093 | [Spading Cat-2 SITE SURVEY] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000094 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000095 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000096 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000097 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000098 | [Spading Cat-2 SITE SURVEY] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000099 | [Spading Cat-2 SITE SURVEY] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000100 | [Spading Cat-2 SITE SURVEY] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000101 | [Spading Cat-2 SITE SURVEY] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000102 | [Spading Cat-2 SITE SURVEY] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000103 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000104 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000105 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000106 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000107 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000108 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000109 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000110 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000111 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000112 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000113 | [Spading Cat-2 DOSSIER FINAL] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000114 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000115 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000116 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000117 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000118 | [Spading Cat-2 SITE SURVEY] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000119 | [Spading Cat-2 SITE SURVEY] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000120 | [Spading Cat-2 SITE SURVEY] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000121 | [Spading Cat-2 SITE SURVEY] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000122 | [Spading Cat-2 SITE SURVEY] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000123 | [Spading Cat-2 SITE SURVEY] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000124 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000125 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000126 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000127 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000128 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000129 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000130 | [Spading Cat-2 SITE SURVEY] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000131 | [Spading Cat-2 SITE SURVEY] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000132 | [Spading Cat-2 SITE SURVEY] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000133 | [Spading Cat-2 SITE SURVEY] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000134 | [Spading Cat-2 SITE SURVEY] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000135 | [Spading Cat-2 SITE SURVEY] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000136 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000137 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000138 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000139 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000140 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000141 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000142 | [Spading Cat-2 SITE SURVEY] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000143 | [Spading Cat-2 SITE SURVEY] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000144 | [Spading Cat-2 SITE SURVEY] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000145 | [Spading Cat-2 SITE SURVEY] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000146 | [Spading Cat-2 SITE SURVEY] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000147 | [Spading Cat-2 SITE SURVEY] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000148 | [Spading Cat-2 SITE SURVEY] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000149 | [Spading Cat-2 SITE SURVEY] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000150 | [Spading Cat-2 SITE SURVEY] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000151 | [Spading Cat-2 SITE SURVEY] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000152 | [Spading Cat-2 SITE SURVEY] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000153 | [Spading Cat-2 SITE SURVEY] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000154 | [Spading Cat-2 SITE SURVEY] 5-DS-3510 Electrostatic Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000155 | [Spading Cat-2 DOSSIER FINAL] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000156 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000157 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000158 | [Spading Cat-2 DOSSIER FINAL] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000159 | [Spading Cat-2 DOSSIER FINAL] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000160 | [Spading Cat-2 DOSSIER FINAL] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000161 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000162 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000163 | [Spading Cat-2 DOSSIER FINAL] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000164 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000165 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000166 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000167 | PIPING NI [Spading-Cat 2 SITE SURVEY] #1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000168 | PIPING NI [Spading-Cat 2 SITE SURVEY] #2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000169 | PIPING NI [Spading-Cat 2 SITE SURVEY] #3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000170 | PIPING NI [Spading-Cat 2 SITE SURVEY] #4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000171 | PIPING NI [Spading-Cat 2 SITE SURVEY] #5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000172 | PIPING NI [Spading-Cat 2 SITE SURVEY] #6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000173 | PIPING NI [Spading-Cat 2 SITE SURVEY] #7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000174 | PIPING NI [Spading-Cat 2 SITE SURVEY] #8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000175 | PIPING NI [Spading-Cat 2 SITE SURVEY] #9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000176 | PIPING NI [Spading-Cat 2 SITE SURVEY] #10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000177 | PIPING NI [Spading-Cat 2 SITE SURVEY] #11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000178 | PIPING NI [Spading-Cat 2 SITE SURVEY] #12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000179 | PIPING NI [Spading-Cat 2 SITE SURVEY] #13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000180 | PIPING NI [Spading-Cat 2 SITE SURVEY] #14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000181 | PIPING NI [Spading-Cat 2 SITE SURVEY] #15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000182 | PIPING NI [Spading-Cat 2 SITE SURVEY] #16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000183 | PIPING NI [Spading-Cat 2 SITE SURVEY] #17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000184 | PIPING NI [Spading-Cat 2 SITE SURVEY] #18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000185 | PIPING NI [Spading-Cat 2 SITE SURVEY] #19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000186 | PIPING NI [Spading-Cat 2 SITE SURVEY] #20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000187 | PIPING NI [Spading-Cat 2 SITE SURVEY] #21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000188 | PIPING NI [Spading-Cat 2 SITE SURVEY] #22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000189 | PIPING NI [Spading-Cat 2 SITE SURVEY] #23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000190 | PIPING NI [Spading-Cat 2 SITE SURVEY] #24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000191 | PIPING NI [Spading-Cat 2 SITE SURVEY] #25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000192 | PIPING NI [Spading-Cat 2 SITE SURVEY] #26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000193 | PIPING NI [Spading-Cat 2 SITE SURVEY] #27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000194 | PIPING NI [Spading-Cat 2 SITE SURVEY] #28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000195 | PIPING NI [Spading-Cat 2 SITE SURVEY] #29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000196 | PIPING NI [Spading-Cat 2 SITE SURVEY] #30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000197 | PIPING NI [Spading-Cat 2 SITE SURVEY] #31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000198 | PIPING NI [Spading-Cat 2 SITE SURVEY] #32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000199 | PIPING NI [Spading-Cat 2 SITE SURVEY] #33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000200 | PIPING NI [Spading-Cat 2 SITE SURVEY] #34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000201 | PIPING NI [Spading-Cat 2 SITE SURVEY] #35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000202 | PIPING NI [Spading-Cat 2 SITE SURVEY] #36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000203 | PIPING NI [Spading-Cat 2 SITE SURVEY] #37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000204 | PIPING NI [Spading-Cat 2 SITE SURVEY] #38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000205 | PIPING NI [Spading-Cat 2 SITE SURVEY] #39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000206 | PIPING NI [Spading-Cat 2 SITE SURVEY] #40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000207 | PIPING NI [Spading-Cat 2 SITE SURVEY] #41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000208 | PIPING NI [Spading-Cat 2 SITE SURVEY] #42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000209 | PIPING NI [Spading-Cat 2 SITE SURVEY] #43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000210 | PIPING NI [Spading-Cat 2 SITE SURVEY] #44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000211 | PIPING NI [Spading-Cat 2 SITE SURVEY] #45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000212 | PIPING NI [Spading-Cat 2 SITE SURVEY] #46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000213 | PIPING NI [Spading-Cat 2 SITE SURVEY] #47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000214 | PIPING NI [Spading-Cat 2 SITE SURVEY] #48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000215 | PIPING NI [Spading-Cat 2 SITE SURVEY] #49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000216 | PIPING NI [Spading-Cat 2 SITE SURVEY] #50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000217 | PIPING NI [Spading-Cat 2 SITE SURVEY] #51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000218 | PIPING NI [Spading-Cat 2 SITE SURVEY] #52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000219 | PIPING NI [Spading-Cat 2 SITE SURVEY] #53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000220 | PIPING NI [Spading-Cat 2 SITE SURVEY] #54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000221 | PIPING NI [Spading-Cat 2 SITE SURVEY] #55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000222 | PIPING NI [Spading-Cat 2 SITE SURVEY] #56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000223 | PIPING NI [Spading-Cat 2 SITE SURVEY] #57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000224 | PIPING NI [Spading-Cat 2 SITE SURVEY] #58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000225 | PIPING NI [Spading-Cat 2 SITE SURVEY] #59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000226 | PIPING NI [Spading-Cat 2 SITE SURVEY] #60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000227 | PIPING NI [Spading-Cat 2 SITE SURVEY] #61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000228 | PIPING NI [Spading-Cat 2 SITE SURVEY] #62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000229 | PIPING NI [Spading-Cat 2 SITE SURVEY] #63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000230 | PIPING NI [Spading-Cat 2 SITE SURVEY] #64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000231 | PIPING NI [Spading-Cat 2 SITE SURVEY] #65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000232 | PIPING NI [Spading-Cat 2 SITE SURVEY] #66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000233 | PIPING NI [Spading-Cat 2 SITE SURVEY] #67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000234 | PIPING NI [Spading-Cat 2 SITE SURVEY] #68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000235 | PIPING NI [Spading-Cat 2 SITE SURVEY] #69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000236 | PIPING NI [Spading-Cat 2 SITE SURVEY] #70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000237 | PIPING NI [Spading-Cat 2 SITE SURVEY] #71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000238 | PIPING NI [Spading-Cat 2 SITE SURVEY] #72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000239 | PIPING NI [Spading-Cat 2 SITE SURVEY] #73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000240 | PIPING NI [Spading-Cat 2 SITE SURVEY] #74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000241 | PIPING NI [Spading-Cat 2 SITE SURVEY] #75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000242 | PIPING NI [Spading-Cat 2 SITE SURVEY] #76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000243 | PIPING NI [Spading-Cat 2 SITE SURVEY] #77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000244 | PIPING NI [Spading-Cat 2 SITE SURVEY] #78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000245 | PIPING NI [Spading-Cat 2 SITE SURVEY] #79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000246 | PIPING NI [Spading-Cat 2 SITE SURVEY] #80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000247 | PIPING NI [Spading-Cat 2 SITE SURVEY] #81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000248 | PIPING NI [Spading-Cat 2 SITE SURVEY] #82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000249 | PIPING NI [Spading-Cat 2 SITE SURVEY] #83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000250 | PIPING NI [Spading-Cat 2 SITE SURVEY] #84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000251 | PIPING NI [Spading-Cat 2 SITE SURVEY] #85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000252 | PIPING NI [Spading-Cat 2 SITE SURVEY] #86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000253 | PIPING NI [Spading-Cat 2 SITE SURVEY] #87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000254 | PIPING NI [Spading-Cat 2 SITE SURVEY] #88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000255 | PIPING NI [Spading-Cat 2 SITE SURVEY] #89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000256 | PIPING NI [Spading-Cat 2 SITE SURVEY] #90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000257 | PIPING NI [Spading-Cat 2 SITE SURVEY] #91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000258 | PIPING NI [Spading-Cat 2 SITE SURVEY] #92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000259 | PIPING NI [Spading-Cat 2 SITE SURVEY] #93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000260 | PIPING NI [Spading-Cat 2 SITE SURVEY] #94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000261 | PIPING NI [Spading-Cat 2 SITE SURVEY] #95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000262 | PIPING NI [Spading-Cat 2 SITE SURVEY] #96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000263 | PIPING NI [Spading-Cat 2 SITE SURVEY] #97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000264 | PIPING NI [Spading-Cat 2 SITE SURVEY] #98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000265 | PIPING NI [Spading-Cat 2 SITE SURVEY] #99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000266 | PIPING NI [Spading-Cat 2 SITE SURVEY] #100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000267 | PIPING NI [Spading-Cat 2 SITE SURVEY] #101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000268 | PIPING NI [Spading-Cat 2 SITE SURVEY] #102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000269 | PIPING NI [Spading-Cat 2 SITE SURVEY] #103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000270 | PIPING NI [Spading-Cat 2 SITE SURVEY] #104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000271 | PIPING NI [Spading-Cat 2 SITE SURVEY] #105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000272 | PIPING NI [Spading-Cat 2 SITE SURVEY] #106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000273 | PIPING NI [Spading-Cat 2 SITE SURVEY] #107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000274 | PIPING NI [Spading-Cat 2 SITE SURVEY] #108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000275 | PIPING NI [Spading-Cat 2 SITE SURVEY] #109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000276 | PIPING NI [Spading-Cat 2 SITE SURVEY] #110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000277 | PIPING NI [Spading-Cat 2 SITE SURVEY] #111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000278 | PIPING NI [Spading-Cat 2 SITE SURVEY] #112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000279 | PIPING NI [Spading-Cat 2 SITE SURVEY] #113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000280 | PIPING NI [Spading-Cat 2 SITE SURVEY] #114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000281 | PIPING NI [Spading-Cat 2 SITE SURVEY] #115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000282 | PIPING NI [Spading-Cat 2 SITE SURVEY] #116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000283 | PIPING NI [Spading-Cat 2 SITE SURVEY] #117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000284 | PIPING NI [Spading-Cat 2 SITE SURVEY] #118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000285 | PIPING NI [Spading-Cat 2 SITE SURVEY] #119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000286 | PIPING NI [Spading-Cat 2 SITE SURVEY] #120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000287 | PIPING NI [Spading-Cat 2 SITE SURVEY] #121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000288 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000289 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000290 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000291 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000292 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000293 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000294 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000295 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000296 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000297 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000298 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000299 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000300 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000301 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000302 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000303 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000304 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000305 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000306 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000307 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000308 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000309 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000310 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000311 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000312 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000313 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000314 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000315 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000316 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000317 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000318 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000319 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000320 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000321 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000322 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000323 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000324 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000325 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000326 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000327 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000328 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000329 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000330 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000331 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000332 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000333 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000334 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000335 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000336 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000337 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000338 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000339 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000340 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000341 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000342 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000343 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000344 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000345 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000346 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000347 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000348 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000349 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000350 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000351 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000352 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000353 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000354 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000355 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000356 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000357 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000358 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000359 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000360 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000361 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000362 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000363 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000364 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000365 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000366 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000367 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000368 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000369 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000370 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000371 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000372 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000373 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000374 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000375 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000376 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000377 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000378 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000379 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000380 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000381 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000382 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000383 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000384 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000385 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000386 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000387 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000388 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000389 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000390 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000391 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000392 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000393 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000394 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000395 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000396 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000397 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000398 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000399 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000400 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000401 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000402 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000403 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000404 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000405 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000406 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000407 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000408 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.06616% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000409 | PIPING NI [SITE SURVEY] #1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000410 | PIPING NI [SITE SURVEY] #2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000411 | PIPING NI [SITE SURVEY] #3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000412 | PIPING NI [SITE SURVEY] #4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000413 | PIPING NI [SITE SURVEY] #5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000414 | PIPING NI [SITE SURVEY] #6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000415 | PIPING NI [SITE SURVEY] #7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000416 | PIPING NI [SITE SURVEY] #8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000417 | PIPING NI [SITE SURVEY] #9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000418 | PIPING NI [SITE SURVEY] #10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000419 | PIPING NI [SITE SURVEY] #11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000420 | PIPING NI [SITE SURVEY] #12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000421 | PIPING NI [SITE SURVEY] #13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000422 | PIPING NI [SITE SURVEY] #14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000423 | PIPING NI [SITE SURVEY] #15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000424 | PIPING NI [SITE SURVEY] #16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000425 | PIPING NI [SITE SURVEY] #17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000426 | PIPING NI [SITE SURVEY] #18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000427 | PIPING NI [SITE SURVEY] #19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000428 | PIPING NI [SITE SURVEY] #20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000429 | PIPING NI [SITE SURVEY] #21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000430 | PIPING NI [SITE SURVEY] #22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000431 | PIPING NI [SITE SURVEY] #23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000432 | PIPING NI [SITE SURVEY] #24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000433 | PIPING NI [SITE SURVEY] #25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000434 | PIPING NI [SITE SURVEY] #26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000435 | PIPING NI [SITE SURVEY] #27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000436 | PIPING NI [SITE SURVEY] #28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000437 | PIPING NI [SITE SURVEY] #29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000438 | PIPING NI [SITE SURVEY] #30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000439 | PIPING NI [SITE SURVEY] #31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000440 | PIPING NI [SITE SURVEY] #32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000441 | PIPING NI [SITE SURVEY] #33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000442 | PIPING NI [SITE SURVEY] #34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000443 | PIPING NI [SITE SURVEY] #35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000444 | PIPING NI [SITE SURVEY] #36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000445 | PIPING NI [SITE SURVEY] #37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000446 | PIPING NI [SITE SURVEY] #38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000447 | PIPING NI [SITE SURVEY] #39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000448 | PIPING NI [SITE SURVEY] #40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-01 | 2022-12-16 |  | 2022-12-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000449 | PIPING NI [SITE SURVEY] #41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000450 | PIPING NI [SITE SURVEY] #42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000451 | PIPING NI [SITE SURVEY] #43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000452 | PIPING NI [SITE SURVEY] #44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000453 | PIPING NI [SITE SURVEY] #45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000454 | PIPING NI [SITE SURVEY] #46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000455 | PIPING NI [SITE SURVEY] #47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000456 | PIPING NI [SITE SURVEY] #48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000457 | PIPING NI [SITE SURVEY] #49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000458 | PIPING NI [SITE SURVEY] #50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000459 | PIPING NI [SITE SURVEY] #51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000460 | PIPING NI [SITE SURVEY] #52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000461 | PIPING NI [SITE SURVEY] #53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000462 | PIPING NI [SITE SURVEY] #54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000463 | PIPING NI [SITE SURVEY] #55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000464 | PIPING NI [SITE SURVEY] #56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000465 | PIPING NI [SITE SURVEY] #57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000466 | PIPING NI [SITE SURVEY] #58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000467 | PIPING NI [SITE SURVEY] #59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000468 | PIPING NI [SITE SURVEY] #60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000469 | PIPING NI [SITE SURVEY] #61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000470 | PIPING NI [SITE SURVEY] #62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000471 | PIPING NI [SITE SURVEY] #63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000472 | PIPING NI [SITE SURVEY] #64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000473 | PIPING NI [SITE SURVEY] #65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000474 | PIPING NI [SITE SURVEY] #66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000475 | PIPING NI [SITE SURVEY] #67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000476 | PIPING NI [SITE SURVEY] #68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000477 | PIPING NI [SITE SURVEY] #69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000478 | PIPING NI [SITE SURVEY] #70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000479 | PIPING NI [SITE SURVEY] #71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000480 | PIPING NI [SITE SURVEY] #72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000481 | PIPING NI [SITE SURVEY] #73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000482 | PIPING NI [SITE SURVEY] #74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000483 | PIPING NI [SITE SURVEY] #75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000484 | PIPING NI [SITE SURVEY] #76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000485 | PIPING NI [SITE SURVEY] #77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000486 | PIPING NI [SITE SURVEY] #78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000487 | PIPING NI [SITE SURVEY] #79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000488 | PIPING NI [SITE SURVEY] #80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-07 | 2022-12-22 |  | 2023-01-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000489 | PIPING NI [SITE SURVEY] #81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000490 | PIPING NI [SITE SURVEY] #82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000491 | PIPING NI [SITE SURVEY] #83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000492 | PIPING NI [SITE SURVEY] #84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000493 | PIPING NI [SITE SURVEY] #85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000494 | PIPING NI [SITE SURVEY] #86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000495 | PIPING NI [SITE SURVEY] #87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000496 | PIPING NI [SITE SURVEY] #88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000497 | PIPING NI [SITE SURVEY] #89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000498 | PIPING NI [SITE SURVEY] #90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000499 | PIPING NI [SITE SURVEY] #91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000500 | PIPING NI [SITE SURVEY] #92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000501 | PIPING NI [SITE SURVEY] #93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000502 | PIPING NI [SITE SURVEY] #94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000503 | PIPING NI [SITE SURVEY] #95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000504 | PIPING NI [SITE SURVEY] #96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000505 | PIPING NI [SITE SURVEY] #97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000506 | PIPING NI [SITE SURVEY] #98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000507 | PIPING NI [SITE SURVEY] #99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000508 | PIPING NI [SITE SURVEY] #100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000509 | PIPING NI [SITE SURVEY] #101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000510 | PIPING NI [SITE SURVEY] #102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000511 | PIPING NI [SITE SURVEY] #103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000512 | PIPING NI [SITE SURVEY] #104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000513 | PIPING NI [SITE SURVEY] #105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000514 | PIPING NI [SITE SURVEY] #106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000515 | PIPING NI [SITE SURVEY] #107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000516 | PIPING NI [SITE SURVEY] #108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000517 | PIPING NI [SITE SURVEY] #109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000518 | PIPING NI [SITE SURVEY] #110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000519 | PIPING NI [SITE SURVEY] #111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000520 | PIPING NI [SITE SURVEY] #112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000521 | PIPING NI [SITE SURVEY] #113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000522 | PIPING NI [SITE SURVEY] #114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000523 | PIPING NI [SITE SURVEY] #115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000524 | PIPING NI [SITE SURVEY] #116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000525 | PIPING NI [SITE SURVEY] #117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000526 | PIPING NI [SITE SURVEY] #118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000527 | PIPING NI [SITE SURVEY] #119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000528 | PIPING NI [SITE SURVEY] #120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000529 | PIPING NI [SITE SURVEY] #121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000530 | PIPING NI# [ISOMETRIC]1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000531 | PIPING NI# [ISOMETRIC]2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000532 | PIPING NI# [ISOMETRIC]3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000533 | PIPING NI# [ISOMETRIC]4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000534 | PIPING NI# [ISOMETRIC]5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000535 | PIPING NI# [ISOMETRIC]6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000536 | PIPING NI# [ISOMETRIC]7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000537 | PIPING NI# [ISOMETRIC]8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000538 | PIPING NI# [ISOMETRIC]9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000539 | PIPING NI# [ISOMETRIC]10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000540 | PIPING NI# [ISOMETRIC]11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000541 | PIPING NI# [ISOMETRIC]12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000542 | PIPING NI# [ISOMETRIC]13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000543 | PIPING NI# [ISOMETRIC]14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000544 | PIPING NI# [ISOMETRIC]15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000545 | PIPING NI# [ISOMETRIC]16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000546 | PIPING NI# [ISOMETRIC]17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000547 | PIPING NI# [ISOMETRIC]18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000548 | PIPING NI# [ISOMETRIC]19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000549 | PIPING NI# [ISOMETRIC]20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000550 | PIPING NI# [ISOMETRIC]21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000551 | PIPING NI# [ISOMETRIC]22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000552 | PIPING NI# [ISOMETRIC]23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000553 | PIPING NI# [ISOMETRIC]24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000554 | PIPING NI# [ISOMETRIC]25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000555 | PIPING NI# [ISOMETRIC]26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000556 | PIPING NI# [ISOMETRIC]27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000557 | PIPING NI# [ISOMETRIC]28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000558 | PIPING NI# [ISOMETRIC]29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000559 | PIPING NI# [ISOMETRIC]30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000560 | PIPING NI# [ISOMETRIC]31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000561 | PIPING NI# [ISOMETRIC]32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000562 | PIPING NI# [ISOMETRIC]33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000563 | PIPING NI# [ISOMETRIC]34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000564 | PIPING NI# [ISOMETRIC]35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000565 | PIPING NI# [ISOMETRIC]36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000566 | PIPING NI# [ISOMETRIC]37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000567 | PIPING NI# [ISOMETRIC]38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000568 | PIPING NI# [ISOMETRIC]39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000569 | PIPING NI# [ISOMETRIC]40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000570 | PIPING NI# [ISOMETRIC]41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-21 | 2023-01-05 |  | 2023-01-20 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000571 | PIPING NI# [ISOMETRIC]42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000572 | PIPING NI# [ISOMETRIC]43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000573 | PIPING NI# [ISOMETRIC]44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000574 | PIPING NI# [ISOMETRIC]45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000575 | PIPING NI# [ISOMETRIC]46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000576 | PIPING NI# [ISOMETRIC]47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000577 | PIPING NI# [ISOMETRIC]48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000578 | PIPING NI# [ISOMETRIC]49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000579 | PIPING NI# [ISOMETRIC]50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000580 | PIPING NI# [ISOMETRIC]51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000581 | PIPING NI# [ISOMETRIC]52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000582 | PIPING NI# [ISOMETRIC]53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000583 | PIPING NI# [ISOMETRIC]54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000584 | PIPING NI# [ISOMETRIC]55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000585 | PIPING NI# [ISOMETRIC]56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000586 | PIPING NI# [ISOMETRIC]57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000587 | PIPING NI# [ISOMETRIC]58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000588 | PIPING NI# [ISOMETRIC]59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000589 | PIPING NI# [ISOMETRIC]60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000590 | PIPING NI# [ISOMETRIC]61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000591 | PIPING NI# [ISOMETRIC]62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000592 | PIPING NI# [ISOMETRIC]63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000593 | PIPING NI# [ISOMETRIC]64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000594 | PIPING NI# [ISOMETRIC]65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000595 | PIPING NI# [ISOMETRIC]66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000596 | PIPING NI# [ISOMETRIC]67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000597 | PIPING NI# [ISOMETRIC]68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000598 | PIPING NI# [ISOMETRIC]69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000599 | PIPING NI# [ISOMETRIC]70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000600 | PIPING NI# [ISOMETRIC]71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000601 | PIPING NI# [ISOMETRIC]72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000602 | PIPING NI# [ISOMETRIC]73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000603 | PIPING NI# [ISOMETRIC]74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000604 | PIPING NI# [ISOMETRIC]75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000605 | PIPING NI# [ISOMETRIC]76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000606 | PIPING NI# [ISOMETRIC]77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000607 | PIPING NI# [ISOMETRIC]78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000608 | PIPING NI# [ISOMETRIC]79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-01 | 2023-01-16 |  | 2023-01-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000609 | PIPING NI# [ISOMETRIC]80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000610 | PIPING NI# [ISOMETRIC]81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000611 | PIPING NI# [ISOMETRIC]82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000612 | PIPING NI# [ISOMETRIC]83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000613 | PIPING NI# [ISOMETRIC]84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000614 | PIPING NI# [ISOMETRIC]85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000615 | PIPING NI# [ISOMETRIC]86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000616 | PIPING NI# [ISOMETRIC]87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000617 | PIPING NI# [ISOMETRIC]88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000618 | PIPING NI# [ISOMETRIC]89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000619 | PIPING NI# [ISOMETRIC]90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000620 | PIPING NI# [ISOMETRIC]91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000621 | PIPING NI# [ISOMETRIC]92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000622 | PIPING NI# [ISOMETRIC]93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000623 | PIPING NI# [ISOMETRIC]94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000624 | PIPING NI# [ISOMETRIC]95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000625 | PIPING NI# [ISOMETRIC]96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000626 | PIPING NI# [ISOMETRIC]97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000627 | PIPING NI# [ISOMETRIC]98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000628 | PIPING NI# [ISOMETRIC]99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000629 | PIPING NI# [ISOMETRIC]100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000630 | PIPING NI# [ISOMETRIC]101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000631 | PIPING NI# [ISOMETRIC]102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000632 | PIPING NI# [ISOMETRIC]103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000633 | PIPING NI# [ISOMETRIC]104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000634 | PIPING NI# [ISOMETRIC]105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000635 | PIPING NI# [ISOMETRIC]106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000636 | PIPING NI# [ISOMETRIC]107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000637 | PIPING NI# [ISOMETRIC]108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000638 | PIPING NI# [ISOMETRIC]109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000639 | PIPING NI# [ISOMETRIC]110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000640 | PIPING NI# [ISOMETRIC]111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000641 | PIPING NI# [ISOMETRIC]112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000642 | PIPING NI# [ISOMETRIC]113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000643 | PIPING NI# [ISOMETRIC]114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000644 | PIPING NI# [ISOMETRIC]115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000645 | PIPING NI# [ISOMETRIC]116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000646 | PIPING NI# [ISOMETRIC]117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000647 | PIPING NI# [ISOMETRIC]118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000648 | PIPING NI# [ISOMETRIC]119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000649 | PIPING NI# [ISOMETRIC]120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000650 | PIPING NI# [ISOMETRIC]121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000651 | PIPING NI [DOSSIER LIFTING] #1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000652 | PIPING NI [DOSSIER LIFTING] #2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000653 | PIPING NI [DOSSIER LIFTING] #3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000654 | PIPING NI [DOSSIER LIFTING] #4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000655 | PIPING NI [DOSSIER LIFTING] #5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000656 | PIPING NI [DOSSIER LIFTING] #6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000657 | PIPING NI [DOSSIER LIFTING] #7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000658 | PIPING NI [DOSSIER LIFTING] #8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000659 | PIPING NI [DOSSIER LIFTING] #9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000660 | PIPING NI [DOSSIER LIFTING] #10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000661 | PIPING NI [DOSSIER LIFTING] #11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000662 | PIPING NI [DOSSIER LIFTING] #12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000663 | PIPING NI [DOSSIER LIFTING] #13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000664 | PIPING NI [DOSSIER LIFTING] #14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000665 | PIPING NI [DOSSIER LIFTING] #15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000666 | PIPING NI [DOSSIER LIFTING] #16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000667 | PIPING NI [DOSSIER LIFTING] #17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000668 | PIPING NI [DOSSIER LIFTING] #18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000669 | PIPING NI [DOSSIER LIFTING] #19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000670 | PIPING NI [DOSSIER LIFTING] #20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000671 | PIPING NI [DOSSIER LIFTING] #21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000672 | PIPING NI [DOSSIER LIFTING] #22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000673 | PIPING NI [DOSSIER LIFTING] #23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000674 | PIPING NI [DOSSIER LIFTING] #24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000675 | PIPING NI [DOSSIER LIFTING] #25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000676 | PIPING NI [DOSSIER LIFTING] #26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000677 | PIPING NI [DOSSIER LIFTING] #27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000678 | PIPING NI [DOSSIER LIFTING] #28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000679 | PIPING NI [DOSSIER LIFTING] #29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000680 | PIPING NI [DOSSIER LIFTING] #30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000681 | PIPING NI [DOSSIER LIFTING] #31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000682 | PIPING NI [DOSSIER LIFTING] #32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000683 | PIPING NI [DOSSIER LIFTING] #33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000684 | PIPING NI [DOSSIER LIFTING] #34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000685 | PIPING NI [DOSSIER LIFTING] #35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000686 | PIPING NI [DOSSIER LIFTING] #36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000687 | PIPING NI [DOSSIER LIFTING] #37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000688 | PIPING NI [DOSSIER LIFTING] #38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000689 | PIPING NI [DOSSIER LIFTING] #39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000690 | PIPING NI [DOSSIER LIFTING] #40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-27 | 2023-04-11 |  | 2023-04-26 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000691 | PIPING NI [DOSSIER LIFTING] #41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000692 | PIPING NI [DOSSIER LIFTING] #42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000693 | PIPING NI [DOSSIER LIFTING] #43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000694 | PIPING NI [DOSSIER LIFTING] #44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000695 | PIPING NI [DOSSIER LIFTING] #45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000696 | PIPING NI [DOSSIER LIFTING] #46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000697 | PIPING NI [DOSSIER LIFTING] #47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000698 | PIPING NI [DOSSIER LIFTING] #48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000699 | PIPING NI [DOSSIER LIFTING] #49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000700 | PIPING NI [DOSSIER LIFTING] #50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000701 | PIPING NI [DOSSIER LIFTING] #51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000702 | PIPING NI [DOSSIER LIFTING] #52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000703 | PIPING NI [DOSSIER LIFTING] #53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000704 | PIPING NI [DOSSIER LIFTING] #54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000705 | PIPING NI [DOSSIER LIFTING] #55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000706 | PIPING NI [DOSSIER LIFTING] #56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000707 | PIPING NI [DOSSIER LIFTING] #57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000708 | PIPING NI [DOSSIER LIFTING] #58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000709 | PIPING NI [DOSSIER LIFTING] #59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000710 | PIPING NI [DOSSIER LIFTING] #60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000711 | PIPING NI [DOSSIER LIFTING] #61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000712 | PIPING NI [DOSSIER LIFTING] #62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000713 | PIPING NI [DOSSIER LIFTING] #63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000714 | PIPING NI [DOSSIER LIFTING] #64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000715 | PIPING NI [DOSSIER LIFTING] #65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000716 | PIPING NI [DOSSIER LIFTING] #66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000717 | PIPING NI [DOSSIER LIFTING] #67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000718 | PIPING NI [DOSSIER LIFTING] #68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000719 | PIPING NI [DOSSIER LIFTING] #69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000720 | PIPING NI [DOSSIER LIFTING] #70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000721 | PIPING NI [DOSSIER LIFTING] #71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000722 | PIPING NI [DOSSIER LIFTING] #72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000723 | PIPING NI [DOSSIER LIFTING] #73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000724 | PIPING NI [DOSSIER LIFTING] #74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000725 | PIPING NI [DOSSIER LIFTING] #75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000726 | PIPING NI [DOSSIER LIFTING] #76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000727 | PIPING NI [DOSSIER LIFTING] #77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000728 | PIPING NI [DOSSIER LIFTING] #78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000729 | PIPING NI [DOSSIER LIFTING] #79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-06 | 2023-04-21 |  | 2023-05-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000730 | PIPING NI [DOSSIER LIFTING] #80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000731 | PIPING NI [DOSSIER LIFTING] #81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000732 | PIPING NI [DOSSIER LIFTING] #82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000733 | PIPING NI [DOSSIER LIFTING] #83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000734 | PIPING NI [DOSSIER LIFTING] #84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000735 | PIPING NI [DOSSIER LIFTING] #85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000736 | PIPING NI [DOSSIER LIFTING] #86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000737 | PIPING NI [DOSSIER LIFTING] #87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000738 | PIPING NI [DOSSIER LIFTING] #88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000739 | PIPING NI [DOSSIER LIFTING] #89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000740 | PIPING NI [DOSSIER LIFTING] #90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000741 | PIPING NI [DOSSIER LIFTING] #91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000742 | PIPING NI [DOSSIER LIFTING] #92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000743 | PIPING NI [DOSSIER LIFTING] #93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000744 | PIPING NI [DOSSIER LIFTING] #94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000745 | PIPING NI [DOSSIER LIFTING] #95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000746 | PIPING NI [DOSSIER LIFTING] #96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000747 | PIPING NI [DOSSIER LIFTING] #97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000748 | PIPING NI [DOSSIER LIFTING] #98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000749 | PIPING NI [DOSSIER LIFTING] #99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000750 | PIPING NI [DOSSIER LIFTING] #100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000751 | PIPING NI [DOSSIER LIFTING] #101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000752 | PIPING NI [DOSSIER LIFTING] #102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000753 | PIPING NI [DOSSIER LIFTING] #103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000754 | PIPING NI [DOSSIER LIFTING] #104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000755 | PIPING NI [DOSSIER LIFTING] #105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000756 | PIPING NI [DOSSIER LIFTING] #106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000757 | PIPING NI [DOSSIER LIFTING] #107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000758 | PIPING NI [DOSSIER LIFTING] #108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000759 | PIPING NI [DOSSIER LIFTING] #109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000760 | PIPING NI [DOSSIER LIFTING] #110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000761 | PIPING NI [DOSSIER LIFTING] #111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000762 | PIPING NI [DOSSIER LIFTING] #112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000763 | PIPING NI [DOSSIER LIFTING] #113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000764 | PIPING NI [DOSSIER LIFTING] #114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000765 | PIPING NI [DOSSIER LIFTING] #115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000766 | PIPING NI [DOSSIER LIFTING] #116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000767 | PIPING NI [DOSSIER LIFTING] #117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000768 | PIPING NI [DOSSIER LIFTING] #118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000769 | PIPING NI [DOSSIER LIFTING] #119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000770 | PIPING NI [DOSSIER LIFTING] #120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000771 | PIPING NI [DOSSIER LIFTING] #121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000772 | PIPING NI# [DOSSIER FINAL] 1 AIR SYSTEM 46005853 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000773 | PIPING NI# [DOSSIER FINAL] 2 AIR SYSTEM 46005855 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000774 | PIPING NI# [DOSSIER FINAL] 3 AIR SYSTEM 46005856 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000775 | PIPING NI# [DOSSIER FINAL] 4 AIR SYSTEM 46007510 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000776 | PIPING NI# [DOSSIER FINAL] 5 CHEMICAL SYSTEM 46006147 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000777 | PIPING NI# [DOSSIER FINAL] 6 COOLING WATER SYSTEM 46005504 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000778 | PIPING NI# [DOSSIER FINAL] 7 COOLING WATER SYSTEM 46005573 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000779 | PIPING NI# [DOSSIER FINAL] 8 COOLING WATER SYSTEM 46005783 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000780 | PIPING NI# [DOSSIER FINAL] 9 COOLING WATER SYSTEM 46005784 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000781 | PIPING NI# [DOSSIER FINAL] 10 COOLING WATER SYSTEM 46005785 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000782 | PIPING NI# [DOSSIER FINAL] 11 COOLING WATER SYSTEM 46005786 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000783 | PIPING NI# [DOSSIER FINAL] 12 COOLING WATER SYSTEM 46005787 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000784 | PIPING NI# [DOSSIER FINAL] 13 COOLING WATER SYSTEM 46005833 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000785 | PIPING NI# [DOSSIER FINAL] 14 COOLING WATER SYSTEM 46005940 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000786 | PIPING NI# [DOSSIER FINAL] 15 COOLING WATER SYSTEM 46005968 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000787 | PIPING NI# [DOSSIER FINAL] 16 COOLING WATER SYSTEM 46006014 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000788 | PIPING NI# [DOSSIER FINAL] 17 COOLING WATER SYSTEM 46006099 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000789 | PIPING NI# [DOSSIER FINAL] 18 COOLING WATER SYSTEM 46006150 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000790 | PIPING NI# [DOSSIER FINAL] 19 COOLING WATER SYSTEM 46006151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000791 | PIPING NI# [DOSSIER FINAL] 20 COOLING WATER SYSTEM 46006181 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000792 | PIPING NI# [DOSSIER FINAL] 21 COOLING WATER SYSTEM 46006223 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000793 | PIPING NI# [DOSSIER FINAL] 22 COOLING WATER SYSTEM 46006624 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000794 | PIPING NI# [DOSSIER FINAL] 23 COOLING WATER SYSTEM 46006636 = 46006425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000795 | PIPING NI# [DOSSIER FINAL] 24 COOLING WATER SYSTEM 46006762 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000796 | PIPING NI# [DOSSIER FINAL] 25 COOLING WATER SYSTEM 46006882 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000797 | PIPING NI# [DOSSIER FINAL] 26 COOLING WATER SYSTEM 46006894 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000798 | PIPING NI# [DOSSIER FINAL] 27 COOLING WATER SYSTEM 46007199 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000799 | PIPING NI# [DOSSIER FINAL] 28 COOLING WATER SYSTEM 46007200 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000800 | PIPING NI# [DOSSIER FINAL] 29 COOLING WATER SYSTEM 46007304 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000801 | PIPING NI# [DOSSIER FINAL] 30 COOLING WATER SYSTEM 46007508 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000802 | PIPING NI# [DOSSIER FINAL] 31 COOLING WATER SYSTEM 46007576 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000803 | PIPING NI# [DOSSIER FINAL] 32 COOLING WATER SYSTEM 46007602 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000804 | PIPING NI# [DOSSIER FINAL] 33 COOLING WATER SYSTEM 46007603 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000805 | PIPING NI# [DOSSIER FINAL] 34 COOLING WATER SYSTEM 46007604 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000806 | PIPING NI# [DOSSIER FINAL] 35 COOLING WATER SYSTEM 46007605 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000807 | PIPING NI# [DOSSIER FINAL] 36 COOLING WATER SYSTEM 46007606 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000808 | PIPING NI# [DOSSIER FINAL] 37 COOLING WATER SYSTEM 46007607 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000809 | PIPING NI# [DOSSIER FINAL] 38 COOLING WATER SYSTEM 46007614 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000810 | PIPING NI# [DOSSIER FINAL] 39 COOLING WATER SYSTEM 46007615 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000811 | PIPING NI# [DOSSIER FINAL] 40 COOLING WATER SYSTEM 46005411 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-25 | 2023-06-09 |  | 2023-06-24 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000812 | PIPING NI# [DOSSIER FINAL] 41 COOLING WATER SYSTEM 46006013 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000813 | PIPING NI# [DOSSIER FINAL] 42 COOLING WATER SYSTEM 46006015 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000814 | PIPING NI# [DOSSIER FINAL] 43 FIREWATER SYSTEM 46004394 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000815 | PIPING NI# [DOSSIER FINAL] 44 FIREWATER SYSTEM 46004801 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000816 | PIPING NI# [DOSSIER FINAL] 45 FIREWATER SYSTEM 46005362 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000817 | PIPING NI# [DOSSIER FINAL] 46 FIREWATER SYSTEM 46005367 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000818 | PIPING NI# [DOSSIER FINAL] 47 FIREWATER SYSTEM 46007197 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000819 | PIPING NI# [DOSSIER FINAL] 48 GAS SYSTEM 46005502 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000820 | PIPING NI# [DOSSIER FINAL] 49 GAS SYSTEM 46006182 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000821 | PIPING NI# [DOSSIER FINAL] 50 GAS SYSTEM 46006183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000822 | PIPING NI# [DOSSIER FINAL] 51 GAS SYSTEM 46006375 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000823 | PIPING NI# [DOSSIER FINAL] 52 GAS SYSTEM 46006660 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000824 | PIPING NI# [DOSSIER FINAL] 53 GAS SYSTEM 46007151 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000825 | PIPING NI# [DOSSIER FINAL] 54 GAS SYSTEM 46007163 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000826 | PIPING NI# [DOSSIER FINAL] 55 GAS SYSTEM 46007268 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000827 | PIPING NI# [DOSSIER FINAL] 56 GAS SYSTEM 46007522 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000828 | PIPING NI# [DOSSIER FINAL] 57 GAS SYSTEM 46007553 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000829 | PIPING NI# [DOSSIER FINAL] 58 GAS SYSTEM 46007577 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000830 | PIPING NI# [DOSSIER FINAL] 59 GAS SYSTEM 46004652 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000831 | PIPING NI# [DOSSIER FINAL] 60 HVAC / HOT WATER SYSTEM 46004662 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000832 | PIPING NI# [DOSSIER FINAL] 61 HVAC / HOT WATER SYSTEM 46005769 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000833 | PIPING NI# [DOSSIER FINAL] 62 HVAC / HOT WATER SYSTEM 46005770 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000834 | PIPING NI# [DOSSIER FINAL] 63 HVAC / HOT WATER SYSTEM 46005915 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000835 | PIPING NI# [DOSSIER FINAL] 64 HVAC / HOT WATER SYSTEM 46005982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000836 | PIPING NI# [DOSSIER FINAL] 65 HVAC / HOT WATER SYSTEM 46007045 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000837 | PIPING NI# [DOSSIER FINAL] 66 HVAC / HOT WATER SYSTEM 46007052 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000838 | PIPING NI# [DOSSIER FINAL] 67 HVAC / HOT WATER SYSTEM 46007566 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000839 | PIPING NI# [DOSSIER FINAL] 68 HVAC / HOT WATER SYSTEM 46004053 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000840 | PIPING NI# [DOSSIER FINAL] 69 HVAC / HOT WATER SYSTEM 46007561-2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000841 | PIPING NI# [DOSSIER FINAL] 70 HVAC / HOT WATER SYSTEM 46007564-4 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000842 | PIPING NI# [DOSSIER FINAL] 71 HVAC / HOT WATER SYSTEM 46007565-21 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000843 | PIPING NI# [DOSSIER FINAL] 72 HVAC / HOT WATER SYSTEM 46007568-29 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000844 | PIPING NI# [DOSSIER FINAL] 73 HVAC / HOT WATER SYSTEM 46007571-34 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000845 | PIPING NI# [DOSSIER FINAL] 74 HVAC / HOT WATER SYSTEM 46007572-35 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000846 | PIPING NI# [DOSSIER FINAL] 75 HVAC / HOT WATER SYSTEM 46007573-39 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000847 | PIPING NI# [DOSSIER FINAL] 76 HVAC / HOT WATER SYSTEM 46007574-40 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000848 | PIPING NI# [DOSSIER FINAL] 77 INERT SYSTEM 46007407 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000849 | PIPING NI# [DOSSIER FINAL] 78 INERT SYSTEM 46007408 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000850 | PIPING NI# [DOSSIER FINAL] 79 OIL SYSTEM 46003301 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000851 | PIPING NI# [DOSSIER FINAL] 80 OIL SYSTEM 46005365 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000852 | PIPING NI# [DOSSIER FINAL] 81 OIL SYSTEM 46005594 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000853 | PIPING NI# [DOSSIER FINAL] 82 OIL SYSTEM 46005766 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000854 | PIPING NI# [DOSSIER FINAL] 83 OIL SYSTEM 46005777 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000855 | PIPING NI# [DOSSIER FINAL] 84 OIL SYSTEM 46005778 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000856 | PIPING NI# [DOSSIER FINAL] 85 OIL SYSTEM 46006416 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-05 | 2023-06-20 |  | 2023-07-05 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000857 | PIPING NI# [DOSSIER FINAL] 86 OIL SYSTEM 46006753 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000858 | PIPING NI# [DOSSIER FINAL] 87 OIL SYSTEM 46007152 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000859 | PIPING NI# [DOSSIER FINAL] 88 OIL SYSTEM 46007161 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000860 | PIPING NI# [DOSSIER FINAL] 89 OIL SYSTEM 46007422 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000861 | PIPING NI# [DOSSIER FINAL] 90 OIL SYSTEM 46007524 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000862 | PIPING NI# [DOSSIER FINAL] 91 OIL SYSTEM 46007525 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000863 | PIPING NI# [DOSSIER FINAL] 92 OIL SYSTEM 46007526 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000864 | PIPING NI# [DOSSIER FINAL] 93 OIL SYSTEM 46007527 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000865 | PIPING NI# [DOSSIER FINAL] 94 OIL SYSTEM 46007528 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000866 | PIPING NI# [DOSSIER FINAL] 95 OIL SYSTEM 46007529 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000867 | PIPING NI# [DOSSIER FINAL] 96 OIL SYSTEM 46007530 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000868 | PIPING NI# [DOSSIER FINAL] 97 OIL SYSTEM 46007531 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000869 | PIPING NI# [DOSSIER FINAL] 98 OIL SYSTEM 46007532 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000870 | PIPING NI# [DOSSIER FINAL] 99 OIL SYSTEM 46007591 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000871 | PIPING NI# [DOSSIER FINAL] 100 OIL SYSTEM 46007592 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000872 | PIPING NI# [DOSSIER FINAL] 101 OIL SYSTEM 46005366 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000873 | PIPING NI# [DOSSIER FINAL] 102 OIL SYSTEM 46006033 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000874 | PIPING NI# [DOSSIER FINAL] 103 OIL SYSTEM 46006283 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000875 | PIPING NI# [DOSSIER FINAL] 104 OIL SYSTEM 46007160 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000876 | PIPING NI# [DOSSIER FINAL] 105 OIL SYSTEM 46007560 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000877 | PIPING NI# [DOSSIER FINAL] 106 OIL SYSTEM 46007562-45 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000878 | PIPING NI# [DOSSIER FINAL] 107 OIL SYSTEM 46007563-3 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000879 | PIPING NI# [DOSSIER FINAL] 108 WATER INJECTION 46007274 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000880 | PIPING NI# [DOSSIER FINAL] 109 GAS SYSTEM 46007556 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000881 | PIPING NI# [DOSSIER FINAL] 110 GAS SYSTEM 46005903 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000882 | PIPING NI# [DOSSIER FINAL] 111 OIL SYSTEM 46005741 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000883 | PIPING NI# [DOSSIER FINAL] 112 OIL SYSTEM 46007132 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000884 | PIPING NI# [DOSSIER FINAL] 113 OIL SYSTEM 46007205 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000885 | PIPING NI# [DOSSIER FINAL] 114 OIL SYSTEM 46006278 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000886 | PIPING NI# [DOSSIER FINAL] 115 OIL SYSTEM 46006632 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000887 | PIPING NI# [DOSSIER FINAL] 116 OIL SYSTEM 46006922 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000888 | PIPING NI# [DOSSIER FINAL] 117 OIL SYSTEM 46007570-33 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000889 | PIPING NI# [DOSSIER FINAL] 118 HVAC / HOT WATER SYSTEM 46004977 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000890 | PIPING NI# [DOSSIER FINAL] 119 HVAC / HOT WATER SYSTEM 46004982 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000891 | PIPING NI# [DOSSIER FINAL] 120 COOLING WATER SYSTEM 46005973-12 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000892 | PIPING NI# [DOSSIER FINAL] 121 COOLING WATER SYSTEM 46007183 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000893 | SMR [SITE SURVEY] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000894 | SMR [SITE SURVEY] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000895 | SMR [SITE SURVEY] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000896 | SMR [SITE SURVEY] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000897 | SMR [SITE SURVEY] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000898 | SMR [SITE SURVEY] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000899 | SMR [SITE SURVEY] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000900 | SMR [SITE SURVEY] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000901 | SMR [SITE SURVEY] #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000902 | SMR [SITE SURVEY] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-15 | 2022-12-30 |  | 2023-01-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000903 | SMR [SITE SURVEY] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-30 | 2023-01-14 |  | 2023-01-29 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000904 | SMR [SITE SURVEY] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-30 | 2023-01-14 |  | 2023-01-29 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000905 | SMR [SITE SURVEY] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2022-12-30 | 2023-01-14 |  | 2023-01-29 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000906 | SMR [ISOMETRIC] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000907 | SMR [ISOMETRIC] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000908 | SMR [ISOMETRIC] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000909 | SMR [ISOMETRIC] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000910 | SMR [ISOMETRIC] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000911 | SMR [ISOMETRIC] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000912 | SMR [ISOMETRIC] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000913 | SMR [ISOMETRIC] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000914 | SMR [ISOMETRIC] #9 - NG-AKP-RFM-2022-000026 - Installation of Dossier Finallation valves on instrument air network - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000915 | SMR [ISOMETRIC] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000916 | SMR [ISOMETRIC] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000917 | SMR [ISOMETRIC] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000918 | SMR [ISOMETRIC] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Dossier Final | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000919 | SMR [DOSSIER LIFTING} #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000920 | SMR [DOSSIER LIFTING} #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000921 | SMR [DOSSIER LIFTING} #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000922 | SMR [DOSSIER LIFTING} #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000923 | SMR [DOSSIER LIFTING} #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000924 | SMR [DOSSIER LIFTING} #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000925 | SMR [DOSSIER LIFTING} #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000926 | SMR [DOSSIER LIFTING} #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000927 | SMR [DOSSIER LIFTING} #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000928 | SMR [DOSSIER LIFTING} #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000929 | SMR [DOSSIER LIFTING} #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000930 | SMR [DOSSIER LIFTING} #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000931 | SMR [DOSSIER LIFTING} #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000932 | SMR [DOSSIER FINAL] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000933 | SMR [DOSSIER FINAL] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000934 | SMR [DOSSIER FINAL] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000935 | SMR [DOSSIER FINAL] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000936 | SMR [DOSSIER FINAL] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000937 | SMR [DOSSIER FINAL] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000938 | SMR [DOSSIER FINAL] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000939 | SMR [DOSSIER FINAL] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000940 | SMR [DOSSIER FINAL] #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000941 | SMR [DOSSIER FINAL] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000942 | SMR [DOSSIER FINAL] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000943 | SMR [DOSSIER FINAL] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000944 | SMR [DOSSIER FINAL] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-30 | 2023-07-15 |  | 2023-07-30 |  |  | 0.2% |  |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000945 | [SITE SURVEY] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000946 | [SITE SURVEY] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000947 | [SITE SURVEY] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000948 | [SITE SURVEY] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000949 | [SITE SURVEY] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000950 | [SITE SURVEY] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000951 | [SITE SURVEY] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000952 | [SITE SURVEY] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000953 | [SITE SURVEY] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000954 | [SITE SURVEY] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000955 | [SITE SURVEY] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000956 | [SITE SURVEY] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000957 | [SITE SURVEY] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000958 | [SITE SURVEY] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000959 | [SITE SURVEY] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000960 | [DOSSIER LIFTING] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000961 | [DOSSIER LIFTING] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000962 | [DOSSIER LIFTING] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000963 | [DOSSIER LIFTING] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000964 | [DOSSIER LIFTING] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000965 | [DOSSIER LIFTING] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000966 | [DOSSIER LIFTING] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000967 | [DOSSIER LIFTING] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000968 | [DOSSIER LIFTING] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000969 | [DOSSIER LIFTING] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000970 | [DOSSIER LIFTING] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000971 | [DOSSIER LIFTING] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000972 | [DOSSIER LIFTING] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000973 | [DOSSIER LIFTING] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000974 | [DOSSIER LIFTING] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000975 | [CLEANING PROCEDURES] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000976 | [CLEANING PROCEDURES] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000977 | [CLEANING PROCEDURES] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000978 | [CLEANING PROCEDURES] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000979 | [CLEANING PROCEDURES] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000980 | [CLEANING PROCEDURES] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000981 | [CLEANING PROCEDURES] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000982 | [CLEANING PROCEDURES] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000983 | [CLEANING PROCEDURES] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000984 | [CLEANING PROCEDURES] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000985 | [CLEANING PROCEDURES] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000986 | [CLEANING PROCEDURES] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000987 | [CLEANING PROCEDURES] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000988 | [CLEANING PROCEDURES] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000989 | [CLEANING PROCEDURES] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000990 | [DOSSIER FINAL] 5-EC-5210 Mp Compressor suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000991 | [DOSSIER FINAL] 5-EC-5510-A Dehydrator intlet Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000992 | [DOSSIER FINAL] 5-EC-5510-B Dehydrator intlet Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000993 | [DOSSIER FINAL] 5-EC-5544 Lean Glycol Cooler (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000994 | [DOSSIER FINAL] 5-EC-5110 LP Compressor Suction Cooler | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000995 | [DOSSIER FINAL] 5-EC-5430-B Gas Export Compressor discharge Coolers B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000996 | [DOSSIER FINAL] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000997 | [DOSSIER FINAL] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000998 | [DOSSIER FINAL] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-000999 | [DOSSIER FINAL] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001000 | [DOSSIER FINAL] 5-EC-9910 Crude Oil Re-Heater | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001001 | [DOSSIER FINAL] 5-EC-3320-B1 Crude Oil Heaters B1 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001002 | [DOSSIER FINAL] 5-EC-3320-B2 Crude Oil Heaters B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001003 | [DOSSIER FINAL] 5-EC-5310-A HP Compressor Suction Cooler A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001004 | [DOSSIER FINAL] 5-EC-5310-B HP Compressor Suction Cooler B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-15 | 2023-06-30 |  | 2023-07-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001005 | [SITE SURVEY] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001006 | [SITE SURVEY] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001007 | [SITE SURVEY] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001008 | [SITE SURVEY] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001009 | [SITE SURVEY] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001010 | [SITE SURVEY] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-16 | 2023-03-03 |  | 2023-03-18 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001011 | [DOSSIER LIFTING] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001012 | [DOSSIER LIFTING] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001013 | [DOSSIER LIFTING] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001014 | [DOSSIER LIFTING] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001015 | [DOSSIER LIFTING] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001016 | [DOSSIER LIFTING] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001017 | [CLEANING PROCEDURES] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001018 | [CLEANING PROCEDURES] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001019 | [CLEANING PROCEDURES] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001020 | [CLEANING PROCEDURES] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001021 | [CLEANING PROCEDURES] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001022 | [CLEANING PROCEDURES] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001023 | [DOSSIER FINAL] 5-DS-5410-A Gas Export Scrubber A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001024 | [DOSSIER FINAL] 5-DS-5410-B Gas Export Scrubber B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001025 | [DOSSIER FINAL] 5-DS-2210 Hp Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001026 | [DOSSIER FINAL] 5-DS-5120 LP Compressor suction Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001027 | [DOSSIER FINAL] 5-DS-2240 LP Fuel Gas Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001028 | [DOSSIER FINAL] 5-DS-5520 Dehydrator Inlet Scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001029 | [SITE SURVEY] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001030 | [SITE SURVEY] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001031 | [SITE SURVEY] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001032 | [SITE SURVEY] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001033 | [SITE SURVEY] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001034 | [SITE SURVEY] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-16 | 2023-03-31 |  | 2023-04-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001035 | [DOSSIER LIFTING] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001036 | [DOSSIER LIFTING] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001037 | [DOSSIER LIFTING] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001038 | [DOSSIER LIFTING] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001039 | [DOSSIER LIFTING] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001040 | [DOSSIER LIFTING] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001041 | [CLEANING PROCEDURES] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001042 | [CLEANING PROCEDURES] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001043 | [CLEANING PROCEDURES] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001044 | [CLEANING PROCEDURES] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001045 | [CLEANING PROCEDURES] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001046 | [CLEANING PROCEDURES] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001047 | [DOSSIER FINAL] 5-DS-3110-A 1 Stage Separator A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001048 | [DOSSIER FINAL] 5-DS-3110-B 1 Stage Separator B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001049 | [DOSSIER FINAL] 5-DS-3210 2 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001050 | [DOSSIER FINAL] 5-DS-3410 3 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001051 | [DOSSIER FINAL] 5-DS-3610 4 Stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001052 | [DOSSIER FINAL] 5-DS-3120 Test Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-06-01 | 2023-06-16 |  | 2023-07-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001053 | [SITE SURVEY] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001054 | [SITE SURVEY] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001055 | [SITE SURVEY] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001056 | [SITE SURVEY] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001057 | [SITE SURVEY] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001058 | [SITE SURVEY] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001059 | [SITE SURVEY] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001060 | [SITE SURVEY] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001061 | [SITE SURVEY] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001062 | [SITE SURVEY] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001063 | [SITE SURVEY] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001064 | [SITE SURVEY] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001065 | [SITE SURVEY] 5-DS-3510 Electrostatic Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-16 | 2023-01-31 |  | 2023-02-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001066 | [DOSSIER LIFTING] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001067 | [DOSSIER LIFTING] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001068 | [DOSSIER LIFTING] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001069 | [DOSSIER LIFTING] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001070 | [DOSSIER LIFTING] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001071 | [DOSSIER LIFTING] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001072 | [DOSSIER LIFTING] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001073 | [DOSSIER LIFTING] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001074 | [DOSSIER LIFTING] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001075 | [DOSSIER LIFTING] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001076 | [DOSSIER LIFTING] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001077 | [DOSSIER LIFTING] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001078 | [DOSSIER LIFTING] 5-DS-3510 Electrostatic Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001079 | [CLEANING PROCEDURES] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001080 | [CLEANING PROCEDURES] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001081 | [CLEANING PROCEDURES] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001082 | [CLEANING PROCEDURES] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001083 | [CLEANING PROCEDURES] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001084 | [CLEANING PROCEDURES] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001085 | [CLEANING PROCEDURES] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001086 | [CLEANING PROCEDURES] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001087 | [CLEANING PROCEDURES] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001088 | [CLEANING PROCEDURES] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001089 | [CLEANING PROCEDURES] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001090 | [CLEANING PROCEDURES] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001091 | [CLEANING PROCEDURES] 5-DS-3510 Electrostatic Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001092 | [DOSSIER FINAL] 5-CA-5530 Glycol Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001093 | [DOSSIER FINAL] 5-DS-2140 LP Flare KO Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001094 | [DOSSIER FINAL] 5-DA-1340 Instrument Air Receveiver | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001095 | [DOSSIER FINAL] 5-DA-5544 Glycol Surge Drum (TEG) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001096 | [DOSSIER FINAL] 5-DS-4110 Oily Water Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001097 | [DOSSIER FINAL] 5-DS-4130 Degassing Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001098 | [DOSSIER FINAL] 5-DA-1630 Hot Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001099 | [DOSSIER FINAL] 5-DA-1540 Cooling Water Expansion Drum | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001100 | [DOSSIER FINAL] 5-TC-1730 Fire Fighting Foam Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001101 | [DOSSIER FINAL] 5-DS-5420-A Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001102 | [DOSSIER FINAL] 5-DS-5420-B Single Filter | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001103 | [DOSSIER FINAL] 5-DA-1350 Cooling Water Expansion Tank | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001104 | [DOSSIER FINAL] 5-DS-3510 Electrostatic Dehydrator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001105 | Valve [SITE SURVEY] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001106 | Valve [SITE SURVEY] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001107 | Valve [SITE SURVEY] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001108 | Valve [SITE SURVEY] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001109 | Valve [SITE SURVEY] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001110 | Valve [SITE SURVEY] #6 - 99-0002 - Suction GX9920 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001111 | Valve [SITE SURVEY] #7 - 31-0003 - check Valve upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001112 | Valve [SITE SURVEY] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001113 | Valve [SITE SURVEY] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001114 | Valve [SITE SURVEY] #10 - 16-0003 - 5ROV 16107A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001115 | Valve [SITE SURVEY] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001116 | Valve [SITE SURVEY] #12 - 16-0003 - 5ROV16111A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001117 | Valve [SITE SURVEY] #13 - 16-0003 - 5ROV16111B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001118 | Valve [SITE SURVEY] #14 - 16-0003 - 5ROV16107B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001119 | Valve [SITE SURVEY] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001120 | Valve [SITE SURVEY] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001121 | Valve [SITE SURVEY] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001122 | Valve [SITE SURVEY] #18 - 16-0006 - Manual Valve bypass of ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001123 | Valve [SITE SURVEY] #19 - 35-0001 - Check Valve downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001124 | Valve [SITE SURVEY] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001125 | Valve [SITE SURVEY] #21 - 41-0003 - Manual Valve at gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001126 | Valve [SITE SURVEY] #22 - 41-0002 - Manual Valve inlet of hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001127 | Valve [SITE SURVEY] #23 - 34-0001 - Manual Valve s to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001128 | Valve [SITE SURVEY] #24 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001129 | Valve [SITE SURVEY] #25 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001130 | Valve [SITE SURVEY] #26 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001131 | Valve [SITE SURVEY] #27 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001132 | Valve [SITE SURVEY] #28 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001133 | Valve [SITE SURVEY] #29 - 30-0002 - Manual Valve on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001134 | Valve [SITE SURVEY] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001135 | Valve [SITE SURVEY] #31 - 99-0002 - ROV on suction of 5GX9920B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001136 | Valve [SITE SURVEY] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001137 | Valve [SITE SURVEY] #33 - 33-0002 - Manual Valve on Oil outlet of the crude heater B1/B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001138 | Valve [SITE SURVEY] #34 - 31-0002 - Last manual ball Valve on oily H20 outlet1st stage B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001139 | Valve [SITE SURVEY] #35 - 71-0004 - Gearbox difficult to manipulate | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001140 | Valve [SITE SURVEY] #36 - 21-0010 - Manual Valve u/s PSV on HGVB does not close fully. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001141 | Valve [SITE SURVEY] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001142 | Valve [SITE SURVEY] #38 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001143 | Valve [SITE SURVEY] #39 - 52-0002 - Manul Valve upstream 5PSV2-52410 (MP Compressor) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001144 | Valve [SITE SURVEY] #40 - 30-0006 - Passing DBB( 1st upstream Valve on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001145 | Valve [SITE SURVEY] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001146 | Valve [SITE SURVEY] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block Valve stuck closed( Valve [SITE SURVEY] seat disengaged from stem). DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001147 | Valve [SITE SURVEY] #43 - 75-0003 - WI50 5HV75244. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001148 | Valve [SITE SURVEY] #44 - 75-0003 - WI10 5 HV75234. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001149 | Valve [SITE SURVEY] #45 - 54-0001 - 5LV54106A is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001150 | Valve [SITE SURVEY] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001151 | Valve [SITE SURVEY] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001152 | Valve [SITE SURVEY] #48 - 54-0005 - Manual Valve [SITE SURVEY] downstream of 5LV54106B is passing when closed. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001153 | Valve [SITE SURVEY] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001154 | Valve [SITE SURVEY] #50 - 94-0001 - Passing manual Valve | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001155 | Valve [SITE SURVEY] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001156 | Valve [SITE SURVEY] #52 - 83-0004 - 8" manual Valve to transfer manifold on offloading line B indicator stuck in the closed position | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001157 | Valve [SITE SURVEY] #53 - 53-004 - 3'' Manual isolation Valve for 5-LT-53206B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001158 | Valve [SITE SURVEY] #54 - 73-0002 - 20'' Manual Butterfly Valve passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001159 | Valve [SITE SURVEY] #55 - 71-0001 - 30'' Manual Butterfly Valve passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001160 | Valve [SITE SURVEY] #56 - 41-0002 - 10'' Manual inlet Valve [SITE SURVEY] to Hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001161 | Valve [SITE SURVEY] #57 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001162 | Valve [SITE SURVEY] #58 - 31-0003 - Water outlet SDV from the test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001163 | Valve [SITE SURVEY] #59 - 31-0003 - Manual Valve [SITE SURVEY] upstream 5LDV31206 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001164 | Valve [SITE SURVEY] #60 - 73-0002 - 20'' Manual Butterfly Valve passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001165 | Valve [SITE SURVEY] #61 - 73-0001 - 5ROV 73350A on fine filter A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001166 | Valve [SITE SURVEY] #62 - 54-0010 - Manual Valve [SITE SURVEY] upstream 5SDV54501 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001167 | Valve [SITE SURVEY] #63 - 73-0001 - 5ROV 73357E on fine filter E | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001168 | Valve [SITE SURVEY] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001169 | Valve [SITE SURVEY] #65 - 74-0002 - 3/4'' Manual gate Valve downstream 5SDV-74101B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001170 | Valve [SITE SURVEY] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001171 | Valve [SITE SURVEY] #67 - 53-0005 - 5-FV-53301B- HP B anti surge Valve | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001172 | Valve [SITE SURVEY] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001173 | Valve [SITE SURVEY] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001174 | Valve [SITE SURVEY] #70 - 54-0012 - 5-FV-54601- GIC anti surge Valve | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001175 | Valve [SITE SURVEY] #71 - 30-0002 - Passing DBB( upstream Valve on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001176 | Valve [SITE SURVEY] #72 - 30-0001 - Passing DBB( upstream Valve on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001177 | Valve [SITE SURVEY] #73 - 75-0003 - All isolation Valvs including 5SDV75232 on water injection string WI-20 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001178 | Valve [SITE SURVEY] #74 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001179 | Valve [SITE SURVEY] #75 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001180 | Valve [SITE SURVEY] #76 - 30-0003 - Passing DBB( upstream Valve on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001181 | Valve [SITE SURVEY] #77 - 34-0001 - 16'' SRI Valves on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001182 | Valve [SITE SURVEY] #78 - Unknown - 16'' SRI Valve s on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001183 | Valve [SITE SURVEY] #79 - Unknown - 16'' SRI Valves on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001184 | Valve [SITE SURVEY] #80 - 34-0001 - All isolation Valves on water injection string WI-10 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001185 | Valve [SITE SURVEY] #81 - 94-0001 - 3" Manual buterfly Valve on the sea water flushing line to discharge of sewage pump A. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001186 | Valve [SITE SURVEY] #82 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001187 | Valve [SITE SURVEY] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001188 | Valve [SITE SURVEY] #84 - 34-001 - Upstream manual Valve of 5PV1-34111 on 3rd stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001189 | Valve [SITE SURVEY] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001190 | Valve [SITE SURVEY] #86 - 31-0003 - manual Valve U/S 5PSV31207 test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001191 | Valve [SITE SURVEY] #87 - 21-0009 - 4'' discharge manual Valve of LP flare drum pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001192 | Valve [SITE SURVEY] #88 - 22-0001 - manual Valve U/S 5PSV1 22113 HP FG scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001193 | Valve [SITE SURVEY] #89 - 31-0001 - manual Valveupstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001194 | Valve [SITE SURVEY] #90 - 31-0001 - manual Valve downstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001195 | Valve [SITE SURVEY] #91 - 54-0001 - MANUAL Valve ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001196 | Valve [SITE SURVEY] #92 - 54-0005 - MANUAL Valve ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001197 | Valve [SITE SURVEY] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001198 | Valve [SITE SURVEY] #94 - 15-0001 - MANUAL ValveS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001199 | Valve [SITE SURVEY] #95 - 33-0002 - MANUAL Valve ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001200 | Valve [SITE SURVEY] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001201 | Valve [SITE SURVEY] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001202 | Valve [SITE SURVEY] #98 - 75-0002 - MANUAL Valve ON MINIMUM FLOWLINE OF WIP C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001203 | Valve [SITE SURVEY] #99 - 54-0007 - MANUAL Valve DOWNSTREAM 5EBDV54318B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001204 | Valve [SITE SURVEY] #100 - 31-0002 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001205 | Valve [SITE SURVEY] #101 - 21-0009 - 2" UPSTREAM MANUAL Valve ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001206 | Valve [SITE SURVEY] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGE ValveS (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001207 | Valve [SITE SURVEY] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGE ValveS (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001208 | Valve [SITE SURVEY] #104 - Unknown - Riser ESDV 30510 passing Valve | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001209 | Valve [SITE SURVEY] #105 - Unknown - Riser ESDV 30610 passing Valve | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001210 | Valve [SITE SURVEY] #106 - Unknown - ISO Valve [SITE SURVEY] DWSTRM - 5-PSV-15302A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001211 | Valve [SITE SURVEY] #107 - Unknown - ISO Valve [SITE SURVEY] DWSTRM - 5-PSV-15304B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001212 | Valve [SITE SURVEY] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001213 | Valve [SITE SURVEY] #109 - Unknown - CO PRE-HEAT M/ Valve [SITE SURVEY] PASSING - HC SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001214 | Valve [SITE SURVEY] #110 - Unknown - CO PRE-HEAT M/Valve [SITE SURVEY] PASSING - DRAIN SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001215 | Valve [SITE SURVEY] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001216 | Valve [SITE SURVEY] #112 - Unknown - HULL VENT BLOWER Valve (8") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001217 | Valve [SITE SURVEY] #113 - Unknown - HULL VENT BLOWER Valve (6") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001218 | Valve [DOSSIER LIFTING] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001219 | Valve [DOSSIER LIFTING] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001220 | Valve [DOSSIER LIFTING] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001221 | Valve [DOSSIER LIFTING] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001222 | Valve [DOSSIER LIFTING] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001223 | Valve [DOSSIER LIFTING] #6 - 99-0002 - Suction GX9920 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001224 | Valve [DOSSIER LIFTING] #7 - 31-0003 - check upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001225 | Valve [DOSSIER LIFTING] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001226 | Valve [DOSSIER LIFTING] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001227 | Valve [DOSSIER LIFTING] #10 - 16-0003 - 5ROV 16107A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001228 | Valve [DOSSIER LIFTING] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001229 | Valve [DOSSIER LIFTING] #12 - 16-0003 - 5ROV16111A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001230 | Valve [DOSSIER LIFTING] #13 - 16-0003 - 5ROV16111B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001231 | Valve [DOSSIER LIFTING] #14 - 16-0003 - 5ROV16107B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001232 | Valve [DOSSIER LIFTING] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001233 | Valve [DOSSIER LIFTING] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001234 | Valve [DOSSIER LIFTING] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001235 | Valve [DOSSIER LIFTING] #18 - 16-0006 - Manual bypass of ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001236 | Valve [DOSSIER LIFTING] #19 - 35-0001 - Check downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001237 | Valve [DOSSIER LIFTING] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001238 | Valve [DOSSIER LIFTING] #21 - 41-0003 - Manual at gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001239 | Valve [DOSSIER LIFTING] #22 - 41-0002 - Manual inlet of hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001240 | Valve [DOSSIER LIFTING] #23 - 34-0001 - Manuals to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001241 | Valve [DOSSIER LIFTING] #24 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001242 | Valve [DOSSIER LIFTING] #25 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001243 | Valve [DOSSIER LIFTING] #26 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001244 | Valve [DOSSIER LIFTING] #27 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001245 | Valve [DOSSIER LIFTING] #28 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001246 | Valve [DOSSIER LIFTING] #29 - 30-0002 - Manual on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001247 | Valve [DOSSIER LIFTING] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001248 | Valve [DOSSIER LIFTING] #31 - 99-0002 - ROV on suction of 5GX9920B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001249 | Valve [DOSSIER LIFTING] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001250 | Valve [DOSSIER LIFTING] #33 - 33-0002 - Manual on Oil outlet of the crude heater B1/B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001251 | Valve [DOSSIER LIFTING] #34 - 31-0002 - Last manual ball on oily H20 outlet1st stage B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001252 | Valve [DOSSIER LIFTING] #35 - 71-0004 - Gearbox difficult to manipulate | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001253 | Valve [DOSSIER LIFTING] #36 - 21-0010 - Manual u/s PSV on HGVB does not close fully. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001254 | Valve [DOSSIER LIFTING] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001255 | Valve [DOSSIER LIFTING] #38 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001256 | Valve [DOSSIER LIFTING] #39 - 52-0002 - Manul upstream 5PSV2-52410 (MP Compressor) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001257 | Valve [DOSSIER LIFTING] #40 - 30-0006 - Passing DBB( 1st upstream on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001258 | Valve [DOSSIER LIFTING] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001259 | Valve [DOSSIER LIFTING] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block stuck closed( seat disengaged from stem). DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001260 | Valve [DOSSIER LIFTING] #43 - 75-0003 - WI50 5HV75244. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001261 | Valve [DOSSIER LIFTING] #44 - 75-0003 - WI10 5 HV75234. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001262 | Valve [DOSSIER LIFTING] #45 - 54-0001 - 5LV54106A is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001263 | Valve [DOSSIER LIFTING] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001264 | Valve [DOSSIER LIFTING] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001265 | Valve [DOSSIER LIFTING] #48 - 54-0005 - Manual downstream of 5LV54106B is passing when closed. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001266 | Valve [DOSSIER LIFTING] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001267 | Valve [DOSSIER LIFTING] #50 - 94-0001 - Passing manual | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001268 | Valve [DOSSIER LIFTING] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001269 | Valve [DOSSIER LIFTING] #52 - 83-0004 - 8" manual to transfer manifold on offloading line B indicator stuck in the closed position | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001270 | Valve [DOSSIER LIFTING] #53 - 53-004 - 3'' Manual isolation for 5-LT-53206B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001271 | Valve [DOSSIER LIFTING] #54 - 73-0002 - 20'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001272 | Valve [DOSSIER LIFTING] #55 - 71-0001 - 30'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001273 | Valve [DOSSIER LIFTING] #56 - 41-0002 - 10'' Manual inlet to Hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001274 | Valve [DOSSIER LIFTING] #57 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001275 | Valve [DOSSIER LIFTING] #58 - 31-0003 - Water outlet SDV from the test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001276 | Valve [DOSSIER LIFTING] #59 - 31-0003 - Manual upstream 5LDV31206 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001277 | Valve [DOSSIER LIFTING] #60 - 73-0002 - 20'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001278 | Valve [DOSSIER LIFTING] #61 - 73-0001 - 5ROV 73350A on fine filter A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001279 | Valve [DOSSIER LIFTING] #62 - 54-0010 - Manual upstream 5SDV54501 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001280 | Valve [DOSSIER LIFTING] #63 - 73-0001 - 5ROV 73357E on fine filter E | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001281 | Valve [DOSSIER LIFTING] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001282 | Valve [DOSSIER LIFTING] #65 - 74-0002 - 3/4'' Manual gate downstream 5SDV-74101B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001283 | Valve [DOSSIER LIFTING] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001284 | Valve [DOSSIER LIFTING] #67 - 53-0005 - 5-FV-53301B- HP B anti surge | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001285 | Valve [DOSSIER LIFTING] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001286 | Valve [DOSSIER LIFTING] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001287 | Valve [DOSSIER LIFTING] #70 - 54-0012 - 5-FV-54601- GIC anti surge | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001288 | Valve [DOSSIER LIFTING] #71 - 30-0002 - Passing DBB( upstream on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001289 | Valve [DOSSIER LIFTING] #72 - 30-0001 - Passing DBB( upstream on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001290 | Valve [DOSSIER LIFTING] #73 - 75-0003 - All isolations including 5SDV75232 on water injection string WI-20 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001291 | Valve [DOSSIER LIFTING] #74 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001292 | Valve [DOSSIER LIFTING] #75 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001293 | Valve [DOSSIER LIFTING] #76 - 30-0003 - Passing DBB( upstream on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001294 | Valve [DOSSIER LIFTING] #77 - 34-0001 - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001295 | Valve [DOSSIER LIFTING] #78 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001296 | Valve [DOSSIER LIFTING] #79 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001297 | Valve [DOSSIER LIFTING] #80 - 34-0001 - All isolations on water injection string WI-10 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001298 | Valve [DOSSIER LIFTING] #81 - 94-0001 - 3" Manual buterfly on the sea water flushing line to discharge of sewage pump A. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001299 | Valve [DOSSIER LIFTING] #82 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001300 | Valve [DOSSIER LIFTING] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001301 | Valve [DOSSIER LIFTING] #84 - 34-001 - Upstream manual of 5PV1-34111 on 3rd stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001302 | Valve [DOSSIER LIFTING] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001303 | Valve [DOSSIER LIFTING] #86 - 31-0003 - manual U/S 5PSV31207 test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001304 | Valve [DOSSIER LIFTING] #87 - 21-0009 - 4'' discharge manual of LP flare drum pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001305 | Valve [DOSSIER LIFTING] #88 - 22-0001 - manual U/S 5PSV1 22113 HP FG scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001306 | Valve [DOSSIER LIFTING] #89 - 31-0001 - manual upstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001307 | Valve [DOSSIER LIFTING] #90 - 31-0001 - manual downstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001308 | Valve [DOSSIER LIFTING] #91 - 54-0001 - MANUAL ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001309 | Valve [DOSSIER LIFTING] #92 - 54-0005 - MANUAL ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001310 | Valve [DOSSIER LIFTING] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001311 | Valve [DOSSIER LIFTING] #94 - 15-0001 - MANUALS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001312 | Valve [DOSSIER LIFTING] #95 - 33-0002 - MANUAL ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001313 | Valve [DOSSIER LIFTING] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001314 | Valve [DOSSIER LIFTING] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001315 | Valve [DOSSIER LIFTING] #98 - 75-0002 - MANUAL ON MINIMUM FLOWLINE OF WIP C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001316 | Valve [DOSSIER LIFTING] #99 - 54-0007 - MANUAL DOWNSTREAM 5EBDV54318B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001317 | Valve [DOSSIER LIFTING] #100 - 31-0002 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001318 | Valve [DOSSIER LIFTING] #101 - 21-0009 - 2" UPSTREAM MANUAL ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001319 | Valve [DOSSIER LIFTING] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001320 | Valve [DOSSIER LIFTING] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001321 | Valve [DOSSIER LIFTING] #104 - Unknown - Riser ESDV 30510 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001322 | Valve [DOSSIER LIFTING] #105 - Unknown - Riser ESDV 30610 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001323 | Valve [DOSSIER LIFTING] #106 - Unknown - ISO DWSTRM - 5-PSV-15302A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001324 | Valve [DOSSIER LIFTING] #107 - Unknown - ISO DWSTRM - 5-PSV-15304B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001325 | Valve [DOSSIER LIFTING] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001326 | Valve [DOSSIER LIFTING] #109 - Unknown - CO PRE-HEAT M/ PASSING - HC SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001327 | Valve [DOSSIER LIFTING] #110 - Unknown - CO PRE-HEAT M/Valve [DOSSIER LIFTING] PASSING - DRAIN SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001328 | Valve [DOSSIER LIFTING] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001329 | Valve [DOSSIER LIFTING] #112 - Unknown - HULL VENT BLOWER (8") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001330 | Valve [DOSSIER LIFTING] #113 - Unknown - HULL VENT BLOWER (6") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-16 | 2023-05-01 |  | 2023-05-16 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001331 | Valve [DOSSIER FINAL] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001332 | Valve [DOSSIER FINAL] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001333 | Valve [DOSSIER FINAL] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001334 | Valve [DOSSIER FINAL] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001335 | Valve [DOSSIER FINAL] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001336 | Valve [DOSSIER FINAL] #6 - 99-0002 - Suction GX9920 C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001337 | Valve [DOSSIER FINAL] #7 - 31-0003 - check upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001338 | Valve [DOSSIER FINAL] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001339 | Valve [DOSSIER FINAL] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001340 | Valve [DOSSIER FINAL] #10 - 16-0003 - 5ROV 16107A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001341 | Valve [DOSSIER FINAL] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001342 | Valve [DOSSIER FINAL] #12 - 16-0003 - 5ROV16111A hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001343 | Valve [DOSSIER FINAL] #13 - 16-0003 - 5ROV16111B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001344 | Valve [DOSSIER FINAL] #14 - 16-0003 - 5ROV16107B hot water pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001345 | Valve [DOSSIER FINAL] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001346 | Valve [DOSSIER FINAL] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001347 | Valve [DOSSIER FINAL] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001348 | Valve [DOSSIER FINAL] #18 - 16-0006 - Manual bypass of ROV 16201C on Hot water inlet to WHRU C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001349 | Valve [DOSSIER FINAL] #19 - 35-0001 - Check downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001350 | Valve [DOSSIER FINAL] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001351 | Valve [DOSSIER FINAL] #21 - 41-0003 - Manual at gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001352 | Valve [DOSSIER FINAL] #22 - 41-0002 - Manual inlet of hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001353 | Valve [DOSSIER FINAL] #23 - 34-0001 - Manuals to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001354 | Valve [DOSSIER FINAL] #24 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001355 | Valve [DOSSIER FINAL] #25 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-01 | 2023-04-16 |  | 2023-05-01 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001356 | Valve [DOSSIER FINAL] #26 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001357 | Valve [DOSSIER FINAL] #27 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001358 | Valve [DOSSIER FINAL] #28 - 34-0001 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001359 | Valve [DOSSIER FINAL] #29 - 30-0002 - Manual on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001360 | Valve [DOSSIER FINAL] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001361 | Valve [DOSSIER FINAL] #31 - 99-0002 - ROV on suction of 5GX9920B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001362 | Valve [DOSSIER FINAL] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001363 | Valve [DOSSIER FINAL] #33 - 33-0002 - Manual on Oil outlet of the crude heater B1/B2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001364 | Valve [DOSSIER FINAL] #34 - 31-0002 - Last manual ball on oily H20 outlet1st stage B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001365 | Valve [DOSSIER FINAL] #35 - 71-0004 - Gearbox difficult to manipulate | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001366 | Valve [DOSSIER FINAL] #36 - 21-0010 - Manual u/s PSV on HGVB does not close fully. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001367 | Valve [DOSSIER FINAL] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001368 | Valve [DOSSIER FINAL] #38 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001369 | Valve [DOSSIER FINAL] #39 - 52-0002 - Manul upstream 5PSV2-52410 (MP Compressor) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001370 | Valve [DOSSIER FINAL] #40 - 30-0006 - Passing DBB( 1st upstream on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001371 | Valve [DOSSIER FINAL] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001372 | Valve [DOSSIER FINAL] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block stuck closed( seat disengaged from stem). DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001373 | Valve [DOSSIER FINAL] #43 - 75-0003 - WI50 5HV75244. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001374 | Valve [DOSSIER FINAL] #44 - 75-0003 - WI10 5 HV75234. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001375 | Valve [DOSSIER FINAL] #45 - 54-0001 - 5LV54106A is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001376 | Valve [DOSSIER FINAL] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001377 | Valve [DOSSIER FINAL] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001378 | Valve [DOSSIER FINAL] #48 - 54-0005 - Manual downstream of 5LV54106B is passing when closed. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001379 | Valve [DOSSIER FINAL] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001380 | Valve [DOSSIER FINAL] #50 - 94-0001 - Passing manual | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001381 | Valve [DOSSIER FINAL] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001382 | Valve [DOSSIER FINAL] #52 - 83-0004 - 8" manual to transfer manifold on offloading line B indicator stuck in the closed position | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001383 | Valve [DOSSIER FINAL] #53 - 53-004 - 3'' Manual isolation for 5-LT-53206B passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001384 | Valve [DOSSIER FINAL] #54 - 73-0002 - 20'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001385 | Valve [DOSSIER FINAL] #55 - 71-0001 - 30'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001386 | Valve [DOSSIER FINAL] #56 - 41-0002 - 10'' Manual inlet to Hydrocyclone A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001387 | Valve [DOSSIER FINAL] #57 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001388 | Valve [DOSSIER FINAL] #58 - 31-0003 - Water outlet SDV from the test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001389 | Valve [DOSSIER FINAL] #59 - 31-0003 - Manual upstream 5LDV31206 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001390 | Valve [DOSSIER FINAL] #60 - 73-0002 - 20'' Manual Butterfly passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001391 | Valve [DOSSIER FINAL] #61 - 73-0001 - 5ROV 73350A on fine filter A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001392 | Valve [DOSSIER FINAL] #62 - 54-0010 - Manual upstream 5SDV54501 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001393 | Valve [DOSSIER FINAL] #63 - 73-0001 - 5ROV 73357E on fine filter E | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001394 | Valve [DOSSIER FINAL] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001395 | Valve [DOSSIER FINAL] #65 - 74-0002 - 3/4'' Manual gate downstream 5SDV-74101B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001396 | Valve [DOSSIER FINAL] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001397 | Valve [DOSSIER FINAL] #67 - 53-0005 - 5-FV-53301B- HP B anti surge | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001398 | Valve [DOSSIER FINAL] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001399 | Valve [DOSSIER FINAL] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001400 | Valve [DOSSIER FINAL] #70 - 54-0012 - 5-FV-54601- GIC anti surge | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001401 | Valve [DOSSIER FINAL] #71 - 30-0002 - Passing DBB( upstream on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001402 | Valve [DOSSIER FINAL] #72 - 30-0001 - Passing DBB( upstream on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001403 | Valve [DOSSIER FINAL] #73 - 75-0003 - All isolations including 5SDV75232 on water injection string WI-20 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001404 | Valve [DOSSIER FINAL] #74 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001405 | Valve [DOSSIER FINAL] #75 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001406 | Valve [DOSSIER FINAL] #76 - 30-0003 - Passing DBB( upstream on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001407 | Valve [DOSSIER FINAL] #77 - 34-0001 - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001408 | Valve [DOSSIER FINAL] #78 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001409 | Valve [DOSSIER FINAL] #79 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001410 | Valve [DOSSIER FINAL] #80 - 34-0001 - All isolations on water injection string WI-10 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001411 | Valve [DOSSIER FINAL] #81 - 94-0001 - 3" Manual buterfly on the sea water flushing line to discharge of sewage pump A. | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001412 | Valve [DOSSIER FINAL] #82 - Unknown - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001413 | Valve [DOSSIER FINAL] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001414 | Valve [DOSSIER FINAL] #84 - 34-001 - Upstream manual of 5PV1-34111 on 3rd stage Separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001415 | Valve [DOSSIER FINAL] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001416 | Valve [DOSSIER FINAL] #86 - 31-0003 - manual U/S 5PSV31207 test separator | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001417 | Valve [DOSSIER FINAL] #87 - 21-0009 - 4'' discharge manual of LP flare drum pump | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001418 | Valve [DOSSIER FINAL] #88 - 22-0001 - manual U/S 5PSV1 22113 HP FG scrubber | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001419 | Valve [DOSSIER FINAL] #89 - 31-0001 - manual upstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001420 | Valve [DOSSIER FINAL] #90 - 31-0001 - manual downstream 5LDV31106A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001421 | Valve [DOSSIER FINAL] #91 - 54-0001 - MANUAL ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001422 | Valve [DOSSIER FINAL] #92 - 54-0005 - MANUAL ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001423 | Valve [DOSSIER FINAL] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001424 | Valve [DOSSIER FINAL] #94 - 15-0001 - MANUALS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001425 | Valve [DOSSIER FINAL] #95 - 33-0002 - MANUAL ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001426 | Valve [DOSSIER FINAL] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001427 | Valve [DOSSIER FINAL] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001428 | Valve [DOSSIER FINAL] #98 - 75-0002 - MANUAL ON MINIMUM FLOWLINE OF WIP C | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001429 | Valve [DOSSIER FINAL] #99 - 54-0007 - MANUAL DOWNSTREAM 5EBDV54318B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001430 | Valve [DOSSIER FINAL] #100 - 31-0002 - Description missing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-30 | 2023-05-15 |  | 2023-05-30 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001431 | Valve [DOSSIER FINAL] #101 - 21-0009 - 2" UPSTREAM MANUAL ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001432 | Valve [DOSSIER FINAL] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001433 | Valve [DOSSIER FINAL] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001434 | Valve [DOSSIER FINAL] #104 - Unknown - Riser ESDV 30510 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001435 | Valve [DOSSIER FINAL] #105 - Unknown - Riser ESDV 30610 passing | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001436 | Valve [DOSSIER FINAL] #106 - Unknown - ISO DWSTRM - 5-PSV-15302A | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001437 | Valve [DOSSIER FINAL] #107 - Unknown - ISO DWSTRM - 5-PSV-15304B | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001438 | Valve [DOSSIER FINAL] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-07 | 2023-05-22 |  | 2023-06-06 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001439 | Valve [DOSSIER FINAL] #109 - Unknown - CO PRE-HEAT M/ PASSING - HC SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001440 | Valve [DOSSIER FINAL] #110 - Unknown - CO PRE-HEAT M/Valve [DOSSIER FINAL] PASSING - DRAIN SIDE | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001441 | Valve [DOSSIER FINAL] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.2% | 2 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001442 | Valve [DOSSIER FINAL] #112 - Unknown - HULL VENT BLOWER (8") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001443 | Valve [DOSSIER FINAL] #113 - Unknown - HULL VENT BLOWER (6") | NG | AKP |  | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-16 | 2023-05-31 |  | 2023-06-15 |  |  | 0.2% | 1 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001444 | [SITE SURVEY] SCAFFOLD P1 | NG | AKP | P1 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001445 | [SITE SURVEY] SCAFFOLD P2 | NG | AKP | P2 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001446 | [SITE SURVEY] SCAFFOLD P3 | NG | AKP | P3 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001447 | [SITE SURVEY] SCAFFOLD P4 | NG | AKP | P4 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001448 | [SITE SURVEY] SCAFFOLD P5 | NG | AKP | P5 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001449 | [SITE SURVEY] SCAFFOLD P6 | NG | AKP | P6 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-28 | 2023-03-15 |  | 2023-03-30 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001450 | [SITE SURVEY] SCAFFOLD P7 | NG | AKP | P7 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001451 | [SITE SURVEY] SCAFFOLD P8 | NG | AKP | P8 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001452 | [DOSSIER FINAL] SCAFFOLD P1 | NG | AKP | P1 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001453 | [DOSSIER FINAL] SCAFFOLD P2 | NG | AKP | P2 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001454 | [DOSSIER FINAL] SCAFFOLD P3 | NG | AKP | P3 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-30 | 2023-04-14 |  | 2023-04-29 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001455 | [DOSSIER FINAL] SCAFFOLD P4 | NG | AKP | P4 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001456 | [DOSSIER FINAL] SCAFFOLD P5 | NG | AKP | P5 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001457 | [DOSSIER FINAL] SCAFFOLD P6 | NG | AKP | P6 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001458 | [DOSSIER FINAL] SCAFFOLD P7 | NG | AKP | P7 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001459 | [DOSSIER FINAL] SCAFFOLD P8 | NG | AKP | P8 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-15 | 2023-05-30 |  | 2023-06-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001460 | [SITE SURVEY] SCAFFOLD S1 | NG | AKP | S1 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-07 | 2023-01-22 |  | 2023-02-06 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001461 | [SITE SURVEY] SCAFFOLD S2 | NG | AKP | S2 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-15 | 2023-01-30 |  | 2023-02-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001462 | [SITE SURVEY] SCAFFOLD S3 | NG | AKP | S3 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-01-30 | 2023-02-14 |  | 2023-03-01 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001463 | [SITE SURVEY] SCAFFOLD S4 | NG | AKP | S4 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-07 | 2023-02-22 |  | 2023-03-09 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001464 | [SITE SURVEY] SCAFFOLD S5 | NG | AKP | S5 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-15 | 2023-03-02 |  | 2023-03-17 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001465 | [SITE SURVEY] SCAFFOLD S6 | NG | AKP | S6 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-02-28 | 2023-03-15 |  | 2023-03-30 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001466 | [SITE SURVEY] SCAFFOLD S7 | NG | AKP | S7 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-07 | 2023-03-22 |  | 2023-04-06 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001467 | [DOSSIER FINAL] SCAFFOLD S1 | NG | AKP | S1 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001468 | [DOSSIER FINAL] SCAFFOLD S2 | NG | AKP | S2 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-01 | 2023-03-16 |  | 2023-03-31 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001469 | [DOSSIER FINAL] SCAFFOLD S3 | NG | AKP | S3 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-15 | 2023-03-30 |  | 2023-04-14 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001470 | [DOSSIER FINAL] SCAFFOLD S4 | NG | AKP | S4 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-03-30 | 2023-04-14 |  | 2023-04-29 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001471 | [DOSSIER FINAL] SCAFFOLD S5 | NG | AKP | S5 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-07 | 2023-04-22 |  | 2023-05-07 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001472 | [DOSSIER FINAL] SCAFFOLD S6 | NG | AKP | S6 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-04-15 | 2023-04-30 |  | 2023-05-15 |  |  | 0.1% | 0 |  |  | DFO
2023 FFSD – AKPO 2023 FULL FIELD SHUT DOWN | NG-AKP-00-SPIE-001473 | [DOSSIER FINAL] SCAFFOLD S7 | NG | AKP | S7 | SPIE | PVV | DOS | Technical | SPIE | TEPNG_130 | DE | N_NAP | NX_NAP |  |  | 1 | 2023-05-01 | 2023-05-16 |  | 2023-05-31 |  |  | 0.1% | 0 |  |  | DFO
Formulas:
Planned IFA = [Planned IFR]+ T1
Planned IFA = [Planned IFR]+15
Planned IFC = [Planned IFA]+T1
Planned IFC = [Planned IFA]+15

## Sheet1 (hidden)
15
4.1 | Spading Cat-1 | By System | Site Survey | 2023-04-01 | Dossier Final | 2023-04-16
4.1 | Spading Cat-2 Vessel | Tag Number | Site Survey | 2023-04-16 | Dossier Final | 2023-05-01
4.1 | Spading Cat-2 Piping | Tag Number | Site Survey | 2023-05-01 | Dossier Final | 2023-05-16
1.1 | Piping NI | Tag Number | Site Survey | 2022-12-15 | Isometric | 2023-01-15 | Dossier Lifiting | 2023-04-15 | Dossier Final | 2023-06-15
1.1 | Piping SMR | Tag Number | Site Survey | 2022-12-30 | Isometric | 2023-01-30 | Dossier Lifiting | 2023-04-30 | Dossier Final | 2023-06-30
2.1 | Vessel Heat Exchanger | Tag Number | Site Survey | 2023-01-16 | N/A |  | Dossier Lifiting | 2023-03-01 | Dossier Final | 2023-04-01
2.1 | Vessel Scrubber | Tag Number | Site Survey | 2023-02-16 | N/A |  | Dossier Lifiting | 2023-04-01 | Dossier Final | 2023-05-01
2.1 | Vessel Separator | Tag Number | Site Survey | 2023-03-16 | N/A |  | Dossier Lifiting | 2023-05-01 | Dossier Final | 2023-06-01
3 | Valve | Tag Number | Site Survey | 2023-02-16 | N/A |  | Dossier Lifiting | 2023-04-16 | Dossier Final | 2023-05-16
5 | Scaffolding | Module | Site Survey | 2023-03-01 |  |  |  |  | Dossier Final | 2023-05-17

## Progress
Actual | time axis 2022-09-05 to 2024-03-11
[45 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | 40% | 60% | 100% |  |  |  | IFR | [8 empty] | IFA | [8 empty] | IFC | [8 empty] | ASB | [8 empty] | 2022-09-05: Planned
DocumentID | Title | Weighting | Planned IFR | Planned IFA | Planned IFD | Actual IFR | Actual IFA | Actual IFC | Transmittal Sent | Sent Date | Rev | Status | Transmittal Received | Return Date | Code | Days take | Remark | Transmittal Sent | Sent Date | Rev | Status | Transmittal Received | Return Date | Code | Days take | Remark | Transmittal Sent | Sent Date | Rev | Status | Transmittal Received | Return Date | Code | Days take | Remark | Transmittal Sent | Sent Date | Rev | Status | Transmittal Received | Return Date | Code | Days take | Remark | [80 empty] | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | time axis 2022-09-05 to 2024-03-11
NG-AKP-00-SPIE-000001 | Master Document Register (MDR) | 3% | 2022-11-25 | 2022-12-10 | 2022-12-25 | 2022-11-25 | 2022-12-10 | 2022-12-25 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000002 | Document Control Procedure | 1% | 2022-11-30 | 2022-12-15 | 2022-12-30 | 2022-11-30 | 2022-12-15 | 2022-12-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000003 | Organization Chart (Preparation) | 2% | 2022-11-30 | 2022-12-15 | 2022-12-30 | 2022-11-30 | 2022-12-15 | 2022-12-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000004 | Meeting Procedure | 1% | 2022-11-30 | 2022-12-15 | 2022-12-30 | 2022-11-30 | 2022-12-15 | 2022-12-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000005 | Progress Control Procedure | 1% | 2022-11-30 | 2022-12-15 | 2022-12-30 | 2022-11-30 | 2022-12-15 | 2022-12-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000006 | Training Matrix For Offshore Personnel | 1% | 2023-02-17 | 2023-03-04 | 2023-03-19 | 2023-02-17 | 2023-03-04 | 2023-03-19 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000007 | Planning, Scheduling and Progress Measurement Plan | 1% | 2022-11-30 | 2022-12-15 | 2022-12-30 | 2022-11-30 | 2022-12-15 | 2022-12-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000008 | List of Spares and Contingency Materials for FFSD Activities | 1% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000009 | PTS & POB Management plan | 1% | 2023-04-10 | 2023-04-25 | 2023-05-10 | 2023-04-10 | 2023-04-25 | 2023-05-10 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000010 | Preparation Phase Schedule | 0.5% | 2022-12-05 | 2022-12-20 | 2023-01-04 | 2022-12-05 | 2022-12-20 | 2023-01-04 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000011 | Execution Phase Schedule (Level 3) | 1% | 2023-01-05 | 2023-01-20 | 2023-02-04 | 2023-01-05 | 2023-01-20 | 2023-02-04 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000012 | Execution Phase Schedule (level 4) | 1% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000013 | Quality Plan | 2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000014 | Inspection & Test Plan Procedure | 2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000015 | Quality Assurance Plan | 1% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000016 | Materials Inspection and Management Procedure | 1% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000017 | Non Conformance Procedure | 1% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000018 | Confined Space Entry Procedure | 1% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000019 | Waste & Environmental Management Procedure | 1% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000020 | Quality Control Plan | 1% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000021 | MEDEVAC Procedure | 1% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000022 | Emergency Response Plan | 1% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000023 | HSE Plan | 2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000024 | Scaffolding Procedure and Management System | 1% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000025 | Lifting Operation Procedure | 1% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000026 | Handling and Transfer Procedure for Materials and Equipment (including containers) | 0.5% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000027 | Job Risk Analysis | 2% | 2023-05-18 | 2023-06-02 | 2023-06-17 | 2023-05-18 | 2023-06-02 | 2023-06-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000028 | Personnel Competency and Fit to Work (FTW) certificates. | 3% | 2023-06-13 | 2023-06-28 | 2023-07-13 | 2023-06-13 | 2023-06-28 | 2023-07-13 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000029 | PTW procedure | 3% | 2023-06-13 | 2023-06-28 | 2023-07-13 | 2023-06-13 | 2023-06-28 | 2023-07-13 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000030 | Performance Measurement and Monitoring Procedure (productive time and downtime) | 3% | 2023-06-13 | 2023-06-28 | 2023-07-13 | 2023-06-13 | 2023-06-28 | 2023-07-13 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000031 | Job Card Template | 3% | 2023-05-18 | 2023-06-02 | 2023-06-17 | 2023-05-18 | 2023-06-02 | 2023-06-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000032 | Flanges/Bolts Torquing Procedure | 3% | 2023-06-13 | 2023-06-28 | 2023-07-13 | 2023-06-13 | 2023-06-28 | 2023-07-13 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000033 | Handling and Transfer procedure for materials and equipment (including containers) | 3% | 2023-06-14 | 2023-06-29 | 2023-07-14 | 2023-06-14 | 2023-06-29 | 2023-07-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000034 | Cleaning and drying procedure for Scrubber and Drum | 3% | 2023-06-14 | 2023-06-29 | 2023-07-14 | 2023-06-14 | 2023-06-29 | 2023-07-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000035 | Spading, De-Spading and Spool Management Procedure | 3% | 2023-06-14 | 2023-06-29 | 2023-07-14 | 2023-06-14 | 2023-06-29 | 2023-07-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000036 | Cleaning and Drying Procedure for exchangers | 3% | 2023-06-14 | 2023-06-29 | 2023-07-14 | 2023-06-14 | 2023-06-29 | 2023-07-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000037 | Cleaning and Drying Procedure for crude oil Vessels separators | 3% | 2023-06-14 | 2023-06-29 | 2023-07-14 | 2023-06-14 | 2023-06-29 | 2023-07-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000038 | Pickling and Passivation Procedure | 3% | 2023-05-18 | 2023-06-02 | 2023-06-17 | 2023-05-18 | 2023-06-02 | 2023-06-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000039 | Flushing & Pressure testing procedure for piping | 3% | 2023-05-18 | 2023-06-02 | 2023-06-17 | 2023-05-18 | 2023-06-02 | 2023-06-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000040 | Pressure testing procedure for Heat Exchangers | 3% | 2023-05-18 | 2023-06-02 | 2023-06-17 | 2023-05-18 | 2023-06-02 | 2023-06-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000041 | Job Cards General Register | 3% | 2023-05-19 | 2023-06-03 | 2023-06-18 | 2023-05-19 | 2023-06-03 | 2023-06-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000042 | [Spading-Cat1 SITE SURVEY ] CARGO OIL HEADERS (1/2) | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000043 | [Spading-Cat1 SITE SURVEY ] CARGO OIL HEADERS (2/2) | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000044 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL HEATERS | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000045 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL METERING | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000046 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING IN BUOY MODE | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000047 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING PUMPS (1/2) | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000048 | [Spading-Cat1 SITE SURVEY ] CRUDE OIL OFFLOADING PUMPS (2/2) | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000049 | [Spading-Cat1 SITE SURVEY ] CRUDE RECIRCULATION HEATER | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000050 | [Spading-Cat1 SITE SURVEY ] GAS EXPORT METERING AND EXPORT LINE | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000051 | [Spading-Cat1 SITE SURVEY ] GAS INJECTION MANIFOLD | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000052 | [Spading-Cat1 SITE SURVEY ] HULL GAS VENT BLOWER | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000053 | [Spading-Cat1 SITE SURVEY ] LIQUID HANDLING PUMPS - COT NETWORK | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000054 | [Spading-Cat1 SITE SURVEY ] METHANOL STORAGE TANK B | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000055 | [Spading-Cat1 SITE SURVEY ] METHANOL SUBSEA DISTRIBUTION HEADER INJECTION LINES | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000056 | [Spading-Cat1 SITE SURVEY ] METHANOL SUBSEA DISTRIBUTION HEADER PRODUCTION LOOP | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000057 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P10L | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000058 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P10R | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000059 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P20L | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000060 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P20R | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000061 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P30L - PID WAS WRONG | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000062 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P30R | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000063 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P40L | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000064 | [Spading-Cat1 SITE SURVEY ] PRODUCTION AND TEST MANIFOLDS FOR P40R | 3% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000065 | [Spading-Cat1 DOSSIER FINAL] CARGO OIL HEADERS (1/2) | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000066 | [Spading-Cat1 DOSSIER FINAL] CARGO OIL HEADERS (2/2) | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000067 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL HEATERS | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000068 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL METERING | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000069 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING IN BUOY MODE | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000070 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING PUMPS (1/2) | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000071 | [Spading-Cat1 DOSSIER FINAL] CRUDE OIL OFFLOADING PUMPS (2/2) | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000072 | [Spading-Cat1 DOSSIER FINAL] CRUDE RECIRCULATION HEATER | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000073 | [Spading-Cat1 DOSSIER FINAL] GAS EXPORT METERING AND EXPORT LINE | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000074 | [Spading-Cat1 DOSSIER FINAL] GAS INJECTION MANIFOLD | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000075 | [Spading-Cat1 DOSSIER FINAL] HULL GAS VENT BLOWER | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000076 | [Spading-Cat1 DOSSIER FINAL] LIQUID HANDLING PUMPS - COT NETWORK | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000077 | [Spading-Cat1 DOSSIER FINAL] METHANOL STORAGE TANK B | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000078 | [Spading-Cat1 DOSSIER FINAL] METHANOL SUBSEA DISTRIBUTION HEADER INJECTION LINES | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000079 | [Spading-Cat1 DOSSIER FINAL] METHANOL SUBSEA DISTRIBUTION HEADER PRODUCTION LOOP | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000080 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P10L | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000081 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P10R | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000082 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P20L | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000083 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P20R | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000084 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P30L - PID WAS WRONG | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000085 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P30R | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000086 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P40L | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000087 | [Spading-Cat1 DOSSIER FINAL] PRODUCTION AND TEST MANIFOLDS FOR P40R | 3% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000088 | [Spading Cat-2 SITE SURVEY] 5-EC-5210 Mp Compressor suction Cooler | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000089 | [Spading Cat-2 SITE SURVEY] 5-EC-5510-A Dehydrator intlet Cooler A | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000090 | [Spading Cat-2 SITE SURVEY] 5-EC-5510-B Dehydrator intlet Cooler B | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000091 | [Spading Cat-2 SITE SURVEY] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000092 | [Spading Cat-2 SITE SURVEY] 5-EC-5110 LP Compressor Suction Cooler | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000093 | [Spading Cat-2 SITE SURVEY] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000094 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000095 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000096 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000097 | [Spading Cat-2 SITE SURVEY] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000098 | [Spading Cat-2 SITE SURVEY] 5-EC-9910 Crude Oil Re-Heater | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000099 | [Spading Cat-2 SITE SURVEY] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000100 | [Spading Cat-2 SITE SURVEY] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000101 | [Spading Cat-2 SITE SURVEY] 5-EC-5310-A HP Compressor Suction Cooler A | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000102 | [Spading Cat-2 SITE SURVEY] 5-EC-5310-B HP Compressor Suction Cooler B | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000103 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5210 Mp Compressor suction Cooler | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000104 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5510-A Dehydrator intlet Cooler A | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000105 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5510-B Dehydrator intlet Cooler B | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000106 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000107 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5110 LP Compressor Suction Cooler | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000108 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000109 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000110 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000111 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000112 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000113 | [Spading Cat-2 DOSSIER FINAL] 5-EC-9910 Crude Oil Re-Heater | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000114 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000115 | [Spading Cat-2 DOSSIER FINAL] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000116 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5310-A HP Compressor Suction Cooler A | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000117 | [Spading Cat-2 DOSSIER FINAL] 5-EC-5310-B HP Compressor Suction Cooler B | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000118 | [Spading Cat-2 SITE SURVEY] 5-DS-5410-A Gas Export Scrubber A | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000119 | [Spading Cat-2 SITE SURVEY] 5-DS-5410-B Gas Export Scrubber B | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000120 | [Spading Cat-2 SITE SURVEY] 5-DS-2210 Hp Fuel Gas Scrubber | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000121 | [Spading Cat-2 SITE SURVEY] 5-DS-5120 LP Compressor suction Scrubber | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000122 | [Spading Cat-2 SITE SURVEY] 5-DS-2240 LP Fuel Gas Scrubber | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000123 | [Spading Cat-2 SITE SURVEY] 5-DS-5520 Dehydrator Inlet Scrubber | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000124 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5410-A Gas Export Scrubber A | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000125 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5410-B Gas Export Scrubber B | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000126 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2210 Hp Fuel Gas Scrubber | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000127 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5120 LP Compressor suction Scrubber | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000128 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2240 LP Fuel Gas Scrubber | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000129 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5520 Dehydrator Inlet Scrubber | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000130 | [Spading Cat-2 SITE SURVEY] 5-DS-3110-A 1 Stage Separator A | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000131 | [Spading Cat-2 SITE SURVEY] 5-DS-3110-B 1 Stage Separator B | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000132 | [Spading Cat-2 SITE SURVEY] 5-DS-3210 2 Stage Separator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000133 | [Spading Cat-2 SITE SURVEY] 5-DS-3410 3 Stage Separator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000134 | [Spading Cat-2 SITE SURVEY] 5-DS-3610 4 Stage Separator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000135 | [Spading Cat-2 SITE SURVEY] 5-DS-3120 Test Separator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000136 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3110-A 1 Stage Separator A | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000137 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3110-B 1 Stage Separator B | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000138 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3210 2 Stage Separator | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000139 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3410 3 Stage Separator | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000140 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3610 4 Stage Separator | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000141 | [Spading Cat-2 DOSSIER FINAL] 5-DS-3120 Test Separator | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000142 | [Spading Cat-2 SITE SURVEY] 5-CA-5530 Glycol Dehydrator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000143 | [Spading Cat-2 SITE SURVEY] 5-DS-2140 LP Flare KO Drum | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000144 | [Spading Cat-2 SITE SURVEY] 5-DA-1340 Instrument Air Receveiver | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000145 | [Spading Cat-2 SITE SURVEY] 5-DA-5544 Glycol Surge Drum (TEG) | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000146 | [Spading Cat-2 SITE SURVEY] 5-DS-4110 Oily Water Drum | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000147 | [Spading Cat-2 SITE SURVEY] 5-DS-4130 Degassing Drum | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000148 | [Spading Cat-2 SITE SURVEY] 5-DA-1630 Hot Water Expansion Drum | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000149 | [Spading Cat-2 SITE SURVEY] 5-DA-1540 Cooling Water Expansion Drum | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000150 | [Spading Cat-2 SITE SURVEY] 5-TC-1730 Fire Fighting Foam Tank | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000151 | [Spading Cat-2 SITE SURVEY] 5-DS-5420-A Single Filter | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000152 | [Spading Cat-2 SITE SURVEY] 5-DS-5420-B Single Filter | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000153 | [Spading Cat-2 SITE SURVEY] 5-DA-1350 Cooling Water Expansion Tank | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000154 | [Spading Cat-2 SITE SURVEY] 5-DS-3510 Electrostatic Dehydrator | 0.1% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000155 | [Spading Cat-2 DOSSIER FINAL] 5-CA-5530 Glycol Dehydrator | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000156 | [Spading Cat-2 DOSSIER FINAL] 5-DS-2140 LP Flare KO Drum | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000157 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1340 Instrument Air Receveiver | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000158 | [Spading Cat-2 DOSSIER FINAL] 5-DA-5544 Glycol Surge Drum (TEG) | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000159 | [Spading Cat-2 DOSSIER FINAL] 5-DS-4110 Oily Water Drum | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000160 | [Spading Cat-2 DOSSIER FINAL] 5-DS-4130 Degassing Drum | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000161 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1630 Hot Water Expansion Drum | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000162 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1540 Cooling Water Expansion Drum | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000163 | [Spading Cat-2 DOSSIER FINAL] 5-TC-1730 Fire Fighting Foam Tank | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000164 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5420-A Single Filter | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000165 | [Spading Cat-2 DOSSIER FINAL] 5-DS-5420-B Single Filter | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000166 | [Spading Cat-2 DOSSIER FINAL] 5-DA-1350 Cooling Water Expansion Tank | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000167 | PIPING NI [Spading-Cat 2 SITE SURVEY] #1 AIR SYSTEM 46005853 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000168 | PIPING NI [Spading-Cat 2 SITE SURVEY] #2 AIR SYSTEM 46005855 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000169 | PIPING NI [Spading-Cat 2 SITE SURVEY] #3 AIR SYSTEM 46005856 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000170 | PIPING NI [Spading-Cat 2 SITE SURVEY] #4 AIR SYSTEM 46007510 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000171 | PIPING NI [Spading-Cat 2 SITE SURVEY] #5 CHEMICAL SYSTEM 46006147 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000172 | PIPING NI [Spading-Cat 2 SITE SURVEY] #6 COOLING WATER SYSTEM 46005504 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000173 | PIPING NI [Spading-Cat 2 SITE SURVEY] #7 COOLING WATER SYSTEM 46005573 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000174 | PIPING NI [Spading-Cat 2 SITE SURVEY] #8 COOLING WATER SYSTEM 46005783 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000175 | PIPING NI [Spading-Cat 2 SITE SURVEY] #9 COOLING WATER SYSTEM 46005784 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000176 | PIPING NI [Spading-Cat 2 SITE SURVEY] #10 COOLING WATER SYSTEM 46005785 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000177 | PIPING NI [Spading-Cat 2 SITE SURVEY] #11 COOLING WATER SYSTEM 46005786 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000178 | PIPING NI [Spading-Cat 2 SITE SURVEY] #12 COOLING WATER SYSTEM 46005787 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000179 | PIPING NI [Spading-Cat 2 SITE SURVEY] #13 COOLING WATER SYSTEM 46005833 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000180 | PIPING NI [Spading-Cat 2 SITE SURVEY] #14 COOLING WATER SYSTEM 46005940 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000181 | PIPING NI [Spading-Cat 2 SITE SURVEY] #15 COOLING WATER SYSTEM 46005968 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000182 | PIPING NI [Spading-Cat 2 SITE SURVEY] #16 COOLING WATER SYSTEM 46006014 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000183 | PIPING NI [Spading-Cat 2 SITE SURVEY] #17 COOLING WATER SYSTEM 46006099 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000184 | PIPING NI [Spading-Cat 2 SITE SURVEY] #18 COOLING WATER SYSTEM 46006150 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000185 | PIPING NI [Spading-Cat 2 SITE SURVEY] #19 COOLING WATER SYSTEM 46006151 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000186 | PIPING NI [Spading-Cat 2 SITE SURVEY] #20 COOLING WATER SYSTEM 46006181 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000187 | PIPING NI [Spading-Cat 2 SITE SURVEY] #21 COOLING WATER SYSTEM 46006223 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000188 | PIPING NI [Spading-Cat 2 SITE SURVEY] #22 COOLING WATER SYSTEM 46006624 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000189 | PIPING NI [Spading-Cat 2 SITE SURVEY] #23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000190 | PIPING NI [Spading-Cat 2 SITE SURVEY] #24 COOLING WATER SYSTEM 46006762 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000191 | PIPING NI [Spading-Cat 2 SITE SURVEY] #25 COOLING WATER SYSTEM 46006882 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000192 | PIPING NI [Spading-Cat 2 SITE SURVEY] #26 COOLING WATER SYSTEM 46006894 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000193 | PIPING NI [Spading-Cat 2 SITE SURVEY] #27 COOLING WATER SYSTEM 46007199 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000194 | PIPING NI [Spading-Cat 2 SITE SURVEY] #28 COOLING WATER SYSTEM 46007200 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000195 | PIPING NI [Spading-Cat 2 SITE SURVEY] #29 COOLING WATER SYSTEM 46007304 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000196 | PIPING NI [Spading-Cat 2 SITE SURVEY] #30 COOLING WATER SYSTEM 46007508 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000197 | PIPING NI [Spading-Cat 2 SITE SURVEY] #31 COOLING WATER SYSTEM 46007576 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000198 | PIPING NI [Spading-Cat 2 SITE SURVEY] #32 COOLING WATER SYSTEM 46007602 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000199 | PIPING NI [Spading-Cat 2 SITE SURVEY] #33 COOLING WATER SYSTEM 46007603 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000200 | PIPING NI [Spading-Cat 2 SITE SURVEY] #34 COOLING WATER SYSTEM 46007604 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000201 | PIPING NI [Spading-Cat 2 SITE SURVEY] #35 COOLING WATER SYSTEM 46007605 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000202 | PIPING NI [Spading-Cat 2 SITE SURVEY] #36 COOLING WATER SYSTEM 46007606 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000203 | PIPING NI [Spading-Cat 2 SITE SURVEY] #37 COOLING WATER SYSTEM 46007607 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000204 | PIPING NI [Spading-Cat 2 SITE SURVEY] #38 COOLING WATER SYSTEM 46007614 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000205 | PIPING NI [Spading-Cat 2 SITE SURVEY] #39 COOLING WATER SYSTEM 46007615 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000206 | PIPING NI [Spading-Cat 2 SITE SURVEY] #40 COOLING WATER SYSTEM 46005411 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000207 | PIPING NI [Spading-Cat 2 SITE SURVEY] #41 COOLING WATER SYSTEM 46006013 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000208 | PIPING NI [Spading-Cat 2 SITE SURVEY] #42 COOLING WATER SYSTEM 46006015 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000209 | PIPING NI [Spading-Cat 2 SITE SURVEY] #43 FIREWATER SYSTEM 46004394 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000210 | PIPING NI [Spading-Cat 2 SITE SURVEY] #44 FIREWATER SYSTEM 46004801 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000211 | PIPING NI [Spading-Cat 2 SITE SURVEY] #45 FIREWATER SYSTEM 46005362 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000212 | PIPING NI [Spading-Cat 2 SITE SURVEY] #46 FIREWATER SYSTEM 46005367 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000213 | PIPING NI [Spading-Cat 2 SITE SURVEY] #47 FIREWATER SYSTEM 46007197 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000214 | PIPING NI [Spading-Cat 2 SITE SURVEY] #48 GAS SYSTEM 46005502 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000215 | PIPING NI [Spading-Cat 2 SITE SURVEY] #49 GAS SYSTEM 46006182 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000216 | PIPING NI [Spading-Cat 2 SITE SURVEY] #50 GAS SYSTEM 46006183 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000217 | PIPING NI [Spading-Cat 2 SITE SURVEY] #51 GAS SYSTEM 46006375 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000218 | PIPING NI [Spading-Cat 2 SITE SURVEY] #52 GAS SYSTEM 46006660 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000219 | PIPING NI [Spading-Cat 2 SITE SURVEY] #53 GAS SYSTEM 46007151 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000220 | PIPING NI [Spading-Cat 2 SITE SURVEY] #54 GAS SYSTEM 46007163 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000221 | PIPING NI [Spading-Cat 2 SITE SURVEY] #55 GAS SYSTEM 46007268 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000222 | PIPING NI [Spading-Cat 2 SITE SURVEY] #56 GAS SYSTEM 46007522 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000223 | PIPING NI [Spading-Cat 2 SITE SURVEY] #57 GAS SYSTEM 46007553 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000224 | PIPING NI [Spading-Cat 2 SITE SURVEY] #58 GAS SYSTEM 46007577 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000225 | PIPING NI [Spading-Cat 2 SITE SURVEY] #59 GAS SYSTEM 46004652 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000226 | PIPING NI [Spading-Cat 2 SITE SURVEY] #60 HVAC / HOT WATER SYSTEM 46004662 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000227 | PIPING NI [Spading-Cat 2 SITE SURVEY] #61 HVAC / HOT WATER SYSTEM 46005769 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000228 | PIPING NI [Spading-Cat 2 SITE SURVEY] #62 HVAC / HOT WATER SYSTEM 46005770 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000229 | PIPING NI [Spading-Cat 2 SITE SURVEY] #63 HVAC / HOT WATER SYSTEM 46005915 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000230 | PIPING NI [Spading-Cat 2 SITE SURVEY] #64 HVAC / HOT WATER SYSTEM 46005982 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000231 | PIPING NI [Spading-Cat 2 SITE SURVEY] #65 HVAC / HOT WATER SYSTEM 46007045 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000232 | PIPING NI [Spading-Cat 2 SITE SURVEY] #66 HVAC / HOT WATER SYSTEM 46007052 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000233 | PIPING NI [Spading-Cat 2 SITE SURVEY] #67 HVAC / HOT WATER SYSTEM 46007566 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000234 | PIPING NI [Spading-Cat 2 SITE SURVEY] #68 HVAC / HOT WATER SYSTEM 46004053 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000235 | PIPING NI [Spading-Cat 2 SITE SURVEY] #69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000236 | PIPING NI [Spading-Cat 2 SITE SURVEY] #70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000237 | PIPING NI [Spading-Cat 2 SITE SURVEY] #71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000238 | PIPING NI [Spading-Cat 2 SITE SURVEY] #72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000239 | PIPING NI [Spading-Cat 2 SITE SURVEY] #73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000240 | PIPING NI [Spading-Cat 2 SITE SURVEY] #74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000241 | PIPING NI [Spading-Cat 2 SITE SURVEY] #75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000242 | PIPING NI [Spading-Cat 2 SITE SURVEY] #76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000243 | PIPING NI [Spading-Cat 2 SITE SURVEY] #77 INERT SYSTEM 46007407 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000244 | PIPING NI [Spading-Cat 2 SITE SURVEY] #78 INERT SYSTEM 46007408 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000245 | PIPING NI [Spading-Cat 2 SITE SURVEY] #79 OIL SYSTEM 46003301 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000246 | PIPING NI [Spading-Cat 2 SITE SURVEY] #80 OIL SYSTEM 46005365 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000247 | PIPING NI [Spading-Cat 2 SITE SURVEY] #81 OIL SYSTEM 46005594 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000248 | PIPING NI [Spading-Cat 2 SITE SURVEY] #82 OIL SYSTEM 46005766 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000249 | PIPING NI [Spading-Cat 2 SITE SURVEY] #83 OIL SYSTEM 46005777 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000250 | PIPING NI [Spading-Cat 2 SITE SURVEY] #84 OIL SYSTEM 46005778 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000251 | PIPING NI [Spading-Cat 2 SITE SURVEY] #85 OIL SYSTEM 46006416 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000252 | PIPING NI [Spading-Cat 2 SITE SURVEY] #86 OIL SYSTEM 46006753 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000253 | PIPING NI [Spading-Cat 2 SITE SURVEY] #87 OIL SYSTEM 46007152 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000254 | PIPING NI [Spading-Cat 2 SITE SURVEY] #88 OIL SYSTEM 46007161 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000255 | PIPING NI [Spading-Cat 2 SITE SURVEY] #89 OIL SYSTEM 46007422 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000256 | PIPING NI [Spading-Cat 2 SITE SURVEY] #90 OIL SYSTEM 46007524 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000257 | PIPING NI [Spading-Cat 2 SITE SURVEY] #91 OIL SYSTEM 46007525 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000258 | PIPING NI [Spading-Cat 2 SITE SURVEY] #92 OIL SYSTEM 46007526 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000259 | PIPING NI [Spading-Cat 2 SITE SURVEY] #93 OIL SYSTEM 46007527 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000260 | PIPING NI [Spading-Cat 2 SITE SURVEY] #94 OIL SYSTEM 46007528 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000261 | PIPING NI [Spading-Cat 2 SITE SURVEY] #95 OIL SYSTEM 46007529 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000262 | PIPING NI [Spading-Cat 2 SITE SURVEY] #96 OIL SYSTEM 46007530 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000263 | PIPING NI [Spading-Cat 2 SITE SURVEY] #97 OIL SYSTEM 46007531 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000264 | PIPING NI [Spading-Cat 2 SITE SURVEY] #98 OIL SYSTEM 46007532 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000265 | PIPING NI [Spading-Cat 2 SITE SURVEY] #99 OIL SYSTEM 46007591 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000266 | PIPING NI [Spading-Cat 2 SITE SURVEY] #100 OIL SYSTEM 46007592 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000267 | PIPING NI [Spading-Cat 2 SITE SURVEY] #101 OIL SYSTEM 46005366 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000268 | PIPING NI [Spading-Cat 2 SITE SURVEY] #102 OIL SYSTEM 46006033 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000269 | PIPING NI [Spading-Cat 2 SITE SURVEY] #103 OIL SYSTEM 46006283 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000270 | PIPING NI [Spading-Cat 2 SITE SURVEY] #104 OIL SYSTEM 46007160 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000271 | PIPING NI [Spading-Cat 2 SITE SURVEY] #105 OIL SYSTEM 46007560 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000272 | PIPING NI [Spading-Cat 2 SITE SURVEY] #106 OIL SYSTEM 46007562-45 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000273 | PIPING NI [Spading-Cat 2 SITE SURVEY] #107 OIL SYSTEM 46007563-3 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000274 | PIPING NI [Spading-Cat 2 SITE SURVEY] #108 WATER INJECTION 46007274 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000275 | PIPING NI [Spading-Cat 2 SITE SURVEY] #109 GAS SYSTEM 46007556 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000276 | PIPING NI [Spading-Cat 2 SITE SURVEY] #110 GAS SYSTEM 46005903 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000277 | PIPING NI [Spading-Cat 2 SITE SURVEY] #111 OIL SYSTEM 46005741 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000278 | PIPING NI [Spading-Cat 2 SITE SURVEY] #112 OIL SYSTEM 46007132 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000279 | PIPING NI [Spading-Cat 2 SITE SURVEY] #113 OIL SYSTEM 46007205 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000280 | PIPING NI [Spading-Cat 2 SITE SURVEY] #114 OIL SYSTEM 46006278 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000281 | PIPING NI [Spading-Cat 2 SITE SURVEY] #115 OIL SYSTEM 46006632 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000282 | PIPING NI [Spading-Cat 2 SITE SURVEY] #116 OIL SYSTEM 46006922 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000283 | PIPING NI [Spading-Cat 2 SITE SURVEY] #117 OIL SYSTEM 46007570-33 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000284 | PIPING NI [Spading-Cat 2 SITE SURVEY] #118 HVAC / HOT WATER SYSTEM 46004977 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000285 | PIPING NI [Spading-Cat 2 SITE SURVEY] #119 HVAC / HOT WATER SYSTEM 46004982 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000286 | PIPING NI [Spading-Cat 2 SITE SURVEY] #120 COOLING WATER SYSTEM 46005973-12 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000287 | PIPING NI [Spading-Cat 2 SITE SURVEY] #121 COOLING WATER SYSTEM 46007183 | 0.06616% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000288 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #1 AIR SYSTEM 46005853 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000289 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #2 AIR SYSTEM 46005855 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000290 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #3 AIR SYSTEM 46005856 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000291 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #4 AIR SYSTEM 46007510 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000292 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #5 CHEMICAL SYSTEM 46006147 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000293 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #6 COOLING WATER SYSTEM 46005504 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000294 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #7 COOLING WATER SYSTEM 46005573 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000295 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #8 COOLING WATER SYSTEM 46005783 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000296 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #9 COOLING WATER SYSTEM 46005784 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000297 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #10 COOLING WATER SYSTEM 46005785 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000298 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #11 COOLING WATER SYSTEM 46005786 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000299 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #12 COOLING WATER SYSTEM 46005787 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000300 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #13 COOLING WATER SYSTEM 46005833 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000301 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #14 COOLING WATER SYSTEM 46005940 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000302 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #15 COOLING WATER SYSTEM 46005968 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000303 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #16 COOLING WATER SYSTEM 46006014 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000304 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #17 COOLING WATER SYSTEM 46006099 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000305 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #18 COOLING WATER SYSTEM 46006150 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000306 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #19 COOLING WATER SYSTEM 46006151 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000307 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #20 COOLING WATER SYSTEM 46006181 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000308 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #21 COOLING WATER SYSTEM 46006223 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000309 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #22 COOLING WATER SYSTEM 46006624 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000310 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000311 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #24 COOLING WATER SYSTEM 46006762 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000312 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #25 COOLING WATER SYSTEM 46006882 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000313 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #26 COOLING WATER SYSTEM 46006894 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000314 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #27 COOLING WATER SYSTEM 46007199 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000315 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #28 COOLING WATER SYSTEM 46007200 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000316 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #29 COOLING WATER SYSTEM 46007304 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000317 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #30 COOLING WATER SYSTEM 46007508 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000318 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #31 COOLING WATER SYSTEM 46007576 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000319 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #32 COOLING WATER SYSTEM 46007602 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000320 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #33 COOLING WATER SYSTEM 46007603 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000321 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #34 COOLING WATER SYSTEM 46007604 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000322 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #35 COOLING WATER SYSTEM 46007605 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000323 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #36 COOLING WATER SYSTEM 46007606 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000324 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #37 COOLING WATER SYSTEM 46007607 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000325 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #38 COOLING WATER SYSTEM 46007614 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000326 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #39 COOLING WATER SYSTEM 46007615 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000327 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #40 COOLING WATER SYSTEM 46005411 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000328 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #41 COOLING WATER SYSTEM 46006013 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000329 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #42 COOLING WATER SYSTEM 46006015 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000330 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #43 FIREWATER SYSTEM 46004394 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000331 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #44 FIREWATER SYSTEM 46004801 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000332 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #45 FIREWATER SYSTEM 46005362 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000333 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #46 FIREWATER SYSTEM 46005367 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000334 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #47 FIREWATER SYSTEM 46007197 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000335 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #48 GAS SYSTEM 46005502 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000336 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #49 GAS SYSTEM 46006182 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000337 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #50 GAS SYSTEM 46006183 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000338 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #51 GAS SYSTEM 46006375 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000339 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #52 GAS SYSTEM 46006660 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000340 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #53 GAS SYSTEM 46007151 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000341 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #54 GAS SYSTEM 46007163 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000342 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #55 GAS SYSTEM 46007268 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000343 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #56 GAS SYSTEM 46007522 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000344 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #57 GAS SYSTEM 46007553 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000345 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #58 GAS SYSTEM 46007577 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000346 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #59 GAS SYSTEM 46004652 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000347 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #60 HVAC / HOT WATER SYSTEM 46004662 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000348 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #61 HVAC / HOT WATER SYSTEM 46005769 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000349 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #62 HVAC / HOT WATER SYSTEM 46005770 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000350 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #63 HVAC / HOT WATER SYSTEM 46005915 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000351 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #64 HVAC / HOT WATER SYSTEM 46005982 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000352 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #65 HVAC / HOT WATER SYSTEM 46007045 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000353 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #66 HVAC / HOT WATER SYSTEM 46007052 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000354 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #67 HVAC / HOT WATER SYSTEM 46007566 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000355 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #68 HVAC / HOT WATER SYSTEM 46004053 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000356 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000357 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000358 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000359 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000360 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000361 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000362 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000363 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000364 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #77 INERT SYSTEM 46007407 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000365 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #78 INERT SYSTEM 46007408 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000366 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #79 OIL SYSTEM 46003301 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000367 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #80 OIL SYSTEM 46005365 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000368 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #81 OIL SYSTEM 46005594 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000369 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #82 OIL SYSTEM 46005766 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000370 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #83 OIL SYSTEM 46005777 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000371 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #84 OIL SYSTEM 46005778 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000372 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #85 OIL SYSTEM 46006416 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000373 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #86 OIL SYSTEM 46006753 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000374 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #87 OIL SYSTEM 46007152 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000375 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #88 OIL SYSTEM 46007161 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000376 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #89 OIL SYSTEM 46007422 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000377 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #90 OIL SYSTEM 46007524 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000378 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #91 OIL SYSTEM 46007525 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000379 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #92 OIL SYSTEM 46007526 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000380 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #93 OIL SYSTEM 46007527 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000381 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #94 OIL SYSTEM 46007528 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000382 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #95 OIL SYSTEM 46007529 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000383 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #96 OIL SYSTEM 46007530 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000384 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #97 OIL SYSTEM 46007531 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000385 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #98 OIL SYSTEM 46007532 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000386 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #99 OIL SYSTEM 46007591 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000387 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #100 OIL SYSTEM 46007592 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000388 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #101 OIL SYSTEM 46005366 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000389 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #102 OIL SYSTEM 46006033 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000390 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #103 OIL SYSTEM 46006283 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000391 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #104 OIL SYSTEM 46007160 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000392 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #105 OIL SYSTEM 46007560 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000393 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #106 OIL SYSTEM 46007562-45 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000394 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #107 OIL SYSTEM 46007563-3 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000395 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #108 WATER INJECTION 46007274 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000396 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #109 GAS SYSTEM 46007556 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000397 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #110 GAS SYSTEM 46005903 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000398 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #111 OIL SYSTEM 46005741 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000399 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #112 OIL SYSTEM 46007132 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000400 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #113 OIL SYSTEM 46007205 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000401 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #114 OIL SYSTEM 46006278 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000402 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #115 OIL SYSTEM 46006632 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000403 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #116 OIL SYSTEM 46006922 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000404 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #117 OIL SYSTEM 46007570-33 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000405 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #118 HVAC / HOT WATER SYSTEM 46004977 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000406 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #119 HVAC / HOT WATER SYSTEM 46004982 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000407 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #120 COOLING WATER SYSTEM 46005973-12 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000408 | PIPING NI [Spading-Cat 2 DOSSIER FINAL] #121 COOLING WATER SYSTEM 46007183 | 0.06616% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000409 | PIPING NI [SITE SURVEY] #1 AIR SYSTEM 46005853 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000410 | PIPING NI [SITE SURVEY] #2 AIR SYSTEM 46005855 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000411 | PIPING NI [SITE SURVEY] #3 AIR SYSTEM 46005856 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000412 | PIPING NI [SITE SURVEY] #4 AIR SYSTEM 46007510 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000413 | PIPING NI [SITE SURVEY] #5 CHEMICAL SYSTEM 46006147 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000414 | PIPING NI [SITE SURVEY] #6 COOLING WATER SYSTEM 46005504 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000415 | PIPING NI [SITE SURVEY] #7 COOLING WATER SYSTEM 46005573 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000416 | PIPING NI [SITE SURVEY] #8 COOLING WATER SYSTEM 46005783 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000417 | PIPING NI [SITE SURVEY] #9 COOLING WATER SYSTEM 46005784 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000418 | PIPING NI [SITE SURVEY] #10 COOLING WATER SYSTEM 46005785 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000419 | PIPING NI [SITE SURVEY] #11 COOLING WATER SYSTEM 46005786 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000420 | PIPING NI [SITE SURVEY] #12 COOLING WATER SYSTEM 46005787 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000421 | PIPING NI [SITE SURVEY] #13 COOLING WATER SYSTEM 46005833 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000422 | PIPING NI [SITE SURVEY] #14 COOLING WATER SYSTEM 46005940 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000423 | PIPING NI [SITE SURVEY] #15 COOLING WATER SYSTEM 46005968 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000424 | PIPING NI [SITE SURVEY] #16 COOLING WATER SYSTEM 46006014 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000425 | PIPING NI [SITE SURVEY] #17 COOLING WATER SYSTEM 46006099 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000426 | PIPING NI [SITE SURVEY] #18 COOLING WATER SYSTEM 46006150 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000427 | PIPING NI [SITE SURVEY] #19 COOLING WATER SYSTEM 46006151 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000428 | PIPING NI [SITE SURVEY] #20 COOLING WATER SYSTEM 46006181 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000429 | PIPING NI [SITE SURVEY] #21 COOLING WATER SYSTEM 46006223 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000430 | PIPING NI [SITE SURVEY] #22 COOLING WATER SYSTEM 46006624 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000431 | PIPING NI [SITE SURVEY] #23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000432 | PIPING NI [SITE SURVEY] #24 COOLING WATER SYSTEM 46006762 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000433 | PIPING NI [SITE SURVEY] #25 COOLING WATER SYSTEM 46006882 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000434 | PIPING NI [SITE SURVEY] #26 COOLING WATER SYSTEM 46006894 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000435 | PIPING NI [SITE SURVEY] #27 COOLING WATER SYSTEM 46007199 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000436 | PIPING NI [SITE SURVEY] #28 COOLING WATER SYSTEM 46007200 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000437 | PIPING NI [SITE SURVEY] #29 COOLING WATER SYSTEM 46007304 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000438 | PIPING NI [SITE SURVEY] #30 COOLING WATER SYSTEM 46007508 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000439 | PIPING NI [SITE SURVEY] #31 COOLING WATER SYSTEM 46007576 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000440 | PIPING NI [SITE SURVEY] #32 COOLING WATER SYSTEM 46007602 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000441 | PIPING NI [SITE SURVEY] #33 COOLING WATER SYSTEM 46007603 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000442 | PIPING NI [SITE SURVEY] #34 COOLING WATER SYSTEM 46007604 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000443 | PIPING NI [SITE SURVEY] #35 COOLING WATER SYSTEM 46007605 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000444 | PIPING NI [SITE SURVEY] #36 COOLING WATER SYSTEM 46007606 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000445 | PIPING NI [SITE SURVEY] #37 COOLING WATER SYSTEM 46007607 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000446 | PIPING NI [SITE SURVEY] #38 COOLING WATER SYSTEM 46007614 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000447 | PIPING NI [SITE SURVEY] #39 COOLING WATER SYSTEM 46007615 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000448 | PIPING NI [SITE SURVEY] #40 COOLING WATER SYSTEM 46005411 | 0.2% | 2022-12-01 | 2022-12-16 | 2022-12-31 | 2022-12-01 | 2022-12-16 | 2022-12-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000449 | PIPING NI [SITE SURVEY] #41 COOLING WATER SYSTEM 46006013 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000450 | PIPING NI [SITE SURVEY] #42 COOLING WATER SYSTEM 46006015 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000451 | PIPING NI [SITE SURVEY] #43 FIREWATER SYSTEM 46004394 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000452 | PIPING NI [SITE SURVEY] #44 FIREWATER SYSTEM 46004801 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000453 | PIPING NI [SITE SURVEY] #45 FIREWATER SYSTEM 46005362 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000454 | PIPING NI [SITE SURVEY] #46 FIREWATER SYSTEM 46005367 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000455 | PIPING NI [SITE SURVEY] #47 FIREWATER SYSTEM 46007197 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000456 | PIPING NI [SITE SURVEY] #48 GAS SYSTEM 46005502 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000457 | PIPING NI [SITE SURVEY] #49 GAS SYSTEM 46006182 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000458 | PIPING NI [SITE SURVEY] #50 GAS SYSTEM 46006183 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000459 | PIPING NI [SITE SURVEY] #51 GAS SYSTEM 46006375 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000460 | PIPING NI [SITE SURVEY] #52 GAS SYSTEM 46006660 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000461 | PIPING NI [SITE SURVEY] #53 GAS SYSTEM 46007151 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000462 | PIPING NI [SITE SURVEY] #54 GAS SYSTEM 46007163 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000463 | PIPING NI [SITE SURVEY] #55 GAS SYSTEM 46007268 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000464 | PIPING NI [SITE SURVEY] #56 GAS SYSTEM 46007522 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000465 | PIPING NI [SITE SURVEY] #57 GAS SYSTEM 46007553 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000466 | PIPING NI [SITE SURVEY] #58 GAS SYSTEM 46007577 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000467 | PIPING NI [SITE SURVEY] #59 GAS SYSTEM 46004652 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000468 | PIPING NI [SITE SURVEY] #60 HVAC / HOT WATER SYSTEM 46004662 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000469 | PIPING NI [SITE SURVEY] #61 HVAC / HOT WATER SYSTEM 46005769 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000470 | PIPING NI [SITE SURVEY] #62 HVAC / HOT WATER SYSTEM 46005770 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000471 | PIPING NI [SITE SURVEY] #63 HVAC / HOT WATER SYSTEM 46005915 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000472 | PIPING NI [SITE SURVEY] #64 HVAC / HOT WATER SYSTEM 46005982 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000473 | PIPING NI [SITE SURVEY] #65 HVAC / HOT WATER SYSTEM 46007045 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000474 | PIPING NI [SITE SURVEY] #66 HVAC / HOT WATER SYSTEM 46007052 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000475 | PIPING NI [SITE SURVEY] #67 HVAC / HOT WATER SYSTEM 46007566 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000476 | PIPING NI [SITE SURVEY] #68 HVAC / HOT WATER SYSTEM 46004053 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000477 | PIPING NI [SITE SURVEY] #69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000478 | PIPING NI [SITE SURVEY] #70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000479 | PIPING NI [SITE SURVEY] #71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000480 | PIPING NI [SITE SURVEY] #72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000481 | PIPING NI [SITE SURVEY] #73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000482 | PIPING NI [SITE SURVEY] #74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000483 | PIPING NI [SITE SURVEY] #75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000484 | PIPING NI [SITE SURVEY] #76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000485 | PIPING NI [SITE SURVEY] #77 INERT SYSTEM 46007407 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000486 | PIPING NI [SITE SURVEY] #78 INERT SYSTEM 46007408 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000487 | PIPING NI [SITE SURVEY] #79 OIL SYSTEM 46003301 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000488 | PIPING NI [SITE SURVEY] #80 OIL SYSTEM 46005365 | 0.2% | 2022-12-07 | 2022-12-22 | 2023-01-06 | 2022-12-07 | 2022-12-22 | 2023-01-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000489 | PIPING NI [SITE SURVEY] #81 OIL SYSTEM 46005594 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000490 | PIPING NI [SITE SURVEY] #82 OIL SYSTEM 46005766 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000491 | PIPING NI [SITE SURVEY] #83 OIL SYSTEM 46005777 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000492 | PIPING NI [SITE SURVEY] #84 OIL SYSTEM 46005778 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000493 | PIPING NI [SITE SURVEY] #85 OIL SYSTEM 46006416 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000494 | PIPING NI [SITE SURVEY] #86 OIL SYSTEM 46006753 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000495 | PIPING NI [SITE SURVEY] #87 OIL SYSTEM 46007152 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000496 | PIPING NI [SITE SURVEY] #88 OIL SYSTEM 46007161 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000497 | PIPING NI [SITE SURVEY] #89 OIL SYSTEM 46007422 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000498 | PIPING NI [SITE SURVEY] #90 OIL SYSTEM 46007524 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000499 | PIPING NI [SITE SURVEY] #91 OIL SYSTEM 46007525 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000500 | PIPING NI [SITE SURVEY] #92 OIL SYSTEM 46007526 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000501 | PIPING NI [SITE SURVEY] #93 OIL SYSTEM 46007527 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000502 | PIPING NI [SITE SURVEY] #94 OIL SYSTEM 46007528 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000503 | PIPING NI [SITE SURVEY] #95 OIL SYSTEM 46007529 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000504 | PIPING NI [SITE SURVEY] #96 OIL SYSTEM 46007530 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000505 | PIPING NI [SITE SURVEY] #97 OIL SYSTEM 46007531 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000506 | PIPING NI [SITE SURVEY] #98 OIL SYSTEM 46007532 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000507 | PIPING NI [SITE SURVEY] #99 OIL SYSTEM 46007591 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000508 | PIPING NI [SITE SURVEY] #100 OIL SYSTEM 46007592 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000509 | PIPING NI [SITE SURVEY] #101 OIL SYSTEM 46005366 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000510 | PIPING NI [SITE SURVEY] #102 OIL SYSTEM 46006033 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000511 | PIPING NI [SITE SURVEY] #103 OIL SYSTEM 46006283 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000512 | PIPING NI [SITE SURVEY] #104 OIL SYSTEM 46007160 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000513 | PIPING NI [SITE SURVEY] #105 OIL SYSTEM 46007560 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000514 | PIPING NI [SITE SURVEY] #106 OIL SYSTEM 46007562-45 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000515 | PIPING NI [SITE SURVEY] #107 OIL SYSTEM 46007563-3 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000516 | PIPING NI [SITE SURVEY] #108 WATER INJECTION 46007274 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000517 | PIPING NI [SITE SURVEY] #109 GAS SYSTEM 46007556 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000518 | PIPING NI [SITE SURVEY] #110 GAS SYSTEM 46005903 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000519 | PIPING NI [SITE SURVEY] #111 OIL SYSTEM 46005741 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000520 | PIPING NI [SITE SURVEY] #112 OIL SYSTEM 46007132 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000521 | PIPING NI [SITE SURVEY] #113 OIL SYSTEM 46007205 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000522 | PIPING NI [SITE SURVEY] #114 OIL SYSTEM 46006278 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000523 | PIPING NI [SITE SURVEY] #115 OIL SYSTEM 46006632 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000524 | PIPING NI [SITE SURVEY] #116 OIL SYSTEM 46006922 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000525 | PIPING NI [SITE SURVEY] #117 OIL SYSTEM 46007570-33 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000526 | PIPING NI [SITE SURVEY] #118 HVAC / HOT WATER SYSTEM 46004977 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000527 | PIPING NI [SITE SURVEY] #119 HVAC / HOT WATER SYSTEM 46004982 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000528 | PIPING NI [SITE SURVEY] #120 COOLING WATER SYSTEM 46005973-12 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000529 | PIPING NI [SITE SURVEY] #121 COOLING WATER SYSTEM 46007183 | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000530 | PIPING NI# [ISOMETRIC]1 AIR SYSTEM 46005853 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000531 | PIPING NI# [ISOMETRIC]2 AIR SYSTEM 46005855 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000532 | PIPING NI# [ISOMETRIC]3 AIR SYSTEM 46005856 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000533 | PIPING NI# [ISOMETRIC]4 AIR SYSTEM 46007510 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000534 | PIPING NI# [ISOMETRIC]5 CHEMICAL SYSTEM 46006147 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000535 | PIPING NI# [ISOMETRIC]6 COOLING WATER SYSTEM 46005504 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000536 | PIPING NI# [ISOMETRIC]7 COOLING WATER SYSTEM 46005573 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000537 | PIPING NI# [ISOMETRIC]8 COOLING WATER SYSTEM 46005783 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000538 | PIPING NI# [ISOMETRIC]9 COOLING WATER SYSTEM 46005784 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000539 | PIPING NI# [ISOMETRIC]10 COOLING WATER SYSTEM 46005785 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000540 | PIPING NI# [ISOMETRIC]11 COOLING WATER SYSTEM 46005786 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000541 | PIPING NI# [ISOMETRIC]12 COOLING WATER SYSTEM 46005787 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000542 | PIPING NI# [ISOMETRIC]13 COOLING WATER SYSTEM 46005833 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000543 | PIPING NI# [ISOMETRIC]14 COOLING WATER SYSTEM 46005940 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000544 | PIPING NI# [ISOMETRIC]15 COOLING WATER SYSTEM 46005968 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000545 | PIPING NI# [ISOMETRIC]16 COOLING WATER SYSTEM 46006014 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000546 | PIPING NI# [ISOMETRIC]17 COOLING WATER SYSTEM 46006099 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000547 | PIPING NI# [ISOMETRIC]18 COOLING WATER SYSTEM 46006150 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000548 | PIPING NI# [ISOMETRIC]19 COOLING WATER SYSTEM 46006151 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000549 | PIPING NI# [ISOMETRIC]20 COOLING WATER SYSTEM 46006181 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000550 | PIPING NI# [ISOMETRIC]21 COOLING WATER SYSTEM 46006223 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000551 | PIPING NI# [ISOMETRIC]22 COOLING WATER SYSTEM 46006624 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000552 | PIPING NI# [ISOMETRIC]23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000553 | PIPING NI# [ISOMETRIC]24 COOLING WATER SYSTEM 46006762 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000554 | PIPING NI# [ISOMETRIC]25 COOLING WATER SYSTEM 46006882 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000555 | PIPING NI# [ISOMETRIC]26 COOLING WATER SYSTEM 46006894 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000556 | PIPING NI# [ISOMETRIC]27 COOLING WATER SYSTEM 46007199 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000557 | PIPING NI# [ISOMETRIC]28 COOLING WATER SYSTEM 46007200 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000558 | PIPING NI# [ISOMETRIC]29 COOLING WATER SYSTEM 46007304 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000559 | PIPING NI# [ISOMETRIC]30 COOLING WATER SYSTEM 46007508 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000560 | PIPING NI# [ISOMETRIC]31 COOLING WATER SYSTEM 46007576 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000561 | PIPING NI# [ISOMETRIC]32 COOLING WATER SYSTEM 46007602 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000562 | PIPING NI# [ISOMETRIC]33 COOLING WATER SYSTEM 46007603 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000563 | PIPING NI# [ISOMETRIC]34 COOLING WATER SYSTEM 46007604 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000564 | PIPING NI# [ISOMETRIC]35 COOLING WATER SYSTEM 46007605 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000565 | PIPING NI# [ISOMETRIC]36 COOLING WATER SYSTEM 46007606 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000566 | PIPING NI# [ISOMETRIC]37 COOLING WATER SYSTEM 46007607 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000567 | PIPING NI# [ISOMETRIC]38 COOLING WATER SYSTEM 46007614 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000568 | PIPING NI# [ISOMETRIC]39 COOLING WATER SYSTEM 46007615 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000569 | PIPING NI# [ISOMETRIC]40 COOLING WATER SYSTEM 46005411 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000570 | PIPING NI# [ISOMETRIC]41 COOLING WATER SYSTEM 46006013 | 0.2% | 2022-12-21 | 2023-01-05 | 2023-01-20 | 2022-12-21 | 2023-01-05 | 2023-01-20 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000571 | PIPING NI# [ISOMETRIC]42 COOLING WATER SYSTEM 46006015 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000572 | PIPING NI# [ISOMETRIC]43 FIREWATER SYSTEM 46004394 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000573 | PIPING NI# [ISOMETRIC]44 FIREWATER SYSTEM 46004801 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000574 | PIPING NI# [ISOMETRIC]45 FIREWATER SYSTEM 46005362 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000575 | PIPING NI# [ISOMETRIC]46 FIREWATER SYSTEM 46005367 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000576 | PIPING NI# [ISOMETRIC]47 FIREWATER SYSTEM 46007197 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000577 | PIPING NI# [ISOMETRIC]48 GAS SYSTEM 46005502 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000578 | PIPING NI# [ISOMETRIC]49 GAS SYSTEM 46006182 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000579 | PIPING NI# [ISOMETRIC]50 GAS SYSTEM 46006183 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000580 | PIPING NI# [ISOMETRIC]51 GAS SYSTEM 46006375 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000581 | PIPING NI# [ISOMETRIC]52 GAS SYSTEM 46006660 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000582 | PIPING NI# [ISOMETRIC]53 GAS SYSTEM 46007151 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000583 | PIPING NI# [ISOMETRIC]54 GAS SYSTEM 46007163 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000584 | PIPING NI# [ISOMETRIC]55 GAS SYSTEM 46007268 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000585 | PIPING NI# [ISOMETRIC]56 GAS SYSTEM 46007522 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000586 | PIPING NI# [ISOMETRIC]57 GAS SYSTEM 46007553 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000587 | PIPING NI# [ISOMETRIC]58 GAS SYSTEM 46007577 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000588 | PIPING NI# [ISOMETRIC]59 GAS SYSTEM 46004652 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000589 | PIPING NI# [ISOMETRIC]60 HVAC / HOT WATER SYSTEM 46004662 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000590 | PIPING NI# [ISOMETRIC]61 HVAC / HOT WATER SYSTEM 46005769 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000591 | PIPING NI# [ISOMETRIC]62 HVAC / HOT WATER SYSTEM 46005770 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000592 | PIPING NI# [ISOMETRIC]63 HVAC / HOT WATER SYSTEM 46005915 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000593 | PIPING NI# [ISOMETRIC]64 HVAC / HOT WATER SYSTEM 46005982 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000594 | PIPING NI# [ISOMETRIC]65 HVAC / HOT WATER SYSTEM 46007045 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000595 | PIPING NI# [ISOMETRIC]66 HVAC / HOT WATER SYSTEM 46007052 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000596 | PIPING NI# [ISOMETRIC]67 HVAC / HOT WATER SYSTEM 46007566 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000597 | PIPING NI# [ISOMETRIC]68 HVAC / HOT WATER SYSTEM 46004053 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000598 | PIPING NI# [ISOMETRIC]69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000599 | PIPING NI# [ISOMETRIC]70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000600 | PIPING NI# [ISOMETRIC]71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000601 | PIPING NI# [ISOMETRIC]72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000602 | PIPING NI# [ISOMETRIC]73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000603 | PIPING NI# [ISOMETRIC]74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000604 | PIPING NI# [ISOMETRIC]75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000605 | PIPING NI# [ISOMETRIC]76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000606 | PIPING NI# [ISOMETRIC]77 INERT SYSTEM 46007407 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000607 | PIPING NI# [ISOMETRIC]78 INERT SYSTEM 46007408 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000608 | PIPING NI# [ISOMETRIC]79 OIL SYSTEM 46003301 | 0.2% | 2023-01-01 | 2023-01-16 | 2023-01-31 | 2023-01-01 | 2023-01-16 | 2023-01-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000609 | PIPING NI# [ISOMETRIC]80 OIL SYSTEM 46005365 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000610 | PIPING NI# [ISOMETRIC]81 OIL SYSTEM 46005594 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000611 | PIPING NI# [ISOMETRIC]82 OIL SYSTEM 46005766 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000612 | PIPING NI# [ISOMETRIC]83 OIL SYSTEM 46005777 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000613 | PIPING NI# [ISOMETRIC]84 OIL SYSTEM 46005778 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000614 | PIPING NI# [ISOMETRIC]85 OIL SYSTEM 46006416 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000615 | PIPING NI# [ISOMETRIC]86 OIL SYSTEM 46006753 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000616 | PIPING NI# [ISOMETRIC]87 OIL SYSTEM 46007152 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000617 | PIPING NI# [ISOMETRIC]88 OIL SYSTEM 46007161 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000618 | PIPING NI# [ISOMETRIC]89 OIL SYSTEM 46007422 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000619 | PIPING NI# [ISOMETRIC]90 OIL SYSTEM 46007524 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000620 | PIPING NI# [ISOMETRIC]91 OIL SYSTEM 46007525 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000621 | PIPING NI# [ISOMETRIC]92 OIL SYSTEM 46007526 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000622 | PIPING NI# [ISOMETRIC]93 OIL SYSTEM 46007527 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000623 | PIPING NI# [ISOMETRIC]94 OIL SYSTEM 46007528 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000624 | PIPING NI# [ISOMETRIC]95 OIL SYSTEM 46007529 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000625 | PIPING NI# [ISOMETRIC]96 OIL SYSTEM 46007530 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000626 | PIPING NI# [ISOMETRIC]97 OIL SYSTEM 46007531 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000627 | PIPING NI# [ISOMETRIC]98 OIL SYSTEM 46007532 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000628 | PIPING NI# [ISOMETRIC]99 OIL SYSTEM 46007591 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000629 | PIPING NI# [ISOMETRIC]100 OIL SYSTEM 46007592 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000630 | PIPING NI# [ISOMETRIC]101 OIL SYSTEM 46005366 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000631 | PIPING NI# [ISOMETRIC]102 OIL SYSTEM 46006033 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000632 | PIPING NI# [ISOMETRIC]103 OIL SYSTEM 46006283 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000633 | PIPING NI# [ISOMETRIC]104 OIL SYSTEM 46007160 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000634 | PIPING NI# [ISOMETRIC]105 OIL SYSTEM 46007560 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000635 | PIPING NI# [ISOMETRIC]106 OIL SYSTEM 46007562-45 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000636 | PIPING NI# [ISOMETRIC]107 OIL SYSTEM 46007563-3 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000637 | PIPING NI# [ISOMETRIC]108 WATER INJECTION 46007274 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000638 | PIPING NI# [ISOMETRIC]109 GAS SYSTEM 46007556 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000639 | PIPING NI# [ISOMETRIC]110 GAS SYSTEM 46005903 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000640 | PIPING NI# [ISOMETRIC]111 OIL SYSTEM 46005741 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000641 | PIPING NI# [ISOMETRIC]112 OIL SYSTEM 46007132 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000642 | PIPING NI# [ISOMETRIC]113 OIL SYSTEM 46007205 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000643 | PIPING NI# [ISOMETRIC]114 OIL SYSTEM 46006278 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000644 | PIPING NI# [ISOMETRIC]115 OIL SYSTEM 46006632 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000645 | PIPING NI# [ISOMETRIC]116 OIL SYSTEM 46006922 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000646 | PIPING NI# [ISOMETRIC]117 OIL SYSTEM 46007570-33 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000647 | PIPING NI# [ISOMETRIC]118 HVAC / HOT WATER SYSTEM 46004977 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000648 | PIPING NI# [ISOMETRIC]119 HVAC / HOT WATER SYSTEM 46004982 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000649 | PIPING NI# [ISOMETRIC]120 COOLING WATER SYSTEM 46005973-12 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000650 | PIPING NI# [ISOMETRIC]121 COOLING WATER SYSTEM 46007183 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000651 | PIPING NI [DOSSIER LIFTING] #1 AIR SYSTEM 46005853 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000652 | PIPING NI [DOSSIER LIFTING] #2 AIR SYSTEM 46005855 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000653 | PIPING NI [DOSSIER LIFTING] #3 AIR SYSTEM 46005856 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000654 | PIPING NI [DOSSIER LIFTING] #4 AIR SYSTEM 46007510 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000655 | PIPING NI [DOSSIER LIFTING] #5 CHEMICAL SYSTEM 46006147 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000656 | PIPING NI [DOSSIER LIFTING] #6 COOLING WATER SYSTEM 46005504 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000657 | PIPING NI [DOSSIER LIFTING] #7 COOLING WATER SYSTEM 46005573 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000658 | PIPING NI [DOSSIER LIFTING] #8 COOLING WATER SYSTEM 46005783 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000659 | PIPING NI [DOSSIER LIFTING] #9 COOLING WATER SYSTEM 46005784 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000660 | PIPING NI [DOSSIER LIFTING] #10 COOLING WATER SYSTEM 46005785 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000661 | PIPING NI [DOSSIER LIFTING] #11 COOLING WATER SYSTEM 46005786 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000662 | PIPING NI [DOSSIER LIFTING] #12 COOLING WATER SYSTEM 46005787 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000663 | PIPING NI [DOSSIER LIFTING] #13 COOLING WATER SYSTEM 46005833 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000664 | PIPING NI [DOSSIER LIFTING] #14 COOLING WATER SYSTEM 46005940 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000665 | PIPING NI [DOSSIER LIFTING] #15 COOLING WATER SYSTEM 46005968 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000666 | PIPING NI [DOSSIER LIFTING] #16 COOLING WATER SYSTEM 46006014 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000667 | PIPING NI [DOSSIER LIFTING] #17 COOLING WATER SYSTEM 46006099 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000668 | PIPING NI [DOSSIER LIFTING] #18 COOLING WATER SYSTEM 46006150 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000669 | PIPING NI [DOSSIER LIFTING] #19 COOLING WATER SYSTEM 46006151 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000670 | PIPING NI [DOSSIER LIFTING] #20 COOLING WATER SYSTEM 46006181 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000671 | PIPING NI [DOSSIER LIFTING] #21 COOLING WATER SYSTEM 46006223 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000672 | PIPING NI [DOSSIER LIFTING] #22 COOLING WATER SYSTEM 46006624 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000673 | PIPING NI [DOSSIER LIFTING] #23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000674 | PIPING NI [DOSSIER LIFTING] #24 COOLING WATER SYSTEM 46006762 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000675 | PIPING NI [DOSSIER LIFTING] #25 COOLING WATER SYSTEM 46006882 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000676 | PIPING NI [DOSSIER LIFTING] #26 COOLING WATER SYSTEM 46006894 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000677 | PIPING NI [DOSSIER LIFTING] #27 COOLING WATER SYSTEM 46007199 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000678 | PIPING NI [DOSSIER LIFTING] #28 COOLING WATER SYSTEM 46007200 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000679 | PIPING NI [DOSSIER LIFTING] #29 COOLING WATER SYSTEM 46007304 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000680 | PIPING NI [DOSSIER LIFTING] #30 COOLING WATER SYSTEM 46007508 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000681 | PIPING NI [DOSSIER LIFTING] #31 COOLING WATER SYSTEM 46007576 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000682 | PIPING NI [DOSSIER LIFTING] #32 COOLING WATER SYSTEM 46007602 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000683 | PIPING NI [DOSSIER LIFTING] #33 COOLING WATER SYSTEM 46007603 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000684 | PIPING NI [DOSSIER LIFTING] #34 COOLING WATER SYSTEM 46007604 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000685 | PIPING NI [DOSSIER LIFTING] #35 COOLING WATER SYSTEM 46007605 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000686 | PIPING NI [DOSSIER LIFTING] #36 COOLING WATER SYSTEM 46007606 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000687 | PIPING NI [DOSSIER LIFTING] #37 COOLING WATER SYSTEM 46007607 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000688 | PIPING NI [DOSSIER LIFTING] #38 COOLING WATER SYSTEM 46007614 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000689 | PIPING NI [DOSSIER LIFTING] #39 COOLING WATER SYSTEM 46007615 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000690 | PIPING NI [DOSSIER LIFTING] #40 COOLING WATER SYSTEM 46005411 | 0.2% | 2023-03-27 | 2023-04-11 | 2023-04-26 | 2023-03-27 | 2023-04-11 | 2023-04-26 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000691 | PIPING NI [DOSSIER LIFTING] #41 COOLING WATER SYSTEM 46006013 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000692 | PIPING NI [DOSSIER LIFTING] #42 COOLING WATER SYSTEM 46006015 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000693 | PIPING NI [DOSSIER LIFTING] #43 FIREWATER SYSTEM 46004394 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000694 | PIPING NI [DOSSIER LIFTING] #44 FIREWATER SYSTEM 46004801 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000695 | PIPING NI [DOSSIER LIFTING] #45 FIREWATER SYSTEM 46005362 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000696 | PIPING NI [DOSSIER LIFTING] #46 FIREWATER SYSTEM 46005367 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000697 | PIPING NI [DOSSIER LIFTING] #47 FIREWATER SYSTEM 46007197 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000698 | PIPING NI [DOSSIER LIFTING] #48 GAS SYSTEM 46005502 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000699 | PIPING NI [DOSSIER LIFTING] #49 GAS SYSTEM 46006182 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000700 | PIPING NI [DOSSIER LIFTING] #50 GAS SYSTEM 46006183 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000701 | PIPING NI [DOSSIER LIFTING] #51 GAS SYSTEM 46006375 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000702 | PIPING NI [DOSSIER LIFTING] #52 GAS SYSTEM 46006660 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000703 | PIPING NI [DOSSIER LIFTING] #53 GAS SYSTEM 46007151 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000704 | PIPING NI [DOSSIER LIFTING] #54 GAS SYSTEM 46007163 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000705 | PIPING NI [DOSSIER LIFTING] #55 GAS SYSTEM 46007268 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000706 | PIPING NI [DOSSIER LIFTING] #56 GAS SYSTEM 46007522 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000707 | PIPING NI [DOSSIER LIFTING] #57 GAS SYSTEM 46007553 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000708 | PIPING NI [DOSSIER LIFTING] #58 GAS SYSTEM 46007577 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000709 | PIPING NI [DOSSIER LIFTING] #59 GAS SYSTEM 46004652 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000710 | PIPING NI [DOSSIER LIFTING] #60 HVAC / HOT WATER SYSTEM 46004662 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000711 | PIPING NI [DOSSIER LIFTING] #61 HVAC / HOT WATER SYSTEM 46005769 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000712 | PIPING NI [DOSSIER LIFTING] #62 HVAC / HOT WATER SYSTEM 46005770 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000713 | PIPING NI [DOSSIER LIFTING] #63 HVAC / HOT WATER SYSTEM 46005915 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000714 | PIPING NI [DOSSIER LIFTING] #64 HVAC / HOT WATER SYSTEM 46005982 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000715 | PIPING NI [DOSSIER LIFTING] #65 HVAC / HOT WATER SYSTEM 46007045 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000716 | PIPING NI [DOSSIER LIFTING] #66 HVAC / HOT WATER SYSTEM 46007052 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000717 | PIPING NI [DOSSIER LIFTING] #67 HVAC / HOT WATER SYSTEM 46007566 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000718 | PIPING NI [DOSSIER LIFTING] #68 HVAC / HOT WATER SYSTEM 46004053 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000719 | PIPING NI [DOSSIER LIFTING] #69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000720 | PIPING NI [DOSSIER LIFTING] #70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000721 | PIPING NI [DOSSIER LIFTING] #71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000722 | PIPING NI [DOSSIER LIFTING] #72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000723 | PIPING NI [DOSSIER LIFTING] #73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000724 | PIPING NI [DOSSIER LIFTING] #74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000725 | PIPING NI [DOSSIER LIFTING] #75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000726 | PIPING NI [DOSSIER LIFTING] #76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000727 | PIPING NI [DOSSIER LIFTING] #77 INERT SYSTEM 46007407 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000728 | PIPING NI [DOSSIER LIFTING] #78 INERT SYSTEM 46007408 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000729 | PIPING NI [DOSSIER LIFTING] #79 OIL SYSTEM 46003301 | 0.2% | 2023-04-06 | 2023-04-21 | 2023-05-06 | 2023-04-06 | 2023-04-21 | 2023-05-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000730 | PIPING NI [DOSSIER LIFTING] #80 OIL SYSTEM 46005365 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000731 | PIPING NI [DOSSIER LIFTING] #81 OIL SYSTEM 46005594 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000732 | PIPING NI [DOSSIER LIFTING] #82 OIL SYSTEM 46005766 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000733 | PIPING NI [DOSSIER LIFTING] #83 OIL SYSTEM 46005777 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000734 | PIPING NI [DOSSIER LIFTING] #84 OIL SYSTEM 46005778 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000735 | PIPING NI [DOSSIER LIFTING] #85 OIL SYSTEM 46006416 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000736 | PIPING NI [DOSSIER LIFTING] #86 OIL SYSTEM 46006753 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000737 | PIPING NI [DOSSIER LIFTING] #87 OIL SYSTEM 46007152 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000738 | PIPING NI [DOSSIER LIFTING] #88 OIL SYSTEM 46007161 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000739 | PIPING NI [DOSSIER LIFTING] #89 OIL SYSTEM 46007422 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000740 | PIPING NI [DOSSIER LIFTING] #90 OIL SYSTEM 46007524 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000741 | PIPING NI [DOSSIER LIFTING] #91 OIL SYSTEM 46007525 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000742 | PIPING NI [DOSSIER LIFTING] #92 OIL SYSTEM 46007526 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000743 | PIPING NI [DOSSIER LIFTING] #93 OIL SYSTEM 46007527 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000744 | PIPING NI [DOSSIER LIFTING] #94 OIL SYSTEM 46007528 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000745 | PIPING NI [DOSSIER LIFTING] #95 OIL SYSTEM 46007529 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000746 | PIPING NI [DOSSIER LIFTING] #96 OIL SYSTEM 46007530 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000747 | PIPING NI [DOSSIER LIFTING] #97 OIL SYSTEM 46007531 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000748 | PIPING NI [DOSSIER LIFTING] #98 OIL SYSTEM 46007532 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000749 | PIPING NI [DOSSIER LIFTING] #99 OIL SYSTEM 46007591 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000750 | PIPING NI [DOSSIER LIFTING] #100 OIL SYSTEM 46007592 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000751 | PIPING NI [DOSSIER LIFTING] #101 OIL SYSTEM 46005366 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000752 | PIPING NI [DOSSIER LIFTING] #102 OIL SYSTEM 46006033 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000753 | PIPING NI [DOSSIER LIFTING] #103 OIL SYSTEM 46006283 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000754 | PIPING NI [DOSSIER LIFTING] #104 OIL SYSTEM 46007160 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000755 | PIPING NI [DOSSIER LIFTING] #105 OIL SYSTEM 46007560 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000756 | PIPING NI [DOSSIER LIFTING] #106 OIL SYSTEM 46007562-45 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000757 | PIPING NI [DOSSIER LIFTING] #107 OIL SYSTEM 46007563-3 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000758 | PIPING NI [DOSSIER LIFTING] #108 WATER INJECTION 46007274 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000759 | PIPING NI [DOSSIER LIFTING] #109 GAS SYSTEM 46007556 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000760 | PIPING NI [DOSSIER LIFTING] #110 GAS SYSTEM 46005903 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000761 | PIPING NI [DOSSIER LIFTING] #111 OIL SYSTEM 46005741 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000762 | PIPING NI [DOSSIER LIFTING] #112 OIL SYSTEM 46007132 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000763 | PIPING NI [DOSSIER LIFTING] #113 OIL SYSTEM 46007205 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000764 | PIPING NI [DOSSIER LIFTING] #114 OIL SYSTEM 46006278 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000765 | PIPING NI [DOSSIER LIFTING] #115 OIL SYSTEM 46006632 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000766 | PIPING NI [DOSSIER LIFTING] #116 OIL SYSTEM 46006922 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000767 | PIPING NI [DOSSIER LIFTING] #117 OIL SYSTEM 46007570-33 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000768 | PIPING NI [DOSSIER LIFTING] #118 HVAC / HOT WATER SYSTEM 46004977 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000769 | PIPING NI [DOSSIER LIFTING] #119 HVAC / HOT WATER SYSTEM 46004982 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000770 | PIPING NI [DOSSIER LIFTING] #120 COOLING WATER SYSTEM 46005973-12 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000771 | PIPING NI [DOSSIER LIFTING] #121 COOLING WATER SYSTEM 46007183 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000772 | PIPING NI# [DOSSIER FINAL] 1 AIR SYSTEM 46005853 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000773 | PIPING NI# [DOSSIER FINAL] 2 AIR SYSTEM 46005855 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000774 | PIPING NI# [DOSSIER FINAL] 3 AIR SYSTEM 46005856 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000775 | PIPING NI# [DOSSIER FINAL] 4 AIR SYSTEM 46007510 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000776 | PIPING NI# [DOSSIER FINAL] 5 CHEMICAL SYSTEM 46006147 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000777 | PIPING NI# [DOSSIER FINAL] 6 COOLING WATER SYSTEM 46005504 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000778 | PIPING NI# [DOSSIER FINAL] 7 COOLING WATER SYSTEM 46005573 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000779 | PIPING NI# [DOSSIER FINAL] 8 COOLING WATER SYSTEM 46005783 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000780 | PIPING NI# [DOSSIER FINAL] 9 COOLING WATER SYSTEM 46005784 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000781 | PIPING NI# [DOSSIER FINAL] 10 COOLING WATER SYSTEM 46005785 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000782 | PIPING NI# [DOSSIER FINAL] 11 COOLING WATER SYSTEM 46005786 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000783 | PIPING NI# [DOSSIER FINAL] 12 COOLING WATER SYSTEM 46005787 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000784 | PIPING NI# [DOSSIER FINAL] 13 COOLING WATER SYSTEM 46005833 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000785 | PIPING NI# [DOSSIER FINAL] 14 COOLING WATER SYSTEM 46005940 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000786 | PIPING NI# [DOSSIER FINAL] 15 COOLING WATER SYSTEM 46005968 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000787 | PIPING NI# [DOSSIER FINAL] 16 COOLING WATER SYSTEM 46006014 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000788 | PIPING NI# [DOSSIER FINAL] 17 COOLING WATER SYSTEM 46006099 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000789 | PIPING NI# [DOSSIER FINAL] 18 COOLING WATER SYSTEM 46006150 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000790 | PIPING NI# [DOSSIER FINAL] 19 COOLING WATER SYSTEM 46006151 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000791 | PIPING NI# [DOSSIER FINAL] 20 COOLING WATER SYSTEM 46006181 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000792 | PIPING NI# [DOSSIER FINAL] 21 COOLING WATER SYSTEM 46006223 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000793 | PIPING NI# [DOSSIER FINAL] 22 COOLING WATER SYSTEM 46006624 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000794 | PIPING NI# [DOSSIER FINAL] 23 COOLING WATER SYSTEM 46006636 = 46006425 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000795 | PIPING NI# [DOSSIER FINAL] 24 COOLING WATER SYSTEM 46006762 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000796 | PIPING NI# [DOSSIER FINAL] 25 COOLING WATER SYSTEM 46006882 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000797 | PIPING NI# [DOSSIER FINAL] 26 COOLING WATER SYSTEM 46006894 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000798 | PIPING NI# [DOSSIER FINAL] 27 COOLING WATER SYSTEM 46007199 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000799 | PIPING NI# [DOSSIER FINAL] 28 COOLING WATER SYSTEM 46007200 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000800 | PIPING NI# [DOSSIER FINAL] 29 COOLING WATER SYSTEM 46007304 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000801 | PIPING NI# [DOSSIER FINAL] 30 COOLING WATER SYSTEM 46007508 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000802 | PIPING NI# [DOSSIER FINAL] 31 COOLING WATER SYSTEM 46007576 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000803 | PIPING NI# [DOSSIER FINAL] 32 COOLING WATER SYSTEM 46007602 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000804 | PIPING NI# [DOSSIER FINAL] 33 COOLING WATER SYSTEM 46007603 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000805 | PIPING NI# [DOSSIER FINAL] 34 COOLING WATER SYSTEM 46007604 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000806 | PIPING NI# [DOSSIER FINAL] 35 COOLING WATER SYSTEM 46007605 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000807 | PIPING NI# [DOSSIER FINAL] 36 COOLING WATER SYSTEM 46007606 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000808 | PIPING NI# [DOSSIER FINAL] 37 COOLING WATER SYSTEM 46007607 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000809 | PIPING NI# [DOSSIER FINAL] 38 COOLING WATER SYSTEM 46007614 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000810 | PIPING NI# [DOSSIER FINAL] 39 COOLING WATER SYSTEM 46007615 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000811 | PIPING NI# [DOSSIER FINAL] 40 COOLING WATER SYSTEM 46005411 | 0.2% | 2023-05-25 | 2023-06-09 | 2023-06-24 | 2023-05-25 | 2023-06-09 | 2023-06-24 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000812 | PIPING NI# [DOSSIER FINAL] 41 COOLING WATER SYSTEM 46006013 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000813 | PIPING NI# [DOSSIER FINAL] 42 COOLING WATER SYSTEM 46006015 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000814 | PIPING NI# [DOSSIER FINAL] 43 FIREWATER SYSTEM 46004394 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000815 | PIPING NI# [DOSSIER FINAL] 44 FIREWATER SYSTEM 46004801 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000816 | PIPING NI# [DOSSIER FINAL] 45 FIREWATER SYSTEM 46005362 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000817 | PIPING NI# [DOSSIER FINAL] 46 FIREWATER SYSTEM 46005367 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000818 | PIPING NI# [DOSSIER FINAL] 47 FIREWATER SYSTEM 46007197 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000819 | PIPING NI# [DOSSIER FINAL] 48 GAS SYSTEM 46005502 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000820 | PIPING NI# [DOSSIER FINAL] 49 GAS SYSTEM 46006182 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000821 | PIPING NI# [DOSSIER FINAL] 50 GAS SYSTEM 46006183 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000822 | PIPING NI# [DOSSIER FINAL] 51 GAS SYSTEM 46006375 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000823 | PIPING NI# [DOSSIER FINAL] 52 GAS SYSTEM 46006660 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000824 | PIPING NI# [DOSSIER FINAL] 53 GAS SYSTEM 46007151 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000825 | PIPING NI# [DOSSIER FINAL] 54 GAS SYSTEM 46007163 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000826 | PIPING NI# [DOSSIER FINAL] 55 GAS SYSTEM 46007268 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000827 | PIPING NI# [DOSSIER FINAL] 56 GAS SYSTEM 46007522 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000828 | PIPING NI# [DOSSIER FINAL] 57 GAS SYSTEM 46007553 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000829 | PIPING NI# [DOSSIER FINAL] 58 GAS SYSTEM 46007577 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000830 | PIPING NI# [DOSSIER FINAL] 59 GAS SYSTEM 46004652 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000831 | PIPING NI# [DOSSIER FINAL] 60 HVAC / HOT WATER SYSTEM 46004662 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000832 | PIPING NI# [DOSSIER FINAL] 61 HVAC / HOT WATER SYSTEM 46005769 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000833 | PIPING NI# [DOSSIER FINAL] 62 HVAC / HOT WATER SYSTEM 46005770 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000834 | PIPING NI# [DOSSIER FINAL] 63 HVAC / HOT WATER SYSTEM 46005915 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000835 | PIPING NI# [DOSSIER FINAL] 64 HVAC / HOT WATER SYSTEM 46005982 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000836 | PIPING NI# [DOSSIER FINAL] 65 HVAC / HOT WATER SYSTEM 46007045 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000837 | PIPING NI# [DOSSIER FINAL] 66 HVAC / HOT WATER SYSTEM 46007052 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000838 | PIPING NI# [DOSSIER FINAL] 67 HVAC / HOT WATER SYSTEM 46007566 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000839 | PIPING NI# [DOSSIER FINAL] 68 HVAC / HOT WATER SYSTEM 46004053 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000840 | PIPING NI# [DOSSIER FINAL] 69 HVAC / HOT WATER SYSTEM 46007561-2 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000841 | PIPING NI# [DOSSIER FINAL] 70 HVAC / HOT WATER SYSTEM 46007564-4 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000842 | PIPING NI# [DOSSIER FINAL] 71 HVAC / HOT WATER SYSTEM 46007565-21 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000843 | PIPING NI# [DOSSIER FINAL] 72 HVAC / HOT WATER SYSTEM 46007568-29 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000844 | PIPING NI# [DOSSIER FINAL] 73 HVAC / HOT WATER SYSTEM 46007571-34 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000845 | PIPING NI# [DOSSIER FINAL] 74 HVAC / HOT WATER SYSTEM 46007572-35 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000846 | PIPING NI# [DOSSIER FINAL] 75 HVAC / HOT WATER SYSTEM 46007573-39 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000847 | PIPING NI# [DOSSIER FINAL] 76 HVAC / HOT WATER SYSTEM 46007574-40 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000848 | PIPING NI# [DOSSIER FINAL] 77 INERT SYSTEM 46007407 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000849 | PIPING NI# [DOSSIER FINAL] 78 INERT SYSTEM 46007408 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000850 | PIPING NI# [DOSSIER FINAL] 79 OIL SYSTEM 46003301 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000851 | PIPING NI# [DOSSIER FINAL] 80 OIL SYSTEM 46005365 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000852 | PIPING NI# [DOSSIER FINAL] 81 OIL SYSTEM 46005594 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000853 | PIPING NI# [DOSSIER FINAL] 82 OIL SYSTEM 46005766 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000854 | PIPING NI# [DOSSIER FINAL] 83 OIL SYSTEM 46005777 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000855 | PIPING NI# [DOSSIER FINAL] 84 OIL SYSTEM 46005778 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000856 | PIPING NI# [DOSSIER FINAL] 85 OIL SYSTEM 46006416 | 0.2% | 2023-06-05 | 2023-06-20 | 2023-07-05 | 2023-06-05 | 2023-06-20 | 2023-07-05 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000857 | PIPING NI# [DOSSIER FINAL] 86 OIL SYSTEM 46006753 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000858 | PIPING NI# [DOSSIER FINAL] 87 OIL SYSTEM 46007152 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000859 | PIPING NI# [DOSSIER FINAL] 88 OIL SYSTEM 46007161 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000860 | PIPING NI# [DOSSIER FINAL] 89 OIL SYSTEM 46007422 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000861 | PIPING NI# [DOSSIER FINAL] 90 OIL SYSTEM 46007524 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000862 | PIPING NI# [DOSSIER FINAL] 91 OIL SYSTEM 46007525 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000863 | PIPING NI# [DOSSIER FINAL] 92 OIL SYSTEM 46007526 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000864 | PIPING NI# [DOSSIER FINAL] 93 OIL SYSTEM 46007527 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000865 | PIPING NI# [DOSSIER FINAL] 94 OIL SYSTEM 46007528 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000866 | PIPING NI# [DOSSIER FINAL] 95 OIL SYSTEM 46007529 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000867 | PIPING NI# [DOSSIER FINAL] 96 OIL SYSTEM 46007530 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000868 | PIPING NI# [DOSSIER FINAL] 97 OIL SYSTEM 46007531 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000869 | PIPING NI# [DOSSIER FINAL] 98 OIL SYSTEM 46007532 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000870 | PIPING NI# [DOSSIER FINAL] 99 OIL SYSTEM 46007591 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000871 | PIPING NI# [DOSSIER FINAL] 100 OIL SYSTEM 46007592 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000872 | PIPING NI# [DOSSIER FINAL] 101 OIL SYSTEM 46005366 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000873 | PIPING NI# [DOSSIER FINAL] 102 OIL SYSTEM 46006033 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000874 | PIPING NI# [DOSSIER FINAL] 103 OIL SYSTEM 46006283 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000875 | PIPING NI# [DOSSIER FINAL] 104 OIL SYSTEM 46007160 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000876 | PIPING NI# [DOSSIER FINAL] 105 OIL SYSTEM 46007560 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000877 | PIPING NI# [DOSSIER FINAL] 106 OIL SYSTEM 46007562-45 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000878 | PIPING NI# [DOSSIER FINAL] 107 OIL SYSTEM 46007563-3 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000879 | PIPING NI# [DOSSIER FINAL] 108 WATER INJECTION 46007274 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000880 | PIPING NI# [DOSSIER FINAL] 109 GAS SYSTEM 46007556 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000881 | PIPING NI# [DOSSIER FINAL] 110 GAS SYSTEM 46005903 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000882 | PIPING NI# [DOSSIER FINAL] 111 OIL SYSTEM 46005741 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000883 | PIPING NI# [DOSSIER FINAL] 112 OIL SYSTEM 46007132 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000884 | PIPING NI# [DOSSIER FINAL] 113 OIL SYSTEM 46007205 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000885 | PIPING NI# [DOSSIER FINAL] 114 OIL SYSTEM 46006278 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000886 | PIPING NI# [DOSSIER FINAL] 115 OIL SYSTEM 46006632 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000887 | PIPING NI# [DOSSIER FINAL] 116 OIL SYSTEM 46006922 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000888 | PIPING NI# [DOSSIER FINAL] 117 OIL SYSTEM 46007570-33 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000889 | PIPING NI# [DOSSIER FINAL] 118 HVAC / HOT WATER SYSTEM 46004977 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000890 | PIPING NI# [DOSSIER FINAL] 119 HVAC / HOT WATER SYSTEM 46004982 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000891 | PIPING NI# [DOSSIER FINAL] 120 COOLING WATER SYSTEM 46005973-12 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000892 | PIPING NI# [DOSSIER FINAL] 121 COOLING WATER SYSTEM 46007183 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000893 | SMR [SITE SURVEY] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000894 | SMR [SITE SURVEY] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000895 | SMR [SITE SURVEY] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000896 | SMR [SITE SURVEY] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000897 | SMR [SITE SURVEY] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000898 | SMR [SITE SURVEY] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000899 | SMR [SITE SURVEY] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000900 | SMR [SITE SURVEY] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000901 | SMR [SITE SURVEY] #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000902 | SMR [SITE SURVEY] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | 0.2% | 2022-12-15 | 2022-12-30 | 2023-01-14 | 2022-12-15 | 2022-12-30 | 2023-01-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000903 | SMR [SITE SURVEY] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | 0.2% | 2022-12-30 | 2023-01-14 | 2023-01-29 | 2022-12-30 | 2023-01-14 | 2023-01-29 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000904 | SMR [SITE SURVEY] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | 0.2% | 2022-12-30 | 2023-01-14 | 2023-01-29 | 2022-12-30 | 2023-01-14 | 2023-01-29 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000905 | SMR [SITE SURVEY] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | 0.2% | 2022-12-30 | 2023-01-14 | 2023-01-29 | 2022-12-30 | 2023-01-14 | 2023-01-29 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000906 | SMR [ISOMETRIC] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Dossier Final | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000907 | SMR [ISOMETRIC] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Dossier Final | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000908 | SMR [ISOMETRIC] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Dossier Final | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000909 | SMR [ISOMETRIC] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Dossier Final | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000910 | SMR [ISOMETRIC] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Dossier Final | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000911 | SMR [ISOMETRIC] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000912 | SMR [ISOMETRIC] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000913 | SMR [ISOMETRIC] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000914 | SMR [ISOMETRIC] #9 - NG-AKP-RFM-2022-000026 - Installation of Dossier Finallation valves on instrument air network - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000915 | SMR [ISOMETRIC] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000916 | SMR [ISOMETRIC] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000917 | SMR [ISOMETRIC] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000918 | SMR [ISOMETRIC] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Dossier Final | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000919 | SMR [DOSSIER LIFTING} #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000920 | SMR [DOSSIER LIFTING} #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000921 | SMR [DOSSIER LIFTING} #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000922 | SMR [DOSSIER LIFTING} #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000923 | SMR [DOSSIER LIFTING} #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000924 | SMR [DOSSIER LIFTING} #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000925 | SMR [DOSSIER LIFTING} #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000926 | SMR [DOSSIER LIFTING} #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000927 | SMR [DOSSIER LIFTING} #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000928 | SMR [DOSSIER LIFTING} #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000929 | SMR [DOSSIER LIFTING} #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000930 | SMR [DOSSIER LIFTING} #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000931 | SMR [DOSSIER LIFTING} #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000932 | SMR [DOSSIER FINAL] #1 - NG-AKP-RFM-2022-000007 - Gas injection FV-54801 replacement and installation of PT on GIC inlet scrubber - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000933 | SMR [DOSSIER FINAL] #2 - NG-AKP-RFM-2022-000004 - Modification of AKPO GI & GE manifold depressurization line - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000934 | SMR [DOSSIER FINAL] #3 - AKP-21-001 - Installation of PDT as LT for flare HP KO drum - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000935 | SMR [DOSSIER FINAL] #4 - AKP-20-001 - Installation of DP LDT 35108 on 5DS3510 - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000936 | SMR [DOSSIER FINAL] #5 - AKP-21-009 - Installation of new AKPO LP/HP flare tips - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000937 | SMR [DOSSIER FINAL] #6 - NG-AKP-RFM-2022-000013 - Installation of PP on TEG regeneration package - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000938 | SMR [DOSSIER FINAL] #7 - NG-AKP-RFM-2022-000015 - Installation hydrocarbon blanketing and vent recovering - Survey Report | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000939 | SMR [DOSSIER FINAL] #8 - NG-AKP-RFM-2022-000020 - HVAC piping system modifications - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000940 | SMR [DOSSIER FINAL] #9 - NG-AKP-RFM-2022-000026 - Installation of isolation valves on instrument air network - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000941 | SMR [DOSSIER FINAL] #10 - AKP-20-006 - Installation of sampling points on AKPO production risers - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000942 | SMR [DOSSIER FINAL] #11 - NG-AKP-RFM-2022-0000XX - MP switch tie-in modifications - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000943 | SMR [DOSSIER FINAL] #12 - NG-AKP-RFM-2022-0000YY - Modifications of AKPO GEL arrival PV on Amenam - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000944 | SMR [DOSSIER FINAL] #13 - NG-AKP-RFM-2022-000019 - Design of support for PT 31011 and 31013 on test manifold - Survey Report | 0.2% | 2023-06-30 | 2023-07-15 | 2023-07-30 | 2023-06-30 | 2023-07-15 | 2023-07-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000945 | [SITE SURVEY] 5-EC-5210 Mp Compressor suction Cooler | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000946 | [SITE SURVEY] 5-EC-5510-A Dehydrator intlet Cooler A | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000947 | [SITE SURVEY] 5-EC-5510-B Dehydrator intlet Cooler B | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000948 | [SITE SURVEY] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000949 | [SITE SURVEY] 5-EC-5110 LP Compressor Suction Cooler | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000950 | [SITE SURVEY] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000951 | [SITE SURVEY] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000952 | [SITE SURVEY] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000953 | [SITE SURVEY] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000954 | [SITE SURVEY] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000955 | [SITE SURVEY] 5-EC-9910 Crude Oil Re-Heater | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000956 | [SITE SURVEY] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000957 | [SITE SURVEY] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000958 | [SITE SURVEY] 5-EC-5310-A HP Compressor Suction Cooler A | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000959 | [SITE SURVEY] 5-EC-5310-B HP Compressor Suction Cooler B | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000960 | [DOSSIER LIFTING] 5-EC-5210 Mp Compressor suction Cooler | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000961 | [DOSSIER LIFTING] 5-EC-5510-A Dehydrator intlet Cooler A | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000962 | [DOSSIER LIFTING] 5-EC-5510-B Dehydrator intlet Cooler B | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000963 | [DOSSIER LIFTING] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000964 | [DOSSIER LIFTING] 5-EC-5110 LP Compressor Suction Cooler | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000965 | [DOSSIER LIFTING] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000966 | [DOSSIER LIFTING] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000967 | [DOSSIER LIFTING] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000968 | [DOSSIER LIFTING] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000969 | [DOSSIER LIFTING] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000970 | [DOSSIER LIFTING] 5-EC-9910 Crude Oil Re-Heater | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000971 | [DOSSIER LIFTING] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000972 | [DOSSIER LIFTING] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000973 | [DOSSIER LIFTING] 5-EC-5310-A HP Compressor Suction Cooler A | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000974 | [DOSSIER LIFTING] 5-EC-5310-B HP Compressor Suction Cooler B | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000975 | [CLEANING PROCEDURES] 5-EC-5210 Mp Compressor suction Cooler | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000976 | [CLEANING PROCEDURES] 5-EC-5510-A Dehydrator intlet Cooler A | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000977 | [CLEANING PROCEDURES] 5-EC-5510-B Dehydrator intlet Cooler B | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000978 | [CLEANING PROCEDURES] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000979 | [CLEANING PROCEDURES] 5-EC-5110 LP Compressor Suction Cooler | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000980 | [CLEANING PROCEDURES] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000981 | [CLEANING PROCEDURES] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000982 | [CLEANING PROCEDURES] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000983 | [CLEANING PROCEDURES] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000984 | [CLEANING PROCEDURES] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000985 | [CLEANING PROCEDURES] 5-EC-9910 Crude Oil Re-Heater | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000986 | [CLEANING PROCEDURES] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000987 | [CLEANING PROCEDURES] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000988 | [CLEANING PROCEDURES] 5-EC-5310-A HP Compressor Suction Cooler A | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000989 | [CLEANING PROCEDURES] 5-EC-5310-B HP Compressor Suction Cooler B | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000990 | [DOSSIER FINAL] 5-EC-5210 Mp Compressor suction Cooler | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000991 | [DOSSIER FINAL] 5-EC-5510-A Dehydrator intlet Cooler A | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000992 | [DOSSIER FINAL] 5-EC-5510-B Dehydrator intlet Cooler B | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000993 | [DOSSIER FINAL] 5-EC-5544 Lean Glycol Cooler (TEG) | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000994 | [DOSSIER FINAL] 5-EC-5110 LP Compressor Suction Cooler | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000995 | [DOSSIER FINAL] 5-EC-5430-B Gas Export Compressor discharge Coolers B | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000996 | [DOSSIER FINAL] 5-EC-3310-A1 Crude Oil Pre-Heaters A1 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000997 | [DOSSIER FINAL] 5-EC-3310-A2 Crude Oil Pre-Heaters A2 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000998 | [DOSSIER FINAL] 5-EC-3310-B1 Crude Oil Pre-Heaters B1 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-000999 | [DOSSIER FINAL] 5-EC-3310-B2 Crude Oil Pre-Heaters B2 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001000 | [DOSSIER FINAL] 5-EC-9910 Crude Oil Re-Heater | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001001 | [DOSSIER FINAL] 5-EC-3320-B1 Crude Oil Heaters B1 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001002 | [DOSSIER FINAL] 5-EC-3320-B2 Crude Oil Heaters B2 | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001003 | [DOSSIER FINAL] 5-EC-5310-A HP Compressor Suction Cooler A | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001004 | [DOSSIER FINAL] 5-EC-5310-B HP Compressor Suction Cooler B | 0.2% | 2023-06-15 | 2023-06-30 | 2023-07-15 | 2023-06-15 | 2023-06-30 | 2023-07-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001005 | [SITE SURVEY] 5-DS-5410-A Gas Export Scrubber A | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001006 | [SITE SURVEY] 5-DS-5410-B Gas Export Scrubber B | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001007 | [SITE SURVEY] 5-DS-2210 Hp Fuel Gas Scrubber | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001008 | [SITE SURVEY] 5-DS-5120 LP Compressor suction Scrubber | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001009 | [SITE SURVEY] 5-DS-2240 LP Fuel Gas Scrubber | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001010 | [SITE SURVEY] 5-DS-5520 Dehydrator Inlet Scrubber | 0.2% | 2023-02-16 | 2023-03-03 | 2023-03-18 | 2023-02-16 | 2023-03-03 | 2023-03-18 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001011 | [DOSSIER LIFTING] 5-DS-5410-A Gas Export Scrubber A | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001012 | [DOSSIER LIFTING] 5-DS-5410-B Gas Export Scrubber B | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001013 | [DOSSIER LIFTING] 5-DS-2210 Hp Fuel Gas Scrubber | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001014 | [DOSSIER LIFTING] 5-DS-5120 LP Compressor suction Scrubber | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001015 | [DOSSIER LIFTING] 5-DS-2240 LP Fuel Gas Scrubber | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001016 | [DOSSIER LIFTING] 5-DS-5520 Dehydrator Inlet Scrubber | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001017 | [CLEANING PROCEDURES] 5-DS-5410-A Gas Export Scrubber A | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001018 | [CLEANING PROCEDURES] 5-DS-5410-B Gas Export Scrubber B | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001019 | [CLEANING PROCEDURES] 5-DS-2210 Hp Fuel Gas Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001020 | [CLEANING PROCEDURES] 5-DS-5120 LP Compressor suction Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001021 | [CLEANING PROCEDURES] 5-DS-2240 LP Fuel Gas Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001022 | [CLEANING PROCEDURES] 5-DS-5520 Dehydrator Inlet Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001023 | [DOSSIER FINAL] 5-DS-5410-A Gas Export Scrubber A | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001024 | [DOSSIER FINAL] 5-DS-5410-B Gas Export Scrubber B | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001025 | [DOSSIER FINAL] 5-DS-2210 Hp Fuel Gas Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001026 | [DOSSIER FINAL] 5-DS-5120 LP Compressor suction Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001027 | [DOSSIER FINAL] 5-DS-2240 LP Fuel Gas Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001028 | [DOSSIER FINAL] 5-DS-5520 Dehydrator Inlet Scrubber | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001029 | [SITE SURVEY] 5-DS-3110-A 1 Stage Separator A | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001030 | [SITE SURVEY] 5-DS-3110-B 1 Stage Separator B | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001031 | [SITE SURVEY] 5-DS-3210 2 Stage Separator | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001032 | [SITE SURVEY] 5-DS-3410 3 Stage Separator | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001033 | [SITE SURVEY] 5-DS-3610 4 Stage Separator | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001034 | [SITE SURVEY] 5-DS-3120 Test Separator | 0.2% | 2023-03-16 | 2023-03-31 | 2023-04-15 | 2023-03-16 | 2023-03-31 | 2023-04-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001035 | [DOSSIER LIFTING] 5-DS-3110-A 1 Stage Separator A | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001036 | [DOSSIER LIFTING] 5-DS-3110-B 1 Stage Separator B | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001037 | [DOSSIER LIFTING] 5-DS-3210 2 Stage Separator | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001038 | [DOSSIER LIFTING] 5-DS-3410 3 Stage Separator | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001039 | [DOSSIER LIFTING] 5-DS-3610 4 Stage Separator | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001040 | [DOSSIER LIFTING] 5-DS-3120 Test Separator | 0.2% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001041 | [CLEANING PROCEDURES] 5-DS-3110-A 1 Stage Separator A | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001042 | [CLEANING PROCEDURES] 5-DS-3110-B 1 Stage Separator B | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001043 | [CLEANING PROCEDURES] 5-DS-3210 2 Stage Separator | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001044 | [CLEANING PROCEDURES] 5-DS-3410 3 Stage Separator | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001045 | [CLEANING PROCEDURES] 5-DS-3610 4 Stage Separator | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001046 | [CLEANING PROCEDURES] 5-DS-3120 Test Separator | 0.2% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001047 | [DOSSIER FINAL] 5-DS-3110-A 1 Stage Separator A | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001048 | [DOSSIER FINAL] 5-DS-3110-B 1 Stage Separator B | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001049 | [DOSSIER FINAL] 5-DS-3210 2 Stage Separator | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001050 | [DOSSIER FINAL] 5-DS-3410 3 Stage Separator | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001051 | [DOSSIER FINAL] 5-DS-3610 4 Stage Separator | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001052 | [DOSSIER FINAL] 5-DS-3120 Test Separator | 0.2% | 2023-06-01 | 2023-06-16 | 2023-07-01 | 2023-06-01 | 2023-06-16 | 2023-07-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001053 | [SITE SURVEY] 5-CA-5530 Glycol Dehydrator | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001054 | [SITE SURVEY] 5-DS-2140 LP Flare KO Drum | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001055 | [SITE SURVEY] 5-DA-1340 Instrument Air Receveiver | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001056 | [SITE SURVEY] 5-DA-5544 Glycol Surge Drum (TEG) | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001057 | [SITE SURVEY] 5-DS-4110 Oily Water Drum | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001058 | [SITE SURVEY] 5-DS-4130 Degassing Drum | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001059 | [SITE SURVEY] 5-DA-1630 Hot Water Expansion Drum | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001060 | [SITE SURVEY] 5-DA-1540 Cooling Water Expansion Drum | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001061 | [SITE SURVEY] 5-TC-1730 Fire Fighting Foam Tank | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001062 | [SITE SURVEY] 5-DS-5420-A Single Filter | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001063 | [SITE SURVEY] 5-DS-5420-B Single Filter | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001064 | [SITE SURVEY] 5-DA-1350 Cooling Water Expansion Tank | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001065 | [SITE SURVEY] 5-DS-3510 Electrostatic Dehydrator | 0.2% | 2023-01-16 | 2023-01-31 | 2023-02-15 | 2023-01-16 | 2023-01-31 | 2023-02-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001066 | [DOSSIER LIFTING] 5-CA-5530 Glycol Dehydrator | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001067 | [DOSSIER LIFTING] 5-DS-2140 LP Flare KO Drum | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001068 | [DOSSIER LIFTING] 5-DA-1340 Instrument Air Receveiver | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001069 | [DOSSIER LIFTING] 5-DA-5544 Glycol Surge Drum (TEG) | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001070 | [DOSSIER LIFTING] 5-DS-4110 Oily Water Drum | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001071 | [DOSSIER LIFTING] 5-DS-4130 Degassing Drum | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001072 | [DOSSIER LIFTING] 5-DA-1630 Hot Water Expansion Drum | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001073 | [DOSSIER LIFTING] 5-DA-1540 Cooling Water Expansion Drum | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001074 | [DOSSIER LIFTING] 5-TC-1730 Fire Fighting Foam Tank | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001075 | [DOSSIER LIFTING] 5-DS-5420-A Single Filter | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001076 | [DOSSIER LIFTING] 5-DS-5420-B Single Filter | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001077 | [DOSSIER LIFTING] 5-DA-1350 Cooling Water Expansion Tank | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001078 | [DOSSIER LIFTING] 5-DS-3510 Electrostatic Dehydrator | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001079 | [CLEANING PROCEDURES] 5-CA-5530 Glycol Dehydrator | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001080 | [CLEANING PROCEDURES] 5-DS-2140 LP Flare KO Drum | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001081 | [CLEANING PROCEDURES] 5-DA-1340 Instrument Air Receveiver | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001082 | [CLEANING PROCEDURES] 5-DA-5544 Glycol Surge Drum (TEG) | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001083 | [CLEANING PROCEDURES] 5-DS-4110 Oily Water Drum | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001084 | [CLEANING PROCEDURES] 5-DS-4130 Degassing Drum | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001085 | [CLEANING PROCEDURES] 5-DA-1630 Hot Water Expansion Drum | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001086 | [CLEANING PROCEDURES] 5-DA-1540 Cooling Water Expansion Drum | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001087 | [CLEANING PROCEDURES] 5-TC-1730 Fire Fighting Foam Tank | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001088 | [CLEANING PROCEDURES] 5-DS-5420-A Single Filter | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001089 | [CLEANING PROCEDURES] 5-DS-5420-B Single Filter | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001090 | [CLEANING PROCEDURES] 5-DA-1350 Cooling Water Expansion Tank | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001091 | [CLEANING PROCEDURES] 5-DS-3510 Electrostatic Dehydrator | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001092 | [DOSSIER FINAL] 5-CA-5530 Glycol Dehydrator | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001093 | [DOSSIER FINAL] 5-DS-2140 LP Flare KO Drum | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001094 | [DOSSIER FINAL] 5-DA-1340 Instrument Air Receveiver | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001095 | [DOSSIER FINAL] 5-DA-5544 Glycol Surge Drum (TEG) | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001096 | [DOSSIER FINAL] 5-DS-4110 Oily Water Drum | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001097 | [DOSSIER FINAL] 5-DS-4130 Degassing Drum | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001098 | [DOSSIER FINAL] 5-DA-1630 Hot Water Expansion Drum | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001099 | [DOSSIER FINAL] 5-DA-1540 Cooling Water Expansion Drum | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001100 | [DOSSIER FINAL] 5-TC-1730 Fire Fighting Foam Tank | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001101 | [DOSSIER FINAL] 5-DS-5420-A Single Filter | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001102 | [DOSSIER FINAL] 5-DS-5420-B Single Filter | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001103 | [DOSSIER FINAL] 5-DA-1350 Cooling Water Expansion Tank | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001104 | [DOSSIER FINAL] 5-DS-3510 Electrostatic Dehydrator | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001105 | Valve [SITE SURVEY] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001106 | Valve [SITE SURVEY] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001107 | Valve [SITE SURVEY] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001108 | Valve [SITE SURVEY] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001109 | Valve [SITE SURVEY] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001110 | Valve [SITE SURVEY] #6 - 99-0002 - Suction GX9920 C | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001111 | Valve [SITE SURVEY] #7 - 31-0003 - check Valve upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001112 | Valve [SITE SURVEY] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001113 | Valve [SITE SURVEY] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001114 | Valve [SITE SURVEY] #10 - 16-0003 - 5ROV 16107A hot water pump | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001115 | Valve [SITE SURVEY] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001116 | Valve [SITE SURVEY] #12 - 16-0003 - 5ROV16111A hot water pump | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001117 | Valve [SITE SURVEY] #13 - 16-0003 - 5ROV16111B hot water pump | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001118 | Valve [SITE SURVEY] #14 - 16-0003 - 5ROV16107B hot water pump | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001119 | Valve [SITE SURVEY] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001120 | Valve [SITE SURVEY] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001121 | Valve [SITE SURVEY] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001122 | Valve [SITE SURVEY] #18 - 16-0006 - Manual Valve bypass of ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001123 | Valve [SITE SURVEY] #19 - 35-0001 - Check Valve downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001124 | Valve [SITE SURVEY] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001125 | Valve [SITE SURVEY] #21 - 41-0003 - Manual Valve at gas outlet | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001126 | Valve [SITE SURVEY] #22 - 41-0002 - Manual Valve inlet of hydrocyclone A | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001127 | Valve [SITE SURVEY] #23 - 34-0001 - Manual Valve s to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001128 | Valve [SITE SURVEY] #24 - 34-0001 - Description missing | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001129 | Valve [SITE SURVEY] #25 - 34-0001 - Description missing | 0.2% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001130 | Valve [SITE SURVEY] #26 - 34-0001 - Description missing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001131 | Valve [SITE SURVEY] #27 - 34-0001 - Description missing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001132 | Valve [SITE SURVEY] #28 - 34-0001 - Description missing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001133 | Valve [SITE SURVEY] #29 - 30-0002 - Manual Valve on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001134 | Valve [SITE SURVEY] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001135 | Valve [SITE SURVEY] #31 - 99-0002 - ROV on suction of 5GX9920B passing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001136 | Valve [SITE SURVEY] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001137 | Valve [SITE SURVEY] #33 - 33-0002 - Manual Valve on Oil outlet of the crude heater B1/B2 | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001138 | Valve [SITE SURVEY] #34 - 31-0002 - Last manual ball Valve on oily H20 outlet1st stage B passing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001139 | Valve [SITE SURVEY] #35 - 71-0004 - Gearbox difficult to manipulate | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001140 | Valve [SITE SURVEY] #36 - 21-0010 - Manual Valve u/s PSV on HGVB does not close fully. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001141 | Valve [SITE SURVEY] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001142 | Valve [SITE SURVEY] #38 - Unknown - Description missing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001143 | Valve [SITE SURVEY] #39 - 52-0002 - Manul Valve upstream 5PSV2-52410 (MP Compressor) | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001144 | Valve [SITE SURVEY] #40 - 30-0006 - Passing DBB( 1st upstream Valve on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001145 | Valve [SITE SURVEY] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001146 | Valve [SITE SURVEY] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block Valve stuck closed( Valve [SITE SURVEY] seat disengaged from stem). DBB to be replaced. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001147 | Valve [SITE SURVEY] #43 - 75-0003 - WI50 5HV75244. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001148 | Valve [SITE SURVEY] #44 - 75-0003 - WI10 5 HV75234. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001149 | Valve [SITE SURVEY] #45 - 54-0001 - 5LV54106A is passing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001150 | Valve [SITE SURVEY] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001151 | Valve [SITE SURVEY] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001152 | Valve [SITE SURVEY] #48 - 54-0005 - Manual Valve [SITE SURVEY] downstream of 5LV54106B is passing when closed. | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001153 | Valve [SITE SURVEY] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001154 | Valve [SITE SURVEY] #50 - 94-0001 - Passing manual Valve | 0.2% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001155 | Valve [SITE SURVEY] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001156 | Valve [SITE SURVEY] #52 - 83-0004 - 8" manual Valve to transfer manifold on offloading line B indicator stuck in the closed position | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001157 | Valve [SITE SURVEY] #53 - 53-004 - 3'' Manual isolation Valve for 5-LT-53206B passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001158 | Valve [SITE SURVEY] #54 - 73-0002 - 20'' Manual Butterfly Valve passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001159 | Valve [SITE SURVEY] #55 - 71-0001 - 30'' Manual Butterfly Valve passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001160 | Valve [SITE SURVEY] #56 - 41-0002 - 10'' Manual inlet Valve [SITE SURVEY] to Hydrocyclone A | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001161 | Valve [SITE SURVEY] #57 - Unknown - Description missing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001162 | Valve [SITE SURVEY] #58 - 31-0003 - Water outlet SDV from the test separator | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001163 | Valve [SITE SURVEY] #59 - 31-0003 - Manual Valve [SITE SURVEY] upstream 5LDV31206 | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001164 | Valve [SITE SURVEY] #60 - 73-0002 - 20'' Manual Butterfly Valve passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001165 | Valve [SITE SURVEY] #61 - 73-0001 - 5ROV 73350A on fine filter A | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001166 | Valve [SITE SURVEY] #62 - 54-0010 - Manual Valve [SITE SURVEY] upstream 5SDV54501 passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001167 | Valve [SITE SURVEY] #63 - 73-0001 - 5ROV 73357E on fine filter E | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001168 | Valve [SITE SURVEY] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001169 | Valve [SITE SURVEY] #65 - 74-0002 - 3/4'' Manual gate Valve downstream 5SDV-74101B | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001170 | Valve [SITE SURVEY] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001171 | Valve [SITE SURVEY] #67 - 53-0005 - 5-FV-53301B- HP B anti surge Valve | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001172 | Valve [SITE SURVEY] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001173 | Valve [SITE SURVEY] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001174 | Valve [SITE SURVEY] #70 - 54-0012 - 5-FV-54601- GIC anti surge Valve | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001175 | Valve [SITE SURVEY] #71 - 30-0002 - Passing DBB( upstream Valve on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001176 | Valve [SITE SURVEY] #72 - 30-0001 - Passing DBB( upstream Valve on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001177 | Valve [SITE SURVEY] #73 - 75-0003 - All isolation Valvs including 5SDV75232 on water injection string WI-20 passing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001178 | Valve [SITE SURVEY] #74 - Unknown - Description missing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001179 | Valve [SITE SURVEY] #75 - Unknown - Description missing | 0.2% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001180 | Valve [SITE SURVEY] #76 - 30-0003 - Passing DBB( upstream Valve on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001181 | Valve [SITE SURVEY] #77 - 34-0001 - 16'' SRI Valves on WI network( 5GX7520A) passing. | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001182 | Valve [SITE SURVEY] #78 - Unknown - 16'' SRI Valve s on WI network( 5GX7520A) passing. | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001183 | Valve [SITE SURVEY] #79 - Unknown - 16'' SRI Valves on WI network( 5GX7520A) passing. | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001184 | Valve [SITE SURVEY] #80 - 34-0001 - All isolation Valves on water injection string WI-10 passing | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001185 | Valve [SITE SURVEY] #81 - 94-0001 - 3" Manual buterfly Valve on the sea water flushing line to discharge of sewage pump A. | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001186 | Valve [SITE SURVEY] #82 - Unknown - Description missing | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001187 | Valve [SITE SURVEY] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001188 | Valve [SITE SURVEY] #84 - 34-001 - Upstream manual Valve of 5PV1-34111 on 3rd stage Separator | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001189 | Valve [SITE SURVEY] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001190 | Valve [SITE SURVEY] #86 - 31-0003 - manual Valve U/S 5PSV31207 test separator | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001191 | Valve [SITE SURVEY] #87 - 21-0009 - 4'' discharge manual Valve of LP flare drum pump | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001192 | Valve [SITE SURVEY] #88 - 22-0001 - manual Valve U/S 5PSV1 22113 HP FG scrubber | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001193 | Valve [SITE SURVEY] #89 - 31-0001 - manual Valveupstream 5LDV31106A | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001194 | Valve [SITE SURVEY] #90 - 31-0001 - manual Valve downstream 5LDV31106A | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001195 | Valve [SITE SURVEY] #91 - 54-0001 - MANUAL Valve ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001196 | Valve [SITE SURVEY] #92 - 54-0005 - MANUAL Valve ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001197 | Valve [SITE SURVEY] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001198 | Valve [SITE SURVEY] #94 - 15-0001 - MANUAL ValveS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001199 | Valve [SITE SURVEY] #95 - 33-0002 - MANUAL Valve ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001200 | Valve [SITE SURVEY] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001201 | Valve [SITE SURVEY] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001202 | Valve [SITE SURVEY] #98 - 75-0002 - MANUAL Valve ON MINIMUM FLOWLINE OF WIP C | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001203 | Valve [SITE SURVEY] #99 - 54-0007 - MANUAL Valve DOWNSTREAM 5EBDV54318B | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001204 | Valve [SITE SURVEY] #100 - 31-0002 - Description missing | 0.2% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001205 | Valve [SITE SURVEY] #101 - 21-0009 - 2" UPSTREAM MANUAL Valve ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001206 | Valve [SITE SURVEY] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGE ValveS (WATER INJECTION PUMP -B) | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001207 | Valve [SITE SURVEY] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGE ValveS (WATER INJECTION PUMP -B) | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001208 | Valve [SITE SURVEY] #104 - Unknown - Riser ESDV 30510 passing Valve | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001209 | Valve [SITE SURVEY] #105 - Unknown - Riser ESDV 30610 passing Valve | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001210 | Valve [SITE SURVEY] #106 - Unknown - ISO Valve [SITE SURVEY] DWSTRM - 5-PSV-15302A | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001211 | Valve [SITE SURVEY] #107 - Unknown - ISO Valve [SITE SURVEY] DWSTRM - 5-PSV-15304B | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001212 | Valve [SITE SURVEY] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001213 | Valve [SITE SURVEY] #109 - Unknown - CO PRE-HEAT M/ Valve [SITE SURVEY] PASSING - HC SIDE | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001214 | Valve [SITE SURVEY] #110 - Unknown - CO PRE-HEAT M/Valve [SITE SURVEY] PASSING - DRAIN SIDE | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001215 | Valve [SITE SURVEY] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001216 | Valve [SITE SURVEY] #112 - Unknown - HULL VENT BLOWER Valve (8") | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001217 | Valve [SITE SURVEY] #113 - Unknown - HULL VENT BLOWER Valve (6") | 0.2% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001218 | Valve [DOSSIER LIFTING] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001219 | Valve [DOSSIER LIFTING] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001220 | Valve [DOSSIER LIFTING] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001221 | Valve [DOSSIER LIFTING] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001222 | Valve [DOSSIER LIFTING] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001223 | Valve [DOSSIER LIFTING] #6 - 99-0002 - Suction GX9920 C | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001224 | Valve [DOSSIER LIFTING] #7 - 31-0003 - check upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001225 | Valve [DOSSIER LIFTING] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001226 | Valve [DOSSIER LIFTING] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001227 | Valve [DOSSIER LIFTING] #10 - 16-0003 - 5ROV 16107A hot water pump | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001228 | Valve [DOSSIER LIFTING] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001229 | Valve [DOSSIER LIFTING] #12 - 16-0003 - 5ROV16111A hot water pump | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001230 | Valve [DOSSIER LIFTING] #13 - 16-0003 - 5ROV16111B hot water pump | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001231 | Valve [DOSSIER LIFTING] #14 - 16-0003 - 5ROV16107B hot water pump | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001232 | Valve [DOSSIER LIFTING] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001233 | Valve [DOSSIER LIFTING] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001234 | Valve [DOSSIER LIFTING] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001235 | Valve [DOSSIER LIFTING] #18 - 16-0006 - Manual bypass of ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001236 | Valve [DOSSIER LIFTING] #19 - 35-0001 - Check downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001237 | Valve [DOSSIER LIFTING] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001238 | Valve [DOSSIER LIFTING] #21 - 41-0003 - Manual at gas outlet | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001239 | Valve [DOSSIER LIFTING] #22 - 41-0002 - Manual inlet of hydrocyclone A | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001240 | Valve [DOSSIER LIFTING] #23 - 34-0001 - Manuals to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001241 | Valve [DOSSIER LIFTING] #24 - 34-0001 - Description missing | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001242 | Valve [DOSSIER LIFTING] #25 - 34-0001 - Description missing | 0.2% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001243 | Valve [DOSSIER LIFTING] #26 - 34-0001 - Description missing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001244 | Valve [DOSSIER LIFTING] #27 - 34-0001 - Description missing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001245 | Valve [DOSSIER LIFTING] #28 - 34-0001 - Description missing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001246 | Valve [DOSSIER LIFTING] #29 - 30-0002 - Manual on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001247 | Valve [DOSSIER LIFTING] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001248 | Valve [DOSSIER LIFTING] #31 - 99-0002 - ROV on suction of 5GX9920B passing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001249 | Valve [DOSSIER LIFTING] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001250 | Valve [DOSSIER LIFTING] #33 - 33-0002 - Manual on Oil outlet of the crude heater B1/B2 | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001251 | Valve [DOSSIER LIFTING] #34 - 31-0002 - Last manual ball on oily H20 outlet1st stage B passing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001252 | Valve [DOSSIER LIFTING] #35 - 71-0004 - Gearbox difficult to manipulate | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001253 | Valve [DOSSIER LIFTING] #36 - 21-0010 - Manual u/s PSV on HGVB does not close fully. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001254 | Valve [DOSSIER LIFTING] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001255 | Valve [DOSSIER LIFTING] #38 - Unknown - Description missing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001256 | Valve [DOSSIER LIFTING] #39 - 52-0002 - Manul upstream 5PSV2-52410 (MP Compressor) | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001257 | Valve [DOSSIER LIFTING] #40 - 30-0006 - Passing DBB( 1st upstream on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001258 | Valve [DOSSIER LIFTING] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001259 | Valve [DOSSIER LIFTING] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block stuck closed( seat disengaged from stem). DBB to be replaced. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001260 | Valve [DOSSIER LIFTING] #43 - 75-0003 - WI50 5HV75244. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001261 | Valve [DOSSIER LIFTING] #44 - 75-0003 - WI10 5 HV75234. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001262 | Valve [DOSSIER LIFTING] #45 - 54-0001 - 5LV54106A is passing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001263 | Valve [DOSSIER LIFTING] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001264 | Valve [DOSSIER LIFTING] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001265 | Valve [DOSSIER LIFTING] #48 - 54-0005 - Manual downstream of 5LV54106B is passing when closed. | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001266 | Valve [DOSSIER LIFTING] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001267 | Valve [DOSSIER LIFTING] #50 - 94-0001 - Passing manual | 0.2% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001268 | Valve [DOSSIER LIFTING] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001269 | Valve [DOSSIER LIFTING] #52 - 83-0004 - 8" manual to transfer manifold on offloading line B indicator stuck in the closed position | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001270 | Valve [DOSSIER LIFTING] #53 - 53-004 - 3'' Manual isolation for 5-LT-53206B passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001271 | Valve [DOSSIER LIFTING] #54 - 73-0002 - 20'' Manual Butterfly passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001272 | Valve [DOSSIER LIFTING] #55 - 71-0001 - 30'' Manual Butterfly passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001273 | Valve [DOSSIER LIFTING] #56 - 41-0002 - 10'' Manual inlet to Hydrocyclone A | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001274 | Valve [DOSSIER LIFTING] #57 - Unknown - Description missing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001275 | Valve [DOSSIER LIFTING] #58 - 31-0003 - Water outlet SDV from the test separator | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001276 | Valve [DOSSIER LIFTING] #59 - 31-0003 - Manual upstream 5LDV31206 | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001277 | Valve [DOSSIER LIFTING] #60 - 73-0002 - 20'' Manual Butterfly passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001278 | Valve [DOSSIER LIFTING] #61 - 73-0001 - 5ROV 73350A on fine filter A | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001279 | Valve [DOSSIER LIFTING] #62 - 54-0010 - Manual upstream 5SDV54501 passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001280 | Valve [DOSSIER LIFTING] #63 - 73-0001 - 5ROV 73357E on fine filter E | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001281 | Valve [DOSSIER LIFTING] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001282 | Valve [DOSSIER LIFTING] #65 - 74-0002 - 3/4'' Manual gate downstream 5SDV-74101B | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001283 | Valve [DOSSIER LIFTING] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001284 | Valve [DOSSIER LIFTING] #67 - 53-0005 - 5-FV-53301B- HP B anti surge | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001285 | Valve [DOSSIER LIFTING] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001286 | Valve [DOSSIER LIFTING] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001287 | Valve [DOSSIER LIFTING] #70 - 54-0012 - 5-FV-54601- GIC anti surge | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001288 | Valve [DOSSIER LIFTING] #71 - 30-0002 - Passing DBB( upstream on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001289 | Valve [DOSSIER LIFTING] #72 - 30-0001 - Passing DBB( upstream on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001290 | Valve [DOSSIER LIFTING] #73 - 75-0003 - All isolations including 5SDV75232 on water injection string WI-20 passing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001291 | Valve [DOSSIER LIFTING] #74 - Unknown - Description missing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001292 | Valve [DOSSIER LIFTING] #75 - Unknown - Description missing | 0.2% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001293 | Valve [DOSSIER LIFTING] #76 - 30-0003 - Passing DBB( upstream on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001294 | Valve [DOSSIER LIFTING] #77 - 34-0001 - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001295 | Valve [DOSSIER LIFTING] #78 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001296 | Valve [DOSSIER LIFTING] #79 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001297 | Valve [DOSSIER LIFTING] #80 - 34-0001 - All isolations on water injection string WI-10 passing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001298 | Valve [DOSSIER LIFTING] #81 - 94-0001 - 3" Manual buterfly on the sea water flushing line to discharge of sewage pump A. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001299 | Valve [DOSSIER LIFTING] #82 - Unknown - Description missing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001300 | Valve [DOSSIER LIFTING] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001301 | Valve [DOSSIER LIFTING] #84 - 34-001 - Upstream manual of 5PV1-34111 on 3rd stage Separator | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001302 | Valve [DOSSIER LIFTING] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001303 | Valve [DOSSIER LIFTING] #86 - 31-0003 - manual U/S 5PSV31207 test separator | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001304 | Valve [DOSSIER LIFTING] #87 - 21-0009 - 4'' discharge manual of LP flare drum pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001305 | Valve [DOSSIER LIFTING] #88 - 22-0001 - manual U/S 5PSV1 22113 HP FG scrubber | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001306 | Valve [DOSSIER LIFTING] #89 - 31-0001 - manual upstream 5LDV31106A | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001307 | Valve [DOSSIER LIFTING] #90 - 31-0001 - manual downstream 5LDV31106A | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001308 | Valve [DOSSIER LIFTING] #91 - 54-0001 - MANUAL ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001309 | Valve [DOSSIER LIFTING] #92 - 54-0005 - MANUAL ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001310 | Valve [DOSSIER LIFTING] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001311 | Valve [DOSSIER LIFTING] #94 - 15-0001 - MANUALS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001312 | Valve [DOSSIER LIFTING] #95 - 33-0002 - MANUAL ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001313 | Valve [DOSSIER LIFTING] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001314 | Valve [DOSSIER LIFTING] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001315 | Valve [DOSSIER LIFTING] #98 - 75-0002 - MANUAL ON MINIMUM FLOWLINE OF WIP C | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001316 | Valve [DOSSIER LIFTING] #99 - 54-0007 - MANUAL DOWNSTREAM 5EBDV54318B | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001317 | Valve [DOSSIER LIFTING] #100 - 31-0002 - Description missing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001318 | Valve [DOSSIER LIFTING] #101 - 21-0009 - 2" UPSTREAM MANUAL ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001319 | Valve [DOSSIER LIFTING] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001320 | Valve [DOSSIER LIFTING] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001321 | Valve [DOSSIER LIFTING] #104 - Unknown - Riser ESDV 30510 passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001322 | Valve [DOSSIER LIFTING] #105 - Unknown - Riser ESDV 30610 passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001323 | Valve [DOSSIER LIFTING] #106 - Unknown - ISO DWSTRM - 5-PSV-15302A | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001324 | Valve [DOSSIER LIFTING] #107 - Unknown - ISO DWSTRM - 5-PSV-15304B | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001325 | Valve [DOSSIER LIFTING] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001326 | Valve [DOSSIER LIFTING] #109 - Unknown - CO PRE-HEAT M/ PASSING - HC SIDE | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001327 | Valve [DOSSIER LIFTING] #110 - Unknown - CO PRE-HEAT M/Valve [DOSSIER LIFTING] PASSING - DRAIN SIDE | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001328 | Valve [DOSSIER LIFTING] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001329 | Valve [DOSSIER LIFTING] #112 - Unknown - HULL VENT BLOWER (8") | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001330 | Valve [DOSSIER LIFTING] #113 - Unknown - HULL VENT BLOWER (6") | 0.2% | 2023-04-16 | 2023-05-01 | 2023-05-16 | 2023-04-16 | 2023-05-01 | 2023-05-16 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001331 | Valve [DOSSIER FINAL] #1 - 19-0001 - Manual Valve upstream PSV1 19110 A (MeOH drum) | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001332 | Valve [DOSSIER FINAL] #2 - 36-0001 - 4th stage separator gas outlet to LP compressor | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001333 | Valve [DOSSIER FINAL] #3 - 55-0003 - Manual Valve downstream 5 PV2 55319 (glycol contactor to flare) | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001334 | Valve [DOSSIER FINAL] #4 - 72-0001 - Discharge GX 7221 to sea water lift pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001335 | Valve [DOSSIER FINAL] #5 - 75-0002 - 1.5" drain manual Valve on pump 5 GX 7520 C | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001336 | Valve [DOSSIER FINAL] #6 - 99-0002 - Suction GX9920 C | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001337 | Valve [DOSSIER FINAL] #7 - 31-0003 - check upstream 5PSE31214 on gas outlet line of test sep to gas dehydration cooler before 5ROV 31201 | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001338 | Valve [DOSSIER FINAL] #8 - 31-0003 - 1st check Valve upstream of 5 ROV 31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001339 | Valve [DOSSIER FINAL] #9 - 30-0007 - 5ROV 30717 inlet of 5DG 3070 | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001340 | Valve [DOSSIER FINAL] #10 - 16-0003 - 5ROV 16107A hot water pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001341 | Valve [DOSSIER FINAL] #11 - 31-0003 - 2nd check Valve upstream of 5 ROV4-31201 to HP comp.suction cooler train A/B. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001342 | Valve [DOSSIER FINAL] #12 - 16-0003 - 5ROV16111A hot water pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001343 | Valve [DOSSIER FINAL] #13 - 16-0003 - 5ROV16111B hot water pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001344 | Valve [DOSSIER FINAL] #14 - 16-0003 - 5ROV16107B hot water pump | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001345 | Valve [DOSSIER FINAL] #15 - 30-0003 - P20R / manual Valve upstream 5 SDV 30425 | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001346 | Valve [DOSSIER FINAL] #16 - 54-0010 - 5 SDV 54510 drain of Gas injection inlet scrubber to 1st stage separators | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001347 | Valve [DOSSIER FINAL] #17 - 16-0006 - ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001348 | Valve [DOSSIER FINAL] #18 - 16-0006 - Manual bypass of ROV 16201C on Hot water inlet to WHRU C | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001349 | Valve [DOSSIER FINAL] #19 - 35-0001 - Check downstream 5SDV35110 on DS3510 (Electro-static dehydrator) is passing. | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001350 | Valve [DOSSIER FINAL] #20 - 30-0003 - 5 ROV 30317 upstream P20L pig trap | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001351 | Valve [DOSSIER FINAL] #21 - 41-0003 - Manual at gas outlet | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001352 | Valve [DOSSIER FINAL] #22 - 41-0002 - Manual inlet of hydrocyclone A | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001353 | Valve [DOSSIER FINAL] #23 - 34-0001 - Manuals to Closed Drain Header from 3rd Stage separator to Closed Drain are passing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001354 | Valve [DOSSIER FINAL] #24 - 34-0001 - Description missing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001355 | Valve [DOSSIER FINAL] #25 - 34-0001 - Description missing | 0.2% | 2023-04-01 | 2023-04-16 | 2023-05-01 | 2023-04-01 | 2023-04-16 | 2023-05-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001356 | Valve [DOSSIER FINAL] #26 - 34-0001 - Description missing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001357 | Valve [DOSSIER FINAL] #27 - 34-0001 - Description missing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001358 | Valve [DOSSIER FINAL] #28 - 34-0001 - Description missing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001359 | Valve [DOSSIER FINAL] #29 - 30-0002 - Manual on Inlet of P10 R PIG Trap ( upstream of 5 ROV30217) is passing. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001360 | Valve [DOSSIER FINAL] #30 - 30-0002 - 5 ROV 30217 upstream P10 R PIG Trap is passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001361 | Valve [DOSSIER FINAL] #31 - 99-0002 - ROV on suction of 5GX9920B passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001362 | Valve [DOSSIER FINAL] #32 - 34-0001 - First 6" check v/v on wash water line to 3rd stage pump | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001363 | Valve [DOSSIER FINAL] #33 - 33-0002 - Manual on Oil outlet of the crude heater B1/B2 | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001364 | Valve [DOSSIER FINAL] #34 - 31-0002 - Last manual ball on oily H20 outlet1st stage B passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001365 | Valve [DOSSIER FINAL] #35 - 71-0004 - Gearbox difficult to manipulate | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001366 | Valve [DOSSIER FINAL] #36 - 21-0010 - Manual u/s PSV on HGVB does not close fully. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001367 | Valve [DOSSIER FINAL] #37 - 75-0003 - All four HCVs on watr injection flowline wirh eroded internals, no flow control | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001368 | Valve [DOSSIER FINAL] #38 - Unknown - Description missing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001369 | Valve [DOSSIER FINAL] #39 - 52-0002 - Manul upstream 5PSV2-52410 (MP Compressor) | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001370 | Valve [DOSSIER FINAL] #40 - 30-0006 - Passing DBB( 1st upstream on the DBB) of 5 PT 30607 on P30R. DBB to be replaced. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001371 | Valve [DOSSIER FINAL] #41 - 31-0001 - SDV31117A-Oil outlet 1st stage separator A.-PASSING | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001372 | Valve [DOSSIER FINAL] #42 - 30-0006 - DBB of 5PT1-30602 is bad. First block stuck closed( seat disengaged from stem). DBB to be replaced. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001373 | Valve [DOSSIER FINAL] #43 - 75-0003 - WI50 5HV75244. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001374 | Valve [DOSSIER FINAL] #44 - 75-0003 - WI10 5 HV75234. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001375 | Valve [DOSSIER FINAL] #45 - 54-0001 - 5LV54106A is passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001376 | Valve [DOSSIER FINAL] #46 - 54-0001 - 5SDV54110A - Outlet SDV on the GEC A scrubber outlet to 2nd stage separator is stuck | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001377 | Valve [DOSSIER FINAL] #47 - 84-0008 - 4ROV84010 - Liquid handling pumps to loading manifold is passing | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001378 | Valve [DOSSIER FINAL] #48 - 54-0005 - Manual downstream of 5LV54106B is passing when closed. | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001379 | Valve [DOSSIER FINAL] #49 - 54-0010 - 5SDV54508 Passing on GIC scrubber inlet by pass SDV,unable to depressurise GIC below 4.2bar | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001380 | Valve [DOSSIER FINAL] #50 - 94-0001 - Passing manual | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001381 | Valve [DOSSIER FINAL] #51 - 4-71-0002 - ROV on 24" Seawater supply line to Hull Machinery space | 0.2% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001382 | Valve [DOSSIER FINAL] #52 - 83-0004 - 8" manual to transfer manifold on offloading line B indicator stuck in the closed position | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001383 | Valve [DOSSIER FINAL] #53 - 53-004 - 3'' Manual isolation for 5-LT-53206B passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001384 | Valve [DOSSIER FINAL] #54 - 73-0002 - 20'' Manual Butterfly passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001385 | Valve [DOSSIER FINAL] #55 - 71-0001 - 30'' Manual Butterfly passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001386 | Valve [DOSSIER FINAL] #56 - 41-0002 - 10'' Manual inlet to Hydrocyclone A | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001387 | Valve [DOSSIER FINAL] #57 - Unknown - Description missing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001388 | Valve [DOSSIER FINAL] #58 - 31-0003 - Water outlet SDV from the test separator | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001389 | Valve [DOSSIER FINAL] #59 - 31-0003 - Manual upstream 5LDV31206 | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001390 | Valve [DOSSIER FINAL] #60 - 73-0002 - 20'' Manual Butterfly passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001391 | Valve [DOSSIER FINAL] #61 - 73-0001 - 5ROV 73350A on fine filter A | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001392 | Valve [DOSSIER FINAL] #62 - 54-0010 - Manual upstream 5SDV54501 passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001393 | Valve [DOSSIER FINAL] #63 - 73-0001 - 5ROV 73357E on fine filter E | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001394 | Valve [DOSSIER FINAL] #64 - 15-0003 - 5TV15311 is passing, causing a temperature rise in the cooling water network | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001395 | Valve [DOSSIER FINAL] #65 - 74-0002 - 3/4'' Manual gate downstream 5SDV-74101B | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001396 | Valve [DOSSIER FINAL] #66 - 71-0001 - 5-PV2-71509 on seawter sysytem | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001397 | Valve [DOSSIER FINAL] #67 - 53-0005 - 5-FV-53301B- HP B anti surge | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001398 | Valve [DOSSIER FINAL] #68 - 54-0003 - 5-SDV-54314A on GEC A cooler outlet | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001399 | Valve [DOSSIER FINAL] #69 - 32-0001 - 5-PV2-32111 on 3rd stage seperator gas outlet | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001400 | Valve [DOSSIER FINAL] #70 - 54-0012 - 5-FV-54601- GIC anti surge | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001401 | Valve [DOSSIER FINAL] #71 - 30-0002 - Passing DBB( upstream on the DBB) of 5 PT3 30201 on P10R. DBB to be replaced. | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001402 | Valve [DOSSIER FINAL] #72 - 30-0001 - Passing DBB( upstream on the DBB) of 5 PT1 30101 on P10L. DBB to be replaced. | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001403 | Valve [DOSSIER FINAL] #73 - 75-0003 - All isolations including 5SDV75232 on water injection string WI-20 passing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001404 | Valve [DOSSIER FINAL] #74 - Unknown - Description missing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001405 | Valve [DOSSIER FINAL] #75 - Unknown - Description missing | 0.2% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001406 | Valve [DOSSIER FINAL] #76 - 30-0003 - Passing DBB( upstream on the DBB) of 5 PT2 30301 on P20L. DBB to be replaced. | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001407 | Valve [DOSSIER FINAL] #77 - 34-0001 - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001408 | Valve [DOSSIER FINAL] #78 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001409 | Valve [DOSSIER FINAL] #79 - Unknown - 16'' SRIs on WI network( 5GX7520A) passing. | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001410 | Valve [DOSSIER FINAL] #80 - 34-0001 - All isolations on water injection string WI-10 passing | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001411 | Valve [DOSSIER FINAL] #81 - 94-0001 - 3" Manual buterfly on the sea water flushing line to discharge of sewage pump A. | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001412 | Valve [DOSSIER FINAL] #82 - Unknown - Description missing | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001413 | Valve [DOSSIER FINAL] #83 - 34-001 - 16" PV on 3rd Stage Separator gas outlet to flare | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001414 | Valve [DOSSIER FINAL] #84 - 34-001 - Upstream manual of 5PV1-34111 on 3rd stage Separator | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001415 | Valve [DOSSIER FINAL] #85 - 31-001 - LDV on water outlet of 1st stage Separator A (5LDV31106A) | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001416 | Valve [DOSSIER FINAL] #86 - 31-0003 - manual U/S 5PSV31207 test separator | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001417 | Valve [DOSSIER FINAL] #87 - 21-0009 - 4'' discharge manual of LP flare drum pump | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001418 | Valve [DOSSIER FINAL] #88 - 22-0001 - manual U/S 5PSV1 22113 HP FG scrubber | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001419 | Valve [DOSSIER FINAL] #89 - 31-0001 - manual upstream 5LDV31106A | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001420 | Valve [DOSSIER FINAL] #90 - 31-0001 - manual downstream 5LDV31106A | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001421 | Valve [DOSSIER FINAL] #91 - 54-0001 - MANUAL ON LINE FROM GEC A TO 2ND STAGE SEPARATOR | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001422 | Valve [DOSSIER FINAL] #92 - 54-0005 - MANUAL ON LINE FROM GEC B TO 2ND STAGE SEPARATOR | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001423 | Valve [DOSSIER FINAL] #93 - 51-0002 - 5PV1-36111 ON LP COMPRESSOR DISCHARGE | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001424 | Valve [DOSSIER FINAL] #94 - 15-0001 - MANUALS ON SEA WATER INLET AND OUTLET LINES OF SEA WATER/ COOLING WATER EXCHANGER B | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001425 | Valve [DOSSIER FINAL] #95 - 33-0002 - MANUAL ON OUTLET LINE OF CRUDE OIL HEATER A1/A2 | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001426 | Valve [DOSSIER FINAL] #96 - 99-0002 - SUCTION 5ROV99203A OF DEAD OIL CIRCULATION PUMP A | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001427 | Valve [DOSSIER FINAL] #97 - 99-0002 - SUCTION 5ROV99203D OF DEAD OIL CIRCULATION PUMP D | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001428 | Valve [DOSSIER FINAL] #98 - 75-0002 - MANUAL ON MINIMUM FLOWLINE OF WIP C | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001429 | Valve [DOSSIER FINAL] #99 - 54-0007 - MANUAL DOWNSTREAM 5EBDV54318B | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001430 | Valve [DOSSIER FINAL] #100 - 31-0002 - Description missing | 0.2% | 2023-04-30 | 2023-05-15 | 2023-05-30 | 2023-04-30 | 2023-05-15 | 2023-05-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001431 | Valve [DOSSIER FINAL] #101 - 21-0009 - 2" UPSTREAM MANUAL ON GIC SCRUBBER LINE TO 1ST STAGE SEPARATOR B PASSING | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001432 | Valve [DOSSIER FINAL] #102 - 75-0002 - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001433 | Valve [DOSSIER FINAL] #103 - Unknown - 5GX-7520B SUCTION AND DISCHARGES (WATER INJECTION PUMP -B) | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001434 | Valve [DOSSIER FINAL] #104 - Unknown - Riser ESDV 30510 passing | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001435 | Valve [DOSSIER FINAL] #105 - Unknown - Riser ESDV 30610 passing | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001436 | Valve [DOSSIER FINAL] #106 - Unknown - ISO DWSTRM - 5-PSV-15302A | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001437 | Valve [DOSSIER FINAL] #107 - Unknown - ISO DWSTRM - 5-PSV-15304B | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001438 | Valve [DOSSIER FINAL] #108 - Unknown - GAS LEAK ON MV UPSTRM 5-PSV1-54610 | 0.2% | 2023-05-07 | 2023-05-22 | 2023-06-06 | 2023-05-07 | 2023-05-22 | 2023-06-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001439 | Valve [DOSSIER FINAL] #109 - Unknown - CO PRE-HEAT M/ PASSING - HC SIDE | 0.2% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001440 | Valve [DOSSIER FINAL] #110 - Unknown - CO PRE-HEAT M/Valve [DOSSIER FINAL] PASSING - DRAIN SIDE | 0.2% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001441 | Valve [DOSSIER FINAL] #111 - Unknown - ESDV 22311 (SYNERGI CASE) | 0.2% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001442 | Valve [DOSSIER FINAL] #112 - Unknown - HULL VENT BLOWER (8") | 0.2% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001443 | Valve [DOSSIER FINAL] #113 - Unknown - HULL VENT BLOWER (6") | 0.2% | 2023-05-16 | 2023-05-31 | 2023-06-15 | 2023-05-16 | 2023-05-31 | 2023-06-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001444 | [SITE SURVEY] SCAFFOLD P1 | 0.1% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001445 | [SITE SURVEY] SCAFFOLD P2 | 0.1% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001446 | [SITE SURVEY] SCAFFOLD P3 | 0.1% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001447 | [SITE SURVEY] SCAFFOLD P4 | 0.1% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001448 | [SITE SURVEY] SCAFFOLD P5 | 0.1% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001449 | [SITE SURVEY] SCAFFOLD P6 | 0.1% | 2023-02-28 | 2023-03-15 | 2023-03-30 | 2023-02-28 | 2023-03-15 | 2023-03-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001450 | [SITE SURVEY] SCAFFOLD P7 | 0.1% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001451 | [SITE SURVEY] SCAFFOLD P8 | 0.1% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001452 | [DOSSIER FINAL] SCAFFOLD P1 | 0.1% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001453 | [DOSSIER FINAL] SCAFFOLD P2 | 0.1% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001454 | [DOSSIER FINAL] SCAFFOLD P3 | 0.1% | 2023-03-30 | 2023-04-14 | 2023-04-29 | 2023-03-30 | 2023-04-14 | 2023-04-29 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001455 | [DOSSIER FINAL] SCAFFOLD P4 | 0.1% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001456 | [DOSSIER FINAL] SCAFFOLD P5 | 0.1% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001457 | [DOSSIER FINAL] SCAFFOLD P6 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001458 | [DOSSIER FINAL] SCAFFOLD P7 | 0.1% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001459 | [DOSSIER FINAL] SCAFFOLD P8 | 0.1% | 2023-05-15 | 2023-05-30 | 2023-06-14 | 2023-05-15 | 2023-05-30 | 2023-06-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001460 | [SITE SURVEY] SCAFFOLD S1 | 0.1% | 2023-01-07 | 2023-01-22 | 2023-02-06 | 2023-01-07 | 2023-01-22 | 2023-02-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001461 | [SITE SURVEY] SCAFFOLD S2 | 0.1% | 2023-01-15 | 2023-01-30 | 2023-02-14 | 2023-01-15 | 2023-01-30 | 2023-02-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001462 | [SITE SURVEY] SCAFFOLD S3 | 0.1% | 2023-01-30 | 2023-02-14 | 2023-03-01 | 2023-01-30 | 2023-02-14 | 2023-03-01 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001463 | [SITE SURVEY] SCAFFOLD S4 | 0.1% | 2023-02-07 | 2023-02-22 | 2023-03-09 | 2023-02-07 | 2023-02-22 | 2023-03-09 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001464 | [SITE SURVEY] SCAFFOLD S5 | 0.1% | 2023-02-15 | 2023-03-02 | 2023-03-17 | 2023-02-15 | 2023-03-02 | 2023-03-17 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001465 | [SITE SURVEY] SCAFFOLD S6 | 0.1% | 2023-02-28 | 2023-03-15 | 2023-03-30 | 2023-02-28 | 2023-03-15 | 2023-03-30 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001466 | [SITE SURVEY] SCAFFOLD S7 | 0.1% | 2023-03-07 | 2023-03-22 | 2023-04-06 | 2023-03-07 | 2023-03-22 | 2023-04-06 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001467 | [DOSSIER FINAL] SCAFFOLD S1 | 0.1% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001468 | [DOSSIER FINAL] SCAFFOLD S2 | 0.1% | 2023-03-01 | 2023-03-16 | 2023-03-31 | 2023-03-01 | 2023-03-16 | 2023-03-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001469 | [DOSSIER FINAL] SCAFFOLD S3 | 0.1% | 2023-03-15 | 2023-03-30 | 2023-04-14 | 2023-03-15 | 2023-03-30 | 2023-04-14 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001470 | [DOSSIER FINAL] SCAFFOLD S4 | 0.1% | 2023-03-30 | 2023-04-14 | 2023-04-29 | 2023-03-30 | 2023-04-14 | 2023-04-29 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001471 | [DOSSIER FINAL] SCAFFOLD S5 | 0.1% | 2023-04-07 | 2023-04-22 | 2023-05-07 | 2023-04-07 | 2023-04-22 | 2023-05-07 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001472 | [DOSSIER FINAL] SCAFFOLD S6 | 0.1% | 2023-04-15 | 2023-04-30 | 2023-05-15 | 2023-04-15 | 2023-04-30 | 2023-05-15 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NG-AKP-00-SPIE-001473 | [DOSSIER FINAL] SCAFFOLD S7 | 0.1% | 2023-05-01 | 2023-05-16 | 2023-05-31 | 2023-05-01 | 2023-05-16 | 2023-05-31 | [36 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 40% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Abbreviations
Class 1 | Company Acceptance Mandatory | This document requires Company Acceptance in order to be issued with an incremented step. Lead time for Company review and Company acceptance shall be specified in contract.
Class 2 | Company Review Requested | Company Acceptance is not mandatory but review is requested. Lead time for Company review shall be specified in contract.
Class 3 | Acceptance or Review NOT Requested | Document sent for Company information.
IFR | Issued for review | Applies to class 1 and class 2 documents
IFA | Issued for acceptance | Applies to class 1 documents
IFD | Accepted for design
IFC | Accepted for construction
IAB | As built
IFI | Issued for information | Applies to class 3 documents

## Doc sequence number
Structure of 6 digits number:
Discipline numbering code |  |  | Serial number
1st three digits |  |  | 2nd three digits
X | X | X | Z | Z | Z
000 | PJM | Project management | 0 | General documents (procedures, specifications, calculation notes, register, weekly report…)
010 | PRO | Process | 1 | General arrangement drawings, ESD, Layouts, PFD, Plot plan…
020 | ARC | Architectural | 2 | PID, detail drawing, isometrics, support booklet…
025 | SPS | Subsea layout | 3 | List (equipment instruments, lines, tie-in…)
030 | CST | Construction, lift and installation | 4 | Datasheets
040 | CIV | Civil works | 5 | Particular documents as needed
045 | HVA | Building and HVAC | 6 | Management of change (TQ only)
050 | PVV | Piping, valves and vessels | 7 | Management of change (other types: COR, DCR, DGS, VAR)
060 | ELE | Electrical
070 | INS | Instrumentation
075 | TEL | Telecommunication
080 | GEO | Topography
090 | STR | Structural
100 | MEC | Mechanical
110 | PLR | Pipelines, sealines and risers
120 | DRI | Drilling and production, wells
130 | LCS | Loss contol and safety

## Discipline code
ARC | Architectural
CIV | Civil Engineering
CMG | Commissioning
COM | Communication
COR | Corrosion
ELE | Electrical
ENG | Engineering Management
FGS | Fire and Gas
GEO | Geotechnic - Geophysic - Oceano Meteo
HRS | Human Resources
HSE | Health - Safety - Environment
HVA | Heating - Ventilation - Air Conditioning
INS | Instrumentation
INT | Integrity
ISP | Inspection
IWO | Installation Work
LEG | Legal - Compliance
LCS | Loss Control and Safety
LOG | Logistics
MEC | Mechanical (Machinery)
MIE | Maintenance Inspection Engineering
MNT | Maintenance (Operation)
MTI | Management of Technical Information (management of data)
NAV | Naval Architecture and Mooring
OPE | Field Operations
PCM | Project Control Management
PJM | Project Management
PLR | Pipelines - Risers - Umbilicals
PRO | Process
PVV | Piping - Valve - Vessel
QUA | QA - QC - Certification
RES | Reservoir
SEC | Security
SPS | Sub sea Production System
STR | Structure
TEL | Telecommunication
WEL | Well Performance engineering
XTR | Extraction (mining)

## Document type code
ACC | Accounting (Cost control / Finance) Document
ANL | Analysis
BLD | Block Diagram
BOD | Basis of Design
BOQ | Bill of Quantities
CAL | Calculation Note
CFT | Call for Tender
CHA | Charter
CHT | Chart - Histogram
CNT | Contract
CRT | Certificate
CRV | Curves
DCF | Data Collection File
DCS | Distributed Control System (Instrumentation)
DCT | Data Collection Template
DER | Derogation Request
DGA | Other Digital Asset
DRW | Drawings (other type)
DSS | Dossier (mix of different types of docs)
DTL | Details
DTS | Data Sheet
ESD | Logic Diagram
EST | Estimation - Assessment
FOR | Form
GEA | General Arrangement
GUA | Guarantee
INR | Inspection Report
ISO | Isometric
LAY | Layout
LEG | Legal - Compliance Document
LIC | Licence - Authorisation
LIS | List - Index - Schedule - Listing
LPD | Loop Diagram
MAN | Manual
MAP | Map
MNR | Maintenance Report
MOD | Model
MTO | Material Take Off
NCR | Non Conformance Reports
NFI | Notification for Inspection
PFD | Process Flow Diagram
PHI | Philosophy
PHO | Photograph
PID | Process and Instruments Diagram
PLN | Plan - Program
PLT | Plot Plan
PRC | Procedure
PRM | Permit
PRP | Proposal
PSP | Presentation
PUR | Purchase Order
RCM | Recommendation
REC | Record
REG | Register
REP | Report
REQ | Request - Requisition
SCH | Schedule
SCN | Scope Change Notice
SOR | Statement of Requirements
SDB | SUPPLIER Data Book
SLD | Single Line Diagram
SMR | Study and Modification Request
SOW | Scope of Work
SPE | Specification
SRV | Survey
STD | Standard
STU | Study
TMC | Terms and Conditions
TQR | Technical Query
TSD | Trouble Shooting Diagram
TST | Acceptance and Performance Test
TYP | Typical
UFD | Utility Flow Diagram
VDB | Vendor data book
VID | Video
WIR | Wiring Diagram

## Phase code
PS | Pre-Study
FE | FEED engineering
PP | Pre-Project
BE | Basic Engineering
DE | Detailed Engineering
CS | Construction
PC | Pre-Commissioning
TI | Transport Installation and Survey
HU | Hook-up
CO | Commissioning
SU | Start Up