## Checklist
PRODUCT & PROCESS CONFORMITY ASSESSMENT - Checklist
Part Name (Designation): | PiècePlastique
Project (Nbr): | 123456ABC
Customer: | Le Client
Cavity: | 4 |  |  | s
Colonne1 | Colonne2 | Colonne3 | Colonne4 | Runs → | FOT | SOT | TOT | 4OT | 5OT | 6OT
|  |  |  | Trying Plant → | Chine | France | France | France | Pologne | Pologne
To be completed by trying plant only |  | SC CC |  | Date Criticity | 2021-02-23 | 2021-05-24 11:24 | 2021-09-24 11:24 | 2021-11-24 11:24 | 2022-01-24 11:27 | 2022-02-24 11:27
Raw Material
Raw Material | The raw material used is according the customer specifications ? | s | 6 | High | NOK | OK | OK | OK | OK | OK
Raw Material certificate | The raw material certificate is available and all properties are inside tolerances ranges (ash content, melt rate..) ? | s | 6 | High | NOK | NOK | NOK | NOK | NOK | OK
Colorant / ink certificate | The colorant/ink certificate is available and includes the good reference and properties ? All specifications are ok ? |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Raw Material |  |  |  | Result: | 0% | 60% | 60% | 60% | 60% | 100%
Components
Component status | All components pass the incoming inspection ? in case of multiple components, please put the worse assessment |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Sub supplier PSW | All components have been validated internally and by the customer ? in case of multiple components, please put the worse assessment |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Components |  |  |  | Result: | 0% | 50% | 100% | 100% | 100% | 100%
Process status (injection)
Press force (T) |  |  | 1 | 200 | 300 | 250 | 220 | 200 | 200 | 180
Weight 1 shot + sprue portion (g) | GRAPHINJ |  | 1 | 20 | 25 | 22 | 22 | 21 | 20 | 17
% Colorant |  |  | 1 | 5% | 10% | 7% | 7% | 6% | 5% | 4%
Operators quantity |  |  | 1 | 1 | 2 | 1.5 | 1.5 | 1.5 | 1 | 0.5
Run Duration (in mim and including stops and breaks) |  |  |  |  | 60 | 60 | 60 | 60 | 60 | 60
Stoppage time (min) |  |  |  |  | 15 | 7 | 5 | 4 | 3 | 1
Overall Equipment Effectiveness | GRAPHINJ |  | 1 | 90% | 75% | 88.33% | 91.67% | 93.33% | 95% | 98.33%
Production time (min) |  |  |  |  | 45 | 53 | 55 | 56 | 57 | 59
Production Qty |  |  |  |  | 500 | 600 | 700 | 800 | 900 | 1000
Cycle time (sec) | GRAPHINJ |  | 1 | 34 | 21.6 | 21.2 | 18.8571 | 16.8 | 15.2 | 14.16
Manufacturing line rate (Part/hour) |  |  | 1 | 423.5294 | 666.6667 | 679.2453 | 763.6364 | 857.1429 | 947.3684 | 1016.9492
Qty of NOK parts |  |  |  |  | 50 | 40 | 30 | 20 | 18 | 10
Scrap rate (%) | GRAPHINJ |  | 1 | 2% | 10% | 6.667% | 4.286% | 2.5% | 2% | 1%
Deliverable parts qty. |  |  |  |  | 450 | 560 | 670 | 780 | 882 | 990
Process status (injection) |  |  |  | Result: | 25% | 25% | 37.5% | 50% | 100% | 100%
Process status (assembly, welding, printing, hot stamping, ..)
Sensors and Poka-Yoke | Sensors and poka-yoke are in place and works well ? |  | 1 | OK/NOK | NOK | NOK | NOK | OK | OK | OK
Operators quantity |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
Run Duration (in mim and including stops and breaks) |  |  |  |  | 90 | 90 | 90 | 90 | 90 | 90
Stoppage time (min) |  |  |  |  | 30 | 20 | 15 | 10 | 8 | 2
Overall Equipment Effectiveness | GRAPHASSY |  | 1 | 95% | 66.67% | 77.78% | 83.33% | 88.89% | 91.11% | 97.78%
Production time (min) |  |  |  |  | 60 | 70 | 75 | 80 | 82 | 88
Production Qty |  |  |  |  | 100 | 130 | 200 | 250 | 320 | 480
Cycle time (sec) | GRAPHASSY |  | 1 | 45 | 36 | 32.3077 | 22.5 | 19.2 | 15.375 | 11
Manufacturing line rate (Part/hour) |  |  | 1 | 160 | 200 | 222.8571 | 320 | 375 | 468.2927 | 654.5455
Qty of NOK parts |  |  |  |  | 50 | 40 | 30 | 20 | 15 | 10
Scrap rate (%) | GRAPHASSY |  | 1 | 5% | 50% | 30.77% | 15% | 8% | 4.688% | 2.083%
Deliverable parts qty. |  |  |  |  | 50 | 90 | 170 | 230 | 305 | 470
Process status (assembly, welding, printing, hot stamping, ..) |  |  |  | Result: | 50% | 50% | 50% | 66.67% | 83.33% | 100%
To be completed by quality service only
Dimensional |  |  |  | Percentage of OK characteristics ALL CAVITIES COMBINED
CC | Percentage of critical characteristics that are conform (All cavities combined) | s | 6 | High | 50% | 60% | 70% | 80% | 90% | 100%
SC | Percentage of significant characteristics that are conform (All cavities combined) | s | 6 | High | 50% | 60% | 70% | 80% | 90% | 100%
| Percentage of normal characteristics that are conform (All cavities combined) |  | 3 | Medium | 50% | 60% | 70% | 80% | 90% | 100%
Cpk | Percentage of capability studies that are conform (All cavities combined) | s | 6 | High | 50% | 60% | 70% | 80% | 90% | 100%
Wheight (g) | 254g ±5% |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Dimensional |  |  |  | Result: | 43.75% | 65% | 73.75% | 82.5% | 91.25% | 100%
Fit & Function
Fit assessment | Assembly trials are OK internally and at the customer ? | s | 6 | High | NOK | NOK | OK | OK | OK | OK
Functionnal assessment | Functionnal trials are OK internally and at the customer ? | s | 6 | High | NOK | OK | NOK | OK | OK | OK
Gap and flush assessment | Gap & Flush assessment after assembly is validated by the customer ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Fit & Function |  |  |  | Result: | 0% | 40% | 60% | 100% | 100% | 100%
Aspect
Marking | Presence and good readability of logo, part number, raw material identification… |  | 3 | Medium | NOK | OK | NOK | OK | OK | OK
Burrs / Flash | Part aspect is free from burrs and flash. |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Spots/ sink marks / welding lines | Part aspect is free from white spots, sink marks, welding lines. |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Gloss measurement | Gloss level is according the specifications ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Color measurement | Colorimetery is according the specifications ? |  | 3 | Medium | NOK | OK | NOK | NOK | OK | OK
Aspect |  |  |  | Result: | 0% | 60% | 60% | 80% | 100% | 100%
Tracability
Date clock up to date | Presence and good readability of date clock and up to date ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Maturity level up to date | Maturity level is visible and up to date ? |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Cavity number conformity | Cavity number is visible and up to date ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Batch identification (QR …) | Batch identification is visible and up to date ? |  | 3 | Medium | NOK | OK | NOK | NOK | NOK | OK
Tracability |  |  |  | Result: | 0% | 50% | 75% | 75% | 75% | 100%
DVP (Validation plan and testing)
Raw material testing | All tests of the DVP list are OK or derogated by the customer ? |  | 3 | Medium | NOK | OK | OK | OK | OK | OK
Product performance testing | All performance tests are OK or derogated by the customer ? |  | 3 | Medium | NOK | NOK | NOK | OK | OK | OK
DVP (Validation plan and testing) |  |  |  | Result: | 0% | 50% | 50% | 100% | 100% | 100%
Checking Aids
Checking Aids reception | All checking aids are received ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Checking aids validation | All checking aids are R&R and registred into ISIS ? |  | 3 | Medium | NOK | OK | NOK | OK | OK | OK
Checking aids in serial plant | All checking aids are transfered to serial plant ? |  | 3 | Medium | NOK | NOK | OK | OK | OK | OK
Checking Aids |  |  |  | Result: | 0% | 33.33% | 66.67% | 100% | 100% | 100%
PPAP status
Current status of the parts | Full acceptance of PPAP from the customer |  | 6 | High | NOK | NOK | NOK | NOK | NOK | OK
PPAP status |  |  |  | Result: | 0% | 0% | 0% | 0% | 0% | 100%
CONFIDENTIEL
+

## Settings
A - General Informations
Project Number: | 123456 | Comments:
Project Name: | ProjetTest
Customer: | Gabin
Part Name: | Une Jolie Pièce
Part Designation: | COVER BIDULE
Part Weight (g): | 254
Tool Number: | 13456
Cavitation: | 4
Cavitation Assy: | 2
Final Serial Plant: | Pologne
Cycle Time INJ | 34
Cycle Time ASSY | 45
B - Targets
Trial Number (Please, don't rename table's heading)
Caractéristiques | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Raw Material | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Components | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Process status (injection) | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Process status (assembly, welding, printing, hot stamping, ..) | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Dimensional | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Fit & Function | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Aspect | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Tracability | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
DVP (Validation plan and testing) | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Checking Aids | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
PPAP status | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
C - Criticity
Criticity | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30%: Coefficient; 50% 50% 50% 50% 50% 50% 50% 50% 50% 50% 50%: Assessment; 60% 60% 60% 60% 60% 60% 60% 60% 60% 60% 60%: SCORE
High | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30%: 6; 50% 50% 50% 50% 50% 50% 50% 50% 50% 50% 50%: OK; 60% 60% 60% 60% 60% 60% 60% 60% 60% 60% 60%: 1
Medium | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30%: 3; 50% 50% 50% 50% 50% 50% 50% 50% 50% 50% 50%: NOK; 60% 60% 60% 60% 60% 60% 60% 60% 60% 60% 60%: 0
Low | bar: 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30%

## Injection Overview
Colonne1 | Colonne2 | Runs → | FOT | SOT | TOT | 4OT | 5OT | 6OT
Weight 1 shot + sprue portion (g) | GRAPHINJ | 20 | 25 | 22 | 22 | 21 | 20 | 17
Overall Equipment Effectiveness | GRAPHINJ | 0.9 | 1 | 0.88333 | 0.91667 | 0.93333 | 0.95 | 0.98333
Cycle time (sec) | GRAPHINJ | 34 | 22 | 21.2 | 18.8571 | 16.8 | 15.2 | 14.16
Scrap rate (%) | GRAPHINJ | 0.02 | 0 | 0.066667 | 0.042857 | 0.025 | 0.02 | 0.01

## Assy Overview
Colonne1 | Colonne2 | Runs → | FOT | SOT | TOT | 4OT | 5OT | 6OT
Overall Equipment Effectiveness | GRAPHASSY | 0.95 | 1 | 0.77778 | 0.83333 | 0.88889 | 0.91111 | 0.97778
Cycle time (sec) | GRAPHASSY | 45 | 36 | 32.3077 | 22.5 | 19.2 | 15.375 | 11
Scrap rate (%) | GRAPHASSY | 0.05 | 0 | 0.30769 | 0.15 | 0.08 | 0.046875 | 0.020833

## Source
Attribut | Numéro Essai | Caractéristique | Réel
FOT | 1 | Raw Material | 0
FOT | 1 | Components | 0
FOT | 1 | Process status (injection) | 0.25
FOT | 1 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5
FOT | 1 | Dimensional | 0.4375
FOT | 1 | Fit & Function | 0
FOT | 1 | Aspect | 0
FOT | 1 | Tracability | 0
FOT | 1 | DVP (Validation plan and testing) | 0
FOT | 1 | Checking Aids | 0
FOT | 1 | PPAP status | 0
SOT | 2 | Raw Material | 0.6
SOT | 2 | Components | 0.5
SOT | 2 | Process status (injection) | 0.25
SOT | 2 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5
SOT | 2 | Dimensional | 0.65
SOT | 2 | Fit & Function | 0.4
SOT | 2 | Aspect | 0.6
SOT | 2 | Tracability | 0.5
SOT | 2 | DVP (Validation plan and testing) | 0.5
SOT | 2 | Checking Aids | 0.33333
SOT | 2 | PPAP status | 0
TOT | 3 | Raw Material | 0.6
TOT | 3 | Components | 1
TOT | 3 | Process status (injection) | 0.375
TOT | 3 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5
TOT | 3 | Dimensional | 0.7375
TOT | 3 | Fit & Function | 0.6
TOT | 3 | Aspect | 0.6
TOT | 3 | Tracability | 0.75
TOT | 3 | DVP (Validation plan and testing) | 0.5
TOT | 3 | Checking Aids | 0.66667
TOT | 3 | PPAP status | 0
4OT | 4 | Raw Material | 0.6
4OT | 4 | Components | 1
4OT | 4 | Process status (injection) | 0.5
4OT | 4 | Process status (assembly, welding, printing, hot stamping, ..) | 0.66667
4OT | 4 | Dimensional | 0.825
4OT | 4 | Fit & Function | 1
4OT | 4 | Aspect | 0.8
4OT | 4 | Tracability | 0.75
4OT | 4 | DVP (Validation plan and testing) | 1
4OT | 4 | Checking Aids | 1
4OT | 4 | PPAP status | 0
5OT | 5 | Raw Material | 0.6
5OT | 5 | Components | 1
5OT | 5 | Process status (injection) | 1
5OT | 5 | Process status (assembly, welding, printing, hot stamping, ..) | 0.83333
5OT | 5 | Dimensional | 0.9125
5OT | 5 | Fit & Function | 1
5OT | 5 | Aspect | 1
5OT | 5 | Tracability | 0.75
5OT | 5 | DVP (Validation plan and testing) | 1
5OT | 5 | Checking Aids | 1
5OT | 5 | PPAP status | 0
6OT | 6 | Raw Material | 1
6OT | 6 | Components | 1
6OT | 6 | Process status (injection) | 1
6OT | 6 | Process status (assembly, welding, printing, hot stamping, ..) | 1
6OT | 6 | Dimensional | 1
6OT | 6 | Fit & Function | 1
6OT | 6 | Aspect | 1
6OT | 6 | Tracability | 1
6OT | 6 | DVP (Validation plan and testing) | 1
6OT | 6 | Checking Aids | 1
6OT | 6 | PPAP status | 1

## Expectations
Numéro Essai | Caractéristique | Attendu
1 | Raw Material | 0.3
2 | Raw Material | 0.4
3 | Raw Material | 0.5
4 | Raw Material | 0.6
5 | Raw Material | 0.7
6 | Raw Material | 0.8
7 | Raw Material | 0.9
8 | Raw Material | 1
1 | Components | 0.3
2 | Components | 0.4
3 | Components | 0.5
4 | Components | 0.6
5 | Components | 0.7
6 | Components | 0.8
7 | Components | 0.9
8 | Components | 1
1 | Process status (injection) | 0.3
2 | Process status (injection) | 0.4
3 | Process status (injection) | 0.5
4 | Process status (injection) | 0.6
5 | Process status (injection) | 0.7
6 | Process status (injection) | 0.8
7 | Process status (injection) | 0.9
8 | Process status (injection) | 1
1 | Process status (assembly, welding, printing, hot stamping, ..) | 0.3
2 | Process status (assembly, welding, printing, hot stamping, ..) | 0.4
3 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5
4 | Process status (assembly, welding, printing, hot stamping, ..) | 0.6
5 | Process status (assembly, welding, printing, hot stamping, ..) | 0.7
6 | Process status (assembly, welding, printing, hot stamping, ..) | 0.8
7 | Process status (assembly, welding, printing, hot stamping, ..) | 0.9
8 | Process status (assembly, welding, printing, hot stamping, ..) | 1
1 | Dimensional | 0.3
2 | Dimensional | 0.4
3 | Dimensional | 0.5
4 | Dimensional | 0.6
5 | Dimensional | 0.7
6 | Dimensional | 0.8
7 | Dimensional | 0.9
8 | Dimensional | 1
1 | Fit & Function | 0.3
2 | Fit & Function | 0.4
3 | Fit & Function | 0.5
4 | Fit & Function | 0.6
5 | Fit & Function | 0.7
6 | Fit & Function | 0.8
7 | Fit & Function | 0.9
8 | Fit & Function | 1
1 | Aspect | 0.3
2 | Aspect | 0.4
3 | Aspect | 0.5
4 | Aspect | 0.6
5 | Aspect | 0.7
6 | Aspect | 0.8
7 | Aspect | 0.9
8 | Aspect | 1
1 | Tracability | 0.3
2 | Tracability | 0.4
3 | Tracability | 0.5
4 | Tracability | 0.6
5 | Tracability | 0.7
6 | Tracability | 0.8
7 | Tracability | 0.9
8 | Tracability | 1
1 | DVP (Validation plan and testing) | 0.3
2 | DVP (Validation plan and testing) | 0.4
3 | DVP (Validation plan and testing) | 0.5
4 | DVP (Validation plan and testing) | 0.6
5 | DVP (Validation plan and testing) | 0.7
6 | DVP (Validation plan and testing) | 0.8
7 | DVP (Validation plan and testing) | 0.9
8 | DVP (Validation plan and testing) | 1
1 | Checking Aids | 0.3
2 | Checking Aids | 0.4
3 | Checking Aids | 0.5
4 | Checking Aids | 0.6
5 | Checking Aids | 0.7
6 | Checking Aids | 0.8
7 | Checking Aids | 0.9
8 | Checking Aids | 1
1 | PPAP status | 0.3
2 | PPAP status | 0.4
3 | PPAP status | 0.5
4 | PPAP status | 0.6
5 | PPAP status | 0.7
6 | PPAP status | 0.8
7 | PPAP status | 0.9
8 | PPAP status | 1

## Power Bi
Attribut | Numéro Essai | Caractéristique | Réel | TableauAttendu.Attendu
FOT | 1 | Fit & Function | 0 | 0.3
FOT | 1 | PPAP status | 0 | 0.3
FOT | 1 | Dimensional | 0.4375 | 0.3
FOT | 1 | Aspect | 0 | 0.3
FOT | 1 | Checking Aids | 0 | 0.3
FOT | 1 | DVP (Validation plan and testing) | 0 | 0.3
FOT | 1 | Tracability | 0 | 0.3
FOT | 1 | Raw Material | 0 | 0.3
FOT | 1 | Process status (injection) | 0.25 | 0.3
FOT | 1 | Components | 0 | 0.3
FOT | 1 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5 | 0.3
SOT | 2 | Process status (injection) | 0.25 | 0.4
SOT | 2 | Dimensional | 0.65 | 0.4
SOT | 2 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5 | 0.4
SOT | 2 | Tracability | 0.5 | 0.4
SOT | 2 | Aspect | 0.6 | 0.4
SOT | 2 | DVP (Validation plan and testing) | 0.5 | 0.4
SOT | 2 | Fit & Function | 0.4 | 0.4
SOT | 2 | Components | 0.5 | 0.4
SOT | 2 | Raw Material | 0.6 | 0.4
SOT | 2 | Checking Aids | 0.33333 | 0.4
SOT | 2 | PPAP status | 0 | 0.4
TOT | 3 | Process status (assembly, welding, printing, hot stamping, ..) | 0.5 | 0.5
TOT | 3 | Fit & Function | 0.6 | 0.5
TOT | 3 | Dimensional | 0.7375 | 0.5
TOT | 3 | Aspect | 0.6 | 0.5
TOT | 3 | Checking Aids | 0.66667 | 0.5
TOT | 3 | Tracability | 0.75 | 0.5
TOT | 3 | PPAP status | 0 | 0.5
TOT | 3 | DVP (Validation plan and testing) | 0.5 | 0.5
TOT | 3 | Process status (injection) | 0.375 | 0.5
TOT | 3 | Raw Material | 0.6 | 0.5
TOT | 3 | Components | 1 | 0.5
4OT | 4 | Checking Aids | 1 | 0.6
4OT | 4 | Fit & Function | 1 | 0.6
4OT | 4 | PPAP status | 0 | 0.6
4OT | 4 | Tracability | 0.75 | 0.6
4OT | 4 | Raw Material | 0.6 | 0.6
4OT | 4 | Components | 1 | 0.6
4OT | 4 | DVP (Validation plan and testing) | 1 | 0.6
4OT | 4 | Process status (injection) | 0.5 | 0.6
4OT | 4 | Process status (assembly, welding, printing, hot stamping, ..) | 0.66667 | 0.6
4OT | 4 | Aspect | 0.8 | 0.6
4OT | 4 | Dimensional | 0.825 | 0.6
5OT | 5 | Raw Material | 0.6 | 0.7
5OT | 5 | DVP (Validation plan and testing) | 1 | 0.7
5OT | 5 | Aspect | 1 | 0.7
5OT | 5 | Process status (injection) | 1 | 0.7
5OT | 5 | Checking Aids | 1 | 0.7
5OT | 5 | PPAP status | 0 | 0.7
5OT | 5 | Components | 1 | 0.7
5OT | 5 | Dimensional | 0.9125 | 0.7
5OT | 5 | Fit & Function | 1 | 0.7
5OT | 5 | Tracability | 0.75 | 0.7
5OT | 5 | Process status (assembly, welding, printing, hot stamping, ..) | 0.83333 | 0.7
6OT | 6 | PPAP status | 1 | 0.8
6OT | 6 | Checking Aids | 1 | 0.8
6OT | 6 | Dimensional | 1 | 0.8
6OT | 6 | Fit & Function | 1 | 0.8
6OT | 6 | Components | 1 | 0.8
6OT | 6 | Process status (assembly, welding, printing, hot stamping, ..) | 1 | 0.8
6OT | 6 | Process status (injection) | 1 | 0.8
6OT | 6 | DVP (Validation plan and testing) | 1 | 0.8
6OT | 6 | Raw Material | 1 | 0.8
6OT | 6 | Aspect | 1 | 0.8
6OT | 6 | Tracability | 1 | 0.8