## EXTRACT X-DRCL
|  | DELIVERABLES CHECK LIST DR1 - EXTRACT TOOLS - X-DRCL | [7 empty] | CRITICALY POINTS |  | REVIEW DATE | Date : 26/03/2019 | 26/03/2019 | 26/03/2019 | Date : 16/03/2021
|  | Chemin d'accès complet de la DR1 : Full access path of the DR1 : | C:\Users\brenaud\Desktop\TEST DR1 |  |  | 2 - Choise your DRCL (Gate Review) : |  | S-DRCL |  | LOW : | 6 |  | Date : 26/03/2019 | Date : 26/03/2019 |  | Date :
|  | DR LEADER NAME : | Bernard RENAUD |  | Function : | 3 - CLICK HERE for EXTRACT the X-DRCL |  |  |  | MEDIUM : | 1 |  | Date : 26/03/2019 |  |  | 2021-03-16
|  | DATE VALIDATED by E-SST : | 2021-03-29 |  | EQE |  |  |  |  | HIGH : | 0 |  | 26/03/2019
Date : | 2021-03-18 | 2.4[CLM] - Provide proper climate |  |  | SERVICE : | ENG. QUALITY | Departement : | QUALITY DEPARTEMENT |  |  |  |  | 26/03/2019
⚠ Activer le "CONTENU" avant les Macro ⚠ Vérifier que vous êtes bien connecté au réseau : Pulse Secure ⚠ Activate "CONTENT" before Macro ⚠ Check that you are well connected to the network : Pulse Secure |  |  | ⚠ Attention : N'utilisez pas de filtre (ex sur NOK) dans le fichier X-DRCL ⚠ Warning : Do not use a filter (e.g. on NOK) in the X-DRCL file |  |  | ⚠ Attention : Si 2 FICHIERS (.xls) ou plus derrière le chemin d'accès de la DR1 ⚠ Warning : If 2 FILES (.xls) or more behind the DR1 access path | [6 empty] | 26/03/2019
Id | Questions / Proof request | Answer (refer to deliverables if any) | Status | Issue and Risk description | Current Risk Criticality | Mitigation plan | PIC | target date | OIL ?
S.D.R. |  | 2.4[CLM] - Provide proper climate |  | Date : 26/03/2019
Id | Questions / Proof request | Answer (refer to deliverables if any) | Status | Issue and Risk description | Current Risk Criticality | Mitigation plan | PIC | target date
0 | OVERALL PROGRESS (Is the technical progress sufficient to perform the design review ?)
0.1 | Is the operation of driver and maintainer defined in OCD regarding the concerned functions? Provide doc reference and main comments from reviewer. | No OCD for the project | OK | NA Driver and maintenance functions are not defined but will be based on Smart metro
0.2 | Is the function 2,4[CLM] - Provide proper climate in the RSAD train completed and signed ? Provide doc reference and main comments from reviewer. | ADL1 will be finished for the SDR TCMS. SPP is finalised. | NOK | ADL1 will to be done fort the TCMS SDR. | LOW |  | JF. Boucault | 2019-07-15 | NOK
0.3 | Is RSAD L2 HVAC sub system issued and signed ? | TPSv2 done and commited | OK
1 | REQUIREMENTS
1.2 | Are the requirements coming from customer clarified (and shared with customer) regarding - saloon HVAC - cabin climatisation Present the requirements considered as gap with reference solution. Is one identified as risk? | The project confirms the cooling mode conditions : train at standstill but without sun Waiting for the customer aproval on Alstom proposal : replace the maintenance switch with DDU function | NOK |  | LOW | The maintenance switch is included on the e-box. If the customer accepts to make the function by the DDU, we will remove the switch | Brassart | 2019-04-15 | NOK
1.4 | Are the requirements coming from certification clarified on regulation to fulfil for the function 2.4[CLM] ? |  | OK | NA, HVAC is not involved in the train certification
2 | SOLUTION DESIGN
2.1 | Architecture : Present the architecture for saloon and cabin heat ventilation and air conditioning. Present component, responsibility, location, numbering. What are the gaps vs. ref sol ? | There is only one "double" HVAC unit by car. The e-box is a different box, not included in the HVAC box. GPE HVAC is completely different from the Smart solution. | OK
2.2 | Product : Present saloon and cabin HVAC product reference selected and GAPS for this project. | CP1354-51-FA01E_Rev.G=Technical proposal for saloon HVAC system \\SRSDC107184x010\LR_PTF1\GPE\02_Design\H-Sous-Systèmes\09. Climatisation\04-Documentation Technique\Descriptifs techniques | OK
2.3 | Present train level effect on service in case of loss of function or main sub component of the HVAC (detrain , end of line end of day, wait for repair). Is it in accordance with customer requirement? | Electrical drawing is designed to respond to the availability requirement : in case of single failure, at least 50% of the heating, cooling and ventilation functions are available. AVARIE : loss of 50% of the ventilation, loss 100% of the heating, 50 and 100% of the cooling HLP : loss of 100% of the ventilation + temperature Degraded modes for HVAC will be described in the FMECA | NOK |  | LOW |  | King | 2019-04-15 | NOK
2.4 | Present cooling/heating calculation note with assumptions showing that it reaches thermal performances in nominal and degraded mode. | Cooling/heating calulations are the same as in the technical description from the tender phase with the following details 1. Cooling performance has to be calculated in standstill instead for 55km/h (requierment from a customer desing review in december 2018) 2. The heating is calculated without passengers. Thermal balance is available : \\SRSDC107184x010\LR_PTF1\GPE\02_Design\H-Sous-Systèmes\09. Climatisation\12-Bilan thermique | OK
2.5 | Present electrical power consumption calculation. Present also calculation in case of loss of HV and battery charger that proves it meets the customer requirements for emergency ventilation. | CP1354-51-QT03E_Rev.A=Power consumption of saloon \\SRSDC107184x010\LR_PTF1\GPE\02_Design\H-Sous-Systèmes\09. Climatisation\04-Documentation Technique\Consommation électrique To verify if the train electrical consumption balance is OK with the HVAC consumption | NOK |  | LOW |  | Kamenova | 2019-04-15 | NOK
2.6 | Is the way driver or operator operate cooling or heating for cab and saloon clarified ? List interfaces on driver desk and possibly local panel in each car ( Switch, PB , PB , DDU). Can it be operated only from active cab, any cab of a unit or all cab ? Has maintenance operation been taken into account ? Is it agreed with customer ? | Will be described in the AD Only software involved | OK
2.7 | Has supplier committed on the type of AC power supply (EN50533 class 1 or 3 in particular DV/DT) and the related technology of AC motor? Is there any customer specific requirement for AC motor technology? | EC motors for the ventilation OK for the EN50533 class 1 | OK
2.8 | Show if there is any Safety requirement to HVAC and how it is implemented, in particular emergency ventilation in case of loss of HV and possible requirement of tunnel air cut out in case of fire. | The HVAC is cut in case of internal smoke The HVAC closes fresh air dampers in case of external smoke The HVAC has emergency ventilation in case of HV loss or TCMS loss | OK
2.9 | Check for each HVAC component if electrical interface is defined : type and location of connector, number of pin, voltage, consumption. Has the supplier in its electrical supply confirmed compliance to PPPL? | 2 connectors has to be changed by the supplier | NOK |  | LOW |  | King | 2019-04-10 | NOK
2.1 | Check for each HVAC component if mechanical interface is defined : fixing, maintenance access, aerolic, ... What are the issues identified during Integration Review ? | OK for HVAC, volume of the e-box to be validated by TD | NOK |  | MEDIUM |  | Weerts | 2019-04-15 | NOK
2.11 | Is a preliminary version of ICD defined with supplier containing control data? Is maintenance data defined ? Does data include preventive maintenance data : duration of operation of compressor, heater, ventilator, number of operation of contactor ? Is it memorised on CLM or TCMS ? | Based on Smart Will be done for SGR TCMS | NOK |  | LOW |  | JF. Boucault | 2019-07-15 | NOK
2.12 | Is maintenance SW provided by HVAC supplier ? What are the function supported ? | Webservice | OK
2.13 | Has supplier committed on Network interfaces ? Is the degraded mode of loss of one electronic (HVAC, RIOM, MPU, SWITCH) in accordance with train operation constraints? |  | OK
2.14 | Have alternative solutions been studied? Justify the choice done. |  | OK | NA
2.15 | What are the failure modes with the higher rating identified in the Train level FMECA and present associated action plan if any. |  | OK | NA
3 | VERIFICATION & VALIDATION
3.1 | Are there requirements linked to the function without mean of proof defined? | MOP in the CbC | OK
3.2 | Are there any verification activities planned and/or realized regarding this function ? Are they formalized in the DJD ? What are the results (if any) ? | Thermal balance OK, but V0 to be created Refer to SDR Climatic comfort to the gradient | OK
3.4 | Present the Certification Requirement Identification & Certification Mean of Proof regarding the function "Provide proper climate" | Functionnal tests to be planified forMOP Arrêté tunnel | OK
3.7 | Are there any tests (validation or certification) planned to be performed on train related to the function "Provide proper climate" ? | Climatic chamber test scheduled for March 2021 | OK
4 | MISCELANEOUS
4.1 | Are there specific items associated to technical risks or difficulties which have not been reviewed in the upper part? |  | OK
4.2 | Are there open items in PSLI linked to the function 2.4[CLM], which have not been reviewed in the upper part? |  | OK
4.3 | Which tools and processes (check-lists, templates, guidelines...) clarifications/improvements could be useful? |  | OK
5 | COMMITMENT
5.1 | Is there any other risk or difficulty able to trouble the QCD commitment ? |  | OK
6 | D.R. STATUS | OK
1
2
EXTRACT X-DRCL
3

## EXTRACT X-DRCL OVERVIEW
DELIVERABLES CHECK LIST DR1 - EXTRACT TOOLS - X-DRCL OVERVIEW | [5 empty] | SDR | S-DRCL | TEMPLATE | S-DRCL Overview | JALON | PROJECT NAME | #VALUE!
| SPECIFICATION DESIGN REVIEW CHECK LIST |  |  |  | S-DRCL Overview |  | T-DRCL | T-DRCL Overview | TENDER DESIGN REVIEW CHECK LIST | TDR
| C:\Users\brenaud\Desktop\TEST DR1 |  | DR LEADER NAME : |  | Bernard RENAUD |  | L-DRCL | L-DRCL Overview | LAUNCH DESIGN REVIEW CHECK LIST | LDR
|  |  | EDU / SERVICE : |  | ENG. QUALITY |  | S-DRCL | S-DRCL Overview | SPECIFICATION DESIGN REVIEW CHECK LIST | SDR
|  |  | 4 - CLICK HERE for EXTRACT the X-DRCL OVERVIEW |  |  |  | P-DRCL | P-DRCL Overview | PRELIMINARY DESIGN REVIEW CHECK LIST | PDR
2.4[CLM] - Provide proper climate | [6 empty] | C-DRCL | C-DRCL Overview | CRITICAL DESIGN REVIEW CHECK LIST | CDR
[7 empty] | GFV-DRCL | GFV-DRCL Overview | GO FOR VALIDATION DESIGN REVIEW CHECK LIST | GFV
PROJECT NAME : |  | Agreement for X-DRCL : |  | DRCL Ref.: | 0 |  | IQ-DRCL | IQ-DRCL Overview | INTERNAL QUALIFICATION DESIGN REVIEW CHECK LIST | IQR
REVIEW DATE : | 26/03/2019 | 0 |  | DRCL Rev.: | 0 |  | V-DRCL | V-DRCL Overview | VALIDATION DESIGN REVIEW CHECK LIST | VDR
EXTRACT OVERVIEW
4