## SECURITY MEASURES
C2-Confidential |  |  |  | SECURITY MEASURES |  |  | XX | [5 empty] | IMPLEMENTATION at the end of the program |  |  | PROJECT EXECUTION |  |  |  | PLANNING |  |  |  |  | BUDGET (k€) | [14 empty] | ENTITY Private columns |  | CHECKS
[13 empty] | (including already implemented measures) | [12 empty] | TOTAL |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023
BU | Region | Entity | Index | Security pack | Topic | Measure ID | Priority | Measure | Description | Deliverables | Dependencies | Reference | Target status | Target scope | Target justification (if<100%) | Status | Implementation progress rate | CISO assessment | CISO Comments | Resource allocated | Main actor | Kick-off | Initial end | Re-estimated end | Total Initial | Total re-estimated | Total Spent | Initial 2020 | Reestimated 2020 | Spent 2020 | Initial 2021 | Reestimated 2021 | Spent 2021 | Initial 2022 | Reestimated 2022 | Spent 2022 | Initial 2023 | Reestimated 2023 | Spent 2023 | <Local use 1> | <Local use 2> | Global Progress rate | Impl_Yes | Impl_Date | DataInconsistency | EmptyFields
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 95% | No alert | XX | [5 empty] | 0 | 0 | 0 | [14 empty] | 95% | 0 | 2020-01-01 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX | [5 empty] | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX | [5 empty] | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX | [5 empty] | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 99% | No alert | XX |  |  | 2016-01-01 | 2018-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 99% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX |  |  | 2019-06-10 | 2019-12-31 | 2020-04-30 | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-04-30 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX |  |  | 2019-01-01 | 2019-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% | No alert | XX |  |  | 2019-06-30 | 2019-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 95% | No alert | XX |  |  | 2019-06-30 | 2019-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 95% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 30% | No alert | XX |  |  | 2019-01-01 | 2019-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 30% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 50% | No alert | XX |  |  | 2018-01-01 | 2018-12-31 | 2020-12-31 | 0 | 0 | 0 | [14 empty] | 50% | 0 | 2020-12-31 | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% | No alert | XX |  |  | 2018-01-01 | 2018-12-31 | 2020-12-31 | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - | 2019-04-01 | 2019-09-01 |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 20% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 20% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 20% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 20% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 10% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 10% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | DONE | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 1 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 50% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 50% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 50% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 50% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 32% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 60% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 24% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 70% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 70% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 40% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 40% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 48% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - |  |  |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 | 2020-01-01 | #REF! | 2
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 40% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 30% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 30% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 70% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 70% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 50% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 50% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 20% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 20% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 40% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX |  |  | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 |  | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NOT APPLICABLE | Not applicable | - | NO PROJECT | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [15 empty] | 0 |  | #REF! | 0
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 60% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 60% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 40% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 40% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 40% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 80% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 80% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 80% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | PARTIAL IMPLEMENTATION + RA | 20% | - | TO BE STARTED | 0% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 0% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 60% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 60% | 0 | 2020-01-01 | #REF! | 1
XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FULL IMPLEMENTATION | 100% | - | IN PROGRESS | 100% |  | XX |  | - |  |  |  | 0 | 0 | 0 | [14 empty] | 100% | 0 | 2020-01-01 | #REF! | 1
Formulas:
Impl_Date = IF(GLOBAL_DATA[[#This Row],[Status]]=Status_No_Project,"",MAX(GLOBAL_DATA[[#This Row],[Initial end]],GLOBAL_DATA[[#This Row],[Re-estimated end]],43831))
Note on R4: (Done = 100%)

## DATA (hidden)
C2-Confidential
File_Version | Security packs EN | Security packs FR | Acronym / Acronyme |  | Status_Choice | Rank | Months overdelay | # | Entity | BU | Region | Country | Level | Language | Pack EN | Pack FR | Theme EN | Theme FR | Acronym theme | Acronym combined | ID
5.0 | Advanced protection | Protection avancée | ADP |  | NO PROJECT | 1 | 3 | 1 | BDK | EURO | - | Allemagne | 3 | EN | Advanced protection | Protection avancée | Analytic security | Sécurité analytique | ANS | ADP_ANS | Advanced protectionAnalytic security
| Cloud | Cloud | CLD |  | TO BE STARTED | 2 |  | 2 | BDP | AFMO | Outre-mer | Polynésie française | 3 | FR | Advanced protection | Protection avancée | Cyber Incident | Incident cyber | CYI | ADP_CYI | Advanced protectionCyber Incident
Deadline | Data protection | Protection des données | DTP |  | IN PROGRESS | 3 | Ressources | 3 | BFCOI | AFMO | Outre-mer | La Réunion | 3 | FR | Advanced protection | Protection avancée | Endpoint security | Sécurité des terminaux | ENS | ADP_ENS | Advanced protectionEndpoint security
2023-12-31 | Exposed services | Services exposés | EXS |  | DONE | 4 | Not secured | 4 | BRD | EURO | - | Roumanie | 1 | EN | Advanced protection | Protection avancée | Filtering security | Sécurité des flux | FLS | ADP_FLS | Advanced protectionFiltering security
| Internal fraud protection | Protection contre la fraude interne | IFP |  | CHECKED CISO | 5 | Secured | 5 | BRD Finance | EURO | - | Roumanie | 3 | EN | Advanced protection | Protection avancée | Sensitive Assets | Actifs sensibles | SEA | ADP_SEA | Advanced protectionSensitive Assets
Date | Operational security | Sécurité opérationnelle | OPS |  | VERIFIED | 6 |  | 6 | CGI Finance | EURO | - | France | 2 | FR | Advanced protection | Protection avancée | User Security | Sécurité des utilisateurs | UZS | ADP_UZS | Advanced protectionUser Security
#REF! | Security in product lifecycle | Sécurité dans le cycle de vie produit | SPL |  |  |  |  | 7 | EQDOM | AFMO | Maroc | Maroc | 3 | FR | Cloud | Cloud | Cloud Management | Gestion du Cloud | MNG | CLD_MNG | CloudCloud Management
| Third parties and supply chain | Tiers et supply chain | TPS |  |  |  |  | 8 | Essox | EURO | - | République Tchèque | 3 | EN | Cloud | Cloud | Availability | Disponibilité | AVA | CLD_AVA | CloudAvailability
| Training and awareness | Formation et sensibilisation | TAA |  | Target_Status_Choice | Value | Target of scope | 9 | Fiditalia | EURO | - | Italie | 2 | EN | Cloud | Cloud | IAM | IAM | IAM | CLD_IAM | CloudIAM
[5 empty] | RISK ACCEPTED | 0% | Not applicable | 10 | Hanseatic Bank | EURO | - | Allemagne | 3 | EN | Cloud | Cloud | Data Protection | Protection des données | DTP | CLD_DTP | CloudData Protection
[5 empty] | PARTIAL IMPLEMENTATION + RA | 1% | 0% | 11 | KB | EURO | - | République Tchèque | 1 | EN | Cloud | Cloud | Incident management | Gestion des incidents | IMN | CLD_IMN | CloudIncident management
CISO assessment | Pack | Pack Formula | Acronyme | Order index | FULL IMPLEMENTATION | 100% | 20% | 12 | ROSBANK | RUSS | - | Russie | 1 | EN | Cloud | Cloud | Services access | Accès aux services | SAC | CLD_SAC | CloudServices access
No alert | Operational security | Operational security | OPS | 1 | NOT APPLICABLE | NOT APPLICABLE | 40% | 13 | Rusfinance | RUSS | - | Russie | 2 | EN | Cloud | Cloud | Architecture | Architecture | ARC | CLD_ARC | CloudArchitecture
Warning | Training and awareness | Training and awareness | TAA | 2 |  |  | 60% | 14 | SGA | AFMO | Méditerranée | Algérie | 2 | FR | Cloud | Cloud | Access filtering | Filtrage d'accès | ACF | CLD_ACF | CloudAccess filtering
Alert | Data protection | Data protection | DTP | 3 | RAF_Status_Choice | Rank | 80% | 15 | SGABS | AFMO | COO | Maroc | 1 | FR | Cloud | Cloud | Infrastructure security | Sécurité de l'infrastructure | IFS | CLD_IFS | CloudInfrastructure security
| Internal fraud protection | Internal fraud protection | IFP | 4 | NOT APPLICABLE | 1 | 100% | 16 | SGB | AFMO | Afrique de l'ouest | Bénin | 3 | FR | Cloud | Cloud | Log management | Gestion des traces | LGM | CLD_LGM | CloudLog management
| Advanced protection | Advanced protection | ADP | 5 | TO BE DONE | 2 |  | 17 | SGBF | AFMO | Afrique de l'ouest | Burkina Faso | 3 | FR | Data protection | Protection des données | Data cartography | Cartographie des données | DCT | DTP_DCT | Data protectionData cartography
| Exposed services | Exposed services | EXS | 6 | TO BE UPDATED | 3 |  | 18 | SGBGE | AFMO | Afrique centrale et Australie | Guinée équatoriale | 3 | FR | Data protection | Protection des données | Data classification | Classification des données | DCL | DTP_DCL | Data protectionData classification
| Cloud | Cloud | CLD | 7 | IN PROGRESS | 4 |  | 19 | SGC | AFMO | Afrique centrale et Australie | Congo | 3 | FR | Data protection | Protection des données | Monitoring | Monitoring | MON | DTP_MON | Data protectionMonitoring
| Third parties and supply chain | Third parties and supply chain | TPS | 8 | SUBMITTED | 5 |  | 20 | SGCAM | AFMO | Afrique centrale et Australie | Cameroun | 3 | FR | Data protection | Protection des données | Data leakage | Fuite de données | DLK | DTP_DLK | Data protectionData leakage
| Security in product lifecycle | Security in product lifecycle | SPL | 9 | VALIDATED | 6 |  | 21 | SGCB | AFMO | Outre-mer | Nouvelle Calédonie | 3 | FR | Data protection | Protection des données | Encryption | Chiffrement | ENC | DTP_ENC | Data protectionEncryption
| ATM | ATM |  | 10 |  |  |  | 22 | SGCI | AFMO | Afrique de l'ouest | SGCI | 3 | FR | Data protection | Protection des données | Anonymisation | Anonymisation | ANO | DTP_ANO | Data protectionAnonymisation
| Global Overview | * |  | 11 |  |  |  | 23 | SGGH | AFMO | Afrique de l'ouest | Ghana | 3 | EN | Data protection | Protection des données | Big Data | Big data | BDT | DTP_BDT | Data protectionBig Data
[8 empty] | 24 | SGGN | AFMO | Afrique de l'ouest | Guinée | 3 | FR | Exposed services | Services exposés | Secure Hosting Baseline | Hébergement de référence sécurisé | SHB | EXS_SHB | Exposed servicesSecure Hosting Baseline
[8 empty] | 25 | SGM | AFMO | Afrique de l'ouest | Mauritanie | 3 | FR | Exposed services | Services exposés | Customer Identity Mangement | Gestion de l'identité des clients | CIM | EXS_CIM | Exposed servicesCustomer Identity Mangement
[8 empty] | 26 | SGMA | AFMO | Maroc | Maroc | 2 | FR | Exposed services | Services exposés | DNS security | Sécurité du DNS | DNS | EXS_DNS | Exposed servicesDNS security
[8 empty] | 27 | SGMADA | AFMO | Afrique centrale et Australie | Madagascar | 2 | FR | Exposed services | Services exposés | E-fraud | E-fraud | EFD | EXS_EFD | Exposed servicesE-fraud
[8 empty] | 28 | SGMZ | AFMO | Afrique centrale et Australie | Mozambique | 3 | EN | Exposed services | Services exposés | Internet application security | Sécurité des applications web | IAS | EXS_IAS | Exposed servicesInternet application security
[8 empty] | 29 | SGSN | AFMO | Afrique de l'ouest | Sénégal | 3 | FR | Exposed services | Services exposés | Mobile Banking Security | Sécurité des services bancaires mobile | MBS | EXS_MBS | Exposed servicesMobile Banking Security
[8 empty] | 30 | SGT | AFMO | Afrique centrale et Australie | Tchad | 3 | FR | Exposed services | Services exposés | Open Banking and API security | Open Banking et sécurité des API | OBS | EXS_OBS | Exposed servicesOpen Banking and API security
[8 empty] | 31 | SGTG | AFMO | Afrique de l'ouest | Togo | 3 | FR | Exposed services | Services exposés | Secure usage of internet services | Utilisation sécurisée des services web | SUI | EXS_SUI | Exposed servicesSecure usage of internet services
[8 empty] | 32 | UIB | AFMO | Méditerranée | Tunisie | 3 | FR | Internal fraud protection | Protection contre la fraude interne | Governance | Gouvernance | GOV | IFP_GOV | Internal fraud protectionGovernance
[15 empty] | Internal fraud protection | Protection contre la fraude interne | Prevention | Prévention | PRV | IFP_PRV | Internal fraud protectionPrevention
[9 empty] | 32 | 3 | 7 | 26 |  |  | Internal fraud protection | Protection contre la fraude interne | Detection | Détection | DET | IFP_DET | Internal fraud protectionDetection
[15 empty] | Operational security | Sécurité opérationnelle | Know your IT | Connaître son SI | KYI | OPS_KYI | Operational securityKnow your IT
[15 empty] | Operational security | Sécurité opérationnelle | Incident management | Gestion des incidents | IMN | OPS_IMN | Operational securityIncident management
[15 empty] | Operational security | Sécurité opérationnelle | Access management | Gestion des accès | ACM | OPS_ACM | Operational securityAccess management
[15 empty] | Operational security | Sécurité opérationnelle | Privileged Access management | Gestion des accès à privilèges | PAM | OPS_PAM | Operational securityPrivileged Access management
[15 empty] | Operational security | Sécurité opérationnelle | Secure your IT | Sécuriser son SI | SYI | OPS_SYI | Operational securitySecure your IT
[15 empty] | Operational security | Sécurité opérationnelle | Secure your Endpoints | Protéger ces postes de travail | SYE | OPS_SYE | Operational securitySecure your Endpoints
[15 empty] | Operational security | Sécurité opérationnelle | Maintain IT Security | Maintenance de la sécurité du SI | MIS | OPS_MIS | Operational securityMaintain IT Security
[15 empty] | Operational security | Sécurité opérationnelle | Monitoring | Monitoring | MON | OPS_MON | Operational securityMonitoring
[15 empty] | Operational security | Sécurité opérationnelle | Evaluate your Security | Evaluer la sécurité | EYS | OPS_EYS | Operational securityEvaluate your Security
[15 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Project Methodology | Méthodologie Projet | PMD | SPL_PMD | Security in product lifecycleProject Methodology
[15 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Agile Project Methodology | Méthodologie Projet Agile | APM | SPL_APM | Security in product lifecycleAgile Project Methodology
[15 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Dev. Security | Sécurité des développements | DVS | SPL_DVS | Security in product lifecycleDev. Security
[15 empty] | Security in product lifecycle | Sécurité dans le cycle de vie produit | Devops | Devops | DVO | SPL_DVO | Security in product lifecycleDevops
[15 empty] | Third parties and supply chain | Tiers et supply chain | Third Parties Management | Gestion des tiers | TPM | TPS_TPM | Third parties and supply chainThird Parties Management
[15 empty] | Third parties and supply chain | Tiers et supply chain | Third Parties Access | Accès des tiers | TPA | TPS_TPA | Third parties and supply chainThird Parties Access
[15 empty] | Third parties and supply chain | Tiers et supply chain | Monitoringand control | Suivi et contrôle | MNC | TPS_MNC | Third parties and supply chainMonitoringand control
[15 empty] | Third parties and supply chain | Tiers et supply chain | End of the contract | Fin de contrat | EOC | TPS_EOC | Third parties and supply chainEnd of the contract
[15 empty] | Training and awareness | Formation et sensibilisation | Governance | Gouvernance | GOV | TAA_GOV | Training and awarenessGovernance
[15 empty] | Training and awareness | Formation et sensibilisation | Training | Formation | TRN | TAA_TRN | Training and awarenessTraining
[15 empty] | Training and awareness | Formation et sensibilisation | Awareness | Sensibilisation | AWA | TAA_AWA | Training and awarenessAwareness
[15 empty] | Training and awareness | Formation et sensibilisation | Specific comunication | Communication spécifique | SPC | TAA_SPC | Training and awarenessSpecific comunication
[15 empty] | Training and awareness | Formation et sensibilisation | Customer awareness | Sensibilisation du client | CAW | TAA_CAW | Training and awarenessCustomer awareness
[15 empty] | Training and awareness | Formation et sensibilisation | Third Parties | Tiers | TPT | TAA_TPT | Training and awarenessThird Parties
[15 empty] | 9 |  | 57