## Intervention Cards
Day | Shift | ATIS QLS | MSN | Station | N° of IC Card | Closed(ok/NOK) | If NOK ,Airbus responsible name | Comments
2020-11-09 | AM | BOB | 10335 | L1 St 41 | 1241860 | OK
2020-11-09 | AM | BOB | 10211 | L3 St 42 | 1241172 | NOK | Guesme / Thierry | NC 207871454 still open
2020-11-09 | AM | BOB | 10146 | L3 St 23 | 1240585 | OK
2020-11-09 | AM | BRUNO | 10180 | L3 St 35 | 1235945 | OK
2020-11-09 | AM | BOB | 10363 | L3 St 25 | 1243912 | NOK | Romanzin / Cuziat | NC 14742433 still open
2020-11-09 | AM | BOB | 10210 | L1 St 40 | 1240467 | OK
2020-11-09 | AM | BOB | 10306 | L1 St 35 |  | OK
2020-11-09 | AM | BOB | 10174 | H14 Nord | 1223680 | OK
2020-11-09 | AM | BOB | 10145 | H7.2 | 207894459 | OK
2020-11-09 | AM | BRUNO | 10020 | H14 Rest | 1213777 | OK
2020-11-09 | AM | BOB | 10010 | H14 Nord | 1243852 | OK
2020-11-09 | PM | BOB | 10253 | L1 St 25 | 1241610 | OK
2020-11-09 | PM | BOB | 10245 | WP 241 | 1226103 | OK
2020-11-09 | PM | BOB | 10210 | L1 St40 | 1240470 | OK
2020-11-09 | PM | BRUNO | 10265 | L3 St40 | 1241650 | OK
2020-11-09 | PM | BRUNO | 10180 | L3 St35 | 1235947 | OK
2020-11-09 | PM | BRUNO | 10265 | L3 St40 | 1241649 | OK
2020-11-09 | PM | BRUNO | 10265 | L3 St41 | 1241650 | OK
2020-11-09 | PM | BRUNO | 10211 | L3 St 42 | 1241172 | OK
2020-11-09 | PM | BOB | 10211 | L3 St 43 | 1241180 | OK
2020-11-09 | PM | BOB | 10277 | L3 St 43 | 1243728 | OK
2020-11-10 | AM | BOB | 10265 | St.40 L3 | 1241651 | OK
2020-11-10 | AM | BOB | 10010 | H14. N2 | 1225337 | OK
2020-11-10 | AM | BRUNO | 10367 | St.42 L1 | 1240764 | OK
2020-11-10 | AM | BRUNO | 10354 | St.42 L3 | 1240602 | OK
2020-11-10 | AM | BRUNO | 10354 | St.42 L3 | 1240601 | OK
2020-11-10 | AM | BRUNO | 10391 | St.41 L1 | 1240549 | OK
2020-11-10 | AM | BOB | 10180 | St.35 L3 | 1235948 | OK
2020-11-10 | AM | BOB | 10034 | St.42 L3 | 1238087 | OK
2020-11-10 | AM | BOB | 10146 | St.35 L3 | 1243593 | OK
2020-11-10 | AM | BOB | 10391 | St.25 L1 | 1240535 | OK
2020-11-10 | AM | BOB | 10367 | St.42 L1 | 1240763 | OK
2020-11-10 | PM | BOB | 10341 | St.42 L2 | 1241449 | OK
2020-11-10 | PM | BOB | 10100 | St.41 L2 | 1243863 | OK
2020-11-10 | PM | BOB | 10341 | St.42 L2 | 1241450 | NOK | Leclercq | WO 1010980863 still open

## WO
Day | Shift | ATIS QLS | MSN | WO | Status | Closure status | Comments
2020-11-09 | AM | BRUNO | 10265 | 1010984221 | checked, OK | transferred to AIB | No SAP PEA rights for closure
2020-11-09 | PM | BRUNO | 10210 | 1011016152 | checked, OK | transferred to AIB | step10 not closed by prod
2020-11-09 | PM | BOB | 10210 | 1010748635 | checked, OK | transferred to AIB | step20 not closed by prod
2020-11-09 | PM | BRUNO | 10210 | 1010788764 | checked, OK | transferred to AIB | step10/20 not closed by prod
2020-11-09 | PM | BRUNO | 10267 | 1011016150 | checked, OK | transferred to AIB | step10 not closed by prod
2020-11-09 | PM | BRUNO | 10335 | 1011016148 | checked, OK | transferred to AIB | step10 not closed by prod
2020-11-10 | AM | BOB | 10100 | 1011000554 | checked, OK | transferred to AIB | step 10 not closed by prod
2020-11-10 | AM | BRUNO | 10367 | 1010984354 | checked, OK | transferred to AIB | No SAP PEA rights for closure
2020-11-10 | AM | BRUNO | 10354 | 1010976419 | checked, OK | transferred to AIB | No SAP PEA rights for closure
2020-11-10 | AM | BRUNO | 10354 | 1010984336 | checked, OK | transferred to AIB | No SAP PEA rights for closure
2020-11-10 | PM | BRUNO | 10341 | 1010976414 | checked, OK | transferred to AIB | step10 not closed by prod
2020-11-10 | PM | BOB | 10341 | 1011016154 | checked, OK | transferred to AIB | step10 not closed by prod
2020-11-10 | PM | BRUNO | 10100 | 1011016145 | checked, OK | transferred to AIB | step10 not closed by prod

## NC
Day | Shift | ATIS QLS | MSN | NC | Status | Closure status | Comments
2020-11-09 | AM | BOB | 10254 | 14752074 | checked, OK | answered by RS
2020-11-09 | AM | BRUNO | 10270 | 14745278 | checked, OK | answered by RS
2020-11-09 | AM | BOB | 10100 | 14754203 | checked, OK | answered by RS
2020-11-09 | AM | BOB | 10306 | 14754220 | checked, NOK | transferred to Roman for return to production/given back to ACM | Job described on NC not done. Unclear and missing docu. No SAP PDA rights for return to Prod.
2020-11-09 | AM | BOB | 10146 | 14752092 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-09 | AM | BOB | 10174 | 14754214 | checked, NOK | transferred to Roman for return to production/given back to ACM | Clash still visible. Rework needed. No SAP PDA rights for return to Prod.
2020-11-09 | AM | BOB | 10145 | 14753862 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-09 | AM | BRUNO | 10020 | 14718717 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-09 | AM | BOB | 10306 | 14754220 | checked, OK | transferred to AIB | 2nd Check. Croquis provided. Status on A/C i.a.w Croquis.
2020-11-09 | AM | BOB | 10174 | 14754214 | checked, OK | transferred to AIB | 2nd Check. No SAP PDA rights for closure.
2020-11-09 | AM | BOB | 10211 | 207871454 | checking blocked by Access | returned to production/given back to ACM | Cargo Door closed.
2020-11-09 | AM | BOB | 10363 | 14742433 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-09 | PM | BRUNO | 10253 | 14754167 | checked, NOK | returned to production/given back to ACM | Tyrap and harness loose on Fin 4LX
2020-11-09 | PM | BRUNO | 10211 | 207871454 | checked, OK | closed by MB
2020-11-09 | PM | BRUNO | 10245 | 14750566 | checked, NOK | returned to production/given back to ACM | Harness not refixed on the bracket at C29 p`25
2020-11-09 | PM | BRUNO | 10245 | 14750566 | checked, OK | answered by MB | 2nd Check. Live rework with production OK.
2020-11-09 | PM | BRUNO | 10151 | 14755022 | checked, OK | answered by MB
2020-11-09 | PM | BOB | 10391 | 14754064 | checked, OK | answered by MB | paper back to TC for NC rappo
2020-11-09 | PM | BOB | 10210 | 207746143 | checked, OK | transferred to AIB | FW suffix must be cross
2020-11-09 | PM | BOB | 10254 | 14754501 | checked, OK | answered by MB
2020-11-09 | PM | BRUNO | 10100 | 14754471 | checked, OK | answered by MB
2020-11-09 | PM | BOB | 10100 | 14754746 | checked, OK | answered by MB
2020-11-09 | PM | BOB | 10265 | 14751124 | checked, OK | answered by MB
2020-11-09 | PM | BOB | 10180 | 14755143 | checked, OK | answered by MB
2020-11-09 | PM | BOB | 10253 | 14754167 | checked, OK | answered by MB | 2nd Check
2020-11-10 | AM | BOB | 10254 | 14754641 | checked, OK | answered by RS
2020-11-10 | AM | BRUNO | 10151 | 14754369 | checked, OK | answered by RS
2020-11-10 | AM | BOB | 10228 | 14755239 | checked, OK | answered by RS
2020-11-10 | AM | BOB | 10010 | 14755261 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-10 | AM | BOB | 10211 | 207871878 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-10 | AM | BOB | 10265 | 14754403 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-10 | AM | BRUNO | 10211 | 14755280 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-10 | AM | BRUNO | 10391 | 14754718 | checked, OK | transferred to AIB | No SAP PDA rights for closure.
2020-11-10 | PM | BRUNO | 10254 | 14755357 | checked, OK | answered by MB

## Defect Characterization
Day | Shift | ATIS QLS | MSN | NC /Mapping | Status | Closure status | Comments

## FOD Inspections
Day | Shift | ATIS QLS | MSN | Station | Zone | OK/NOK | Report Send on | Comments
2020-11-09 | AM | BOB | 10034 | 40 | 80VU | OK | 2020-11-09
2020-11-09 | AM | BRUNO | 10034 | 40 | 90VU | NOK | 2020-11-09
2020-11-09 | AM | BOB | 10265 | 40 | 80VU | NOK | 2020-11-09
2020-11-09 | AM | BOB | 10265 | 40 | 90VU | NOK | 2020-11-09
2020-11-09 | AM | BOB | 10080 | 35 | 80VU | NOK | 2020-11-09
2020-11-09 | PM | BOB | 10224 |  | 90VU | OK | 2020-11-09
2020-11-09 | PM | BOB | 10224 |  | 80VU | OK | 2020-11-09
2020-11-09 | PM | BRUNO | 10256 |  | 90VU | OK | 2020-11-09
2020-11-09 | PM | BOB | 10275 |  | 90VU | OK | 2020-11-09
2020-11-09 | PM | BOB | 10275 |  | 80VU | OK | 2020-11-09
2020-11-09 | PM | BOB | 10314 |  | 90VU | OK | 2020-11-09
2020-11-09 | PM | BOB | 10314 |  | 80VU | OK | 2020-11-09
2020-11-09 | PM | BRUNO | 10335 |  | 90VU | NOK | 2020-11-09 | Form A 334741 check not ok
2020-11-09 | PM | BRUNO | 10335 |  | 80VU | OK | 2020-11-09
2020-11-09 | PM | BRUNO | 10211 |  | 90VU | OK | 2020-11-09
2020-11-10 | AM | BRUNO | 10100 | 41 | 80VU | NOK | 2020-11-10
2020-11-10 | AM | BOB | 10341 | 42 | 80VU | NOK | 2020-11-10
2020-11-10 | AM | BRUNO | 10151 | 35 | 80VU | NOK | 2020-11-10
2020-11-10 | AM | BOB | 10100 | 41 | 90VU | NOK | 2020-11-10
2020-11-10 | AM | BOB | 10341 | 42 | 90VU | NOK | 2020-11-10
2020-11-10 | AM | BOB | 10151 | 35 | 90VU | NOK | 2020-11-10
2020-11-10 | AM | BOB | 10034 | 37 | 90VU | NOK | 2020-11-10 | Form A 359222 check not ok
2020-11-10 | AM | BOB | 10265 | 40 | 80VU | NOK | 2020-11-10 | Form A 359442 check not ok
2020-11-10 | AM | BRUNO | 10265 | 40 | 90VU | NOK | 2020-11-10 | Form A 359442 check not ok

## CPB
Day | Shift | ATIS QLS | MSN | CPB | Subject | Inspection Status | NC | FormA | Comments
2020-11-09 | AM | BRUNO | 10080 | 6039558-02 | FOD Check 80VU | NOT OK |  | 359241 | FA give to ACM - Rework in Progress
2020-11-09 | AM | BOB | 10034 | 6039558-07 | FOD Check 80VU | OK |  |  | No FOD found
2020-11-09 | AM | BOB | 10265 | 6039558-10 | FOD Check 80VU | NOT OK |  | 359442 | FA give to ACM - Rework in Progress
2020-11-09 | AM | BOB | 10265 | 6039545-10 | FOD Check 90VU | NOT OK |  | 359442 | FA give to ACM - Rework in Progress
2020-11-09 | AM | BOB | 10034 | 6039545-07 | FOD Check 90VU | NOT OK |  | 359222 | FA give to ACM - Rework in Progress
2020-11-09 | PM | BOB | 10224 | 6039545-19 | FOD Check 90VU | OK |  |  | No FOD found
2020-11-09 | PM | BRUNO | 10224 | 6039558-19 | FOD Check 80VU | OK |  |  | No FOD found
2020-11-09 | PM | BOB | 10256 | 6039545-08 | FOD Check 90VU | OK |  |  | No FOD found
2020-11-09 | PM | BOB | 10275 | 6039545-04 | FOD Check 90VU | OK |  |  | No FOD found
2020-11-09 | PM | BOB | 10275 | 6039558-04 | FOD Check 80VU | OK |  |  | No FOD found
2020-11-09 | PM | BOB | 10314 | 6039545-14 | FOD Check 90VU | OK |  |  | No FOD found
2020-11-09 | PM | BRUNO | 10314 | 6039558-14 | FOD Check 80VU | OK |  |  | No FOD found
2020-11-09 | PM | BRUNO | 10335 | 6039545-17 | FOD Check 90VU | NOT OK |  | 334741 | FA give to ACM - Rework in Progress
2020-11-09 | PM | BRUNO | 10335 | 6039558-17 | FOD Check 80VU | OK |  |  | No FOD found
2020-11-09 | PM | BRUNO | 10211 | 6039545-18 | FOD Check 90VU | OK |  |  | No FOD found
2020-11-10 | AM | BOB | 10100 | 6039558-12 | FOD Check 80VU | NOK |  | 359461 | Form A gave to ACM - rework in progress
2020-11-10 | AM | BRUNO | 10341 | 6039558-16 | FOD Check 80VU | NOK |  | 367061 | Form A gave to ACM - rework in progress
2020-11-10 | AM | BOB | 10151 | 6039558-05 | FOD Check 80VU | NOK |  |  | FOD removed
2020-11-10 | AM | BOB | 10100 | 6039558-12 | FOD Check 90VU | NOK |  | 359461 | Form A gave to ACM - rework in progress
2020-11-10 | AM | BOB | 10341 | 6039545-16 | FOD Check 90VU | NOK |  | 367061 | Form A gave to ACM - rework in progress
2020-11-10 | AM | BOB | 10151 | 6039545-05 | FOD Check 90VU | NOK |  | 359203 | Form A gave to ACM - rework in progress