## >Input
New task : | Tasks : | Apartement analysis | Names : | Vincent
|  | Appartement |  | Paul
BDS
BPM
Electricity
Energy Analysis
Fee calculation
Fire analysis
Industrialized building component
Instalations and shaft arrangements
Instalations(kitchen, bath…)
Insulation
Key figure
Lay out
Life cycle costing
Meeting/planning
Planning
Poster
Power point and presentation
Procurement
Site
Sound analysis
Structure
Successive estimation
Sustainbility
U-value
Ventilation analysis

## >Table
[5 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40
Task | Group | Planned/ Used | Planned Hours | Used Hours | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 2 | 37 F: 2
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 3 | 37 F: 3
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 4 | 37 F: 4
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 5 | 37 F: 5
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 6 | 37 F: 6
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 7 | 37 F: 7
Sustainbility | >Table | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 8 | 37 F: 8

## >Planning group
[5 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40
Task | Group | Planned/ Used | Planned Hours | Used Hours | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
|  | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
|  | Used |  | 2 | 37 F: 2

## Vincent
[5 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40
Task | Group | Planned/ Used | Planned Hours | Used Hours | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Sound analysis | Vincent | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sound analysis |  | Used |  | 2 | 37 F: 2
U-value | Vincent | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
U-value |  | Used |  | 3 | 37 F: 3
Sustainbility | Vincent | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 4 | 37 F: 4

## Paul
[5 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40
Task | Group | Planned/ Used | Planned Hours | Used Hours | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Sustainbility | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Sustainbility |  | Used |  | 2 | 37 F: 2
Procurement | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Procurement |  | Used |  | 3 | 37 F: 3
Successive estimation | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Successive estimation |  | Used |  | 4 | 37 F: 4
Site | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Site |  | Used |  | 5 | 37 F: 5
Ventilation analysis | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Ventilation analysis |  | Used |  | 6 | 37 F: 6
Insulation | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Insulation |  | Used |  | 7 | 37 F: 7
Instalations and shaft arrangements | Paul | Planned | 8 |  | 37 TH: 2; 38 M: 2; 39 M: 2; 40 M: 2
Instalations and shaft arrangements |  | Used |  | 8 | 37 F: 8